## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | EGM_Ver1.3_08.03.24_Component 1_Manufacture issued Timber Cut Production_Inspection | [5 empty] | EGM_Ver1.3_08.03.24_Component 1_Manufacture issued Timber Cut Production_Inspection
section | Element_Component 1_Manufacture Issued-Timber Cut Production Inspection
checkpoint | Records - Document / Attachment / Link / Photo
checkpoint | Check and review as per Approved Manufacture Issued Saw Cutting File.
checkpoint | Ostendo - Timber Component Line Bar Code, completed.
checkpoint | Station - Correct manufacture issued auto-saw cut files for each element code.
checkpoint | Station - Cutting Element lot completed, checked, and as per approved element code plan.
textbox | Operator name:
checkpoint | Improvement or Re-Occuring Issues Records - Document / Attachment / Link / Photo
checkpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
section | Component 1 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Confirm Ostendo Component materials where scanned
checkpoint | Photo required - Evaluated RFI Minor issue:
checkpoint | Photo required - Evaluated RFI Major issue:
checkpoint | Photo required - Evaluated NCR Critical issue:
holdpoint | Hold point: Signed off by Team Leader before going to next step (If No RFI)
checkpoint | Hold Point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Component 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signed off RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Signed off RFI Minor Review and Final Check by Production Manager Final Check (If No RFI)
section | Component 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold Point: Quality & Compliance Manager
holdpoint | Hold point: Signed off RFI Major Final Check by Quality & Compliance Manager
section | Component 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Component Pre-Assembly 1_Structural Stud_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Component Pre-Assembly 1_Structural Stud_Inspection | 112f2ef4-27d6-472a-a9b4-2a67371b53d1
section | Element Pre-Assembly 1_Structural Stud Inspection
checkpoint | Check and review as per Approved Shop Drawing & template pilot hole, and provide picture of the respective plan which clearly shows page number.
checkpoint | Station - Mark up correct, as per correct template.
checkpoint | Component - Pre-Stud brackets & Rothoblaas install, as per specification and tolerance.
checkpoint | Component - Pre-Stud nail stitching install, as per specification and tolerance and photo required.
checkpoint | Component - Glue laminate Lintels, with correct glue and method, completed.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 1 Inspection__Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Review of Ostendo Element Pre-Assembly materials where scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated NCR Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold Point: QA Manager
holdpoint | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold Point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Pre-Assembly 1_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Element Assembly 3_Frame Structure_Ceiling Cassette / CE _Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Element Assembly 3_Frame Structure_Ceiling Cassette / CE _Inspection | ae179d75-3f18-486c-92be-89b0a9aa9be0
section | Element Assembly 3_Structural Framing and Pre-line Inspection
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint | Install all ceiling framing elements and fixings as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan
checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
textbox | Diagonal #1:
textbox | Diagonal #2:
checkpoint | Check and verify structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Check and verify installed nogs/blockings as per Approved Shop Drawing Plan
checkpoint | Hold point: Review and Signoff by Operator before going to next step
section | Element Assembly 3_Fire Lining 1st Layer
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint | Install 1st Layer and fixing as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 3_Fire Lining 2nd Layer
checkpoint | Check and review correct Approved Shop Drawing
checkpoint | Install 2nd Layer and fixing as per Approved Shop Drawing Plan
textbox | Operator name:
checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 3 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated NCR Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold Point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Element Assembly 3_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Element Assembly 3_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold Point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Element Assembly 3_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Component Pre-Assembly 2_Pilot Holes_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Component Pre-Assembly 2_Pilot Holes_Inspection | 2a31650e-02d4-4cc4-b915-4af8330d77d3
section | Component Pre-Assembly 2_Pilot Holes Inspection
checkpoint | Check and review as per Approved Shop Drawing & template pilot hole, and provide picture of the respective plan which clearly shows page number
checkpoint | Station - Mark up correct, as per correct template, and photo required
checkpoint | Station - Pilot Holes, as per specification and tolerance and photo required.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 2 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated NCR Critical issue - Photo required:
holdpoint | Hold point: Review & Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold Point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 2_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 2_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold Point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Pre-Assembly 2_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Element Assembly 5_Plumbing & Drainage - Floor Cassette_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Element Assembly 5_Plumbing & Drainage - Floor Cassette_Inspection | 9028fb35-8c6e-47a3-9cdb-4e17a08455b7
section | Element Assembly 5_Pre-plumbing and Drainage Inspection_Module B
checkpoint | Check and review as per As Build Drawing Plumbing and Drainage Services Plan, and provide picture of the respective plan.
checkpoint | Install and verify pipework installed as per As Build Drawing and manufacture products instructions, photo required.
textbox | Operator Name:
checkpoint | Check and verify foul water pipe gradients compliant and install timber joist stiffeners where drainage pipework penetration occur, photo required.
checkpoint | Ensure to secure all water pipework cross-over and through timber penetrations, with applied sealant, photo required.
checkpoint | Lagging to drainage pipework, as per project specifications/ manufactruer, photo required.
textbox | Operator Name:
checkpoint | Drainage pipework, Complete Air Test to AS/NZS3500 and photo required.
textbox | Operator Name:
holdpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Element Assembly 5 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated NCR Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold Point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Element Assembly 5_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Element Assembly 5_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold Point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Element Assembly 5_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Station 1_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Station 1_Inspection | 77049c9b-f85d-4349-9c7a-7c9fb83ffc24
section | Station 1_Electrical & Mechanical - First Fix_DB_Ducting_Penetrations Inspection_Module A or B
checkpoint | Check and review as per Approved Shop Drawing Electrical Services Plan and provide photo
checkpoint | Ostendo Station 1 Module material scan, completed
checkpoint | Install Distribution Board as per approved electrical services plan
checkpoint | Install all electrical cabling as per approved electrical services plan
checkpoint | Check and verify installed switchgear valves as per plan
checkpoint | All conduit, cables are noted correctly
checkpoint | Drill penetrations through timber frame from external for internal wires
checkpoint | Ensure all screws are torqued to correct specification
checkpoint | Visual inspection: Cable protection/Support/Fixing are in good condition without obvious damage
checkpoint | External mark-out and cut fireboxes through ply/GIB, and overview photo required
checkpoint | Mechanical Ducting install as per mechanical service plan, and overview photo required
textbox | Operator Name:
checkpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
holdpoint | Hold point: Signed off by Team Leader before going to next step (If No RFI)
section | Station 1_Plumber & Drainage Team_First Fix Wingbacks Inspection_Module B
checkpoint | Check and review as per project Architectural Drawing and reference respective detail plan page number
checkpoint | Ensure all plumbing pipework is secure with applied sealant where required, prior to overview photo's
checkpoint | Install all required wingbacks (cylinder) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (water meter) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (toilet) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (laundry) as per manufacturers specification, and overview photo required.
checkpoint | Install all required wingbacks (shower) as per manufacturers specification, and overview photo required.
checkpoint | Water pipework, complete water test test to AS/NZS 3500, (by-pass mixer) require photo.
checkpoint | Install shower mixer as per manufacturers specification, and overview photo required.
textbox | Operator Name:
holdpoint | Hold point: confirm photo taken and signed off by Operator before going to next step (If No RFI)
checkpoint | Hold Point: Team Leader
holdpoint | Hold point: Signed off by Team Leader before going to next step (If No RFI)
section | Station 1_ Module Assembly _Bulkhead Inspection_Module B
checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint | Install bulkhead partially (leave bottom open for ducting install) as per approved plan and manufacturer specification
checkpoint | Ostendo Station 1 Module material scan, completed
textbox | Operator Name:
checkpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
section | Station 1 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Review of Station 1 Module materials where scanned
checkpoint | Photo required - Evaluated RFI Minor issue:
checkpoint | Photo required - Evaluated RFI Major issue:
checkpoint | Photo required - Evaluated NCR Critical issue:
holdpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signed off RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Signed off RFI Minor Review and Final Check by Production Manager Final Check
section | Station 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signed off RFI Major Final Check by Quality & Compliance Manager
section | Station 1_QA RFI_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.0_22.11.23_Station 5_Inspection | [5 empty] | EGM_Ver1.0_22.11.23_Station 5_Inspection | b1c05ace-2cad-4bf1-8b8b-0c137fcdc946
section | Station 5_First Fix Plumbing and Drainage_Module B
checkpoint | Install floor waste flange, (if required), provide photo.
checkpoint | After plasterboard (GIB) installation, mains water pressure test for leaks, or mechanical fixing puncture to water pipework.
textbox | Operator Name:
checkpoint | Hold point: Signed off by Operator before going to next step (If No RFI)
holdpoint | Hold point: Signed off by Plumbing Team Leader before going to next step (If No RFI)
section | Station 5_Gib Stopping 1st Coat - Internal Walls_Module A or B
checkpoint | Install internal Gib stopping as per approved plans
textbox | Operator name:
checkpoint | Check and verify the installed GIB stopping as per approved plans
holdpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
section | Station 5_Gib Stopping 2nd Coat - Wall and Ceiling_Module A or B
checkpoint | Install internal Gib stopping as per approved plans
textbox | Operator name:
checkpoint | Check and verify the installed GIB stopping as per specifications & approved plans
holdpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
section | Station 5_Putty Holes - Arichtraves & Skirting_Module A or B
checkpoint | Install internal putty holes to architraves & skirting as per approved plans
textbox | Operator name:
checkpoint | Check and verify the installed putty to holes of architraves and skirting as per specifications & approved plans
holdpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
section | Station 5 Inspection_Signoff
checkpoint | Hold Point: Contractor
holdpoint | Hold point: Signed off by Contractor before going to next step (If No RFI)
checkpoint | Photo required - Evaluated RFI Minor issue:
checkpoint | Photo required - Evaluated RFI Major issue:
checkpoint | Photo required - Evaluated NCR Critical issue:
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 5_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signed off RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Signed off RFI Minor Review and Final Check by Production Manager Final Check
section | Station 5_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold Point: Quality & Compliance Manager
holdpoint | Hold point: Signed off RFI Major Final Check by Quality & Compliance Manager
section | Station 5_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Station 11_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Station 11_Inspection | 349f92f7-bbf9-4669-8e49-331b50c955aa
section | Station 11_Kitchen Cabinets Inspection_Module B
checkpoint | Contractor - Kitchen Cabinets, refer to separate checklist
checkpoint | Station 11_Electrical & Mechanical Team_Second Fix Electrical & Mechanical Inspection_Module A or B
checkpoint | Check and review as per Approved Shop Drawing Electrical and Mechanical Services Plan and provide picture of the respective plan which clearly shows page number
checkpoint | Install all power points and light switches.
checkpoint | Install all lights.
checkpoint | Install heat pumps. (Onsite install)
checkpoint | Install heat towel rail. (If required)
checkpoint | Install mechanical ventilation/Bathroom/Laundry/Kitchen.
checkpoint | Install HW cylinder
checkpoint | Install Kitchen oven/hob.
checkpoint | Install wall heaters.
checkpoint | Check, by contractor smoke alarm, installed - completed
textbox | Operator Name:
checkpoint | Hold Point: Overall photo required and signed off by Operator before going to next step (If No RFI)
holdpoint | Hold point: Signed off by Team Leader before going to next step (If No RFI)
section | Station 11_Final Fix Plumbing and Drainage Inspection_Module B
checkpoint | Install HW cylinder as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install toilet as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install kitchen sink plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install shower fittings as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install vanity plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install floor waste as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install supertub & plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install shower tray waste plumbing as per Approved Shop Drawing plans and manufacture instructions.
textbox | Operator Name:
checkpoint | Hold point: All photos taken and signed off by Operator before going to next step (If No RFI)
holdpoint | Hold point: Review and signed off by Team Leader before going to next step (If No RFI)
section | Station 11 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Review of Station 4 Module materials where scanned
checkpoint | Photo required - Evaluated RFI Minor issue:
checkpoint | Photo required - Evaluated RFI Major issue:
checkpoint | Photo required - Evaluated NCR Critical issue:
holdpoint | Hold point: Signed off by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 11_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signed off RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Signed off RFI Minor Review and Final Check by Production Manager Final Check
section | Station 11_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signed off RFI Major Final Check by Quality & Compliance Manager
section | Station 11_QA NCR_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.
checklist | EGM_Ver1.1_08.03.24_Station 12_Inspection | [5 empty] | EGM_Ver1.1_08.03.24_Station 12_Inspection | d9ce08fc-a231-4a39-83aa-7bf64628ec2b
section | Station 12_Final Testing Plumbing and Drainage Inspection - Module B
checkpoint | SS Drainage pipework flood test, provide photo
checkpoint | Visual check all pipework, no leaking detected, during testing
checkpoint | Visual check all fixtures & fitting, no leaking detected, during testing
textbox | Operator Name:
checkpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
holdpoint | Hold point: photo required and signed off by Team Leader before going to next step (If No RFI)
section | Station 12_Electrical Testing (Inform electrician to carry out the required electrical testing of all installation)_Module A & B
checkpoint | Electrical Testing-Earth Resistance and Continuity, Insulation Resistance, Polarity and Phase, Correct Circuit connection, etc.
checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint | RCD's Test
checkpoint | Hold point: All photos taken and signed off by Electrical Team Leader before going to next step (If No RFI)
holdpoint | Hold point: Signed off by Team Leader before going to next step (If No RFI)
section | Station 12_Hardware_Module A or B
checkpoint | Check and review as per approved Shop Drawing Plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint | Complete all hardware as per approved Shop Drawing plans and specifications.
textbox | Operator Name:
checkpoint | Hold point: photo required and signed off by Operator before going to next step (If No RFI)
holdpoint | Hold point: photo required and signed off by Team Leader before going to next step (If No RFI)
section | Station 12 Inspection_Signoff
checkpoint-no-status | Inspection
textbox | Operator Name:
checkpoint | Review of Station 4 Module materials where scanned
checkpoint | Photo required - Evaluated RFI Minor issue:
checkpoint | Photo required - Evaluated RFI Major issue:
checkpoint | Photo required - Evaluated NCR Critical issue:
holdpoint | Hold point: Signed off by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 12_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signed off RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Signed off RFI Minor Review and Final Check by Production Manager Final Check
section | Station 12_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signed off RFI Major Final Check by Quality & Compliance Manager
section | Station 12_QA RFI_Critical
checkpoint | Photo required - NCR Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signed off RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signed off NCR Critical Approved MV Approved Final Check by QCM before NCR report.