## PORT ROAD ITP - SP3
INSPECTION & TEST PLAN
Contract Name:
6970 PORT ROAD INTERSECTION UPGRADE (SP3)
TASK | SPECIFICATION REFERENCE | ACTIVITY/TASK | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | DATE | COMMENTS
PAVEMENTS
Subgrade | Pavement and Surfacing Technical Specification, clause 2.1 | Scala and/or Benkelman Beam Deflections | After excavation and prior to any construction, installation or backfilling | Areas that fail to achieve the minimum subgrade CBR and deflection criteria will require the construction of Subgrade Improvement Layers (SIL). Acceptance by Engineer before proceeding.
Imported Granular Fill |  | Record of Fill | On completion of granular fill layer. | Submitted to Engineer.
SIL Material Testing | Pavement and Surfacing Technical Specification, clause 2.2.2 | Material Test Certificates | Prior to using the material on site | Material meets specification. Material approval by Engineer.
Subgrade Improvement Layer | Pavement and Surfacing Technical Specification, clause 2.2 | Benkelman Beam Deflections | Benkelman Beam testing where possible on completion Subgrade Improvement Layers. On completiond of the Subgrade Improvement layer. Inspection by the Engineer. | Benkelman Beam Deflections meet specification. Acceptance by Engineer before proceeding.
Lean Mix Concrete Layer |  | Concrete Dockets, Benkelman Beam Deflections | On completion of the Lean Mix Concrete layer. | Increase in Benkelman Beam Deflections meet Engineers criteria. Acceptance by Engineer before proceeding.
Lower Subbase Material Testing | Pavement and Surfacing Technical Specification, clause 2.3.2 | Material Test Certificates | Prior to using the material on site | Material meets specification. Material approval by Engineer.
Lower Subbase | Pavement and Surfacing Technical Specification, clause 2.3 | NDM Testing and Benkelman Beam Deflections | On completion of the Lowe Subbase layer, prior to construction Upper Subbase layer. | NDM results and Benkelman Beam Deflections meet specification. Acceptance by the Engineer.
Upper Subbase Material Testing | Pavement and Surfacing Technical Specification, clause 2.4.2 | Material Test Certificates | Prior to using the material on site | Material meets specification. Material approval by Engineer.
Upper Subbase | Pavement and Surfacing Technical Specification, clause 2.4 | NDM Testing and Benkelman Beam Deflections | On completion of the Upper Subbase layer, prior to construction of the Basecourse layer. | NDM results and Benkelman Beam Deflections meet specification. Acceptance by the Engineer.
Basecourse Material Testing | CON21015 Project Specification, clause 23.8 | Material Test Certificates | Prior to using the material on site | Material meets specification. Material approval by Engineer.
Basecourse | CON21015 Project Specification, clause 23.8 | NDM Testing and Benkelman Beam Deflections | On completion of the Basecourse layer, prior to construction of the deep lift or wearing course layers. | NDM results and Benkelman Beam Deflections meet specification. Acceptance by the Engineer.
AC20 Material Testing | NZTA M10 Specification | Material Test Certificates | Prior to using the material on site | Material meets specification. Material approval by Engineer.
AC20 Deep Lift Layers | NZTA M10 Specification | Testing as per NZTA M10 | On completion of the AC20 Deep Lift Layers, prior to construction of the AC14 wearing course. | Testing results meet specification. Acceptance by the Engineer.
AC14 Material Testing | NZTA M10 Specification | Testing as per NZTA M10 | Prior to using the material on site | Material meets specification. Material approval by Engineer.
AC14 Wearing Course | NZTA M10 Specification | Testing as per NZTA M10 | On completion of the AC14 wearing course. | Testing results meet specification. Acceptance by the Engineer.
Two Coat Chip Seal Surfacing | Pavement and Surfacing Technical Specification, clause 2.12 | Testing as per clause 2.12
STORMWATER
Stormwater Construction Methodology | CON21015 Project Specification, clause 18 | Construction Methodology submitted for specific works | Prior to the commencement of specific works | Construction Methodology accepted by the Engineer.
Stormwater Installation |  | Photos, as-built drawings and CCTV of installed stormwater | On completion of the installation of the stormwater system. | Installation meets WDC Engineering Standards.
SEWER
Sewer Construction Methodology | CON21015 Project Specification, clause 18 | Construction Methodology submitted for specific works | Prior to the commencement of specific works | Construction Methodology accepted by the Engineer.
Sewer Installation |  | Photos, PE weld records, pressure testing records, as-built drawings | On completion of the installation of the sewer system. | Installation meets WDC Engineering Standards.
WATER
Water Construction Methodology |  | Construction Methodology submitted for specific works | Prior to the commencement of specific works | Construction Methodology accepted by the Engineer.
Watermain Installation |  | Photos, PE weld records, pressure testing records, chlorination records, as-built drawings | On completion of the installation of the watermain system | Installation meets WDC Engineering Standards and WDC Water Services General Specification.
CONCRETE WORKS
Kerb and Channel | CON21015 Project Specification, clause 22.3 | Photos, concrete dockets | On completion of kerb and channel construction. | Construction meets specification.
Vehicle Crossings | CON21015 Project Specification, clause 22.6 | Photos, concrete dockets, CIV results | On completion of vehicle crossing construction. | Construction meets specification.
Concrete Footpaths | CON21015 Project Specification, clause 22.5 | Photos, concrete dockets, CIV results | On completion of shared user path construction. | Construction meets specification.
Coloured Concrete (Islands, KiwiRail) |  | Photos, concrete dockets | On completion of coloured concrete construction. | Construction meets specification.
LIGHTING
Lighting Material Supply | CON21015 Project Specification, clause 26.3 | Material dockets/statements | On completion of lighting installation. | Materials meet lighting specification.
Lighting Installation | CON21015 Project Specification, clause 26.3 | Checklists confirming installation and electrical testing | On completion of lighting installation. | Installation meets lighting specification.
TRAFFIC SIGNALS
Traffic Signals Material Supply | CON21015 Project Specification, clause 25.8 | Material dockets/statements | On completion of traffic signal installation. | Materials meet traffic signal specification.
Traffic Signals Installation | CON21015 Project Specification, clause 25.8 | Checklists confirming installation and electrical testing | On completion of traffic signal installation. | Materials meet traffic signal specification.
TRAFFIC SERVICES
Pavement Marking | CON21015 Project Specification, clause 25.2 | Material dockets/statements, set-out | On completion of pavement marking. | Pavement markings meet NZTA M07 specification and IFC drawings.
Tactile Ground Indicators | CON21015 Project Specification, clause 25.2 | Photos, material dockets | On completion of tactile paving installation. | Tactile paving installed as per IFC drawings.
FINISHING WORKS
Landscaping | Port Road Roundabout Landscape Drawings (IFC) | Photos, Supplier Dockets | On completion of landscaping/installation. | Installation as per IFC Port Road Roundabout Landscape Drawings
Reserve Fencing |  | Photos | On completion of reserve fencing. | Installation as per Engineers instruction.
KIWIRAIL LEVEL CROSSING
Pedestrian Access and Fencing |  | Photos | On completion of pedestrian access installation. | Installation as per IFC Drawings.