## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | CS-4000 - 1M Scala Worksheet |  | CS-4000 - 1M Scala Worksheet |  | e0ceddf4-dbc2-4a86-b227-bbe1fc7de040
| checkpoint-no-value | 1M Scala Worksheet
8c70d012-7b29-5ceb-8f2b-4966af8255d9 | textbox | CH & Offset:
f91c5aa5-a40b-56e1-81ad-3aff7730a18d | textbox | Date:
4adee10b-90ff-5259-9f78-eace029e5e69 | textbox | Start Depth (mm):
| checkpoint | Depth [mm] - 0-100
003160ba-4f48-5109-af01-d668eb15cbbd | textbox | No. of Blows
cf7fafe6-1125-5d4b-b8bc-f72172206367 | textbox | mm / blow
d0cd8f70-4df2-537c-ac44-26775e67927d | textbox | CBR
| checkpoint | Depth [mm] - 100-200
5d1f9fac-a126-5cca-bfa8-59cbb003213d | textbox | No. of Blows
f97a0b48-4ea9-5424-a466-82700040d4aa | textbox | mm / blow
4208a88e-4230-5417-b2a2-b17c9ab66d14 | textbox | CBR
| checkpoint | Depth [mm] - 200-300
1a014fbe-86f9-55c9-867d-6ab7b0b5e4ca | textbox | No. of Blows
def71663-8d59-5114-995c-9d514137bd45 | textbox | mm / blow
affacdd3-29e5-5e29-8cd5-84314019cb78 | textbox | CBR
| checkpoint | Depth [mm] - 300-400
a053d265-45de-5659-82a1-31df64c5f73b | textbox | No. of Blows
5f826073-73da-53eb-96a4-6d7a89d59ad7 | textbox | mm / blow
d125ca15-8309-5d94-b4ba-38dcbe1f954a | textbox | CBR
| checkpoint | Depth [mm] - 400-500
56d1f06c-f822-5c90-b3cb-a3a5d65ee6ed | textbox | No. of Blows
eee7bee8-09d1-546d-9720-c9bc9bedd5e1 | textbox | mm / blow
0ea3bf8b-223c-5f80-b3e8-bbee9c63c96c | textbox | CBR
| checkpoint | Depth [mm] - 500-600
da2965fa-0d41-584a-8035-f5fc66b13489 | textbox | No. of Blows
67748d25-edee-521c-a392-2b83647c1d92 | textbox | mm / blow
b1045f3b-75b6-54a9-9288-fcca1f7136f8 | textbox | CBR
| checkpoint | Depth [mm] - 600-700
b9be3314-ccd3-54a7-955b-4c4e77649f16 | textbox | No. of Blows
9bf6301a-fcf9-5f49-b6a8-aa4a465b6153 | textbox | mm / blow
ad1305e8-4b16-58ec-bb93-46dc4871e958 | textbox | CBR
| checkpoint | Depth [mm] - 700-800
731bb428-afe1-5a05-b2cb-c983fe9177f8 | textbox | No. of Blows
0f5a7739-0107-51c5-8791-af3a4e694a9b | textbox | mm / blow
dbceaef5-0b38-5c0b-8419-3dfadfb992a5 | textbox | CBR
| checkpoint | Depth [mm] - 800-900
6c59e348-7cba-55dd-b154-3046f5892905 | textbox | No. of Blows
7c4600c9-5d8c-5669-8e69-5f00f422e83c | textbox | mm / blow
4e0012e7-26c9-52b6-9434-cb99bccff19d | textbox | CBR
| checkpoint | Depth [mm] - 900-1000
1db9f546-0f97-523b-9281-abe6b52fc35a | textbox | No. of Blows
73ddad95-ac6d-5f51-a6b6-34830cfe49cf | textbox | mm / blow
592c6d4d-e556-5663-997b-1255f23989a4 | textbox | CBR
| checkpoint-no-value | Tested by:
dd3c9977-abf5-5475-9544-965230612ea3 | textbox | Tested by:
| checkpoint-no-value | Checked by:
04e447b7-8ecd-51de-8967-b2d79e7deb1c | textbox | Checked by:
| checklist | CS-4001 - Subsoil Dipsheet |  | CS-4001 - Subsoil Dipsheet |  | aa2bc76f-2544-4463-b263-723d82e4bde4
| checkpoint-no-value | Details
72524a50-fc86-58e9-9e01-fbc4d712f09d | textbox | Work Area:
ad27c923-761f-5a9a-a8b5-4482cbc44418 | textbox | Sub Work Area:
186580b2-7f31-531f-998a-43f63a07de20 | textbox | Lot:
77f89de0-6014-5792-bca1-2d29ba588944 | textbox | Sublot:
e3611f28-237f-5438-b8cd-ff31f9a43d87 | date | Document Date:
41b89b0f-cb15-548d-ba60-30e1cc28a5cc | textbox | Created By:
| checkpoint-no-value | Note that depth is to be checked every 10m as a minimum.
58cc5f60-d74a-524a-adad-1a054e97853b | textbox | Drawing No:
d4521694-b5bf-5dc3-8e15-4f038e30a34f | textbox | Rev No:
| checkpoint | Chainage - 1
ab52f780-9d0b-5972-8c1d-8b56c797db38 | textbox | Depth:
| checkpoint | Chainage - 2
38e509d9-ca13-514b-842c-891d445cec8c | textbox | Depth:
| checkpoint | Chainage - 3
37fceb9f-fd6d-5872-ab6a-dd33b0a20358 | textbox | Depth:
| checkpoint | Chainage - 4
423a6377-2038-582c-9230-83ce55436157 | textbox | Depth:
| checkpoint | Chainage - 5
7e1eb064-0c56-505a-b453-5a1e368a5b2b | textbox | Depth:
| checkpoint | Chainage - 6
97e0e55a-068d-5074-8109-15c0593c4157 | textbox | Depth:
| checkpoint | Chainage - 7
f5ed682e-d40e-54c7-853f-dbd0162e2e37 | textbox | Depth:
| checkpoint | Chainage - 8
b6e45df0-ddb8-5204-b88d-fc3a0cf00986 | textbox | Depth:
| checkpoint | Chainage - 9
b9a3b5e7-9068-5567-a91d-f3d97065cbc3 | textbox | Depth:
| checkpoint | Chainage - 10
da3b8425-c11b-53e8-9a35-93b82287d469 | textbox | Depth:
| checkpoint | Chainage - 11
f6e6e8c8-10d7-55a3-98a6-72cec2697662 | textbox | Depth:
| checkpoint | Chainage - 12
882ff3ff-26d4-58a7-8f62-daefa8f37dac | textbox | Depth:
| checkpoint | Chainage - 13
2fe03918-6a07-5783-af2c-3472fc6653eb | textbox | Depth:
| checkpoint | Chainage - 14
bfcd3eaa-a684-5de2-be3a-5c04920ea347 | textbox | Depth:
| checkpoint | Chainage - 15
1e12f2b7-1609-5d2d-9b11-d9f9a995e9fa | textbox | Depth:
| checkpoint | Chainage - 16
bd4f1b3a-b5bb-576c-8fae-ff8867bfddfa | textbox | Depth:
| checkpoint | Chainage - 17
07ba1f66-04a5-5909-9e00-393d862fcda0 | textbox | Depth:
| checkpoint | Chainage - 18
a1526be0-ac87-5bc1-a550-1438b3a36895 | textbox | Depth:
| checkpoint | Chainage - 19
72b2b901-307a-5421-a833-46e7cfdfb1f6 | textbox | Depth:
| checkpoint | Chainage - 20
bbe9b221-cc26-5f3d-9508-cb623cb9a158 | textbox | Depth:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions.
d084c812-9e19-5a27-b945-ff4dedc0a055 | textbox | Name:
d8121ef4-d10d-528c-b569-4891dd2273bb | textbox | Position:
aa4cbc16-3d59-5f22-972c-416c38f618b9 | date | Date:
| signoff | Signature
| checklist | CS-4002 - Concrete Pump Operator |  | CS-4002 - Concrete Pump Operator |  | fe4f3028-0ae0-4b68-9d8c-b900c4e3fb6b
| section | DETAILS
| checkpoint-no-value | Details:
3ad4de38-4aee-5c6f-bd6b-f47614352567 | textbox | Project No.:
f1773bcd-0b3a-55a3-b3df-6643c21db8b1 | date | Date:
859a16dd-90a2-5cec-b5be-7a10618e1ce1 | textbox | Name:
4f97e874-3453-5088-95a7-394695049dc9 | textbox | Area:
47705d35-11a3-582f-a34d-e9cda12e6056 | textbox | Location:
5887b714-303d-55c4-aa2d-b11bb68cabf7 | textbox | Fleet No.:
4d5c0c41-5f8c-543b-9ca2-acae9e0222b2 | textbox | Make/Model:
ad8b487b-a09d-558b-8198-61fb4379716a | textbox | Hour Meter: Start:
4051c9e4-5bee-50df-9fcf-339ef5af5528 | textbox | Hour Meter: Finish:
| section | CHECK BEFORE STARTING
| checkpoint | Grease Points
8e846919-bc69-5258-ac9b-66654363aedb | note | PASS = OK
e139042c-a2aa-55fd-afe9-8b0705bce703 | note | FAIL = Defect
| checkpoint | Oil / Water Leaks
44ffe946-877d-51f4-9f13-a18174d9cb5a | note | PASS = OK
8cdb942b-cc3d-56b1-ac48-5cc56eb5fd63 | note | FAIL = Defect
| checkpoint | Radiator & Fuel Tank Level
ee3acc40-4f2f-578e-87e8-17fe82d4b531 | note | PASS = OK
5567e4d7-5ff1-58ab-bef8-213bcfc34994 | note | FAIL = Defect
| checkpoint | Engine Oil Level
3dbb125e-d874-54ba-acd2-a422fc310ed8 | note | PASS = OK
e285fa47-f43e-537f-8c80-315a19de9621 | note | FAIL = Defect
| checkpoint | Hydraulic Oil Level
cd03af49-4d8a-57c0-b163-4e6500c6a118 | note | PASS = OK
a311bc22-eef3-5ad0-b3f9-2c89ff82aeb7 | note | FAIL = Defect
| checkpoint | Fire Extinguisher & First Aid Kit
22cb9ad7-63f6-5420-b810-387b6c94bb3d | note | PASS = OK
e3bb0335-8ec3-5da5-9219-3df058e96a9b | note | FAIL = Defect
| checkpoint | Pump set up level & secure
cc2d0845-36d0-591e-8bf7-5592a94ca5a0 | note | PASS = OK
e1649c67-1799-5372-95c2-f7fcc46252c4 | note | FAIL = Defect
| checkpoint | Water Box Full
22b5525b-0bab-589e-a778-70cb16e6ff14 | note | PASS = OK
23e9c290-b1f0-5647-9030-d8288ca2da7f | note | FAIL = Defect
| checkpoint | Guards and Covers in Place
9f900d27-d60c-5819-a4b3-04d52b3be807 | note | PASS = OK
2316d994-6dad-5dfb-8075-8367c2122895 | note | FAIL = Defect
| checkpoint | Delivery Pipes condition & cleanliness
c32e76d8-2314-5562-94df-794730874294 | note | PASS = OK
739eae1c-453c-5c9f-8912-b44073bb8820 | note | FAIL = Defect
| checkpoint | Delivery Pipe Connections correct & Locking Pins Fitted
a4a8f7c9-5519-53a3-bbb6-c6339ab46efa | note | PASS = OK
8d0bc61b-75cb-5cac-8b4a-4d714d5b5929 | note | FAIL = Defect
| checkpoint | Delivery Line Adequately Supported
6f7f7b3b-8f88-5fa1-b61b-37a344872f02 | note | PASS = OK
cb9b128d-43f3-5c90-a3cf-dfbdd4efa1d5 | note | FAIL = Defect
| section | CHECK AFTER START-UP
| checkpoint | Oil Pressure
6e90af60-c7b5-5866-a0f6-2d92ed6b7751 | note | PASS = OK
0bab14d1-d1bc-5043-be02-88837cf25b14 | note | FAIL = Defect
| checkpoint | Water Temperature
c5960124-aea5-5c88-9d86-d465dd59e4e5 | note | PASS = OK
6498b812-7bb9-5566-b219-a0f9b5acba40 | note | FAIL = Defect
| checkpoint | Emergency Stop Button
cde7eb6e-cc71-50c2-9a60-8eb899ef0b36 | note | PASS = OK
31c83374-d116-5a6a-892f-ba53cfe229dc | note | FAIL = Defect
| checkpoint | Remote Control Functioning
63ace290-d8c0-53c5-a232-1e62ba3e35bd | note | PASS = OK
907d079c-9925-516b-83a7-08a7d56b2ce2 | note | FAIL = Defect
| checkpoint | Hydraulic Oil Pressure
070d0983-0389-5a1a-968e-3b2e883e03b7 | note | PASS = OK
0f0c6cd4-cd67-5308-8502-6bc7c6826070 | note | FAIL = Defect
| section | DEFECTS
| checkpoint | DEFECTS:
8a386d5b-64e5-5530-8244-bcbc9397b5da | radio | (Select One) | No Defects Found, Unsatisfactory Condition Found
30d4ff46-c64e-539e-8421-86ab49c805dc | note | Defects Corrected By:
5da0dfb0-5792-58be-97ad-171fe0ff57c7 | textbox | Name: |  |  | (print)
70ff7f9e-107e-58c8-9fec-52b23d513a88 | date | Date:
| section | CHECK DURING OPERATION
| checkpoint | Deliver Lines Grouted
a86b8a75-21f8-5c3e-bf87-4be18db88339 | note | PASS = OK
ffa81002-a4ba-5b47-b71a-294262d6b70c | note | FAIL = Defect
| checkpoint | Concrete Slump
81ad622b-c164-5a2b-b896-9ad1079467d1 | note | PASS = OK
2ba309d9-b213-5d9d-8ac3-e56c1807dd37 | note | FAIL = Defect
| checkpoint | Hydraulic Pressure during Pumping Max 160 Bar
6c000d27-0f3f-5541-b7d7-5ae1ccbf9e0f | note | PASS = OK
5916a961-0d2c-5609-8cc3-ea521bb07c89 | note | FAIL = Defect
| section | CHECK DURING CLEANING
| checkpoint | Direction of Cleaning
592ccb3e-c747-5d26-ae72-442e97e963d2 | note | PASS = OK
62a54905-4366-5eac-b288-4a3df2000191 | note | FAIL = Defect
| checkpoint | Reducer & Rubber Hose removed
b43b2f2f-6a9c-5e83-adde-8da5d73bbe7d | note | PASS = OK
1405723c-435d-5570-b115-12f9a0e9bf0e | note | FAIL = Defect
| checkpoint | Air manifold and Catch Basket Fitted
629cae30-be07-58b6-b589-29c33efe6ae9 | note | PASS = OK
3edb1131-74c9-515f-a39a-8a9fbfc23b59 | note | FAIL = Defect
| checkpoint | Personnel Clear of Discharge End
6d95e179-aa53-5fff-827e-1829c56a1e5a | note | PASS = OK
ac4f91f6-a1bf-5d40-b4dc-b379a937ce07 | note | FAIL = Defect
| checkpoint | Air Pressure Max 40 Bar
882df109-5f2c-534e-ac0d-b2962b670ea0 | note | PASS = OK
44b61534-435c-5307-b2ef-93a4966d34e5 | note | FAIL = Defect
| checkpoint | Equipment Clean
3e8c4d08-0618-593a-b6f9-259bf819f5c0 | note | PASS = OK
5e0f592c-3d72-5c0b-b0b3-df186f32c48b | note | FAIL = Defect
| section | COMMENTS
| checkpoint-no-value | COMMENTS:
9834caad-2fa2-535c-845f-ab2cf474b00d | note | This report MUST be handed into your supervisor at the end of each pumping operation
| checklist | CS-4006 - Manhole Catchpit Record |  | CS-4006 - Manhole Catchpit Record |  | e2d3c0ed-258d-4d9e-8660-e578326ca17f
| section | Details
| checkpoint-no-value | Details
414be580-0fce-5138-8a30-e5e82e08276e | textbox | Drawing No:
529e90c1-bc2d-534f-9c37-6247b87c4e4d | textbox | Rev No:
e04b148a-b814-559d-b70c-6f3993d8798b | textbox | Manhole/Catchpit:
| section | Inspection Stage
| checkpoint | 1 - Setout
244918f8-02da-5bd3-9824-a947a7dd58db | textbox | Initials:
a7d1ab42-08fb-547d-8708-933f1daa063d | date | Date:
| checkpoint | 2 - Excavation
40919602-85c7-505e-a9d9-3e325d47807b | textbox | Initials:
142c17f3-1311-57d2-ac6a-130d049d5d46 | date | Date:
| checkpoint | 3 - Prepare & Level Base Bedding – Testing req?
21ab549b-e0a6-521a-b68e-c645acb229bf | textbox | Initials:
95e7fc00-e478-5366-ba56-3ef91ba523e2 | date | Date:
| checkpoint | 4 - Confined Space Permit required?
c0e191ce-d484-59d4-9eec-4bf81d004149 | textbox | Initials:
6b5d29fa-92c5-57b8-b74c-0242ca791520 | date | Date:
| checkpoint | 5 - Installation of Precast Base Unit on Bedding
933ddd24-efaa-5369-a543-e2f03fd1e3fb | textbox | Initials:
01008f4d-099a-5124-8075-0b48e5647c91 | date | Date:
| checkpoint | 6 - Installation of Precast Risers to Lid Level
6c099bf1-b5d1-578d-b5d9-87040583d5fe | textbox | Initials:
76dcb82d-3334-5975-a8f8-dbad60b02ed1 | date | Date:
| checkpoint | 7 - Installation of Manhole/Catchpit Furniture, Steps / clamps
feebc52f-af35-53fa-8c8c-6bf50c6b6058 | textbox | Initials:
3b56a44a-74ed-5663-9d39-78c16b7afccf | date | Date:
| checkpoint | 8 - Haunching / Make Good Base. Joints sealed
e7c38bf8-e76a-51a6-80cf-c8f990d40071 | textbox | Initials:
01785f5a-942f-57f2-b192-cc82fba8dadf | date | Date:
| checkpoint | 9 - Installation of Precast Lid
7493fbbe-de24-5ef8-a5ac-ce66a187beef | textbox | Initials:
afe0691b-032d-522a-9863-a7923a05a3de | date | Date:
| checkpoint | 10 - Backfill Around Manhole/Catchpit – Tested
942303ee-d382-5013-9b34-566a35b9141b | textbox | Initials:
993f980c-3b87-59e8-85dc-1ea94e2fa786 | date | Date:
| checkpoint | 11 - Installation of Cast Iron Frame A Cover Lid Level – set with contour
736a1513-f370-59fb-b51d-dff97d1cb9d6 | textbox | Initials:
c5713a83-23c1-58cc-a07d-bdeeb7a8d812 | date | Date:
| checkpoint | 12 - Final Inspection
f72aa8d8-f244-5930-a856-e829bc357a00 | textbox | Initials:
f8bd47f7-508a-58e1-a2c5-ca9681ee1eec | date | Date:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
9cd44cd3-d8f9-5c06-84f9-ab9bf1ac4541 | textbox | Name:
2d16cb33-0110-5f64-b86f-56c1414949cd | textbox | Position:
ff7999b2-e02d-5324-ab57-cd8bd756dc2c | date | Date:
| signoff | Signed by
| checkpoint-no-value | Location/Chainage
7e585026-809c-5cf3-8dc2-02edc6db9a68 | textbox | Location/Chainage:
fe0db3c3-d986-5f17-8341-52cce4ea33f2 | textbox | Size:
a57a0258-2e18-5f3c-95ca-33048dad8a31 | textbox | Class:
0f84955f-6504-5f46-9eed-b4dd8a416b05 | textbox | Concrete manhole lid opening diameter: |  |  | mm
| checklist | CS-4009 - Socket Foundation Install Checklist |  | CS-4009 - Socket Foundation Install Checklist |  | 53edf9e3-1c3c-4f7c-85a5-bc393d312431
| checkpoint-no-value | Details
82068b19-9e2c-5365-bad9-5be44bee4708 | textbox | Date of Pour:
258828c4-28c0-5b92-a5b2-c0dbdfcbe8d4 | textbox | Light Pole Number:
71f5e2d7-66e3-595f-91ca-52f7db5eb9ed | textbox | Pole Type:
9fee506e-a8d8-518d-a9d5-9819500cdf1f | radio | Retention Socket Type: | RS168 x 750DF,RS168 Shallow,Rse273 x 900
4d675c91-9ca0-5c07-8cee-d763b1aa6a6c | radio | Installation: | Street Installation,Rain Garden Installation
e9e0485a-63a1-5176-8f24-1e10b5a42a74 | radio | Services Present: | Yes,No
9beb3117-661c-54e2-8bef-c50f7a80e8bf | textbox | Services Maximum Depth:
5c4dc65f-9d33-52b9-aebb-b7b83bf7f65f | textbox | Lateral Measurement – Foundation to Services:
6a34fa7a-34f3-5f61-849b-14ab03a5ff71 | textbox | Maximum Foundation Depth:
09403e2a-3bbc-5b19-9222-f9b927f3d7d4 | radio | Finished Ground Level Confirmed and Rebar Cage in correct location: | Yes,No
| checkpoint | Has minimum cover to rebar of 75mm been achieved?
730a2b27-c23a-5021-b166-a74c0f1a3fa0 | radio | Foundation layout as per approved drawings: | Yes,No
6f4e5884-a6a6-55eb-86cd-eccb783bd149 | note | (If NO what approved action is taken?)
9fc46d81-8b01-58b0-a7dd-41ed5a8a1c86 | textbox | Action:
dbbd4959-1b1a-54c0-9ebc-09db67adfcca | radio | Photos of pre pour foundation taken: | Yes,No
| checkpoint | RS168 Foundations Stub Pole in place and checked level. (1)
| checkpoint | RSe273 Foundations – Correct pre chamber allowed. (1)
| checkpoint-no-value | Water present in base of foundation to be removed:
997730d2-1ac1-542a-83c0-7150b2eb1d43 | textbox | Maximum allowable water in base is:
| checkpoint | All fixing locations secure pre concrete pour.
aaf931c4-4468-59d5-af0e-40e31689043e | textbox | Concrete Batch Number:
0c86adeb-71ee-550a-a592-dc905d314f70 | radio | Pour Correctly Vibrated: | Yes,No
| checkpoint | RS168 Foundations Stub Pole in place and checked level. (2)
| checkpoint | RSe273 Foundations – Correct pre chamber allowed. (2)
| checkpoint | Stub pole should in centre of foundation.
| checkpoint | Ensure top of pile is roughed up
| checkpoint | All rebar starters are installed
| checkpoint-no-value | Supervisor
daa28347-8c9c-5b6a-ac78-f4bec8493edb | textbox | Supervisor Name:
| checkpoint-no-value | Levels to be recorded
6a8aeed1-7678-5a0a-a2f0-40adfdf47bca | textbox | Ground Level:
13f5594d-ee6c-5d11-9b30-112445e6cf83 | textbox | Base of Foundation:
b8d31db6-10d1-5f64-9a23-ec85ef96473d | textbox | If Plug used base of Plug:
| checklist | CS-4010 - Services Relocation Checklist |  | CS-4010 - Services Relocation Checklist |  | b93d2aab-9b8a-473f-9ba8-57673015ab76
| section | Details
| checkpoint-no-value | Details
b557098e-83f4-5409-8c82-56fdaa7f08ca | textbox | Drawing No:
e85d045f-c1f2-510e-8ac1-18d4740c9b8d | textbox | Rev No:
b29f7551-b36d-50e0-97fc-8f9b56eec8eb | textbox | Chainage:
| section | Inspection Stage
| checkpoint | 1 - Set out by surveyor & handover to Site Engineer completed
b29bdd00-b4a3-5ff1-9ec9-219e351b8da5 | textbox | Initials:
b4ac4b99-83b0-5990-86f6-1e981d90f501 | date | Date:
| checkpoint | 2 - All existing services exposed and identified before trenching
3cc5f551-03a3-5e9a-ab96-3f022e14205c | textbox | Initials:
77bd7d49-43c2-595d-a0c5-72bda6fd3a28 | date | Date:
| checkpoint | 3 - Trench line and profile as per IFC drawings and as set out by surveyors
bf7a1686-03b2-5aae-ad05-61830a661f4c | textbox | Initials:
297cad10-a16c-5361-bebb-ce473e868b4d | date | Date:
| checkpoint | 4 - Trench must be made safe before any person may enter the trench
f3e5b131-aff9-5c90-b8e3-294eb3177203 | textbox | Initials:
f8062ec3-2839-5d51-8cb1-bed10dec146a | date | Date:
f30bcde1-a985-5791-b395-6f5df94a13f5 | note | Comments: Trench depth > 1.5m must be shored or battered.
| checkpoint | 5 - Base of trench inspected and tested if required.
5882ef8a-e3ce-56a0-b5f6-36dcb8b283ea | textbox | Initials:
da7cd4f0-65c5-5817-81c8-8ac703221f66 | date | Date:
320b0ff3-8fa7-50eb-b393-3a7e54e57849 | radio | Under cut required | Yes,No
| checkpoint | 6 - Ensure sufficient protection layer is placed around the new services cable
390a041d-a604-5fa6-992d-45ced10d6865 | textbox | Initials:
4bd734d9-bfdf-58d6-84de-babdb9e46da3 | date | Date:
43cbb162-9fec-5857-864a-c3ce967b5bc3 | textbox | At least: |  |  | mm
| checkpoint | 7 - Ensure warning tape and/or magslab is laid at the correct cover over the new services cable
be7f75b6-8309-55a5-82e4-3f5c5524b679 | textbox | Initials:
06d8d084-2a1c-5b37-ac3d-57195f199a0c | date | Date:
| checkpoint | 8 - Ensure backfill material is suitable and un-contaminated
944cf640-4561-5dc1-a9d1-9e5707fe2256 | textbox | Initials:
35287ff6-cc27-5ce5-b12a-7a61457ca1a9 | date | Date:
| checkpoint | 9 - Backfill compaction tested at every ____mm lift
15a77c68-2097-5b7b-b340-8bc1c6020ff1 | textbox | Initials:
42e2716e-ff28-52ae-8470-62e516b39d9c | date | Date:
| checkpoint | 10 - As-builts updated and surveyed when required
0ffaa3c4-8341-5ce2-9354-52c393c02000 | textbox | Initials:
6b26a1aa-3f7a-5a4b-8246-3f37daa1b1f5 | date | Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
4e2e1917-dbec-5485-a58a-30844247af38 | note | Position: Site Engineer
006d38d3-614b-516f-af7b-408203fb58e1 | textbox | Site Engineer - Name:
fd36aaaf-df6b-590c-9138-198e99f0b472 | date | Site Engineer - Date:
ccbb0241-0a91-509c-86c4-e5d82b30d727 | note | Position: Design Engineer
86d921dd-a57a-5b1e-b445-f7322618f907 | textbox | Design Engineer - Name:
9e72dd92-ac6e-5ff1-abd8-9d6ace156053 | date | Design Engineer - Date:
| signoff | Sign
| checklist | CS-4011 - Bored Pile Record (to be used in conjunction with WTPA-CS-4083) |  | CS-4011 - Bored Pile Record (to be used in conjunction with WTPA-CS-4083) |  | c6b9a959-6e4d-420b-9aba-4ebbd9d16be8
| section | Details
| checkpoint-no-value | Details
4f9f7310-e30f-54a4-9c5d-3bc0580ebe41 | textbox | Work Area(s):
5cfd1600-ac87-50e3-a677-29c7bcdcb2e2 | textbox | Sub Work Area(s):
a09c4ba2-35b1-51eb-a710-f0ff10203237 | textbox | Lot(s):
1d7b1a4a-44f3-50e5-abeb-6b3c8482d8f8 | textbox | Sublot(s):
599572ca-bc98-5713-b9e4-c4029ef0ea07 | date | Document Date:
788b187c-f962-5e12-8e5d-0f414fddbee6 | textbox | Created By:
d4ccf115-650a-5908-a4fb-680b6a960a70 | textbox | Drawing No:
7e7f6075-46be-5d58-b276-7e1dbb7e804f | textbox | Concrete Grade: |  |  | Mpa
8023604c-825d-524b-9256-4ecd9dc0df42 | textbox | Pile No:
2bec978f-3416-5482-9631-79314f3ea69b | textbox | Diameter: |  |  | mm
| section | Set Up
| checkpoint | Piling Platform Compacted & Level
3a2f52ab-f1cb-5746-b1ba-11b3f21ad4b9 | textbox | Initials:
eab11901-6826-5372-b340-24a60349f71b | date | Date:
| checkpoint | Permit to Dig Obtained
3bbde87e-9a0a-5bd0-98d7-ff7ab8c3268c | textbox | Initials:
14167d19-50cb-533a-8be0-bcc17078b59a | date | Date:
| checkpoint | Pile Set Out & Checked
d6801791-dd6e-576c-a037-ded33373b4ba | textbox | Initials:
2ea4b8e9-31e6-5f28-bb36-c3261084247e | date | Date:
| checkpoint | Erosion & Sediment Controls in place
693b50a1-e7c7-57c1-9329-62c70441d082 | textbox | Initials:
f2433b24-e974-576a-b2b9-b13a8f680afe | date | Date:
| section | Drilling
| checkpoint | Design Engineer Notified
a2db02b0-f0f5-5c2f-944f-fa32a9b8cf1d | textbox | Initials:
67c305ed-67cc-5d14-9953-3b91f5295a04 | date | Date:
| checkpoint | Pile Casing Installed to Rockhead
83573c03-de02-59ef-8639-7568c5bb08e3 | textbox | Initials:
59a12f2a-e429-53a3-97bc-d084b17bd1c4 | date | Date:
| checkpoint | Pile Bore Logged
73ab9b7c-1ae6-5fd4-848e-bfdfd97aa4bd | textbox | Initials:
58872e18-37af-5aae-9a13-70410b0d8d4e | date | Date:
b6b06cac-8166-582f-bceb-9e6515d05ab4 | note | Comments: CS-4083
| checkpoint | Pile Drilled to Required Toe Level
11d50dc3-0d4e-5c89-91fc-0ff3a05151f4 | textbox | Initials:
97f4adcf-2da2-546a-838c-4d09e176351e | date | Date:
| checkpoint | Pile Sides Grooved
a6906926-7781-5e16-8e3e-7079d7fa3316 | textbox | Initials:
6469e1e5-81b9-55fc-911c-5239c24e703e | date | Date:
| checkpoint | Design Engineer Inspection of Bore
d9030add-35b0-5e18-a0a0-df95d2d5d498 | textbox | Initials:
3c0d00c3-a917-5faa-9912-f9b70f532a60 | date | Date:
| checkpoint | Pile Toe Cleaned
a8fb9589-87cd-5051-a241-7836e3ab88e1 | textbox | Initials:
07b10a6e-855b-528e-b4c4-7d3e49cc4f04 | date | Date:
| checkpoint | Pile Pumped Dry
f691c211-6bb4-54f6-a149-78f0438025b1 | textbox | Initials:
2498c165-4365-54e7-9190-300851317261 | date | Date:
| section | Reinforcement
| checkpoint | Reinforcement Content, Grade and size
1506ba79-c769-58d4-baa3-4d0866368827 | textbox | Initials:
ab2174cb-307e-554b-8dd3-bd8d2f309e09 | date | Date:
| checkpoint | Placement, tolerance, clearance
b03d9188-52b6-5388-85c8-ad8e8c819c95 | textbox | Initials:
8e1e781a-fbb2-5944-a66a-74b5f7bad125 | date | Date:
| checkpoint | Rigidity and cover spacers fitted
1fb4bb5b-5dd8-57a6-a51a-1ab15a56f1f7 | textbox | Initials:
f322d6d4-904e-5bff-a768-7da95882e6d6 | date | Date:
| checkpoint | Clean steel
d84572ce-df70-5d72-830f-60d77c2079d1 | textbox | Initials:
3161b196-5e5a-53b7-a107-dcd405958b09 | date | Date:
| checkpoint | Lap location and lengths
f529999e-adb1-55f9-be87-9674831f4ccc | textbox | Initials:
d8fbe4ab-3afb-5ac6-9db7-8257394f95ae | date | Date:
| checkpoint | Foam liners fixed to Starter bars
4305ad05-78d7-58d2-aa69-f6060c20bfce | textbox | Initials:
34724a74-d1ff-50bb-a000-f42ce2d9368f | date | Date:
| section | Other
| checkpoint | Correct mix ordered
c58dffe1-91fb-5dfe-999f-3d32d1bff21b | textbox | Initials:
71cc36b0-06db-576a-bbda-ea36123ded30 | date | Date:
| checkpoint | Design Engineer Notified
87245fb5-d8cc-5a06-8664-00fa3f4cac4a | textbox | Initials:
f74cd68d-3e33-5ca9-bde4-91df897bc861 | date | Date:
| checklist | CS-4012 - MSE Wall Geogrid Checklist |  | CS-4012 - MSE Wall Geogrid Checklist |  | cad5c834-006b-49b3-94ee-a48691c20d58
| section | Details
| checkpoint-no-value | Details
1195d586-dc74-50ec-95cc-31d039761edd | textbox | Work Area:
5a9e5bb4-e90e-5b32-85f9-c9fa1e94e8cf | textbox | Sub Work Area:
5d0c3ecf-a3ed-55a7-a908-91d2da34d0b5 | textbox | Lot:
f07f7bc9-4fe8-54d2-b761-aec52986a68c | textbox | Sublot:
08ef3f1d-52fd-519a-b915-371bbbda5f50 | date | Document Date:
f6cbef0d-dc5c-52f7-8044-5546067fbcad | textbox | Created By:
29731692-3809-55be-879b-7a807d5fd535 | textbox | Structure Name:
bcd0767f-0a3a-5d96-ae4f-2e00ef9061ba | textbox | Drawing No:
ac46c1cb-c24f-5ae7-ae07-ed301da219f9 | textbox | Grid Layer Number:
e7fbd54c-ec64-5171-8265-9d87884ecb42 | textbox | Structure Location:
0f2d77a5-05e6-5f2e-8574-885ba035b6e8 | textbox | Drawing Rev No:
a59a6692-c3ae-5dc7-9c64-fee05b6835d0 | textbox | Grid RL:
| section | Conformance Criteria
| checkpoint | Check installation of each course
f1987c8c-3826-508f-a598-4b3b9045abb3 | note | No gaps between adjacent units, max. vertical height prior to backfill is 2 units, min. pin connections per block is 2 upper and 2 lower.
27e2439a-997e-52a5-8a12-bb938b54e4da | textbox | Initials:
ba7ba686-b370-553c-88c0-01c1439fb79c | date | Date:
| checkpoint | Confirm front face alignment in each course is within the allowable tolerance
c21cf561-6d41-5c3b-9c99-17b408461463 | textbox | Initials:
48753f23-956f-58ce-bda6-4955b71fc735 | date | Date:
| checkpoint | Inspect wall batter, wall batter to be within 2 degrees of design batter.
6cb9fda4-fcb7-5a35-9fe0-45e6178c005e | textbox | Initials:
8d003abc-cc79-5b3f-b6a8-e1cf9379efe3 | date | Date:
| checkpoint | Confirm density results before placing Geogrid layer
ad7bd405-f2f3-5f2a-b86e-ba5be48b0d6f | textbox | Initials:
67e77b02-5e27-5174-83a4-115d10230bd7 | date | Date:
| checkpoint | Confirm the type of Geogrid
b4849e20-b2b3-5f36-a25b-8559dc678e5a | textbox | Initials:
c66059af-e663-52fd-a28f-6e387d08387c | date | Date:
| checkpoint | Confirm the correct length of Geogrid
8da9de4a-4a67-5742-ba70-c67288d38d0b | note | Inspect bodkin joints (where used) to join shorter pieces of Geogrid, 1 max. per length of Geogrid.
8c0ff96c-cb32-5070-9345-563659e20a43 | textbox | Initials:
4febca39-99e0-55a7-9074-bebf53cee8c0 | date | Date:
| checkpoint | Confirm the correct elevation of Geogrid.
3c3fb2b5-6f78-57e7-b36c-c95c173f650f | note | Place within 75mm of design elevation
499662d5-c30a-5b0d-9e9f-6f69c3c71aba | textbox | Initials:
71fbae10-f166-5cf7-b467-52ba0c030243 | date | Date:
| checkpoint | Ensure Geogrid is placed flat on top of the compacted layer
0d6700c4-9e49-5fb6-98b5-f7d64571aeca | textbox | Initials:
6c01f4c2-6868-5ead-af43-2033a1c52538 | date | Date:
| checkpoint | Ensure Geogrid is connected correctly to the block pin connectors.
a0e5db4e-36cb-550e-befd-3c5fdd237262 | note | Max horizontal distance between geogrids at wall face is 10mm
b5dc1acb-0553-5b01-908b-d86e8757f30f | textbox | Initials:
8c41dde2-8e54-5509-8568-d7e095175e72 | date | Date:
| checkpoint | Ensure plant does not track over Geogrid
ec1d7c02-a694-574a-9b9f-384bb1790667 | textbox | Initials:
7d559460-7844-5eb7-8fd4-c567aa92103c | date | Date:
| checkpoint | Tension geogrid and peg to hold geogrid tight
3209ddb7-cac5-5d77-90c3-12de4a4d5ead | textbox | Initials:
bf554995-3141-50d5-bded-8e588fef96c6 | date | Date:
| checkpoint | Place backfill across the geogrid, plant can track onto geogrid when 150mm min backfill has been placed
1d316e68-0320-53ca-8f74-ac25b1576bf2 | textbox | Initials:
71cd74af-04d2-50ff-973a-9b6055ccdb6f | date | Date:
| checkpoint | Monitor plant and equipment keep 1m from front face of wall.
54b7b6fb-df59-51e4-bc97-a5b07ca21c67 | textbox | Initials:
ce953209-b5d0-553e-ab4a-58fbeb1d5b9c | date | Date:
| checkpoint | Design Engineer inspection?
852dfec1-525f-552c-8abb-062990479ff2 | textbox | Initials:
173fb9e5-1e19-5aa7-80fc-762187923104 | date | Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
59c482a7-0c3d-506c-995e-f9f24611d1c8 | note | Position: Site Engineer
5fb43b88-9a52-565c-ad10-f3bd439b5706 | textbox | Site Engineer - Name:
40cdb972-13d4-5820-b9b8-bb28d6f17742 | date | Site Engineer - Date:
dea3eedd-4b7c-5fec-abc0-6c10be82549e | note | Position: Design Engineer
7c7fe613-9bb6-51d2-b2c5-851c2306ada7 | textbox | Site Engineer - Name:
da9037a6-cf4a-54c9-afd3-4c61314c7bd8 | date | Site Engineer - Date:
499aa3b8-aeef-59ed-bcdd-7b0ffe6d8636 | note | (Note: Attach a sketch showing grid on a separate sheet as necessary)
| signoff | Sign
| checklist | CS-4015 - Shop Drawings Checksheet |  | CS-4015 - Shop Drawings Checksheet |  | d8d03cb5-b8c1-47da-b07a-83671e380bc2
| section | Shop Drawing Check Form
| checkpoint-no-value | Shop Drawing Check Form
253a7918-7d82-5249-a007-f45d635f432e | textbox | I |  |  | (name)
584ffa1d-bf99-5523-956b-fbfd7fe1cab8 | textbox | of |  |  | (firm’s name)
ccc475fe-d7f5-5914-9225-47b85ecdf8e8 | note | being the Construction Team’s designated person responsible for the preparation of the shop drawings required by specification C0600.7, certify that the drawings listed below have been prepared, reviewed, co- ordinated and checked prior to submission to the Design Team in accordance with the requirements of C0600.7.
| checkpoint | 1.0 - Shop Drawings prepared to an acceptable presentation standard
| checkpoint | 2.0 - Shop Drawing revisions noted and clouded
| checkpoint | 3.0 - Dimensions:
acc832cb-ceb9-528e-a10c-b4c977d04d51 | note | Relevant dimensions indicated
f393e5c1-ca67-5656-b8fa-3445cc7b7a29 | note | Site measurement noted and checked
0dcc1b2e-034c-5af7-94ad-8c7233b2820b | note | Dimensions co-ordinated and checked with the requirements of the Contract documents and other trades
| checkpoint | 4.0 - Drawing numbers and revisions from which Shop Drawings have been prepared noted on the Shop Drawing
| checkpoint | 5.0 - All relevant contract information including specification requirements indicated on Shop Drawings
| checkpoint | 6.0 - Shop Drawings checked and co-ordinated with the requirements of all Drawings and Specifications (e.g. Architectural, Civil, Structural, Building Services, etc)
| checkpoint | 7.0 - Shop Drawing checked and co-ordinated with the requirements of other trades Shop Drawings
| checkpoint | 8.0 - Drawings checked for corrections prior to re-submission, where required by Design Team to be re-submitted
| checkpoint | 9.0 - Shop Drawings approved by the Construction Team for fabrication, signed and dated
| checkpoint | Signoff
3a839867-064a-5245-a452-ed2c1504dd20 | textbox | POSITION:
5f4c25e3-d1b2-589b-941f-b0c588259e60 | date | DATE:
| signoff | SIGNED
| section | Drawing Numbers to which certification applies are listed on the following page
| checkpoint-no-value | 1 - Drawing
8fa05cef-bf33-5b8d-b24e-28b976c621d4 | textbox | DRAWING No.
f77ee527-1aaf-5fd8-8dfe-660460d90ff2 | textbox | REVISION No.
d34f9457-63d7-5223-91b1-f5ad0c86d28b | textbox | TITLE:
aa81a07a-4382-59e5-9cb4-4806cb71e4f5 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 2 - Drawing
fc092a87-ac42-5b65-a43f-4586196f33c0 | textbox | DRAWING No.
40a3b08a-19ad-57e5-b4e1-0bc96ff87898 | textbox | REVISION No.
8f1dd44e-f9e3-57a7-b1f1-fac486641046 | textbox | TITLE:
18cda69b-edb3-5298-8239-9c152267134c | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 3 - Drawing
977269eb-f884-587f-9eb5-d4c57ac4cf5d | textbox | DRAWING No.
701905b9-444e-54d8-9719-950ede7d0ae3 | textbox | REVISION No.
cfbce92c-7bf3-511e-aa38-93ddf49a6ff1 | textbox | TITLE:
ee9cb0d3-aff8-5dd4-8179-81ff6337c1c8 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 4 - Drawing
35819759-9bf2-5c64-bd81-8810f9acd143 | textbox | DRAWING No.
d914e6a0-ec5a-5fe5-8d32-84022530476c | textbox | REVISION No.
5b37bc5f-5b7d-5eb1-90d5-93bbdc122578 | textbox | TITLE:
3fe6a7a5-40dd-564c-984f-2c60c386a9a3 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 5 - Drawing
421a90c1-9ebf-53ac-ab09-ea05bbbde447 | textbox | DRAWING No.
fcdd60ed-34ac-5d6c-a894-60714e3fedd4 | textbox | REVISION No.
7a71cbb4-5b75-5dc5-8d3f-4955dcf0d7b4 | textbox | TITLE:
e54b6c1d-5cb6-5c64-b113-0380a4d621a1 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 6 - Drawing
ccc6ec0a-2a42-5005-b2d5-025bb1a16215 | textbox | DRAWING No.
683737ec-b441-55ba-8ce9-bee012f4073b | textbox | REVISION No.
885f3420-657f-59e7-ab19-3aab40c93ef5 | textbox | TITLE:
95b335aa-6b38-5abd-8c85-23be5e3bf748 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 7 - Drawing
60580d4f-44d9-58d2-a5d9-72331a78bbc3 | textbox | DRAWING No.
af7fc6d1-dc62-5942-9a95-16707df921a3 | textbox | REVISION No.
83aab29c-f456-5c56-a33d-9ec3c39be87d | textbox | TITLE:
0cc86ad7-919d-57b6-a142-cb5502c495b0 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 8 - Drawing
7ac2ed21-f540-58d1-bc56-30113149e783 | textbox | DRAWING No.
f7526aa4-7396-5ca7-9906-452deeb1ccd6 | textbox | REVISION No.
d70106f5-7f99-5990-8265-4fd7ddbce95b | textbox | TITLE:
59b10cc4-e2e3-59c5-8a44-537e595fef7e | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 9 - Drawing
6044475a-d9b3-50a9-8200-323b95d8db05 | textbox | DRAWING No.
231177c7-487f-564a-821b-f688ef505b2c | textbox | REVISION No.
cfa139f9-f04c-5761-8512-a8a8a5ba5d63 | textbox | TITLE:
9cb26ee1-6af4-5215-a09b-4c20944a704a | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 10 - Drawing
430f3d53-c84b-571d-8b1d-8731ec8598d8 | textbox | DRAWING No.
9fe6dc7c-313a-55b2-8302-ffa08560cfd4 | textbox | REVISION No.
1581b3a1-4e63-5208-9295-b755e6644c8a | textbox | TITLE:
bb4d58cd-c636-5214-b97f-dc408f333d8c | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 11 - Drawing
5528a500-45be-52b3-8094-bfa69c8b1c36 | textbox | DRAWING No.
5dbcba74-fa5b-5cbf-8dcb-51cb460b6f00 | textbox | REVISION No.
34e37db9-0ee1-592d-8bb7-78a1f6019e91 | textbox | TITLE:
d47250fe-8153-5a51-a721-1d1132460017 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 12 - Drawing
f29c2ab0-4327-586b-b390-06e0e88a4ede | textbox | DRAWING No.
61ec56b5-89a4-5a2e-9b06-123aabadbe48 | textbox | REVISION No.
b7722e32-a78e-53f9-ab0b-8fc955d6f2a9 | textbox | TITLE:
9da21b2e-39e3-5cce-86a9-a4dd6242b773 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 13 - Drawing
a0efa52e-eaec-502a-907a-3a52965189db | textbox | DRAWING No.
21d64917-3af0-5a00-9cb8-ea6d18ae3763 | textbox | REVISION No.
4fd9236d-4cc5-514c-b6e2-e008ec02e208 | textbox | TITLE:
0ad899ff-d115-5ca6-89f1-df877d57f92d | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 14 - Drawing
260a941f-832f-5626-81ac-0bd004a4b874 | textbox | DRAWING No.
424edb0b-5d68-5bb2-984c-603cf055c1c5 | textbox | REVISION No.
d578d9f3-2a5e-56a8-ae86-1f561e20000c | textbox | TITLE:
e87651e9-663a-5006-92f5-1117d6a8a9e2 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 15 - Drawing
0e33114c-d9c8-5a24-a388-744fd804a678 | textbox | DRAWING No.
a1f55ec7-3f0a-51a1-88aa-97420f8343a9 | textbox | REVISION No.
fb18a90d-7453-5a39-8e7d-7847434e9b93 | textbox | TITLE:
f1f456cb-2fa2-5a78-a9c9-adfa333d53c2 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 16 - Drawing
bb27a9e4-c27a-5ea9-9bc4-58a763f07762 | textbox | DRAWING No.
74a13cf6-e1db-5cab-9401-b253d127ac1a | textbox | REVISION No.
fc6d26de-a4cd-56d1-ba1f-fe194e19277d | textbox | TITLE:
6afe01a0-b29c-5ede-8fcb-c327ce2ab4d4 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 17 - Drawing
5ecba2f9-cc65-5464-bff2-18b3aed0c05f | textbox | DRAWING No.
ee32e4ac-d318-5361-be6f-93818061ab77 | textbox | REVISION No.
d1a46329-9fe7-5717-9626-20506fe454e7 | textbox | TITLE:
116ce161-4528-5ce8-b2d3-d23dd861aada | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 18 - Drawing
f43599bc-9581-5057-97f4-834439beeb70 | textbox | DRAWING No.
bef8c980-db34-5c58-b378-9de086563d02 | textbox | REVISION No.
c669955f-0e13-5559-834d-d8f2931c04d0 | textbox | TITLE:
571dedf4-cbb7-5adb-bee8-504385740dc5 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 19 - Drawing
37dac657-a1d4-5e18-ac22-573ed9be601b | textbox | DRAWING No.
ffa16e67-8dd0-5b45-a547-5d39fcb334df | textbox | REVISION No.
9b6cbb22-c468-5abe-acfc-bd118346200b | textbox | TITLE:
46fc2dac-d1c7-5d94-8e1c-0d40e99fbffd | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 20 - Drawing
089650aa-d6c1-5619-b967-999ab626a714 | textbox | DRAWING No.
26ca9b8a-5b62-5254-8db0-f5f0212b6452 | textbox | REVISION No.
001433c0-7051-5556-a1c7-6c2933138f6a | textbox | TITLE:
df740cc2-be6a-5056-af56-cd71a12a94e3 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 21 - Drawing
4b09548d-dfd2-5d8c-9b51-5a91c4c9ba49 | textbox | DRAWING No.
3143d83f-991d-565f-9833-3653a0dbabc4 | textbox | REVISION No.
a9f04b75-c88f-5659-9696-49bde141b403 | textbox | TITLE:
4eb21972-6e17-5287-8275-f57388ded638 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 22 - Drawing
d2845909-503a-57c9-9aca-5bf3c04c00c9 | textbox | DRAWING No.
98044886-16f5-5fdc-89b1-7bd5989b35eb | textbox | REVISION No.
1d96ffb6-e821-5c37-baf5-50c3412f9b70 | textbox | TITLE:
b8731bb9-8a39-5946-9450-ba408e4da58e | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 23 - Drawing
b4c70c0a-c0f5-5608-b3d5-ea365b76431e | textbox | DRAWING No.
fe6022f6-f98a-548d-a49c-a3b4327a3b12 | textbox | REVISION No.
8a345893-41ff-593a-aada-f952f5ad500f | textbox | TITLE:
e5ef7641-e460-5d16-9799-59073b82ef39 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 24 - Drawing
df86cc99-e0ba-5f9f-a589-da4efb578b37 | textbox | DRAWING No.
8d90ccec-c9ee-5e3f-ae85-d175fa6166c4 | textbox | REVISION No.
e63c36ae-7a68-5369-8708-bb284b00bfc6 | textbox | TITLE:
111fd689-cdda-5677-bb24-fea7e434b7c6 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 25 - Drawing
0ed3cba2-095b-5f7e-a8f5-7e45a3f8a35d | textbox | DRAWING No.
49e8d6be-1ea2-5a60-a297-3619986dafd3 | textbox | REVISION No.
62e54f83-b7e3-5891-8a0f-b048638f37e2 | textbox | TITLE:
511d0f3a-ca1f-5fc1-ba4c-f783d6a2f574 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 26 - Drawing
4b932adc-aafd-5234-be79-a7b4edd64e9b | textbox | DRAWING No.
47fbcf5a-db48-5a43-a51b-cdb2f59b5ccc | textbox | REVISION No.
2c5bf03f-e51b-52fa-9de5-0d30cebc1264 | textbox | TITLE:
2c0ddfa0-f696-5fbe-b2e6-195c3e5d0f45 | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | 27 - Drawing
71ce01c1-af7b-5f30-80e8-73ad09ad3565 | textbox | DRAWING No.
e78ea8d7-8c14-59f6-9386-d89a65b71268 | textbox | REVISION No.
4d02dcd6-10ef-53e0-89a9-ba62c7bb15a3 | textbox | TITLE:
a125fa53-ebfa-506f-bbad-491cb3220f7f | date | DATE ISSUE TO DESIGN TEAM:
| checkpoint-no-value | Note: A completed copy of this form shall accompany all shop drawing submissions to the Design Team.
| checklist | CS-4020 - Bulk Fill Earthworks Record |  | CS-4020 - Bulk Fill Earthworks Record |  | b43a6f20-3c9f-4762-928a-9a2538c2d7c7
| section | Details
| checkpoint-no-value | Details
82d2cb43-dbc7-5ca2-98b3-54c0617e3ca4 | textbox | Work Area:
0b27267f-d2c7-52d0-9d35-955848c41c3e | textbox | Sub Work Area:
9a7f0ba6-24e3-5484-8c7a-8ae7f7a21e09 | textbox | Lot:
d939f761-badd-521d-86d2-6fdebe884a5a | textbox | Sublot:
f5a64cdf-5dc8-5b02-99eb-d6650d332e69 | date | Document Date:
da8f6bbc-e8c7-5665-b3c3-d134117ceb64 | textbox | Created By:
| section | Pre-Construction Phase
| checkpoint | 1. First 1st lift - Ensure underlying layer has been signed off by Design Engineer – CS-4100
| checkpoint | 2. For subsequent layers - Ensure Underlying layer has been signed off by the Site Engineer and/or Design Engineer as well
| checkpoint | 3. Ensure previously constructed fill has not deteriorated from required fill standards before placing new fill
| checkpoint | 4. All source testing completed in accordance with Specification XXXX – (Example - 1 x PSD completed @ 3000m3)
| signoff | Site Engineer Verification Signature:
| section | Construction Phase
| checkpoint | 1. Batters to be overfilled by 250mm – Specification XXXX
| checkpoint | 2. Visual inspection of fill for contamination, segregation & oversize particles
| checkpoint | 3. Minimum dry densities: Example – 95% MDD - MDD = 2200 kg/m3 - Specification XXXX
| checkpoint | 4. Scala/Shear Vane/Clegg limits: Example Scala – 2 blows per 100mm (Type 1 material) – 4 blows per 100mm (Type 2 material) – Specification XXXX
| checkpoint | 5. Measure Lift thickness and confirm applicable roller and passes are applied in accordance with embankment trial results
| checkpoint | 6. Vibratory roller to operate at 3km/hr (or less)
| signoff | Site Engineer Verification Signature:
| section | Bulk Fill Earthworks Record
| checkpoint-no-value | Details
fdcb37f3-e287-5a2a-abc5-ddd97ad4717e | textbox | Weather conditions:
0124251c-186b-5ea9-b4a6-e8340e02e3c9 | textbox | Supervisor/Foreman Name:
| checkpoint | 1
d1b1daee-c676-5844-b179-46c134f34206 | textbox | Lift #:
14597f30-99e5-5b98-aaca-1644cfe3fb30 | textbox | Chainage From:
2bdcbbda-8b28-583b-ac31-e10edc61efac | textbox | Chainage To:
903813b3-eb93-5b08-8667-7bf94bfcbcb0 | textbox | Test Spec:
2bfcf86f-e95c-5d35-81cf-9a717ce7d754 | textbox | Material Visually Inspected:
a8fed40c-c0a7-5ef9-8935-30ffcc7f3f7a | textbox | Extent of overfilling checked:
ce90f6f7-c502-56fc-b2da-c09d96790891 | textbox | Lift thickness (mm):
e6504faa-da9b-5f79-8554-947aad08bf3e | textbox | Roller type:
3e7347ec-b765-5241-a8ad-d3376f49475b | textbox | Minimum Passes:
16b782f1-5639-5aa1-8994-f885f8853940 | textbox | URN test numbers:
335bdb9e-f102-5054-97f0-b7eec713c3a0 | date | Date Completed:
b9da4007-8ef8-5139-ba0c-4b78694df112 | textbox | Site Engineer Initial:
7ce9b335-4d32-5c07-9770-3b1e28a0616a | textbox | Design Engineer Initial:
| checkpoint | 2
5fd73407-d77d-5f3d-a1cb-25d76e1c111f | textbox | Lift #:
d98fb1f9-bb02-5f5c-a807-68dc9a326442 | textbox | Chainage From:
f9c5df50-7303-563b-89b0-4ef376dd2c67 | textbox | Chainage To:
de484948-b240-55bd-b5d9-b807e99a56a3 | textbox | Test Spec:
fa1b1959-06f4-573a-a8ab-0f0325e5f4e5 | textbox | Material Visually Inspected:
dc8be1c9-3b2b-5ea8-8064-a3fadb81ac4d | textbox | Extent of overfilling checked:
b1c0f5bd-2dbe-59aa-b009-6d526bc14d3b | textbox | Lift thickness (mm):
6f0d2d00-a8de-58da-abd5-7dc203c7668b | textbox | Roller type:
5b899932-71fe-52d2-894f-63aee3dea86f | textbox | Minimum Passes:
7ebe5d82-66a3-54ab-b05f-7c0a5be3d4b3 | textbox | URN test numbers:
2aa75bb5-e3f4-59ff-bbd3-d8536f6572d6 | date | Date Completed:
d920f610-dec6-55c0-8b91-cb578b52bb85 | textbox | Site Engineer Initial:
acf76ce0-5086-59be-9242-aafed3dfb224 | textbox | Design Engineer Initial:
| checkpoint | 3
f77682b1-1c01-53d4-9c9b-c7facb7fab7d | textbox | Lift #:
db7c28ef-f076-568d-98c5-1d5cdeec9158 | textbox | Chainage From:
6cde2a9c-8414-5425-8f2e-82c002d2af9b | textbox | Chainage To:
012776d9-e022-5016-96a9-697fe6a8d399 | textbox | Test Spec:
1b78d463-4df9-509f-9ef3-357a290bead0 | textbox | Material Visually Inspected:
b153c96e-b4c5-5ef3-b37f-1602dc436c45 | textbox | Extent of overfilling checked:
e4fb126e-88f6-5e3f-8663-368fc5dbdb6e | textbox | Lift thickness (mm):
9002747e-e292-5e9b-846a-e42a77619950 | textbox | Roller type:
0e78ccb6-07a9-5307-ae73-b683fa9ae7d7 | textbox | Minimum Passes:
643264a5-a0a2-509c-a898-7ff40cff5d74 | textbox | URN test numbers:
7a0aca8c-85cd-5052-9c8c-57d17a8605bf | date | Date Completed:
766af33e-4f83-5964-9540-d04d5c1206c1 | textbox | Site Engineer Initial:
a39daf78-3826-550e-951a-8eb1f3757f05 | textbox | Design Engineer Initial:
| checkpoint | 4
338d1d82-b41a-5ea6-a3ec-e06a99b8d9c8 | textbox | Lift #:
9b0de1c5-5f2a-58e3-a88d-158dcb2677ef | textbox | Chainage From:
8e96b469-4307-5587-98f7-90f21ac70bd3 | textbox | Chainage To:
32089386-729a-5922-8069-1fe84880ebb8 | textbox | Test Spec:
5936df39-1395-56e7-8aed-a810c4750ca1 | textbox | Material Visually Inspected:
71899587-baeb-57ab-a780-3bd7f8955ca6 | textbox | Extent of overfilling checked:
e783f768-e696-59e1-b894-3e7c7aae2196 | textbox | Lift thickness (mm):
297f5f47-6b8f-5639-a7f0-f62528e2009a | textbox | Roller type:
a36f1655-ba42-5cac-af86-0671ab71c4ab | textbox | Minimum Passes:
97deb59e-bdb4-5d69-8b71-499193be5c79 | textbox | URN test numbers:
7985efc6-9920-5ae3-b171-d73e77b378f7 | date | Date Completed:
dd331189-1c5f-5477-8bdf-18e029928c2e | textbox | Site Engineer Initial:
3f52ea13-49e1-5843-861d-70fc028c430c | textbox | Design Engineer Initial:
| checkpoint | 5
ef168a70-a193-52cd-9408-a20a51e776be | textbox | Lift #:
3bb1b30b-884e-5753-89d1-99be4f7eb586 | textbox | Chainage From:
39474d63-c03b-551c-994d-aa1dcd6787b1 | textbox | Chainage To:
31ec63df-cb7e-549c-b540-d2fbbb50f871 | textbox | Test Spec:
6dd00b0f-df2b-533d-a4cf-fdce586bf517 | textbox | Material Visually Inspected:
ddab98aa-a72c-56a5-9231-1b7e09cf02b1 | textbox | Extent of overfilling checked:
28e9267b-b249-5440-93ad-8d1376f03cef | textbox | Lift thickness (mm):
6c361fde-529b-531f-9077-9b5dc82b0607 | textbox | Roller type:
9797a1f6-bf27-5aee-aa4d-44ca813a8a9f | textbox | Minimum Passes:
3ca1ca1f-cc4e-5bd1-8024-68be813bc33f | textbox | URN test numbers:
8cf44da2-c593-5e1f-8663-f9d1f77ffd39 | date | Date Completed:
26888401-7631-5bf6-bfa1-9bf85331f435 | textbox | Site Engineer Initial:
b8bbdde7-8cb5-58f0-95a4-28658abda0fe | textbox | Design Engineer Initial:
| checkpoint | 6
b83c8108-2150-503a-ab93-9e2409774c94 | textbox | Lift #:
e79b48b8-6006-5b19-872d-371d23867ce3 | textbox | Chainage From:
2a01930c-d7b9-5bc9-a77d-160ac4e79cc5 | textbox | Chainage To:
cd4ce2cc-6505-51c3-92d5-f5edcd2abf6e | textbox | Test Spec:
9d6ace94-36d2-5d49-803f-3a8e045aa97b | textbox | Material Visually Inspected:
42b1c110-eeee-5be5-888d-841383a81851 | textbox | Extent of overfilling checked:
bd260bb6-e4d0-5129-a0da-1e40325009ad | textbox | Lift thickness (mm):
91b8d576-7abd-5927-b8ff-f78eff4ef018 | textbox | Roller type:
38f802b5-12b7-5583-9b8e-baa8f3d551fd | textbox | Minimum Passes:
213d75a9-43bf-5865-8577-726cd5d7f7d4 | textbox | URN test numbers:
92b70eb7-f304-5e5e-b3e2-561ab0db6b44 | date | Date Completed:
cc34b9cb-4852-57e1-b319-61ea96ddc425 | textbox | Site Engineer Initial:
7e8dc411-abd3-5194-9819-be7d0ca2045e | textbox | Design Engineer Initial:
| checkpoint | 7
c48e70fe-523c-5031-97ea-bc9011399a64 | textbox | Lift #:
2a85ca4e-2512-5b5f-965d-26c2d9485a46 | textbox | Chainage From:
1a54057d-67c1-5d75-b7de-aaf43cd9bb81 | textbox | Chainage To:
0d811e81-622e-51f4-9dd9-8627707af12f | textbox | Test Spec:
3dbc6424-9324-5763-94ca-b6db4dfaa137 | textbox | Material Visually Inspected:
53ef4596-c688-568b-a572-c7377affc1e6 | textbox | Extent of overfilling checked:
f3d2f489-d780-5685-b63b-de0222c1e8f7 | textbox | Lift thickness (mm):
610166f5-f8c3-52cd-8a16-0589cae54c3d | textbox | Roller type:
7bc63d26-7d4d-5d7e-b42b-5a7c0851be6d | textbox | Minimum Passes:
52d9fb2f-1c86-5a50-b44d-cfb6344756c9 | textbox | URN test numbers:
8d508f80-bfa4-5b85-8653-5e8f0a69018b | date | Date Completed:
41a0c67d-26ad-5851-9bf4-ee345cac7216 | textbox | Site Engineer Initial:
3081d995-8070-5381-8890-7f1579554b7d | textbox | Design Engineer Initial:
| checkpoint | 8
8cb86a0f-0fbe-5e39-92bf-a86ef815a094 | textbox | Lift #:
d50b7a95-19dd-5237-b3f3-ebc1708f2c16 | textbox | Chainage From:
43c8ac1c-58c2-50f7-a728-dc2a834f21a9 | textbox | Chainage To:
495d019d-ba9e-5639-9b46-987043f1c74f | textbox | Test Spec:
3e6d2959-d5a0-5f06-bb83-7d5d58d7c2e4 | textbox | Material Visually Inspected:
4f620e7a-eb5f-5c2d-8369-8c8044695b92 | textbox | Extent of overfilling checked:
809f7a4b-2acc-55cc-894f-b6ae21746f65 | textbox | Lift thickness (mm):
cb53c632-d40f-549e-b32e-f753356bf1b5 | textbox | Roller type:
7d167da4-a4cf-5583-bd28-f2906ee358f1 | textbox | Minimum Passes:
c3e15a8c-9f0d-531a-bc01-2d8b6d01b11d | textbox | URN test numbers:
4e89331e-0acc-5815-8415-aa8927d07825 | date | Date Completed:
42f1d8bc-4f41-5302-bd70-4e71ad5179e9 | textbox | Site Engineer Initial:
230adc0c-06a0-5ced-9de4-0ced8b15a9aa | textbox | Design Engineer Initial:
| checkpoint | Signoff
996db487-667d-50b6-8b3f-71f85474bc8e | textbox | Site Engineer:
cb344002-fd99-5987-9fd0-c24e6d52e9a0 | date | Date:
| signoff | Signature
| checkpoint-no-value | Other Information/Comments (photos, survey records, sketches etc.)
0ade57b3-bc6e-5e8d-a472-dadbd51c9489 | note | Additional Information please document
b3bd2eaf-491f-5b0d-a545-d48bc895faa2 | textbox | Quality Manager:
29e13a60-c891-52d3-9bb0-b10612700fbc | date | Date:
| signoff | Signature
| checklist | CS-4025 - Drainage Line Record |  | CS-4025 - Drainage Line Record |  | ef3c272a-93d9-4e6f-bade-e06f515a2dd2
| section | Details
| checkpoint-no-value | Details
9bb8d8d9-d3a6-5bef-9f52-a1e4d005273e | textbox | Drawing No (& Rev No):
59537013-33c8-552c-9e48-5f765622f513 | textbox | Drainage Line:
cbb69cd9-c184-5713-b515-1026a8b1fa37 | radio | HS3 / HS2 / H2 | HS3,HS2,H2
29d0de88-cef9-5821-92a8-bf923cedf1b5 | date | Date:
| section | Inspection Stage
| checkpoint | Set out by surveyor & handover to subcontractor completed
5054a653-5d97-5d26-b003-e3a6f419a90f | textbox | Initials:
080a7af2-f1a2-58ec-8348-1e07c8b28839 | date | Date:
| checkpoint | Start point (i.e. manhole/headwall) checked for line & level prior to commencing this drainage line
a0baa160-49bb-54a8-a563-823c2a44b48f | textbox | Initials:
a15ee73b-7323-562d-a78b-f512dbb895f6 | date | Date:
| checkpoint | Foundation Undercut Compaction base of trench subgrade Scalas taken every __m
e581a2da-184a-5bc4-bba3-55812ce4e6bb | textbox |  |  |  | m
3b8a5192-5d2a-5020-bc6b-7f9aa35e76c5 | textbox | Initials:
af81223f-efbb-5d77-9b60-c24dd27e8964 | date | Date:
689d72bd-f039-5951-a2e7-1f2885dacbbc | note | Comments:
d7d03e34-6683-56b4-9403-7efa25874ad2 | radio | Under cut required? | Yes,No
d32a7be0-11ff-5381-b580-01e0792fc381 | textbox | Depth:
| checkpoint | Bedding Zone Compaction Testing every __m
5d2329b7-0a18-5b31-984e-689d0c972553 | textbox |  |  |  | m
62d5b174-4e99-55b2-97f8-e1f6d67d3586 | textbox | Initials:
9d823bd7-22b5-50c1-821c-773ee1da0ac9 | date | Date:
cb0257ed-e131-5bc4-b5f7-bef438dc49b5 | note | Comments:
45c64dd7-ef97-58d9-b31a-5c473636ca01 | textbox | Material:
| checkpoint | Engineer to inspect base of trench
cbb8d52c-75fb-5266-afac-651ced800722 | textbox | Initials:
81c9c1c9-57f2-52b9-907a-1379700a4d3f | date | Date:
| checkpoint | Trench width per __m culvert line
1cdd8626-82dd-57aa-97f3-305b749790f7 | textbox |  |  |  | m
bd56ce60-883b-50de-8787-b2b00d61bf7d | textbox | Initials:
30171b06-2783-5813-aef5-b60feeea1427 | date | Date:
| checkpoint | Pipe Laying Inspected and approved by Site Engineer
80bc31ea-9746-590e-87a8-f58c0a7ec62c | textbox | Initials:
202e1165-4d37-56e5-961d-6735eb47894a | date | Date:
| checkpoint | All Connections completed and inspected as per specifications
b2abc755-6df8-5161-8836-0ded1059c87b | textbox | Initials:
cadda24c-df7c-5a85-95ef-4894356ec9cb | date | Date:
b3e11363-4cf0-539d-8611-1db2b1be06e7 | note | Comments:
99b371af-b2c7-556d-b131-6ac823bec3f8 | textbox | Structure (In):
ed743099-9857-5109-82d3-ddacd2bfb595 | textbox | Structure (Out):
| checkpoint | Haunch Zone Compaction Testing every __m
ae05ad46-6f86-5f7e-943a-7e5149dbd5d4 | textbox |  |  |  | m
056e2a0d-3b1e-5268-b13a-9c1fa6333073 | textbox | Initials:
2525d9ee-b7fb-557e-8a1b-78a42a30d0a8 | date | Date:
cae3493c-07cc-52fe-8fff-b4df6ce7bbe8 | note | Comments:
a342b88f-b2f7-5a75-a580-f7fac13ba9a5 | textbox | Material:
| checkpoint | Side Zone Compaction Testing every __m
d7042613-6c7b-5463-9d5b-73e871788385 | textbox |  |  |  | m
dbb79555-e196-5e95-9050-7260a192cc7e | textbox | Initials:
4fb8449c-56e4-51de-a70e-12f8550c5a50 | date | Date:
62daf727-7fb7-524d-b60d-da8715fd02ec | note | Comments:
ff884d3f-846f-5d48-8c0b-918215957b5f | textbox | Material:
| checkpoint | Manhole Conections to Pipe Joints Haunched/Concreted/Epoxied
6a0c7be7-1e9e-5795-8288-6e1f2c405126 | textbox | Initials:
3cb27725-297b-5962-9529-f0dbf17d83ba | date | Date:
| checkpoint | CCTV Completed and passed
8d74fe57-8878-5552-987c-dee45f11cbd3 | textbox | Initials:
74d2c8f0-8e0f-5eb6-abc6-3f5209f304c9 | date | Date:
| checkpoint | Water tightness test passed
4a36c675-b41e-5a42-9d27-c00ccd043802 | textbox | Initials:
122cc6da-e07b-5608-89e2-45da5fabc72e | date | Date:
| checkpoint | Final visual Inspection Completed and approved by Engineer
34112031-0f4e-51e3-8109-f33f7ec8071a | textbox | Initials:
f1a579a3-683a-5c02-94c3-3d149e029bf7 | date | Date:
013491c2-8f1e-5b04-b4c4-37769c2b140e | radio | Invitation to inspect: | Accepted,Declined
d4afc681-ae01-52a4-941e-073a5b0f570d | note | Design Team
7c0553f5-eda6-5193-a5dd-eaba8b3b42dd | textbox | Design Team - Rep:
56162ec4-2a98-5dfa-8474-512537207827 | date | Design Team - Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
4139a277-e277-5d32-aa3c-5f83587778e2 | textbox | Name:
54357385-50fc-5f5a-b2a9-9c62ee32ba32 | textbox | Position:
4d105e5f-841e-5408-b3c2-fa21fc61fcea | date | Date:
| signoff | Sign
| section | Drainage Line Record
| checkpoint-no-value | Direction of Flow
be22d9c1-8960-5050-ade2-db29cb62f3e0 | radio | Indicate Direction of Flow | <,>
| checkpoint-no-value | Invert Level (In)
9b8d0530-9b62-5293-989b-97b13212a4e9 | textbox | Design:
838f8837-1dc8-51aa-9489-9d1b4a1a0b38 | textbox | As-Built:
| checkpoint-no-value | Invert Level (Out)
22939f4e-ba5c-56c4-963a-b22a2271bb4c | textbox | Design:
fca65562-bd51-57db-bdc8-ff224882634d | textbox | As-Built:
| checkpoint-no-value | Structure (1)
4d210f38-14d8-59aa-9034-382f60cb49c6 | textbox | Structure Name:
bcc6d046-4a61-5074-9dc4-8fdfab907fb5 | note | Status: New
1a645d5b-4abe-5b71-957c-48e0393838d4 | textbox | (New) Dia:
0150fe4f-795d-5e9b-bb72-d01db0cba21b | note | (New) Type: MH
7aa0084b-b1c8-5ae0-829d-54f2152da1d1 | textbox | (New) Distance to Flexi Joint:
688726d1-daab-5593-a997-fe1ce8a8831c | textbox | (New) Epoxied:
37fb1e9f-4485-540f-80ff-1351eeb401d9 | textbox | (New) Water tight:
b6e6d16a-5288-51db-9802-543002ca59f3 | textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
de58c5fd-83d8-5cdf-8b63-3a6c30da6b0b | textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
70d35401-9f02-5868-bd20-7315184a6869 | note | Status: Existing
8e40e2aa-d9b6-5425-9b4f-f4343b9d5618 | textbox | (Existing) Dia:
02400286-af35-5df8-b6ee-8dc38c642479 | note | (Existing) Type: WW
d965d09d-e906-512a-a53a-b46a76196c61 | textbox | (Existing) Distance to Flexi Joint:
5320dcc1-35d3-5043-ae35-4d9e0e175a93 | textbox | (Existing) Epoxied:
754c31bc-17be-58a0-8251-9e8b79759382 | textbox | (Existing) Water tight:
7ee30c10-d31c-5356-8627-23996941f89f | textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
3afdcd7d-c894-59b9-af35-6d20a2f9dd04 | textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
| checkpoint-no-value | Pipe Details
e27de804-e7b6-50d4-956c-0dd7b7bab038 | textbox | (1) Dia:
0501baeb-8565-5e54-9ae5-d52bd9292899 | textbox | (1) Length:
666b3fa8-b819-5f27-b19b-cd755f2ba680 | textbox | (1) Material:
674f3601-a80b-5fce-b26b-f9c68f3b49d2 | textbox | (1) Class:
ea9cecd3-a175-5183-85bc-aac69ce01a0b | date | (1) Test Date:
8543a9df-a44e-589c-aab2-edcf4ec4bf59 | note | (1) Air test: Pass
1f4e6a0e-b68e-52dc-9306-9ff2b81ca170 | textbox | (2) Dia:
0418068c-6ef1-5dd3-98d9-6c56bea46611 | textbox | (2) Length:
74ed4e74-a033-5966-82a1-7ec51269a38b | textbox | (2) Material:
915de46e-6781-5ccc-9506-43e86f1ab87d | textbox | (2) Class:
c632dbf6-266a-51c4-87a8-7b23e100c221 | date | (2) Test Date:
36d71739-f1a6-5694-8d46-1500bb0e9499 | note | (2) Air test: Fail
| checkpoint-no-value | Structure (2)
3d672ac6-31d3-5124-a019-ae5878651d9a | textbox | Structure Name:
f39de27b-670f-5547-bb33-798eab59e6bc | note | Status: New
a735686e-45ce-55c6-9396-6a37194c7832 | textbox | (New) Dia:
e62af161-1f4d-50f8-89b6-8fd400fc3954 | note | (New) Type: MH
359738b8-d77f-559a-a6b6-991725ea38c0 | textbox | (New) Distance to Flexi Joint:
7efed5ea-7099-5ef5-aea8-546ec8b353be | textbox | (New) Epoxied:
e0cd3cea-a2e3-549e-81ca-0f54e1674b7b | textbox | (New) Water tight:
949a78f6-c0f5-5add-b706-f645e5478f00 | textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
31411b3f-21a9-579b-867e-cbe2ea19b80e | textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
0819d80f-26b8-5fa2-bd56-fe54d12f4902 | note | Status: Existing
a694d71d-74fc-520a-a549-891f35bb5ca3 | textbox | (Existing) Dia:
afbd538f-9709-5209-8211-2cc14c6bc990 | note | (Existing) Type: WW
3baa25e0-08fb-535a-9494-de434aa2ab2f | textbox | (Existing) Distance to Flexi Joint:
91cae105-53ff-5c26-bc3d-f246afc87cc0 | textbox | (Existing) Epoxied:
6496eeca-60ab-5b6a-b9b0-c26245dc3bb0 | textbox | (Existing) Water tight:
c3a9a485-5742-5bff-8bec-6c2eb9a556ca | textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
f8451c39-ec74-535b-b1c4-fe4a7e031ef2 | textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
| checkpoint-no-value | MATERIAL TYPES AND SOURCE
9ccca302-94f3-5b1f-add6-96e2c4562f0a | textbox | Undercut Depth:
ad17e669-e794-5994-8694-00e66926fc4b | textbox | Undercut Depth - Type:
dbc818a8-6800-5e31-b5ab-c3cb1785ce1d | textbox | Undercut Depth - Source:
11b17403-b65a-5b0c-adab-bef50cb20df8 | textbox | Bedding, Haunch & Side Zone Depth:
485ea3a8-ed41-5bbb-ae0c-31923a89c0bc | textbox | Bedding, Haunch & Side Zone Depth - Type:
874e705a-c4fe-5620-81f5-0e0f3d91bb37 | textbox | Bedding, Haunch & Side Zone Depth - Source:
5f8d0c0e-42ce-5dd2-9a4e-4b118106c045 | textbox | Backfill Depth:
e04df638-c13b-5551-b89b-e4aac47b92a2 | textbox | Backfill Depth - Type:
34bbacb1-4ce2-5943-a459-d364c1c928cb | textbox | Backfill Depth - Source:
d5bd86c8-1a04-5ee0-ba03-58a93fa7038d | textbox | Design Grade:
37bf3932-3b36-521a-95fc-27df6ca2bebb | textbox | As-Built Grade:
| section | Connections
| checkpoint-no-value | 1
fef94c28-2c61-5aaa-aaba-97f6abc69c4c | textbox | Distance (m)
8e61bbe0-d69f-5134-b3aa-f6ce486a58a2 | textbox | Dia (mm)
28456859-9178-5fee-87c7-8b393aaef0ff | textbox | Depth @ BDY
b7946066-37d2-50f1-bfe7-bd842be6ceac | textbox | House / Lot No.
5b5b0e1b-a0dc-5a1f-81a2-119ecbef0040 | textbox | Length (m)
| checkpoint-no-value | 2
407fbdd8-7875-5393-9568-494115ebb3c1 | textbox | Distance (m)
54c2b4d3-d0b9-5423-9742-39649bfb29cb | textbox | Dia (mm)
1af77ad9-b2f7-5165-8192-6498da28111d | textbox | Depth @ BDY
aeffc733-5d22-5e92-8721-1299af8cac62 | textbox | House / Lot No.
c7a24eb9-f675-5cac-9a08-bd250bffa6d6 | textbox | Length (m)
| checkpoint-no-value | 3
5efb43b8-5f76-5a6f-bc5b-4eea49aaa284 | textbox | Distance (m)
62ad3c16-c44e-564e-aaff-2ba2cbc1ea18 | textbox | Dia (mm)
8f6f9d81-9e5d-5d5f-9efd-1cae40da4ffd | textbox | Depth @ BDY
909be3b8-6086-5bd3-8246-caddc604d84d | textbox | House / Lot No.
86cc6e10-bfce-5b5d-97c8-cf0404fbdab2 | textbox | Length (m)
| checkpoint-no-value | 4
5e38d997-de84-56a7-8f1b-6f05a0f3b7c6 | textbox | Distance (m)
850dfc94-3ec4-5d92-a535-f0c718f14571 | textbox | Dia (mm)
3345f7c8-f8e8-5d80-931c-920ca2ed2798 | textbox | Depth @ BDY
9762f23a-9ba3-531a-8697-fbae9a2a0886 | textbox | House / Lot No.
bc231a32-ab7b-51fa-985b-c612aeed8762 | textbox | Length (m)
| checkpoint-no-value | 5
bcfbd2ff-6127-5b59-b640-cd8413416cea | textbox | Distance (m)
7b423c45-5ecb-5992-9664-99b03a74c7c7 | textbox | Dia (mm)
c9f7674a-6ae0-5f93-a674-0653ac7e0dca | textbox | Depth @ BDY
514b8835-621a-58a7-a093-7d857f4e46ab | textbox | House / Lot No.
401eba0d-0ca6-5425-9402-2110759c252c | textbox | Length (m)
| checkpoint-no-value | 6
a607fe27-af8f-567c-b32d-9e9d72ccb0b0 | textbox | Distance (m)
00970bc3-a1bb-5920-9fad-6255f2fe73f9 | textbox | Dia (mm)
3d13ddb0-3e5f-5115-8f40-1fe71db23bc7 | textbox | Depth @ BDY
3464e334-017a-5680-9a9f-b6072d07d803 | textbox | House / Lot No.
f24e49ef-f726-5d32-8d67-5621c6041736 | textbox | Length (m)
| checkpoint-no-value | 7
a43f27fe-5f0b-5b2e-ac65-81d32bd987df | textbox | Distance (m)
628ce4d8-e1ed-5724-bdec-3b1484c0c242 | textbox | Dia (mm)
35b924e9-fce5-56e7-8ca5-4f5edd0d2c11 | textbox | Depth @ BDY
7e78cb2c-e56a-5fc3-a4d9-da6db61581ae | textbox | House / Lot No.
718843a3-5c1c-5ef9-a1e3-c8d051eb3973 | textbox | Length (m)
| checkpoint-no-value | 8
cbbb8a1c-b844-5eeb-8b50-240eb848fdea | textbox | Distance (m)
2a490a21-99f8-5383-8f1f-00ae8b0130c0 | textbox | Dia (mm)
c1e3e874-3a84-5fc3-a8c3-dd850bbdec45 | textbox | Depth @ BDY
6273894b-312f-541d-a2c9-06405a1a8dc4 | textbox | House / Lot No.
2d0145fe-8f0d-5b49-b7f1-db12a6fb9d71 | textbox | Length (m)
| checkpoint-no-value | 9
b155c03f-d919-56cc-96b4-6537a609d852 | textbox | Distance (m)
8813e822-7a87-5c98-bffe-bf556fd72290 | textbox | Dia (mm)
260f03a9-c8de-59d2-915e-471d76a7143c | textbox | Depth @ BDY
6778e4c9-b5d9-5619-9778-74ac3920fa4c | textbox | House / Lot No.
2793ec44-4390-5ee6-b676-31b0844d4d2a | textbox | Length (m)
| checkpoint-no-value | 10
caec4def-1fc2-55e4-b32b-63fd8d12165e | textbox | Distance (m)
c5c3369b-d741-53f6-9678-11ec31f5f165 | textbox | Dia (mm)
f599eece-f9c3-5dd4-81e3-c519ffd1712c | textbox | Depth @ BDY
efbd8b87-ffd5-559e-bc90-eddabff527ad | textbox | House / Lot No.
b0490c67-819d-5801-822d-1579067693de | textbox | Length (m)
| checkpoint-no-value | 11
1fcd3798-4640-5256-a453-8293f4b4f318 | textbox | Distance (m)
b9c027b3-8fa0-5985-8d20-c7805e191b09 | textbox | Dia (mm)
8e6baf7d-3d05-5f7a-af18-b7a505ce82b3 | textbox | Depth @ BDY
f40f481d-a050-5c0e-ac5c-996056fa9b88 | textbox | House / Lot No.
df0f1178-83cb-5594-91b7-7d45e9fa8e86 | textbox | Length (m)
| checkpoint-no-value | 12
c55097ae-a4ce-52b8-baab-13af0aa585bf | textbox | Distance (m)
6d6dbed4-836f-53a3-9570-1208cc65762e | textbox | Dia (mm)
9a253afd-8ccd-5318-ba97-d48d1c77b025 | textbox | Depth @ BDY
6abbaec4-c63a-5c50-8b02-7394d8be9910 | textbox | House / Lot No.
4759782d-eed2-5fdc-bd8c-0b50e1e0c32f | textbox | Length (m)
| checkpoint-no-value | 13
8b3fc0c5-5637-5979-86eb-c6c746b96268 | textbox | Distance (m)
de0710de-3c35-5a65-ba39-0f15ed2aee54 | textbox | Dia (mm)
f87248cf-a53d-54a7-acc0-95e6ede83808 | textbox | Depth @ BDY
71623cb9-198a-5c20-a17f-0bcd7853ec04 | textbox | House / Lot No.
d9f155de-4454-50aa-b39a-4cc372c69f9a | textbox | Length (m)
| checkpoint-no-value | 14
3efa676d-c7f7-54d7-bbc9-8d0c12f389bc | textbox | Distance (m)
32e6a20d-bfc5-5e92-8e17-71083c1df8ff | textbox | Dia (mm)
77e83605-4a54-56dd-9a48-363a1907b188 | textbox | Depth @ BDY
8942c735-6994-51be-b13b-69b989a06780 | textbox | House / Lot No.
ed3e569d-3095-5687-b6cc-d4542c2d56c3 | textbox | Length (m)
| checkpoint-no-value | 15
be1cdb7b-b650-5827-9aeb-c780a33791cd | textbox | Distance (m)
7ba01e03-237a-52cf-99c1-953fca398686 | textbox | Dia (mm)
549d279b-3e1b-5801-be8a-eb823fbf0196 | textbox | Depth @ BDY
5d184b27-0dba-5fda-94f9-dfdf57afbc70 | textbox | House / Lot No.
72cff308-49d7-5f68-bbf2-b2a15ddcc99b | textbox | Length (m)
| checkpoint-no-value | 16
e02a4c4d-a1b6-5fec-ab7a-45662f52a13e | textbox | Distance (m)
8febeca3-303d-5d82-a9ed-f5e3a24eb6d7 | textbox | Dia (mm)
a6fb3fba-0e9a-58a6-8ac5-a1adc166b1ee | textbox | Depth @ BDY
19a902d8-9aea-5c85-a081-24146a9ca194 | textbox | House / Lot No.
b2aeb76d-8ef6-5e39-bb50-c2e3e6a91000 | textbox | Length (m)
| checkpoint-no-value | 17
78d4cb35-e1ee-5306-b89e-f84c337dd3d7 | textbox | Distance (m)
d07344a3-0afd-546a-aa03-53aac474d07f | textbox | Dia (mm)
dcbe3be4-08dc-5b5a-99fe-e294b8943d66 | textbox | Depth @ BDY
8c5e5b21-bfd9-5ce3-9c37-0fb85ff132ec | textbox | House / Lot No.
560a0240-c781-5779-8f16-b91d53260ccc | textbox | Length (m)
| checkpoint-no-value | 18
78939e4d-4e1d-5baf-9212-94d461e62e7a | textbox | Distance (m)
8687ae1c-d96e-5566-b52f-bb323a21c05e | textbox | Dia (mm)
16987ded-9bcf-5e17-9655-44c551225ce2 | textbox | Depth @ BDY
875ec6d1-f216-5200-a2e1-3befd7c00ada | textbox | House / Lot No.
22a5f39f-4593-5bc5-96cf-d2eb7aa83031 | textbox | Length (m)
| checkpoint-no-value | 19
321e509a-1f2d-53ce-9306-262713b85e52 | textbox | Distance (m)
b1f533c6-f95c-56a9-a826-8ac2b2555538 | textbox | Dia (mm)
18568d73-869d-558e-99d2-6525cd8ed60e | textbox | Depth @ BDY
bec10dd4-60fa-5cb2-af04-423ea5169086 | textbox | House / Lot No.
c7249236-7b97-5070-93df-9c798aa83b20 | textbox | Length (m)
| checkpoint-no-value | 20
84cc089a-abcc-5175-92de-a607a409f807 | textbox | Distance (m)
06faa542-2d20-5b97-a091-a1fab94606be | textbox | Dia (mm)
8f924f6c-eb4c-513a-afc1-ad94a77f93f6 | textbox | Depth @ BDY
d0386c88-d488-5ae4-9614-fabf7c2f31ef | textbox | House / Lot No.
c8707a23-02e9-574c-b4a1-c10055204386 | textbox | Length (m)
| checkpoint-no-value | 21
aece24f3-5238-523f-a351-c1cc99f045f9 | textbox | Distance (m)
e73d1711-fc8a-5eb5-9bbf-8e182e48b3f8 | textbox | Dia (mm)
f808d8d8-ade0-595f-93a3-7de366720608 | textbox | Depth @ BDY
e0b2ad3b-71be-5bcf-954f-6fde1a4f1278 | textbox | House / Lot No.
71c53539-8652-5107-a9d2-d58cdd8e4df9 | textbox | Length (m)
| checkpoint-no-value | 22
01d3fa1f-d5e8-5307-b44f-0d2424194f0e | textbox | Distance (m)
b72e8f26-17a9-5c3e-8878-75913fd5b2c1 | textbox | Dia (mm)
ec8ed97d-2de8-5619-8a37-33c02cf50ed0 | textbox | Depth @ BDY
342f866b-dd2e-5fd4-90b3-8d9d0b0ecdf7 | textbox | House / Lot No.
47caaaff-de33-58f9-9ead-909b16e2db85 | textbox | Length (m)
| checkpoint-no-value | 23
e8cc353c-7e6a-5b66-887d-4d9db75866d8 | textbox | Distance (m)
b083278b-5c9d-5811-9772-3f63974d1201 | textbox | Dia (mm)
d9202851-5155-5587-8bd1-2fc7f2418a4b | textbox | Depth @ BDY
fe48007a-16e0-5569-ae07-2e76d2ea84bc | textbox | House / Lot No.
c8a0b1e9-d593-52c8-a1aa-a3a1da1c570a | textbox | Length (m)
| checkpoint-no-value | 24
240c675b-038b-5c9b-85af-9bc55eb08434 | textbox | Distance (m)
99c5e649-c3e1-5992-834e-2b4abe642143 | textbox | Dia (mm)
1c03aa27-ecd5-5377-aa01-cbcdf995fe55 | textbox | Depth @ BDY
ce3617f1-5f1c-5fe2-bf20-5bcab23a14ba | textbox | House / Lot No.
2b64b0e9-1fee-5681-a481-96125413c65d | textbox | Length (m)
| checkpoint-no-value | 25
db66102c-2932-52d0-8140-6b797048c4de | textbox | Distance (m)
ac52825c-557d-54d5-adba-43519a251253 | textbox | Dia (mm)
20eb0797-5f10-59cb-8f63-cb6335a44b76 | textbox | Depth @ BDY
fc022a44-c28d-5ead-9fcc-041d7e9301b2 | textbox | House / Lot No.
3ff2902d-0a92-5f85-a3eb-b2b119186afa | textbox | Length (m)
| checkpoint-no-value | 26
d2af8b83-375a-567c-b84e-bbe17716c23e | textbox | Distance (m)
7f5cf4cc-88c3-5734-9801-37eb311afe46 | textbox | Dia (mm)
4f59b1ca-dcf7-5250-91e0-306ee3be92e7 | textbox | Depth @ BDY
f00bfe7a-cefd-5d5e-9e90-6f0bddb9bf38 | textbox | House / Lot No.
e5af7f52-57a5-56c2-9256-bccb1e51a965 | textbox | Length (m)
| checkpoint-no-value | 27
eef66dbe-3689-5a6b-8915-1eec26f1e422 | textbox | Distance (m)
f2867c90-9c25-5e2d-bed5-9929298dc5d6 | textbox | Dia (mm)
984126a6-f5a8-5e3a-a85e-7ec3db5a687d | textbox | Depth @ BDY
c349ff68-bc21-5369-a5b3-d162c38fee4f | textbox | House / Lot No.
f4822f22-cd58-5acf-abb7-2f0f3c0e5410 | textbox | Length (m)
| checkpoint-no-value | 28
4dcaced2-f1cc-573a-9ec4-aeedeb542845 | textbox | Distance (m)
2d4bab82-0b68-5321-ae61-7d3411f10057 | textbox | Dia (mm)
0be4b85c-f9a0-5c34-b2c6-5bab4f7754b9 | textbox | Depth @ BDY
3381cd49-a58a-5a72-b73d-c495625020f8 | textbox | House / Lot No.
a0de2e6b-f815-54bd-8672-0f8121516fd5 | textbox | Length (m)
| checkpoint-no-value | 29
e13ec354-d4d2-5499-b30a-b183b6b81d71 | textbox | Distance (m)
424e5f68-4ece-5403-8181-815d075a721b | textbox | Dia (mm)
46142e2e-8c69-5283-adc4-7d97626f8de1 | textbox | Depth @ BDY
0793fa0b-fb10-51a1-849e-6c3301270797 | textbox | House / Lot No.
e67ffd69-a0a6-5fa4-b599-4186870a32b5 | textbox | Length (m)
| checkpoint-no-value | 30
f9a30ebe-8150-57ff-a9fa-a0daf2ff7374 | textbox | Distance (m)
95ceeeac-e30b-5a40-a004-0e29f0f25dd6 | textbox | Dia (mm)
44f382da-1cc5-581a-ae57-7f2c2508fb95 | textbox | Depth @ BDY
03294e55-e794-5280-9219-14d3b0579cfd | textbox | House / Lot No.
9621b184-ce96-564b-a085-d161005370d7 | textbox | Length (m)
| checkpoint-no-value | 31
1510caed-32ff-595c-b45f-524c6d139bd3 | textbox | Distance (m)
9f72c562-a6f3-5c6b-9f6a-b4a9528ecf7a | textbox | Dia (mm)
b1434eed-1a3c-575d-a9b1-e6c8c19396ce | textbox | Depth @ BDY
c5c9241e-079c-5c7a-aae2-d2a9a046b9ce | textbox | House / Lot No.
9bbcb10f-1005-5846-b1f7-56af8e0c4166 | textbox | Length (m)
| checkpoint-no-value | 32
606a1e85-baa0-5cfd-8ba9-e5d5117f5f86 | textbox | Distance (m)
a0750f25-2c3d-501f-8094-5b38a39cabe8 | textbox | Dia (mm)
5aa4c599-5f8c-563b-b0c0-9fc6ae9664f2 | textbox | Depth @ BDY
fc72abcd-c531-5718-9a93-c663898c55c6 | textbox | House / Lot No.
41baebe3-f5d8-5d7f-8085-b69ff6e7a03b | textbox | Length (m)
| checklist | CS-4029 - Concrete Pump - Permit to Pump |  | CS-4029 - Concrete Pump - Permit to Pump |  | 2ad94da0-1a88-4ed5-adf0-6bcce63c5894
| checkpoint-no-value | Concrete Pump - Permit to Pump
fe638e5f-553d-5ed7-9338-905bf9dd1f8f | textbox | Project No.:
88d8c831-dd4d-53a2-ad41-6b524c0e197c | textbox | Location:
| checkpoint | Pump Operator Pre-start Checks Completed
6cda8204-4064-5c72-a9ad-d9c93a9fb16a | textbox | Initial:
d5dd19da-37d6-5e57-b943-f111aaea19cf | date | Date:
| checkpoint | Pump set up level
b1064950-fa30-51a6-a9c2-b984f57c9c08 | textbox | Initial:
4f395a0d-bf82-588c-adc4-8da186b0a24e | date | Date:
| checkpoint | Steel delivery line in good condition
ce49c8c0-bbfe-528d-829e-00ddd6ecd070 | textbox | Initial:
35dd2998-6786-505e-81f6-c08283c9e401 | date | Date:
| checkpoint | Rubber Delivery hose in good condition
6bd614f1-b369-52eb-98d7-3d2a0a52eec3 | textbox | Initial:
50f4ea99-149b-5085-885d-1d99ca2b08ed | date | Date:
| checkpoint | Delivery Line Adequately Supported
c15e40df-5474-5f74-8c8d-2789dd8903e5 | textbox | Initial:
19fd51d6-4957-558e-935e-1d551c0a0f61 | date | Date:
| checkpoint | Delivery Pipe Connections correct & Locking Pins Fitted
ab21c98a-b41f-5263-bee1-4875274c3ecc | textbox | Initial:
71605f7b-9f82-5d62-8acc-4c5721ed9be1 | date | Date:
| checkpoint | All radios are working satisfactorily and communication checks have been carried out
38c25f13-d70a-5ae1-9292-1085b48c37a3 | textbox | Initial:
90c74837-8cc7-59d5-8d2f-dfe1064057a2 | date | Date:
| checkpoint | Concreting Crew briefed on Work Instruction
46cd3090-9681-540b-96a3-f0ce9ff4002a | textbox | Initial:
b1132919-7f60-50fe-b3a8-abeb7330ab62 | date | Date:
| checkpoint | All crew have correct PPE, skin fully covered (arms and legs)
0db91b63-9ace-5240-ada2-32f7b382ed04 | textbox | Initial:
eda65675-542d-588e-9228-f3366828ceef | date | Date:
| checkpoint | Permit to Pump
a55c0917-91a8-59e6-b5dc-a263027525c0 | radio | Permit to Pump – Issued / Rejected | Issued,Rejected
70fb9f41-17e2-5e52-bd74-10dcf3b392f2 | note | Project Engineer / Construction Manager / Superintendent
1b45dcc4-4009-5337-b026-2529fe1097f2 | textbox | Name:
df638b6a-2eb6-5174-9af9-cf58d1191867 | date | Date:
| signoff | Signed:
| checkpoint | Prior to Cleaning Lines
d85ff6e0-0a60-5fc6-951a-3757d82caab1 | note | Reducer and Hose removed
| checkpoint | Permit to Clean Lines
e2763b59-5f98-500d-b199-b3da84745ba5 | radio | Permit to Clean Lines – Issued/Rejected | Issued,Rejected
89b6ac59-ed4a-544b-af5c-e9d55a258ee4 | note | Project Engineer / Construction Manager / Superintendent
8917cbda-caad-575d-908b-d80c95f91036 | textbox | Name:
6c91ff8b-d176-5b76-9317-a40845be4332 | date | Date:
| signoff | Signed:
| checklist | CS-4040 - Concrete Inspection Record |  | CS-4040 - Concrete Inspection Record |  | 1fd0b5fc-6a9f-4fe4-a5f9-1d145bdb021e
| section | Details
| checkpoint-no-value | Concrete Inspection Record
027effd2-a858-5c79-b391-70245ee53b6a | textbox | Location / Description of Pour:
c33ebd8b-3f21-5e02-9e3f-15f3f6a927ed | textbox | Drawings & Revision No. used to check off Pre Pour Inspection:
83fd61e8-2217-5007-97f4-0b105068cfec | textbox | Concrete Grade |  |  | MPa
53c84e75-f898-520a-89bf-3d39c16b40a4 | textbox | Concrete Quantity |  |  | M3
116cee17-b98d-5522-ae29-6ec1414d7853 | textbox | Pour No.:
| section | Formwork
| checkpoint | Adequately braced and supported
| checkpoint | Grout tight
| checkpoint | Correct dimensions
| checkpoint | Cleaned and oiled
| checkpoint | Formed surfaces straight
| checkpoint | Major penetrations located
| checkpoint | Embedded items located
| checkpoint | Specified surface finish:
| checkpoint | Adequate seating Pre Cast units
| checkpoint | Permit to Load Obtained
| section | Reinforcement
| checkpoint | Reinforcement Content and size
| checkpoint | Grade markings:
| checkpoint | Placement, tolerance, clearance
| checkpoint | Rigidity and cover
| checkpoint | Clean steel
| checkpoint | Lap location and lengths
| checkpoint | Starters/dowels correctly located
| section | Construction Joints
| checkpoint | Location
| checkpoint | Roughened
| checkpoint | Clean
| checkpoint | Water bar placed if specified
| section | Other
| checkpoint | Mix ordered:
c138aba5-1210-57e6-9531-6f9c4ab1e045 | textbox | Mix ordered:
| checkpoint | Independent Survey – Check off critical survey points
| checkpoint | CPS Engineer notified (48)
| section | Pre-Pour
| checkpoint | Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer
| signoff | Add Signature
| section | Wet Concrete Checks
| checkpoint | Mix delivered:
6bbcf374-65ad-5b0e-99cb-f6b026e01162 | textbox | Mix delivered:
| checkpoint | Slump/flow Target:
8004fab2-3d96-5997-8a45-51993ac164aa | textbox | Slump/flow Target:
| checkpoint | Compliance Cylinders Taken
| checkpoint | Site Cured Cylinders Taken
| checkpoint | Concrete Vibrated
| checkpoint | Mandrels drawn through all ducts to verify no leakage / disconnection
| checkpoint | Finished Level: Finished to grout check / angle fillet worked to
| checkpoint | Surface to required finish eg U2, U4
b9f0a7e8-8780-5910-8254-9634668aba3a | textbox | Surface finish achieved:
| checkpoint | Retarder applied at end of the pour
| checkpoint | Curing applied (specify type)
| checkpoint | Concrete Supply Dockets collected
40a167be-06a8-5119-a980-73d895e50ffd | textbox | Pour Start Time:
423d4eeb-62fe-52cd-84c1-adde3c24f531 | textbox | Pour Complete Time:
2e17bc70-26f5-543f-965f-5ed8fef066ef | textbox | Volume Placed:
| checkpoint-no-value | POUR ISSUES – Add as comments (e.g. formwork failure)
| section | Post Concrete Inspection
| checkpoint | Curing correctly carried out
0f526c77-d4f7-594b-9068-31ba2162602e | textbox | Concrete Strength for Striking:
df14a079-76d3-503d-93ba-1a22deb0cbf1 | textbox | Concrete Strength for backfilling:
| checkpoint | Preparation of Construction Joints Completed
| checkpoint | Blow holes, tie bar holes filled
| checkpoint | Inspection of surface/s & any authorised repairs have been completed
1af75cac-b272-55ed-9880-2c70c6a93956 | note | CPS Engineer Inspected.
| checkpoint | As-Built complete
| checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
48be283f-368f-5d16-96f4-5c611bee1fe6 | textbox | Site Engineer:
| signoff | Add Signature
| checklist | CS-4041 - Bearing Installation Record |  | CS-4041 - Bearing Installation Record |  | fecbed2a-b02a-4425-8f6b-557078546bac
| section | DETAILS
| checkpoint-no-value | DETAILS
3522ebe1-56d1-53fd-a5b5-68332f4ca392 | textbox | Project No.:
| section | Pre – Installation
| checkpoint | Abutment/Column surface level survey within tolerance
82eb8edc-e60f-572c-bf55-cc742b50aec9 | textbox | Initial:
cc27ca5e-ed64-5ad8-b682-4fc35e61afbb | date | Date:
| checkpoint | Bearing pockets cleaned and free from debris
92d33d76-47bd-55ff-b22f-b896ca807862 | textbox | Initial:
7e6fbeb9-3b9e-52d9-ba21-965bfa6896ae | date | Date:
| checkpoint | Bearing pockets in correct position
db622f87-3e4f-5843-86d9-e6bc8e25c627 | textbox | Initial:
8f7cf7a4-b7e1-5b9e-8a14-faf79d03a477 | date | Date:
| checkpoint | Abutment/Column under bearing surface roughened, cleaned and free from debris
99007476-9e61-577a-a6f4-5489791f7ade | textbox | Initial:
81bfaab9-cce4-559b-a667-b2d426208f5c | date | Date:
| checkpoint | Centre lines clearly marked on pier head
f8976f6b-7d23-5f27-b912-e5e3c7812303 | textbox | Initial:
7bab3034-39e4-5874-b1a4-d8beddf77600 | date | Date:
| checkpoint | Plastic shims positioned and levelled correctly
7747ffe0-d0cc-58df-aa8a-b214fccf29cd | textbox | Initial:
53895c3f-45d6-57a8-bfd7-aba360a1040d | date | Date:
| checkpoint | All GEWI bars firmly attached to bottom and top, plate and anchor plates fitted using RIC500A epoxy mortar
3a99b195-7962-57e9-8fc8-544e986da90e | textbox | Initial:
9f812ea6-4fab-5d3e-be64-6aed7209d63c | date | Date:
| checkpoint | Approval to lift and position Bearing Unit
c92bcc69-00a8-51ee-b9ae-0b6aaa55ec50 | textbox | Site Engineer - Name:
8e26bd09-4c23-539b-887d-f1c84719a921 | date | Site Engineer - Date:
| signoff | Sign:
| section | Post – Installation
| checkpoint | Top of bearing level checked on all corners
1e47ff08-1e92-5a27-b31c-dd9b16922ca4 | textbox | Initial:
9cc22960-6ba5-5404-a4c8-f2f1254e989e | date | Date:
| checkpoint | Bearing orientated correctly (B o/s North G,H o/s South)
000e73a0-b112-5a27-aeec-4260dfa5e4d9 | textbox | Initial:
450fbe38-b31d-536e-821d-6433f6a4cfc7 | date | Date:
| checkpoint | Surveyed centre line of bearing within tolerance
e63b8cdc-1452-5d83-a88d-4910012d1c14 | textbox | Initial:
8f474f02-088c-558a-8968-d212727457c4 | date | Date:
| checkpoint | Sufficient space for grouting under bottom plate
c576cadd-8c9a-5c26-9ac9-441bd42c04f3 | textbox | Initial:
00884d95-a49a-5152-9c0f-6d8affdf62c5 | date | Date:
| checkpoint | As built survey carried out
0bfd4a60-3faf-50b6-938c-83f73a5cc8b3 | textbox | Initial:
085cd624-033c-535d-8bd3-4fd6b67dd6a9 | date | Date:
| checkpoint | Bearing covered and pockets sealed to prevent filling with debris and water
e49e1a13-f3c4-5677-aaed-7696cb48b5a9 | textbox | Initial:
efce578c-9321-5ff2-90d4-2ffffc9c9154 | date | Date:
| checkpoint | Bearing completed & approval to commence given by Design Engineer
d70170f9-6ce1-593d-a574-dbd59ee7d03e | textbox | Site Engineer - Name:
9933c4f2-de9c-5229-be10-fef53ea90eb4 | date | Site Engineer - Date:
10641cee-bd70-5896-9efa-d989c26d809b | textbox | CPS Engineer - Name:
a57e4ece-23a3-58e8-99d1-6b2d7060a990 | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4044 - Roundabout Kerb Construction Record |  | CS-4044 - Roundabout Kerb Construction Record |  | 380ee95a-0b21-48b2-a288-3ba86d6a6a05
| section | DETAILS
| checkpoint-no-value | DETAILS
a3e0e624-9144-5edd-8963-4de2330c066b | textbox | Project No:
7cf8753f-b4fc-50cd-a870-aa793a1526d3 | textbox | Description of Pour:
e0bbbc77-96c2-5cf8-ba3a-dd14fed7ddf8 | textbox | Concrete Qty:
9ef81936-ffd3-5770-aa10-41d893aba79b | textbox | Kerb Type & Dimensions:
f0574407-7fce-5e25-85e3-bb3f0c369cfb | textbox | Concrete Grade: |  |  | Mpa
96a13ef4-7872-5fd9-a303-0641b05bc919 | textbox | Weather conditions:
f563f56b-bfe7-5f5f-b636-fd86a7d83051 | textbox | Dwg No/Rev:
| section | Formwork Mould
| checkpoint | 1. Cleaned and oiled
f75e98ea-910c-5592-ae48-52f070f9d3fe | textbox | Initials:
a99bfecd-7c4a-596a-bc47-759252a5c37e | date | Date:
| checkpoint | 2. Correct profile/dimensions for Kerb Type
a4a1bc09-638f-52f9-9703-0ffdbad53c73 | textbox | Initials:
ac758409-b5e6-535d-833a-23314bcda7cd | date | Date:
| section | Subgrade
| checkpoint | 3. Ensure subgrade construction is complete and suitable for kerb
bdd91e35-6e8a-5b03-ad9f-731e03b0dea5 | textbox | Initials:
f73979a6-431d-5d80-b4b6-6886712b9423 | date | Date:
| checkpoint | 4. Cesspit protection in place
5a5f931f-2a42-5caf-ae7b-a2e42c7bbb7b | textbox | Initials:
ba7c1924-2a44-533f-b5a5-2f72b73f55bf | date | Date:
| section | Survey set out
| checkpoint | 5. Check survey set out
7770cda7-0c09-5116-90bf-d19c1b738c2a | textbox | Initials:
6f47ef0d-c025-55ef-ab7c-74d720dd5662 | date | Date:
| checkpoint | 6. Check subcontractors string lines for machine
dbe5e7b7-6a13-52f7-9710-5f49b8bd4aee | textbox | Initials:
87f998ce-a3c2-53aa-b807-2456f56ebdd0 | date | Date:
| checkpoint | 7. Check crossfall from RAB collar to kerb lip using a tape and level every 5m before kerb is poured
782afe60-ec93-5fe6-9ef5-21366288e3e7 | textbox | Initials:
a5fc3f9a-fcc7-5e30-8078-723355e373a0 | date | Date:
| checkpoint | 8. Vertical levels correct to design +/-5mm vertical tolerance
c92ec0c6-f80a-5b76-897f-7a7dd2df633b | textbox | Initials:
3cf6d111-0861-5f6a-b125-e57702be5b61 | date | Date:
| checkpoint | 9. Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
3ea8bc5c-5acd-50bf-89c5-bbf3fadcdd38 | textbox | Initials:
2feb2fd3-d21b-5e5b-b9f2-f7f42759fd66 | date | Date:
| checkpoint | 10. Crossings / kerb transitions set out
444b8889-5c9f-5aa9-ab6e-5d3b291b623a | textbox | Initials:
8181ae9c-017b-516e-90cc-59bb540c29b9 | date | Date:
| checkpoint | 11. Engineer to mark kerb types at crossings and kerb transitions
632a49d1-bc59-519c-a802-91bbfa8ec392 | textbox | Initials:
2dca1c61-f2ae-5039-a46a-ec19e7b6bf99 | date | Date:
| checkpoint | 12. Ensure channels fall towards catchpit locations
1fbb1fbf-09fe-528c-b9fc-6c0f46624a08 | textbox | Initials:
334d6b3c-0f8b-5d30-9674-bb52ee0ab263 | date | Date:
| section | Miscellaneous
| checkpoint | 13. Construction joint roughened & clean
4f05db3d-27cb-5484-a7ea-0362eacfcdc7 | textbox | Initials:
46476752-3db9-579e-b023-9f04da1c670e | date | Date:
| checkpoint | 14. Correct mix ordered
3e5d828e-b077-58a6-9f3a-3c75a45b5f8b | textbox | Initials:
9db8ee67-7c07-56cb-905a-5bc2c3ea8b85 | date | Date:
| checkpoint | Pre-pour check – HOLD POINT
f89201e7-b5d5-5c18-a138-e51d6db09685 | textbox | Site Engineer - Name:
bc5761fe-4bec-5561-bbb3-f8f02914402a | date | Site Engineer - Date:
e6d40474-6cc4-51fc-9fe2-8051acec1e48 | textbox | Design Engineer - Name:
9e6816af-1102-5f08-9f79-1efc00e96b47 | date | Design Engineer - Date:
| signoff | Sign:
| section | Concrete Checks
| checkpoint | 15. Correct mix delivered?
46e567e2-b8d3-5a72-a665-6d7a402e16da | textbox | Initials:
0abf0a5c-1a69-527b-afa7-44018a51d749 | date | Date:
| checkpoint | 16. Correct slump (within tolerances)?
8e424592-6045-5947-ba4e-baa64971d2f0 | textbox | Initials:
175ac56a-ce99-54de-b66a-4edc2f8f7570 | date | Date:
| checkpoint | 17. Concrete Supply Dockets collected?
0ff8a5b8-0560-5573-8212-b41d38ae3570 | textbox | Initials:
c16d912d-edce-5752-81d6-470ed1e91958 | date | Date:
| checkpoint | 18. Batching Plant Records received?
47ae9a90-edab-541e-b3b9-345a921423f1 | textbox | Initials:
c1436b6b-82eb-56d9-b255-b93b35e64cbb | date | Date:
| checkpoint | 19. Kerb meters completed in m
7b983a7c-1ce5-5c0e-a2b5-d070ba94552e | textbox | Completed: |  |  | m
2696f578-25b5-53f3-bf0d-32754eac2ad7 | textbox | Initials:
e671adf5-eaf1-52fe-b140-da8dfc84b904 | date | Date:
| section | DURING CONCRETE POUR INSPECTION
| checkpoint | 20. Check height between base prep & kerb lip is consistent with #7 during kerb pouring
c37d8fad-d9d9-55ba-843d-7c4d143a80ce | textbox | Initials:
336cf160-b7cf-5dda-8073-38e018574461 | date | Date:
| checkpoint | 21. Ensure correct kerb type is being installed in the correct location(s)
b5cb407d-759c-57de-a8ac-582f06f0983c | textbox | Initials:
6603be0a-d61c-5fc5-9b8c-2abe861eb0f1 | date | Date:
| checkpoint | 22. Constantly check levels and line to ensure kerb is within design tolerances
052d89d5-3deb-5c22-8361-dae054d7704f | textbox | Initials:
971f7abe-1433-53a7-8254-4f015b91ebb9 | date | Date:
| checkpoint | 23. Ensure protruded kerb has U4 finish
c92fdf7b-09f9-5007-8072-efdb1fee99ee | textbox | Initials:
8e79136f-4f6e-580a-88e3-4b1c48f14ed4 | date | Date:
| checkpoint | 24. Ensure Expansion joints are installed
39f78d98-ce4b-5e3b-a914-89e2d2eef5fd | textbox | Initials:
0e8b3299-7f67-5d8c-9742-880e44763af7 | date | Date:
| section | CONCRETE INFILL ISLANDS
| checkpoint | 25. ENSURE F3 FINISH AND THE CONCRETE LEVEL IS NO HIGHER THAN THE TOP OF THE KERB THAT FORMS THE MEDIAN/ISLAND
cc54a625-2a01-5d23-8b50-125b26bd78ef | textbox | Initials:
e430579d-66a7-5eb2-8776-fbb4874be10d | date | Date:
| section | TIE INS TO PRE-CAST ELEMENTS
| checkpoint | 26. Aprons to be formed around pre-cast elements
b6f8dcc0-ae86-5940-98c7-c5c0be8076b5 | textbox | Initials:
7c7fb4fc-1eb2-537c-8d18-1c0779245d2d | date | Date:
df0e5d17-b73e-578d-b100-dc276f672c13 | textbox | Pour Start Time:
b3303a93-bc78-545f-8ad4-7e3ec5ccf8de | textbox | Pour Complete Time:
a0a6673b-afff-55c3-bf16-5e072814f8aa | textbox | Volume Placed:
| section | PROTECTION
| checkpoint | 27. Warning tape to be placed over kerb to prevent any damage
7eb59469-4ed9-5fe5-8c27-f86c86ae03e3 | textbox | Initials:
027a6823-6c64-573a-bb1c-ac9b96c49928 | date | Date:
| checkpoint | 28. Backfilling to commence after 72 hours curing time
fdbcc662-b98e-5a28-80f2-c931ff58d479 | textbox | Initials:
890e09ba-495a-5d5a-bd51-f36b94cb50b2 | date | Date:
| section | POST CONCRETE INSPECTION
| checkpoint | 29. Complete #7 again after pouring using actual kerb lip
ada06e78-fbb7-5e9c-ae0b-25496a126c99 | textbox | Initials:
2d6ec250-ed4c-543b-9bc9-e1aeac50291b | date | Date:
| checkpoint | 30. Surface Finish and levels acceptable
8110263e-553e-56cb-84e4-e89671b517dc | textbox | Initials:
c9449c20-42de-589a-9bd3-de3e2ff0613f | date | Date:
| checkpoint | 31. Expansion joints satisfactorily completed
0cf1471d-cba7-586b-8b2e-8caf964d07c4 | textbox | Initials:
aaa2696c-dde2-570f-bceb-139a07d53916 | date | Date:
| checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
ca151c57-19d0-50d8-829a-0bd558434d98 | textbox | Site Engineer - Name:
f9a8c429-4c8b-509e-8740-04a2839750ad | date | Site Engineer - Date:
786fa4a9-966f-5550-9a41-7da261c92634 | textbox | Design Engineer - Name:
02889a0f-7342-5489-b78d-feb035bbb2fb | date | Design Engineer - Date:
| signoff | Sign:
| checklist | CS-4045 - Kerb Construction Record |  | CS-4045 - Kerb Construction Record |  | 7deac9fd-64b1-46eb-a5c3-ab7879415e04
| section | Kerb Construction Record
| checkpoint-no-value | Kerb Construction Record
48819678-62e1-5931-af1d-2b9f0ee668dc | textbox | Description of Pour:
340deec4-0ef5-54f1-abb0-5d7775cc2c4a | textbox | Kerb Type & Dimensions:
c9ed0682-470c-58f4-bc15-5d8e21c080aa | textbox | Weather conditions:
245c0321-1056-5bf6-a8c8-a919dc53f58b | textbox | Concrete Qty:
89bca87c-6020-5a4c-b791-f368aba23f1b | textbox | Concrete Grade: |  |  | MPa
6509c059-63bf-5798-85b3-2fb4afcd0ba0 | textbox | Dwg No/Rev:
| section | Formwork Mould
| checkpoint | Cleaned and oiled
| checkpoint | Correct profile/dimensions for Kerb Type
| section | Subgrade
| checkpoint | Ensure subgrade construction is complete and suitable for kerb
| checkpoint | Cesspit protection in place
| section | Survey Set Out
| checkpoint | Check survey set out
| checkpoint | Check subcontractors string lines for machine
| checkpoint | Vertical levels correct to design +/-5mm vertical tolerance
| checkpoint | Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
| checkpoint | Crossings / kerb transitions set out
| checkpoint | Engineer to mark kerb types at crossings and kerb transitions
| checkpoint | Ensure channels fall towards catchpit locations
| section | Miscellaneous
| checkpoint | Construction joint roughened & clean
| checkpoint | Correct mix ordered
| section | Pre-pour check – HOLD POINT
| checkpoint | Site Engineer
0cd42c3f-8850-50e5-af17-aa6801802188 | textbox | Name:
| signoff | Add Signature
| checkpoint | Design Engineer
0aa45f11-4d6a-593f-9cba-e117f9107a08 | textbox | Name:
| signoff | Add Signature
| section | Concrete Checks
| checkpoint | Correct mix delivered?
| checkpoint | Correct slump (within tolerances)?
| checkpoint | Concrete Supply Dockets collected?
| checkpoint | Batching Plant Records received?
| checkpoint | Kerb meters completed in m
d2e8ca99-50d2-5045-b0a2-0f2475c86208 | textbox | Kerb meters: |  |  | m
| section | During Concrete Pour Inspection
| checkpoint | Ensure correct kerb type is being installed in the correct location(s)
| checkpoint | Constantly check levels and line to ensure kerb is within design tolerances
| checkpoint | Ensure protruded kerb has U4 finish
| checkpoint | Ensure Expansion joints are installed
| section | Concrete Infill Islands
| checkpoint | Ensure F3 finish and the concrete level is no higher than the top of the kerb that forms the median/island
| section | Tie ins to pre-cast elements
| checkpoint | Aprons to be formed around pre-cast elements
| section | Pour Time
| checkpoint-no-value | Pour Time
c9d6abc2-bfe4-5c48-8149-9530e23678e5 | textbox | Pour Start Time:
e3aedb11-14a1-5092-8621-03020773c53f | textbox | Pour Complete Time:
170e2298-a653-5aa4-a1a3-945342b7e846 | textbox | Volume Placed:
| section | Protection
| checkpoint | Warning tape to be placed over kerb to prevent any damage
| checkpoint | Backfilling to commence after 72 hours curing time
| section | Post Concrete Inspection
| checkpoint | Surface Finish and levels acceptable
| checkpoint | Expansion joints satisfactorily completed
| checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
| checkpoint | Site Engineer
135d8bbe-a64e-5ce3-aa0b-c2748d26108e | textbox | Name:
| signoff | Add Signature
| checkpoint | Design Engineer
98b276f4-bf10-59c9-9546-542b8b92db5f | textbox | Name:
| signoff | Add Signature
| checkpoint | Ensure surface varies no more than 5mm when checked with a 3m straight edge
| checklist | CS-4046 - Barrier Concrete Inspection Record |  | CS-4046 - Barrier Concrete Inspection Record |  | 6bfe4412-9af3-43c5-9617-dbddfe4fccff
| section | DETAILS
| checkpoint-no-value | DETAILS
c9eb58f6-09ed-575b-8b8a-bb32649326c5 | textbox | Project No.
af19922f-8020-563f-b27c-24dbd33527bf | textbox | Location / Description of Pour:
85e4a529-45c7-553b-86cd-7851bcf99b57 | textbox | Concrete Grade |  |  | Mpa
e216dbcd-ffec-548c-8f45-e11c484be7d3 | textbox | Drawings & Revision No. used to check off Pre Pour Inspection:
9aef8932-5951-5d27-9d30-a3bc84e183f3 | textbox | Pour No.
| section | Formwork Mould
| checkpoint | Cleaned and oiled
655f421a-284f-596b-bd8a-73c8de0a187f | textbox | Initials:
50bf4bd9-871f-5763-bd1e-9f0ae09416bd | date | Date:
| checkpoint | Correct profile/ dimensions for Barrier
3ae7e5d4-7360-5ebb-871d-d45c64c384e9 | textbox | Initials:
22441ae0-c494-5d1f-8f53-43e4fe91fef4 | date | Date:
| checkpoint | Check set out – 350mm from face of Barrier
5087338d-7ab2-5468-8982-d86a53089cc3 | textbox | Initials:
d985f0c1-38a9-5302-8150-d3a4228a6c5f | date | Date:
| checkpoint | Embedded items in correct location
a1802f54-9188-584a-b90f-bc67ce7763ea | textbox | Initials:
1801eaa7-41a4-558d-9da3-7e87a6c54f30 | date | Date:
| checkpoint | Horizontal and vertical alignment correct to design
4d32bcfc-1084-5237-93c6-ec9299a7e68d | textbox | Initials:
4fb86390-5a87-59cd-a89e-4cfec0067666 | date | Date:
| checkpoint | Stop-end coated with Rugasol MH Extra, installed and braced
be9ae44d-2f38-5134-a3a6-8538e624b61e | textbox | Initials:
6785babb-0278-5cdf-9753-2f5c2acb5be1 | date | Date:
| checkpoint | Grout tight
a95d526e-b995-5975-bbd8-90e19871a810 | textbox | Initials:
57d3e59a-a6e5-542b-938c-c2f5da350271 | date | Date:
| checkpoint | Voids set out
7c310d0d-3318-56d9-bd73-c3343a1e15b4 | textbox | Initials:
fab271de-c284-5187-aa95-1cfa613a49e9 | date | Date:
| section | Reinforcement/ Strains
| checkpoint | Strains/ reinforcement content correct
12481998-8f99-50f0-9cbf-1cb01482765d | textbox | Initials:
e569a826-cc35-56d2-9a61-53c4fd88090c | date | Date:
| checkpoint | Correct grade markings
567d19b3-03f9-5046-8d6f-859f22953c00 | textbox | Initials:
a78780ff-48b9-5a2d-9f3d-4694d2cef910 | date | Date:
| checkpoint | Correct cover
6e7485ce-835d-537a-88c4-09da23aa198a | textbox | Initials:
085ac872-f799-57bd-aeb9-5fc68a54daf2 | date | Date:
| checkpoint | Lap location and lengths
8930a171-5165-5efc-a386-758807b6f0ba | textbox | Initials:
28b5505c-10a7-5ee5-9d6f-1f095d302c7f | date | Date:
| checkpoint | Strains placed in correct location
0aa44172-9417-5324-a055-e5755929fab7 | textbox | Initials:
39bb39b5-f8d1-5974-a97f-b147940f0f56 | date | Date:
| section | Subbase/Basecourse
| checkpoint | Suitable for Barrier
f4fb688e-6aef-516d-a200-50041234cb63 | textbox | Initials:
39430cff-1f33-5f2d-8301-aced9c9c292b | date | Date:
| checkpoint | Cesspit protection in place
8f2c782e-2cdd-5220-b5e5-04178c0ceb91 | textbox | Initials:
ed86cc0f-ee86-5b50-b37c-4b52ea332e9c | date | Date:
| section | Other
| checkpoint | Correct mix ordered
4f823ff4-5641-5574-8eca-a0553ade81da | textbox | Initials:
08c5327f-fa25-5856-9eba-2a87c1f5cd3c | date | Date:
| checkpoint | Construction joint roughened & clean
941e2610-92c4-53ca-bbb1-19b53d39da85 | textbox | Initials:
4f46056d-3625-5a60-a2c0-2ba9222fcaa7 | date | Date:
| checkpoint | Road Light/ BG 800 openings secured
d843d181-be8e-5f6a-b2f5-de5da81d8b41 | textbox | Initials:
f7d91d6a-48a6-5d61-a500-2938aa0e672e | date | Date:
| checkpoint | Independent Survey – Check off critical survey points
2ebd8bdf-bfb9-5786-a26a-d68616b83428 | textbox | Initials:
c42d4df2-55c4-59e0-a2fe-88db5e5a9098 | date | Date:
| checkpoint | CPS Engineer Notified
4970719c-4de7-512a-a9ac-63610d9c599f | textbox | Initials:
11bfb706-3a36-5997-a4dd-e998a27ae005 | date | Date:
| checkpoint | Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer & Engineer’s Rep to sign
6c698196-5442-5974-a458-f9dcfdbc4b1f | textbox | Site Engineer - Name:
95a7192e-adc1-5d9d-a52b-f0ec7fcd5072 | date | Site Engineer - Date:
6405eb40-d6a8-53cf-8bc9-d6cd39c4f097 | textbox | CPS Engineer - Name:
98cdc575-324c-5a7e-bdc2-5129c37aa09e | date | CPS Engineer - Date:
| signoff | Sign:
| section | Wet Concrete Checks
| checkpoint | Correct mix delivered
d2c17977-44d1-5051-9b4f-b7fc1d5c89ed | textbox | Initials:
09b1253e-95f2-5939-aa98-1c34c963483c | date | Date:
| checkpoint | Slump/flow Target
c2ee1396-0452-51f4-98e0-4f499d07944f | textbox | Initials:
9db1fcf2-f0f2-5a5b-9c86-399aaa63a451 | date | Date:
| checkpoint | Compliance Cylinders Taken
472ef426-6327-52be-83ce-e862928a40c6 | textbox | Initials:
9b048229-6c90-58f2-b0ed-891b43340762 | date | Date:
| checkpoint | Site Cured Cylinders Taken
1afae564-7931-53fb-975f-4c84eb851cf5 | textbox | Initials:
cdf5dcc8-e598-5108-89a6-594b80a43374 | date | Date:
| checkpoint | Concrete Vibrated
6b5e57c4-4acf-520d-81df-8a152ce78db4 | textbox | Initials:
851c34c3-23f3-5bc5-8fad-4bd2554cceda | date | Date:
| checkpoint | Finished Level: Finished to grout check / angle fillet worked to
4d0d9656-fd51-5843-96de-426a435482c9 | textbox | Initials:
f0f8c3b7-4397-5a96-a7e5-883b77e95035 | date | Date:
| checkpoint | Surface to required finish
cd50f76d-7f94-523a-9dce-1a134384d772 | textbox | Initials:
a483ac03-4695-51ef-8b02-5154bcc1a0d6 | date | Date:
| checkpoint | Curing applied (specify type)
c2b79bd8-9b12-5e87-9c6d-0b9d41e34d21 | textbox | Initials:
05594515-1ad9-5016-98c2-6bfc730448a9 | date | Date:
| checkpoint | Concrete Supply Dockets collected
9740d0a2-5d0c-54ea-a70e-41738ce516fb | textbox | Initials:
23a571f2-5f7f-5840-8d2e-821330d15518 | date | Date:
e06f3004-0a58-5cf9-8d2b-cdd6c06b6239 | textbox | Pour Start Time:
55c5eeca-55e9-5662-bfdc-94cff20d9afa | textbox | Pour Complete Time:
45311d0c-92f5-53cc-a29a-6bc7cb04dd62 | textbox | Volume Placed:
| section | Post Concrete Inspection
| checkpoint | Surface Finish F4 or F3
1b6b49eb-c0d3-50b7-b9b2-fb5639af9087 | radio | (select one) | F4,F3
afaf5b1a-98da-5f5e-a5aa-2119e1b943de | textbox | Initials:
6ce6a6ea-9922-5df7-a61f-c8687a974894 | date | Date:
| checkpoint | Curing correctly carried out following application of water
6518d774-5430-5fd7-8690-6e303fe69e96 | textbox | Initials:
3fe870a7-5518-54a8-bb2b-e78020def9f2 | date | Date:
| checkpoint | Barrier saw cut within 24h
dff6e4ae-4915-5d96-a700-ffc3dc2b0f8c | textbox | Initials:
bd1686f3-fa83-55a8-ad75-adbc38d7f35d | date | Date:
| checkpoint | Preparation of Construction Joints Completed
054b45a9-6d8f-5cb2-9bd7-6db2badc050e | textbox | Initials:
9706a43f-4700-5bfc-9ab2-2a2edc5c193d | date | Date:
| checkpoint | Blow holes, tie bar holes filled
1fa4b99d-3d4c-5314-b163-bcafbc81ef27 | textbox | Initials:
7b4e8909-253d-5ed1-b98e-869539dd9a86 | date | Date:
| checkpoint | Inspection of surface/s & any authorised repairs have been completed
381ccf74-f1f1-5608-a457-563bed0ed1b3 | note | CPS Engineer Inspected.
91634fde-e2ea-58f9-9f73-1e91904c1f1b | textbox | Initials:
6a689345-4618-579f-b014-5055ae5a48a7 | date | Date:
| checkpoint | As-Built complete
d1ba7074-10ec-5c92-8f41-0f85d67d31e3 | textbox | Initials:
83cce45c-96ad-5fcf-a651-d59d90f2ec99 | date | Date:
| checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
78237217-25e7-592f-b686-04ebefa29dcc | textbox | Site Engineer - Name:
b0e4ae50-a632-5b64-90e7-652aff2e02bc | date | Site Engineer - Date:
e6301536-a92d-5a84-8f2b-226856de4d32 | textbox | CPS Engineer - Name:
37ce3fc8-fb2a-546b-acac-e6797910a364 | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4047 - Traffic Sign Installation Record |  | CS-4047 - Traffic Sign Installation Record |  | a966ce17-2434-48d2-9e00-e681d1c67c75
| section | DETAILS
| checkpoint-no-value | DETAILS
a16ef052-1989-556e-9d76-3b8f865326df | textbox | Project No.
7cd59a5e-e555-57d0-815c-a2762db218cb | textbox | Drawing No:
8fa6afc8-57cf-59aa-b5f1-ac7677e7a36e | textbox | Sign No:
| section | Installing Sign(s)
| checkpoint | Ensure the posts are the correct length to ensure the sign will be installed at the correct height
327b18c2-20ba-5bbb-814e-897ac56fe88f | textbox | Initials:
1e3543ac-c5bb-5d98-97f0-5d78511d3e2a | date | Date:
5c8441bf-3fb4-5a57-a730-42688da95442 | note | Comments: Minimum mounting height 2m from the underside of the sign(s) and the adjacent road pavement, trafficable shoulder or top of kerb whichever the critical dimension shall be. The exception is for exit signs where the minimum mounting height is 1.2m.
| checkpoint | Ensure posts are connected to foundations with correct fixing bolts/brackets and are fixed securely to ensure the posts are firmly installed in the vertical position
cb0e20df-3ef2-5f8d-a5de-ff8136be08d2 | textbox | Initials:
b0b8296b-dbc7-5aa3-9600-4b4f0b951a72 | date | Date:
| checkpoint | Once posts have been installed check they are plumb and to the correct spacing apart at the location of the sign
55ea0157-0c89-58b6-b88e-88b3bd34db92 | textbox | Initials:
117fe1ef-3419-581a-b18a-d7f793094407 | date | Date:
| checkpoint | Check the sign before installation and ensure the sign is exactly as per the shop drawing
f2a00f42-5c13-5e57-9d0c-c8fe0280f010 | textbox | Initials:
1179106f-c6d7-549a-af01-7d944b22ca88 | date | Date:
| checkpoint | Inspect the sign and make a note of any damage
4f7f1c94-b1bc-56a2-bd31-de127476b7c0 | textbox | Initials:
621a5f03-cefd-53a3-a36a-742f2d6b733a | date | Date:
2460a507-3c63-5c32-9bfd-9113d9288c45 | textbox | Comments: Record any damage:
| checkpoint | Ensure graffiti guard or dew guard is present on the sign
0ebd5cd2-64d5-5b09-9d1f-6f5c72b54aae | textbox | Initials:
9f5ef4d9-d8ae-58fa-8cb8-87f931a68bf4 | date | Date:
6a771fef-794c-5206-a05b-04134d6e1d9e | note | Comments: Graffiti Guard on Sign, Dew Guard on Sign
| checkpoint | Clean the sign (if required) as directed by the manufacturer
d825234b-915e-5bce-a432-8b748da39ff8 | textbox | Initials:
b2b856fd-5d08-5a62-9cc7-f734c7a31624 | date | Date:
cdf3e9db-2ddd-5b21-be76-ce2f58da615a | note | Comments: Signs shall be cleaned in a manner and frequency that maintains visibility of the sign at all times
| checkpoint | Ensure signs are connected to posts with correct fixing bolts/brackets and are fixed securely to ensure the sign is firmly installed in the vertical position
e509095b-1642-5128-8ba7-17790ee337b7 | textbox | Initials:
828dc56d-7985-5598-b925-a103c7280e95 | date | Date:
d93efb26-8f3a-5f3d-a6fb-f15d3e9c8e4b | note | Comments: Do not fix signs to posts by bolting through the sign unless approved otherwise by the CPS Engineer
| checkpoint | Overhead mounted signs - Ensure horizontal and vertical axis are checked
bd1c5426-d441-558a-adf8-990461515035 | textbox | Initials:
0700915f-5aa0-5adc-9506-4ea0f7018b5f | date | Date:
edc9df7f-b4a6-5e01-bc18-d755fe920c25 | note | Comments: Where the road gradient approaching the sign is =2.0% or greater, position the sign so the vertical axis is parallel to a plumb line and the horizontal axis is at right angles to the road.
7036ba5d-0cae-5d4e-91d6-39f06b4da907 | note | ○ Where the road gradient approaching the sign is =2.0% or less the sign shall be positioned so its horizontal axis is at right angles to the road, and the vertical axis of the sign is inclined to face upward at a rate of 3mm per 300mm of vertical sign surface for each 1% the road gradient differs from +2%.
| checkpoint | For sign installation follow the Work Instruction and ensure Lifting and Working at Height permits are in place
8752b158-bfe9-5c18-a2c5-9c3dbed8eb32 | textbox | Initials:
23fed698-0047-573c-92b3-78671543b7bf | date | Date:
| checkpoint | Measure the mounting height after the sign is installed to ensure it complies with MOTSAM Part 3, Section 1.18.2c) for Ground mounted signs or Section 1.18.3c) for overhead signs
04959ec8-c7e9-54c2-a75a-b3e982be01b2 | textbox | Initials:
5dc23c28-3477-5ca8-b184-26efce707da9 | date | Date:
0078b90c-b38e-5f47-abf5-d4c0329d80f8 | textbox | Comments: Mounting Height =
| checkpoint | Ensure the sign is installed above the hinge where hinges are required (Breakaway signs)
34a6c232-1818-5c20-abb5-f8e6c07f4c1c | textbox | Initials:
6523fab8-f789-51e7-938f-994fc3957191 | date | Date:
| checkpoint | Undertake a ‘drive by’ with CPS Engineer and ensure the sign(s) are orientated correctly and sign off below
911be62b-81bb-54ea-94ed-d15b60a56708 | textbox | Initials:
ba4e2584-774e-5f3a-bf78-b9d47daebbaa | date | Date:
16b0d412-33c5-52aa-a9c5-631283f3a20d | note | Comments: Ensure signs are directing traffic the right way and are visible.
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
0af85ce2-66b6-51da-b3bb-f00deac49b21 | note | Position: Site Engineer
e2006f49-7c42-57f5-983b-2f7a1f5f0f2d | textbox | Site Engineer - Name:
6dcc70d5-8745-5e56-8dc3-28c1c3f248c8 | date | Site Engineer - Date:
d16708c9-309e-521c-95e9-6f3310f988db | note | Position: CPS Engineer
6bf1a409-6dc7-5c18-b931-ddb7a949695f | textbox | CPS Engineer - Name:
df5e066f-616f-59b4-97d5-1c61f5f023cc | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4048 - ITS Duct Installation |  | CS-4048 - ITS Duct Installation |  | 1a549985-5f6b-44a3-b235-636801545d8e
| section | DETAILS
| checkpoint-no-value | DETAILS
15db25fc-f486-5a1b-be5f-252ba200a3de | textbox | Project No.
90b69b3e-a30d-5410-bf5f-379fce618869 | textbox | Drawing No (& Rev No):
32ef01b7-4eb8-5e3d-a2ca-1cdd774d1a69 | textbox | CH Start:
09f9f6c8-ab29-51f8-b308-58044e4533c5 | textbox | CH Finish:
| section | Inspection
| checkpoint | Pull Pit/ intermediate line points set out by surveyor
218a05a3-bd5c-5fb1-b51e-ab0f58fb22fc | textbox | Initials:
4398a1e4-c066-59ae-8ec0-2b58c77ba286 | date | Date:
09cecd25-b153-5e5d-9235-bbde036735f0 | note | Comments: Survey Receipt
| checkpoint | All existing services exposed and identified before trenching
fad993ec-4602-5381-8a6c-d1beb2264903 | textbox | Initials:
513a5ca2-8c02-5c2b-ae34-f971606e7fe1 | date | Date:
| checkpoint | Trench must be made safe before any person may enter the trench
3b8241ba-4a56-51bd-9d0c-eb293f36c4e9 | textbox | Initials:
34090621-1a15-5031-be92-727d9e51a8b8 | date | Date:
5ded4b57-dbb3-5948-9d51-a970bd3d6462 | note | Comments: Trench depth > 1.5m must be shored or battered.
| checkpoint | Base of trench is clean and inspected by engineer
203abf17-aa66-5da0-9680-4f9d4e40b65c | textbox | Initials:
de5d27c4-b4b4-5b51-92f9-0cbcc498a7eb | date | Date:
c057ce96-e6c8-51ba-a069-4ee38bd900b1 | note | Comments: Base to be as flat as possible
| checkpoint | Bedding material to be placed in layers 100mm thick
276e6d70-8022-57dd-b3da-a338f5e67bbe | textbox | Initials:
6958769d-31fc-5bab-8046-0744f339804e | date | Date:
bc1d36d3-f89c-583e-b457-0fba5a39e1a9 | note | Comments: Lab test 85% of MDD (CIV=8) or 95% of MDD under carriageway, Frequency 1/20m
| checkpoint | Glue ducts together and lower carefully into trench.
a7bf8176-7647-5594-b314-8bbd03e09f14 | textbox | Initials:
1cf3568d-d7be-5303-a90c-d68d9e5e4466 | date | Date:
1d537949-4943-5ffa-be5b-241583171b8e | note | Comments: All open ends shall be taped up to prevent material entering
| checkpoint | Guide wire installed in ducts before lowered into the trench
fe742993-b284-5c30-8ac5-97ab3ab9bfb0 | textbox | Initials:
79faf838-587f-55d8-a0a9-b8577e54e988 | date | Date:
| checkpoint | As built survey every 20m
f9df219b-183f-5825-832f-951c3f2be94d | textbox | Initials:
d33e2346-e0bc-508d-b375-3a08708ef3a9 | date | Date:
c5f6b3ec-0706-5f4d-8b33-419a09cca933 | note | Comments: Must pick up all changes in direction
| checkpoint | Ensure 50mm gap between ducts sitting in the base of trench
55c552d5-f976-5bb2-aeb8-67eeaccf6f23 | textbox | Initials:
1e90c513-2af2-5be7-83b0-dd283544c181 | date | Date:
3347cd57-3014-54f3-aa04-20cbbbbe9ec1 | note | Comments: Check gaps before backfilling
| checkpoint | Ensure backfill material is suitable and un-contaminated. Compacted and tested in 200mm lifts
fe7a8fd8-708d-500c-a285-bc85973d6697 | textbox | Initials:
025252b5-bbe2-5f9a-a03f-c9e5821ba28a | date | Date:
db9d65e6-b3c0-518b-ba1f-9d7633fcd692 | note | Comments: Footpath/Berm - Backfill with excavated material. CIV 8 required.
f098bc85-1c72-5323-a959-a4192686d44b | note | ○ Carriageway – Hardfill (GAP65) 95% of MDD
| checkpoint | Warning Tape to be installed 200mm above the top ducts
b660a1ce-ce0c-5aff-b324-f1d5f6aa68d7 | textbox | Initials:
36bb7bf3-da50-5b93-8876-3a45066a0d2c | date | Date:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
8227cd1c-602f-5d40-b5fd-3bff248f1060 | textbox | Name:
c2f86c36-e59e-5595-9845-6b649febe134 | textbox | Position:
d367a5de-c8f3-5861-918f-6846efe35d0b | date | Date:
| signoff | Sign:
| checkpoint-no-value | Trench Cross Section
006a33ba-3de5-5da9-bb61-51be0d0b26fb | textbox | H |  |  | (m)
91b98746-5041-57cb-b55f-7eceab5588ee | textbox | L |  |  | (m)
c49b045f-fd9a-598b-a088-421d48c84fb0 | textbox | Backfill: Warning Tape 200mm above top of duct
a96ada8e-eab7-5f00-8e45-77baa3ee2b98 | textbox | Backfill Material Type & Source
7b6266d9-0808-5717-9e41-5c2dfff7c7fe | textbox | Bedding layer Material Type & Source
| checklist | CS-4052 - Landscaping Planting Checksheet |  | CS-4052 - Landscaping Planting Checksheet |  | cf9f940b-1d98-4587-91b9-f685ada0ffef
| section | Details
| checkpoint-no-value | Details
5d3b6c64-7aa1-5753-8ba0-066dce3bf1d6 | textbox | Work Area:
4585a45a-904e-5b40-9bb0-ddd2ed60b642 | textbox | Sub Work Area:
92f02194-704c-515d-b42f-859c7e8c92fb | textbox | Lot:
0154f83d-a973-566a-8de2-a340d5d1b6ad | textbox | Sub-lot:
c76e9b58-5c42-52ca-b6d3-3919db89b83a | date | Document Date:
9523e0a0-3e38-538b-b744-9888f3cdda8f | textbox | Created By:
96eaf698-b7c0-5e07-84fe-30cd1b7e21f0 | textbox | Drawing Number/s & Revision:
8daa6c03-b5ab-56e4-8038-4feebba679dd | note | Raingarden (RG), Garden Bed (GB), ), Tree pit (TP), number:
c0194094-a377-519d-a164-8008df72ed55 | textbox | RG #:
bbc8f254-bd06-5da5-b54d-39cdf1b4fa9b | textbox | GB #:
077e2356-7658-54d8-bccd-7842885f695b | textbox | TP #:
| section | Spec./Site Preparation for Seeding or Planting
| checkpoint | 8321/8332/Any other site works that will cause rework to landscaping & planting has been completed.
a70587e9-4743-5ae9-913c-c3c99036cc41 | textbox | Initials:
ebc59b18-19d8-5be3-b0bc-7857d8573c45 | date | Date:
| checkpoint | 8321/Check for service in the area of this work. Avoid interference or damage to them
9d410fd5-b2bd-54ad-b9ab-23ddf56d5671 | textbox | Initials:
d477f772-e3c9-514a-8551-4be4797bf665 | date | Date:
| checkpoint | 8321/ HOLD POINT. Garden bed to be approved by Landscape Architect prior to installation of soil media. Strata Vault installation to align with manufacturers recommendations. Photographs to be provided.
1b682279-3f91-5c05-948c-f42470a27fd0 | textbox | Initials:
7691ffc1-3864-5405-abf4-ddaf9090b3d7 | date | Date:
bbda3e7b-00a9-5ed6-a21b-133e3a8c1794 | note | Comments: Date/Signature Landscape Architect
| signoff | HOLD POINT
| checkpoint | HOLD POINT. Raingarden drainage layers to be approved by Landscape Architect. Photographs to be provided.
5def7448-6a08-5f50-8caa-1dea7e9cf95f | textbox | Initials:
05672ea6-5dbd-513a-8444-e3e6548053cb | date | Date:
ff6112a7-bfd9-54e1-ab3c-e3b6622742bd | note | Comments: Date/Signature Landscape Architect
| signoff | HOLD POINT
| checkpoint | Raingardens - hydraulic conductivity to be tested to prove this is in line with raingarden material specification.
83ac54b1-7c9f-5418-a31e-1c8ddb1c6663 | textbox | Initials:
ffefd189-b2e2-589d-9c1f-a16e23f10e5c | date | Date:
| checkpoint | Soil to be adequately compacted in 200-300mm layers to ensure no pockets of air within garden bed / tree pit.
6ab1ce43-6872-5330-ac16-af78429ba24a | textbox | Initials:
03f6e643-91e2-5bf7-bc37-3965600325a1 | date | Date:
| checkpoint | HOLD POINT. Garden bed profile to be approved by Landscape Architect and Stormwater Engineer post soil media install. Photographs to be provided.
9cee2fac-c22b-5a3b-85f2-d47a52207eba | textbox | Initials:
1cef82e0-459f-545e-b1a3-2d38cce240e6 | date | Date:
1dedfb95-c8c0-5dc7-8b17-4b5757af0ce8 | note | Comments: Date/Signature Landscape Architect
| signoff | HOLD POINT
| checkpoint | Should the soil in the garden bed become compromised (by ongoing site works or any other concern) – pH to be tested to prove this is still in line with the soil product specification.
37552d2a-6c0c-541f-b8a6-e1c434f167b1 | textbox | Initials:
cea409b3-57a8-5af9-9844-07a75472bf08 | date | Date:
| section | Spec./Planting
| checkpoint | Ensure no standing water at base of tree pits – report to Engineer.
775fbd63-ac78-54dd-87f6-174842bc5bb3 | textbox | Initials:
da63897d-ff18-5b4d-9a15-29a7af4acac3 | date | Date:
| checkpoint | 8332/Plant material origin checked on delivery for plant material quality and accepted. All plants to be inspected and approved by Landscaping Architect prior to installation.
f93331ab-ff05-5950-a909-bdc0fdfe730e | textbox | Initials:
5940adf5-e95d-5c09-958e-563fc6aa98b1 | date | Date:
c8b4141e-0a85-5eb0-95cf-48d7b5cabb53 | note | Comments: Date/Signature Landscape Architect
| signoff | SIGNATURE
| checkpoint | All trees to be inspected and approved by Landscape Architect prior to delivery on site. 6 monthly photographs to be provided.
e8b1ea9c-2081-5eae-94b4-3ec77e171978 | textbox | Initials:
d1ee6294-171e-5dcf-ac4f-1206f6cbb908 | date | Date:
85f6cada-29ef-5cd9-81bf-3a559e5ad32a | note | Comments: Date/Signature Landscape Architect
| signoff | SIGNATURE
| checkpoint | 8332/Plant material suitability. Roots eased where root bound. Plants not removed from container too far in advance (avoid drying out).Root balls are moist (not dry).
4e7e2cbe-7783-5c98-8947-141719a94ffe | textbox | Initials:
4566c9b6-cc8b-5221-b199-84e70b647a20 | date | Date:
| checkpoint | 8332/Spacing and set out in accordance with Landscaping plans and consistent & correct to specification and schedule. Tree species according to drawings. Approved by Landscaping Architect. Specific placement and orientation of trees to be confirmed with Landscape Architect on site – including any required pruning.
44b8080c-39a1-5841-b85d-a98c3236e8ee | textbox | Initials:
f3d31eaf-3390-57ab-8013-65915c2a832b | date | Date:
a3b6a811-4ddd-5f81-9a59-3805e582e804 | note | Comments: Date/Signature Landscape Architect
| signoff | HOLD POINT
| checkpoint | 8332/Fertiliser/ Crystal Rain Gel incorporated to manufacturers specification
c5a45beb-5121-5828-91d0-86217f8bc50f | textbox | Initials:
8b165713-9d2e-52aa-9fcc-dd7b93a2f669 | date | Date:
| checkpoint | 8332/All plants shall be thoroughly watered a few hours prior to planting and again immediately after planting.
e8d6daa6-70fc-56d3-b911-f66d0e3ac695 | textbox | Initials:
9d93b73a-51a9-5e2f-9b65-0d5164c12a08 | date | Date:
| checkpoint | 8332/Mulch clear of plant stem, Soil not left on top or mixed with bark mulch.
514d88d8-8520-5e6a-bf18-2c7ba78d442c | textbox | Initials:
9d572bea-2ca1-5834-a998-1e3e4488a39a | date | Date:
| checkpoint | 8332/Stakes where required to specification, level and with ties fixed securely.
807e07dd-11ef-51b0-90f5-75e980f3d9c7 | textbox | Initials:
8f9b6f58-41ab-5b63-a520-e1d99fd484ee | date | Date:
| section | Spec./Turf Laying
| checkpoint | 8333/Landscape Architect to inspect area prior to turf laying. If not available on site then photos to be provided.
2326a9df-32db-57bf-ba3e-de60266730cd | textbox | Initials:
5a75aa2e-531d-5849-9e57-3c23c8a3f24d | date | Date:
bf474a86-cc5b-5163-a794-328648419e45 | note | Comments: Date/Signature Landscape Architect
| signoff | SIGNATURE
| checkpoint | Lawn areas to be finished 25mm higher than adjacent hard paving to allow for settlement.
8968d042-23f3-577d-9c86-708c1b2742a1 | textbox | Initials:
154a0af5-ca76-5c56-90d6-524ce38e0fad | date | Date:
| checkpoint | 8333/Landscape Architect to inspect area after completion of turf establishment. If not available on site then photos to be provided.
a3f5c445-a79f-5356-b382-070ae57cd778 | textbox | Initials:
b145ea43-a210-58ae-922c-518d84faa3f5 | date | Date:
98e20ebe-e88e-5a2f-952d-ace90c8e7883 | note | Comments: Date/Signature Landscape Architect
| signoff | SIGNATURE
| checkpoint | 8333/Remove weeds, root material, stones, rubble and any other debris exposed during cultivation.
8be0a41d-3d8e-5e08-9374-2aa100def40d | textbox | Initials:
e4a91559-d21d-5933-9f18-cc6f1a5b8600 | date | Date:
| checkpoint | 8333/ Apply a dressing of fertiliser and work into the top 50mm of soil immediately prior to sowing.
fb6c5e6d-bcad-53e5-a9fe-6e96d51e54db | textbox | Initials:
d0afd24a-1f82-51d3-bfa7-10454226e11b | date | Date:
| checkpoint | Additional areas to be planted/areas missed (mark-up drawings where additional planting may be required)
e2e3372e-b2c6-5289-8daf-5d67f424db27 | textbox | Initials:
eb527558-7461-5e87-b906-d431f7a82239 | date | Date:
| section | Spec./Daily Clean Up
| checkpoint | 8332/Surplus plants removed to storage area per specification.
a191d8f9-cbc9-5749-9d10-186c4cc71e2f | textbox | Initials:
21cc83d7-8853-5293-919d-3177b4c11234 | date | Date:
| checkpoint | 8332/8333 Site cleared of rubbish and surplus materials (containers) removed
e0b8c457-f841-53e4-9c58-a818909f69a5 | textbox | Initials:
89234719-cb7d-5768-8d16-d5e8b3bc4127 | date | Date:
| checkpoint-no-value | Weather
a7d858c3-8724-5db6-be2e-485982f36bd6 | radio | (select relevant condition) | Sunny (check plants not left bare root in sun),Raining (ensure soil is not saturated which prevents proper planting),Frost (No planting to be carried out until frost thaws out),Overcast (Good Planting condition)
| checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
7da54ba4-b0a3-51ce-bf90-39644a2150a5 | textbox | Site Engineer - Name:
c9e429d9-3f67-581e-bf26-74eea68c236a | date | Site Engineer - Date:
3e3515ff-d08c-503d-8975-ed2aaee90cc9 | textbox | Landscape Architect - Name:
005046e6-4b65-5a51-851e-ab4a646fde84 | date | Landscape Architect - Date:
| signoff | SIGN
| checklist | CS-4053 - Fencing Checksheet |  | CS-4053 - Fencing Checksheet |  | c1355756-b134-491a-93d4-20262bc424cc
| section | DETAILS
| checkpoint-no-value | DETAILS
f6c8bc53-46ae-54ef-a3b7-f8854472a55a | textbox | Project No.
| section | Inspection
| checkpoint | Fence Height - 1200mm
c83b3b91-d1cf-5f6e-b60f-62666188c624 | textbox | Initials - Site Engineer:
3313057e-7023-5f1d-9ac2-13826d68d4a6 | date | Date:
| checkpoint | Strainers 2.4m long, 1.2m embedded, (min 1.1m)
2696395f-ca44-5722-ab56-57da165d548c | textbox | Initials - Site Engineer:
d7c9b061-d6e5-5245-87a2-6d0cb6ac21d9 | date | Date:
2dbce8cb-9952-5115-9b1a-19ed43b18c21 | note | Comments: Max dist between strainers 300m
| checkpoint | Posts 1.8m long, 0.6m embedded
94791c3e-1e87-5076-ba46-74966ec0076a | textbox | Initials - Site Engineer:
4e60f993-1aa9-52f1-b1b8-2e1706f129f6 | date | Date:
4991841b-8a3e-5585-828c-3c9cca40e5fa | note | Comments: Max distance between posts 5m, slope spacing as required.
| checkpoint | Battens 1.14 x 50 x40
b7defd65-18a0-5a4f-bf76-eff4fe071291 | textbox | Initials - Site Engineer:
5b4b09a2-7c1a-5168-b446-61229fdbf5b0 | date | Date:
c3c0b1ed-b35e-527b-9b54-8b95c5958000 | note | Comments: Battens placed at not more than 1.0m intervals and stapled at each wire.
| checkpoint | 9 wires 2.5mm HT
0c1ca1ba-c76e-528a-9c0c-c4ff4b565635 | textbox | Initials - Site Engineer:
ab371e88-e989-5c63-b1d5-567b4e582c8b | date | Date:
47c8f3c6-b690-54a2-85a9-63458b78c8fa | note | Comments: Bottom wire to be max 100mm from ground level
d3c96a65-56e2-5c2b-9bb1-2f490dcf5e4b | note | ○ Wires spaced at 75, 100, 100, 120, 130, 130, 150, 160, 180mm and all stapled to post/battens.
132efad5-83b0-5877-ada8-65ddcaf68fa3 | note | ○ Top wire min 100mm from ground.
| checkpoint | Stays
ae56248a-6ad8-5c26-9182-f9af040b1dec | textbox | Initials - Site Engineer:
fda38787-df81-5613-a934-2ab092cff59f | date | Date:
bd363ddf-be5a-59d5-9afa-109cf2d3ce2c | note | Comments: Footed stays must be used on all strainers.
e42bcd9a-3959-5c96-8f52-989f628837e2 | note | ○ ‘Feet” also to be used on posts in the bottom of gulley’s to prevent pulling out when wire tensioned.
| checkpoint | Gate min height 1.2m
b1106b55-504d-5bf1-943b-9a0a41a176dc | textbox | Initials - Site Engineer:
806527c6-e76c-597b-8448-b6885db7b236 | date | Date:
694dda17-d3ae-5e0d-b7bd-4e173529abd8 | note | Comments: Alloy/wooden gate new or reused. Hung correctly/does it open?
| checkpoint | Is fence vertical & true to line?
370d0d78-fd7f-5b30-935a-3f9d869b18dd | textbox | Initials - Site Engineer:
7b9df5a5-ba8c-59ba-baca-a2c1ce8142b5 | date | Date:
| checkpoint | Fence Height 1200mm
9c7d5ee2-1f59-5267-b089-9a3a577cde01 | textbox | Initials - Site Engineer:
7e0474e8-44f5-5b13-b67d-010b0a30c563 | date | Date:
| checkpoint | Strainers 2.4m long, 1.2m embedded, (min 1.1m)
8204addd-950a-5b12-9eee-98ed7ee0e1d6 | textbox | Initials - Site Engineer:
710ff736-a940-5b77-a412-40e3756f8d71 | date | Date:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
fa91c7b6-2826-5672-a896-9c2c2920d472 | note | Position: Site Engineer
5be73000-f500-5089-b88b-93681acc2fed | textbox | Site Engineer - Name:
cb6b5cd9-b8a4-5127-82c2-c7be894327df | date | Site Engineer - Date:
f38ca19e-e127-59d0-b047-d96ace4a7a08 | note | Position: CPS Engineer
8bba08c8-cbaa-5c77-bc64-42ec0bfeb78e | textbox | CPS Engineer - Name:
2ef743a6-a96e-5910-a3fc-9022288cdfd2 | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4055 - Pavement Layers Checksheet |  | CS-4055 - Pavement Layers Checksheet |  | 3b035369-6d5d-4a1e-b5eb-cfbf6fa43594
| checkpoint-no-value | Details
9500a7f6-33bf-556d-a289-3ec3e71675a5 | textbox | Paved Date:
3255e6c2-24ca-5fdd-b83a-f67b716cd620 | textbox | Location/ Direction:
5ee027c8-0023-5152-a02c-c7f65b5d77bb | textbox | Day:
1504fd52-6a09-5484-8d4f-e8269edefc3f | textbox | Shift:
ecb3f789-59bb-5362-8663-bf29e9e5d17f | textbox | Chainage(s) From:
9de43c51-23a3-5876-8cd9-26ad3fe33394 | textbox | Chainage(s) To:
03dd13b6-2e5c-5d68-99c2-8051aabc1700 | textbox | Previous Lot(s):
954735cc-f204-5d5a-a84c-f13b0f67eba7 | button | Previous Lot(s) Comply? | Yes, No
a50ef4bf-01c7-5e7d-bfd6-532d6b2eddeb | textbox | Corrective action?
| checkpoint | HOLD POINT: Previous Layers Quality Manager signed off
2a3c7dd4-04ea-5966-89eb-d9db7273a5ab | button | Pave this layer | Yes, No
| checkpoint | Layer Type:
ac630b80-fc13-50c7-8afa-4813a10c9753 | tickbox | AC___ Layer # 1
5c7357ea-2d27-5e5c-b72f-5e769030951b | tickbox | AC___ Layer # 2
7b704ddb-cd92-5fb3-acd4-257955b6faee | tickbox | OGPA / SMA
44bd65ff-0744-59f3-bdc0-7e788f75a7e2 | textbox | Other:
e48d61f5-6db8-5c9e-872f-7c3786495cb6 | textbox | Nominal Depth To Pave:
a75a62c7-277a-5f55-a029-969a31ef09aa | textbox | m² Paved:
bc8804b3-b058-5868-9ff4-7f3c8d0a5990 | textbox | Linear(m):
442640e1-ec4a-56e8-9b4f-38479bec25f7 | textbox | Tack coat/Membrane l/m²:
f93fda96-7e91-50b1-a653-3148f463062b | textbox | Nº of Cores required:
1cb9b98c-8d7a-5cd0-aaa0-d896e884258f | textbox | Mat:
5255b66d-37d1-5358-88f7-41f1887a698e | textbox | Joint:
fa18662f-0a08-564e-8944-358d1e48330e | textbox | Nº of Cores taken:
867735f1-1a85-58ae-b93f-04de555a2c48 | textbox | Mat:
dbb27469-7928-55ee-a368-7f46ae85a769 | textbox | Joint:
056f6656-5c4b-59f2-938e-fd7d06bd8380 | button | Cores Taken: | Yes, No
710cad00-5fc9-5c17-8c0f-416412a3b4bd | button | Cores Filled: | Yes, No
50a339cb-093f-5431-90a9-766e08b599db | textbox | Laid (Ton):
86202897-0f5c-5f1a-af50-aa11de4aa295 | textbox | Nº of Binder & Gradings required:
df62aa3c-4102-5df1-a640-06343d482a57 | textbox | Nº of Binder & Gradings supplied:
425e5fa0-b934-5b4c-892c-25c51a524cf2 | textbox | Lab Air Voids (%)
668233fb-73fb-5bb9-85b8-99353551d487 | button | Binder & Gradings Comply? | Yes, No
628b5c82-0772-5740-a6f4-1852a5c39de3 | button | As built Survey Completed? | Yes, No
| checkpoint | Air Voids - Run 1
5d75597b-c1f9-5618-b20a-38f41ba7a354 | textbox | Characteristic High:
be1754e2-2149-5bc0-8ca5-bcc1454e949a | textbox | Characteristic Low:
d78eb99f-2032-571a-97e9-b68e704b6643 | textbox | Average:
14404926-1711-508f-8a54-9f693c5c8f4d | textbox | Joint:
| checkpoint | Air Voids - Run 2
2548a894-7a6e-5c35-bb72-530129aef8df | textbox | Characteristic High:
78ccc117-d49f-51f0-be61-e320ee7a8623 | textbox | Characteristic Low:
83804908-033a-545a-8a37-3354c84f8161 | textbox | Average:
a1463881-5057-59a8-a66b-343d853570d9 | textbox | Joint:
| checkpoint | Air Voids - Run 3
c3c30cc8-1b25-5644-9700-7502ca2f2189 | textbox | Characteristic High:
e1ab6fca-42de-5000-9884-86a9972af74c | textbox | Characteristic Low:
f5777d48-7eb1-54bc-a53b-b7e49921a069 | textbox | Average:
733a8cc9-07c5-5e90-b5c4-90795971696b | textbox | Joint:
ff77e33c-f5a1-5828-854f-fac03495c0ef | button | Air Voids Comply? | Yes, No
b3d003a1-b6d3-59c5-aa01-ecf9beabda24 | button | Core Thickness Comply? | Yes, No
7b8c7525-2bdf-50a5-a945-b0f27e400615 | button | OFI attached for non-conformance | Yes, No
| checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
b4b514fd-2f28-59c6-b410-ca75a3317827 | button | HOLD POINT: Does everything above comply? | Yes, No
a3560b25-2bc3-5de4-be01-3cf1c840a9ca | button | Pave next layer | Yes, No
| checkpoint | Site Engineer
01771c9e-2a02-5adf-9f30-ddc0673aa5f7 | textbox | Name:
| signoff | Add Signature
| checkpoint | Quality Engineer
9a911a1a-6138-5f0c-be84-165d1a882cb7 | textbox | Name:
| signoff | Add Signature
| checklist | CS-4060 - Pre-Seal Checksheet |  | CS-4060 - Pre-Seal Checksheet |  | 665ebeb8-f04b-49b5-9286-97b6619c443e
| section | DETAILS
| checkpoint-no-value | DETAILS
d516fac1-68e1-5253-aacc-13ceac4622ce | textbox | Project No.:
| section | Surface Shape Check
| checkpoint | Surface Shape Check:
288f73d8-9865-5f54-a4d6-e789491729ae | note | No point of the surface shall vary more than 10mm when checked with a 3m straight edge (Measurements to be undertaken at a frequency of 1 every 100m)
2a53e0bb-7008-57f7-bf7e-d7c13a9bb386 | note | Note: Left and Right when facing increasing chainage.
| checkpoint-no-value | Chainage (1)
7e02c059-e3d0-5c83-b96c-c46c12782c1d | textbox
29088593-96b6-54a1-af17-37b0205ff67d | note | Measurement taken from straight edge to surface level
ac7e2a4d-f9f1-5f15-aded-2b98ebc4b8e5 | textbox | Bound Left
09b7729b-c4c3-5d6c-9d0a-d252a6915074 | textbox | Bound Left - Left:
fd63bc5a-f2e5-5465-85d1-42c9fece5d7e | textbox | Bound Left - Right:
658801d6-79f0-5893-97c6-8e58471312ec | note | ––––––––––
83cf45ed-04ab-57cd-b382-212e1eeaec42 | textbox | Bound Right
fcb4e10e-bdcf-5c7f-85b8-5f9551b926dd | textbox | Bound Right - Left:
708bf958-841c-5be0-80d7-ef4a570955e6 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (2)
bbceb4cd-e61f-5ffa-b270-ee31b7e4df1e | textbox
b586be0f-bbde-5c94-bf96-afe0a715794e | note | Measurement taken from straight edge to surface level
5c466f0f-c069-52d5-a667-5074d93bb996 | textbox | Bound Left
c7408dca-eb42-5c5a-ba54-fe94cba5fd7a | textbox | Bound Left - Left:
4c929668-0d5a-592c-ab21-5aa6a649a00e | textbox | Bound Left - Right:
ae5b2d99-52eb-552a-93e5-3205c5d4418b | note | ––––––––––
44e5313e-be31-53d0-a99c-e913a5f333dd | textbox | Bound Right
8f2fac36-6458-543a-b89b-bf2b8ef35cdd | textbox | Bound Right - Left:
eed4d1a1-3838-5bff-98b3-8830e29c5937 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (3)
8f24b108-99b6-5757-b25b-8d6f90cb2e4b | textbox
d7b23651-80cc-5d32-8b1c-3e779743ade2 | note | Measurement taken from straight edge to surface level
5420b686-8bb1-511d-a754-683abd726df2 | textbox | Bound Left
27a703ce-fbf3-51a9-bd61-8e32894482f2 | textbox | Bound Left - Left:
beb914b2-a37b-5d3d-8709-3ba8ad5cdbeb | textbox | Bound Left - Right:
e09cd3b9-7a41-52ca-bbe6-c33978d5a811 | note | ––––––––––
3a5f5036-8218-57e2-9912-81e56498f7e5 | textbox | Bound Right
e01a9694-54ca-5bbd-a539-7b4f05541d56 | textbox | Bound Right - Left:
36ff9a74-c658-5f56-a68a-33859ec91cff | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (4)
cfa466e2-cb92-5498-8479-2b2b21fa741d | textbox
28f11970-849b-5834-81d5-558aa71f9c25 | note | Measurement taken from straight edge to surface level
a874b990-eda7-5e93-8069-28c246c78a04 | textbox | Bound Left
c731a0c0-056f-5cc8-a9fc-cd16d269f00e | textbox | Bound Left - Left:
c0a413e3-e058-5fa3-9bd6-9f1da72fb56a | textbox | Bound Left - Right:
16c166dd-b384-5e85-88c3-490ab666f693 | note | ––––––––––
94c20ede-a592-5ba6-bdc8-6dcc2f280c01 | textbox | Bound Right
1b2f0934-88fe-5980-8456-b3545ad6e9e2 | textbox | Bound Right - Left:
4f340aff-8c19-5b17-9c76-a5a59f9b7d21 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (5)
7fdbd86d-0f2f-55a4-909d-b7a60f1794cb | textbox
3f764d9f-91e7-521f-820b-97c3b33a52bb | note | Measurement taken from straight edge to surface level
0c4e1c61-88f2-5952-a6db-c18466e38912 | textbox | Bound Left
4d64c4e7-5f2a-5eeb-a42d-48dfe06a0ceb | textbox | Bound Left - Left:
5d3e66c5-dce8-5895-8938-a3fa7ac96d25 | textbox | Bound Left - Right:
f8e7a6d4-2ef5-562a-b59d-07708f51071d | note | ––––––––––
65264fd0-8c72-507c-9171-198f01216d90 | textbox | Bound Right
46516c58-9b3c-5c27-9fb5-cfa566ba681a | textbox | Bound Right - Left:
77b8c5b9-872e-5694-ba98-06ff2c215cbd | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (6)
995eed9b-e439-5211-ba72-fa3369282a37 | textbox
a18474b1-5ba0-500c-b97d-1780e4c78f06 | note | Measurement taken from straight edge to surface level
a25cc02e-8ec3-56c2-a1d3-4c9534aff1a0 | textbox | Bound Left
452f6d53-7555-50f1-a9ae-e8c9ad4f682e | textbox | Bound Left - Left:
923a08f2-977c-50dd-8b27-c7500eee5977 | textbox | Bound Left - Right:
b2736d17-d8b2-56b5-9837-eae5c7cd3fdc | note | ––––––––––
cb15447e-ba2e-59f1-b97a-88b3110d256b | textbox | Bound Right
3563c2bc-b4cd-5f9e-aadf-c43a96230f13 | textbox | Bound Right - Left:
2261ee7e-6818-585f-9a48-0c5082b2c228 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (7)
aeaadfa1-4035-59dc-9f61-3650425c942c | textbox
be143674-1e52-561e-b56f-3a699875dbfa | note | Measurement taken from straight edge to surface level
7817140f-1a3d-52b3-ae42-b823ed5d6012 | textbox | Bound Left
1e529ee5-dd15-52c3-908c-c5ed4d770c10 | textbox | Bound Left - Left:
0db22940-c5fc-500b-9476-aee47cbdc54f | textbox | Bound Left - Right:
116e5340-f99c-5f87-9fec-453cdbe8631b | note | ––––––––––
7ba52c54-6555-5769-9c91-1b5816443d4d | textbox | Bound Right
3d6c9f67-e604-5be3-b753-877d2bbcc09c | textbox | Bound Right - Left:
401d6970-28bf-5210-8b78-e6b404ac5747 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (8)
6e2307f6-605b-5608-882e-39b4cbe4fb36 | textbox
c43a52fd-438d-50dd-8b74-c53e2fa71173 | note | Measurement taken from straight edge to surface level
8cff1552-37a1-567c-a463-24f6822b19b7 | textbox | Bound Left
48c933f1-48b7-5f2d-9d86-c39ffaaba173 | textbox | Bound Left - Left:
92275a68-a0f7-581e-85db-9ea5cb65b06c | textbox | Bound Left - Right:
cbc4f8ce-0a81-570d-89f4-fd9b15acb2ed | note | ––––––––––
cfc398d7-44c5-56e0-a0b0-0bb00c4b281e | textbox | Bound Right
32161ec4-4e73-5dec-9bb3-cddfd6f4b64f | textbox | Bound Right - Left:
8e48253c-ed5a-5bff-a212-d8e45a256e26 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (9)
9a87c76f-6967-5cfd-b9b8-0d6685de6acb | textbox
0c5ea306-2b67-5e4c-96c4-bfe026bf59b1 | note | Measurement taken from straight edge to surface level
1a432006-58b4-5f1a-a89d-5c1535d81348 | textbox | Bound Left
863bb107-f842-596c-ad49-1b93ddb3e624 | textbox | Bound Left - Left:
1bc328be-0f00-5abf-828e-c7d14182491a | textbox | Bound Left - Right:
42528aa0-48d7-5840-b9d3-770613ec04c6 | note | ––––––––––
2b946db9-a6e9-593d-9261-f06e66d08c2d | textbox | Bound Right
3a361744-0cc9-533e-b7fe-5391f3fbc6fd | textbox | Bound Right - Left:
3249b266-0857-5994-bb87-cf0c587844bf | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (10)
935a83d6-e10b-57a8-9758-05dda7a05506 | textbox
9c83eaf6-2b0b-50d7-bc7e-f0ea26bcac78 | note | Measurement taken from straight edge to surface level
96a28ba8-337c-5a4e-be41-bc75c2681e80 | textbox | Bound Left
c48e2c6a-ccff-53c1-90a2-8139007c7bd9 | textbox | Bound Left - Left:
e69896a0-a839-5707-9622-667f65a2e1fd | textbox | Bound Left - Right:
da4c9665-c6ce-5e05-b6f6-741b26c54aa1 | note | ––––––––––
090ab2eb-4f17-53f0-ae88-febef61c5279 | textbox | Bound Right
d653b8e1-ff9a-5ed2-a0c3-e14eec7552e4 | textbox | Bound Right - Left:
55a2f298-60cb-5a15-8de0-c793ace998ba | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (11)
1fd9c345-7a18-5bc5-aa75-7e1b066164b7 | textbox
d1d5c134-ec6a-5a0d-9fca-a8d6977b2173 | note | Measurement taken from straight edge to surface level
61ce066f-47f0-57aa-aa37-a4dce82db438 | textbox | Bound Left
cb5d14e8-463b-5785-a4d6-478c77ef14da | textbox | Bound Left - Left:
4fac4006-c42a-5522-a5e8-fcef1327eec0 | textbox | Bound Left - Right:
e5056b60-742d-5843-9c77-3f9bb822e150 | note | ––––––––––
783ddb58-b64b-5a4c-be90-2e13b71ebd9d | textbox | Bound Right
5f85477a-44bc-5a90-9138-873356a86fe7 | textbox | Bound Right - Left:
2d8d3831-0856-51a2-8cb7-900f28fea968 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (12)
8f98eb3b-9f8f-59ec-9db4-e7d7b73e0306 | textbox
6f91e4c4-b9fe-5db2-94b4-843f7af232a2 | note | Measurement taken from straight edge to surface level
3bfbc52d-15b7-55c0-ad03-6cdef179c11d | textbox | Bound Left
0939510a-9e85-5929-ad1a-bc8a2dca78fe | textbox | Bound Left - Left:
d5f56541-2979-5e73-84aa-90f7fa476e74 | textbox | Bound Left - Right:
89fa01ba-cee7-5bf0-8975-07b0af0bc4ab | note | ––––––––––
fd014fbe-7837-58df-b142-2c9be00834cf | textbox | Bound Right
702342d9-2b8a-5cfa-aeb4-38ea27ca3a42 | textbox | Bound Right - Left:
c6a2b243-6ea8-5d3a-9f36-a53ed8ea388d | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (13)
1da80591-5409-50b5-b39b-d1c636467c93 | textbox
4ade6d8e-1fa8-5524-b594-4bb65072dee6 | note | Measurement taken from straight edge to surface level
ab771565-98aa-57e7-8590-12b1d335c416 | textbox | Bound Left
b35ff412-39af-5239-927c-301bc0e12dc2 | textbox | Bound Left - Left:
5a4bff3c-ce8f-54c1-b927-cbc410a0ce97 | textbox | Bound Left - Right:
0cdf9925-6b78-59f4-8d31-e852c4329826 | note | ––––––––––
68f8d581-fbf6-50a5-99fc-c92636038bd5 | textbox | Bound Right
5fcbd1bd-e498-5bec-baf7-9ba6876a86e1 | textbox | Bound Right - Left:
2f4fc7d0-adb4-5135-b651-5da5ada9325c | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (14)
3b562440-55c0-52e1-ad14-fc05ee3e9795 | textbox
cf9d63d2-570e-52d3-8dcf-83b14183152d | note | Measurement taken from straight edge to surface level
76ed6824-666f-527d-84c4-ef4cb239538e | textbox | Bound Left
d5f7a3c6-b6a2-5188-b308-86570539a104 | textbox | Bound Left - Left:
8da42575-0446-5d36-a200-5e8a5d3aa9be | textbox | Bound Left - Right:
2d703fe2-a7ab-5369-bbcd-04c2a7232328 | note | ––––––––––
d6adaf97-31c4-52ba-bfa1-be2bbb49ca25 | textbox | Bound Right
d64a1b7c-7b75-5766-886a-e1800bde631e | textbox | Bound Right - Left:
b29f14de-faf8-559c-9d52-d93eef7f69ed | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (15)
816baa4d-deeb-5bff-a9f8-70b929f29274 | textbox
33eadbd1-3dc5-58a5-9246-af2e5d21eb9b | note | Measurement taken from straight edge to surface level
b6e4582a-c446-5b2e-9182-524f7934c085 | textbox | Bound Left
7549c887-4c87-5afb-acd6-9038616bc7d1 | textbox | Bound Left - Left:
ed3f000a-2d89-5c17-a83f-b91e7fa1dafe | textbox | Bound Left - Right:
c3d3593a-b4d0-50e3-83dc-300f45736bc6 | note | ––––––––––
80c55f3a-a1d9-5847-9431-597a2d89d2be | textbox | Bound Right
a6abe2e8-859d-58e1-858d-1c80721e69b1 | textbox | Bound Right - Left:
ffed0534-53fd-5e0e-bb86-7c7106da2437 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (16)
8071be5f-1878-50f2-8aba-8b46c6bdb073 | textbox
1963fd54-7a80-5609-8725-1821bfdf7851 | note | Measurement taken from straight edge to surface level
60af88e6-e163-5ab7-89ee-c2f56e436a20 | textbox | Bound Left
fe4b72de-863d-5bfa-870c-01308967119c | textbox | Bound Left - Left:
67a5a18a-61ae-5019-aebf-7f47d1648cf8 | textbox | Bound Left - Right:
1e804593-b52e-56e5-9cbc-43cfb5fac2da | note | ––––––––––
52136c63-a2b4-515b-b7ee-55d38bb562be | textbox | Bound Right
0ef14e9a-0441-52aa-940e-7509180af3b4 | textbox | Bound Right - Left:
4f498316-ba27-53ee-96a3-c19f9798a897 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (17)
4e021122-c241-5b3a-bfd9-82094cf2f5f1 | textbox
eb74cf50-ea66-5db9-97f9-ec55955620c2 | note | Measurement taken from straight edge to surface level
815a8553-8cf2-5e9d-a049-a244892b9d32 | textbox | Bound Left
c0fbb48d-395c-5ffd-808c-68df1236ee7d | textbox | Bound Left - Left:
d55a75c2-751d-5466-adfa-8bf5f8fec81d | textbox | Bound Left - Right:
069d20fb-4b91-5695-9e54-584fca60e662 | note | ––––––––––
109372d3-eb5d-5ed1-8476-f4b26d33eec9 | textbox | Bound Right
427c4e81-922d-5ae4-b127-d3e5a6e55e22 | textbox | Bound Right - Left:
13486197-3857-5a0f-8467-debc1f80f763 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (18)
717caec5-6566-509e-86b7-b091dcc9d7b8 | textbox
0627bcad-c1eb-5c27-a3d1-511110d3f95d | note | Measurement taken from straight edge to surface level
190e9a69-5645-5440-8e5e-1d318d08aee2 | textbox | Bound Left
34fda833-28fe-5b9c-9a82-9afb45441709 | textbox | Bound Left - Left:
61d7cd59-9810-5e6f-8ed0-68ac18c13ce3 | textbox | Bound Left - Right:
a303fd7d-6db1-52e8-bc61-6289e56ce2ea | note | ––––––––––
69e4ef68-76f9-5a95-b16b-e4ee75c40f0f | textbox | Bound Right
0963fbcd-c18f-568c-a576-01bffa0255f7 | textbox | Bound Right - Left:
f08829b2-09b2-58a4-a9c6-6feec13371f6 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (19)
d67cfc4a-f81b-5747-8480-ea6561257f08 | textbox
d18e7b65-64c7-513e-a7fe-5de03f6dd9b7 | note | Measurement taken from straight edge to surface level
fa752585-e5d9-5b83-a1c0-07dc0e87d3d9 | textbox | Bound Left
9a554a4d-b760-569b-9521-b6fb59db3d52 | textbox | Bound Left - Left:
8823df05-b7a0-5464-bfdf-e4ad1544061c | textbox | Bound Left - Right:
eaa2d3a6-2683-572a-b851-be9177ed4b65 | note | ––––––––––
8e8d8866-dfc3-5a90-b9e1-142ee1230ef9 | textbox | Bound Right
ae2fc34f-3b0b-57a0-b18b-d0c7448b8f6f | textbox | Bound Right - Left:
5284f27e-19c6-5750-918e-6901b45ffe9f | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (20)
473ca4ab-a920-5c0f-92b1-899947faabe3 | textbox
018742e6-2a93-5e88-bd4f-df17e129f71e | note | Measurement taken from straight edge to surface level
65395114-0761-591e-856d-4885ffe71c48 | textbox | Bound Left
990f1e6a-416a-5ccb-b736-0c8aa21a51d2 | textbox | Bound Left - Left:
320cb02d-e1be-534b-963a-41807dbd6370 | textbox | Bound Left - Right:
3558e2be-ffaa-5c7c-a348-5ca9b7899022 | note | ––––––––––
4b5dad61-023e-54e3-a1e5-48f71b8efe4e | textbox | Bound Right
15e53579-9869-59d7-955a-4baaee58ad76 | textbox | Bound Right - Left:
91049d72-cc1d-5b64-9c2e-04370d80db73 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (21)
33ca3fb4-7e7d-5ab2-80db-8e402b5e5c22 | textbox
448ab753-0adf-574f-acc8-994f5c8b1f30 | note | Measurement taken from straight edge to surface level
0d5baac5-3dcf-574c-9611-4692e87d14e0 | textbox | Bound Left
5f79be93-47c3-5729-b9c4-79248e55d225 | textbox | Bound Left - Left:
d89611f0-59f4-57d1-842c-bc82d3db68a2 | textbox | Bound Left - Right:
98c118b1-9d2c-5aeb-b5b2-653c82654b08 | note | ––––––––––
66c05965-8d74-5685-b382-90209194b067 | textbox | Bound Right
2f2e795a-0852-5cbe-a304-fb47ab3a770f | textbox | Bound Right - Left:
e2c999b5-9cc0-5ffe-a6c9-bf0c29ac999b | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (22)
0d24fd6a-97ac-53d9-ba3e-36f75ea05689 | textbox
a81826db-8bd4-583c-974b-a548cb3ea7ec | note | Measurement taken from straight edge to surface level
2fa1420b-5ebc-518d-af8b-b485c8232b5e | textbox | Bound Left
8e610976-86bb-5324-93e4-3d3b3f7c7679 | textbox | Bound Left - Left:
ec7f84b7-4e38-5dd7-8351-bc749e244fca | textbox | Bound Left - Right:
a4ddbae3-c9c9-5687-aa19-926b49135988 | note | ––––––––––
0edfad93-c483-52be-aea9-957d0317d146 | textbox | Bound Right
dfa2f0d5-a5bd-5080-b2d9-9ee39fa16780 | textbox | Bound Right - Left:
7342a6c1-1b70-5cc8-ad49-142225ab0e30 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (23)
9b6fe5de-645b-590a-a4ed-075b7f59ae55 | textbox
f7ff168a-b5f1-578d-84b5-06a62b1155de | note | Measurement taken from straight edge to surface level
2f08ac34-fcfa-5ce6-8acf-ef93b349a954 | textbox | Bound Left
c966849e-3905-5c38-ad62-642cf68ac4d6 | textbox | Bound Left - Left:
89a75bda-589b-585b-b29f-640fb3ca1362 | textbox | Bound Left - Right:
0a508756-66e1-5e06-9cdc-0dd107683bfe | note | ––––––––––
a81fbe4f-a07d-5a71-ae22-a357d65221a0 | textbox | Bound Right
c7695f6b-386e-53d2-9f1d-3a4cf6d6bee6 | textbox | Bound Right - Left:
e8d28f07-e700-518e-aef2-6d3589d1624f | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (24)
1576365e-2f01-5642-b6c8-0981b16f54f1 | textbox
0a403890-f32d-5d9d-b5a0-be01a0843781 | note | Measurement taken from straight edge to surface level
ec755512-a673-5aae-93c3-fa738b234a4b | textbox | Bound Left
f64171dd-0ad4-5e30-a467-53d152bbc9da | textbox | Bound Left - Left:
12526088-5ff9-5429-9790-b2ae5333222b | textbox | Bound Left - Right:
54395948-2f9d-5489-a6ca-840394538857 | note | ––––––––––
fe6d3bbc-58e5-5c26-81cb-b6d45bff4ef0 | textbox | Bound Right
0bfffdff-c857-5677-9519-e0cacbd87d03 | textbox | Bound Right - Left:
9107df97-aeb7-5e24-aadb-e4f63107f9e3 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (25)
ca1c24d6-fe4f-5926-a676-c333fded1ba5 | textbox
f7df284f-6bdb-5909-b31e-3f4b5bb5e3ab | note | Measurement taken from straight edge to surface level
a0e7c933-008d-511e-b0f3-34564a70a99c | textbox | Bound Left
ba595d32-5656-516c-915e-355b212a6393 | textbox | Bound Left - Left:
df41cb2e-0d59-5b9a-800e-eec4eeb4ae7f | textbox | Bound Left - Right:
322f71d1-cede-5187-ac99-7c104aa9d78a | note | ––––––––––
96808f38-c547-51aa-b645-c0d62e2a24f7 | textbox | Bound Right
c309d634-4972-5ccf-aa62-25c900f803a5 | textbox | Bound Right - Left:
c6cde08e-0f03-5e44-a093-9a3c24d03bbd | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (26)
f2640f07-e4bd-54b7-9c42-8090b5cae7e9 | textbox
cd61fb5c-cd17-520a-b319-a90e2a829402 | note | Measurement taken from straight edge to surface level
f4b3bd06-8ed6-560d-8a62-99ad19bc3c24 | textbox | Bound Left
3c39646c-0863-5317-b2b6-fb02a63b9bf6 | textbox | Bound Left - Left:
44e4f47a-3a13-5b19-ba49-d18b2f99ad67 | textbox | Bound Left - Right:
fa0307a7-cd91-55a7-8212-acf8d0516b37 | note | ––––––––––
ec247ce0-bab1-5901-bf7d-5ae2996e827a | textbox | Bound Right
2edd1eb6-29fd-5403-a7d7-58079dd1d6df | textbox | Bound Right - Left:
2d435444-4429-5746-9747-804dffd1c100 | textbox | Bound Right - Right:
| checkpoint-no-value | Chainage (27)
387539a5-8259-560d-8022-1eecb955ddb6 | textbox
b3f66b70-4520-5e71-b4b6-8da7bbcfacd1 | note | Measurement taken from straight edge to surface level
53030b42-8564-5bb8-b8f8-5481a873a59f | textbox | Bound Left
760bb409-d3fe-58c0-b1af-2fd610e50ab8 | textbox | Bound Left - Left:
001864dd-65ab-5001-80ab-bd32f619ddf2 | textbox | Bound Left - Right:
7c83bcca-2463-580a-8df5-b273698c3267 | note | ––––––––––
3f26105e-a071-5cd2-a831-964616c1ce53 | textbox | Bound Right
d7ef3942-826e-5566-b7e5-31a1615b6c06 | textbox | Bound Right - Left:
c158f826-867c-5c1b-85a8-4a615a3ec2bf | textbox | Bound Right - Right:
| section | Cross Fall Check
| checkpoint | Cross Fall Check:
c1cd0bc7-7ff8-5bc9-87eb-76c847f46457 | note | The cross fall between 2 points more than 2m apart, traverse to the centre line shall not depart from the design cross fall by more than 0.5% (Measurements to be undertaken at a frequency of 1 every 100m)
237d1edf-8393-52f6-81f1-6b38471f421c | note | Note: Left and Right when facing increasing chainage.
| checkpoint | Chainage
664c4574-172d-5a72-ad66-3d5d423f437b | textbox | Bound
051c4303-6d40-53ca-903d-c78ca64f22be | radio | Left Lane / Right Lane (Select one) | Left Lane,Right Lane
| checkpoint-no-value | Chainage (1)
2d65e017-fcca-5f00-90c6-434617386ee4 | textbox
5025c7a1-7bb3-5072-8d89-ecf8e7326235 | textbox | Measurement taken from straight edge to surface level at 2m from known point
ed302977-4035-531f-8afb-1d307f244fe1 | note | Cross Fall tolerance <= 0.5%
f5dc9546-a9e4-5b8c-80bd-e10c97eaa71f | textbox | Calculated Cross fall
750dda77-c2e3-5313-8d9d-1fa64af4255d | textbox | Design Cross fall
b48bf3dc-66ea-5fe7-946f-44c486783064 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (2)
09b32439-2287-5ee2-bae5-8379089d4a36 | textbox
7c51f382-bdf3-59d4-ab0c-c6cb64572c50 | textbox | Measurement taken from straight edge to surface level at 2m from known point
d5a295ae-305c-5c7c-b71a-b22f0799dd92 | note | Cross Fall tolerance <= 0.5%
5cc631a8-7e66-52a0-936c-1151e5a7872c | textbox | Calculated Cross fall
4a86a3f2-16b0-5cd0-9978-e2301b06d98b | textbox | Design Cross fall
b939c0f6-cf0f-5848-810d-59cea23832d8 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (3)
13b57d50-c79d-529d-87a8-f60c1851531c | textbox
24085c88-e101-5afc-b7a9-4700f6e45a57 | textbox | Measurement taken from straight edge to surface level at 2m from known point
fc9f2cfd-c496-5cf3-be43-c0cbd332ccb5 | note | Cross Fall tolerance <= 0.5%
f4d5282e-c1d7-5d1b-a154-ec5bd62a4681 | textbox | Calculated Cross fall
c739eafd-78e7-56a1-b1a5-5ea37484c766 | textbox | Design Cross fall
72133ea4-aae9-540e-9f24-a6765a242719 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (4)
5230fb52-2d7a-5dba-8778-3b56afad03d9 | textbox
946d6834-8169-587d-b8f9-72f951697766 | textbox | Measurement taken from straight edge to surface level at 2m from known point
8cc14ee6-1c32-5c43-9385-9b49c4e6b713 | note | Cross Fall tolerance <= 0.5%
1587148d-2036-515b-860f-11b0c1760883 | textbox | Calculated Cross fall
eec1e0ed-109e-5271-9fcc-704928f9bb19 | textbox | Design Cross fall
3a50c8db-b895-5670-b7eb-abe49c0f1f36 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (5)
9e72f5d4-e44e-51d3-89d4-d2d03499b195 | textbox
2570048a-1330-52b9-8e8e-fdbb2b96c19a | textbox | Measurement taken from straight edge to surface level at 2m from known point
dfe03200-b2ad-5799-8475-30db1f958978 | note | Cross Fall tolerance <= 0.5%
016e88ee-9dba-5508-a5f4-56964b464c9d | textbox | Calculated Cross fall
b3ada4ed-fb78-59d7-beb4-bf320aa58477 | textbox | Design Cross fall
e8e1b6b9-0f66-5eed-82ab-b1f4e4f8f839 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (6)
70088175-6d79-5420-84bd-b5181f1c1ed5 | textbox
80b99d4e-2d35-5d10-ada8-0be8fb16a83d | textbox | Measurement taken from straight edge to surface level at 2m from known point
46cfb937-2a9c-5bd0-a185-72db3083cb2b | note | Cross Fall tolerance <= 0.5%
65db414b-f1ba-5fa7-929e-c4b4a3869b38 | textbox | Calculated Cross fall
c5621ad0-eb5a-59dd-aa44-1b225678e3bf | textbox | Design Cross fall
ddabbf77-7b83-56ba-a018-34292c953093 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (7)
765ccc78-1583-5873-b670-58fae9934807 | textbox
6980f47c-df27-5526-b8ef-3362c19a63de | textbox | Measurement taken from straight edge to surface level at 2m from known point
99ac9674-4fbb-5bc1-b437-0e9284a8ae99 | note | Cross Fall tolerance <= 0.5%
1f83bd32-f161-5dc1-ad1c-0f6bc51ddf69 | textbox | Calculated Cross fall
d85af46c-b367-5a5e-ae98-1d370f1e7cd5 | textbox | Design Cross fall
30833d8f-8735-5511-9bb8-50091fcc46bc | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (8)
8d51603b-2906-567f-a3c1-a92760b57f21 | textbox
6b17a098-1c4c-5e9f-b85f-d71868a525bd | textbox | Measurement taken from straight edge to surface level at 2m from known point
31c1db06-3e78-5983-9887-51f2993f7bdf | note | Cross Fall tolerance <= 0.5%
1fe67b11-6180-546c-ac40-652c40b1aee8 | textbox | Calculated Cross fall
02bdadd4-1d3b-5bf6-80a5-c83b9586de7b | textbox | Design Cross fall
193eed54-595a-5f13-bf8c-327e3fb5f4b9 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (9)
66d0cbfc-a4dd-5afc-812b-2522eca93bb6 | textbox
30d89ee5-7d5b-58f1-87a5-743cd93ec6a1 | textbox | Measurement taken from straight edge to surface level at 2m from known point
7dff83bd-b571-5d63-9274-876b10e82a58 | note | Cross Fall tolerance <= 0.5%
15370f15-33c4-5e3a-83d1-20894ac3c089 | textbox | Calculated Cross fall
fbf467d2-5c56-5782-af57-4088ae14c8bd | textbox | Design Cross fall
cfea47dd-af7b-533c-be60-e8ab332cab53 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (10)
92d9818a-cde7-5835-aec3-9aba013efe61 | textbox
caf7eb5d-fc3e-5f24-9491-ffeaad0f0478 | textbox | Measurement taken from straight edge to surface level at 2m from known point
b6bc361c-b5cf-5437-8c82-997286da5508 | note | Cross Fall tolerance <= 0.5%
a345e1b2-c296-57fb-bc43-38b4a335202b | textbox | Calculated Cross fall
07c77c2a-30b4-5a5e-8148-cce79f8890ea | textbox | Design Cross fall
c2bb89b7-df47-591d-9780-d6b071510293 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (11)
0840ab14-6b88-5e0b-a7d1-a6cecd6509b9 | textbox
0b8113ee-f59f-5ca3-ba17-b153df9f928a | textbox | Measurement taken from straight edge to surface level at 2m from known point
80ba30c6-98d0-5eaa-b1ac-99edf46f647a | note | Cross Fall tolerance <= 0.5%
d797e02c-d57f-5558-950a-0393d0a9f49b | textbox | Calculated Cross fall
afdfc9e8-7b4e-58d3-9040-cf54d4a2d6e7 | textbox | Design Cross fall
2b7fcf21-b265-5593-9061-e5a9b1d2d231 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (12)
bbc2eab6-a635-54a2-b5be-c75fb87a909a | textbox
07bf40bb-4aa5-5266-8b97-db8b98a7cfc3 | textbox | Measurement taken from straight edge to surface level at 2m from known point
a2a39f41-3ce8-5857-be9b-8e59762f049e | note | Cross Fall tolerance <= 0.5%
a50cb5d2-ac70-5c7c-8edb-c40a04e1bd1b | textbox | Calculated Cross fall
14df3d94-0bbb-5b11-8ebd-81ceb163fc46 | textbox | Design Cross fall
95cbb5e9-974e-57a3-8b67-75826eeab2c9 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (13)
4210d9a5-35a2-5c77-b3d9-721715062687 | textbox
25837365-a827-5c81-9fae-d65ac31f4893 | textbox | Measurement taken from straight edge to surface level at 2m from known point
5b4e2809-0a96-5e63-b3ad-655cfb1d18a4 | note | Cross Fall tolerance <= 0.5%
12786ee9-2576-50e6-88ee-6f8a7804c448 | textbox | Calculated Cross fall
7dba8262-016b-5acb-818a-133e1a7c0b5a | textbox | Design Cross fall
7b8c7b64-f456-5141-a24a-023b7b1cdd7c | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (14)
0ad920db-b965-5586-8ce8-871768369945 | textbox
6c3486e1-376d-5314-9d10-e7fbd5e9b275 | textbox | Measurement taken from straight edge to surface level at 2m from known point
99771771-57c5-551d-8330-841972c4fed4 | note | Cross Fall tolerance <= 0.5%
a04672c5-fb8d-58a3-9b5e-48b62d06801e | textbox | Calculated Cross fall
2d408a76-e5b1-5787-abbb-c2a420320ea8 | textbox | Design Cross fall
8ab5e08d-5232-58fe-8961-fba862404769 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (15)
e33ccbeb-c493-5017-bdf1-d6e41a39bc16 | textbox
a9bb79e0-0d51-5db8-852a-e4a5bb8140cf | textbox | Measurement taken from straight edge to surface level at 2m from known point
47c037d5-0080-5698-bd80-eebfa6937705 | note | Cross Fall tolerance <= 0.5%
042ebb43-4757-5fcb-8922-b6a2282347e2 | textbox | Calculated Cross fall
661c7ee7-8f33-5fae-b4e7-1a3140a08d28 | textbox | Design Cross fall
d4b5a7f8-ff1a-52d0-b9ac-56c4b9a6f7bb | button | Within Tolerance (Y/N) | Yes,No
| checkpoint-no-value | Chainage (16)
824a5acc-1758-5748-b5f0-85b146d4970e | textbox
0e01dba9-56f2-5668-b2d2-70f082e1eaab | textbox | Measurement taken from straight edge to surface level at 2m from known point
57101c82-49cd-5ab5-88c3-0d048a8038d5 | note | Cross Fall tolerance <= 0.5%
1543ba83-4bfd-5136-8bfd-05985c92e719 | textbox | Calculated Cross fall
c530dfdf-9894-5b3c-9b94-57f5d7005d34 | textbox | Design Cross fall
1d6fe066-5d4f-5664-83bc-9a8c10304211 | button | Within Tolerance (Y/N) | Yes,No
| checkpoint | Pavement Construction Test Results Spreadsheet – Tests Completed, Checked & Signed
| checkpoint | Surface Finish Check
ad9922a5-1af6-5c92-8472-89e98ffd6134 | note | Site visual Inspection carried out by CPS Engineer & Construction Manager after sweeping and prior to sealing taking place.
4d02dfa9-38ba-5bc3-af45-01c712b07c2d | note | Checking that the large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping.
| section | HOLD POINT – Final Surface Sign Off & Approval given to Seal Area
| checkpoint | Final Surface Sign Off & Approval given to Seal Area
4e2ff48f-6d5c-5d5d-8bf8-987ad9f8e008 | textbox | Name: Site Engineer
f946d54c-4762-5b18-a49a-eda96c311a4e | date | Site Engineer - Date:
e9b46678-62a5-5f9f-b1b1-9746a16ea3e0 | textbox | Name: Construction Manager
8483c27e-944d-5f89-a625-9309b7deba1c | date | Construction Manager - Date:
e9f82647-8972-559b-958d-87eb3e94f31c | textbox | Name: CPS Engineer
a2616465-bb06-50dc-bbe2-319f5b859cdb | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4065 - Blast Record |  | CS-4065 - Blast Record |  | d73ba3f7-8cfe-4e4f-9315-ee0a21dea5ee
| checkpoint-no-value | Blast Record
2fd94cac-c1e1-55b6-a0c6-9be86f82aff0 | textbox | Project No.
fcd671de-b5c0-5a80-9ce9-7891e9ace8ae | date | Date:
caa2129b-6a83-5bbe-92f3-f8af237abd09 | textbox | Blast No:
6f9b983f-6aff-5139-b942-e808860067cc | textbox | Location:
314b1c96-4699-54bb-8b90-8b4cfd54ff45 | textbox | Shot Firer:
| checkpoint | Design Powder Factor
fadde783-a7ae-56a5-b881-e6d653034ae5 | textbox | Initials:
98acb61a-e1d8-5623-8b3d-cbd63339411b | date | Date:
| checkpoint | Diam. Hole
0c810e43-298e-5be1-8312-63948a4ea78e | textbox | Initials:
e8aa6cde-b08b-5ea4-8630-9b7cb3fc9b46 | date | Date:
da15f9c7-c8db-55fa-b0d6-e32f32e97add | textbox | Comments: Diam. Hole |  |  | mm
| checkpoint | Shot plan attached
1164f838-7bbe-501e-a438-46e21a2c738c | textbox | Initials:
fb302fae-e191-51ed-8fa1-55029b72fb99 | date | Date:
| checkpoint | Monitor 1 vibration & overpressure report attached
8ef980b4-45b1-51f6-af0c-024b6fffa668 | textbox | Initials:
dc449734-ea25-5601-9273-eeb485fccdd5 | date | Date:
| checkpoint | Monitor 2 vibration & overpressure report attached
e4c06e19-68a0-5342-bac0-fdfc9cdff03b | textbox | Initials:
78efd06f-ba3b-5543-92a7-4e11c64b8f0d | date | Date:
| checkpoint | Vibration & overpressure beneath consented limits (PPV 10mm/sec (5mm/sec 95% of time) 128 dB) if not OFI
9b7d3873-5ee8-5f8a-bf5c-3d13ceee3a6d | textbox | Initials:
e3d5367f-bd98-5a41-8b17-6ce6d2d62431 | date | Date:
| checkpoint | Shot Firer’s Blast Evaluation attached
3bdc7dc8-f8a2-5193-8a65-b1da24c3de94 | textbox | Initials:
00c4f750-db3d-520b-85c6-d3256d5842a7 | date | Date:
| checkpoint | Coordinate (GPS) plan attached on (Contract Name) grid reference
ed9c4f31-ded8-5c12-9f41-a9b23a5b9068 | textbox | Initials:
ea3c668f-b45b-544f-8323-9b0031e53758 | date | Date:
| checkpoint | Actual powder factor
481a10d1-310c-545b-bfa0-c7264e1f3cac | textbox | Initials:
6f46cd5e-6ecd-5cb5-b262-a7bd8c466fb6 | date | Date:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
d7a0d59a-747b-55eb-88ce-5ee0001d94b6 | note | Position: Site Engineer/Supervisor
83a9e66d-ec3b-587d-9dbd-fa3ce45ebb7a | textbox | Site Engineer/Supervisor - Name:
a7537afe-1a36-5709-aea2-1eafe48c8ed3 | date | Site Engineer/Supervisor - Date:
89e89ff6-9cd4-5c2b-b311-98ef70a0f5b5 | note | Position: Shot Firer
d305344b-7aab-581c-b41f-cc296b8c245d | textbox | Shot Firer - Name:
b73844e7-c7c2-5ca9-b112-99030616147c | date | Shot Firer - Date:
| signoff | Sign:
| checklist | CS-4069 - Stringline Dipsheet |  | CS-4069 - Stringline Dipsheet |  | 162365f0-c450-4fe1-b1c7-078a6187be74
| section | DETAILS
| checkpoint-no-value | DETAILS
f03cdd11-a244-5869-a734-09b1565ee7cd | textbox | Project No.
91c23354-ebb4-5073-aa36-beefcbc0740d | textbox | Stage:
e03054d6-3794-538a-ad06-b11928f6d298 | textbox | Material:
c6e8d299-234a-500a-a325-e5d1fcad6d67 | note | ○ Subgrade TNZ F/1 Tolerance: -30mm / 0mm
c3584e3d-4b8d-5816-bb7d-d7ed3b5e6ed5 | note | ○ SIL TNZ F/1 Tolerance: -30mm / 0mm
e5488a17-8c69-5890-8b9c-466e4948bb14 | note | ○ Subbase TNZ B/2 Tolerance: -25mm / +5mm
f79c4ae2-8564-565f-a5bd-8529e645d950 | note | ○ Basecourse TNZ B/2 Tolerance: -5mm/+15mm without concrete channel
21753f56-d929-5852-9906-691e69d532c6 | note | ○ Basecourse TNZ B/2 Tolerance: -5mm/+5mm with concrete channel in locations close to or at the lip of the channel
02a2104a-f6ed-577d-b707-f28e7156e6d2 | textbox | String Lift: |  |  | mm
| section | Chainage
| checkpoint-no-value | Chainage (1)
5b887981-a24d-52d3-803f-befbabfe7558 | textbox | (m)
d1054695-eb95-57da-afab-34410e99e0d8 | textbox | Width - Left Shoulder:
912b6276-827a-5a51-b201-d08ffe04176b | textbox | Depth Below String line - Left edge:
d2f2e5e1-57fa-5cec-96e1-e34664b70301 | textbox | Depth Below String line - Left mid-lane:
cff7f958-4ac9-51b1-8fad-7f28a2020a19 | textbox | Depth Below String line - Centreline:
31e501e6-70bc-5677-8288-4e1626a87435 | textbox | Depth Below String line - Right mid-lane:
268b7f86-96b9-584f-8faa-86adc2fb3998 | textbox | Depth Below String line - Right edge:
ba57e9e2-43c3-5d71-bf59-09636c1911d7 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (2)
bac71a2d-fd7a-5376-b01c-ef0b461803ef | textbox | (m)
c575cb9f-4ec3-57c5-8d70-4b2450a4f2d0 | textbox | Width - Left Shoulder:
b26c1ecd-0fd3-5b51-b198-840cb75da9ca | textbox | Depth Below String line - Left edge:
4dbd5b71-f4d0-57c5-a1ad-2a08f110972a | textbox | Depth Below String line - Left mid-lane:
953797cc-bae7-51bb-a6d9-60772bef3a4e | textbox | Depth Below String line - Centreline:
0fb033fd-c371-5b29-a1ce-9a3c1e235dfa | textbox | Depth Below String line - Right mid-lane:
b7ce021a-5cc6-594f-956b-f8fdd6da17c8 | textbox | Depth Below String line - Right edge:
8c3894d7-5517-57c1-bc2b-2de08217cf4d | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (3)
af8d92a3-7ab7-5dae-9391-4d75adffc78b | textbox | (m)
0f56d08a-5a65-53ea-814a-23b3735c8039 | textbox | Width - Left Shoulder:
d45b9516-267e-5703-a402-6aafdecf8fe6 | textbox | Depth Below String line - Left edge:
9188639b-ed99-590f-a13e-7b14fbedcc0d | textbox | Depth Below String line - Left mid-lane:
7251606c-1972-55b5-96cb-2c1a73ec237c | textbox | Depth Below String line - Centreline:
7b34f12d-4de1-56be-ba7e-e2d31bb1e38f | textbox | Depth Below String line - Right mid-lane:
b5aa37c5-7909-5d54-b690-2b3c7e6d4192 | textbox | Depth Below String line - Right edge:
612f2ee6-7149-592e-9e9c-7866a9a91de0 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (4)
057f57f3-e08d-5e42-a035-452c48ee9c12 | textbox | (m)
2c8c28bf-7969-5a44-8281-bad9b9d8b676 | textbox | Width - Left Shoulder:
ef38fe96-33d3-5c92-b582-89e7fe02b84a | textbox | Depth Below String line - Left edge:
86e8667f-deb3-5cdf-b92e-820f8b5f397b | textbox | Depth Below String line - Left mid-lane:
103aee6d-a2d4-59ee-bfc5-32fbe7fbd98a | textbox | Depth Below String line - Centreline:
3df5444b-57a2-52e4-bc81-0d771bf00069 | textbox | Depth Below String line - Right mid-lane:
f2e70831-e8e0-553a-9e2a-17fe7f1ff6b8 | textbox | Depth Below String line - Right edge:
1624e91d-cb3b-5259-9203-f954ebdebd17 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (5)
03568f72-fdbf-56ed-8c6a-c4e19e35b2f9 | textbox | (m)
b72da2a2-c9a4-5dba-8c56-ec6a8caca0be | textbox | Width - Left Shoulder:
d8a5cadf-fcf5-56f3-ae6d-aa443f525b59 | textbox | Depth Below String line - Left edge:
9f63b3c6-6a2f-5aa3-ab57-6becdb7c8e88 | textbox | Depth Below String line - Left mid-lane:
a42d6360-5843-5e71-9469-473c15c586bc | textbox | Depth Below String line - Centreline:
a1303e46-bcd4-561f-80b1-adc7070e3041 | textbox | Depth Below String line - Right mid-lane:
9c83d70b-cd54-59fd-aba7-0c97349f1859 | textbox | Depth Below String line - Right edge:
7be5fb6f-88af-5545-aeb8-6db9d8c81294 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (6)
9e81bc47-c736-53e9-93f0-7dadab65ed00 | textbox | (m)
243efd87-21f0-554d-b7d3-7d723a0a3504 | textbox | Width - Left Shoulder:
018fbda3-a63c-593c-8810-239e75f7a37f | textbox | Depth Below String line - Left edge:
14625a6c-7136-5c02-b8d2-aee09b4cb6de | textbox | Depth Below String line - Left mid-lane:
37aceb65-0942-5f5c-8d5c-ebdd3c7480f5 | textbox | Depth Below String line - Centreline:
52ea3e27-eb1d-57fd-a18e-904b2ee60255 | textbox | Depth Below String line - Right mid-lane:
3c35f5be-8a4e-57b8-9fff-dbd303cacbf5 | textbox | Depth Below String line - Right edge:
6ddd3930-edb4-5d40-a39f-20b5af16d03a | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (7)
890edba3-0c36-5e38-9d23-6c30d1c072ea | textbox | (m)
14dbd725-83c1-53d0-b04a-729b711c9de7 | textbox | Width - Left Shoulder:
310b0911-e03d-5194-8552-aae089cfe40d | textbox | Depth Below String line - Left edge:
360dfb32-61ea-5055-89d7-a8db751292f1 | textbox | Depth Below String line - Left mid-lane:
21b1c1c1-7940-5d4c-af00-9c77b82def79 | textbox | Depth Below String line - Centreline:
311b562c-c911-5a09-bacc-95f2b763efc0 | textbox | Depth Below String line - Right mid-lane:
fa02bbcf-833b-5ef4-8742-60de4bf60faa | textbox | Depth Below String line - Right edge:
829d55c6-f6be-58bd-a583-546bdb78881e | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (8)
88be5677-b441-58b8-ba0a-4e984cb973fa | textbox | (m)
d1145507-58a2-54c7-b068-7dd390cbbff2 | textbox | Width - Left Shoulder:
e838e1df-6a1c-5428-b165-6a38d6b1e3a8 | textbox | Depth Below String line - Left edge:
c54730fd-b623-5820-ae06-fab642df2191 | textbox | Depth Below String line - Left mid-lane:
00caf130-f48b-539a-8810-c194c9678d0e | textbox | Depth Below String line - Centreline:
0e55d838-089e-5e0d-aacb-20c91eda5631 | textbox | Depth Below String line - Right mid-lane:
af06f511-40c8-5818-8456-ef53e14ace1a | textbox | Depth Below String line - Right edge:
b8d9d73e-b426-5651-863d-89360886f280 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (9)
c458f1a5-b46d-59c9-881f-2e4ca16f2904 | textbox | (m)
41949429-3442-5400-8bfd-fe8524de644c | textbox | Width - Left Shoulder:
a9ac9056-1f55-5e67-b6ea-e7f999c4c655 | textbox | Depth Below String line - Left edge:
6b54170f-e2d7-5017-87b7-2cb4f3b7c1ee | textbox | Depth Below String line - Left mid-lane:
1d93064d-62d7-507f-981a-eea588244a22 | textbox | Depth Below String line - Centreline:
42c66217-3d65-5cce-a75f-c88042f78bff | textbox | Depth Below String line - Right mid-lane:
12f15c16-c170-5280-afe7-1a75655c85ad | textbox | Depth Below String line - Right edge:
820b24ea-8301-569b-97ed-ac5da6a1bc99 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (10)
222da97f-d75d-5476-84bf-df55a18ac99b | textbox | (m)
ae082ab9-6d65-5de1-b0db-82b6a2c98293 | textbox | Width - Left Shoulder:
99441f79-56b9-5df9-8390-438d48e7b923 | textbox | Depth Below String line - Left edge:
052676a6-868f-5a64-93f1-908fb56d58bb | textbox | Depth Below String line - Left mid-lane:
878684c1-5785-52e0-a4da-7569f3f86b4d | textbox | Depth Below String line - Centreline:
a20aef90-bcc5-5821-aa18-c4ae35e27baf | textbox | Depth Below String line - Right mid-lane:
6963ba7f-ff36-5e87-a43c-149a0e00cb6f | textbox | Depth Below String line - Right edge:
7980c9d8-a3f2-5aa4-8fc6-f6dd3bfaa0a5 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (11)
5e32d484-946a-53b0-9ee1-d6b8fb0d55cd | textbox | (m)
e8de5566-886c-5c28-acf9-40b9eba841f4 | textbox | Width - Left Shoulder:
76c2f7c0-77b2-5023-9ea4-1cca22e16a63 | textbox | Depth Below String line - Left edge:
48e892db-b03f-5d63-982f-61e41081979c | textbox | Depth Below String line - Left mid-lane:
e56b3f31-631c-50c4-b862-37760ce5e974 | textbox | Depth Below String line - Centreline:
5d02816b-6839-519c-9311-dae27992e9e5 | textbox | Depth Below String line - Right mid-lane:
a96273fc-2b12-5b64-885e-bcec1300cfd1 | textbox | Depth Below String line - Right edge:
f466df12-ff76-5901-a4c3-f42fd7091f02 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (12)
68778421-d077-5ff0-b4e8-6a070bb62b0a | textbox | (m)
4e10cf00-f100-5a00-b49c-0f804225774d | textbox | Width - Left Shoulder:
36b91b03-f173-5647-8c8c-35d3c8d5e831 | textbox | Depth Below String line - Left edge:
6a44d0f3-117c-5598-89d0-d588ba1226b0 | textbox | Depth Below String line - Left mid-lane:
7e98f28a-d761-5372-b6a2-23c6babd316c | textbox | Depth Below String line - Centreline:
a531c501-77f0-532b-b9c7-8302e8a5b7eb | textbox | Depth Below String line - Right mid-lane:
65179592-b1fc-5c05-9944-37c37e3a8b9b | textbox | Depth Below String line - Right edge:
11bc14fa-e4d2-5bfd-9621-9d94bb5cfbbb | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (13)
bd3ac0db-bb8e-512b-9093-5e676670a8f5 | textbox | (m)
5a3d4ffb-5670-5f99-bfae-8253c197ddc1 | textbox | Width - Left Shoulder:
21719b03-3594-59c3-9274-0a450e89ea00 | textbox | Depth Below String line - Left edge:
88129c6d-de7d-5f32-88b1-00ca4c0117aa | textbox | Depth Below String line - Left mid-lane:
bd6199e1-6d9d-57fa-8400-b827f1ef2c7e | textbox | Depth Below String line - Centreline:
664ff525-9741-5d94-b5bd-b97254784ed0 | textbox | Depth Below String line - Right mid-lane:
033b2c27-f7da-56cc-9307-4077863798c8 | textbox | Depth Below String line - Right edge:
d265f2d9-7828-5a77-af4d-f1a3733ea096 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (14)
230f39ba-f88b-5721-bf4d-6adb6791ff4b | textbox | (m)
d69898be-1444-59bd-ac4e-805966ca57db | textbox | Width - Left Shoulder:
648e3385-60e5-557b-8940-d250e6fe362e | textbox | Depth Below String line - Left edge:
ec8377d3-8fa1-508a-abd0-116e97d7e97f | textbox | Depth Below String line - Left mid-lane:
5840e63a-bdc9-5292-83a5-b75ef606c55b | textbox | Depth Below String line - Centreline:
2a7571bf-e8a2-59ff-8a51-804112fbd073 | textbox | Depth Below String line - Right mid-lane:
6c456bc7-e9f8-563d-8f26-64b8a36eaf54 | textbox | Depth Below String line - Right edge:
192fa368-d1e5-5da7-b906-4abf5c67b532 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (15)
12d2aaa1-1b3f-58e2-b2db-3254b0fbeee8 | textbox | (m)
0f876d93-c92a-5527-988b-3d9ec0accc9d | textbox | Width - Left Shoulder:
da3c3033-0e36-517e-a888-54fb9489259a | textbox | Depth Below String line - Left edge:
9187cd92-5abc-5c9d-a29c-d3ea60ae2dc8 | textbox | Depth Below String line - Left mid-lane:
15a2adf7-5711-52bc-a41d-841aff371b0c | textbox | Depth Below String line - Centreline:
10393f5f-65d7-582f-9523-2b0b6f0addb1 | textbox | Depth Below String line - Right mid-lane:
87cc4cf7-d59e-5726-8267-d9958d5e8c31 | textbox | Depth Below String line - Right edge:
13431708-35fe-5f53-8085-e49da6417d87 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (16)
866b5e67-e0eb-5b9b-b03d-828aad6ff263 | textbox | (m)
c88f2289-675a-5b3c-ac8c-4ca883ace9c9 | textbox | Width - Left Shoulder:
791d83fc-d40e-5d81-96f5-e93ae21c7212 | textbox | Depth Below String line - Left edge:
3b564a85-aa86-5eee-af63-24c9a39d0493 | textbox | Depth Below String line - Left mid-lane:
4f847f7c-2b5f-5b84-98a1-8987154063f2 | textbox | Depth Below String line - Centreline:
c12051ba-4c75-59e6-96e6-80ed1820851b | textbox | Depth Below String line - Right mid-lane:
331eaaa6-2c3f-56c4-adbc-ca89e6ae4152 | textbox | Depth Below String line - Right edge:
c595c366-311d-5aea-991e-c16aaa0ef7aa | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (17)
693d1996-e9d6-596b-bf76-f3c7eccaf7bc | textbox | (m)
cafbbbdc-dca9-5af1-a0c1-418245a38b4b | textbox | Width - Left Shoulder:
7e82e9f7-a2ad-5ccd-addc-b6b4660464f8 | textbox | Depth Below String line - Left edge:
a5130b3c-79a8-5a8f-a4d8-63e7b2c600a5 | textbox | Depth Below String line - Left mid-lane:
1fd73b2a-0eaf-5f1a-93a3-832a5ff7b263 | textbox | Depth Below String line - Centreline:
dcbca0b1-12b7-5c98-b7a6-95117a0e5839 | textbox | Depth Below String line - Right mid-lane:
627c0a77-51e4-5187-9f7e-4692807a8886 | textbox | Depth Below String line - Right edge:
2c458328-9477-5a39-afb9-618935d638eb | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (18)
3f0bb176-2090-581f-a561-9352bb407156 | textbox | (m)
999fb65c-0b17-5c7d-87aa-ba6dc6a208d3 | textbox | Width - Left Shoulder:
d1da1704-a305-5acf-812f-05377d0f9eb2 | textbox | Depth Below String line - Left edge:
e2395ddc-4a9e-5bf8-9121-d8882a90a373 | textbox | Depth Below String line - Left mid-lane:
752b5df8-021b-5220-90dc-a05272a011ed | textbox | Depth Below String line - Centreline:
08c09bf7-2942-52bc-860e-70cdb5bc4b98 | textbox | Depth Below String line - Right mid-lane:
46f085c6-aabe-58d2-817e-63a86b3294b5 | textbox | Depth Below String line - Right edge:
3c0ddbb6-333c-53bc-8103-8f668ea0676a | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (19)
29cbc3e4-6af8-54ba-abf8-083f861a5d78 | textbox | (m)
891300e4-59d9-554b-bc71-63e820352367 | textbox | Width - Left Shoulder:
57a061e7-b08a-577e-a7bd-53fa7c0c4137 | textbox | Depth Below String line - Left edge:
a25d8233-abe0-5897-8163-1f9f1d89f02f | textbox | Depth Below String line - Left mid-lane:
6931bf3e-8a3d-550e-8443-e23299414d55 | textbox | Depth Below String line - Centreline:
4b12b8f2-a4ce-53e5-a860-f0b0d10aee73 | textbox | Depth Below String line - Right mid-lane:
53cfae27-966c-5998-bbfa-5a28c421a945 | textbox | Depth Below String line - Right edge:
5dee7b72-ad61-5a77-aacb-8d6e93fbaf49 | textbox | Width - Right shoulder:
| checkpoint-no-value | Chainage (20)
8ed07a57-e5a0-5f2d-a402-c2a7e5fe851a | textbox | (m)
e86a5584-0077-531b-827e-f826e20fe833 | textbox | Width - Left Shoulder:
41695aaf-feb9-590c-89a5-d6f57fb4ddba | textbox | Depth Below String line - Left edge:
63387926-875e-5e3f-82fd-4ee67578b636 | textbox | Depth Below String line - Left mid-lane:
d01d7904-1019-52ee-aa32-1256cf17cbe5 | textbox | Depth Below String line - Centreline:
f2952d48-6dbf-51b6-834b-ecd16cbd3f5a | textbox | Depth Below String line - Right mid-lane:
9cc42e13-8d4f-552c-8b2e-2d9c3ed8fa42 | textbox | Depth Below String line - Right edge:
74f29bf2-c6ba-5781-b640-3e66947af4ec | textbox | Width - Right shoulder:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
6b1f1326-e7d6-5b48-820a-a6aa22290ec4 | textbox | Site Engineer - Name:
cc0962b8-7969-5ce2-bd6b-2debc96f98e2 | textbox | Site Engineer - Date:
7153d825-7488-5ea7-99de-1e5434618c66 | textbox | CPS Engineer - Name:
5d250e0c-0dc9-5dd5-ba64-b6573b887719 | textbox | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4072 - ITS Pit Inspection Record |  | CS-4072 - ITS Pit Inspection Record |  | 0172b0c6-fd6e-4711-81a1-3f0f9891c839
| checkpoint-no-value | ITS Pit Inspection Record
2c8070b3-95cd-5021-9333-587624d9f659 | textbox | Project No.
2619c507-9ec4-5774-b096-88f252f5affa | textbox | Drawing No (& Rev No):
cbe6387f-8219-5b8f-88cb-7736cf1358ab | textbox | Pit #:
| checkpoint | Pull Pit/ Joint chamber set out by surveyor
62109141-7e69-580d-90db-701a38fe0375 | textbox | Initials:
c624d3fe-81cc-5e87-a28f-9b05004ddb07 | date | Date:
5e0bf12c-4568-501e-ba6b-9d395062920b | note | Comments: Survey Receipt
| checkpoint | All existing services exposed and identified before trenching
de02bc6b-c561-5f65-91de-da0c798d68a8 | textbox | Initials:
683bf4f5-dab2-5e64-ae08-74e3219640b1 | date | Date:
| checkpoint | Depth shall be determined prior to excavating
bddd8583-8abf-5961-af82-022a00c7758d | textbox | Initials:
afc8908e-a5b8-57e8-9b49-ed8630d7b39e | date | Date:
0f15d416-1551-58a1-94b3-1363418c79c5 | note | Comments: Grass/Concrete/Asphalt areas – Lid must be flush to FL
862108ff-f688-5b71-82e5-9d5707b31089 | note | ○ Planted areas – Lid must be 100mm above ground level with a sloping concrete apron
| checkpoint | Slopes >30 lid shall be 100mm above GL on the upper side. Slopes 10-30 lid shall be flush with the GL on the upper side.
da8d7830-6d37-567c-afc6-71d052882651 | textbox | Initials:
218c2195-4c8f-54b6-a5b8-ebfff13fbd00 | date | Date:
| checkpoint | Bedding shall be 150mm of GAP65 compacted
584b57e7-166d-573f-a3d9-ecd0acea8599 | textbox | Initials:
4783374c-bed7-5473-b6db-64b1f56b237d | date | Date:
| checkpoint | Ducts shall be connected perpendicular to the chamber wall.
cdd0dc5c-b076-5795-9b0d-f300f36fc979 | textbox | Initials:
4373ede8-6b5f-5a24-9edf-9cd1ddc783f4 | date | Date:
a9ddf59e-8882-5d43-9222-9d3f0c76c933 | note | Comments: Ducts must not protrude more than 100mm into the chamber
| checkpoint | Seal ducts using suitable epoxy resin (outside) to ensure water tight
0e6f8026-3ac7-52f6-a92d-5beef6b0e36a | textbox | Initials:
43a76e1b-d89b-5b7e-b80e-f9103d8f7bf3 | date | Date:
5c4e0fc4-da15-583c-9eb9-44c0a5499fd5 | note | Comments: All joints must be smoothed off to form a fillet between the duct & chamber wall
| checkpoint | Ensure all ducts are capped inside the chambers to keep water tight
ee8f6737-42cc-5670-a6c1-e569400bb3ec | textbox | Initials:
bda02b42-ceaf-5615-8b42-4d3df0c524f2 | date | Date:
| checkpoint | Ensure backfill material is correct and compacted
269735df-08f8-5887-aa80-a97fcb3a0e5e | textbox | Initials:
07342369-6422-5011-beef-0e32142cefb0 | date | Date:
dcbc114d-e6c4-56e8-b65f-37703b84005d | note | Comments: Berm – sand/excavated material 200mm lifts CIV of 8
925c0021-529f-5d7d-9e53-95e09ed0c454 | note | ○ Carriageway – GAP65 200mm lifts 95% MDD
| checkpoint | Top 300mm of the chamber shall be concreted to a width of 150mm around the lid
9d701df5-ad71-56ad-8f31-7de93111e586 | textbox | Initials:
640f93e6-e9dd-5906-b9a2-c735670991dd | date | Date:
| checkpoint | Roof, collar & lid installed to manufacturer’s requirements
91521ed0-9b3c-5c9c-8e72-95365a745ca7 | textbox | Initials:
02ff7b6e-b5fe-5036-b1da-6de52104e108 | date | Date:
| checkpoint | Clean out jointing chambers at completion.
9a474b3a-a3b5-53bc-bf75-1187abbbc07f | textbox | Initials:
c6c6ddcf-6d8d-5e98-971b-505f2b9b1e18 | date | Date:
def5f9a7-52e1-555c-bab3-9b80e9dbd759 | note | Comments: Remove any construction materials or contaminates from Pit
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
97a76f6c-abcd-53c0-95d3-0f96695cf78a | textbox | Name:
b7809d2f-995c-55e0-afc2-475ca6b19725 | textbox | Position:
e080ec35-5df4-55c3-ba61-559b68c6c1ec | date | Date:
| signoff | Sign:
| checklist | CS-4073 - Drainage Structure Water Tightness Test Record |  | CS-4073 - Drainage Structure Water Tightness Test Record |  | e26c0ef5-1548-49ed-b05d-1d8e16386deb
| checkpoint-no-value | Drainage Structures Water Tightness Test Record
214d5c27-ff09-5165-9c20-966b6d406c73 | textbox | Project No.
f270f3c8-7b35-53db-8172-f3ffdb7f1a5b | textbox | Weather:
874a3e39-db80-5ec1-9ac9-ffc7c69d9f4d | textbox | Location:
6c9d4b55-f848-5bc6-98c7-1a657549c9d4 | date | Date:
6bac14d2-0254-5d0e-8f75-a8faecb42990 | textbox | Personnel conducting test - Drain Layer:
5de10c2e-476e-53d6-8bc8-1b1b38e42522 | textbox | Personnel conducting test - Design Team Rep:
0f8879af-4252-53cf-8e5b-15423d79d58a | textbox | Personnel conducting test - Site Engineer:
| checkpoint | Structure type & Chainage
0e62d030-d370-5ad9-a409-e3a8e492ed9b | textbox | Size of structure (mm dia) |  |  | mm dia
9a261ecd-51d3-5cba-b73a-26b1a32958d1 | note | or
bc2641c2-2d84-54f8-b59c-5dbb3bed44d4 | textbox | Size of structure (mm x mm)
6f7367c7-c693-5e47-8bc0-81435895a906 | textbox | Depth |  |  | mm
b5571d11-3154-5d9d-a895-e4b5302509db | dropdown | Drainage plugs used | Rubber & Aluminium Plugs,Rubber Blow up plugs
6e92e0f2-2c71-575e-ab9c-fc2e87db34d8 | button | Plugs Braced? | Yes,No
a85db535-0ee3-5896-8db2-b0d7b149fb6c | textbox | Structure filled with water |  |  | am/pm
8a464f20-e06d-5d61-9650-0281e448c1e1 | textbox | Water absorption duration |  |  | hrs mins
7b58342c-e823-5bf3-bc3c-4d97de288669 | textbox | Test start time: |  |  | am/pm
1b48c149-5990-5a95-b8cf-25e55a3c13ac | textbox | Test finish time: |  |  | am/pm
50418b01-75b7-540f-ba02-e50e216c7eda | textbox | Duration of test |  |  | mins
| checkpoint | Acceptance level shall be no more than a 5mm drop of water level in 10 minutes
860d7086-d250-558f-8329-5680c2005daa | note | Measure water level from top of structure
2d79bb70-5b4b-53a5-9837-bed9a0eb2af4 | textbox | Start |  |  | mm
44283825-3cd5-5d9f-bbfb-01027ed3786b | textbox | Finish |  |  | mm
e58bea29-9113-5acb-b090-0ab9d0d74b39 | textbox | Water level drop |  |  | mm
| checkpoint | Test Result
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
9bd79914-a9fc-5e96-add0-fa33cc349e5c | textbox | Name:
dc5c574f-b33e-5833-a23e-917e1bfdb45e | textbox | Position:
1a88a7b6-f675-59ae-b16e-111f0fd8d7f9 | textbox | Date:
| signoff | Sign:
| checklist | CS-4074A - Low Pressure Air Test Record for PVC pipes |  | CS-4074A - Low Pressure Air Test Record for PVC pipes |  | 4fdcc923-f1b1-4921-8860-14317c73a8f8
| checkpoint-no-value | Details
e6c5aff2-ffc6-51e2-ad9d-5523e40cb063 | textbox | Work Area(s):
fbb0b252-807a-5712-a8a1-406b93258bfb | textbox | Sub Work Area(s):
7976f0a3-bfd9-5472-9f37-228e445235f7 | textbox | Lot(s):
d779cccd-88fa-518f-8762-58925bb01a58 | textbox | Sublot(s):
87108388-3341-506e-9cfd-3beadc56784e | textbox | Document Date:
7c7c6902-73bc-5633-be86-8c08d80d4ae6 | textbox | Updated By:
d0ba2fe3-5da6-529d-be74-4bc2f5cb04d9 | textbox | Area:
c1e87fb5-e211-5f6f-85d8-b1ca0e6f75e9 | radio | Weather: | Fine,Overcast,Showers,Rain
a28eb7a4-83b1-59b8-bc69-f243070287d4 | textbox | Location:
c5ca1b6d-7867-54ff-87b5-589a7b1e4aed | date | Date:
26e7850d-5eaf-5ac6-9f24-47296af2fcf5 | note | Personnel Conducting:
0430ff42-e839-5e9c-a9ce-a59c4256fe37 | textbox | Drain Layer:
e48a0564-e00f-52e7-871a-afe23e8564ca | note | Witnesses Requiring Notice of Test:
3afe3912-176a-5685-b854-0332b7e9ab2f | textbox | QLDC Rep:
0f9913ce-bf48-51a2-96b2-0e4096def94b | textbox | CPS Engineer:
cfa13bb9-8921-5237-a5b6-aa11a1657b53 | textbox | Site Engineer:
| checkpoint-no-value | Pipeline
46c40af9-9971-5367-b854-ffcfa4e686f5 | textbox | Pipeline:
bf2a26d1-41d7-5cb8-887a-f78ea5639cec | textbox | US MH Number:
420f5660-1d4d-58e3-a28b-a7d421aeed84 | textbox | DS MH Number:
fc44bd16-d7cf-51f9-ada5-0cd48ece73de | textbox | Drainage Plugs used: Rubber & Aluminium Plugs, Rubber Blow up plugs
c012fc41-858b-519e-a0d0-affb474da9f3 | radio | Plugs Braced? | Yes,No
| checkpoint-no-value | Pipeline Material (non-concrete):
07d8b9bb-40e0-5a32-a657-a7d23b09f452 | textbox | Pipeline DN (mm):
91eb1047-12d4-5183-bc41-37913849777c | textbox | Pipeline Length (m):
e8768aca-e1d6-5de4-b096-8e0f175f1539 | textbox | Test Time as per Table C1:
| checkpoint-no-value | Prelim Checks:
e5bae442-52b7-5756-af13-9afa9107cc21 | radio | Line at pressure and maintained for 3mins? | Y,N
6508629a-5efb-5e1c-beff-2eeb4043b4c6 | radio | No Leaks Detected? | Y,N
| checkpoint-no-value | Start Pressure
38a97ee3-54f9-5156-9af3-6d4d30752dbc | textbox | kPa:
5ae2f1c4-c54f-5516-890b-a85b99df80af | textbox | Time: |  |  | am/pm
| checkpoint-no-value | End Pressure
a5d411dc-d93b-55ff-b843-24111200d87a | textbox | kPa:
4a0d7f1c-1a4b-5d5e-99dc-e70aaa88be9d | textbox | Time: |  |  | am/pm
| checkpoint-no-value | Pressure Drop:
9aaa9e4f-89b3-5885-b244-e9cf39942650 | textbox | kPa:
9895d553-ad87-5258-b443-92681f7ccfb2 | textbox | Duration of Test: |  |  | Mins
| checkpoint | Test Result
7e6d0b7a-4e90-5188-9d59-3a7f30140893 | note | Acceptance where the gauged pressure has dropped less than 7 kPa for the time interval shown in table C1 after the shut-off of the air supply.
ef638fcb-fbf9-51a0-afdc-cae4155f4ead | note | ○ The test length shall be acceptable where the gauged pressure exceeds 18 kPa (or not more than 7 kPa less than the pressure at the start of the test) for the time interval shown in table C1 after the shut-off of the air supply.
ec6d25f1-00d8-5c1f-b10e-ea4c80bab25f | note | ○ Table C1 is based on an air test pressure of 25 kPa (in excess of any external hydrostatic pressure due to groundwater)
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions for the purpose of this test
e0e0fc8b-d334-57e1-944d-c3748baf6026 | textbox | Name:
c44fff85-a269-5893-8ffe-f1c36833a5dc | note | Position: Site Engineer
272174f6-97b4-5d80-be30-47bce6b9065e | date | Date:
| signoff | SIGN
| checklist | CS-4074B - Low Pressure Air Test Record for Concrete Pipes |  | CS-4074B - Low Pressure Air Test Record for Concrete Pipes |  | d0b0bbb8-acac-4497-b30d-288379b839f1
| checkpoint-no-value | Details
2bc24c62-3743-51b1-98bc-7301f65f2261 | textbox | Work Area(s):
139705d8-9405-5c18-888b-6d27f0cf7999 | textbox | Sub Work Area(s):
35fa834d-63ce-5950-9878-7bc628a63cfe | textbox | Lot(s):
5c9830cf-fa86-5b77-b6f5-986795d941fe | textbox | Sublot(s):
7a1771c3-ff3c-56f5-a183-b8f4c9f48039 | textbox | Document Date:
16ae0449-b2ed-51e4-8bee-3411abf0de80 | textbox | Updated By:
ec396bc1-545b-5ba0-80aa-da97e730e1d9 | textbox | Area:
d57c094a-4c3f-5c2e-a3e2-bfbde47b42c4 | radio | Weather: | Fine,Overcast,Showers,Rain
fdd03647-931a-5cee-bcf1-70d553b48db7 | textbox | Location:
bb2cb1e4-5fe6-58f6-bfea-84c8aae00859 | date | Date:
c4124be0-9daf-5285-b81f-c38049aef862 | note | Personnel Conducting:
7a9dd5bf-6bd0-5ae1-b95e-b5a93d9e152b | textbox | Drain Layer:
f53a33f7-a3ce-5a02-8267-1fd1314556d6 | note | Witnesses Requiring Notice of Test:
7ea0dc27-83db-5f82-bb98-d5ed9ddd36b5 | textbox | QLDC Rep:
48e71688-0207-53d5-9aee-446449232385 | textbox | CPS Engineer:
cdd549eb-f40e-5544-9ac6-5c49a1d7a9d5 | textbox | Site Engineer:
| checkpoint-no-value | Pipeline
bbf69f6b-f867-5dce-a4fc-5d90524e3791 | textbox | Pipeline:
12d48aca-f412-5ba2-8d4e-4859e6c7ed9e | textbox | US MH Number:
0be386ec-6017-532a-88fb-c18a978a6ab5 | textbox | DS MH Number:
d14b3ef3-48aa-56f9-9ab1-c484f506b21a | textbox | Drainage Plugs used: Rubber & Aluminium Plugs, Rubber Blow up plugs
b1fab6a2-6225-5c30-b148-e7458ada7fb5 | radio | Plugs Braced? | Yes,No
| checkpoint-no-value | Pipeline Material (concrete):
daf9c8ce-db7d-5073-abb7-0940624d9c47 | textbox | Pipeline DN (mm):
699cd874-895d-5596-af08-25690e78e6a2 | textbox | Pipeline Length (m):
821b496e-54fd-5cab-880b-3fbb7b6731f0 | textbox | Test Time as per Table B1:
| checkpoint-no-value | Prelim Checks:
5e07332f-16d7-5290-9c71-3a4006faf1b6 | radio | Stabilisation period (at 10 kPa) for minimum of 15 minutes. Soap solution used to check plugs/fittings. | Y,N
d54d253d-ba7b-5026-a27d-8260d55d43e6 | radio | Line water soaked for 24 hours | Y,N
2e878e58-6147-53c2-9b5d-2271cb280b02 | radio | No Leaks Detected? | Y,N
| checkpoint-no-value | Start Pressure
2e215554-c013-5790-9463-a8f216a8cbca | textbox | kPa:
fa94420c-7db9-508f-8ed7-1762ba8e48d8 | textbox | Time: |  |  | am/pm
| checkpoint-no-value | End Pressure
ed325181-660c-5635-a2f4-f4b63cab2d65 | textbox | kPa:
3c56c482-0209-5e01-8d5f-f9dd787cc22b | textbox | Time: |  |  | am/pm
| checkpoint-no-value | Pressure Drop:
61eb01dd-b980-5ae3-b654-de061423cadb | textbox | kPa:
16d6c893-f45b-53e8-98eb-57be62bcbb9a | textbox | Duration of Test: |  |  | Mins
| checkpoint | Test Result
f4d8b110-b79c-598c-9a65-49dd5ae0a133 | note | Acceptance where the gauged pressure has dropped less than 2 kPa for the time interval shown in table B1 after the shut-off of the air supply.
f698cf87-9b55-5dd9-9382-177afcb96882 | note | ○ The test length shall be acceptable where the gauged pressure exceeds 8 kPa (or not more than 2 kPa less than the pressure at the start of the test) for the time interval shown in table B1 after the shut-off of the air supply.
55629989-73fc-52fa-86c3-4b9afb419da4 | note | ○ Table B1 is based on an average air test pressure of 9 kPa. Start pressure is 10 kPA.
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions for the purpose of this test
231897f2-96cf-5f9f-8bb0-e314b8a9affd | textbox | Name:
2733b816-5df0-5bb7-8ab0-cb3925cbdee9 | note | Position: Site Engineer
b3615c86-3413-57a5-b74a-63bf32940deb | date | Date:
| signoff | SIGN
| checklist | CS-4076 - Asphalt Laying Checklist |  | CS-4076 - Asphalt Laying Checklist |  | beb4df46-b62a-4a90-bcea-e380551fa81a
| section | Pre Laying (Tasks 1-7)
| checkpoint | Final confirmation job is ready (Site Handover, Job Instruction sheet)
| checkpoint | Undertake Emulsion Tack Coat Risk Assessment
ab25d602-3f29-59d4-b195-aeb9c63b2209 | note | By Who: Foreman
| checkpoint | Confirm job matches Laying Plan. If not, confirm and communicate variation with manager/ customer
398515c2-b193-55a3-b0b0-c3b43d7e3fc0 | note | By Who: Foreman
| checkpoint | Visual Inspection of site and stringlines completed as per Site Handover
| checkpoint | Daily Pre-Start Meeting/Hazard ID completed
| checkpoint | Approved Traffic Management Plan on site (implemented and effective)
| checkpoint | Vehicle Movement Plan
| checkpoint | Fences, walls, kerbs protected and environmental controls in place
| checkpoint | Pre-seal prep including offset of services/ roadmarking and protection of fixtures
| checkpoint | Laying Plan and Rolling pattern confirmed
| checkpoint | Paver setup. Screed checked at start of the day (level and feed controls functional)
| checkpoint | Stringline Tie in points to calculate required asphalt thickness
| checkpoint | Starting blocks in place (including compaction allowance)
| section | During Laying (Tasks 8-9)
| checkpoint | Tack coat applied and cured
| checkpoint | Mix visually inspected and the ‘in hopper’ temperature is within tolerances (contract-specific)
| checkpoint | Mat depth control (contract-specific)
| checkpoint | Stringline Tie in points for correct depth
| checkpoint | Rollers working to agreed pattern
| checkpoint | Shape and levels achieved as per specification
| checkpoint | QA forms completed as per Job Instruction form
| section | Post Laying (Tasks 10-11)
| checkpoint | Measure and record area, quantities and spread rate
| checkpoint | Post-paving subcontractors notified
| checkpoint | Collate QA forms and supporting documentation (refer Job Instruction)
| checkpoint | Post paving as-builts, coring, survey
| checkpoint | Plant de-established and off-hired as appropriate
| checkpoint | Roadmarking checked and completed
| checkpoint | Traffic loops / counter loops reinstated
| checkpoint | Traffic management de-established
| checkpoint | Services exposed, raised and painted
| checkpoint | (hydrants, valves, manholes)
| checkpoint | Job site safe and tidy
| checkpoint | Job site tidy. All AC piles picked up. Kerbs chipped and swept. Drains checked for AC. No footprints left in gardens/berms
| checkpoint | Transition joins/tie ins are tight and flush (no high/low ridges, no risk of plucking out).
| checkpoint | Longitudinal and fresh joins are all tight and flush (no high/low ridges, no risk of plucking out – water running freely across joins).
| checkpoint | Kerbs – height/finish requirements met across 100% of job (refer Job Instruction)
| checkpoint | Ride Quality – Drive over site - no bumps can be felt
| checkpoint | No visible surface defects (roller / stretch marks)
| section | General comments
| checkpoint-no-value | General comments:
7b350b9e-2519-56ce-9f26-45281e8d5a13 | note | Score Guideline (record comments/details)
bd5e81c4-d3c7-5802-a41d-8b110f53f12a | note | 1 - Not Acceptable (remedial/rework required, advise Manager)
a37d136d-201f-5697-b9cf-38fc5127c0d6 | note | 2 - Acceptable (no obvious problems, can be handed over to client)
afe886e0-5a52-5f73-a551-173e2893b80a | note | 3 - Excellent (entire job above standard)
| checkpoint-no-value | Job quantities/spread rate
d34c01a6-4266-5c4b-82e3-bc665c2578f4 | textbox | Hand lay (H), Paver lay (P)
16fb11d2-ff59-5b8e-a729-13f91af14e76 | textbox | Mix Type
b26223e4-42ac-521c-83cb-5cafe313fb39 | textbox | Area (m2)
0ccd3b27-3adf-5a33-bdd6-b3c080bedbed | textbox | Depth as per Job Sheet
a0fa4032-b559-5c7b-a7a4-163d6714fb53 | textbox | Tonnes Purchased
8f928c30-8cf9-5cbb-ba29-3b89b7322a40 | textbox | Wastage Tonnes
23fa7a60-72be-5809-9d4d-563b4593836b | textbox | Tonnes Laid
43aa292b-9ee8-5156-802e-10c110c5bb26 | textbox | Average Depth (mm)
3e722871-fe13-5a96-89e4-820493be7ac9 | textbox | Emulsion Primer (l)
4738022d-5131-521e-835b-9bda5def189a | note | Depth = Tonnes ÷ Conversion Factor (Density) ÷ area (m2)
| checkpoint | Signoff
f0ca86d2-a695-5db1-82c7-9ccead4861d3 | textbox | Signed by Foreman:
8a3c3654-dd0c-5747-b6ae-75fb22c739f6 | date | Signed by Foreman - Date:
3e666f62-220d-5420-aec0-c4ecb9067b89 | textbox | Reviewed by Manager:
df8cabcb-f5b7-5e57-b0cd-495bd8b8956e | date | Reviewed by Manager - Date:
| signoff | SIGNATURE
| checklist | CS-4077 - Light Column Installation Record |  | CS-4077 - Light Column Installation Record |  | 97786229-a699-4b5b-9ba8-d4fb97dcada9
| section | Details
| checkpoint-no-value | Details
249808da-d237-5009-9929-a0106541552e | textbox | Drawing No:
2de6866c-c10d-5b48-8aad-12ee2849b257 | textbox | Pole No:
| section | Column Foundation
| checkpoint | Confirm Light Pole Locations are as per latest Drawing revision and does not clash with other Services.
1cb45f60-e33b-578e-a8ce-ebbb6e4b39f4 | textbox | Initials:
e4710577-53f9-5ecb-bc77-806f7c71ac6b | date | Date:
dd18a04c-1e12-5565-8273-0dd2ddf0e954 | note | Comments: Design Engineer to approve if the location needs to be moved.
c13efc77-55a1-5c0b-a80f-36b40547dba8 | textbox | OFI No:
| checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
b1dae590-a47c-5aa6-bc30-44b6b4e68ec7 | textbox | Initials:
481f14d0-7cfd-5e02-9ee0-a719f1aa9687 | date | Date:
| checkpoint | Confirm Foundation Type i.e. Ground plant, Barrier mount etc.
64b9a11f-2b4e-5f43-bf3b-090de3bfdfee | textbox | Initials:
4065e3b0-e014-5a2d-9e05-61bf88f4c38e | date | Date:
| section | Excavation
| checkpoint | Pothole existing services within close proximity to the foundation.
984eb8f6-2c40-535c-9eaf-1f8547cbe933 | textbox | Initials:
5dec71fd-3225-5260-a9c0-1338400b7253 | date | Date:
| checkpoint | Ensure permit to dig is in place.
9712f4be-abe9-5c14-a40b-6b81a63a9b7b | textbox | Initials:
ea7b2890-a39f-5dec-ad74-0ffc5ef34f3e | date | Date:
| checkpoint | Check depth and diameter at completion.
4a1ada57-3ee7-5e43-bc48-d56c58e7f661 | textbox | Initials:
0b0e8585-5e5c-578a-a8bf-82e6eb9e44d3 | date | Date:
| checkpoint | Ensure base of shaft is clean and dry.
e7b03885-5760-5efd-9925-a28afa12ed0d | textbox | Initials:
c11ec448-e8f6-51ef-b556-c9318eb4394c | date | Date:
| checkpoint | If fixing onto barrier ensure bolts drilled to correct depth.
90bcc8db-6286-52d9-b55a-bbbcf2207140 | textbox | Initials:
5341e6f7-51b8-56ae-9294-26a50c6b80f1 | date | Date:
| section | Concreting & Backfilling
| checkpoint | Check the location, orientation, level and verticality of foundation prior to pouring/backfilling.
8fa206c6-cc66-5dda-bb3a-99104893e4ba | textbox | Initials:
0f0cee5d-4946-524e-936a-cc378d88e84e | date | Date:
| checkpoint | Ensure 1 x 65mm dia flexi duct is installed and taped off at each end.
663d90fa-1233-5d28-bc2f-62cae167a237 | textbox | Initials:
bb7057b5-673c-5d79-bd67-b84908715415 | date | Date:
| checkpoint | Design Engineer inspected the foundation prior to pouring
d3d276c9-b111-5b05-b4a5-05217e14484b | textbox | Initials:
dde11fc8-a82f-57e3-a03b-988902c23d21 | date | Date:
| checkpoint | Order concrete for shear base, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
4925ffd9-98ac-57da-868d-2e8e4a4b3766 | textbox | Initials:
454cae8e-f9ee-5009-afb0-0b911ed1fddb | date | Date:
43ec2133-6e69-54cd-9aea-3ae9d9e68fa7 | note | Comments:
758852f2-12bd-5b74-ab05-6b9420957828 | textbox | Concrete strength |  |  | Mpa
997c7f27-2c2a-5c03-aaa0-8739fe7f5977 | note | Attach delivery dockets and write the road light column numbers on the docket
| checkpoint | Suitable backfill material to be placed and tampered for compaction
7b795629-114b-515f-8716-7c58f8c0bf81 | textbox | Initials:
d4a5848c-efd6-5093-87f8-f2e569414915 | date | Date:
| checkpoint | Concrete/backfill placed to just below the shear base and concrete splashes onto column washed off.
60dfaea9-7a7b-5b81-832f-00535cbaa39b | textbox | Initials:
00191d65-92d7-5071-8b9e-7670c10c6256 | date | Date:
| checkpoint | At the completion of the concreting/backfilling check the foundation location, level, verticality and height from FRL.
f34645d2-c727-5d25-a3e3-6b03338b3afa | textbox | Initials:
29badc79-f8c2-5743-9488-31cbfa3fa3ec | date | Date:
c5aca3dc-d8ee-5f0a-96fd-3ba6288b45e2 | note | Comments: Foundation may have moved during concreting/backfilling
| section | Installing Column & Outreach
| checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting road light column
c0f3df34-e8ae-51e7-98cc-1166c9fdfbe7 | textbox | Initials:
f259e8ba-55f9-5669-a292-861091970711 | date | Date:
| checkpoint | Check road light column for any damage
ac66eb8c-448b-5bef-af6f-54398749319b | textbox | Initials:
6e09bfb1-d6b5-50c3-bce3-ae46b227fd89 | date | Date:
ee1869c0-f23c-53af-a7fe-825861429310 | note | Comments: Do not install if damaged
| checkpoint | Assemble Light column on the ground (protect column by blocking off the ground)
ca05abd1-47aa-583a-a0c3-41afca17bd6d | textbox | Initials:
547cf460-757e-5104-aa89-e3650eec091f | date | Date:
f6f921d1-118f-5c2d-99c2-c9c9f3324d03 | note | Comments:
851c32ca-c784-5436-9a61-17388248db2f | textbox | Column Type:
5371a149-1d7f-59eb-8056-02c7e0c2b54c | textbox | Outreach Type:
647f19d3-e56a-5b28-964f-f205eac7c8d0 | textbox | Outreach Length:
f119c576-9bf0-5bd8-9f46-9ddb4796790a | textbox | Luminaire Type:
| checkpoint | Check all bolts on shear bases have been torqued
ce2dbbdb-6126-5dcc-9878-de877cb81213 | textbox | Initials:
9f810774-0959-5042-8a64-f1d0353af045 | date | Date:
36af2da0-538a-51af-ae2f-ef054b53d5cd | note | Comments: Adjust column to ensure vertical
| checkpoint | Check orientation of road light column and outreach
768faafa-39a1-54fa-b025-7bb2085b6908 | textbox | Initials:
281402c3-142c-5e74-97c4-75ad210c75e6 | date | Date:
cae9a2fb-f5a0-56c9-8677-9bed35e5ce26 | note | Comments: Torque to 200kPa, check the bolt and slack back to 100kPa
| checkpoint | Check the internal wiring of the road lighting column. Ensure 2.5mm2 cables, 2 core NS
47891be0-d66f-5a7f-a5fd-8e8dd2f1b0ac | textbox | Initials:
7d482acd-4924-514a-96f4-50341be3dd4e | date | Date:
| checkpoint | Check Connectors & Earth Conductors have been installed
9db13d47-24c3-548e-b366-01ad18b930c4 | textbox | Initials:
5ffee646-3c82-59e4-8813-2d1f1be8f345 | date | Date:
| checkpoint | Danger Live Wires sticker on gear door
ebc3adaa-d86f-5c14-87f3-803e2eb50dda | textbox | Initials:
60a5d71c-8134-5e78-83d4-a8b5f2dc8476 | date | Date:
| checkpoint | Check that the Road light is installed to the design height above road level
16785c67-e7b8-5aae-9b2a-7be8ada4c475 | textbox | Initials:
07dc9735-ff25-5968-a40b-81ab3fcf5a44 | date | Date:
22e19d9b-210a-5d77-b28e-e46a9407e5a0 | note | Comments:
94925597-d73d-5931-ba45-5dc420332e15 | textbox | Laser Measurement:
ea3718ff-11fe-54e4-90fd-9701b65c29ab | textbox | Design Measurement:
1945acc0-d423-5671-901b-d3c3785c9e66 | note | Tolerance = +/-500mm
| section | Signoff
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
9b8fd8b6-d2a5-5467-baad-f9440f86708e | note | Position: Site Engineer
96025105-6a2a-58ec-b470-7eb7f7618270 | textbox | Site Engineer - Name:
e0b228fd-4cdf-5718-a388-455586849ca6 | date | Site Engineer - Date:
dddb08f4-a527-578e-8486-0fb7ecd3e931 | note | Position: Design Engineer
3ef3f619-dc85-51af-aaa5-47630fb51947 | textbox | Design Engineer - Name:
047e5444-de35-57bb-a504-99dff4de7bcf | date | Design Engineer - Date:
| signoff | SIGN
| checklist | CS-4078 - Signal Pole Installation Record |  | CS-4078 - Signal Pole Installation Record |  | ebf62ff5-210e-4c9a-bae8-ba0565fa8409
| section | Details
| checkpoint-no-value | Details
124f5993-fe2d-5cf4-b5be-d4219cbb0321 | textbox | Drawing No:
084a361d-3e77-5711-b3aa-97a63176d93d | textbox | Pole No:
| section | Pole Footing
| checkpoint | Confirm signal pole locations are as per latest Drawing revision and does not clash with other Services.
e6a10d41-7b0f-5e14-8fc8-33cbe7f97b04 | textbox | Initials:
b8248792-c436-544f-be90-585a5855c1fd | date | Date:
4832e8a5-84b8-53b9-b610-5b91ab811411 | note | Comments: Design Engineer to approve if the location needs to be moved.
| checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
69fba348-2fa6-57c1-b60a-08e770bec971 | textbox | Initials:
3e3fc71a-7cec-50af-a5b6-c1f49228221f | date | Date:
| checkpoint | Footing Type
aaef06af-73ce-51ff-ab80-bf8fb303e93d | textbox | Initials:
68e6f87a-1407-5b47-929d-48820ba413f0 | date | Date:
21d3193c-0021-5d23-846d-eb830cdecfec | note | Comments:
18d52426-efda-510c-868b-be6e5e611f54 | note | ○ RS 115
f1cdfb76-545d-5622-9759-fd6a0476d1df | note | ○ RS 168
| section | Excavation
| checkpoint | Pothole existing services within close proximity to the foundation.
416ca2fb-3639-5463-97a8-e54d7f1f8c54 | textbox | Initials:
1023ea56-a4e2-5c10-aa38-834ce326fea0 | date | Date:
| section | Socket / Flange Installation
| checkpoint | Ensure duct is connected to socket.
3af5d5e4-b727-59e2-bb26-b36040e02e7b | textbox | Initials:
470d9844-8772-5324-bdef-79de258d94db | date | Date:
| checkpoint | Design Engineer inspected the foundation prior to pouring
86f1b5fc-4728-5ef3-b2f9-c1fa007b9b8b | textbox | Initials:
e040e739-50b1-52d3-a240-bff596d89e0f | date | Date:
| checkpoint | Prepour checksheet completed
916fbe8f-97c1-53f1-8ecc-3ea4ef4564a0 | textbox | Initials:
a53b2fd3-ef28-5c3c-a09e-a61987a41042 | date | Date:
| checkpoint | Order concrete for footing, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
ff099841-d870-5eda-8c73-f234b52e9129 | textbox | Initials:
45d13fab-319f-58a6-8225-266b48b7ed5f | date | Date:
d9f89a33-24ff-53c8-91b9-3a0fed55d1a7 | note | Comments:
d62bb668-9324-5634-a58b-2f4403f2ae80 | textbox | Concrete strength |  |  | MPa
1f28c9ab-c1c9-5cf4-b157-00018d1290c8 | note | Attach delivery dockets and write the road light column numbers on the docket
| checkpoint | Use a stump pole to check verticality and height from FRL.
93c58b41-93f8-57b5-8ba4-20f1599b34cd | textbox | Initials:
fd7d37d8-bccb-55d0-b34b-b4ba7ad56f83 | date | Date:
| section | Installing Signal Pole
| checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting signal pole
0852b329-bc1a-533b-b5e8-f9ab2de3c274 | textbox | Initials:
bf392836-448e-513b-aa5e-52f43bad8a20 | date | Date:
| checkpoint | Check signal pole for any damage
7d5ae10e-4654-5597-8dd3-b0fa6b15a753 | textbox | Initials:
1067aa7a-c4a8-507e-937a-845697e4c53b | date | Date:
3881024d-0944-58f9-81f6-2c807dcd39b7 | note | Comments: Do not install if damaged
| checkpoint | Assemble signal pole on the ground (protect column by blocking off the ground)
00d34749-3c69-5bf8-8815-d2d1b9420123 | textbox | Initials:
322eb955-21dd-5d68-b9b2-de903303108f | date | Date:
5bf50e68-0e65-5d41-b122-10df33b02f36 | note | Comments:
b6c2469b-e2fb-525d-a809-5f982195c7e2 | textbox | Pole Type:
5141473b-8650-5189-8f14-977d668fb3a9 | textbox | P43 DWG:
| checkpoint | Check orientation of signal lanterns
d3a7e0e5-b2bc-5080-a74e-1a78709ef0c1 | textbox | Initials:
72ddcc8f-acc4-5c19-857f-e0b598bb8804 | date | Date:
| checkpoint | Pole identification completed
7629ea88-0c89-5d3b-8af1-ef9b0e211ffe | textbox | Initials:
e9df72fd-2655-5596-8c0d-77cbc18e2095 | date | Date:
| section | Signoff
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
efa0d589-f232-5a5f-8c83-77346c022f0b | note | Position: Site Engineer
6b096d6f-2ad5-5c20-94f4-7bf8627aa262 | textbox | Site Engineer - Name:
5fb1959d-2073-50a2-a6af-ed2d3ee6dc68 | date | Site Engineer - Date:
38598a0c-6f49-5f2f-8ce6-2f6ec6674a2b | note | Position: Design Engineer
adcf7903-b78f-532b-a220-bee35e4f6602 | textbox | Design Engineer - Name:
35495dec-3957-5498-9469-d8be7cdcf81d | date | Design Engineer - Date:
| signoff | SIGN
| checklist | CS-4083 - Bored Piling Inspection (to be used in conjunction with CS-4011) |  | CS-4083 - Bored Piling Inspection (to be used in conjunction with CS-4011) |  | 6baec0e3-02ac-46ae-aae8-8cb3e326b51e
| section | DETAILS
| checkpoint-no-value | Details
59aa3793-30f3-50b9-8b89-3edf3cdcf188 | textbox | Pile no:
72801494-dcff-58dc-8798-414c3e0bd9e9 | textbox | Address:
069f117c-16b6-5bb1-aa5e-045541da7000 | textbox | Area:
2f008aaf-4aa3-503f-910a-f0c86622b54f | date | Start Date:
8e6e3901-ae77-5906-9190-96cab370ce51 | textbox | Start Time:
57f8bb74-6426-57ab-a499-3bbc6e2ae7f9 | date | Finish Date:
26924288-55c6-5073-a9d5-4d7e7c505f86 | textbox | Completion Time:
| section | Piling Bore Log
| checkpoint | Pile Diameter (Circle):
62b16fb6-c469-5483-9486-cb415555f9b7 | textbox | Casing Length: |  |  | m
d329cd64-4044-5ad4-b74c-4a368101a507 | textbox | RL Ground Surface: |  |  | m
0fbcf773-c039-5001-8659-76dd3a19e644 | textbox | RL Top of Casing: |  |  | m
9763acdc-80ce-5940-a8a5-d48fc23c16eb | textbox | RL Bottom of Casing: |  |  | m
4fc7e046-0b15-55f8-8da1-470793de3ffe | textbox | RL Underground Water: |  |  | m
| checkpoint | RL Founding Levels:
b266db71-88ce-5074-b204-914dcf0ba53d | textbox | Constructed: |  |  | m
e080e398-1a4b-5eea-86fd-480c47998921 | textbox | Design: |  |  | m
| checkpoint | Shaft Length (top of casing to founding depth):
99cf5c67-a397-5966-9cb8-27aec5cc0746 | textbox | Constructed: |  |  | m
f1037be3-5126-56e2-80fd-5778b5bd50fb | textbox | Design: |  |  | m
| checkpoint | Pile Inspection (Site Engineer):
2e2879d0-f783-5aac-80df-35633bb28998 | textbox | Name:
baa34219-d1f8-53b5-97b9-2ed82e0aeb23 | date | Date:
adcc02c2-9474-5a69-87aa-d8433a70c707 | textbox | Time:
| checkpoint | Pile Inspection (Design Engineer):
1b063e6a-da8f-516e-aed0-cdb47b946320 | textbox | Name:
770b862b-bff3-522e-b260-0c9c61065e8d | date | Date:
95820456-3475-512d-994a-66c295ea252b | textbox | Time:
| section | Depth from GL
| checkpoint-no-value | 1 - Depth from GL (m)
5fb0f89c-e2bd-55fc-9fa1-2c7718892d89 | textbox | Depth from GL (m):
ec91d355-ff4f-5253-9683-7d738968e811 | textbox | Soil Description:
4586cd94-b89e-5908-b3b6-cc4c80eb91ae | date | Date:
2483f64d-b198-5923-962c-b971b87252b0 | textbox | Time:
| checkpoint-no-value | 2 - Depth from GL (m)
d949d79c-2bc7-5b44-91d7-530f7ea0c04b | textbox | Depth from GL (m):
e2d15935-b0f5-5d86-8946-57087978e053 | textbox | Soil Description:
f17240ac-6377-5205-9f55-cf915a33426f | date | Date:
0d75b4e9-0e06-5fc6-afbb-cd2ba72b5e8d | textbox | Time:
| checkpoint-no-value | 3 - Depth from GL (m)
fccb6616-c903-568f-b207-48c334761fc7 | textbox | Depth from GL (m):
df5ade37-f67d-50de-a467-9e0cdd33b4ad | textbox | Soil Description:
b42f9ab5-5026-54fe-8378-60d56b494f6e | date | Date:
91981a9a-ec8f-5760-bd0a-f764a663d6ee | textbox | Time:
| checkpoint-no-value | 4 - Depth from GL (m)
d1e75735-d7a8-5501-adbe-fb0d8f5cace1 | textbox | Depth from GL (m):
d7439868-c8f2-529c-9756-a4a13f3aab9b | textbox | Soil Description:
180e5f15-110b-5637-971c-51d5312764ac | date | Date:
7711b5eb-6628-5419-ba28-4d16d559385c | textbox | Time:
| checkpoint-no-value | 5 - Depth from GL (m)
2c59cd9c-0701-5462-88c0-c308fca736da | textbox | Depth from GL (m):
be0b3dfa-335d-5841-96f1-167593ecde17 | textbox | Soil Description:
e341d431-2b33-5c5a-8507-f573941f1dfc | date | Date:
84e21671-8fb8-55b6-a085-40098b9aec95 | textbox | Time:
| checkpoint-no-value | 6 - Depth from GL (m)
4bfb3f97-724e-5434-bc58-907bbc9bb188 | textbox | Depth from GL (m):
f1bd6362-54af-5af6-84bc-a388a4dd17ba | textbox | Soil Description:
d4e2121c-10ac-5e54-891d-dd0c47e5fd02 | date | Date:
5357c778-4d80-5ccf-b72f-81d375ff697f | textbox | Time:
| checkpoint-no-value | 7 - Depth from GL (m)
b07d9bfd-d63c-55bd-9657-2ffb36f3e44e | textbox | Depth from GL (m):
be4c3b4b-1414-5f5d-93a6-729167426de9 | textbox | Soil Description:
1b694eb9-dbf3-5ac6-8cb1-bf43ef28eb95 | date | Date:
eebbfdc6-6c25-58dc-9622-de6334b0279f | textbox | Time:
| checkpoint-no-value | 8 - Depth from GL (m)
580868bc-fc4e-53d5-aadd-dc7f6abd8b41 | textbox | Depth from GL (m):
68b830e8-ca0d-5c7f-ba25-b90210ee93fe | textbox | Soil Description:
2c5ff590-9a01-5dae-8970-801908a5a225 | date | Date:
c1ab54b8-c273-530d-879d-cf952c99a1a0 | textbox | Time:
| checkpoint-no-value | 9 - Depth from GL (m)
962c773e-1095-5020-a1c4-f3000f56f72d | textbox | Depth from GL (m):
a307f18f-4573-5061-92bb-589391bcf424 | textbox | Soil Description:
c7e3c690-56e8-5e8b-ad62-124233ee7b4f | date | Date:
08e09319-7964-5372-bfd6-7338e4aa4d3a | textbox | Time:
| checkpoint-no-value | 10 - Depth from GL (m)
0e3f6cfe-a90e-5ea6-a6d6-7d435692839f | textbox | Depth from GL (m):
f1d96b72-469f-51cd-a834-b8d2d884eb0d | textbox | Soil Description:
fb4fb900-f494-58e2-a90d-fb5aba5b955e | date | Date:
ca5f8f04-6378-56ec-9290-c76bc5fadc3a | textbox | Time:
| checkpoint-no-value | 11 - Depth from GL (m)
41672869-42c8-51cb-ba9f-d71896871e6d | textbox | Depth from GL (m):
4c899851-0a60-53fb-8241-af6b2b6c0e05 | textbox | Soil Description:
d03c9218-bd38-5c1b-ac50-db2a7441c4aa | date | Date:
ee901b44-93e0-5cd7-a32f-7e3eb29a626b | textbox | Time:
| checkpoint-no-value | 12 - Depth from GL (m)
29373faf-bbba-5d4f-9689-89d9cf7b4437 | textbox | Depth from GL (m):
e72d637c-21de-5eae-89e8-71d2bd9599d6 | textbox | Soil Description:
44b74bc5-da79-5807-9268-5836cfb1ccfd | date | Date:
98b9118f-924f-558d-8c58-4a9a4bdb36e8 | textbox | Time:
| checkpoint-no-value | 13 - Depth from GL (m)
2ce31fdd-954c-5025-9c17-aaa10c070eea | textbox | Depth from GL (m):
020aaae7-943c-5ac7-9699-c078611e2dff | textbox | Soil Description:
ca1d64dc-270c-522e-8f07-02216da1030c | date | Date:
605da5ff-28e7-5f0c-a60e-5087e9fc2624 | textbox | Time:
| checkpoint-no-value | 14 - Depth from GL (m)
28b28828-fd3b-5a2a-8fe4-153cbebf0382 | textbox | Depth from GL (m):
39575489-006d-5cce-a31c-8375a5521a46 | textbox | Soil Description:
9af32d86-be41-588c-bf43-e8d13e6e31f4 | date | Date:
584b570e-d396-5f1a-bec3-836228bbc2e4 | textbox | Time:
| checkpoint-no-value | 15 - Depth from GL (m)
53262ccf-ea78-5a75-899a-d549b3cc8295 | textbox | Depth from GL (m):
00b40d0a-6ad2-538a-861c-cf91a1108af7 | textbox | Soil Description:
773eac9c-5b60-54b6-b8ed-3a4af1f8147e | date | Date:
cb43a8ed-cd5d-5c59-b3e0-0771e30898b0 | textbox | Time:
| section | Signoff
| checkpoint-no-value | Comments:
| checkpoint | Piling Foreman Sign
5c8c703a-2dee-52e7-a01e-383bad3c71f6 | textbox | Name:
c01c5e2a-9482-534e-893e-edd1dd71b9c3 | date | Date:
| signoff | SIGN
| checklist | CS-4090 - Utilities Check Sheet |  | CS-4090 - Utilities Check Sheet |  | 78954d02-bc04-402b-af34-f24176af41bf
| section | Pre Construction
| checkpoint | Underground services checked
| checkpoint | Survey Set Out
| checkpoint | Correct materials and sufficient lengths on site
| section | Material Approval
| checkpoint | Bedding Material approval
| checkpoint | Hard fill approval
| checkpoint | Draw wired is 10 gauge galvanised mild steel complying with NZS 3471
| section | Construction
| checkpoint | Trench correct depth and width
| checkpoint | Subgrade check (scalas), min. 3 % CBR
| checkpoint | Bedding laid in trench to correct depth (100mm)
| checkpoint | Correct cable and duct sizes laid as per service drawings
| checkpoint | Gas provider trench approval
| checkpoint | Chorus provider trench approval
| checkpoint | Power provider trench approval
| checkpoint | Services laid with correct spacing
| checkpoint | Irrigation provided to all Rain Gardens and Garden Beds
| checkpoint | Lot connections laid 500mm into lot boundary
| checkpoint | Street light cables laid to pole locations
| checkpoint | As built service locations
| checkpoint | Draw wire in all ducts
| checkpoint | All ducts end capped
| checkpoint | Mag Slab laid
| checkpoint | Bedding covering services to correct depth (100mm over Gas, 50mm over all other services)
| checkpoint | Approved backfill material placed in 200mm layers
| checkpoint | NDM tests every 30m³ of backfill material, 95% of MDD
| checkpoint | Warning Tape 400mm below finished surface
| checkpoint | Irrigation Pressure Test complete
| checkpoint | Gas Pressure Test complete
| checkpoint-no-value | Weather
4ee64fc8-8e5a-593e-a4cc-bbb10d5e563f | button | Weather | Sunny (check plants not left bare root in sun), Raining (ensure soil is not saturated which prevents proper planting), Frost (No planting to be carried out until frost thaws out), Overcast (Good Planting condition)
| checkpoint | Sign Off - Site Engineer
00c0331f-5855-5ef0-95df-6a816bdc7954 | note | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
| signoff | Add Signature
| checklist | CS-4095 - Spunlite - Pile Foundation Checksheet |  | CS-4095 - Spunlite - Pile Foundation Checksheet |  | cd182cad-3f92-4615-94ff-4d700e580c6d
| checkpoint-no-value | Details
746b7afd-4b94-509d-8aea-66b0812242ce | textbox | Project Area:
9e03c454-99eb-57e6-8466-e5f67c8af5e1 | textbox | Supervisor:
7fd9f115-fc39-5f97-abfa-7ab1315f69ab | textbox | Site Engineer:
0df1a632-eaac-50eb-a5d6-e462345907ca | textbox | Pile Number:
69bd5f67-a817-59cc-86fb-c6e1ce2baaf0 | textbox | Location Reference:
539065a6-00a4-57b9-b777-78ed6fcad5be | textbox | Service Investigation:
| checkpoint | PRE-PILING SUMMARY
fead7324-bdc9-59c5-9c1a-6606f28e0d79 | textbox | Piling Foreman/Supervisor:
a6182f42-ed94-5990-a6aa-32aa6815d9c8 | date | Hydro-excavation Date:
a0c086bf-a196-56a6-a61f-9bfb21742e13 | textbox | Casing Length:
c67c453c-e03d-5c55-9323-a0c6641b5029 | textbox | Cage Length
f903b59b-d199-5d75-93dc-99602452578a | textbox | Design Pile Depth (min):
3acbe2a7-29bf-5eff-aea8-c9bfa533b23e | textbox | Design Pile Diameter (min):
0bb99db9-db7b-5b4c-ae8a-7abba6b8eb53 | textbox | Casing Diameter:
553bdc9b-1d3d-5f11-9724-11ca32ab92f3 | textbox | Cage Diameter:
102d80d8-7db2-5f4c-a6e1-d86f4c0530a5 | radio | Pole Type / Socket Type: | Standard – RS168 x 750DF,Catenary – RSe273 x 900,Short – RS115
| checkpoint | DRILLING AND PRE-POUR CHECKS
7ede1fe7-e688-5946-9c90-d5d5a159bc87 | textbox | Services check (depths and offsets):
f1ca1187-8f79-5e85-8c6c-c7d22574f4d3 | date | Casing Install Date:
1639156f-9b14-5870-97e8-30b6d5af24e1 | textbox | Piled depth:
0296dddb-848e-5ab7-8fba-c70772c6b2f4 | radio | Plug Type: | Soil,Concrete,Not required
c20bbe11-fc45-530b-abde-15d763dff80c | radio | Top of casing to FL check: | 90mm (Catenary),110mm (Standard)
ae3be759-2bbc-544b-9922-ce03575c8159 | note | Pre-pour checks
d22adaa0-7cdf-5cde-ada7-1b4289f5789d | tickbox | Speed form
0e3d94af-26f5-5187-b2e8-4558eb3b8cc7 | tickbox | Cage placed (75mm cover to reo)
b2486b83-03b7-568d-aaef-6107c42082df | tickbox | Socket set in place (check pole centre)
096b6eeb-61fc-5a36-b076-3e6e3babde2f | tickbox | Socket plumb check (pre-camber check for catenary poles)
1e1e015d-1f60-5a81-9e46-a61751c76b09 | tickbox | D16 starters installed
262b0444-adb6-5515-bc7e-9f0fc5229ebf | textbox | Concrete Mix Type:
bd467069-d9a3-5358-8901-bc1f4396cffd | textbox | Docket number
45e05e3f-7ccf-5a11-8c03-9c2e80d9eece | date | Tremie Pour Date:
| checklist | CS-4096 - Bottom Driven Pile Record |  | CS-4096 - Bottom Driven Pile Record |  | 90b55a99-5b4b-4c24-8637-d4aaf4c44e5c
| section | DETAILS
| checkpoint-no-value | DETAILS
e1c21a45-e738-5484-b3c7-bce3c112cf38 | textbox | Project No.
f5491bbf-e532-504a-a3cf-e4f502c382e0 | textbox | Drawing No:
502de51d-aa45-56ef-bd38-c4e7bd6bcd97 | textbox | Concrete Grade: |  |  | MPa
4d210420-aca4-5a7a-a92a-8d60470d6ae8 | textbox | Pile No:
c7505824-ad2b-5224-8f16-07b2c71a3e9b | textbox | Diameter: |  |  | mm
97befcd5-028b-5d85-a6fa-909a0d022837 | textbox | Pile Depth Required: RL:
2d1a9759-1b49-577b-9a25-46f470c6e4d4 | textbox | Pile Depth Achieved: RL:
2601e78b-d46b-5807-a502-baa8fc1789bd | textbox | Ultimate Bearing capacity required: |  |  | kN
0b1b0025-8b57-5871-8765-f7ccac1b1d3b | textbox | Ultimate Bearing capacity achieved: |  |  | kN
0543a629-8383-544c-851b-d740667349bf | note | (Note problems experienced during construction on a separate sheet and attach)
| section | Set Up
| checkpoint | Piling Platform Compacted & Level
b7a113ef-ec2f-538f-bdee-aafad574d7fa | textbox | Initials:
6b59f187-8318-5422-a377-53e5dd0e0374 | date | Date:
| checkpoint | Permit to Dig Obtained
6813012a-edb1-53d0-8ee7-72863a923483 | textbox | Initials:
79566dbe-d951-52ba-ae40-7253df17a36f | date | Date:
| checkpoint | Pile Set Out & Checked
90c356cd-deec-556a-a0f2-141feb419496 | textbox | Initials:
56e7619f-3657-5272-a5f1-63c765ffacd1 | date | Date:
| checkpoint | Erosion & Sediment Controls in place
c9515638-523d-5319-bbac-5897458c4e8d | textbox | Initials:
9d5badb5-680b-5ab8-8575-cf7bcd1a0e53 | date | Date:
| section | Driving
| checkpoint | Design Engineer Notified
577eb630-f709-59dc-9b4f-ad95de1396f6 | textbox | Initials:
d46c859f-442f-564d-b3b0-926812f9dbf3 | date | Date:
| checkpoint | Hammer drop measured within 500mm of pile set
553742fa-8a52-51d0-aa8a-12356a3ce3c0 | textbox | Initials:
f68020d9-7d5f-5917-b239-48f67556a17c | date | Date:
| checkpoint | Damage observed
560a2fed-f20b-5f03-adfc-5109e76d09b1 | textbox | Initials:
ce7823f3-a67a-55f2-873f-5d6baf2fcd93 | date | Date:
| checkpoint | Pile Driving Record attached
d2da737b-3444-52a6-b385-722c2cfdc891 | textbox | Initials:
6e68adbd-c1ec-5eda-b60c-e7b22a251a58 | date | Date:
| checkpoint | Rebound card attached
80156ab3-8976-5abc-8045-9a12d3ac6a88 | textbox | Initials:
0ab535f6-01b0-5060-8a69-26d0339df8d5 | date | Date:
| checkpoint | Last blow less then mean set over last ten blows
633b8642-b725-5c46-8505-118cf12928bc | textbox | Initials:
013d9a2b-58ce-5985-96b3-5b9ba55e99ce | date | Date:
| checkpoint | Any Interruptions to driving
7329eaa0-010d-5e9f-b3f1-a658c9ea61be | textbox | Initials:
f248684f-1d95-53f8-b0ec-c444c9dc186b | date | Date:
| section | Reinforcement
| checkpoint | Reinforcement Content, Grade and size
1d6973a1-6d95-592f-8ed2-fe3ddc7f0f89 | textbox | Initials:
1d0a096e-6078-5c5e-bbb7-a2646c1572f9 | date | Date:
| checkpoint | Placement, tolerance, clearance
edca19f2-d556-5f89-9a3e-d7c29a852df0 | textbox | Initials:
574dbad3-704b-5582-8c07-37ce9facb432 | date | Date:
| checkpoint | Rigidity and cover spacers fitted
2176f7a4-2c96-5bb6-b94c-5ec1c0ea21c9 | textbox | Initials:
d479e0fa-27c6-5921-8037-ffe2dacc24c6 | date | Date:
| checkpoint | Clean steel
8c41fd65-4e42-5baa-9c4a-ee4f48001801 | textbox | Initials:
26e14af6-d4be-5984-a152-50b5458b4f47 | date | Date:
| checkpoint | Lap location and lengths
ce05bf3a-16ed-5092-9f79-c9332b59d5c7 | textbox | Initials:
c0cd5b9d-1dc8-5e30-85fe-f9d976c98fdc | date | Date:
| section | Splice Welding if Applicable
| checkpoint | Visual Scan 100%
f4b37199-f832-5d7e-b92b-7f9338b56bb4 | textbox | Initials:
374bb9ea-1d9e-573b-872c-d874cc5461ca | date | Date:
| checkpoint | Visual Examination 100%
46d6d156-5c1b-5b78-a23c-8cc8b49f0298 | textbox | Initials:
825ec529-86c6-5e12-be79-d5a3ddaff449 | date | Date:
| checkpoint | Radiography
59cbe31f-a121-5064-b132-cf4558927f5f | textbox | Initials:
7c8e0b75-1054-5aa8-8af3-3fc13f6d114a | date | Date:
| section | Pre Pour Check
| checkpoint | As-Built Survey Complete and Within Tolerances (50mm in plan, 2% rake)
ff082d0d-ac2a-5112-b377-544b67f649fb | textbox | Initials:
833d03cd-1c18-5f93-8873-fd97566d3ff5 | date | Date:
| checkpoint | Correct mix ordered
41297d04-d2a6-5d01-8e51-610aa6229cbc | textbox | Initials:
deaf5104-994c-5286-a75b-a65c591e0786 | date | Date:
| checklist | CS-4098 - Bottom Driven Pile Card |  | CS-4098 - Bottom Driven Pile Card |  | 0bb50945-c377-46ce-a952-f269dda10da0
| section | DETAILS
| checkpoint-no-value | DETAILS
8adbe2b0-be40-57f5-8929-df35c661bc16 | textbox | Project No.
1a297583-c94d-555d-a9d2-d67f3446dce7 | textbox | Pile Type:
671c3990-a2eb-508d-a5e6-c44549776e27 | textbox | Yield Stress: |  |  | MPa
7119a28f-e327-5d98-8157-f42ec85215c5 | textbox | Capacity kN (calculated):
b68762be-790d-56b4-becc-35274ff52568 | textbox | Capacity kN (required):
69cb9681-40be-55d5-8eda-aadea40cbcaa | textbox | Temporary Compression (C): |  |  | Mm measured
f1810efb-6e0d-50b4-aaff-b84c13ec68dc | textbox | Set mm (measured):
979cf3d1-3b38-5b58-a610-7b7268d8cb96 | textbox | Set mm (required):
1d699f13-b686-5ccd-b2b9-d782537f42bf | textbox | Hammer (mass): |  |  | tonnes
f45a5bfd-320c-5c73-a08d-910806fe73d1 | textbox | Hammer (drop): |  |  | metres
f69ce5a0-12e7-585a-a8a5-4a99c6410f0d | textbox | Hammer (Efficiency): |  |  | %
54f5721f-e282-5f95-ba34-949c35c64792 | textbox | RL top of Pile (1): |  |  | m
1d2d1c9f-7f70-5b7f-bcb2-dfd905eb6a93 | textbox | RL top of Pile (2): |  |  | m
c75b77a9-509f-5ec0-b2c8-36f329a83f81 | textbox | Pile Length: |  |  | m
| section | Pile Construction
| checkpoint | Pre-Drive / Bore / Jet
e1551dae-2fc6-59b2-b8c4-c7e4a66ce5b0 | date | Date:
ce5651f2-be30-5246-8bc6-a137e1f5468b | textbox | Start Time:
2eefd7ba-55fb-5a9b-8e98-2195b7f4452d | textbox | Finish Time:
1d85cc74-822f-5b23-9e1d-4131f367ecf7 | textbox | Hrs:
23cacb85-d1c7-5ffb-becc-acc17b27fdde | textbox | Conditions:
| checkpoint | Drive No. 1
4f561ddc-6d30-5502-a957-5e0b4f3a36ff | date | Date:
6519b0d5-860e-5791-9158-cd382a911b02 | textbox | Start Time:
dab68389-129d-5b98-9963-a0c8d02524df | textbox | Finish Time:
6d1e315a-7388-5eca-9d43-582b52eae1f8 | textbox | Hrs:
71846ab7-8fd4-5955-ac13-4fdda160e07b | textbox | Conditions:
| checkpoint | Drive No. 2
43cb7179-46d1-589a-aa2e-8c3731507ab4 | date | Date:
3fa59600-feca-5a4a-90aa-b7e38c0ae440 | textbox | Start Time:
9707bcf2-8960-5859-b3cf-1b2ff2fb405a | textbox | Finish Time:
02c6642a-db61-5184-b5a5-c665707f8b3f | textbox | Hrs:
a9ce3f66-75ad-5dde-bf44-797596a39676 | textbox | Conditions:
| checkpoint | Drive No. 3
1c827f49-c318-5a8d-8a24-134888975be0 | date | Date:
e774cf63-6cf7-5b29-aa8c-382b158bd89a | textbox | Start Time:
5a84a170-59ef-552a-b40f-80771b8e5fbd | textbox | Finish Time:
a823b8d4-25a0-51bd-b260-205eb8b5f671 | textbox | Hrs:
ac523ad4-7c9f-54e9-931c-5850d6f71c3b | textbox | Conditions:
| checkpoint | Re Drive:
7975760d-4fad-5883-a048-d66b0b7be421 | date | Date:
fbc7a32b-9915-5ade-bec8-1725aa03286f | textbox | Start Time:
3996de73-16ee-5d36-98cc-f39521e50ef4 | textbox | Finish Time:
21db50b0-8268-54d0-9545-d7b2001a5410 | textbox | Hrs:
7cb461d1-0962-59c4-8367-db38e67e07e4 | textbox | Conditions:
| section | Obstructions Encountered
| checkpoint | Obstructions Encountered:
d0951fc7-f15d-5899-a41c-621a1f74555c | textbox | Type:
1b911ca7-977d-5a19-a60c-042990678eab | textbox | Depth:
3e069d63-7ed1-512e-99d5-3cb2d7338ee9 | textbox | Action Taken:
| section | Penetration
| checkpoint | Penetration (1 m):
30733ddd-3649-5782-bc4d-161d75145241 | date | Date:
eff45dc0-6b87-50a0-b902-76fb2ed79bf2 | textbox | Time:
908d98d0-bf77-5030-99a9-a18572f4afd8 | textbox | No. Of Blows:
| checkpoint | Penetration (2 m):
00c1026e-6951-54bf-a288-f9d15cc32c3e | date | Date:
a1527a68-602d-5262-a21e-53e1d1d4bf28 | textbox | Time:
cdde67a3-be89-566e-8194-e8cf837a3b67 | textbox | No. Of Blows:
| checkpoint | Penetration (3 m):
8bb25850-e743-5c24-8714-88d9cc4f8d73 | date | Date:
62387102-1fe7-5350-bc2c-411e433cd9a0 | textbox | Time:
37528fff-2d2e-584d-9171-3ef8dcef95b5 | textbox | No. Of Blows:
| checkpoint | Penetration (4 m):
f87d538c-e40b-5779-9654-4ee450bb8897 | date | Date:
2c8064ca-54da-5a6f-89e1-245b19dfa497 | textbox | Time:
4a1f2341-0778-5132-b747-92f50281650f | textbox | No. Of Blows:
| checkpoint | Penetration (5 m):
62ec8174-5349-541c-b6cf-23225a702805 | date | Date:
dba5437d-b8f1-5e38-8c6f-a61fbe8d3a73 | textbox | Time:
5b572ac4-d3b7-58d4-beb7-8b36fa3db367 | textbox | No. Of Blows:
| checkpoint | Penetration (6 m):
0fbcf11a-7d03-5c8a-9998-06b2e468b2e1 | date | Date:
9f170fcf-59c6-505b-82e1-e86433023efb | textbox | Time:
b973d15c-3381-5b76-a8ee-6b1671ac9a67 | textbox | No. Of Blows:
| checkpoint | Penetration (7 m):
ec232c16-6a90-58c6-b596-c40ff4d184cc | date | Date:
c4180661-8752-51bc-8bb2-88dd22bb8b27 | textbox | Time:
dacff850-fed4-5fee-a22b-30e44d73f289 | textbox | No. Of Blows:
| checkpoint | Penetration (8 m):
605a065d-7df9-5a53-ad87-3d90098b57e2 | date | Date:
92fedec1-09c8-5216-b220-0bdc5a771059 | textbox | Time:
467a08b4-7ef0-59f8-8333-9bee9f660fa6 | textbox | No. Of Blows:
| checkpoint | Penetration (9 m):
f6a9f6bb-bdee-5bed-ac9e-17eb09959029 | date | Date:
7d0e3e18-eaf0-576f-9e21-1a0e9b1a62d0 | textbox | Time:
d4f4d74f-af3b-5374-9fdb-3b000369e2d6 | textbox | No. Of Blows:
| checkpoint | Penetration (10 m):
d8528d24-25e2-5792-bcb5-bffc804ce6a6 | date | Date:
b6e11ee3-10dd-5aad-86a9-b5190f8c277f | textbox | Time:
3b838c26-fed0-5515-b525-34b60a491d6c | textbox | No. Of Blows:
| checkpoint | Penetration (11 m):
52d963aa-eb2c-54ca-b855-be3dcddf500c | date | Date:
c3a405a0-a1f8-5d7f-9466-6e7172c9532f | textbox | Time:
4b381039-d592-5211-a690-68810d0e9c6a | textbox | No. Of Blows:
| checkpoint | Penetration (12 m):
362e1a47-e09e-512b-8755-c45ae2e6b41e | date | Date:
1329f83a-3238-5a14-ae8f-264defe15d94 | textbox | Time:
beb327ea-26a7-57f4-b146-6bf2d12e5f60 | textbox | No. Of Blows:
| checkpoint | Penetration (13 m):
0590d268-a8b3-504b-824f-fc886b4db180 | date | Date:
83ee8bc5-7f21-5e36-9f86-795fd5aa475a | textbox | Time:
7c03f3c8-2b46-552d-bb30-97522b94ba6c | textbox | No. Of Blows:
| checkpoint | Penetration (14 m):
e485604f-255e-5c48-9a2d-e99c4ebaefa4 | date | Date:
058a94a1-cf97-56c0-9833-0d98184ffacb | textbox | Time:
4c6b2f88-cad2-532c-83bc-7df57d3001a4 | textbox | No. Of Blows:
| checkpoint | Penetration (15 m):
6b88eeb5-a2f4-5f11-a3c7-df13460f9a9c | date | Date:
8660e853-33c7-53bf-abdd-94cb7d99b32c | textbox | Time:
34240e49-5d54-5ed2-b7cc-a3dc1b47d6f1 | textbox | No. Of Blows:
| checkpoint | Penetration (15.5 m):
508f68d6-c4c5-5862-81e9-432dbb96b644 | date | Date:
7e78f254-0810-5b79-97fb-c38979eb2e5a | textbox | Time:
0b082392-1353-52ca-9b38-d7b43a891608 | textbox | No. Of Blows:
| checkpoint | Penetration (16 m):
3cc064f3-2da7-5056-b7e7-2ca7264a3d43 | date | Date:
87731744-981e-577b-8ca4-6b3c678bb951 | textbox | Time:
3416a8b4-f317-5e95-8da8-ee750468d5d1 | textbox | No. Of Blows:
| checkpoint | Penetration (16.5 m):
d4029bf0-b562-5d15-a250-37f3805e3fb1 | date | Date:
0695d9e3-969b-5ad1-a4cf-2d3a1655707d | textbox | Time:
5e3fd34d-5f53-5a38-a6eb-a37f4125c2e0 | textbox | No. Of Blows:
| checkpoint | Penetration (17 m):
c193c761-8c68-5374-9444-e8deff241f19 | date | Date:
118057f5-2e0a-5489-a13c-c897d0b33a04 | textbox | Time:
1256f360-337b-59ed-90a5-45bfd388e0f5 | textbox | No. Of Blows:
| checkpoint | Penetration (17.5 m):
d021896a-4196-5c18-b593-ba4151786bde | date | Date:
979c22ce-97ed-50a6-86ef-1d9fb094e20b | textbox | Time:
e5bf035d-49bf-5ced-b19b-ee4fecfec97d | textbox | No. Of Blows:
| checkpoint | Penetration (18 m):
de61762c-d15e-5e73-a8b8-88b6a88f964e | date | Date:
1223fcee-483b-5d0a-9338-220e5cf4af3d | textbox | Time:
f031bc1f-06a2-5932-9e00-4aba1caaee9d | textbox | No. Of Blows:
| checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
1cb59a59-af85-5963-9f43-282f480d5b91 | textbox | Name: Site Engineer
ac03ef07-8354-5c68-8737-3f2a6ba9c940 | date | Site Engineer - Date:
621219e3-7ba2-5e42-aacc-b17c86ceb603 | textbox | Name: CPS Engineer – Geotechnical
fec96a31-286b-589c-8622-f5476c84b845 | date | CPS Engineer – Geotechnical - Date:
80dce77c-5688-5f03-b042-1b3c1c54d324 | textbox | Name: CPS Engineer - Structural
22f7b3fd-8099-583b-9251-1bb7233a1ba1 | date | CPS Engineer - Structural - Date:
| signoff | Sign:
| checklist | CS-4099 - Watermain Disinfection Checksheet |  | CS-4099 - Watermain Disinfection Checksheet |  | b55c632b-9603-43f7-b7c6-0e4ebf597ae4
| section | DETAILS
| checkpoint-no-value | Details
83eac77d-a10e-54ba-b1a8-496ae47d6c62 | textbox | Work Area(s):
a3217c23-40e2-58bb-b1d9-11a39002e082 | textbox | Sub Work Area(s):
d5e68965-3472-5e39-bf22-efddac8f99db | textbox | Lot(s):
b15425c7-e65a-5641-9407-8157e551cbb7 | textbox | Sublot(s):
09e510cc-cf92-5279-af2b-83064fd1310f | date | Document Date:
11843db5-1a15-5e98-9b21-3c14d8f42805 | textbox | Updated By:
| checkpoint-no-value | GENERAL INFORMATION
506759f0-5d7f-58af-8887-6f4e5274c287 | textbox | Contract No. or Resource Consent No.:
7a6e34b3-038e-552f-8df3-cca13bd90f2f | textbox | Contractor:
9ae2f80d-5bef-5716-baa0-8f1c9414ba3c | textbox | Site Supervisor:
6f183817-24a7-5930-a19b-2bdc5096e830 | textbox | Site Location:
f2d0d026-f6f7-5ece-a5f1-0abdd6eade3c | date | Date:
eaeb41e3-b9e1-517d-95bd-efbe59304d76 | textbox | Time:
cb23d758-0a3b-5d69-ab89-423fee114754 | textbox | Pipe ID:
08d0fdea-38dd-51b5-879c-3c0f91152b63 | textbox | Chlorine Type Added:
f3589ddf-f5f7-5ecd-a944-2674911bb15e | textbox | Pipe Diameter:
53065a2f-e30a-598b-91f6-db7af4fed8f8 | textbox | Pipe Length:
| section | TEST RESULTS
| checkpoint-no-value | Table 1 Acceptable Laboratory Test Results
72d3bf6c-ec98-5690-8083-d77c6825576f | note | Parameter ¦¦ Acceptable Value
28732d85-1131-56f6-9b73-d6e9e1e4d53a | note | – – – – – – – – – – – – – – – – – – – –
7d522a3e-10f7-5c3d-951e-26f80fe50804 | note | Residual Chlorine ¦¦ Between 0.5 and 1.0 mg/l
f16d3226-ce05-5c8f-abdd-9c97359e1031 | note | Turbidity ¦¦ <1 NTU
5c56cb1c-bf48-511b-a6b8-ae4134b5ee8b | note | E. coli ¦¦ <1/100ml
| checkpoint | Test Point (1)
425fff5e-36ee-570a-80dd-b92cc4076012 | textbox | Test Point:
30b07283-cedc-5d20-b707-8c1c73913164 | textbox | Initial (mg/l)
c660cb61-d768-5b6c-80dd-8f8bb99feff0 | textbox | 24 Hours (mg/l)
| checkpoint | Test Point (2)
5ef96d2c-0780-5e66-afa9-22d4cbe9582f | textbox | Test Point:
dc1d81dc-f9c0-5150-a016-79c952a869f1 | textbox | Initial (mg/l)
0d9b5c12-d878-5a5c-8a47-59650077d678 | textbox | 24 Hours (mg/l)
| checkpoint | Test Point (3)
b5a8531c-750e-5e02-a01d-2bd321827dad | textbox | Test Point:
f8f3ea7a-6078-5032-b97f-6aed0ff85574 | textbox | Initial (mg/l)
2b3ae6f0-dac8-5f5d-a63e-b2dfe16c433c | textbox | 24 Hours (mg/l)
| checkpoint | Test Point (4)
067b17c0-c57a-549b-b5dd-1ad65fd6a5e5 | textbox | Test Point:
89dc3ab6-662b-54e3-aa25-b0a74b10349c | textbox | Initial (mg/l)
2f4d6670-6512-5907-8983-0d8b0a62f9b7 | textbox | 24 Hours (mg/l)
| checkpoint | Test Point (5)
06f77f59-02be-55a5-b907-b4ddac7572a5 | textbox | Test Point:
999fd985-ec1e-5ce8-b6fc-f62a3885232a | textbox | Initial (mg/l)
70545087-8e92-5a6b-9666-54ebcece4fd1 | textbox | 24 Hours (mg/l)
| checkpoint | Test Point (6)
57a9d08d-0a6b-59ff-8043-c68f51266971 | textbox | Test Point:
69f3836f-c320-50c0-b26d-ab412f790e6d | textbox | Initial (mg/l)
0a884dcc-66fa-5861-9e7e-55d321d8c795 | textbox | 24 Hours (mg/l)
| checkpoint | Test Point (7)
889fe097-513c-503a-bc38-8ae258aaad05 | textbox | Test Point:
6404c17f-4d2d-531d-8f33-7594174082fe | textbox | Initial (mg/l)
0673ddec-a4df-5ca5-ab3a-c7dd7b5322d5 | textbox | 24 Hours (mg/l)
| checkpoint | Laboratory Results Acceptable (Attach)
c1fa0e9f-5330-56af-b978-742a8d5ccf00 | textbox | pH Reading after 12 hours:
| checkpoint | Signed:
2aa6d580-84ea-5533-bb09-820a3295a1bf | textbox | Print Name:
| signoff | SIGNED
| checkpoint | Signed CPS:
aafbb568-c63d-5ff2-b5e9-47ce3b6e9e86 | textbox | Print Name:
| signoff | SIGNED CPS
| checklist | CS-4100 - Subgrade Approval Checksheet |  | CS-4100 - Subgrade Approval Checksheet |  | b0b52cb6-ff20-48ff-a5dd-13d1e918080a
| checkpoint | Area completely stripped of topsoil & organics
22f1b41a-7f2e-5a38-8a68-838796a34476 | textbox | Initials - Design Engineer:
0f0242c0-fc11-51b6-97db-314624f95cb1 | date | Date:
76c7cd2c-8637-5d2d-af79-51971b4d9356 | note | Comments:
b2aaffb7-0348-58da-be3b-4e61fed2a372 | textbox | Chainage Start:
b9eec41c-1065-5598-a9a4-6bfbf1efecd6 | textbox | Finish:
131c3094-f9ff-56de-b523-e05b71e6ef9c | note | Photos of area are taken & kept with QA records
| checkpoint | Topsoil strip topo survey carried out
4f9c6697-f29c-53f1-97c9-526802a93975 | textbox | Initials - Site Engineer:
e4279bbc-da97-5eea-a53a-e1fd7772a0f3 | date | Date:
1ce29c49-1c1e-54ce-a66b-9f9f42522261 | note | Comments:
9f82d474-33fe-5b3d-b7ae-b617938032ad | textbox | Survey receipt #
| checkpoint | Scala Penetrometer Test carried out
0caec590-5fe2-51f3-a91c-42d286da6678 | textbox | Initials - Site Engineer:
dd65d6f3-ed98-50ca-9509-5b1e14045278 | date | Date:
d37b8262-1423-5a3d-903b-9575c49b10e6 | note | Comments: To the correct frequency & results captured on the earthwork lab testing register
| checkpoint | Proof Roll carried out & witnessed
8d097cbf-8086-57fe-a29f-4642702238de | textbox | Initials - Design Engineer:
c60ea4c5-c71b-5de0-9a9e-34ba9b4b7963 | date | Date:
e3182ff3-13f9-58b2-bb4f-a0c865283959 | note | Comments:
9b1da30c-a097-5d94-ad0c-c43aa4810b11 | textbox | Equipment used:
| checkpoint | Did Proof Roll pass
bd41df85-6089-5820-81f8-ae8360fc4153 | textbox | Initials - Design Engineer:
5bcfa9cf-97da-559b-bb4c-6dd9cceb7ced | date | Date:
577a6f14-0194-59b8-bb9a-61073a0d89ff | note | Comments: If yes moved to #10, If not undercut required continue below
| checkpoint | Undercut area is to be marked out onsite by Design Engineer
604057e9-3a25-54ab-a784-4373b9f6d77e | textbox | Initials - Design Engineer:
8ec1a189-d594-51be-8d6e-3ef935a82c69 | date | Date:
| checkpoint | Undercut to be inspected before backfilling commences by Design Engineer
4fd64929-e633-52f0-8197-41e710bb068f | textbox | Initials - Design Engineer:
2684c7ea-e1e7-5f34-81ec-cb219d7ef83e | date | Date:
2dcc71c2-9f42-5207-9f3c-e8f88a63551a | note | Comments: To determine that all undercut areas are prepared to the specifications
| checkpoint | Undercut area to be surveyed
07df737b-828e-585b-b0d9-823f4ffa27f6 | textbox | Initials - Site Engineer:
e14bf673-e09f-5f7f-b5b3-2c584bcde719 | date | Date:
ba726da4-2b14-5417-9590-09c61b65acf1 | note | Comments:
d1642d63-a637-5aad-8ca2-11239b9f6f54 | textbox | Survey receipt #
| checkpoint | Backfill material is approved to be used and is tested in accordance with specifications
bf5740e3-ca0a-556b-9298-d3c0f60f8ef4 | textbox | Initials - Site Engineer:
7b583b6b-fafc-52f9-be36-ac5e64fab8e4 | date | Date:
ad3cd54e-193a-57a5-90e5-a650d09ef1f1 | note | Comments: Lab Test Result register
| checkpoint | Site is prepared for bulk filling to commence
450efe08-b43e-5045-8ebb-2c20048da63f | textbox | Initials - Site Engineer:
080be7b5-7194-5a51-ad54-96ae190bcfdc | date | Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
348d0ddb-8a75-5aa8-997a-e77f7ebeb7e6 | note | Position: Site Engineer
f030357d-770c-54b9-b216-5c49f9637cd9 | textbox | Site Engineer - Name:
f7f5af3b-9165-5bc6-b9d1-437e9e7730c1 | date | Site Engineer - Date:
39838c88-fdd8-5656-86f5-912b8441366b | note | Position: Design Engineer
7ad3cefe-fabb-5c23-83d5-26f09e2f9bde | textbox | Design Engineer - Name:
46a15695-7424-5da2-a60f-4c68d65075d7 | date | Design Engineer - Date:
| signoff | SIGN
| checklist | CS-4100a - Subbase Approval Checksheet |  | CS-4100a - Subbase Approval Checksheet |  | 4fc6edcb-2972-4fc8-8184-4fe3b88628e8
| checkpoint | GAP65 material mat testing - PSD(Grading), Sand Equivalent >=25; and Plasticity Index<8 (IANZ Test Reports required)
dad77b8a-afba-59fa-a53d-75533bdebc17 | note | ○ Note 1: Test frequency as per ITP
7bc1a5d8-dd03-5804-a268-e961288c26b3 | note | ○ Aggregate material compliance for Subbase stockpiles – CPS Hold Point
c5c4dbd9-178a-5a69-b9b3-c18866090f8b | textbox | Initials: CPS / Design Engineer
fc8a8883-28f8-51cb-bce1-a0d035cd19c8 | date | Date:
b3b01d0a-fb8c-518d-ac7b-d3acb6b6da6a | note | Comments: Material Test Report – Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab Test for MDD at OWC
| signoff | HOLD POINT
| checkpoint | Subgrade final trim inspected, and a proof roll witnessed by CPS/Designer – CPS Hold Point
350090fd-416e-53dd-95a3-66f677cf8a26 | textbox | Initials: CPS / Design Engineer
5520fdc1-06e6-55d2-8899-10bbcb013ed5 | date | Date:
4add1324-b7f4-5b12-81e4-94b1dc6963bb | note | Comments: Visual Inspection
| signoff | HOLD POINT
| checkpoint | Subbase Compaction - NDM tested (Mean>=95% of MDD; Minimum>= 92% of MDD) – IANZ Test Report required – CPS Hold Point
cbe4039f-0e09-5d6c-9e70-5f2334bcad21 | note | ○ Note 1: To test every 30m of road per lane, staggered at 15m
b224eb82-13a4-53ef-bce4-3e6837b70184 | textbox | Initials: CPS / Design Engineer
acd1abdf-9c55-5d7e-940d-653ed2320571 | date | Date:
c49868f8-6718-595c-8ffe-515571b97690 | note | Comments: IANZ Test Report
| signoff | HOLD POINT
| checkpoint | Saw cutting – proposed Saw cut line to be inspected by the Engineer – CPS Hold Point
b745a7ce-cf05-570d-b151-ef24718b8abe | textbox | Initials: CPS / Design Engineer
f7908cd4-5856-5acb-9e18-03519ac31678 | date | Date:
8c71081f-f6db-5d70-856f-92a813e69869 | note | Comments: Visual inspection – Project specification 6.6. Photos provided
| signoff | HOLD POINT
| checkpoint | Surface shape check prior to Basecourse construction - stringing line checked and no point of the surface shall vary more than 10mm over a 3m long straight edge – CPS Hold Point
7367d667-e8cd-5a2d-95d0-5ef3a6f7cf74 | note | ○ Note 1: To check every 10m both parallel and perpendicular to centreline
3e08785f-00aa-5aae-9fb8-d292dff16878 | textbox | Initials: CPS / Design Engineer
950e856c-4536-5d1d-abee-86dd22848506 | date | Date:
c0f8a32f-9101-5822-a6c6-716b6fe7d838 | note | Comments: Measurement Stringing line Record Sheet
| signoff | HOLD POINT
| checkpoint | Subbase as-builts: Width, Levels and Crossfall within tolerances:
9c3fa2e6-4115-5b6b-9e78-72d282214a97 | note | (a) Width: Unconstrained: –20 mm +100 mm; Constrained: Zero
97fbd82c-a01b-5132-b86a-76418b126ad6 | note | (b) Level: -25mm +5 mm
713302ea-a6bc-598e-94e0-8579e7128dc9 | note | (c) Crossfall: no depart from the design crossfall by more than 0.5%
f0901d8b-d2b8-53c3-8ee2-380626c59630 | note | ○ Note 1: To survey 1/10m intervals
1b85b6c9-cfb5-50c1-92b5-d887dc250c56 | textbox | Initials: Site Engineer
5f684db6-4314-5bff-932d-3b72febde5d7 | date | Date:
0955b3a7-434c-574b-940d-4c69d69e3795 | note | Comments: Survey Record Sheet
| checkpoint | Final Inspection - a proof roll witnessed by CPS/Design prior to basecourse (Deflection no greater than 10mm, and no visual cracking or deformation remaining after pass) – CPS Hold Point
891bcb4d-89ac-5a35-a826-5c1144fd853b | textbox | Initials: CPS / Design Engineer
e32dad61-70f6-5e89-beaf-bf9faa9be236 | date | Date:
51c91594-4fa8-5c80-9e86-1fde9038ceec | note | Comments: Visual Inspection
| signoff | HOLD POINT
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
fee3cd76-d91c-56db-99f4-e19a15f6e14b | note | Position: Site Engineer
7d0bc603-2a91-584f-a340-c14740445f48 | textbox | Site Engineer - Name:
8f8c37da-221c-5702-9335-b52cdb00c6b3 | date | Site Engineer - Date:
800527e2-5de3-561d-88d0-67845b6ac0fc | note | Position: CPS / Design Engineer
62e4f3de-1abe-5848-8091-3fa102cad7dd | textbox | CPS / Design Engineer - Name:
194df51f-449c-56ff-92c7-14e750d732b0 | date | CPS / Design Engineer - Date:
| signoff | Sign:
| checklist | CS-4100b - Basecourse Approval Checksheet |  | CS-4100b - Basecourse Approval Checksheet |  | cdf100e4-dfe1-4a6d-a203-b3e35ae5030c
| checkpoint | Material production testing (1/source and at least 1/3 months):
3d2b1110-9503-5044-b16a-817a67a781f6 | note | – PSD: NZTA M/4 Section 4.2.3 Table 2and 3;
41eb930c-5b6c-595a-9dbd-14d48c5ec73f | note | – Sand equivalent: >=40;
c70649f1-485f-5170-8ab7-b3ad11e21bad | note | – Clay Index (material passing 75µm): <=3;
85549dc1-8abb-52b5-aefa-5a7565d5cbcd | note | ○ Plasticity Index (material passing 425µm) :<=5
51d64e70-6f56-57c0-9ec6-83dbb3fb97b6 | note | ○ Aggregate material compliance for Basecourse stockpiles – CPS Hold Point
a7071819-48ca-59ca-8381-ddfd0c96f434 | textbox | Initials: CPS / Design Engineer
bb9374a7-08f1-5331-ad16-01ef00b999e6 | date | Date:
f9d4093b-d9be-5077-95f6-6a62b87dc9c2 | note | Comments: Material Test Report – Aggregate shall comply with TNZM/4
| signoff | HOLD POINT
| checkpoint | Visual inspection for any defects on the subbase – CPS Hold Point
ccb6e976-4360-51e7-88ad-61a72d77debd | textbox | Initials: CPS / Design Engineer
03e1d47f-c7db-51b4-9d53-efc4cde7073d | date | Date:
5893a188-8d18-5f94-b809-085c596c6ed2 | note | Comments: Visual Inspection
| signoff | HOLD POINT
| checkpoint | Basecourse Compaction: - NDM tested (Mean>=98% of MDD; Minimum>= 95% of MDD) – CPS Hold Point
773cccd1-cb9b-573b-abab-a73315e5d6a0 | note | ○ Note 1: To test every 30m of road per lane, staggered at 15m
9dbe9343-d47b-5adf-b975-1ec2fa9ada6b | textbox | Initials: CPS / Design Engineer
5eb2ac4d-9d2a-5b6b-9f20-4dfb36315a95 | date | Date:
dcd55c0b-a5f9-52a3-b53e-6c1402cd39d2 | note | Comments: IANZ Test Report
| signoff | HOLD POINT
| checkpoint | Basecourse Benkelman Beam Test (only when specified on IFC drawings):
9db5bc1b-2861-5c6e-8ddf-7593258d565d | note | ○ No more than 5% of the deflections exceed 1.4; No single deflection exceeds 1.5mm -- check moisture content if high deflections are obtained.
45aaa502-2b81-5cee-bef7-35e9ecf8be85 | note | ○ Note 1: At 10m interval in each traffic lane- staggered
3441342b-ee9a-5e6a-937d-3547810528d4 | textbox | Initials: Site Engineer
c1203ef6-6fec-5b46-b63d-3515415c1383 | date | Date:
36696e61-fda6-5807-9e7a-e92233cbfb60 | note | Comments: Benkelman Beam Deflection Test Record – only if required
| checkpoint | Basecourse FWD: Testing to only be performed post Benkelman Beam deflection testing based on results. Not required for chip seal roads – CPS Hold Point
f999e157-1831-5455-8a00-bfd26507e695 | note | ○ Note 1: At 20m staggered intervals in each traffic lane
eae522c7-3865-595a-bbd4-fdc6046b60fe | textbox | Initials: Site Engineer
ec2951c0-9992-5d16-aca6-19616c45e8f7 | date | Date:
1bf548ee-53ae-5025-a910-70705478d298 | note | Comments: Only if required
| signoff | HOLD POINT
| checkpoint | Basecourse surface shape - stringing line checked and within tolerances:
1dd1f34c-b412-5c04-8fc4-050fa9eb9b5a | note | (a) Level: with concrete channel and at or close to the lip of channel –5 mm +5 mm; other locations -5mm +15mm (Survey Report attached);
f6c186c1-2b76-55ba-99ab-c83db96c61ff | note | (b) Crossfall: no depart from the design crossfall by more than 0.5%;
db8fdeb0-41e3-5892-99ee-0d4daa560ab7 | note | (c) Manhole lids must be in line with the crossfall.
5feaccc8-72e3-5435-86eb-1000ebbe596d | note | ○ Note 1: 1/10m intervals and across manhole lids – CPS Hold Point
3102205e-65ee-593d-8dfb-3e036fe128df | textbox | Initials: CPS / Design Engineer
e4d8eb81-6d5e-5ae9-bae4-a5c2a1d9c1cd | date | Date:
0044e013-3432-5c9d-a453-3f6d8090b082 | note | Comments: Survey Record Sheet & Stringing record sheet – no point of the surface shall vary more than 10mm over a 3m long straight edge
| signoff | HOLD POINT
| checkpoint | Final Inspection - Prior to chip sealing or asphalt surfacing – CPS Hold Point
47999f3b-62c1-54ed-9bf3-57a36bbb8145 | textbox | Initials: CPS / Design Engineer
c3dc1aba-e28b-5071-9f2c-d3ab593f0c34 | date | Date:
4d2caf99-07a7-5b27-9f13-48de07b58a40 | note | Comments: Visual Inspection – the large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
| signoff | HOLD POINT
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
b7cb5b67-82e6-5b44-ac2a-9dde019c82b0 | note | Position: Site Engineer
78301d2a-d67b-578c-87ef-78abde26eeef | textbox | Site Engineer - Name:
6f3d706e-8cf7-5638-b979-3464e131b0ba | date | Site Engineer - Date:
f359b41c-5326-5581-a752-8205a3d0fd8a | note | Position: CPS / Design Engineer
ce6580cd-d5bb-5182-802e-c1e768e0e950 | textbox | CPS / Design Engineer - Name:
5572acbc-4aed-58a2-95c6-61d6c6cc0e8d | date | CPS / Design Engineer - Date:
| signoff | Sign:
| checklist | CS-4101 - Water Main Line Record |  | CS-4101 - Water Main Line Record |  | ebd39e27-5415-4c0b-85de-da053049d5a4
| checkpoint-no-value | Details
ab3de763-9c0f-54d5-a0a6-d364dbf90739 | textbox | Drawing No:
97246357-bf8e-58b4-926b-7e4f3b8b438c | textbox | Rev No:
3e2c2229-6580-5636-aa83-0785c405b641 | textbox | Chainage:
| checkpoint | Set out by surveyor & handover to Site Engineer completed
62f0a881-7425-5a8e-b599-7c9c18f8a78d | textbox | Initials:
cce95abe-4546-55b3-b21a-29d6191faea7 | date | Date:
| checkpoint | All existing services exposed and identified before trenching
fd53d545-0345-521c-a3cd-c080734f44fb | textbox | Initials:
99d50591-04a2-59a4-8b88-7adf6ac9eff8 | date | Date:
| checkpoint | Trench line and profile as per IFC drawings and as set out by surveyors
0a2007d1-ee16-585a-96d2-195a740eaf2a | textbox | Initials:
91071a7b-bc5c-5553-b776-c68deb2da249 | date | Date:
| checkpoint | Trench must be made safe before any person may enter the trench
8cb09c1d-5d68-54c3-ab22-9ed89443901f | textbox | Initials:
2722ff4c-5d3b-5aeb-b1c9-532318bfb06b | date | Date:
5bbe1e12-c08e-592b-98bd-9eaf7b306e05 | note | Comments: Trench depth > 1.5m must be shored or battered.
| checkpoint | Base of trench inspected and tested if required.
060c0f61-c770-5f1b-ba8b-81cc5c8a5b77 | textbox | Initials:
55e8064e-e03a-5982-8bd8-44c885411748 | date | Date:
24160c56-44a3-5e15-8c6b-8b88488ed337 | note | Comments:
9e1c0efd-8859-535b-b09a-e88838f806ea | radio | Under cut required | Yes,No
| checkpoint | Bedding is to be tested
bc6c79d7-b698-53cd-9879-3fbac32a0a82 | textbox | Initials:
51e31283-33ac-549f-a6bd-23f0c894385d | date | Date:
| checkpoint | Pipe is laid with appropriate clearance to other services
b8d9e5a6-7b39-5ef6-9a40-a62c7ac53886 | textbox | Initials:
4ba16fcf-89e0-504e-ab47-868dbc4632e2 | date | Date:
1a739d74-899b-5177-80a3-51d92e1d1d76 | note | Comments: See “Table 5: Clearances from underground services”
| checkpoint | Survey to asbuilt top of pipe before backfilling commences
68abf43d-9943-5732-a83b-fb97cab9dc00 | textbox | Initials:
d77ef568-1ecf-501d-a3ea-e4fa822c206d | date | Date:
| checkpoint | Ensure warning tape and/or magslab is laid at the correct cover over the new pipes
ec1ddf5a-fe10-53f5-b9b4-0a010624607c | textbox | Initials:
17b899fe-ae71-59b4-800e-db73597e057f | date | Date:
| checkpoint | Ensure backfill material is suitable and un-contaminated
6e91806b-d206-54d0-9e32-be947e4b1494 | textbox | Initials:
b701351f-97c2-52e1-92df-f5fb049f7a3a | date | Date:
| checkpoint | Backfill compaction tested at every __mm lift
794992d5-2d7f-57be-9c2b-16f118a4fa8e | textbox |  |  |  | mm
2d25f8ed-aa20-5b60-8f65-f7dad0f032aa | textbox | Initials:
1cf681cd-7d03-555b-8efd-ca4b26f13a65 | date | Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
f5616414-c342-53b8-96c9-fc5dd105d83f | note | Position: Site Engineer
812680f8-603b-51a9-a2a6-f4edfee387cf | textbox | Site Engineer - Name:
48f20e80-6d47-5258-91b2-fd0ba00d869a | date | Site Engineer - Date:
ac10e55b-028f-5faf-8f51-1f03ca188bee | note | Position: Design Engineer
19e92298-9895-5c8d-bd7f-d27627aadcfe | textbox | Design Engineer - Name:
d1b278a2-c198-5ece-be7a-2f6d8449e851 | date | Design Engineer - Date:
| signoff | SIGN
| checklist | CS-4102 - Pressure Rebound Test |  | CS-4102 - Pressure Rebound Test |  | f042a2a3-fd4e-4ed9-8ed1-0ae344ce458b
| section | DETAILS
| checkpoint-no-value | Details
8692735f-1f32-5fa1-911d-f761dfef13ef | textbox | Contract:
d419001b-4ed3-5fe4-8ae3-7ac1118c98c4 | textbox | Sub Work Area(s):
2d12ee94-0e18-532f-bf6d-99d40abf24ee | textbox | Sublot(s):
2503ad36-e12a-5fbc-893b-5985911400d2 | textbox | Work Area(s):
76895275-42b9-5bdf-81a7-bf0b0969c497 | textbox | Lot(s):
979c7f24-2a36-5521-9868-b2eb01241b8d | date | Date:
| checkpoint-no-value | Personnel Conducting Test
3dd01c39-dae0-5e13-815f-6a9e00c61b20 | textbox | Drain Layer:
f87cc9a4-e012-591f-bff4-13f73784a94e | textbox | Site Engineer:
6a12e515-95c6-560a-94c3-f495bd214c08 | textbox | CPS Engineer
| section | Pressure Testing Record Sheet For Pressure Pipelines
| checkpoint | Pressure Testing Record Sheet For Pressure Pipelines
cdae0b1a-857c-557e-8284-95e4fdac7cc1 | textbox | Pipe Material and Rating:
57b952a1-4eb7-5b70-a19d-d9bd308184c9 | textbox | Test Length (m) L:
8790a58d-8966-50d7-82eb-84bc5314c3c9 | textbox | Pipe Internal Diameter (mm) D:
92aed249-d384-5329-ad8c-3f1aeb86dfae | textbox | Depth of Pipe Below Water Table:
0dfe5a60-2c76-503b-b1e9-a6ba041f4514 | note | Attach Test Section Sketch (show heights, air valves, gauges and filling points)
1ccb427b-12c6-5050-afd0-ce9cef484b22 | textbox | Ambient Air Temperature: |  |  | °C
d0554e86-68fe-5df9-8ebf-9c2ae3c91f61 | textbox | Water Temperature: |  |  | °C
| section | Pressure Rebound Method
| checkpoint | Standard Test Pressure
55c650a7-ec4c-5f9b-a58e-727b900f0dbc | textbox | Pressure Applied: |  |  | kPa
| checkpoint | Preliminary Phase
16c966d8-3afb-5ca3-aea3-05db3abe2483 | note | P60 > 70% STP
3622e030-6f42-5dff-89d1-c40277000878 | textbox | Acceptance:
| checkpoint | Air Volume Assessment
fa946e68-0a37-57bd-ad20-7585c7371520 | note | 1. Reduce pressure by 10%-15% STP (ΔP)
a7664b3c-bdb8-5dc6-a256-c708cc0db2ca | note | 2. Measure water volume bled out (ΔV)
34ac6d46-72fd-533a-9ee8-ad238581f824 | note | 3. Calculate ΔV max allowable
07199629-ded5-52b2-ba93-36cbd681597c | note | Where: 〖∆𝑉〗_max⁡𝑎𝑙𝑙𝑜𝑤𝑎𝑏𝑙𝑒 =1.2𝑉∆𝑃(1/𝐸_(𝑤 ) +𝐷/(𝑒𝐸_𝑅 ))
4c0c30e4-dd47-5c7a-9d0a-755cd04aa0e5 | note | Acceptance: ΔV < ΔVmax allowable
cd68ce22-4873-5035-9c95-953d0c789c0e | note | – – – – – – – – – – – – – – – – – –
d60f9554-ae49-537f-9cf6-e4804f1b86b1 | note | Air Volume Assessment Parameters
e4c5aaf2-545b-586a-a4b1-4478cebd0f4f | note | – – – – – – – – – – – – – – – – – –
a2a485d0-0884-50cb-9ef1-7da001aa831e | textbox | Nominal Size (mm):
4730ce39-5387-530a-81ee-2f79eee06fbc | textbox | Mean Bore (mm):
5c9961bc-e279-5b81-903a-e6a6e8f0d41f | textbox | Tested Length (m):
e554faba-c503-536a-9037-ec346402bc8c | textbox | V (m3):
6d6c77b9-286c-53d2-a446-63c22abdd5aa | textbox | e (mm):
41ce9492-9509-5ef5-8987-032ae65f63fc | textbox | Ew (kPax103):
d070c8d3-4a03-5bd8-a120-1b1ded10f42f | textbox | Er (kPax103):
67cf9f5f-2d1e-58ed-854d-4a238b9154c2 | textbox | ΔP (kPa):
2ad3d82d-3312-5985-b890-603590ecea75 | textbox | ΔVmax allowable (L):
7362c0b1-5e1e-5be3-bb20-84c2739896c2 | textbox | ΔV (L):
db31472a-f386-5685-80ee-22ea8b9385a7 | textbox | Acceptance:
| checkpoint | Main Test Phase
674d4131-4f38-5717-b65a-a15ce41c859b | note | Observe and record pressure for 0.5 - 1.5hrs
3ac59707-d1e2-555b-9330-b6e7fc79b43e | note | Acceptance:
2e2fd257-968e-5acf-a875-956bbd63babb | note | 1. No failure of any thrust block, pipe, fitting, joint or other pipeline component present
db84421c-f92a-5e49-b693-234fb6873a16 | note | 2. No visible leakage present
646b7991-d0d4-57d4-bfd6-efec607c362a | note | 3. Pressure rises or remains static for 30min period
af5ec85d-30fc-5959-9fe3-cef5b6f0be1e | note | 4. If doubt exists extend pressure recovery to 90min where pressure drop is to be < 20kPa
| checkpoint-no-value | Comments:
| checkpoint-no-value | General Methodology Details
a02808df-0fb5-5549-ae38-40841b5494dc | textbox | Process for removal of air
85a1b965-3653-55a2-8553-859576dd68f5 | textbox | Details of water meter
3002a4da-08aa-57a5-9fcd-d329b7eecfb5 | textbox | Details of pressure gauge
07ff6dd7-43c2-5b6b-b39b-b6c7277e8899 | textbox | Details of pump
3ec96cc5-8e86-51cb-8338-c53f7c7518b3 | textbox | Water source
972bce81-2cf5-5316-880d-e59f3b345d13 | textbox | Water Disposal
| section | Signoff
| checkpoint | Checked and Signed by Site Engineer
129aacaa-0e84-549c-b624-9d29130521b5 | date | Date:
| signoff | Signature
| checkpoint-no-value | Site Photo Records
| checklist | CS-4103 - Water Loss Test |  | CS-4103 - Water Loss Test |  | 56a03c2a-94a4-4935-b27f-f2d3c161a078
| section | DETAILS
| checkpoint-no-value | Details
288afc6b-9ac6-54d0-a4ee-6299c6e692dd | textbox | Contract:
58d75d67-5b8a-5505-9a0a-390eee8f9da3 | textbox | Sub Work Area(s):
ab8ab6ae-211d-5b24-beaa-82d92de567db | textbox | Sublot(s):
acb4534d-ba28-5ebb-87b2-dfe98df22772 | textbox | Work Area(s):
49886100-6e2b-5d87-a5e9-889709e2e1c6 | textbox | Lot(s):
0882c5cf-6246-5b52-96af-45869a1a1977 | date | Date:
| checkpoint-no-value | Personnel Conducting Test
b5b2c2ad-1592-51d8-b70d-08cbaff051e5 | textbox | Drain Layer:
4969c795-aca5-50e9-a520-001e4ce56038 | textbox | Site Engineer:
821b85da-9c9d-576d-b042-3ff3a10ea11d | textbox | CPS Engineer:
f6e3b130-0712-521e-b73b-f72b2f79651e | textbox | Qualification:
| section | Pipe Material and Rating
| checkpoint | Pipe Material and Rating
7d403dc1-7490-5a7a-9862-dd51f6463537 | textbox | Pipe Internal Diameter (mm) D:
8f5704a5-ac18-572e-8a0f-2868877dc530 | textbox | Depth of Pipe Below Water Table:
ab15845d-032b-551d-8d68-8bbe4bb21173 | textbox | Ambient Air Temperature: |  |  | °C
cfe19bb9-d33c-5da4-84fe-96ee61b189a9 | textbox | Water Temperature: |  |  | °C
| section | Water Loss Method
| checkpoint | Water Loss Method
beb6a27a-6f47-5dad-8960-176abda3f474 | note | Procedure
d2e8b394-9644-519a-a04b-79a7893602fc | note | 1. Remove air from pipeline
7428bfbf-9253-57b8-b279-9642e5e7110c | note | 2. Apply test pressure to pipeline
0d8a91e1-3caf-5904-a3c5-0c261699c5d3 | note | 3. Allow pressure to settle for 12 hours
c9c1747c-c64a-5cf9-83c0-75a02096463b | note | 4. Re-apply and maintain test pressure for 5 hours by successively pumping a sufficient amount of water
f06001fb-dbe2-5caf-8a6b-89d18fba0fb5 | note | 5. Measure water volume required to maintain pressure between Hour 2 and Hour 3 - V1
7e2ed1d2-f818-592b-8e51-6e45ecfd8e5a | note | 6. Measure water volume required to maintain pressure between Hour 4 and Hour 5 - V2
cca26ad7-86a5-5021-a951-efeb301376fc | note | 7. Calculate:
da01a1a6-ed98-5b6c-9aaa-5dcc48811457 | note | Where:
b174b57c-9e8b-5c6f-a867-6b16908783a9 | note | Q = allowable make up water, (L/hr)
8a85b745-907e-5a5c-bc9e-7a4f6a388bc6 | note | D1 = nominal diameter of pipe size #1, (m)
d07d18c4-4b4c-5236-a6b2-d05f65ec153c | note | L1 = length of pipe size #1, (km)
548edc9b-3815-549a-b6a8-77e8c0848c6d | note | D2 = nominal diameter of pipe size #2, (m)
a8f6f256-fd44-5736-8dc8-63b7e66c4bd2 | note | L2 = length of pipe size #2, (km)
30636b82-01ea-56ec-bcae-c96cef930834 | note | D3 = nominal diameter of pipe size #3, (m)
45b60ae2-c8da-5577-90ac-15d25ae9ab55 | note | L3 = length of pipe size #3, (km)
d02027c6-62c5-5319-82d5-11f523680da1 | note | H = average test head of pipeline, (m)
7a27e895-436b-599f-81ac-8c6d04e5dfb9 | textbox | Standard Test Pressure: |  |  | kPa
8ee20d50-8b6e-573f-86f5-fbeee3572438 | note | – – – – – – – – – – – – – – –
db8512c1-5da9-5fca-9e2f-0b84bf0f1f9b | note | Water Meter Readings
07283fc0-9c27-5fcd-bca0-5dee984cc116 | note | – – – – – – – – – – – – – – –
c8577294-a2b3-5a31-ad7c-b633d636cddb | note | Test Time ¦¦ Time of Day ¦¦ Reading (m3)
eb3dbaeb-0b5b-57c4-8a32-992e8ef272f9 | textbox | Start ¦¦ 0:00:00 ¦¦
9340be2c-d35f-579e-a84c-edf5f29f321f | textbox | 2 hr ¦¦ 2:00:00 ¦¦
975f10e2-949c-5dc6-8d11-52f6f2de845f | textbox | 3 hr ¦¦ 3:00:00 ¦¦
a6fb76ab-25a1-53aa-a4a3-21e6fab87883 | textbox | 4 hr ¦¦ 4:00:00 ¦¦
478f5d3a-ce8e-5365-93e4-aa596d4a8c2a | textbox | 5 hr ¦¦ 5:00:00 ¦¦
bc883463-253b-5395-bcf6-fcd9771792f8 | note | – – – – – – – – – – – – – – –
23fd416e-32db-5945-a047-99f867875ebc | note | Water Loss Method Parameters
f325dff0-be55-55ef-b927-af97faafc67d | note | – – – – – – – – – – – – – – –
9c5c0a0d-bb73-5f97-9853-3286801cf31e | textbox | L1 (m)
4e4270c8-837d-540b-b7b5-a93b408429ca | textbox | D1 (mm)
f1d307fb-ddf5-50d5-9252-9a2be207b2ae | textbox | H (m)
363bfdf1-5fe6-5724-8211-35f5af625880 | textbox | Q (L/hr)
1a3a20b1-4e2a-5d7b-8a7a-c7f775e7739b | textbox | V1 (L)
bba63ead-be7b-553c-bf5a-026bbcae452f | textbox | V2 (L)
fef85cf2-de25-5627-8bb9-4be2950ddf99 | textbox | 0.55 V1 + Q
9a28a968-3991-5be0-8847-4bed3fb7b8be | textbox | V2 ≤ 0.55 V1 + Q
| checkpoint | Acceptance
6996848b-820c-5463-81ce-f69dacb4e12e | note | The test length shall be acceptable where:
44c9c0e9-26c5-5f17-99e0-38135e76ad8a | note | 1. No failure of any thrust block, pipe, fitting, joint or any pipeline component
8187dea2-4334-57f2-ad5a-a827e338ef87 | note | 2. No visible leakage present
7a800a43-63b7-52a6-b0b2-ebcf5100bca6 | note | 3. 𝑉_2≤0.55𝑉_1+𝑄
| checkpoint-no-value | Comments:
0b02acc0-60a9-5a79-9eeb-3169464775c6 | note | Attach Test Section Sketch (show heights, air valves, gauges and filling points)
| checkpoint-no-value | General Methodology Details
dc8d4b48-0164-55af-b706-23229ad6f082 | textbox | Process for removal of air
2f869da7-a377-539a-a9c8-2a35eeb80070 | textbox | Details of water meter
78920c02-8dff-5273-8be4-06c99e04c3dc | textbox | Details of pressure gauge
c4124bd2-1f17-5c67-9f4a-948005797504 | textbox | Details of pump
3ba4dab3-6423-5a88-95c7-4ebe5a51b518 | textbox | Water source
ead9cc03-c21a-5012-8e82-b59bde12827c | textbox | Water Disposal
| section | Signoff
| checkpoint | Checked and Signed by Site Engineer
b1138729-581d-5000-a819-7ee52d26b4e1 | date | Date:
| signoff | SIGNATURE
| checkpoint-no-value | Site Photo Records
| checklist | CS-4105 - Road Lighting & Cable Installation Record |  | CS-4105 - Road Lighting & Cable Installation Record |  | 2aca6d17-ab11-471d-b24e-d75aa9449a80
| checkpoint-no-value | Road Lighting Trench & Cable Installation Record
f174cabc-e960-5aad-b42b-56caffad2aa1 | textbox | Project No.
578c2c10-63e4-5abc-b095-aa3b4b397ec9 | textbox | Drg No:
aa6b8374-3aef-5c22-a896-ec6e2146284b | textbox | Rev No:
a6373b20-b0bd-5a67-8eda-cb7dfd4736f3 | textbox | Chainage/Road Light No.:
| checkpoint | Road Light Locations set out by Surveyor.
e8a61bea-bf20-503e-beb1-9bde5fdbabef | textbox | Initials:
f138a6f6-fd44-5021-bbd6-291f053a0cfa | date | Date:
cb47faae-a6a7-5155-a31d-a9fd05db7ec7 | note | Comments: Consistency with Construction Drawing, Details and Notes.
| checkpoint | Pothole existing services that cross the line of the trench.
583e9f28-a5c8-5a72-8324-9b8934852f34 | textbox | Initials:
5822879b-1844-5047-adde-6053ac8a06fc | date | Date:
| checkpoint | Permit to dig obtained and underground services marked out.
889e1bc4-a54b-54bc-b96e-9632f13ed6ce | textbox | Initials:
25db49bb-e7ce-5248-9161-14d660eeb401 | date | Date:
| checkpoint | Trench location marked out with offset pegs and checked that it clears other services.
adea30a0-d95c-59d4-835a-dc2ebe2fa9cb | textbox | Initials:
f67ee27e-651a-536b-9d67-cfc40a9c3554 | date | Date:
| checkpoint | Inspect trench and ensure it is required depth below Ground level and free from obstruction.
2e9832f4-4bb0-5e3f-b963-e27293597bd0 | textbox | Initials:
94a0ed6c-0fc8-55a4-a9db-5bd632942f49 | date | Date:
dad22563-4f58-594c-85dd-c86a4c0e98fe | note | Comments: 600mm below open areas and under footpaths, 900m under roadways and free from obstruction
| checkpoint | Ensure the correct cable is being placed in the trench and check if direct buried or duct required.
5c10e600-8f8d-5468-b3ed-dc10e95c64da | textbox | Initials:
1a371c59-af1b-5b78-b660-8580326f5c7d | date | Date:
c303880d-71bc-5b03-9398-9a779cfe561e | note | Comments: Ducting is required under roadways, within bridges and when entering concrete foundations
| checkpoint | Ensure cable ducts (where required) are clear of obstructions, fitted with Draw Wires and are easily accessible for cable drawing.
fa8f4eac-eeb0-560e-925a-90d273526048 | textbox | Initials:
dc01f48f-6623-5b9c-af18-c452c971a0b0 | date | Date:
| checkpoint | Ensure cables are laid without sharp kinks and loops for connection are provided at Pole locations.
a36c7395-53e0-5ceb-ab43-4f61acbe173d | textbox | Initials:
a4ea7962-260a-560a-98a6-f36c6558bb13 | date | Date:
1f14eff6-9335-5503-98c2-1d4744909c62 | note | Comments: 3m loop on continuous cable, 1.5m loop at cable ends
| checkpoint | As built survey Cable in the trench. Ensure the As Built information includes the number and the type of cables and circuit numbers
425297b7-499b-598e-9ba5-594d39bf3307 | textbox | Initials:
48c15b3e-acee-59da-9815-b6654dd84c09 | date | Date:
| checkpoint | Cables buried directly into the ground shall be enclosed.
9f1d8ac8-b883-583e-8501-0e8c96212601 | textbox | Initials:
96d8c681-3d02-5847-b90a-74520b3571a8 | date | Date:
d7c94b85-d0e4-5b2c-ac01-628626e930a2 | note | Comments: Min. 50mm of Sand on all sides of the cables or Soil which passed through sieve no greater than 10mm
| checkpoint | Ensure trench is backfilled and compacted by hand ramming for the first two layers, followed by power consolidation.
0750cf9a-2780-574a-ac79-f0e4e267fcf0 | textbox | Initials:
23213325-c6cf-59ca-b798-0fec99985ffc | date | Date:
27a4e058-e77b-5d73-b1e1-6936ac010576 | note | Comments: Depth of cover:
2f186851-9c6e-5ff5-8c9f-5045096fad69 | note | ○ Open areas or under footpaths = 600mm Under roadways = 900mm
465af57d-4f6a-56c9-babe-b7fd2e1378a6 | note | ○ Check compaction with Clegg hammer every 20m
| checkpoint | Ensure 100mm Wide Orange Polythene Warning Tape is installed.
a5a3eef6-9acb-507b-b272-56186950c1b4 | textbox | Initials:
a0bc3304-aac3-5836-9344-f91b2d0044de | date | Date:
6d559a6e-05c5-5de3-a5e8-64ce3cdcb9e3 | note | Comments: 150mm below finished surface of trench.
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
00a87e9b-8479-5d09-9413-7b20593af554 | note | Position: Site Engineer
93b7d370-a484-5093-aad6-c62bea594a06 | textbox | Site Engineer - Name:
5cb0407a-8d49-5b4d-9c72-a25e55fe2744 | date | Site Engineer - Date:
0af163aa-3e31-59b8-97fa-c77a35f03667 | note | Position: CPS Engineer
7de82334-31cb-502e-8f45-f82eec613548 | textbox | CPS Engineer - Name:
263988f8-8d1a-5f2b-8cef-ab402c8b87aa | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4106 - Traffic Sign Foundation Record |  | CS-4106 - Traffic Sign Foundation Record |  | 99b2e8ef-ef0f-48b5-99f1-0ce10ddef2d9
| section | DETAILS
| checkpoint-no-value | DETAILS
9af3cdcd-baa2-5181-863b-27b45559a48c | textbox | Project No.
71ea44c8-dda8-5fe5-a69f-fd8acefd975a | textbox | Drawing No:
121c17da-e1cb-59e1-a331-432066a4680e | textbox | Sign No:
| section | Sign(s) Location
| checkpoint | Check sight distances
843ce4a4-f3f2-59ec-98a9-7ccaab2cc186 | textbox | Initials:
b9f9834b-b159-509f-bdec-4a99aedf16f8 | date | Date:
dd831504-50b2-5a93-a861-5ab3b9870426 | note | Comments: Ensure the sign will be in a location where drivers can see it clearly without blocking views from driveways, other roads etc.
| checkpoint | Check Lateral Distance
aa7a65d8-3a47-57b0-a529-0125c134609a | textbox | Initials:
60b7c261-c929-5085-8dd2-2a8bed9ce6e8 | date | Date:
4917bb7f-3f7d-5b02-ba42-2118ac0217be | note | Comments: Ground mounted signs shall be located at least 600mm clear of the outer edge of shoulder, line of edge marker posts or face of road safety barrier; and be between 2-5m clear of the nearest traffic lane edge line
236c32f7-6090-5066-83d0-ebfb39c1dbbe | note | ○ Large ground mounted signs shall be located a minimum of 1m clear of the outer edge of a motorway or expressway shoulder, or 4m from the nearest traffic lane edge line, whichever is the greater, or 1m behind the face of a road safety barrier, or 1m behind the face of a kerb, or 1m clear of the outer edge of a ramp shoulder
| checkpoint | Check location of existing services, if there is a clash with the new sign location seek approval from CPS Engineer to move the sign to a new location
7ec948bf-57e6-5a56-a171-1cbd0c14814e | textbox | Initials:
6ad05527-e402-5bca-9949-56f8356aa09c | date | Date:
43c1557b-8a3c-5df2-81e0-f22915249b2c | textbox | Comments: OFI # |  |  | (if needed)
| section | Sign(s) Foundation
| checkpoint | Expose any existing services by potholing
1c2dbe19-5483-5763-9964-c7956c6373b2 | textbox | Initials:
b7529dbc-ef77-57e9-bdec-807a52c1ccaf | date | Date:
| checkpoint | Confirm Type of Foundation(s) i.e. Ground sockets, Breaksafe etc.
c88fefde-9f89-547b-b53d-978d587359f8 | textbox | Initials:
9182f2f3-3881-555f-8416-46290cc165ae | date | Date:
5d699fa6-3354-5481-bd40-cb34c8072632 | textbox | Comments: Type(s) =
| checkpoint | Confirm depth and diameter required for augering
b4ef6bb9-3568-5cfa-977b-519874e47b89 | textbox | Initials:
1b843759-f058-5b3f-9d0c-a92005ae3579 | date | Date:
a92535db-0412-5203-baa5-9b18f3ce4e8c | note | Comments:
1bba9045-a01b-5275-94a1-358b3b7a5340 | textbox | ○ Depth(s) =
00941eca-93e9-5ac7-a53d-f9c8cc04ef23 | textbox | ○ Diameter(s) =
| checkpoint | Mark out post(s) location(s) remembering lateral distance (above) and sign orientation
6d5c67c2-1602-50b9-9fe8-89ef89601e25 | textbox | Initials:
7e0c2dec-5603-5a4d-a4a7-7dec6d6a9b0d | date | Date:
a064c352-53b7-5c9a-92a2-7c1474dfb3e7 | note | Comments: Sign orientation should be turned about 5 degrees away from the approaching drivers line of sight, this varies depending on the location on site. This is to help reduce possible specular reflection from reflectorised sign surfaces. If there is still specular reflection on a straight when the sign is turned about 5 degrees away from the drivers’ line of sight, then it shall be increased to a maximum of 10 degrees.
| section | Installing Foundation(s)
| checkpoint | Install the foundation(s), Check the correct type and sized foundation is being installed
6c9cab0e-3217-53a1-8ce6-08ff3133fa83 | textbox | Initials:
1fed0a27-6830-5b83-9411-63ebbe0757b0 | date | Date:
c90836e5-d77b-5c10-b504-2fbd0e583fb5 | note | Comments: E.g. Ground socket diameter and length etc.
| checkpoint | Check the location, level and plumbness of foundation(s) prior to pouring concrete
34fd21e4-442b-5bd2-99ba-3b80a5c3f49f | textbox | Initials:
c8a6acd9-28b7-5dca-9766-da7032f5ea47 | date | Date:
| checkpoint | Check the correct distance between foundations (for 2 post signs)
26aa24df-9a1c-57b0-b01d-21e568e2317c | textbox | Initials:
5a5e0cb3-732d-536b-808d-8ef534902a37 | date | Date:
| checkpoint | Check the height from final ground level (FGL) to top of foundation(s)
c9882bc8-a394-5b52-abc0-22427468c02b | textbox | Initials:
bdd9f489-9294-563e-bcfd-cbb23f2a545c | date | Date:
| checkpoint | Check there is equal cover around the foundation(s) prior to pouring concrete
c34da913-0511-51d2-b303-f2727b79ffa2 | textbox | Initials:
e2c7d519-e524-5738-b2c2-127399aa4ecc | date | Date:
| checkpoint | Order concrete, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected and concrete cylinders taken (1 test per group/lot of Signage posts)
1596852b-2d16-5b1c-a78b-ea3db91f0bc1 | textbox | Initials:
35959a99-f80f-5de6-95fd-676bf09210fb | date | Date:
241f7751-623d-562d-975f-29a272b9fac1 | textbox | Comments: Concrete strength ordered = |  |  | MPa
| checkpoint | Pour concrete to top of final ground level and wash off any concrete splashed onto the foundation(s)
d361c93c-cead-5c94-8ea1-058ca06c31a9 | textbox | Initials:
a00f3715-adec-53cb-9f86-3bc8ff2ba73b | date | Date:
| checkpoint | At the completion of the concrete pour check the foundation location, level, plumbness and height from FGL as this may have moved during the concrete pour
fa1549eb-a5a5-597d-9bac-2f131a039066 | textbox | Initials:
663ef515-f238-5598-8652-7ac30b0f7507 | date | Date:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
17b4a9d7-f736-5e25-900b-d2efad8619a7 | note | Position: Site Engineer
120437fa-b1a6-5ed8-890d-60e945974719 | textbox | Site Engineer - Name:
353f689c-75a0-5da0-8a02-89a38915525e | date | Site Engineer - Date:
25795abc-ce6b-550a-bf0d-9ceb99da3ea0 | note | Position: CPS Engineer
202ea3e6-00ee-5c67-9bab-677ac45f64ab | textbox | CPS Engineer - Name:
2c6a3c73-ee50-5c01-b5a1-d596a952bfeb | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4114 - Anti-Graffiti Coating Daily Checksheet |  | CS-4114 - Anti-Graffiti Coating Daily Checksheet |  | 8b9a7f85-b03a-471d-8208-a7eadeeddffd
| section | DETAILS
| checkpoint-no-value | DETAILS
fe5086b3-3add-5688-88bf-ea2556b90d8d | textbox | Project No.
64d1bd82-3c3c-576b-91c0-3dd64249df2e | textbox | Applicator:
e7270034-f1a0-5fa8-b2e1-778c8f796a7f | textbox | Supervisor:
| section | Weather Conditions
| checkpoint | Humidity
a3a4b9cb-8ac5-5277-804a-03b4c81c53c5 | textbox | Result:
| checkpoint | Temperature
bb3fbdcf-e7ed-52b2-bbfb-b5f665934e2b | textbox | Result:
| checkpoint | General (overcast, windy etc.)
7b7ea78d-10f5-59f2-9bdd-f0fa574319b9 | textbox | Result:
| section | Material Application
| checkpoint | Substrate Material
dcf23291-b870-5340-88b1-5af9b83d5978 | textbox | 1st Coat WFT |  |  | (µm)
266c91cf-42ed-5c74-8a82-708a6275b2ae | textbox | 2nd Coat WFT |  |  | (µm)
e123ecb4-4f4f-5911-a055-8c369261b8a9 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Brand Name
ad62fb58-1aca-5204-a1cb-46d7422c2847 | textbox | 1st Coat WFT |  |  | (µm)
378f7264-4f54-5613-99be-d3ac0632b6dc | textbox | 2nd Coat WFT |  |  | (µm)
95095783-7dd5-54e7-9415-aa1de297a5e2 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Batch Number Base
0c4c4bd7-9f5a-5492-9ade-bd53f9b24418 | textbox | 1st Coat WFT |  |  | (µm)
2b82ec1f-73c7-50e3-ac01-47b785b18848 | textbox | 2nd Coat WFT |  |  | (µm)
60c7ee45-c9d1-5bd2-aca2-0c67f12468f6 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Batch Number Hardner
68bcf2cb-6f17-5f6c-bb06-e4b7112584a4 | textbox | 1st Coat WFT |  |  | (µm)
14a47df5-1beb-5938-82e9-e66a4cd1ba4d | textbox | 2nd Coat WFT |  |  | (µm)
a5679282-b5c1-5299-a586-0b1d03da769b | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Colour
46062a61-8e8d-5f49-8f00-8db2b8195178 | textbox | 1st Coat WFT |  |  | (µm)
1adff8a2-1562-56e7-a81d-8f5837749e41 | textbox | 2nd Coat WFT |  |  | (µm)
f6f4af10-edae-5fcc-b7eb-7cd58cec1df5 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Thinner Used (Ref Number)
595261d8-4ba3-5123-b96c-8883ddc55692 | textbox | 1st Coat WFT |  |  | (µm)
a44103aa-936b-574a-8dc8-be3ce2cb8002 | textbox | 2nd Coat WFT |  |  | (µm)
692f2ec6-8b01-598f-8a54-5682730c9dd7 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | % Thinner used
6899f9d5-6f3b-5229-a2c1-3da0fe82c6a9 | textbox | 1st Coat WFT |  |  | (µm)
66d095ce-e9a8-5672-848c-5af109994d7d | textbox | 2nd Coat WFT |  |  | (µm)
147cff98-5f54-5d06-af29-6cc94e81681a | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Brush
e3f0be01-5e80-5281-a2e5-0cd1062a5cb4 | textbox | 1st Coat WFT |  |  | (µm)
1a0d177b-d34b-5582-890d-ca8c4f9ae4c1 | textbox | 2nd Coat WFT |  |  | (µm)
b8d7809e-8e4a-5252-a87e-7a825540801b | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Roller
271e49b3-f989-5a29-b1fa-70ca1c09aa7f | textbox | 1st Coat WFT |  |  | (µm)
0e647adf-3f51-5372-9f7a-e3fdbe014f7d | textbox | 2nd Coat WFT |  |  | (µm)
9dfb1ef1-af3f-5640-863f-4b8424f162c2 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Spray
85268576-31ac-571b-80a0-dc45339dddd8 | textbox | 1st Coat WFT |  |  | (µm)
9d572970-c02f-5532-aa27-e4e29a7c5567 | textbox | 2nd Coat WFT |  |  | (µm)
f6fa1f25-2295-591f-9066-70ede2247627 | textbox | 3rd Coat WFT |  |  | (µm)
| section | To be filled out by Inspector
| checkpoint | Dry Film Thickness (µm)
1ab83756-0dea-5b70-82ca-820e185dc0f7 | textbox | 1st Coat WFT |  |  | (µm)
e026ecbd-8865-57e1-8305-ee758dd5aa73 | textbox | 2nd Coat WFT |  |  | (µm)
47165cad-a51c-52d7-b5d4-8bd82bbe904e | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Specified (µm)
901f9c75-12d2-572e-a6ed-e881d9a5dfb0 | textbox | 1st Coat WFT |  |  | (µm)
82e22dda-99c0-5726-96ee-964a5b055abf | textbox | 2nd Coat WFT |  |  | (µm)
968b34cd-5b2a-537a-bac8-071aa7f00ebe | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Average (µm)
ee355cd8-e843-5597-8270-bfe6072b300d | textbox | 1st Coat WFT |  |  | (µm)
a67dd291-0171-523f-8db0-4cc5e14904e9 | textbox | 2nd Coat WFT |  |  | (µm)
1c7ff3e0-5675-5840-a1a7-bb238be2c2a6 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Maximum (µm)
1cdaa72d-d202-5d5f-8497-2420fe5172aa | textbox | 1st Coat WFT |  |  | (µm)
cb055519-b7e3-54d4-86b2-7504c1cd03e7 | textbox | 2nd Coat WFT |  |  | (µm)
17280c02-9a15-5596-af45-0aad3b1c9fe0 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Minimum (µm)
25f0a1b6-b64f-5d23-a5b6-6c6a119dbcaa | textbox | 1st Coat WFT |  |  | (µm)
a69f0ba0-3911-544b-bd40-8546817b7104 | textbox | 2nd Coat WFT |  |  | (µm)
693b0695-dcb4-585e-b3c9-7c08bbc8eb75 | textbox | 3rd Coat WFT |  |  | (µm)
| checkpoint | Number of Readings taken
e07ee1f8-c36e-55ad-bf2b-3180fa8b2737 | textbox | 1st Coat WFT |  |  | (µm)
7c84a74b-f3f5-5e20-97c3-16469c5722e8 | textbox | 2nd Coat WFT |  |  | (µm)
63d140fa-0e62-5fef-a168-15f241b1cc0f | textbox | 3rd Coat WFT |  |  | (µm)
| section | Outcome
| checkpoint | Passed
| checkpoint | Rejected
b4b3f96f-c82e-501e-8bcb-7fdfd4ebf92e | textbox | OFI #
| checkpoint | Rework
35fa3766-e80d-5964-b59c-aef0a684d780 | textbox | OFI #
| checkpoint | Checked and Accepted – HOLD POINT – Applicator, Site Engineer & CPS Engineer to sign
83377e57-9421-5608-bcb1-f349e9b50e5a | textbox | Name: Applicator
54842b89-4e8f-5006-ab1f-ef65640d917f | date | Applicator - Date:
e4c1f586-b868-5f21-a03e-f4ce4909975f | textbox | Name: Site Engineer
2642180e-e646-5aab-8577-08124ffa77c5 | date | Site Engineer - Date:
4ddc45a4-c68e-5628-ac6c-d80ca70c3e59 | textbox | Name: CPS Engineer
97b9b6a7-30d4-5ebd-a4f8-53cc1ec411fb | date | CPS Engineer - Date:
| signoff | Sign:
| checklist | CS-4117 - Guardrail Installation Record |  | CS-4117 - Guardrail Installation Record |  | 8d8d2869-30b5-44fb-a00b-575c408f0642
| section | DETAILS
| checkpoint-no-value | Details
d2e50bc8-f2f7-548a-ba5f-ad946c7c555d | textbox | Work Area:
3bdff61e-33d7-536f-b099-ec7368264397 | textbox | Sub Work Area:
491ea800-4925-566e-a773-d6745200eae7 | textbox | Lot:
4ea80722-d364-5847-ab97-12083b166e48 | textbox | Sublot:
150466c3-6197-514b-934c-f3817abe9777 | note | Document Date: 27/11/2019
72d9d7d5-4989-51fd-b2c9-4b1c8402a1f4 | note | Created By: Kirsty George
6b38a51b-e4ee-5ef2-94fd-63f883d3123a | textbox | Drawing No:
1be8ed19-9deb-538b-83e5-16e4826e3bb0 | textbox | Rev No:
2369d3aa-c15b-503c-926b-efb4f271deaf | textbox | Chainage:
| section | Guardrail Installation
| checkpoint | When driving post, use a driving cap with timber or plastic insert to avoid damage to the post
83f2d871-362d-503f-ac1f-c45737aff3fd | textbox | Initials:
f7b54828-e77c-5a6d-a68a-555657927c5f | date | Date:
| checkpoint | Height to centre of rail is 635mm
bc478843-0534-5ba8-a195-a82de8c050f9 | textbox | Initials:
9772aefc-9bfa-5a1f-b955-b0b34a71e593 | date | Date:
| checkpoint | Top of post should be a minimum of 20mm above top of guardrail
38293f74-ffc2-5e27-90da-c2e3b0561357 | textbox | Initials:
e5e1fe16-5b5e-5333-970d-a2490d09f9f0 | date | Date:
| checkpoint | Post is aligned with flanges rail for road side applications and alignment is alternating for median applications
27de49e2-7884-5a36-8198-88bdd5fd414e | textbox | Initials:
bcac7e85-4d24-55f8-985a-c5827fabcc21 | date | Date:
| checkpoint | There is a 90mm dia. Washer between rail and post.
ef227bee-f7b8-50bf-b309-1a898e0f5b80 | textbox | Initials:
c02caed4-0931-580b-9348-6594b2b13f89 | date | Date:
| checkpoint | Rail is lapped in the direction of traffic
23bf0b9d-46df-5aa7-9f8a-40ed4685da20 | textbox | Initials:
0d920536-d3f0-5381-aa83-3c43c754ef55 | date | Date:
| checkpoint | All bolts are fully tightened
7f954b67-a095-51fb-80b9-fb3a0f8cdb7b | textbox | Initials:
57613d4a-ec01-506f-94a6-d665e11ee0e2 | date | Date:
| checkpoint | Nut on backside of post is a splice nut
1d102b5e-573b-5ab9-b57b-81b4990d40d7 | textbox | Initials:
7f49bc36-62ff-50fd-a9ca-68709217c734 | date | Date:
| checkpoint | If a median installation-excessive bolt length is cut off on backside
c9b49394-2367-5438-832f-21ce0fe3f77b | textbox | Initials:
68a2ad74-6018-5c1b-b7b3-0dc2de2daadd | date | Date:
| checkpoint | That transition details to existing guardrail or terminations are correct
ad298c4d-d2de-5a53-a381-dd10992c4e12 | textbox | Initials:
d83a0b41-fde9-51a1-8b3f-feb1a685f361 | date | Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
ffaee200-b050-53dc-bf8f-71967cc37a73 | note | Position: Site Engineer
3a7309f4-c214-5061-8220-2e82a357eac4 | textbox | Site Engineer - Name:
2146e471-2bda-58c1-bf05-4eb4ee3c20c3 | date | Site Engineer - Date:
abc073c6-d047-579a-b199-7240768ffcde | note | Position: Design Engineer
3f8127c3-8fb4-555a-8ce7-1fbf1466b6ab | textbox | Design Engineer - Name:
f3463081-297d-5abe-9aca-23969d9de04f | date | Design Engineer - Date:
| signoff | SIGN
| section | Thriebeam Installation
| checkpoint | Panels are pre-bent to suite curves.
c1ed3251-ea01-5e78-b2a9-0338942f27e9 | textbox | Initials:
cac2ec5e-1747-55cf-a9b0-47d641d8d2f5 | date | Date:
| checkpoint | The rail height is in accordance with the plans and specification.
74344dbc-6baa-5268-a854-da763c1ecf99 | textbox | Initials:
b4ed7794-3d36-5a14-ac88-a879f4e94079 | date | Date:
| checkpoint | Correct lapping of rail away from the direction of Traffic.
a2423dc6-efb4-5c06-857a-664ad5d75b7b | textbox | Initials:
12ea2fa9-59b0-57b7-89d1-75a008c71572 | date | Date:
| checkpoint | Timber block outs secured to the post.
84fef50e-4df5-55a0-9fe0-d72a32e57955 | textbox | Initials:
f817110e-0b81-558b-97e5-9a226e185136 | date | Date:
| checkpoint | Rail is aligned and level.
a0525e83-38b7-5a20-a7bc-31db0b2320d8 | textbox | Initials:
c6a90f8c-beaa-56bd-b586-1e57123f8a21 | date | Date:
| checkpoint | Posts align, at correct spacing and backfilled compacted.
87bbcf2c-f726-55fd-9390-05d2297d2e64 | textbox | Initials:
2a557c68-a589-5255-9bb8-ac390888022f | date | Date:
| checkpoint | Post bolts are tight and washer is fitted at the back of post.
b4594f7c-a248-5c85-93ee-2b6be43f25af | textbox | Initials:
d38e856a-51d2-54e5-a578-144d3081cf66 | date | Date:
| checkpoint | Backing pieces are fitted at the intermediate post only.
0a359611-8b9a-5999-bbb7-6f0aad636be5 | textbox | Initials:
e7a443a3-21db-5527-afd6-251ce4391649 | date | Date:
| checkpoint | With flange based post the necked bolts are installed with washer.
88d24382-55e0-5835-b51b-8ff39445f117 | textbox | Initials:
1ecc7858-b480-53b8-8ed3-2013644ffb08 | date | Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
a354c1f3-34f1-5132-9544-934d7668339f | note | Position: Site Engineer
f8bff98b-dacf-5796-afc6-e890f25f2f64 | textbox | Site Engineer - Name:
3daf3e3d-2916-5939-b2c8-bd1f4151e0a2 | date | Site Engineer - Date:
afe9f5e0-a260-51f8-a366-10a0cff7d3b7 | note | Position: Design Engineer
56b12c9e-5c20-5962-acb4-7e44998af662 | textbox | Design Engineer - Name:
0b3ce488-af7d-5b54-b4bb-12fb7fa63d5f | date | Design Engineer - Date:
| signoff | SIGN
| checklist | CS-4120 - Wire Rope Installation Record |  | CS-4120 - Wire Rope Installation Record |  | d9f962f2-250e-4b05-a2d2-308c021ba550
| checkpoint-no-value | Details
df05608a-8933-5e61-a8e4-8d4a3b7e9d3e | textbox | Work Area:
da8409a9-e424-5b5e-b9aa-56dbf3c8ef32 | textbox | Sub Work Area:
7dfc399b-b9cc-54ba-ae70-847b7b27ff3e | textbox | Lot:
86678851-2bf1-57a0-9d0f-4e5e50c147e2 | textbox | Sublot:
e2676622-ea2f-53cf-ba5f-01a79ab5ae68 | note | Document Date: 27/11/2019
3461a34d-98c5-525f-8818-1928a55ea917 | note | Created By: Kirsty George
11a27d8a-9444-548a-969d-1b30b5f2ec7f | textbox | Drawing No:
975fb18f-a3e5-529c-89b0-9fd623d2a43b | textbox | Rev No:
de7783f0-e2a7-5081-a0b6-a150761e0e9a | textbox | Chainage:
| checkpoint | Drilled holes spacing does not exceed 3M and are 300mm diameter and 750mm deep.
d8c01ee7-049b-5480-89c7-7987de652e8a | textbox | Initials:
5f3fd89b-5688-540d-a5c9-ad4a82b08381 | date | Date:
2e3c05b7-d05f-5c73-89fc-c1fac5cc4b99 | note | Comments: Consistency with Construction Drawing, Details and Notes.
| checkpoint | Concrete is 25Mpa.
abfebc64-dc6f-5892-b630-ba838c28c2b6 | textbox | Initials:
efcb847f-a476-5e91-a521-0a08a1f8bc1b | date | Date:
| checkpoint | Concrete Dockets Collected
2d91cbe3-47b8-5f99-86ce-2c5c5aa8cd08 | textbox | Initials:
0a1fd5b3-40a0-5daa-98bf-ed0d1c45f02d | date | Date:
| checkpoint | The plastic Socket is correctly positioned and a rebar ring is placed 100mm down from top.
8c80a268-11ac-596d-a0ae-d2c016d35bc9 | textbox | Initials:
6ac588e5-4bac-5622-88aa-1669bcb6be5e | date | Date:
| checkpoint | Post are installed with slot orientation consistent for the entire length of the barrier.
0f17e3ec-041e-56a1-af3b-eebfb4c69b0c | textbox | Initials:
bfbbe908-566c-57fc-a3bf-607de400a036 | date | Date:
| checkpoint | Top 2 Cables are positioned in the Top slot while the bottom 2 cables sit at the bottom of the slots on either post
2dbeff6b-1591-59ea-85f7-042bec242022 | textbox | Initials:
9c2d3229-fbc1-51b3-ba77-e51998a6573f | date | Date:
658bd789-9850-515c-af9a-272199dcdc7d | note | Comments: Cable Heights 530, 650, 770 and 790mm (+ or – 30mm)
| checkpoint | Ensure no corrosion to the internal collars at swage connection
21ee8856-f1db-518d-8d78-45236969494d | textbox | Initials:
77c7c3aa-8447-5d9c-a766-cf4968287310 | date | Date:
5e7f0b01-2174-507d-a6fa-4bca820c0ae1 | note | Comments: Also check swage seat & collar thread connection. Should be tight and should not be able to undo once in place.
| checkpoint | All posts have a plastic cap inserted in the Top and pushed hard home.
2a645dec-bf2d-5638-82aa-a3f2beb7f337 | textbox | Initials:
52a5039b-b338-528f-a470-bdeff32c3d53 | date | Date:
| checkpoint-no-value | Comments:
| checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
df755e8c-17a0-5f4e-b815-415a7cb545ba | note | Position: Site Engineer
a6aba232-b623-59fe-9727-c406ceed3ff7 | textbox | Site Engineer - Name:
6713eabf-fdbf-5c2f-95eb-6340d31f5678 | date | Site Engineer - Date:
2f883a07-63a7-5d62-b613-09f6c3214d33 | note | Position: Design Engineer
e4965e05-4063-57b3-86ba-67cbb03b66dc | textbox | Design Engineer - Name:
7c61a6f3-0659-553f-bf1c-692dc9d522c2 | date | Design Engineer - Date:
| signoff | SIGN
| checklist | EN-4011 - Environmental Field Inspection Record |  | EN-4011 - Environmental Field Inspection Record |  | 4b7058d4-04d6-4e9f-be62-d41544bb0150
| section | DETAILS
| checkpoint-no-value | DETAILS
0ec173ca-fb0f-57aa-9087-509de2d93199 | textbox | Project No.
e86634d1-f668-582e-bec7-d113bf37bfbd | date | Date of Inspection:
2159d46e-2f54-5837-9a64-1e2451ddaf7b | textbox | Time:
5f06f19c-e9db-5570-b9dc-fd775b7d5bac | textbox | Zone / Area:
18cb1130-f408-5042-8371-d62323a80213 | textbox | Weather:
3c17b127-ed93-5806-bb61-89cd888fbff6 | textbox | Person Contacted During Visit:
| checkpoint | Copies of Inspection Sent to
840cad55-da3e-593c-a16b-d962abe30025 | textbox | Sent to (1):
3ddf7160-a41f-54b7-b4bb-136a5220465a | textbox | Sent to (2):
269773bc-1b78-5530-a7d2-03225417bfe8 | textbox | Email (1):
0fbde90f-1be6-5e0a-ab9c-7e1170b88656 | textbox | Email (2):
3ca5fb67-2763-560f-9fe9-afeff62a6f8f | textbox | Company (1):
e1e79b37-538f-5939-9a57-1c7b89606dcc | textbox | Company (2):
83a15852-1b12-5775-a7a5-af142959f4cd | textbox | Inspected by:
| section | Works Required
| checkpoint | Item No: 1
b93ce969-dd15-5f5c-9f76-5f60f0429919 | textbox | Responsibility:
5278a759-d473-55cb-95c0-034bd964d38b | date | Date to be Completed by:
4b026f23-8f01-5fcc-8cb2-ad6668053783 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 2
e3ed2f81-33d7-55de-8c29-6f6c76f63794 | textbox | Responsibility:
bdae80c6-5d78-589f-ba91-c947a56552dc | date | Date to be Completed by:
15cf22fb-0597-5034-b26d-ed18975436f9 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 3
aa9b0388-1866-5482-8976-2d99256a0b33 | textbox | Responsibility:
54ab8a94-4437-5a23-8d2e-32f07d2a9d41 | date | Date to be Completed by:
f26577ac-1e5f-5939-8f89-4d86104d5a32 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 4
e7377816-6817-552e-8bca-da0af4c537b5 | textbox | Responsibility:
69c254f2-3241-57ad-8249-1ed253594967 | date | Date to be Completed by:
dd926555-776d-5e0f-a759-8ad416266e66 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 5
60b1444e-fe89-5d4f-8acb-dab961b02d86 | textbox | Responsibility:
57da952a-87cf-54c5-87ba-481f338f40f7 | date | Date to be Completed by:
e7bead48-38ef-51d3-85de-5bd684e4a480 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 6
407b2d82-b0fa-5073-ad28-22335c7ad405 | textbox | Responsibility:
7fb6db6d-c8d7-5a51-8439-8fd6186b35c9 | date | Date to be Completed by:
e9a52859-aa67-560c-84c1-152bc386d1f8 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 7
b7f6f71b-a9d6-5152-b240-943891341b32 | textbox | Responsibility:
61cf6772-88fd-5871-bd7d-042897979976 | date | Date to be Completed by:
6127b345-f3de-5ced-9a93-55e0713b5043 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 8
7dc90b7d-7855-51cd-9f9d-ec3a624e176e | textbox | Responsibility:
ecff848d-b41f-5bab-9377-43802b57789d | date | Date to be Completed by:
45c9415f-063c-5b9e-a139-97f1cf2bb586 | textbox | Closed Out Signed Off:
| checkpoint | Item No: 9
eaada2ae-ceb8-5f9c-a973-745cdcee0894 | textbox | Responsibility:
cfc68836-f5e1-5de2-b2fd-51cd5048bdb7 | date | Date to be Completed by:
ca71b73a-8d7c-538c-8a7f-84818cc05bc2 | textbox | Closed Out Signed Off:
| checkpoint | WORKS REQUIRED HAVE BEEN INSPECTED AND APPROVED
b3d24f5f-4ba6-56aa-b6af-31e5f8a0146a | textbox | Site Supervisor:
23403777-47ce-5374-a02c-b9fe8a78169f | textbox | Construction Manager:
74cc6c73-00de-5283-8af3-42800df13128 | date | Date:
| checklist | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works | itp | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works |  | 6efdad45-2af0-4f82-86a7-2306bb896d31
| checkpoint | Project Site reps.
3137e59c-562f-57c5-84ec-3cb23aad058a | textbox | CPS Eng.
572fdb2f-d487-554b-aaa6-6896d474b915 | textbox | Site Engineer
84216fbd-5695-5436-bd92-50b4596428de | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
0efe38c1-8cb7-5228-992a-eae0ad949622 | note | ACTION (Hold, Monitor, Witness) - W
67c57292-2aeb-58d4-9b58-ffa2501a1708 | note | Detail - Set out Base of Wall to 1m offset. Setout and mark all known services along the line of the Retaining Wall.
9c549896-b740-53fa-9d88-8258d828b46e | note | Frequency - Prior to commencement
82d275c8-5884-5006-94bd-6ce59a9a3df2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
df797c94-f776-5ad8-8571-ebf786a0fd00 | note | Conformance Criteria - Consistency with Construction Drawing
7ccf43d5-2551-5733-ab24-45b6ea20c7d7 | note | Records - Survey receipt
| checkpoint | 2 - Material Compliance (Rock Works)
543d2ad0-7120-53de-9307-de780dcd309c | note | ACTION (Hold, Monitor, Witness) - H
c2128041-d5fe-5ae1-b62d-68254b745831 | note | Detail - Material to meet specifications dependant on material type selected
16f1ce5b-aa1f-5a5e-8306-3b1a90e7fb13 | note | Frequency - Each material used
94438825-dde0-5e8c-9c12-955b57a505c1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4b766bd9-6ce6-50da-bbf6-183fe1407706 | note | Records - Lab Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance (Rock Works)
b3b6b3e2-70ac-56d9-9be0-c7dbc4b76082 | note | ACTION (Hold, Monitor, Witness) - W
96bb56d5-d517-5c5d-9aba-f2e06fa9fde8 | note | Detail - Rock Construction Material - consistency though construction
a215f152-d1bf-582e-9925-76668c88ebb4 | note | Frequency - Each rock source
db73cb39-1397-5d3a-860b-6aeaf2841ffe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
94c71316-00b1-5021-b96a-ea8c879cc967 | note | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
2a5fa48b-1c49-58d0-818c-d3bf26eca791 | note | Records - Photos
| checkpoint | 4 - Material Compliance (Geotextile)
5c38672d-2799-5cb3-a127-37d1276cabef | note | ACTION (Hold, Monitor, Witness) - W
6d5916ee-09c9-5d27-81e4-b6fcf9bfc35a | note | Detail - Geotextile for rock works - Rolls delivered and delivery dockets gathered. Compliant with Terratex 750k or similar approved
6f4393b5-b98d-5df1-8c71-2155a634f16e | note | Frequency - Prior to commencement of placement
2c770e31-9980-5be0-ad08-3b1d76196fa1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
1953fd6d-68ab-54cb-837c-a55e530d1ef4 | note | Conformance Criteria - Conformance with Specification
43843e6a-269c-5a2a-a70f-8951180e3980 | note | Records - Delivery Dockets
| checkpoint | 5 - Material Compliance (Geotextile)
6ca6def0-3b6b-59db-b82f-021aadca365d | note | ACTION (Hold, Monitor, Witness) - W
ead8eb9c-e7ad-556f-891d-d9308501baf9 | note | Detail - Geotextile for back of excavation - Rolls delivered and delivery dockets gathered. Strength class C, Filtration Class 2
42bc0e05-8353-57be-b8c2-90dabbe95c6a | note | Frequency - Prior to commencement of placement
49307e0e-0591-5556-91e8-1ed5933827bb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c5e11a35-abd7-5639-912c-e51f18de6a72 | note | Conformance Criteria - Conformance with Specification
325dba8f-f012-5de1-a5b8-a5cdd5d52273 | note | Records - Delivery Dockets
| checkpoint | 6 - Material Compliance (Geogrid)
b6bcb43b-c8bd-5397-8ad3-72ebdd14a8aa | note | ACTION (Hold, Monitor, Witness) - W
e02c98a4-fa2e-5f46-9915-36aeda6f8737 | note | Detail - All rolls of Geogrid are to be checked and left in their protective wrappers until they are required for use
36f32d66-4467-5c22-9b5f-b4a562aabec3 | note | Frequency - Prior to commencement
66e7e001-8a7d-5657-b1dd-d56c0433204d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
5dd97ae4-d1b5-5759-bc99-2e0b8c876354 | note | Conformance Criteria - Any defective rolls are NOT to be used in the wall construction - return to the supplier immediately
| checkpoint | 7 - Material Compliance (Geogrid)
bd130123-97f9-52da-bb6e-16672fa10b5e | note | ACTION (Hold, Monitor, Witness) - W
f9499758-a71a-58cd-a703-86177c4e8e03 | note | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
e36de997-478e-54de-bed5-99074e522ce4 | note | Frequency - Prior to commencement
1739b61f-94da-56a2-9a73-a496135d1832 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
fae52fa6-f4c1-5415-a9bd-1635b7b85d6b | note | Records - Delivery Dockets
| checkpoint | 8 - CTV Culvert
3e3f6c74-dadd-504d-afa1-c224a301a607 | note | ACTION (Hold, Monitor, Witness) - H
c15afd9a-c3a6-507f-ab28-a148a02d0137 | note | Detail - CTV existing culvert to confirm it should be repaired rather than replaced
bc5775a5-7284-5813-ac3b-4bfb5a2fb180 | note | Frequency - Prior to commencement
d5b30e20-2789-5f79-bb7c-2e09f02dc334 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
dc8c9375-657c-53f3-b728-a909ad29d78c | note | Records - Inspection Video
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Culvert Extension
cf583fc6-2e1f-531b-a60c-719e480fec56 | note | ACTION (Hold, Monitor, Witness) - H
61067676-3ad5-534b-9236-d90f8cf0a94d | note | Detail - Confirm extension connection methodology with CPS Engineer
4ef1dabe-5b39-5ef1-94aa-b64eacae6221 | note | Frequency - Prior to commencement
83bb1d19-220b-55d7-8baf-cb19cc96678b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - submission
62e45de4-b2e8-56b5-bf62-f8d211511938 | note | Records - Subcontractor's method statement
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Material Compliance (Anchors)
c07a63e2-bafa-5480-b0eb-8a26cf5366fe | note | ACTION (Hold, Monitor, Witness) - H
c8a4363b-bd5a-544d-910c-9a7a73be670d | note | Detail - Ground Anchors and proprietary components (plate and lock nuts) - Manufacturer’s test certificate for each batch of anchors. Testing shall be undertaken in an Australian / New Zealand Telarc certified laboratory.
dd5d9e5d-eac1-58b7-8809-867545686c93 | note | ○ The required minimum physical material properties information are as follows: Diameter; Steel area; Ultimate load; Proof load at 0.1%; % of Elongation at yield load; Modulus of elasticity; Relaxation after 1000hr. Refer to specifications and drawings, including proof of coating galv and epoxy.
0196a104-6eae-55df-b509-9889c21e01fd | note | Frequency - Prior to commencement
a9de789d-c4f7-5a05-99e4-f4607f4e2d06 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0d9f9efa-072d-5d7a-9f79-c3a951a7b83d | note | Conformance Criteria - Manufacturers compliance test certificate with relevant delivery dockets
3b6b945d-4841-518a-aee0-73cae73f1222 | note | Records - Supplier Certificate, test results and delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Material Compliance (Anchors)
67f8dd90-577f-500e-b7cc-936291d3b0d3 | note | ACTION (Hold, Monitor, Witness) - H
ef0815a4-58c4-5a02-b013-693136393f78 | note | Detail - Grout mix - Approval of grout mix design. Include method of batching and mixing and previous test results for pumpable cement grout mixture. Refer to specifications and drawings for grout details.
fc104a07-66d0-5971-a47d-a21ddbec61db | note | ○ The water-cement ratio shall not be less than w/c = 0.40 and no more than w/c = 0.45. The grout shall not be subject to bleeding in excess of 4% of the initial volume. Admixtures which can control bleed or retard set of the grout shall be used only when approved.
39d74a2c-7277-5737-8d94-dae45e7aefae | note | Frequency - Prior to commencement
681cea4e-fb87-58e8-94b5-952386060fb6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
488a2d06-984c-5a85-8acf-5dd83226fc17 | note | Conformance Criteria - Approval of Mix Design
6ed739ed-43e0-5afa-8ed3-7e83887ed3bb | note | Records - Grout mix and test results within subcontractor's method statement
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Material Compliance (Anchors)
1eb77e36-73f9-5e5c-b90b-51cdd2f3ae37 | note | ACTION (Hold, Monitor, Witness) - H
f03d7ef0-8e35-5868-a4fc-fecf1ae5ec82 | note | Detail - Anchoring methodology - CPS has reviewed methodology including location, drilling method, grouting procedure, stressing and testing methods and reaction frame details
e8ac7ab2-3506-5775-a3b3-97ca26b92757 | note | Frequency - Prior to commencement
aeb327ed-db75-555e-b96d-efedfbd71858 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
46d06781-9aec-5639-ab73-c85719823afb | note | Conformance Criteria - Approved subcontractor's method statement
1017ed5a-b5ff-5747-9124-ce2db3e8815e | note | Records - Subcontractor's method statement
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Material Compliance (Walls)
65b72d5f-0415-50f6-aa8f-885aaf9fb908 | note | ACTION (Hold, Monitor, Witness) - H
38b36c02-55e7-5562-a969-3e1a8abec3be | note | Detail - All blocks that are delivered are to be approved for use and are compliant with the Specifications
aa97b219-d8a6-591a-8b06-10c92336d2c2 | note | Frequency - Prior to commencement
141b9b01-c3cf-5681-ba4e-eae40014ca33 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
514f06d2-e69f-5e9e-8877-c9c1424a464a | note | Conformance Criteria - If patterns are used on walls then ensure that the correct colour blocks are ordered and instruction given to teams
02b64a08-9dc9-5c74-9d55-111ed9e88252 | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Fill Material Compliance
d42b8b6b-7639-576a-b6e6-cb52f0690a1f | note | ACTION (Hold, Monitor, Witness) - H
6c156218-6ea1-5f9d-b931-8c768d35c01d | note | Detail - Material to meet specifications dependant on material type selected
293673fd-16b2-5c33-90fc-3df0b768c8a6 | note | Frequency - Each material used
ea120a3e-8c94-5fe5-abcf-85708f3d089e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d5ac925e-c93e-5f60-8593-542fcc952a3b | note | Conformance Criteria - Compliance with project specification
6e720974-59a4-5464-83db-0bb752caa3a5 | note | Records - CS-4020 Bulk Fill Earthworks Record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Fill Material Compliance
a3d2658b-646c-5142-9a3d-769370e95f32 | note | ACTION (Hold, Monitor, Witness) - H
9a5433fe-d0b5-50e3-aaff-ee4132cb3c6c | note | Detail - Fill Construction Material
eaed13ef-522d-52ca-a09a-e528094af94a | note | Frequency - Each material used / borrow pit
e344952e-5a40-5a35-8868-c80787f06377 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
e9819085-37c6-53ec-96c2-3e1a27e3cb21 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - Repair and Underpin Box Culvert
1d660711-0e30-5864-83db-ebb148aef021 | note | ACTION (Hold, Monitor, Witness) - W
1389cbd5-1c6e-5ca1-8915-db23e3bc9d72 | note | Detail - Repair as per drawings and specifications
55d64c54-3f5b-5f94-a2f7-d2845150fa91 | note | Frequency - As required
1a02c060-9917-52af-8d59-41bce6b7694b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
98273bf0-2a5d-5cba-88a0-a94048bd9323 | note | Conformance Criteria - As per specification and ecology requirements
fd29d97e-c799-54c0-855d-d40a310b0fdf | note | Records - Photographs
| checkpoint | 17 - Excavation / remove temporary fill material
f6f1fe73-1ae2-53b7-a71a-ef2a5c59699c | note | ACTION (Hold, Monitor, Witness) - W
64be7a08-8523-508e-8087-11b9acb668ec | note | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions. Road seal may need to be cut where it is undermined.
33a422f5-dcc0-562f-a129-799488db1830 | note | Frequency - During construction
ec4461ee-e2cd-5e12-a1dd-729882c4a86e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
dd46237a-edf6-588e-9cee-037aab5d11fe | note | Records - Photographs
| checkpoint | 18 - Excavation / remove temporary fill material
4de5d0a4-2fc8-5f4c-986e-8731ed3a2b15 | note | ACTION (Hold, Monitor, Witness) - W
ece43a07-0a9a-5ac6-8c35-06c7d1e34dd3 | note | Detail - Cut inspected by Geotechnical Engineer when conditions/material type change
e0fc5988-3f1b-5b05-b9e5-5c163cf77eaf | note | Frequency - During construction
2da77dbe-cd9a-5ee0-b3d8-030b314c740a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| checkpoint | 19 - Excavation / remove temporary fill material
c63c03e3-d709-5e64-878c-ea65fb089c2f | note | ACTION (Hold, Monitor, Witness) - M
df97b6c5-0082-5e8e-8533-2b23ec058b96 | note | Detail - Ensure cuts are staged. The slope should be trimmed in stages to maintain stability rather than cutting entire slope in one hit
4d4ae65b-b534-56e7-8297-f53e45bf8447 | note | Frequency - During construction
7fbae0c4-d7e7-5caf-b113-96aba2da1884 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| checkpoint | 20 - Excavate Base of Wall
2e2b7811-b1a3-5403-a850-602191a8b7cd | note | ACTION (Hold, Monitor, Witness) - W
78fdf854-659e-59d4-99d3-478ad2a984c6 | note | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
bb879450-efac-5d93-bc7c-6449e1cfe72e | note | Frequency - As required
42bca4aa-8496-5044-b8f0-b25e23fcc7ad | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9379ac16-e85d-5f83-a296-f07f84d16174 | note | Records - Survey Receipt
| checkpoint | 21 - Excavate Base of Wall
6c797fd2-c3c2-5ef4-8b13-b6581b871d1f | note | ACTION (Hold, Monitor, Witness) - H
f9e4500a-d110-5947-b756-f875b986c38c | note | Detail - Test the base of the excavation to ensure it meets Specification.
bfbd1ff9-62b5-57cc-9034-10ba32c3636d | note | Frequency - Prior to backfilling, as per specification
a7b9fd32-bf48-503c-8c11-8c701430636c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala and Shear Vane
7e93245d-6609-58b4-85f8-b3dfeca525c7 | note | Conformance Criteria - In accordance with specification
fc133c33-6324-5587-acf8-02f759023622 | note | Records - Lab test result
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 22 - Excavate Base of Wall
3567d1e1-32ce-5a60-ac31-85f9a1d1760a | note | ACTION (Hold, Monitor, Witness) - H
00662ab0-7961-5035-af89-7ff4bd4cb5ba | note | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
3b1a305f-3493-5396-aa4e-fe34a1a7b1ce | note | Frequency - As required
2a482da3-0e94-54b7-9728-13f3247234ac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
72c89d3b-b4c8-5ef3-b83f-f626fd0f97f0 | note | Records - CS-4100 Subgrade Approval Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 23 - Dewatering
30cc9d36-d545-5180-ab23-c22b760c1eed | note | ACTION (Hold, Monitor, Witness) - M
1ceac54c-3afa-5860-8da7-03b03e399e0c | note | Detail - works shall comply with the relevant consents and the projects Environmental Compliance Requirements
1fb60fe8-0c93-58d2-a264-61918c7dedd6 | note | Frequency - As required
f686a5b6-0606-5ec6-831e-e3214f9e23b1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
5bb30772-4fe8-53f9-bef5-dd57bf49d021 | note | Conformance Criteria - Dewater in order for construction requirements
| checkpoint | 24 - Undercut in areas deemed unsuitable
45b02a34-180f-5cfd-8273-d9045c52b280 | note | ACTION (Hold, Monitor, Witness) - H
a5b94438-0d3b-5915-b8ac-e6a3770d7f9e | note | Detail - Cut to waste as required
447d3787-f6eb-57d8-bbf1-eeb3fdf9c601 | note | Conformance Criteria - As required by specification and CPS engineer
47091562-6fe1-5f35-b57e-73b9377f71d5 | note | Records - CS-4100 Subgrade Approval Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 25 - Geotextile Placement
910eb600-9506-5c4b-9242-a73f3da405c0 | note | ACTION (Hold, Monitor, Witness) - W
6b8f1375-b2e8-5677-886b-d1fcc8bb9cf7 | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
1affba71-c385-54b2-92c7-a20787c8546c | note | Frequency - Daily visual check
43792f9c-a0da-5db0-a0fb-5d597c0a9e4f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ec036213-3d4c-5231-bf23-2f63e65d5ad9 | note | Conformance Criteria - Specification
e60c1236-4244-59a6-9c6a-0d7c1b2119f9 | note | Records - Photographs
| checkpoint | 26 - Riprap Placement
deba4e57-af6a-5446-a89b-f305c41a08c0 | note | ACTION (Hold, Monitor, Witness) - W
b328aaa0-8bf6-5f98-9e8f-fe2b78b6c59d | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
c8b80128-b6c5-5708-852c-c6cacd8c88d7 | note | Frequency - Daily visual check
a1f59599-19ed-57ba-9675-c0bf58da3ef8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
81c32246-cc5a-593e-acaf-5ed17d9787a8 | note | Conformance Criteria - Specification
d7ce471a-2688-5611-9cac-1e1f419b3db2 | note | Records - Photographs
| checkpoint | 27 - Subsoil Drainage
6a3489a7-2036-51a7-90eb-b192d4a7e10a | note | ACTION (Hold, Monitor, Witness) - W
db5bb35a-4e2f-51ce-ac2e-1d908b737a63 | note | Detail - Install subsoil drainage as required in accordance with specification
6fdc6c11-5dec-5eca-b574-c3c8dfcb6e0a | note | Frequency - Prior to construction of wall
fdb50df3-59cc-5217-9161-bf113e5bba01 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
04bcdf19-751c-54cc-a5df-1546d18555ef | note | Conformance Criteria - Specification
db43226e-379d-5de8-a4b2-1634eef92857 | note | Records - Photographs
| checkpoint | 28 - Construct MSE Wall
2d72fcba-2d29-5772-9957-e473f5c52635 | note | ACTION (Hold, Monitor, Witness) - H
44de7b73-8a60-559f-8a7b-11c1598a91ea | note | Detail - Place concrete foundation including grouting starter bars as per specifications/drawings
31569aac-909c-50da-875c-e451fd4e2757 | note | Frequency - Prior to construction of wall
4743b562-280f-52bd-917a-5b0415340a75 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
ab5e8b36-2c5a-5ca6-974d-520a5133d1ce | note | Conformance Criteria - Concrete to meet the specifications, collect all delivery dockets
2233ff98-d576-5420-a662-13d23c24986a | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 29 - Construct MSE Wall
3a4ca5a2-7b3c-5dfd-a3c6-abef4dd7bd1d | note | ACTION (Hold, Monitor, Witness) - H
e02958fc-a58c-5e22-8f51-24c3b37b287b | note | Detail - Confirm with CPS Engineer extent of MSE Wall vs Anchored Section
41be8be1-0131-5b5d-b9ac-43f0536fd0fc | note | Frequency - Prior to construction of wall
f6107d6b-ee5e-58e8-9c79-83e9bbfef757 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
24071834-72aa-5014-8ac2-4337f0da1a55 | note | Records - Submission Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 30 - Construct MSE Wall
254b2522-e3da-58d2-a0e9-487449fc8a17 | note | ACTION (Hold, Monitor, Witness) - W
6b2b8ed6-91d5-590d-bb2b-94106aaba994 | note | Detail - A Permit to Lift has been issued to the contractor carrying out the works and there is a Lift Plan available
6ff4dd1f-50bb-5466-9966-f541910cc108 | note | Frequency - Prior to construction of wall
1bae1e98-b1a7-5198-94e0-dd63acc62f82 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
10767bfc-7a39-5b36-8bc3-735c32c33906 | note | Records - Permit to Lift
| checkpoint | 31 - Construct MSE Wall
a0c99e86-0b5f-55c9-83c8-74a8ac041578 | note | ACTION (Hold, Monitor, Witness) - W
4dbcc38c-fec3-5791-a17f-da88e57081fb | note | Detail - Install Mass Blocks as per Manufacturers specs along the front face of layers to ensure correct line and level.
e9ec4f48-0ba7-57cf-8d37-44121aa545fa | note | Frequency - As required
a84b785c-7f96-503c-9c8b-08cd1922424a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
f1a6da0f-8443-56fc-b64d-e47afb138364 | note | Records - CS-4012 MSE Wall Geogrid Checklist and Photo's
| checkpoint | 32 - Construct MSE Wall
b29918b4-36d4-512f-9cd8-c4fbd6675f60 | note | ACTION (Hold, Monitor, Witness) - W
b85d7fc4-b179-5dd0-a7bb-89495c18048f | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
0efc1591-2eaf-5958-a334-ce4ca6b43471 | note | Frequency - Daily
1ede7997-b47f-58fd-9b70-02bc0ad9a915 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
844849bc-5bd5-5d02-a966-af3dab9e5e52 | note | Records - Photographs
| checkpoint | 33 - Construct MSE Wall
d5ba0742-3f33-5a63-ad63-7109c174a861 | note | ACTION (Hold, Monitor, Witness) - W
c5cd9910-c5d9-50e9-ad45-207ed9583f87 | note | Detail - Install Drainage Blanket as shown on Drawings
3aa46e99-2c45-5943-af61-0df7a5dc7f71 | note | Frequency - As required
06100635-2693-522d-9edc-c9e7e3f077e5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
ecec5d98-06f9-54e8-843d-76c2e7eff424 | note | Records - Photos
| checkpoint | 34 - Construct MSE Wall
3aed1c86-44f4-564a-a8be-bf9c4d19f2db | note | ACTION (Hold, Monitor, Witness) - H
59db43a2-dddf-5053-a2fb-b26b4283e472 | note | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
54c1869b-a2ce-581f-a449-7457c49856c7 | note | Frequency - As required
c387776f-1e0a-53e0-8826-5847c9a9ccc4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
b7397851-a8e9-5937-8850-c5d3a9c465f5 | note | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 35 - Construct MSE Wall
7dfc2f13-b77e-56ba-8be7-47a9b879ada3 | note | ACTION (Hold, Monitor, Witness) - W
7e90d148-46b4-58ec-b9f3-0b4b549d896e | note | Detail - Place fill material on grid layers as per drawings and compact to MSE Wall specifications and test.
e41d9e74-27ef-5ba1-b507-41637247e6cc | note | Frequency - Every lift
77aba6d1-fb95-5be7-87b4-ef3f7b021dbc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
23844160-a9b9-5abe-8b6e-ec91551b899d | note | Conformance Criteria - As per specification
46191cce-67fc-5e6f-a0e3-2fc393c735e2 | note | Records - Lab Reports
| checkpoint | 36 - Construct MSE Wall
b5d14088-584c-5c33-b668-7f4b1291ecaf | note | ACTION (Hold, Monitor, Witness) - W
fe6fc8b3-e751-5f85-b62c-b3eb38c1bc30 | note | Detail - Ensure line and level of front face is as per design
c99ae914-0e5c-5ecd-8751-56e71b1023fa | note | Frequency - Each Lift
dc3af2e4-5266-5287-9239-f630176daeaf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
| checkpoint | 37 - Installation of anchors
50fa01de-d3c0-546a-a9a5-9cbbf9992854 | note | ACTION (Hold, Monitor, Witness) - H
be665be4-2071-5211-86be-b39454e786f6 | note | Detail - Install and test sacrificial test anchors, location to be determined with CPS Engineer, testing after 7 days when the Grout strength has reached 30Mpa
1505a2db-49db-5020-ac75-b987438b299f | note | Frequency - After Construction
a2cac842-03ce-566f-a081-2a23a26f42d2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
697d7126-c507-545b-a7ee-aeb5abd05fc1 | note | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
ae5f2bb6-bb46-5891-a80b-7e4b5e1ab725 | note | Records - NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 38 - Installation of anchors
c45c5dc9-5c83-572d-9d00-a300684935f0 | note | ACTION (Hold, Monitor, Witness) - W
2e2b047a-0eba-54e6-85b6-47a4c80bc31b | note | Detail - Construct working bench, this will form permanent backfill
70b472a6-f8da-5e75-a70f-ad2fb84c917e | note | Frequency - During Construction
08e26c84-ed69-56fa-ab36-27fbd3838172 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
921192f4-9572-5695-aba7-221e608faea5 | note | Records - Photos
| checkpoint | 39 - Installation of anchors
d28d508b-51e3-5acb-bda7-0e97b2fa8007 | note | ACTION (Hold, Monitor, Witness) - H
bfc86560-54b2-52c2-b331-370044ec2d75 | note | Detail - Drill holes as specified
3b483d8e-6642-50b8-8708-75eed815250c | note | Frequency - During Construction
435bf875-0b5b-54a0-b8f2-94a14cbc2bd4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
39f9ca12-afc6-5151-a7af-cb7ae16f75bd | note | Conformance Criteria - Drill within +/- 2 degrees and +/- 100mm of position
f114fce4-b0ff-5ff0-92a3-10593e613b0b | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 40 - Installation of anchors
f1be3477-996e-5e52-afad-2622d5072868 | note | ACTION (Hold, Monitor, Witness) - W
6e3283ab-2052-5003-be3d-4337262c28eb | note | Detail - Install anchors as specified
08aaed4c-3bbe-581f-b660-2ee5f476d5af | note | Frequency - During Construction
24854203-8d18-56b2-bfed-f78ae8ea3a8c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0cb8a8e7-3b00-5fd8-9f33-1cf52e00ed6a | note | Conformance Criteria - Ensure lengths are that specified on the drawings, centralises in place
54f5dd7f-efed-54b3-8091-b22a9db93245 | note | Records - Subcontractor QA Records
| checkpoint | 41 - Installation of anchors
d86887d3-1bd9-5a21-9a4e-d77b9d5cd106 | note | ACTION (Hold, Monitor, Witness) - H
ded0f554-af93-5ac5-9473-5a510f8e502f | note | Detail - Install Grout - take sample of each batch. Note holes not to be left open for more than 24hrs
4d6cbae0-b6f0-55ab-af98-a070f8734d1c | note | Frequency - During Construction
87140848-28a1-5032-8104-1bb8e53031b3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
a1a94c4f-b792-524c-a446-bbf6f5a3a354 | note | Conformance Criteria - Compression cylinders to be tested at Lab
b90d8b07-c65a-56b0-8d11-5b999c70856b | note | Records - Lab Test Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 42 - Installation of anchors
6f60960d-66cb-5524-88af-91fd86fe5761 | note | ACTION (Hold, Monitor, Witness) - H
0730be2d-6f01-5d09-ba81-5a38b84eb884 | note | Detail - Test of Production Anchors - after 7 days when the Grout strength has reached 30Mpa
376e36f9-6629-5965-b756-8e9edf68acc0 | note | Frequency - After Construction
19b89412-607f-538f-9b15-2d056628c7d6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
785e6a09-30a5-568a-b3fd-c843a358f6ee | note | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
78c1fa38-e6ee-5152-935b-6b1b2ed883f3 | note | Records - NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 43 - Installation of anchors
37d049ba-58d6-5bdd-8bb4-095377fe156e | note | ACTION (Hold, Monitor, Witness) - W
44710382-4632-5c71-89b3-594825c3f273 | note | Detail - Extend anchors to tie in with wall face and install washers, nuts, and corrosion protection as required
a290cfc9-685f-538f-8819-5175e6839c08 | note | Frequency - During Construction
9e852cf1-4be9-5d50-aa08-9b84a6f92deb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
f52e8243-e303-5f9c-a4b9-a8fd7e75aa99 | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
41875525-5d0e-57cc-80e8-680a7d4d896f | note | Records - Delivery Dockets
| checkpoint | 44 - Installation of anchors
f6703789-1138-5581-8ba5-9aa248ad8319 | note | ACTION (Hold, Monitor, Witness) - H
2e7160ea-a47d-5f02-be52-84820a66f7a7 | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
0fe9b384-acdc-551d-8e0b-4568d750307e | note | Frequency - After Construction
748afbc4-8b3c-576f-a5a5-9fce86e19ee7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
33d1b9af-010a-51ba-8e70-5561e19fdf38 | note | Conformance Criteria - CPS Engineer to give approval via a NTC
494c715f-640a-500b-ac46-99296aa205a9 | note | Records - NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 45 - Wall Reinforcement (anchored section)
cc996206-e7b0-598d-91be-4c6cf058185b | note | ACTION (Hold, Monitor, Witness) - W
37cfe1d9-a132-5623-8499-556f5145c60e | note | Detail - Check supply and installation of reinforcement in wall
5f5a3498-a53a-5aba-a6db-f8147a1789aa | note | Frequency - As required
d860807f-d525-5634-9d8d-a1e1a215068e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
b7056cd5-7892-53a4-9d52-e75ec5caa114 | note | Records - Subcontractor QA Records
| checkpoint | 46 - Wall Reinforcement (anchored section)
8106273c-926e-5dec-b1bb-457ced577629 | note | ACTION (Hold, Monitor, Witness) - H
d998a4d0-d15d-51c4-90ab-f1e1edc261e1 | note | Detail - Arrange for inspection of installed reinforcement
1a10a070-60c1-5bd5-82e9-8914080116b0 | note | Frequency - Min 48 hours prior to pour
8a0940e4-cef5-55c3-9901-7285e7f0e422 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
04fbee31-34fd-52c3-b75e-340ea0ea3a15 | note | Records - CS-4096 Bottom Driven Pile Record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 47 - Slope Filling Operations
80648372-7225-5782-97ac-596caff823da | note | ACTION (Hold, Monitor, Witness) - W
41e0e1a8-0999-5963-8e3e-3c9fcaf58880 | note | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
31d0b5be-f8c0-510d-9f20-1ca9d6169980 | note | Frequency - As required
e20c72c5-df8c-59e6-ad2a-914ad3cfe26e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
ad29b1c8-f715-5684-923e-df671906be30 | note | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
| checkpoint | 48 - Slope Filling Operations
6709cf61-ce82-5f42-a3f2-1e3251808556 | note | ACTION (Hold, Monitor, Witness) - W
3b1f0c07-cc58-5fce-a026-87b89d58981f | note | Detail - Fill placed within 1m of structures or obstructions shall be placed with care using suitable equipment and shall be placed 100mm thick and shall be 1 lift higher than the level of the surrounding fill
08f1c5be-370b-5a46-9867-54493d332638 | note | Frequency - During fill operations next to structures or obstructions
cbc77a84-1725-5eac-8f9f-2224b13efbb2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
aa756d0b-39a2-572b-a117-9d3b43746ef4 | note | Records - CS-4020 Bulk Fill Earthworks Record
| checkpoint | 49 - Slope Filling Operations
d68b5832-a85f-52e2-9280-20f79b6e6ab4 | note | ACTION (Hold, Monitor, Witness) - W
70cbbb01-5dec-550e-bd19-9a1c53131f82 | note | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
65deb6f0-cc79-577d-82bc-acdd891d9d99 | note | Frequency - Daily visual survey check
27b3916a-c0af-50b4-b4b2-c9abccbfdf6a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
2191dba4-9cbd-5cae-89b2-c60869720bec | note | Conformance Criteria - As built drawings
a3f6d199-89ce-516f-882b-6af8233a4de5 | note | Records - Survey receipt
| checkpoint | 50 - Slope Filling Operations
1cd90cf9-661d-5812-ad7e-79c4655f7756 | note | ACTION (Hold, Monitor, Witness) - W
d30cf8d2-4c32-5b38-ab7b-5cbeeee6f58b | note | Detail - Fill placed in horizontal layers no greater than 250mm and compacted. Site Engineer to instruct lab when and where to carry out testing
85c72bb7-7cb1-5b42-9d4b-190098f7a8a8 | note | Frequency - As required
ed3f1f12-5a5e-5f73-81b3-a54f0fa534b6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
0e3da47a-0d8f-55d5-b160-30a9587f09f8 | note | Conformance Criteria - In accordance with specification
c033f793-58f2-529a-a798-09d6b7e85c45 | note | Records - CS-4020 Bulk Fill Earthworks Record
| checkpoint | 51 - Install Erosion Protection
1bf23029-9b2b-55c0-9bad-a11508301f53 | note | ACTION (Hold, Monitor, Witness) - W
dbe65ab7-9b54-581c-8f60-f10062d3b1d0 | note | Detail - Install T-RECs tuff matting or approved equivalent
b5f965f6-5a8b-5a5e-bf72-91a43128d2e0 | note | Frequency - As shown on drawings
81ddd361-979d-54fe-aa29-3144df007d7e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
dfc57650-7fb3-538a-be8c-d3511c18de91 | note | Conformance Criteria - In accordance with specification
228da73a-88c0-5130-91a0-a565a26bb9d8 | note | Records - Photographs
| checkpoint | 52 - Install Erosion Protection
73713737-5c0f-51ac-9402-e803a68ea621 | note | ACTION (Hold, Monitor, Witness) - W
12cd1247-9175-5ed9-8bd7-d4f442f9febf | note | Detail - Install anchored erosion mesh as specified
e8424d5c-9b82-5055-aa7b-91dc13f80072 | note | Frequency - Details as per anchoring ITP Section
9d4207a3-2a5b-5da1-9602-9555d858c698 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual, Measure, Testing's
fb4f26ad-b576-56f1-b62e-6156b3da88ec | note | Conformance Criteria - In accordance with specification
9fb1a7ba-b5a1-532c-bc8b-211beec72199 | note | Records - Subcontractor QA Records
| checkpoint | 53 - Install Erosion Protection
f8b69db1-47f5-5d30-be51-ff78e7468bbc | note | ACTION (Hold, Monitor, Witness) - W
c5a244dd-b19a-5187-b7fa-eae38dda31a6 | note | Detail - Mesh - Greenax steel mesh or similar approved product installed and joined as per manufacturers guidelines. Fixed to anchor heads correctly, and fix to wall
450084db-5764-541a-8963-7a9b9819102e | note | Frequency - As required
724263c0-0a59-5457-9968-2c3d1ca2d056 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - During installation
ad64122b-cd0f-5501-8ca2-ff24fec099c5 | note | Conformance Criteria - Visual inspection, extent to be confirmed on site with CPS Engineer
bc510f89-e24f-5390-8864-1a28dd28c150 | note | Records - Delivery dockets, Photographic evidence
| checkpoint | 54 - Install Erosion Protection
3c94e5b2-0293-5444-8f28-9208c643c72a | note | ACTION (Hold, Monitor, Witness) - W
33d82d7e-9c04-5dbe-ac86-ed42bb70572f | note | Detail - Ensure that placement of rock material on batters is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked.
0478df86-4da5-52d8-846c-291007a6c78c | note | ○ Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material. geotextile is placed as detailed in Specifications/Drawings with the required laps.
282c6c12-64c0-593d-8058-2cfe47143031 | note | Frequency - Daily visual check
ca13898e-cd45-5964-bc54-f18fbc1da0e6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
61aff1d4-e76f-5ce3-b347-67157bd9f005 | note | Conformance Criteria - Specification
79799cf3-75d3-54d2-921d-527a6d9dbcb5 | note | Records - Photographs
| checkpoint | 55 - Pavement Construction
59c98e56-12d3-553c-b7b6-577fb731a007 | note | ACTION (Hold, Monitor, Witness) - W
42209831-ce90-5054-a2f3-2a48b37bbbf1 | note | Detail - Pavement construction and tie in as per specification
729316ce-0f60-53bc-a176-7db82aab43ce | note | Frequency - As Required
de40b8c9-4017-5e02-831a-b4910f23a76d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
a5eb3eb1-0ce5-54ea-aa1c-9e97c23c572c | note | Conformance Criteria - As per specification
| checkpoint | 56 - Pavement Construction
4e64076f-e73d-5bb0-8686-31b6ba8d9040 | note | ACTION (Hold, Monitor, Witness) - W
20ba0458-8cc0-5767-8e2a-01175e0a371a | note | Detail - Guardrail Installation installed as per manufacturers requirements
2bd1c680-c805-5d5c-8cf0-31fd988f31b1 | note | Frequency - As Required
34aca85e-c04e-50be-9197-5c6ce2673342 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
f270069c-353b-54ff-848e-20f5899ea855 | note | Conformance Criteria - As per specification
| checkpoint | 57 - Survey As Built
92238f9d-25be-542c-a38e-14fd19232225 | note | ACTION (Hold, Monitor, Witness) - H
9c5b113e-0176-5055-b416-a44352b38ad1 | note | Detail - Ensure all works comply with design prior to carrying on with next construction process
17300970-02a9-5c24-a542-28984bcf4054 | note | Frequency - At completion of sub soil drainage line
20b0938f-17de-594f-abf5-5693594f0453 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
6f8c9907-65b2-5639-8aa6-4eff15b726be | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 58 - Confirm testing requirements met
ec5173e6-daf4-5d51-8806-c95cc2384c45 | note | ACTION (Hold, Monitor, Witness) - H
e3de4b3d-394f-5510-95c6-c342247fb7b4 | note | Detail - Ensure correct no. of test sets performed for fill testing
36c6ae7b-d2db-580c-9341-d0a4c739eb46 | note | Frequency - At completion of Lot
9858d43f-5c9d-54d1-b81c-8c2aeb2f7d3b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4c56c10c-5a99-5bff-a1de-d53e5500ecd2 | note | Records - Test results and calculations of fill volume
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 59 - Lot Number QA File
9905a3ff-24ef-501e-99a3-a77ca2bcafdc | note | ACTION (Hold, Monitor, Witness) - W
266b672d-4ee3-5001-ad44-dffedaf56b1d | note | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
ca12fbb1-f10d-52d7-8560-d4fa6962a6c3 | note | Frequency - At completion of Lot
b9ac2b24-faed-5ad1-88f3-2fb1afae33e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d66a8565-58a3-55fe-847c-3d6cda49c56c | note | Conformance Criteria - Ensure all QA is uploaded into M-Files
a935dc42-e83a-527a-8d50-37d46df1d37d | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 60 - Construction Report
415dcb14-8a2c-5d34-a38c-17b6753209ae | note | ACTION (Hold, Monitor, Witness) - H
3b8c60c4-a1d6-5cd7-be9c-d56c9e4e61ae | note | Detail - Construction Report identifying the actual types of materials and methods of construction used throughout the Contract Works.
81f2e026-b08a-51e1-9e64-774823df0d71 | note | a) Explain the problems and defects encountered during the construction of the Contract Works, and how these were overcome or put right;
380f3391-c893-578e-ade7-633a847b6dde | note | b) Comment on the remedial and corrective actions taken;
1350f4ef-a08c-552f-9c9f-443a9d21af37 | note | c) Comment on any construction outcomes that will impact on future maintenance;
15ce5341-2fed-5438-ad7f-141d28f1459c | note | d) Include a complete record of all laboratory (and other relevant testing) information for all Materials used in the Contract Works;
f691588b-4e5f-50e5-8a7b-adb3fb9da934 | note | e) Include mill certificates for all reinforcing steel, pre-stressing strand structural steel and anchors used in the Contract Works;
5921e714-55a3-53b3-88d3-c392054cc506 | note | f) As-built survey along the highway centreline, providing co-ordinates and levels of the highway, at maximum 10 metre intervals, certified by a Registered Surveyor. The survey shall be in terms of an established LINZ datum;
5b27fb06-0d6e-5bc5-a8eb-f6e2b81b7889 | note | g) Material warranties;
05e7fea4-0847-5da5-8599-945967d713f9 | note | h) All information pertaining to the construction of the Reinforced Soil Slope (RSS), MSE retaining walls and scour protection, and any future maintenance requirements.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 61 - As-builts
e1747d79-d1e4-5281-8e0c-63487d12b892 | note | ACTION (Hold, Monitor, Witness) - H
f7a737c1-ad15-5901-b74a-de0847b4bfd3 | note | Frequency - At the completion of the Lot of work
d6c48777-c5a0-5423-bf43-e061dfd63ad1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
7b869b47-8cb9-530c-9eef-9a452e30b928 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails | itp | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails |  | f8bb0e78-656e-47be-8c8c-336fb7830f4e
| section | 1. Minor Earthworks
| checkpoint | Project Site reps.
00440c30-d547-5ec3-8352-9a1e381b689b | textbox | CPS Eng.
ebe45485-b0a7-5d68-928d-4a5e5a34ae7f | textbox | Site Engineer
bf12f35f-64c6-5c3e-929d-6ad6e7acf19c | textbox | Quality Eng.
| checkpoint | 1.1 - Clearing & Earthworks
d8e32a5b-d891-5032-acfc-f96796cc066c | note | ACTION (Hold, Monitor, Witness) - H
729490f3-b0e0-558a-bfe4-7c5afdf54f3f | note | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
cfde101c-023b-5a4d-b86b-df6f78bc674c | note | Frequency - Prior to commencement
4d2054fe-588f-5ecb-9eca-24cefbcbdaca | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a0fe6f21-4387-594c-aa12-b506a9626b01 | note | Conformance Criteria - In accordance with TNZ F/1
40c2be53-ca8b-5b18-af9a-93466b45d860 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Cut/Fill Required
03822524-35fb-5722-a7b7-e43508f9bf84 | note | ACTION (Hold, Monitor, Witness) - H
3c64e834-39d3-5be5-8e1f-c39bb14f58c4 | note | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
220bdb98-009c-5a65-a598-3aa0920facb9 | note | Frequency - Prior to commencement
12413c99-7f97-5ef0-9052-9efc09b203a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
1d8f41f3-e491-5e25-8c24-ccd8b4fea872 | note | Conformance Criteria - In accordance with TNZ F/1.
04e9c7a5-0509-594a-aebf-c76687573c6c | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| section | 2. Material Production
| checkpoint | 2.1 - Material Compliance (Rock Works)
28fe644c-2fc8-5e1c-be20-ac9237f4c651 | note | ACTION (Hold, Monitor, Witness) - H
c94ed8b6-0612-5220-b9e1-fefdfa430ec5 | note | Detail - Material to meet specifications dependant on material type selected
5deb11ce-db25-5af5-ad9c-7223a1279680 | note | Frequency - Source test of each material used (minimum 10 rocks per source)
b374d0b7-6243-5820-8d3f-b658d5eef44c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
fb794b5c-f38f-598a-86ac-a14141793e2d | note | Conformance Criteria - 1. Schmidt Hammer test (minimum of 10 rocks per source) and 90% result ≥ 50 in all direction or
121ac9b8-002d-5500-b27b-0668d060ea90 | note | 2. Weathering resistance AA,AB, BB or CA (NZS4407)
de3f7317-71b6-571f-b66e-c04d13005c78 | note | 3. Specific of gravity ≥ 2.56 or up size rock to compensate
84b18f81-e93d-565e-8cf0-9f38dfe5a260 | note | 4. maximum dimension of any rock ≤ 3 times narrowest dimension
878885f1-cf5d-528f-b87d-8693743a5671 | note | Records - Lab Reports, delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Material Compliance (Rock Works)
164d5bc9-50f5-5672-ac8a-d89f94579f75 | note | ACTION (Hold, Monitor, Witness) - W
b3011cc9-5f3c-5651-800e-853e010a0fd9 | note | Detail - Consistency though construction and clean of dirt
271b0d4d-e3d4-525d-b620-38c5f92641b6 | note | Frequency - Each rock source
333a404a-3550-58be-982a-01421b2c47a0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitor on site
9607f717-3b12-5d24-8d71-a8e1d2b363e4 | note | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
af699c13-6d68-5f49-a55d-87c267c0c0b4 | note | Records - Photos
| checkpoint | 2.3 - Material Compliance Subsoil
6081ee81-3bbd-50ef-9afe-1fddc617881a | note | ACTION (Hold, Monitor, Witness) - W
26a7fd49-04f3-5cc7-9ba6-cbc5fc273121 | note | Detail - Material to meet specifications
870206bf-a920-5b2c-acbe-0ce44929460f | note | Frequency - Each rock source
dd1979d1-ddcb-529a-8d88-73eb7dc28ccd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier certification and delivery dockets
10b1a9ff-19cf-55ea-9812-2e9af4758fcb | note | Conformance Criteria - Prior to megaflow installation
1bd1d1e3-5051-5d0e-b86c-595031025c2d | note | Records - Collect all delivery dockets and photos
| checkpoint | 2.4 - Material Compliance and Methodology Approval
7caa20f3-d02b-5c8b-a3dc-602c94147c75 | note | ACTION (Hold, Monitor, Witness) - H
a67d9443-6850-5b4c-b129-32b9ee76c030 | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
01915dea-3612-5b83-a266-6ec8c355c83b | note | Frequency - Prior to commencement
39516644-e5cf-5cf4-b42a-44ef7970fe81 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
ead264c6-4174-553d-b815-6774599f4e9e | note | Conformance Criteria - Grade 500E soil nail
4e3f27ca-d44f-529a-9454-b3ed3341923d | note | ○ Class II corrosion protection
bb84d162-c6e7-5a4a-9f40-9099964ac1d5 | note | ○ Lengths and diameters shown on drawings are the minimum required
093a306a-feb3-515e-b620-df349582b000 | note | Records - Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Concrete Quality Plan and Work Plan
bd7a686c-5a48-57cf-972f-5afe51b32dd9 | note | ACTION (Hold, Monitor, Witness) - H
15800eac-dab2-5c9a-8855-b268ac0b679b | note | Detail - Concrete Quality Plan and Work Plan
19fab772-f4e9-5d16-948c-6fdfafad9027 | note | Frequency - Prior to commencement
b4dae406-60c7-5cc3-a6cf-cdf579737686 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
a05283eb-5cd2-51b8-a786-0ca540f9d40b | note | Conformance Criteria - Refer to section 8.3.1 for the Contract Quality Plan and Section 8.3.2 for the Work Plan
3ff66707-3488-5774-a261-1d29dd245325 | note | Including:
b3988177-898a-518c-a212-350c5b9c7958 | note | – Name, qualification and experience of concrete works inspector
846169e8-564c-5eed-ac08-72f046806823 | note | – Form and content of concrete placement card
6c32256d-78e9-5b7a-a811-9e8a1863eb22 | note | Records - Email / RFI
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Concrete Supply Plant Approval
23ae677e-4174-505a-b28a-fd20786b21e3 | note | ACTION (Hold, Monitor, Witness) - W
068c7f45-dbae-530d-8a8b-8cb22ca5f460 | note | Detail - Details of concrete supply plant, copy of certificate of audit for plant
26d43b1e-7fec-59ae-b113-4cdf385033f2 | note | Frequency - Three weeks prior to pouring concrete
9fff83ed-50f5-5bd5-8011-a3f7c0cbaea0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
57af2f6c-94b5-557a-8cc6-40c5d753a922 | note | Conformance Criteria - Including:
b66295a8-a1d7-5792-a0e0-08e5f33fe3d4 | note | – Plant test Results
2bb5d547-de6f-5441-97af-8efda291090f | note | – ASR Compliance Records
67c021e9-c770-5715-b6b9-3d151f41b452 | note | Records - Email / RFI
| checkpoint | 2.7 - Reinforcement Steel Certification
a497e2a0-3e8b-5883-842d-26babcebb503 | note | ACTION (Hold, Monitor, Witness) - W
7ce3e3aa-a52d-5a9d-9acc-9d4e6416b8df | note | Detail - Reinforcing steel manufacturers test reports and certificates
097ea0ba-8fcb-594b-90c6-f083fbec7f7f | note | Frequency - Prior to undertaking works
08ff3c71-7e97-54e6-a02c-b84321a509cf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
2ffeec80-91ce-5734-bfb3-e917e0fdedfc | note | Conformance Criteria - Including despatch records
e264e7d2-6100-52fc-9cc3-cb98bc9edef0 | note | Records - Email / RFI
| checkpoint | 2.8 - Concrete Mix Designs
5bf1e082-03b3-54f8-bb9c-c23648b9d8a4 | note | ACTION (Hold, Monitor, Witness) - H
bccb9bd7-8986-5933-b62b-a7fa4086ef4c | note | Detail - Submit all concrete mix designs, trial mixes and compliance records
e15e21d1-8f01-5dc9-bb65-ed2481731184 | note | Frequency - Three weeks prior to pouring concrete
870f2ab3-65e5-51ec-a025-3e5c57bb0929 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
ed6ee4aa-207d-5089-80aa-ae565d96f511 | note | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
27f39fc2-11e8-5b6c-a248-d15782f9e153 | note | Records - Email / RFI
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.9 - Grout Mix Design
dbfdf946-e741-5486-87b3-713d360c6725 | note | ACTION (Hold, Monitor, Witness) - H
9e3cb908-0e0e-5d4f-9fec-54a3651bf0f6 | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
ebd73716-7b0c-549f-b7a3-8de72dc245f8 | note | Frequency - Prior to commencement
3ab055a9-cc7a-5f51-82ce-1e2f3374ac18 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
578a411d-a49e-51a2-96b3-d4c0cabc96d0 | note | Conformance Criteria - Mix design to be approved by CPS Engineer three weeks before commencing construction
701112f2-c8b4-563a-bec5-bde53c2e377b | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.10 - Grout Mix Check - On-site
3d93ec34-0a3f-5c53-975a-7397bcb06b14 | note | ACTION (Hold, Monitor, Witness) - W
551706f9-ddc8-5d7f-949b-1855e6adc162 | note | Detail - Grout checked if its free from lumps & segregation
c9bf6c59-423d-585e-9ea5-2b5f9eed5001 | note | Frequency - Prior to commencement
76f3813c-e270-51ed-8c28-f57b45f45060 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| checkpoint | 2.11 - Alternative Drilling Fluid
a1e41f75-5129-5694-ae03-a90582771c04 | note | ACTION (Hold, Monitor, Witness) - H
67edb5bd-e3e5-59ac-a868-95ec24a67878 | note | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
87b633af-c4ad-54f7-98a0-bdd0cfcb5e74 | note | Frequency - Prior to Commencement
a2b351d7-0089-5faa-a480-b0359d12ea51 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
b0317148-c760-5e8d-ad77-fae58189b073 | note | Conformance Criteria - If required
| signoff | AUTHORITY HOLDPOINT
| section | 3. Soil Nails Installation
| checkpoint | 3.1 - Survey Setout
d753f58e-b1c2-5c9e-917e-54e653901403 | note | ACTION (Hold, Monitor, Witness) - H
b0164de0-788b-502e-96ef-b614040858eb | note | Detail - Arrange for a set out survey to be carried out & check against design drawings including sacrificial nails
dea9a925-99ce-5e82-bfd0-7b25477fdc05 | note | Frequency - Prior to commencement
f74c13f0-52d7-5455-9152-1d335708d843 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
2a59749a-dee4-54ad-bd9d-c9d91422f603 | note | Conformance Criteria - Consistency with Construction Drawing
7b12dc5a-ff08-5c88-a7de-c08d56d3a96a | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Soil Nail Construction Methodology
2fa26c26-0a90-5b55-a579-14c8f5134f6e | note | ACTION (Hold, Monitor, Witness) - H
b5ad95aa-5ead-5052-9fab-9eb85e6b10f0 | note | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
0b6737f6-73a4-53d5-9b32-e2923ed5f520 | note | Frequency - Prior to commencement
a4adf54d-c367-5eb8-96d4-cdaa8689d716 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
3d15c801-295d-5830-9615-b8a2eafb0216 | note | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
ffe7357f-b16e-57b7-bd1a-5a2778ef8c55 | note | Records - Methodology
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Trial installation of Sacrificial Nails
51578571-b723-512a-acd8-e85deaf9e49b | note | ACTION (Hold, Monitor, Witness) - H
d1e0a6c5-3fa0-50ec-8da9-a82ed67f6c18 | note | Detail - Drill hole, install Bolt/Nail, install Grout. Location for Sacrificial Soil Nails to be agreed on Site with CPS Engineer.
23ca16e1-bac4-565b-a54e-0f0c884b14e8 | note | Frequency - Test
cdf42f4f-6b9a-51ae-a868-bb3d194cbbca | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
f389107f-ba77-55f0-ba5d-5b5161574923 | note | Conformance Criteria - Bore logs of Drilling, installation record
3464434a-2773-502e-8a2c-499a301070ea | note | Records - Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Sacrificial Nail Testing
eb5f4f0a-d16a-5c40-9f8a-91632f5b803b | note | ACTION (Hold, Monitor, Witness) - H
2539aa9b-2eb8-52d6-9f51-4d3cc60f25a6 | note | Detail - Test after a 7 day period. Load up to the specified requirements with the CPS Engineer overseeing proceedings
6eb35d3a-1bc3-5acb-9cc4-78b694f8d263 | note | Frequency - Test
9badf5b9-c81c-5d32-b2e3-92f95b8834ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
0d81fd0e-6b8a-569f-a6ed-d2f04144ecb1 | note | Conformance Criteria - Design Team to approve grout test result prior to sacrificial testing being commenced.
3cbc5e8c-8505-5e79-856d-40ae1017b9be | note | ○ Calibration of testing equipment
7728fab2-6338-541e-8116-2c3dd4b3a730 | note | ○ CPS Engineer to observe testing and provide feedback.
12517c57-d435-5711-8e50-29a5ebbbc1a1 | note | Records - Instruction to proceed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Working Bench
48c68db0-ee87-5b63-b26f-bf02a9184a8f | note | ACTION (Hold, Monitor, Witness) - H
618cdb2e-cf4a-576b-ac4d-ce1732451376 | note | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times.
a59514a2-836b-5e45-b6ef-03733fb5bfaf | note | Frequency - Prior to commencement
490d7de9-44b1-5419-81ec-58a34275f52f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
6897087f-992e-5cea-a0c3-715579ea5701 | note | Conformance Criteria -
2ac2e294-5691-5f7b-910a-e83f35eabc3d | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Production Nails Location
3072a15e-51f6-54fb-822a-c325d206847b | note | ACTION (Hold, Monitor, Witness) - H
7178f942-46b8-55ec-a196-18d943a7ffac | note | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
722c34b6-7036-552e-9893-ce863953a615 | note | Frequency - Prior to Trial
54126a1f-048e-5995-8237-3fb47f33e7e8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
f15aa840-45d8-5912-911e-d9b8782fae5e | note | Conformance Criteria -
96d47d32-4886-54d0-b858-cc55b68eb9aa | note | Records - Photos, Site Diary
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Production Soil Nails Bore Hole Drilling
8f5b30c4-f447-5c5c-a165-49bb99296bc5 | note | ACTION (Hold, Monitor, Witness) - W
b3d7e6b4-9503-53c4-b8e7-de36c9155057 | note | Detail - Drill hole
4e9e0a0a-c891-58bc-bcbd-bd9537659463 | note | Frequency - During construction
faadf23e-bc09-51ff-b67e-72b8d8e20321 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
a99b4db1-9cd1-5175-bdaa-563630cb3b27 | note | Conformance Criteria - +/- 2 Degrees
ba13561f-fb30-5f6e-a593-18d1353757f2 | note | ○ Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
c6e76951-9739-5009-9974-1745e7512648 | note | ○ Submit all installation records for each soil nail and pile.
3e213ad5-9efb-51ea-ae73-00688cbbea3d | note | Records - Drill Logs, submission records
| checkpoint | 3.8 - Bore Hole Flushing
b3139f5a-809e-5048-9556-805a393be159 | note | ACTION (Hold, Monitor, Witness) - H
45a0a594-7a69-5c1a-89cd-7b889d8cfa85 | note | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
f6df731f-6df7-5c43-8fa0-ea5a365be57d | note | Frequency - During Construction
3e322e2e-b63f-5edb-87fd-d2b027e4424b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e06f1abf-e983-5dee-8a86-3d5c04617bdb | note | Conformance Criteria -
5adb451c-9325-5b19-823b-40f4841f3faa | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Soil Nails Insertion
846ac870-bf89-5fff-a0c2-45bc3084410a | note | ACTION (Hold, Monitor, Witness) - H
1efa8030-f93d-56ce-b79c-319b12cebe6f | note | Detail - Insert soil nails as specified
56066f57-f0a8-592f-836e-bb5cd6ba398b | note | Frequency - During Construction
4d4f4883-a5ce-5eb1-b04b-1a030f590947 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
79e71df3-89e8-51b3-88a4-af34f0132d45 | note | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevent damage
5733789b-d7d5-5500-9398-a0381e5dcea0 | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Soil Nail Logging
b6eb0ab0-0f07-5567-b71c-de347af66974 | note | ACTION (Hold, Monitor, Witness) - W
62b8a2b5-9098-56ff-b12f-200aa3566181 | note | Detail - A record is to be maintained showing the type and installation date for each soil nail
e790fd68-807b-55e1-9eb9-7b58f57726d9 | note | Frequency - During Construction
20eb6728-f7d8-571b-a258-b917480c9dab | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
23b18756-5d1b-5d12-b625-d73564f3d8c0 | note | Conformance Criteria - Installation records shall include:
e7f60210-e97f-528a-9cb0-22ecd96c2a42 | note | – Length of bar
16f0f5c9-2159-58a6-bafd-aab114062d62 | note | – Depth of drill hole
b1083823-08dd-5a71-8fa8-8e27a00b1ea6 | note | – Inclination/Verticality achieved
00452d58-1573-51fa-8ffc-704639454240 | note | – Level of grout placed
28f28e56-f651-5b6e-b24e-777a7ca65bf3 | note | – Batch numbers associated with grout placed in each hole
1f8c1a8c-0d9d-5863-899f-9565858e7d98 | note | Records - Subcontractor QA Records
| checkpoint | 3.11 - Grouting
971d1ff3-a15e-5960-a9b0-c11d22581638 | note | ACTION (Hold, Monitor, Witness) - H
0e42a7b9-c971-5e62-a447-42e878868bfb | note | Detail - Install Grout. Install Grout on the same day of drilling unless otherwise approved by Designer
9667c879-eab6-5d77-9947-b4103c10231d | note | Frequency - During Construction
b4a87a53-a35b-5de4-9af5-269eb4224ff8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
03b24b0d-940d-5939-82b3-25d1f65883c5 | note | Conformance Criteria - Including:
21f1b4e5-b494-5ee8-9be3-f6c9c2bc8997 | note | – Concrete despatch records
926d95c6-2382-54da-b058-1d57b4e4bb46 | note | – Compression test results
8a09b718-8c63-53e1-b273-d5a52f3a61d7 | note | – Slump and spread test reports
4cdf1e0b-39ca-5ce7-b288-dab6b4b57280 | note | ○ Must notify CPS for any failed result and cease works until resolved
58a96c0f-2d90-58e8-92f4-41234445bc60 | note | Records - Subcontractor QA Records and Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.12 - Grout Sampling
c4b1baee-e035-58cb-a86f-9566fd292ad9 | note | ACTION (Hold, Monitor, Witness) - H
88b28117-88d8-572b-8ccc-261488567357 | note | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
0d6abb6a-6cb2-535f-b67f-2be95b0c1441 | note | Frequency - During Construction
e25aa4c9-d31d-587b-a15f-152b9c0ce2b1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
1ed66778-40bb-5197-a943-ca5eb28906dd | note | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
1c530408-57a1-53fb-a7b6-240357c9e5f0 | note | Records - CONQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Grout Loss Recording
a509821e-9907-598e-b998-a2d5abfb4edc | note | ACTION (Hold, Monitor, Witness) - W
2a6003ac-5432-5f6c-82e9-4070ba26df08 | note | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
1011006b-1dbd-59ec-ab46-9c407f85afb9 | note | Frequency - During Construction
01b5507f-e719-5ea9-b8ff-56fcbe6ed4f5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
00a16777-1259-5f46-ab1c-6083308a9239 | note | Records - Subcontractor QA Records
| checkpoint | 3.14 - Bolts/Washer/Nuts Installation
49b62731-2f5a-5c7e-8d29-a7d5371e1582 | note | ACTION (Hold, Monitor, Witness) - H
88bab05a-1682-52d5-844f-50aab0c8a0ce | note | Detail - Install Bolts/Nails washers & nuts
08fb1317-f0be-5a70-9fc6-06d0c7a5aadb | note | Frequency - During Construction
15192c38-3b9f-5807-be5e-455c0a3d404a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
f8932789-1654-5bf8-a732-f1a2194c75e4 | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
537be528-dc3e-55c3-a99e-d10f9365eb2b | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.15 - Testing of Soil Nails - Each Row
9313176a-f7f0-5b07-a506-50b5a552a01e | note | ACTION (Hold, Monitor, Witness) - H
85cbe815-1f5c-5cfe-a52f-a50b8e19205d | note | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
b09e91fb-3059-54b5-9ab1-8cd311865a2f | note | Frequency - After Construction
e9de091b-dbea-5a40-a2a3-9ebd8c5b2320 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
dbc7cd60-94f3-5630-a945-0c8b6a3bdfb6 | note | Conformance Criteria - Certifications of all testing equipment within the last 3 months
bf534be5-f59a-5206-a93a-d60d5e0aecf2 | note | Records - Certifications
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.16 - Testing of Soil Nails - Minimum Resting Period Before Testing
ef5a51a8-f266-5c07-886c-37141626b172 | note | ACTION (Hold, Monitor, Witness) - H
64c56c14-c982-5940-aff1-90052f72bd9c | note | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
e9ac28a1-b309-5e5e-8c11-fcae26e27be2 | note | Frequency - After Construction
fe866452-51f8-5456-b826-5a8928011f14 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
7157dc27-9baf-5e28-b6fd-834eef1d9fb3 | note | Conformance Criteria -
d38ba849-051c-5f0a-b380-c6518e9a481b | note | Records -
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.17 - Testing of Soil Nails - Testing Specs
44d3e066-d710-55a9-b81e-803ad07ec1f1 | note | ACTION (Hold, Monitor, Witness) - H
16a3adc7-e67a-5d0c-abb9-7d5672c56c28 | note | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
9b634919-238e-59dd-be06-5e6def946b64 | note | Frequency - After Construction
326a2581-badd-5222-914f-e2aabaa2af9f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
3b49f46e-e212-52af-af68-90c83eeb1864 | note | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
872e8e78-5a78-5763-b052-f65d54a6f036 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.18 - Final Inspection Before Next Row Commencement
e691dc89-f4c8-5c26-9625-aba885df213c | note | ACTION (Hold, Monitor, Witness) - H
ad83d3d6-15de-596e-a404-8ab69e46ec5f | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
d652fe92-5ed6-5c24-b744-6ce24b75380e | note | Frequency - After Construction
65458c40-d98d-5906-8059-115cc9be0ef1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
eb5c5f6b-e0a9-5218-a59d-d582b1a19b81 | note | Conformance Criteria - CPS Engineer to give approval via a NTC
54dde10a-142f-5c02-b484-51cd901e1f05 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Subsoil Drainage
be85bef3-4ea9-53a3-aa5d-63ee4fdee561 | note | ACTION (Hold, Monitor, Witness) - W
ddabe305-4ac7-5a10-b754-4622c370976e | note | Detail - Install subsoil drainage as required in accordance with specification
226fbacc-e384-5ae8-a978-8d261c51ac13 | note | Frequency - During Construction
b4772702-3c0f-561c-9041-4b01d2bd4dcb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7ac86e26-4c50-5445-80b8-4b909860c95b | note | Conformance Criteria - As per drawing 1.5m alternate with weep holes
661c65ef-ada8-55ec-8357-2c628d520f20 | note | Records - Photographs
| checkpoint | 3.20 - Shotcreting
74a9857f-3a9b-59df-989d-788ba020f6b5 | note | ACTION (Hold, Monitor, Witness) - W
e16e1d48-88df-527a-9f24-ae5a0d6c058f | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
42b2eae3-6149-5063-b873-2dfed7da7dcc | note | Frequency - During Construction
a76d8b99-3485-5abf-b4d1-1ef8f55844f2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f8534172-df62-5b5e-8b6c-65bae83949ec | note | Conformance Criteria -
356d6c83-811d-5f5b-b0a5-211c6a4e2137 | note | Records - Photos
| checkpoint | 3.21 - Pre-Shotcreting Inspection
7a48db10-7a67-57d2-8e4a-d169c20e4c81 | note | ACTION (Hold, Monitor, Witness) - H
8eec79dc-bc60-5954-ad9e-27f3cc2d0b37 | note | Detail - No concrete shall be placed until the CPS Engineer has had the opportunity to ensure the drawings and specification have been complied with . 48 Hours notice required.
76d42ebb-0722-5986-85b6-8a710802f429 | note | Frequency - During Construction
c40717c4-b9d8-59b6-99ee-539d04e940cf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e8dbc5dd-874d-5039-b542-0f4cdd7f6cd0 | note | Conformance Criteria - Compliance with Drawings and Specification
76a8096b-2d3d-55a6-9d7b-3adf1935d226 | note | Records - COR/Email/Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.22 - Shotcrete Minimum Application Requirements
71b37f27-6b85-59d1-8205-c44d3e139e96 | note | ACTION (Hold, Monitor, Witness) - W
89a294a4-fe8c-561e-a880-78dfe55feb69 | note | Detail - Apply shotcrete - 200mm Nominal thick (Vertical). Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
f4ed0fbd-e3ca-532c-b593-901fcf863eb6 | note | Frequency - During construction
9299dcf8-0131-5b77-8b1c-2476620de876 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
760ee52b-d6f9-5b2a-9aac-0c6d5dca4c57 | note | Records - Photos
| checkpoint | 3.23 - Shotcrete Compression Testing - Core Test
6e3b4379-4158-513f-91eb-cfb97449348a | note | ACTION (Hold, Monitor, Witness) - H
dd3a4815-d3bf-5250-82ef-9f1a85d77d39 | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
42a46b5d-47c2-581a-acbf-70acf9e1ebd0 | note | Frequency - After Construction
c64dda76-65d4-5586-af1c-8d005f1b6533 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d5f868c7-8d5d-53de-b221-57bda0d3e757 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.24 - Final Inspection - Each Shotcrete Soil Nails Row
5ecd819a-2cbd-5c76-a9f7-2fff4b3aa892 | note | ACTION (Hold, Monitor, Witness) - H
362d348c-8ed6-5137-ad45-806e64006e66 | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
e7d237fa-c8b0-5572-bfce-0f119e641222 | note | Frequency - After Construction
a5e1e71b-d560-5dca-8dbc-7d1860c246a8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
dfcd013d-219a-53a4-8d7e-4f0100d44d3b | note | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
15bab154-a597-505d-9868-402da93032a9 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| section | 4. As-built Requirements
| checkpoint | 4.1 - Post Construction Survey
e46d3bff-a6e3-5b04-8f9c-d1532b548e3b | note | ACTION (Hold, Monitor, Witness) - H
5c390b52-dc36-5733-a527-00781c506b92 | note | Detail - Survey final position of bolts for as-built purposes
de14ec71-c9c6-5baa-84a8-38560762c8d0 | note | Frequency - At completion of Lot
3edb73c1-f5c5-5137-a094-528866d836e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a25a0d74-3544-56a0-8179-6752caf38ee6 | note | Conformance Criteria - Survey report complete and conforms to specification
42079f57-929a-5146-80f1-3af65c210666 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Lot Number QA File
cf762284-90f1-55d3-85b2-68bc08a6b75c | note | ACTION (Hold, Monitor, Witness) - W
f76a7599-5e88-5bb5-8f48-5af400f6f80e | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
2a4285b1-ed1b-5421-ba16-3f0088095889 | note | Frequency - At completion of Lot
5d744d6d-d487-5998-8791-0f7f6e35e2dd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
5f268dd3-94e6-56e7-8a17-03f97026911b | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
11b3d128-8f60-5e52-9ca2-c0d453d74bf4 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 4.3 - Subcontractor Quality Assurance
49b012da-ea7b-58e5-ab54-17f1a2b4cf38 | note | ACTION (Hold, Monitor, Witness) - W
1f06d587-23b2-5323-9341-696a3adb2101 | note | Detail - All subcontractor documentation to be included in QA file
bf2bffe0-6a7b-55c2-a68b-cd35c2099e71 | note | Frequency - At completion of Lot
ddb30eb5-8fa3-5b3d-8180-143ece25718d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
214c49ad-e33f-5dc8-8f2f-8bcebeb3b3d8 | note | Records - Subcontractor QA Records
| checkpoint | 4.4 - As-built
5487d1ff-7e20-558d-9f73-ad299d3fa83e | note | ACTION (Hold, Monitor, Witness) - H
57a2fa0a-3ef3-5d9f-94be-0baf9ee799bb | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
11e79958-10e2-5a56-9a5d-b1873b504a4b | note | Frequency - During and at completion of work.
8ebe550c-3665-5d22-a0e9-10ef49b29696 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
5a219cfe-2482-5937-a9f5-ba56b157760c | note | Records - Survey receipts, As-built plans
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Quality Assurance deliverables
5ee410a9-4d38-5745-9a75-3b4b3e47c984 | note | ACTION (Hold, Monitor, Witness) - W
594b8c4f-2f9d-5223-805b-79043a08846c | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
88d40f10-4382-57a2-8803-e7811cd8f58d | note | Frequency - At completion of Lot
f4c04611-b613-53c2-b181-29035cd77a2b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3a51c41b-1150-51c5-8bd3-1010de8353bc | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
59c3532b-ac1b-5880-a07d-b322cdcd286a | note | Records - As-builts, NCR's and RFI's
| checkpoint | 4.6 - Completion Sign Off From Fields Below
1cebdb56-9a10-522b-8fb2-3e5c3059b080 | note | Records - Signatures
| checklist | ITP - B1004C White Pine Bush - Subsoil Drainage | itp | ITP - B1004C White Pine Bush - Subsoil Drainage |  | 72731249-5c49-48b8-845d-b0c8f1394a97
| checkpoint | Project Site reps.
84b01ec0-5ece-51a6-b318-39dcbd1bec4a | textbox | CPS Eng.
d0afc5ed-7923-5c63-be39-c47108639cb8 | textbox | Site Engineer
73647f19-d47f-5921-80b4-e7005452bafe | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
7215b007-1960-5977-bbdb-ce67e9c909ba | note | ACTION (Hold, Monitor, Witness) - W
c06c5818-555a-57f6-8c77-55fbc5295e34 | note | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
7781e379-a401-56a8-94e2-6e5d723649df | note | Frequency - Prior to commencement
89bccb62-5507-56b5-9194-e030b0c1b1ae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
b458e502-b6ef-5223-bc37-aff5328034ab | note | Conformance Criteria - Consistency with Construction Drawing
014d649c-73a1-52e1-ada2-7335edf66196 | note | Records - Survey receipt
| checkpoint | 2 - Material Compliance
69c4c2bb-1067-5b7d-a875-ad509dcf4584 | note | ACTION (Hold, Monitor, Witness) - H
599f95c7-194c-5fa4-9fea-af0ea40b8c9c | note | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
cceefa59-cac0-5318-b26d-34c543244ea2 | note | Frequency - Upon delivery to site
343ff28f-950c-59a7-ab66-44c3f6f380db | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
396f3c03-fc9d-53d0-8cba-9dc0308c7201 | note | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
38f84dd5-29ba-5f4c-a10a-7f4b0cb7b62b | note | Records - Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 -
38ffc647-573c-5394-ad13-b3cad077e858 | note | ACTION (Hold, Monitor, Witness) - H
31506d5d-5b27-54b1-87ff-543a8f860474 | note | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
c07cc873-bf62-5f02-b9de-28e6d26e0ab5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
58cda649-181d-595b-89e1-7c1417994a78 | note | Conformance Criteria - Ensure clean drainage chip
1520a78f-aacd-58ed-9493-22d8a0c79ae4 | note | Records - Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
80edbbb6-70bf-5099-bd74-a9b236aed985 | note | ACTION (Hold, Monitor, Witness) - H
632bfab8-1c61-5b90-83c9-d805049b545a | note | Detail - Ensure the bidim material is A14. A similar material maybe used but it must be approved
54dfd6d7-01d7-56e4-8e28-9fa0bd1f602b | note | Frequency - Upon delivery to site
c4ab6fc4-eaef-5155-ba30-a7784b6a558b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
b560363c-c56d-5d90-847c-178a7b4e3138 | note | Conformance Criteria - Ensure geotextile is approved for use
79cee608-93ff-5717-9be3-aae40a4611c1 | note | Records - Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Trenching
95b8734c-2467-5280-b4a9-14e3e3f62412 | note | ACTION (Hold, Monitor, Witness) - H
ae992298-4fd1-5adb-a2d5-355595f7864d | note | Detail - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
34550bed-3a76-5d24-a47a-1b410c1c93eb | note | Frequency - 10m intervals
eaa27734-a613-52d7-86be-7e8a5df5259e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
62c60d28-cb53-5d36-9a2d-78223567caf1 | note | Conformance Criteria - Record levels of base of trench on dip sheet
aaf0cd6c-2d05-5059-ae5f-03dd94aec9d7 | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 -
9fe3f6c4-7fa1-57df-882e-6302c8a16162 | note | ACTION (Hold, Monitor, Witness) - H
ae03b093-e0dd-57d8-bd5e-9cbcfb6bde8c | note | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
05cdbee9-f92c-5120-8ecd-c9f25050d81c | note | Frequency - 10m intervals
f0e5d0ed-bc05-57cc-9835-b74f4d1a27cc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
dd0097f3-9bcd-56fd-bca9-157abbcaed96 | note | Conformance Criteria - Ensure trench line and levels match the design drawings
57084358-9823-52a0-8b31-1bcde8214126 | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
aec8de2d-ca26-5c26-abbd-621816570bac | note | ACTION (Hold, Monitor, Witness) - H
de409bea-0915-537e-85a5-4fa7594089f0 | note | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
1a28296f-d6ef-587c-bc4e-d8672f61db93 | note | Frequency - As required
b8284b48-cb12-5688-877c-78bbaae44b1e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
42fea2ce-6e9a-5169-8974-0189e7eef72b | note | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
2b8d15b8-ccf8-5b12-b246-8ebbd2cb79ec | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding, pipe installation and Backfill.
a825ac11-005b-5401-935e-505873ba7906 | note | ACTION (Hold, Monitor, Witness) - H
1018487c-d9d9-54f9-8a99-cb347df15dd8 | note | Detail - Upon completion of trenching Bidim 14 or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
679b3b8e-987f-5a3a-ab5e-7f77cf8a6946 | note | Frequency - 10m intervals
757fdb49-f1c0-5632-937b-2b894b91c22e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
844a8133-ac15-553f-8233-85f5bfb0bc7f | note | Conformance Criteria - Ensure material covers the trench and is pinned in place
8d40e38f-1747-53e5-ab52-0bbba4a3b84e | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 -
d344819b-a948-59a6-9e7c-d7771ddcc1b0 | note | ACTION (Hold, Monitor, Witness) - W
b83fabcd-bacc-5b62-9360-1f1d04194314 | note | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
ee9c18d0-4334-5c94-af9c-53669a322e1d | note | Frequency - 10m intervals
b76fd321-2e24-5daf-9766-1254a51d2d4a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
52671053-0fdf-5c32-b034-fb451abcb35e | note | Conformance Criteria - Record levels of top of bedding on dip sheet
43795986-b37e-54ae-a4b8-b7634b825ef0 | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| checkpoint | 10 -
8df46b15-f9b1-5a2d-89f6-5837c2a62272 | note | ACTION (Hold, Monitor, Witness) - W
5d9d00c8-9b40-5e74-a881-cf02c0457309 | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
629b0637-46a9-5775-94ff-357a48c160bf | note | Frequency - 10m intervals
2121decc-a387-599b-909f-cad0bef085c0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
1cade1f6-04d0-552f-8891-503e96e97ceb | note | Conformance Criteria - Consistency with Subsoil Details
b4ae6267-6ec5-566b-bf42-a3a013162972 | note | Records - Photos
| checkpoint | 11 -
5c24dfa6-7b30-549c-8a04-2bf9717c36a5 | note | ACTION (Hold, Monitor, Witness) - H
dee24b3f-94d2-5af4-ba4b-0c1b30b68a00 | note | Detail - As built Survey the Pipe before backfill
90c98a2a-21b3-51ff-b727-5f4c476486b7 | note | Frequency - 10m intervals
8c58fda0-ec21-5050-947b-ef97c0d24ff8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
ffb216a9-428e-5963-8a4c-c86d3a653704 | note | Conformance Criteria - Consistency with Subsoil Details
90bc9bfc-fe52-50ec-bdee-7a0a15a09ead | note | Records - As-built receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 -
ce31224a-0876-5f6a-a51f-f3a0ab5fa4e6 | note | ACTION (Hold, Monitor, Witness) - W
9020b4ed-29cf-56dc-8649-958f12c8834e | note | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
42bc53d6-09e6-516d-b01e-3fcb527e3e12 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
5fddcd8d-ed97-56a5-8d6f-9716db10e459 | note | Conformance Criteria - Ensure good coverage
20880f36-21db-5a2e-8983-eb3c5cb6dda1 | note | Records - Photos
| checkpoint | 13 -
6f1adb94-feab-5a97-a160-a51cc7ea6c47 | note | ACTION (Hold, Monitor, Witness) - W
d5d2ef24-631e-522f-9055-713f2c52fcbc | note | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
712b3111-5670-52e5-b80b-40fe287fad40 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
| checkpoint | 14 - As-builts
5b8f5813-24e1-5ea2-a436-18dc0d6e3cf0 | note | ACTION (Hold, Monitor, Witness) - H
43097f8a-6f28-5805-8f7d-9fe4aab81e98 | note | Detail - Red pen mark up drawings to be included in QA file
97ed391f-a8fa-508e-8ecb-a98252b3bd1c | note | Frequency - At the completion of the Lot of work
34aef70f-0f3b-5d47-9d3d-3c918ec23732 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
c8fc1e81-5ed3-597c-a1e3-bc671e4cccd7 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt Surfacing V2 | itp | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt Surfacing |  | 9d617e70-f1e5-4686-9238-4584fd472829
| section | Asphalt - Surfacing (AC 14)
| checkpoint | Project Site reps.
ee190d90-3d86-58f6-a6c6-d9bffa466a82 | textbox | CPS Eng.
11fa5f4e-7937-5386-ab8e-5631764c3726 | textbox | Site Engineer
6304bdb9-c9ac-5eab-8992-52619b2b0229 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
cd6e042a-4654-581a-bbae-7870489bd0c0 | note | ACTION (Hold, Monitor, Witness) - H
acafc2a4-3ab0-5503-ba93-84cb0788694c | note | Detail - Set out pegs installed every 20m if required
bbd28be3-dd78-5143-ba76-a2119384fe2f | note | Frequency - Prior to commencement
cd7b564f-3a6f-5b36-87de-089a02b7d1c4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
43ad8b17-7634-51f8-b76f-38554af6269d | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
da18a30f-5f48-5d39-9cd6-c689d9680bfa | note | ACTION (Hold, Monitor, Witness) - W
8ddb7e90-e8ec-5c89-9f49-dc7d743f5d4e | note | Detail - Determine paving run start/stop locations
ebbd04d5-1e88-5012-9186-e2bd60323442 | note | Frequency - Prior to commencement
1faa64af-a80f-5f57-be77-013e03db32f6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
d15a5786-1ae7-56c6-a85c-9b51f4a37275 | note | Conformance Criteria - Mark out on site
daeb8406-a8ed-5fe9-9c1c-e1ed3095f520 | note | Records - Subcontractor QA Records
| checkpoint | 3 - Material Compliance
3601c097-194b-579e-9d23-b41c1c7f4800 | note | ACTION (Hold, Monitor, Witness) - H
d3777e2f-aee4-58f0-ab08-ceecac174122 | note | Detail - Mix Design approved including peer review
cb478996-6698-5129-baee-485997dde801 | note | Frequency - Prior to commencement
7da723e8-f8f5-5edd-bcaa-b40ed39de493 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
42268bfa-235e-518b-acea-0502356cb59f | note | Conformance Criteria - Material is approved by a Notice to Supplier being issued
11828e6d-65cf-5cb8-ba19-b5b43e40f553 | note | Records - Mix Design
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Material Compliance
0dca4c6a-5a26-5c22-9bc8-c2cb6178d48a | note | ACTION (Hold, Monitor, Witness) - H
782d0af5-6615-501a-9be1-768cc1f1211b | note | Detail - Asphalt Material Quality Testing
6c999260-3af4-5abf-80d6-8441f7c9953d | note | Frequency - Prior to commencement
fb095ab4-66ce-50ce-a47a-75083f28e8ab | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
5b9c29f7-705f-53f0-a438-b5f3ac281a32 | note | Conformance Criteria - Fine and Coarse aggregate Weathering, Crushing, Sand Equivalent, Broken faces, PSD, PSV. Bitumen testing, Penetration @ 25 degrees Celsius, Dynamic Viscosity at 60 degrees Celsius
2cf8c556-4dc2-55f6-9277-20e36daca62c | note | Records - Asphalt Plant Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Asphalt Production Testing
9e136aa4-d12c-5a33-af6f-f37602860b39 | note | ACTION (Hold, Monitor, Witness) - H
27c014de-4015-5639-ad06-3d3fcc86bf5c | note | Detail - Full volumetric and air voids test 1 test - 1 test per day
cc537174-d76b-5389-a90f-a5cd634631d5 | note | ○ Binder content and grading 1 test per 100t.
d7461b3d-e731-5f23-a8fd-f5d9d34fc77b | note | Frequency - Prior to commencement
ed98e696-bc9d-5a4f-8ab3-d9ebf3386fb4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing and measurements
a1f8ff2d-7a05-53e3-9d4c-44ff6e77133c | note | Conformance Criteria - Binder content, PSD, Mix Volumetric, Mix performance related properties resilient Modulus and wheel tracking, mix production temperature and load out temperature
929ab1af-da33-5caf-b528-f2decda2b4e4 | note | Records - Asphalt Plant Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Tack Coat
6e114c51-e434-50a3-9298-07fda70cc838 | note | ACTION (Hold, Monitor, Witness) - M
d5ff4330-b770-577c-b62a-0e3ac9338694 | note | Detail - A Spray sheet for every day
e8359d2e-60ba-5795-81f1-1b71e826f188 | note | Frequency - Prior to placing Surfacing AC
0ba6d3cf-2418-54e2-9baf-711844020070 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
834052af-6e0f-5d1a-b1d6-fb11ae40b4d4 | note | Conformance Criteria - Showing the required spray rate 0.2 L/m2 with a tolerance of +or- 0.1 L/m2
5071ce36-91cc-51f7-9aed-0c57781542c9 | note | Records - Subcontractor QA Records
| checkpoint | 7 - Construction of Surfacing Asphaltic Concrete
3df799e3-092a-5967-b442-16652946e42a | note | ACTION (Hold, Monitor, Witness) - H
e4d8d781-d512-5989-8fa1-0990aa255fd1 | note | Detail - Site team QA Checks
062ef966-0e39-52e5-b9b7-61f49ebf2204 | note | Frequency - During Construction
7235b7c6-4ac5-5db9-b465-c08472fc7c5c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
76378479-46e1-5aaf-ae1d-784fd19e1aa3 | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
98530902-5dce-52e4-910a-8cdaed3f2066 | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Surface finish visual inspection
b6795b9f-e2cf-56e8-8ca8-2b72d15f9ad2 | note | ACTION (Hold, Monitor, Witness) - H
11e75f24-6ab0-5585-91c5-e0cae34603ec | note | Detail - Site walk over
32ec15b0-dbc1-5b3e-8973-3738c931094a | note | Frequency - Post Construction
a53e2b2d-d986-5139-8d3d-2f754ef8032f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b6d36f74-cfbe-5ed7-ac7b-669188ac2671 | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
a394fe70-cfed-5337-8044-c7d6781c1ebf | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| section | Asphalt - Surfacing (AC 14)
| checkpoint | 9 - Final Walkover (Snags)
9daf2657-595d-5b75-b5a4-deb17da58295 | note | ACTION (Hold, Monitor, Witness) - H
b19d482e-9302-50d0-8177-f1e0434d5008 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
6a8b72df-e116-5c95-8bc7-4d51a6345011 | note | Frequency - At the completion of the Lot of work
903b3b33-7039-53b3-bef9-584877607ae5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
dc8ddcdb-ca9f-5bd8-b539-643a15a16c78 | note | Conformance Criteria - Completed report
e7fa0f43-274a-51da-835c-e6ee32837502 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Survey As-builts
b179254e-202a-5ffa-9069-d906ff85606a | note | ACTION (Hold, Monitor, Witness) - H
3d2c4c38-f97f-5aca-9a3d-86473779101f | note | Detail - Red pen mark-up drawings are to be included in the QA file.
28b421fd-a702-5a3a-a897-a2a8f3a0d9e9 | note | ○ A survey as-built of completed work must be provided
eb5a94e7-3b7b-5d12-8cc7-1b643dfc2022 | note | Frequency - At the completion of the CWP of work
be5865d3-f4a4-537f-8ee4-ef7e169bfda2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
12cd6fd1-ca8a-5be8-9382-843578b4c8c9 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
3ee47fc1-797e-56c3-afcc-b4f5f674eda6 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Quality Assurance Deliverables
bf44627a-4336-509a-b7fd-b0a9406da1f9 | note | ACTION (Hold, Monitor, Witness) - W
65a2d5a8-c4c5-54c4-a172-384eedca78b1 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
f39f4558-28a4-5117-8e5f-166e50eacef2 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
789f0a49-eef0-5649-acfb-05efe69ec35c | note | Frequency - At the completion of the CWP
24d611a1-91d9-56dd-925b-9a07cb3b4dd3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
2ed824ab-3cf3-505f-8053-9d66eb41b5de | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
c3921459-0a0d-5cfb-ae15-25815f756569 | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Guardrail V2 | itp | ITP - B1004F - Tangoio Falls Steep Underslip - Guardrail |  | 55202a61-8adc-463d-9d6e-a561a18f7c95
| section | Guardrail Installation
| checkpoint | Project Site reps.
84bcda9f-cb71-5c76-aca2-a018423528b8 | textbox | CPS Eng.
def4f8a9-8da7-5610-94d8-b904ba1024f2 | textbox | Site Engineer
465c107a-d49e-56b6-90e2-a894dd211b63 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
a00b1d58-523a-5444-818b-cb4132d3fa65 | note | ACTION (Hold, Monitor, Witness) - H
dfe031f8-250f-5fac-b52c-2c587fac3c4d | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
fcc668fe-642b-5b6e-9834-d04eda6361fd | note | Frequency - Prior to commencement
c8b981c5-d1a7-536c-9ecb-f691949e60ac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
c65af77b-929c-5520-bd1b-bfb5d001651c | note | Conformance Criteria - National Standard for Traffic Signal
a56db5d3-b797-55b4-9bf7-6f0717b47223 | note | Records - OFI or NTD/NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
dacc620c-7509-5403-9a32-92ef1fe80ba9 | note | ACTION (Hold, Monitor, Witness) - H
9809afa9-3e72-5ceb-b878-5f05f921a170 | note | Detail - Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred.
34519b57-a17d-5e82-8765-ac34d4475090 | note | Frequency - Prior to commencement
3f59ce4f-a81e-5509-9b99-665991f42cd4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
b66113fa-f599-5be7-9c1d-b37edef0257c | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
a7d0b712-2d8a-57d4-9301-37b4cc66dc81 | note | Records - Approved Construction Drawing.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance
14ed9500-a196-5234-9706-59e1d6fd1642 | note | ACTION (Hold, Monitor, Witness) - H
13777ff1-0741-54eb-9cbe-c519cda07831 | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
88b11f0a-ac0c-5ece-be2a-56b86b2ae4db | note | Frequency - Prior to commencement
3036809b-ee42-52b4-b3de-034bc1a69e92 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
bdbc51c4-ed3d-58b6-8dfd-8de7bebe96c6 | note | Conformance Criteria - TNZ M/23:2009
4af21f72-e1fb-5788-ab37-9e63e16c09f4 | note | Records - Manufacturing certificates and delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Guardrail Installation
0ad75034-1e75-53e4-a92a-c5a3f5ebc76c | note | ACTION (Hold, Monitor, Witness) - W
11bf54da-dc76-5f72-a68b-d34a3ab92649 | note | Detail - Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
336ab228-65c5-5573-ac03-b3ad26ccdd49 | note | Frequency - During installation and on completion
c5aa9bd9-15b0-5bb9-891c-9260ecd303b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
1700ea8f-549b-564b-b945-0fc282728c97 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
fe707625-df85-5b1f-aef1-2ed02531b593 | note | Records - CS-4117
| checkpoint | 5 - Guardrail Installation
e0854348-e7b9-55e1-82a0-e69d90b213f7 | note | ACTION (Hold, Monitor, Witness) - W
ad637255-a479-5762-8276-cc97ecc4397f | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
b1a0c518-26d9-589f-bd96-010209adc186 | note | Frequency - During installation and on completion
005798a0-4e73-5431-a18c-ca16adf645bb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
cf9970c9-3e52-5aad-a9a4-d57c7e8e228b | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
8baa1438-1fef-5c33-a837-6d020bfc3d70 | note | Records - CS-4117
| checkpoint | 6 - Guardrail Installation
f1f5a120-d6f2-5b36-9858-35a55cd8a48a | note | ACTION (Hold, Monitor, Witness) - W
d4470976-9a52-5425-9168-c9abcc19d363 | note | Detail - Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
ad40fd65-7be2-5940-9f09-8684dc350f96 | note | Frequency - During installation and on completion
ca1540e4-2360-582e-a8c6-b16a83d25cb5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
df1dc594-d6aa-5886-a79c-ac90f8773602 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
31a84553-b69f-5d79-8b13-c94e13314a88 | note | Records - CS-4117
| checkpoint | 7 - RSHDS Inspection
91a411ac-3aa1-5bff-996f-c083b2a2fa2b | note | ACTION (Hold, Monitor, Witness) - H
ecf6c798-47ca-5a5a-b511-70a086680fbf | note | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
c7dcbbd0-30b4-5bcd-a685-99f5cfe9545b | note | Frequency - At completion of Safety Barrier Installation
21c46ba9-99ac-5a24-b125-7da52adcbd8b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
fd8d289b-995d-560e-9de2-a19660c72519 | note | Records - RSHDS Audit Form
| signoff | AUTHORITY HOLDPOINT
| section | Post-Construction
| checkpoint | 8 - Final Walkover (Snags)
8753b4fe-8b51-562f-a5f0-1c324cad9120 | note | ACTION (Hold, Monitor, Witness) - H
6651a55e-edd3-5f9e-b8a8-0e06da684337 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
9b965300-0d14-551e-8378-79c22dc8fb2c | note | Frequency - At the completion of the Lot of work
e9b5bc9d-ed9a-51e7-956e-87c1841108a4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
35c47a8e-1105-53af-a586-36af199db417 | note | Conformance Criteria - Completed report
4be9afe3-3ff1-514e-bcf3-efeef0edf772 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Survey As-builts
0cef8774-07a4-538e-9f01-7a19f60c1a84 | note | ACTION (Hold, Monitor, Witness) - H
92f2e754-f8de-50cb-9bd5-1db3e15e44c0 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
faa1c20a-e519-56f2-90e7-21ce46d1c02e | note | ○ A survey as-built of completed work must be provided
7ebc6ffb-f07d-526d-9085-cc990d3876f8 | note | Frequency - At the completion of the CWP of work
c5732c3f-431e-5db0-a031-03ce2219040f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
5cc3b071-c09a-5fcb-8c31-38449a81e143 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
ffbd2eb2-91b2-5d2e-a374-193b4e20db69 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Quality Assurance Deliverables
9b509e5a-c473-5640-88e5-bc83e2bc0bd7 | note | ACTION (Hold, Monitor, Witness) - W
790941d1-79de-5bab-bb3d-dd0c2022c59d | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
5dc63dd9-c92f-598d-ba8c-a7d2b2594b3d | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
050e5ed2-50d7-5510-81bb-ac5575699606 | note | Frequency - At the completion of the CWP
5134840e-3163-53f7-913f-a631ca69609c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
8dfaf052-04b3-59fa-ba8f-c0bc638b265f | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
0d016bb1-d3ae-500b-93c0-6e9543358bc3 | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel V2 | itp | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel |  | 0fc5c6f1-0c06-4185-bc2b-075e2b9573c7
| section | Kerb & Channel
| checkpoint | Project Site reps.
dbb22b29-9e52-5acf-9668-ea63d148f258 | textbox | CPS Eng.
9d599114-ef0c-5e22-904d-6acd5b11a4d3 | textbox | Site Engineer
882dbeed-d21f-5283-8388-9e51f3d55706 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
b5b45492-7e8d-5ec8-b13e-cd2cfe8838a2 | note | ACTION (Hold, Monitor, Witness) - H
55b6b305-2d61-5360-9fde-77e46cc8920d | note | Detail - Set out kerb line and level at 1m offset to EOS
eac8e00b-c49f-5f5c-982b-59c6e8378387 | note | Frequency - Prior to commencement
231d2ea0-f29c-510f-b813-bd558d3e9600 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
97ce3e3c-3d7c-5c96-a9fd-39c41fd98ec7 | note | Conformance Criteria - Consistency with Construction Drawing
cac702a4-4712-5a67-bd63-af9cdfc43c04 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Material Compliance
ba3592bb-7dfc-5284-be97-21129fa188fe | note | ACTION (Hold, Monitor, Witness) - H
c2a60710-998d-5c26-8982-00eaebbe5da5 | note | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
ae16e2b8-2331-5217-9972-2be6f6c26f03 | note | Frequency - 1/600m3, minimum of 1 per source
7b4508f1-fa96-5c34-a070-d0fce1322353 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
73fddc50-8101-5051-ad47-768773400e94 | note | Conformance Criteria - 20MPa at 28 days
1980bb65-7a1c-51ed-9ca7-517d9465cf5c | note | Records - Concrete Delivery Dockets and lab test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance
ff76586d-1cc5-59e6-b287-082879e1c622 | note | ACTION (Hold, Monitor, Witness) - H
9a91e578-6a3e-5e7e-83c0-5fea3b7f0074 | note | Detail - Ensure the slip form moulds match the dimensions of the design kerb
d55f1b74-8135-5ddf-9c68-16dc7684b615 | note | Frequency - Prior to commencement
547ed728-5859-5215-81c2-708522861169 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
15d6622f-ef33-5e85-b4ac-84b7cb33b755 | note | Conformance Criteria - Measurements match the design kerb dimensions
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Kerb Foundation
2bee1d83-9dcd-5575-8fbd-637335794dd9 | note | ACTION (Hold, Monitor, Witness) - H
971c0d65-b7ae-5969-b3aa-094eb6dc6ed4 | note | Detail - Ensure Sub base construction is completed
53439be2-3d2f-555c-86f5-a076a5de6fcc | note | Frequency - Prior to commencement
6dd3559b-cf62-5b50-86fb-c643f2b523a3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f6d949e9-a0c0-5269-9f5b-300b85153883 | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
794abf86-015d-5ea3-8de0-4b8f3445564d | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Stringing
e90bc948-64fc-5c65-a7e4-5a784dae3aa2 | note | ACTION (Hold, Monitor, Witness) - W
1420e126-5fb9-5d97-86ed-94344e05bfaf | note | Detail - Check weather forecast and avoid adverse conditions
d4301282-d9ac-519d-91e1-e99d71a0b281 | note | Frequency - Prior to commencement
e49b1cd0-4efa-544f-8c41-54709730972f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
6f5cd9f2-f89a-5d7f-b062-19166f446211 | note | Conformance Criteria - No concrete to be placed in adverse weather conditions
b4e61546-fc1b-5503-af55-75853a5413e5 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 6 - Stringing
eb44be04-1902-52fe-a1c6-b4c58e1e756f | note | ACTION (Hold, Monitor, Witness) - W
17fc42bf-be91-53f8-87c6-b67e830c1701 | note | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
34f5c519-e05d-58dd-b28e-a1800a24f325 | note | Frequency - Prior to commencement
ab096e13-1826-5cc4-b5b7-e89b36025a2c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
575b2961-bae0-58ef-b6e8-0caa5b7b13dc | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
005c20ad-efdc-56c3-8f7b-27f7e3790b40 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 7 - Stringing
413812ba-a609-529c-926d-072dd442ec6b | note | ACTION (Hold, Monitor, Witness) - W
59113092-3879-5449-a1d0-c3c41ca3528e | note | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
e8c33dda-2a2b-502c-8f53-3906c40bda3d | note | Frequency - Prior to commencement
a16f566c-04b2-5f89-adc0-1d63d40573eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
fcf66c9c-02b4-5bb1-a8e2-58ad8185fe57 | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
f0c4dbc2-dbc5-556f-8862-41d9354306a1 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 8 - Slip forming
bb678dac-2e52-56fd-864e-bf230ea6159c | note | ACTION (Hold, Monitor, Witness) - W
9daa5f3c-4ba5-5a28-9f87-6d7519e81f8a | note | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
99d2be85-5d39-5a35-ae37-7bc49a37d840 | note | Frequency - Prior to slip forming
9354c0d1-3dc1-555f-af40-7417720250f6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
a403a226-c195-5ddf-84f0-566be878fdbe | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
915e5cff-4f92-591c-8ce4-646acd44b06e | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 9 - Slip forming
e0233fbe-982a-5989-9022-e69aed7b7ea2 | note | ACTION (Hold, Monitor, Witness) - W
0c62eefb-323c-55bd-8b67-d88ea2450549 | note | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
ffcc5d0f-c155-5bc0-9c68-79e256d88690 | note | Frequency - During Slip forming
c1361e91-a2f6-58f0-a8fb-4818d4febfe0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
01a16861-b4b4-5241-bf40-353bdb1afc29 | note | Conformance Criteria - To ensure the correct concrete mix is delivered
990d7f01-65ae-5115-add9-5f490acf5960 | note | Records - Concrete Delivery Dockets and lab test results
| checkpoint | 10 - Slip forming
71c7077e-f508-5c48-95c2-13a08829034b | note | ACTION (Hold, Monitor, Witness) - W
6c18ddba-b330-5c65-a792-52dd887e4fc3 | note | Detail - Expansion joints to be formed at 5m centres
d99c9dd4-50ff-5566-883f-5fb0fda39aaa | note | Frequency - During Slip forming
7773ed64-1214-5256-87e3-dea6d13542ce | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
c758e18f-de23-52fa-8d7d-707d20ab68d6 | note | Conformance Criteria - Kerbing Specification
28b1d204-4822-5d58-b10d-2defe0f57e95 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 11 - Tie-in with pre-cast components
e8406d51-cf57-5b72-b71b-08878102427e | note | ACTION (Hold, Monitor, Witness) - W
5e3118f4-f13f-546d-a931-7aa01354aae7 | note | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
8b7820d2-b64d-51eb-bc1e-bdb47ce73fd7 | note | Frequency - During Slip forming
32db712d-1b20-55e3-9f87-f53f9300b5aa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
dde7d952-1800-5ae7-acc0-177f4679f813 | note | Conformance Criteria - Consistency with Work Instruction
57ebc59e-252f-5586-9c27-32932835f70b | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 12 - Protection
2d02e9a1-0399-59fc-9bfd-c434e568b5ed | note | ACTION (Hold, Monitor, Witness) - W
18bd6483-1a7c-5ac4-ad7e-964f3c9a95ee | note | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
80f3fca1-8c48-51fc-a0fd-d3a113847998 | note | Frequency - Prior to backfilling
90ac1a8b-d2d7-5eda-ab6f-249c883ccf90 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
bc1d703c-f3b6-5624-b8a8-b17be3a9d833 | note | Conformance Criteria - Backfilling to commence only after 72 hours
| section | Post-Construction
| checkpoint | 13 - Final Walkover (Snags)
84242f67-1b4e-5376-ba5c-20f569da11cf | note | ACTION (Hold, Monitor, Witness) - H
b7078104-dd0f-5f9d-ba53-531ea0a99c52 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
f8daacc7-7e59-5436-8a59-03ba728b6cae | note | Frequency - At the completion of the Lot of work
119ea6d8-e7b7-54a2-bbd8-08b203b3a4b7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
f9c4d177-c341-5454-8621-d92d50f819d8 | note | Conformance Criteria - Completed report
b40a67a8-fb8d-5258-b66f-138d5fc41c52 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Survey As-builts
c8ca1653-e55a-5ea5-90dc-3effc5f3f80f | note | ACTION (Hold, Monitor, Witness) - H
58149ac1-ba98-5c26-8397-9bc11b0f002a | note | Detail - Red pen mark-up drawings are to be included in the QA file.
48a5af9c-9c88-54b6-a764-9fc2b66fe7d6 | note | ○ A survey as-built of completed work must be provided
c54cf4a5-ea53-5125-af4b-774540d22ff6 | note | Frequency - At the completion of the CWP of work
f64c3358-91eb-59f1-9a86-d5abf7180cbb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
23a928fa-633e-55a4-805b-999e00899e3b | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
b208d245-c1c4-58aa-b6e9-3d9547eeb0f4 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Quality Assurance Deliverables
5b697eb5-9195-5448-b637-a49a816ac140 | note | ACTION (Hold, Monitor, Witness) - W
a62d9604-3ca9-5d9f-9201-3e3aa75d6d27 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
4359709f-a866-538d-abd8-1b4d5fd50c2e | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
a9a9a2b8-a2fc-5010-bee9-72ed7b68259f | note | Frequency - At the completion of the CWP
b70daac8-0d4e-5d73-af63-531e82f0f7fa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c19c8a79-ec04-5897-81e9-491f7d701f3b | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
813bd9d3-57c6-5fbb-9c43-d10b06d33798 | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Reinforced Slope (Rock Bolts, Soils Nails) V2 | itp | ITP - B1004F - Tangoio Falls Steep Underslip - Reinforced Slope (Rock Bolts, Soils Nails) |  | dc159693-1a67-4606-aacf-3e9ab154c94b
| section | Preliminary & Setout
| checkpoint | Project Site reps.
c597509f-a0d6-5925-8bbe-8f7d9cd5d283 | textbox | CPS Eng.
f1b41ed8-a41a-594d-a548-827a32b04661 | textbox | Site Engineer
d4b5b0cd-6be6-5275-a324-d7327441f494 | textbox | Quality Eng.
| checkpoint | 1 - Vegetation Clearance
92794bef-88c9-5bcc-9e5e-4d382d552801 | note | ACTION (Hold, Monitor, Witness) - H
6dbc1eab-402b-5e41-a82a-953b6076fe62 | note | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
c9304622-c35f-5da6-b3a4-40440e87b0a9 | note | Frequency - Prior to commencement
fd65e04c-1444-548c-92ed-f1ff720f5e22 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0bea21ed-27e9-5849-9f98-ca3344ea294d | note | Conformance Criteria - In accordance with TNZ F/1
c4cb0c52-7e85-5629-a39f-39a9b592a0da | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Excavation Clearance
4ec20830-a207-5513-995f-20b3a35783a5 | note | ACTION (Hold, Monitor, Witness) - H
4c9b120a-f6a1-511c-9ef1-8145f43f9f13 | note | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
7e5ca8e0-22cd-5c6e-9a4f-afd6b8a4f927 | note | Frequency - Prior to commencement
d6cbab65-4df9-5e3a-b7ea-9f8e161cb503 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
96ecd08c-9404-501a-92a1-94136ab8dc74 | note | Conformance Criteria - In accordance with TNZ F/1.
ee4a2a36-a260-56fa-a4c7-0b6d40363788 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout
ae00cd3a-4d2b-5222-870c-968a57dedc56 | note | ACTION (Hold, Monitor, Witness) - H
79187153-a368-5d72-b72b-a8e6970c8edd | note | Detail - Arrange for a set out survey to be carried out & check against design drawings
efde8262-726c-5ffb-a00d-9d1aaf0db3e8 | note | Frequency - Prior to commencement
bd9e8712-915e-581c-a477-dea41edce1ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9112c6de-91d1-5211-a5ab-3e2df0da749c | note | Conformance Criteria - Consistency with Construction Drawing
f5efd13c-4ad1-5bd7-97b4-29f116b31132 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| section | Material Compliance
| checkpoint | 4 - Material Compliance - Rock Bolt & Soil Nail
c9a7282c-2a78-5ba7-90c4-3fca28a62eb8 | note | ACTION (Hold, Monitor, Witness) - H
91fff0f9-fca7-5948-a926-905fe77794f9 | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
7a71d360-6b29-557b-86bc-c2bb4083406e | note | Frequency - Prior to commencement
9c4c906e-4d12-5e69-a7d8-8fa5f8ad4828 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
8dc8edcb-6cf9-5748-b6d4-96e9a0f41026 | note | Conformance Criteria - Grade 500E soil nail
303e96a0-5a4e-5c5f-8ccc-111059a80148 | note | ○ Class II corrosion protection
e0a18e25-a967-5995-a42e-52f34affe939 | note | ○ Lengths and diameters shown on drawings are the minimum required
25f4ba8d-2713-5b37-856b-1b72a62631d9 | note | Records - Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance - reinforcing steel
98fcb961-4786-5a73-8de4-69eb74cfcdbe | note | ACTION (Hold, Monitor, Witness) - W
703cf1ee-a272-55d8-8942-0f32ba7ad5d7 | note | Detail - Reinforcing steel manufacturer's test reports and certificates
a103564b-0409-5a21-940c-490509c42af2 | note | Frequency - Prior to undertaking works
9c233152-98ac-53a2-8ec5-48bd631fabea | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
74cd483e-ea70-5b5f-b968-65f775c295d6 | note | Conformance Criteria - Including despatch records
7ec918cc-c199-5d66-8afe-91d06fca1e5d | note | Records - Email
| checkpoint | 6 - Concrete quality plan
782f2a5a-e0ce-589b-b6fb-2419767c85a5 | note | ACTION (Hold, Monitor, Witness) - H
f7cda1d5-2690-578e-81b8-5d5406fd2763 | note | Detail - Concrete quality plan to be produced and approved before work starts
86dfa2d6-175e-5beb-b681-d001d56766bd | note | Frequency - Prior to commencement
e2369fbf-137b-59a9-b07f-257b33b1885c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
935ffd4a-4c77-5160-b2b2-ada04611901b | note | Conformance Criteria - Including:
230ef11e-d99b-5186-b650-1f798df0680b | note | ○ Name, qualificationand expoerience of concrete works inspector
66eb45c5-49a4-5c78-ba89-1341ff061a14 | note | ○ Form and content of concrete placement card
af693f71-eb8c-539e-9216-998a609d151f | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Concrete plant compliance cert
e84f5e66-c2a6-5a7d-801f-2e36dbad02fe | note | ACTION (Hold, Monitor, Witness) - W
f6d6060d-4a83-5c17-889c-2c2213b8beab | note | Detail - Details of concrete supply plant, copy of certificate of audit for plant
6a2a58bf-d5d2-5ff3-8d5f-7cdbd7f47d50 | note | Frequency - Three weeks prior to pouring concrete
2cb0f2fe-3edc-535f-b25a-eb733f60b4f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
3da03a8b-668c-50bc-968e-955b679cddc1 | note | Conformance Criteria - Including:
67182d49-4c88-53cf-8e80-4395010768c7 | note | ○ Plant test Results
7534d6b3-3db6-52bf-819b-5be0af77e6c4 | note | ○ ASR Compliance Records
a1c99cfa-b766-52e2-b5d1-9725765eaace | note | Records - Email
| checkpoint | 8 - Concrete mix designs
144ed046-16d5-5db1-9b37-ffac5dfa8b35 | note | ACTION (Hold, Monitor, Witness) - H
a502f3da-7f60-59a9-9fb9-0a878f003b92 | note | Detail - Submit all concrete mix designs, trial mixes and compliance records
4b267ddb-a853-5a0c-b6ff-820ee9ebb3bf | note | Frequency - Three weeks prior to pouring concrete
c30e1a7a-397c-5b4b-975e-782e47062636 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
b2637857-b4fa-5382-97fa-3acf07b43485 | note | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
9a823e33-19a3-5803-a788-e5647bb53a8a | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Grout Mix
91555d57-6e85-5b50-a627-0192afd90e8f | note | ACTION (Hold, Monitor, Witness) - H
ef095c7a-e4f4-5a58-ac4b-677f84108f7c | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
0f1718c2-cf71-50c2-be5e-58af8abd1840 | note | Frequency - Prior to commencement
5da17bb4-03b4-5d37-a4fb-017aa16ec1c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
c007b909-13b4-5455-9144-56cb300f0f80 | note | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
9d76be13-976a-5e5b-9a31-4f195f7082d4 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Grout Checks
a3ad5ee8-63ec-596f-9d94-a99edbf4b60b | note | ACTION (Hold, Monitor, Witness) - W
d90bafd2-6791-5a8c-8a50-a2918e2ae8f1 | note | Detail - Grout checked if its free from lumps & segregation
19fc3b3c-fb6e-5962-9cea-ee9138808230 | note | Frequency - Prior to commencement
9c463533-6c21-5807-8c5e-804f1b0b597c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| checkpoint | 11 - Request for use of alternative Drilling Fluid
17bea228-b675-5592-98be-7408985cb1b3 | note | ACTION (Hold, Monitor, Witness) - H
33087294-5f76-5c10-9eec-6a710d171ed8 | note | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
a00edb68-d87e-538a-b61e-7ee1bc62d5ed | note | Frequency - Prior to Commencement
d0b48531-bdcc-5d95-9439-2cf31ff3547c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
ee1b0e4d-6c39-5371-9936-df31cf0998d2 | note | Conformance Criteria - If required
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Soil Nail construction methodology
97f745c7-055b-5727-b758-584dde58df74 | note | ACTION (Hold, Monitor, Witness) - H
f77610c4-fbcd-5a8a-a0c6-03d49c9889c6 | note | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
7fdcd5de-f183-5a3c-9122-0e3d2ebe4eb9 | note | Frequency - Prior to commencement
ccfdd90a-8e9a-5ffe-a5cd-ea400eafab0f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
afc7badc-8c7f-54d8-8f81-3d20eff19608 | note | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
| section | Construction
| checkpoint | 13 - Working Bench
6197bd08-cc04-5394-83f1-73c229accc82 | note | ACTION (Hold, Monitor, Witness) - H
d408ea98-8a50-50d5-83cd-17888494bf20 | note | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times.
b5f98dce-11b7-5f3e-9321-9ec54e1d8c8f | note | Frequency - Prior to commencement
c8220563-aee4-5a13-ac14-3a87fec9b275 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
d44fbe0e-0a63-546a-89c9-9e246dfb4922 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Test Nail Locations
b76dbd7b-7bc6-5604-a66e-d30813174489 | note | ACTION (Hold, Monitor, Witness) - H
0ae5424d-f67e-52b8-9abf-4658b7a24881 | note | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
72a60394-5f9f-5d1d-b4d6-461c1ed7197d | note | Frequency - Prior to Trial
845e43d1-4953-534b-976a-cc61a9971c76 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
7d45b2ce-3bb2-573f-a7fd-493f67b9ee73 | note | Records - Photos, Site Diary
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Insert micropile bar
c0342f8e-1d95-5b6d-aefc-91940d30cc2f | note | ACTION (Hold, Monitor, Witness) - H
6e6e6742-ed2e-5c15-80ab-d908e0e36b32 | note | Detail - Insert micropile bar (ReidBar RB32) to full required length
d70551df-255d-5534-bbae-9d18588dd3a2 | note | Frequency - During Construction
d6e3594d-9c9a-5941-b3da-36e297009206 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
6e046df4-f623-5bfe-83e9-6dc12557b56b | note | Conformance Criteria - Embedded length of micropile 3.0m into ground
5068e1b4-172f-5a82-b52f-a364fc6ede5c | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - Drill Holes
047d52f7-5465-5e15-a656-b6ae72d9ef1b | note | ACTION (Hold, Monitor, Witness) - H
a9bcade7-229b-5118-b9e4-1708e23dac3c | note | Detail - Drill hole
f5113170-80ac-521c-b0b7-1bff4c0302e9 | note | Frequency - During construction
81b1db31-4f21-54b3-aae5-91512e678d66 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
ba97d82e-d6d0-574b-b9b6-bc753e7cfb4a | note | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
88492e18-7334-5586-a0fb-9f894393c9ce | note | ○ Submit all installation records for each soil nail and pile.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - Flush holes
ac57f2e5-5dc5-5383-8983-fd9a26937b1c | note | ACTION (Hold, Monitor, Witness) - H
2c1aaead-e5c0-581c-81a1-c35d731942b6 | note | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
e911033b-7bc7-5016-a046-a69d4b99e03b | note | Frequency - During Construction
7d4131cd-ef2c-55d0-b503-330eeeb6ec4c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - Insert soil nails
80d853c0-6321-5575-af0a-a7d2b72712a2 | note | ACTION (Hold, Monitor, Witness) - H
edc3bf28-4063-5e0f-ade3-47e18ebc8ea5 | note | Detail - Insert soil nails as specified
88967146-12d7-5c25-933d-8cbb58b16292 | note | Frequency - During Construction
061fcf95-6bde-5a92-90d8-a8e9df29a9bc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
775d6676-62ac-58e0-bc5d-2dcaed27b243 | note | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
db8d0566-5278-5c04-9521-4398c8e6ea7f | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 19 - Installation Records
15137362-950d-5d5f-b3bd-5a624ca03f56 | note | ACTION (Hold, Monitor, Witness) - W
468f8286-7f38-50a9-9625-80ccf7f0eb0a | note | Detail - A record is to be maintained showing the type and installation date for each soil nail
be584b8f-9a67-5130-b1c3-2d5627ec4f5d | note | Frequency - During Construction
c8ab16f7-d88e-54d6-998f-5c645f2735db | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
b7d69505-ba18-57c9-8e9c-2cacaa51fa19 | note | Conformance Criteria - Installation records shall include:
04c49ce7-e443-5acf-81e5-b69c03cc6779 | note | ○ Length of bar
e34e81b6-b6ff-52c2-8779-c4c9d90647b5 | note | ○ Depth of drill hole
4a6216f2-054e-5177-863c-6be3852d4f23 | note | ○ Inclination/Verticality achieved
a1a8d5a1-95b7-5f57-9c22-773db7132096 | note | ○ Level of grout placed
bc381ab5-7957-53fa-9277-386a47106268 | note | ○ Batch numbers associated with grout placed in each hole
8656ce83-ecc4-5259-87cb-5942c664c361 | note | Records - Subcontractor QA Records
| checkpoint | 20 - Install Grout
88c393cf-2ab2-5db4-8b88-c41808a29a47 | note | ACTION (Hold, Monitor, Witness) - W
0df75351-a6b2-5abd-9861-28ab7f8faf98 | note | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
846bc6ba-902b-50fa-83af-ae46b560847c | note | Frequency - During Construction
69f6d250-6942-5f6a-94d8-edc8864010d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c9a6d5ce-70ea-5306-954e-529517d66046 | note | Conformance Criteria - Including:
87fb3884-0c0a-5f16-9269-89053dccf5f5 | note | ○ Concrete despatch records
f89fb700-1bf5-5637-aefe-9e1cc58a6360 | note | ○ Compression test results
506aa84b-cb14-583e-8001-cb6c4f9965a2 | note | – Must notify CPS for any failed result and cease works until resolved
2bb957c2-383b-5143-816b-9f478c27c0c0 | note | Records - Subcontractor QA Records
| checkpoint | 21 - Grout Sample Testing
181d725a-12e2-5416-858b-f31faeb05a51 | note | ACTION (Hold, Monitor, Witness) - H
bdaa09f6-15bc-565d-8234-0d879842f753 | note | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
6077ce32-d765-56d7-9e3e-42f3a1b8e631 | note | Frequency - During Construction
6ec55729-17e3-5000-8eb6-94a5156fa3ca | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
5b8dad5a-eea1-554d-85b4-dc5779496630 | note | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
a473c828-cf33-54e4-9038-473e41a188dc | note | Records - CONQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 22 - Monitoring of grout loss
822374f8-7cbd-519e-af21-ba00bbd4c79c | note | ACTION (Hold, Monitor, Witness) - W
b7baccdf-fa61-584a-9399-128b486e6147 | note | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
787617a1-e07f-5014-aae7-53ba091d8417 | note | Frequency - During Construction
51414012-5de3-5ed5-801b-e8f5ed0b5c69 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4b0137b8-684c-513c-a4f3-89d6ec03d4c9 | note | Records - Subcontractor QA Records
| checkpoint | 23 - Install Bolts/Nails washers & nuts
dbfcf1bf-837d-576a-a7da-85821541b817 | note | ACTION (Hold, Monitor, Witness) - H
b931ce4a-1ddb-5208-9fd8-81060f172aea | note | Detail - Install Bolts/Nails washers & nuts
897dcde2-38b5-51bf-9615-66b13e347354 | note | Frequency - During Construction
284f8d3f-4636-5c60-a159-7ed7bed57e8e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
3d9d295d-584a-5462-a203-a21b0439cb48 | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
cc8d7a1a-1f88-57e7-b7b0-1f3b47e045fe | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 24 - Testing of Soil Nails
47c6bea9-4053-5477-b2cb-01c74585b7d2 | note | ACTION (Hold, Monitor, Witness) - H
ff36b338-6dee-5dbe-8189-5b5e45617c24 | note | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
8158d5dd-5157-5f51-be87-2f10a20d655e | note | Frequency - After Construction
e5c44c2e-af75-55d7-95d6-fd6b46bb3823 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
da0641e0-6d92-59db-b5e2-a6f73dc71190 | note | Conformance Criteria - Certifications of all testing equipment within the last 3 months
d61ac91e-64ff-5b04-8cfb-fc4d907d0cbb | note | Records - Certifications
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 25 - Testing of Soil Nails
dc207b1d-7de7-55ee-b3e9-7eeeb5b0cb1c | note | ACTION (Hold, Monitor, Witness) - W
4137ec2b-3f74-5051-b751-af7d6dc2a057 | note | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
f02b6ef5-66f5-5b6e-8e75-315016c673fd | note | Frequency - After Construction
011ec301-5529-500f-b71b-799635f2e560 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
1465fb60-cc80-5fd2-9960-13c32056bdc1 | note | Conformance Criteria -
| checkpoint | 26 - Testing of Soil Nails
ba2ea797-126f-5a45-a408-a877022b2e5a | note | ACTION (Hold, Monitor, Witness) - H
f01c5263-03da-58da-9c1c-44136bdb9d4a | note | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
480e6246-d1e2-5478-9b0a-4513fcdc1d5f | note | Frequency - After Construction
63a68129-5873-5627-bfc0-95ae19f1881b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
dd8fa0fa-58ce-590f-9fd3-6a7965a3885f | note | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
bc1f6335-0e33-538a-be34-977fc47019c3 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 27 - Soil Nail Final Inspection
61c45d6f-486e-56c9-8231-d44a0a2cc1e2 | note | ACTION (Hold, Monitor, Witness) - H
a9b5bcc6-b602-5076-a59a-9f04aa9f9750 | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
4dddc209-39f5-5d20-a155-0437c2842d7c | note | Frequency - After Construction
d3af11d0-b942-52ee-baf0-3428ebd3a284 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
77547439-1f73-5305-b1f3-84a809239b5d | note | Conformance Criteria - CPS Engineer to give approval via a NTC
c91694d6-3121-5851-81f8-40c07dd66818 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 28 - Shotcreting- prepare surface
626210ac-4e8f-57c6-92a9-f5bc5f00fa85 | note | ACTION (Hold, Monitor, Witness) - H
1e7b2e30-cf35-5ba2-9073-b57d41442484 | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
41b7cc92-897a-5754-94ef-125769ce5be3 | note | Frequency - During Construction
3a98218c-ebc3-5212-8ce7-40e30d0e45a0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
358e1c4d-f551-584a-8d16-64c00211a8c5 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 29 - Shotcreting- apply vertical
78f95401-83f3-5ecf-9ac8-0250256fac72 | note | ACTION (Hold, Monitor, Witness) - W
0b4ddb97-e833-5e3a-bed1-13248906e0de | note | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
092b04f4-77cc-5f86-8e9c-e2b31186f22c | note | Frequency - During construction
7ab7aee1-7ed9-50e8-a352-471b4dc4f748 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
05780c4b-adda-58d0-b6a2-d176a0c62c84 | note | Records - Photos
| checkpoint | 30 - Shotcreting- apply horizointal
78dac9d9-3e0d-557e-a0a1-ac0b5565746b | note | ACTION (Hold, Monitor, Witness) - W
e23a6f5e-2b4d-5139-9b5c-f947fc26568f | note | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
27cb846a-e9e3-53c4-9340-4189f027d337 | note | Frequency - During Construction
9a532789-21a2-5971-bb86-1d299237f214 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
93c15a71-6dce-5f79-ac38-5a845f29f289 | note | Records - Photos
| checkpoint | 31 - Shotcreting- compression testing
dcbe3aca-7490-59c7-980f-e8416e4f082a | note | ACTION (Hold, Monitor, Witness) - H
62347d3b-e868-546d-979b-1e82798a1c69 | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
d12fd928-f04b-535a-88d8-e8da556d87ce | note | Frequency - After Construction
d0fae98b-92ab-50e6-8831-825df4308f74 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0fcd638f-7948-5ff0-b696-2bf9d950ffe9 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 32 - Shotcreting- surface inspection
c2597081-27a2-5695-837b-2ed1122a293b | note | ACTION (Hold, Monitor, Witness) - H
412af196-695c-5444-94dd-7806a3521815 | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
2222f226-0cfa-5cb4-960c-4e47f451682c | note | Frequency - After Construction
51f7f8b6-ce97-5907-85bb-1402fdbf8644 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bf680958-ad8f-5fde-a02d-5134301c2118 | note | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
63b288ce-eda6-5563-b46c-cbfaad124dc1 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| section | Post-Construction
| checkpoint | 33 - Final Walkover (Snags)
d09194e4-32a7-5623-a4f9-b276065effba | note | ACTION (Hold, Monitor, Witness) - H
a58889d7-80d9-5bb4-b5a9-6c7ad7a5c645 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
6a192b10-e9fe-525d-86b9-f16053050ebf | note | Frequency - At the completion of the Lot of work
ca3d7870-84ef-5aa7-a276-2c9432e14afb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
17aab5b6-0bb5-5cc1-b2e0-a49e1dc671f2 | note | Conformance Criteria - Completed report
46aeeed9-0c9c-58b4-8ade-d9e158578049 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 34 - Survey As-builts
9e538293-317d-56e1-a24e-c5cd4c0742eb | note | ACTION (Hold, Monitor, Witness) - H
eadbdcc5-4ab7-595a-a0bc-bee0fe393d09 | note | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided
153a928e-2d9b-5729-a19d-b2221077a255 | note | Frequency - At the completion of the CWP of work
412f7365-6f16-555c-ae07-3580d3807b98 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
80f62c3b-2e5e-5a01-a3e0-2f0ee98a79f3 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
7533c7c7-ebf1-5e61-90fb-99c12c0a5350 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 35 - Quality Assurance Deliverables
7c2f208b-87ee-5fe7-84bf-cf58fcb9e46a | note | ACTION (Hold, Monitor, Witness) - W
6febf0a5-0b8d-59c6-b112-05711e6494c6 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
f36e118f-30bf-5cbd-b971-ea0e7f7c8765 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
d9029c43-a925-50d7-b304-27c96969a01d | note | Frequency - At the completion of the CWP
9fdfea99-1a38-5c96-bac4-f66fc2e82efe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4ba0ea1b-2990-518e-8215-71c27d7e2318 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
4bc73f4e-f7cb-5233-a0e8-b134adeb9091 | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Stormwater V2 | itp | ITP - B1004F - Tangoio Falls Steep Underslip - Stormwater |  | 65ebef39-f04f-4380-b48a-0346fd4e743b
| section | Pre-Construction
| checkpoint | Project Site reps.
6220c117-c015-51fa-8c9e-77cb300afcaf | textbox | CPS Eng.
6aa861b5-db44-513b-af43-7da6d5b079a2 | textbox | Site Engineer
e08f5f1b-51f6-5ccd-9377-4e9ff265159d | textbox | Quality Eng.
| checkpoint | 1 - Drawings and Specification
9d747c6d-442c-5824-a75e-73d05a6a91c0 | note | ACTION (Hold, Monitor, Witness) - M
a81ba1f7-fcee-527f-a5ad-1773fd9e2766 | note | Detail - Check drawings and spec are the latest version.
21125791-5d53-581a-ae15-e0fca20d9cc0 | note | Frequency - Prior to commencement
de8f8ce0-db4f-5edf-9ce5-33d3e14c77ce | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
| checkpoint | 2 - Survey Setout
1d8697d2-0bc3-5772-b2cb-23e5035f77b4 | note | ACTION (Hold, Monitor, Witness) - W
58b27af7-8c8b-57bd-b575-405399e9685e | note | Detail - Set out as per design
8ae68ba1-27aa-595c-9e34-9359a7e9b13d | note | Frequency - Prior to commencement
25977267-24a3-5099-99e4-1a182dfd4560 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
45d3b2e0-58fb-51f6-baf3-688d60b5ba10 | note | Conformance Criteria - Check against plans for any discrepancies
c958387f-e254-5516-b5ff-a1c64c9e0c2d | note | Records - Survey receipt
| checkpoint | 3 - Material Approval
917d99e1-4d86-5e3a-8a34-a402a70ea7a6 | note | ACTION (Hold, Monitor, Witness) - M
0e977ee3-5b07-5056-830d-6675f7c14fb4 | note | Detail - Materials as per design
05c416d4-e773-5598-80c2-72216a53d144 | note | Frequency - Prior to commencement
02d98666-240f-569a-8317-16b1892f1d0d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
b8a0e1d6-a1d3-567d-8531-feea647ddf8a | note | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
| checkpoint | 4 - Location of underground services
3a8ea60b-309a-59a9-b984-0653d01d7c44 | note | ACTION (Hold, Monitor, Witness) - H
80aa3ca5-9ce0-537f-9420-b5283ce3e9c5 | note | Detail - Ensure underground services are positively identified and asbuilt. If the service conflicts with the design confirm resolution with CPS
ccf67b87-a4f8-5301-aa6d-879700752e27 | note | Frequency - Prior to commencement
b2124213-f235-5e91-9794-61a878454449 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Drainlayer Qualifications
b25c39f2-f98f-5310-a2e9-6e5716deb4ea | note | ACTION (Hold, Monitor, Witness) - W
e5a88de2-5465-5521-867b-e25b8b28eacc | note | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
a92c4cdb-3226-56cf-b1ad-82d5b52ff011 | note | Frequency - Prior to commencement
61fd68ba-11cf-52de-a016-4d0ef7cf25da | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
6aec0071-c2c0-5cde-b39f-00b85b374e33 | note | Conformance Criteria - Drainlayer Certs
| section | Construction
| checkpoint | 6 - Trench and excavate for pipeline to design subgrade
98776d47-8abc-58dd-ad54-30588b8ff976 | note | ACTION (Hold, Monitor, Witness) - W
a6af873c-0dbc-524e-9636-341d496f910e | note | Detail - Check subgrade with visual inspection and
2e2cb3d3-f74b-5764-a457-b2102f82ac9c | note | Frequency - During Construction
a11ac627-c1db-53ca-9d66-e2c18c125210 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
16a50f5c-47f5-521c-929e-2ae6109c9cf7 | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
47b1a5ed-4006-5833-847f-57272f7fdb61 | note | Records - Subcontractor QA Records
| checkpoint | 7 - Surface finish visual inspection
4e2ddf35-8221-5e4b-8db7-89caf33b8f67 | note | ACTION (Hold, Monitor, Witness) - H
ec33dd3d-716c-5054-9175-fa8ee1586eba | note | Detail - Site walk over
82314387-cf26-5d15-8b49-4b93ab1d0931 | note | Frequency - Post Construction
3c6e9ff2-44fa-5134-8588-b81ac40ed1ce | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8d3732f1-e2a4-5afa-b3d2-1e02a0ceb5cf | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
7810ed82-37fc-5cb9-85c9-b4a6acfa3675 | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| section | Post-Construction
| checkpoint | 8 - Final Walkover (Snags)
a86ae5ca-e65b-536c-adba-3ea64a1d1b22 | note | ACTION (Hold, Monitor, Witness) - H
2dab9dd6-a1e9-599e-b4f2-fe1f38437a6d | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
f9b4497a-5779-5903-874c-7567231522bb | note | Frequency - At the completion of the Lot of work
1beea9fc-ab98-53d3-8f0c-afec2401dc01 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
9b89cd32-2f5a-57a9-af9f-9d39adc7caa9 | note | Conformance Criteria - Completed report
199975a0-f1e6-5723-bbd9-e5a6a95f4385 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Survey As-builts
1739a0bc-0f92-5ea5-bfba-93f4e0d17b15 | note | ACTION (Hold, Monitor, Witness) - H
5a068a1e-d4d6-549b-9085-3e4f2c4be294 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
f15d03a6-3915-59ae-99e2-5ae412c46577 | note | ○ A survey as-built of completed work must be provided
5e1f749b-20e3-5640-9688-fd939b34ec46 | note | Frequency - At the completion of the CWP of work
4646584e-da72-5436-9de5-b0c6ca49a052 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
76aae6dd-efe0-5a31-952f-4a69c13d17a7 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
4a3dda18-8e34-510f-ad26-22b50aec4538 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Quality Assurance Deliverables
17d68903-6821-59e8-afe6-8bcb9e7ab26b | note | ACTION (Hold, Monitor, Witness) - W
f8a8daab-1911-5567-8111-a62887ebc49d | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
f0acf346-f8e4-5825-9636-a81415c976a5 | note | Frequency - At the completion of the CWP
3e1380ec-d731-59fd-8197-6192552013af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
92c99287-201a-5afd-84a3-ac923a449d95 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
c3bfca17-e614-55a2-bcfa-974ff5d2285c | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt | itp | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt |  | 0d04d2e0-3ff5-4777-b70f-a37f59f54c15
| section | 1 - Milling Operations
| checkpoint | Project Site reps.
09847663-c7ce-550d-aa98-915a297dea66 | textbox | CPS Eng.
c98707ff-ff0d-50c4-933a-def70ee9f98f | textbox | Site Engineer
6f381376-03f4-5f3e-afa4-2b31c1a0409c | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout - Milling
8a7c79a5-54e2-5e0f-a89e-50ebc0da92f6 | note | ACTION (Hold, Monitor, Witness) - W
8ffb1962-c0f3-59ff-bea4-1044bb714c06 | note | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
4fdb9593-e254-5efb-82a8-122988265e0c | note | Frequency - Prior to commencement
d80184c7-a931-5978-bdb5-e991654a535a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Survey
8d3585c0-54ad-5f99-a02c-b0f6e234657a | note | Conformance Criteria - Mark out on site, confirmed by CPS Engineer
3d797218-ec2c-5885-b7ef-7ea7531bf6c1 | note | Records - Survey, Photos, COR
| checkpoint | 1.2 - Milling Existing AC
4dc67849-b8a1-5b65-bc5e-54f8aaeac922 | note | ACTION (Hold, Monitor, Witness) - M
b51d0aab-aa44-5dc4-9af2-25031329b373 | note | Detail - Milling undertaken to correct depth of 50mm ±5mm nominal thickness
ea25c596-38b4-57b3-8f8a-cf17d8b68f11 | note | Frequency - During operation
02d59097-f7cd-58c8-9d09-9cc7334a8601 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Dip checks
dd200693-df6d-5e07-8c09-25fa8fb7ecfe | note | Conformance Criteria - Design Report, depth of milling confirmed by CPS
0c35b98f-6820-514a-bd59-86d6928e7838 | note | Records - QA Records, Photos
| checkpoint | 1.3 - Waterproofing Exposed Layer
039256cb-f33e-54cc-a77f-606b4bad7bac | note | ACTION (Hold, Monitor, Witness) - M
f8c3518f-cbe8-5aa9-a10c-d48dd6d5f98f | note | Detail - Exposed Basecourse waterproofed / levelled
d8a9ecac-d131-5894-a9ce-aa111d36e463 | note | Frequency - Post milling, before asphalt
76395e77-537d-58bd-b258-10b4e91215d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
2d5faa86-2eb1-541b-85e8-2282c54fec88 | note | Conformance Criteria -
8ba4302e-0d01-5735-92b2-454be6fef092 | note | Records - QA Records, Photos
| section | 2 - Material Compliance
| checkpoint | 2.1 - Binder Penetration Grade
5aa3e481-84bd-592c-ba00-1b944b5622a2 | note | ACTION (Hold, Monitor, Witness) - W
ea5ea0ac-e4a5-5369-9b92-ea4d44a251c3 | note | Detail - To comply with NZTA M01: 2020 - Table 6.1 and TNZ P11: 2007 - Table 5.2 Lab Mix
d12bbd47-e97e-568c-be51-8920f9d6d9a2 | note | Frequency - Prior to commencement
5e92a0d7-19d8-5f3c-b42d-31663e067f48 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
14b1ded4-c378-586f-8d42-0fbc99471c56 | note | Conformance Criteria - NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
21c96e78-fd28-510e-89a0-058061c93a33 | note | Records - IANZ Report
| checkpoint | 2.2 - Coarse Aggregate Source
77d9a518-4e51-55f4-b752-39b99dbb72f1 | note | ACTION (Hold, Monitor, Witness) - W
0c2c20bf-a395-560d-aab6-0db8b8f3d016 | note | Detail - To comply with TNZ P11: 2007
8bb7e16c-45e9-5adb-b42b-232d8915c114 | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
876a5cc3-809a-58f3-8999-5ab4d350ac32 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
88fe4985-4c75-5c1a-af51-d584abd9c05c | note | Conformance Criteria - 230kN minimum Crushing Resistance, AA or BA Weathering Quality Index
277234d7-d7c3-543e-95c0-09e0e4fae9b5 | note | Records - IANZ Report
| checkpoint | 2.3 - Coarse Aggregate Production
32e4718e-2ca3-5a51-ba72-ce315d459553 | note | ACTION (Hold, Monitor, Witness) - W
d073c1f3-abe9-538a-9ade-2f8f8c12bd59 | note | Detail - To comply with SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007 and RPT-21711902a-PVT-PV310-H01
89760bec-b341-5210-b1ab-41dd1c331f2c | note | Frequency - Prior to commencement
d63a7974-8670-58da-b222-8183a46c2bd7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
af7c9e60-9692-5588-af5a-56f80baf0868 | note | Conformance Criteria - PSV: ≥ 58. (At least 85% by mass of minimum PSV) Table 3.13 for various sites
354409f5-6d3c-5b11-8bb3-68227fc468a6 | note | Records - IANZ Report
| checkpoint | 2.4 - Fine Aggregate Source
0e99430c-be38-5b5c-95b5-3f1853e8d410 | note | ACTION (Hold, Monitor, Witness) - W
57515e84-bec6-5fd7-bd91-23eab047e8e7 | note | Detail - To comply with TNZ P11: 2007
bea7d6cb-fc75-56fa-9bb2-9662e1daeac5 | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
59af343b-5c2b-5bba-a6ee-8a58150d9f1a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
a6673a07-edcd-5f04-a743-e80b45b713a0 | note | Conformance Criteria - 130kN minimum Crushing Resistance
221522fd-3edc-502f-a4e9-ba3d7f9e2fb7 | note | Records - IANZ Report
| checkpoint | 2.5 - Blended Coarse Aggregate Production
b453b16b-8f9f-5837-b2be-3c9ce670a20d | note | ACTION (Hold, Monitor, Witness) - W
9db91e05-3e9c-5a3b-9330-2e5a93e148d9 | note | Detail - To comply with TNZ P11: 2007
ef4d5b3f-7801-5250-83ed-b32d885acb41 | note | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
e05ed9cd-1dac-5438-aaa0-183867640e34 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
689f9682-88f8-557a-9dda-c696defeac6a | note | Conformance Criteria - 2.25 Max Particle Shape
cd3e9658-6798-596d-af4a-9d53f969e0e3 | note | ○ 98% Broken Faces
3887d104-f285-5a8b-93a3-c300f94e8743 | note | ○ Report Value - 5 minimum Cleanness Value
13661301-2f5b-5c6b-900e-2452bfdc29e4 | note | Records - IANZ Report
| checkpoint | 2.6 - Asphalt Mix Design
d75aa424-d085-5ae6-90c6-d73c044d1ec0 | note | ACTION (Hold, Monitor, Witness) - W
fc7ca3c4-bd18-54c9-9310-18723992137f | note | Detail - Mix Design approved including peer review to comply with TNZ P11: 2007
ff2b588b-f229-57f5-b8e7-3400009a07b3 | note | Frequency - 10 days minimum prior to paving
c2659c6a-7e5e-58af-8a65-3486c32876b4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
9047101d-c58b-5701-a04b-506067af0458 | note | Conformance Criteria - TNZ P11: 2007 Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements
f070fe00-1eda-53df-b073-27c30a861061 | note | Records - IANZ Report, Mix Design
| section | 3 - Construction
| checkpoint | 3.1 - Survey Setout - Paving
c7ee423e-e9f6-5f32-b18c-183b993bc79a | note | ACTION (Hold, Monitor, Witness) - W
d048bb33-fdf6-5d05-8e39-3ed3c94d4214 | note | Detail - Determine paving run start/stop locations
38014465-bc27-52d5-b591-adad74ffcf7b | note | Frequency - Prior to commencement
9081a92c-89cc-58bc-8d26-2984d07fae0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
9aec2b6f-1a3a-597e-9dca-e112c90b4477 | note | Conformance Criteria - Ensure accurate survey setting out is in place.
9281ffe8-3e6a-510a-959d-ed825e9a9afd | note | Records - Survey Record
| checkpoint | 3.2 - Weather Check
7b509b82-c3df-5430-8602-de7763a80d45 | note | ACTION (Hold, Monitor, Witness) - W
eca038b6-61d4-56e5-a4d7-bbaf562ab0e6 | note | Detail - Ensure weather conditions are acceptable for work to proceed
fc2ed29f-0bbe-5d72-bd85-6ced7ebd93dc | note | Frequency - Prior to commencement
efb6aedd-b033-5bf1-84fa-c775a0ba17a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
d0dd1508-c956-50fc-8fd9-6bef159aa6f1 | note | Conformance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers)
0e491b82-b99a-5df4-9670-ce8df7ff76fd | note | Records - Forecast Records, QA Records
| checkpoint | 3.3 - Surface Preparation
f8839a99-e277-548c-847f-547fbb084818 | note | ACTION (Hold, Monitor, Witness) - W
4e9c65ae-94c4-5376-a112-0e8f6ec4bd34 | note | Detail - Ensure previous layer is broomed clean.
3b8f844e-479d-5e75-ae4f-b3d69e0f0d1c | note | Frequency - Prior to commencement
08b850fb-343f-5ecb-8f66-85ec31c55820 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6548f8c4-c3a2-5f12-af89-8afeee21c140 | note | Conformance Criteria - Truck broom to have been used and surface approved by CPS Engineer
d94a0a6f-b5fd-5450-b754-27575a915d62 | note | Records - QA Records, COR
| checkpoint | 3.4 - Tack Coat
61e99cce-bbed-5713-b59e-556837dddaf0 | note | ACTION (Hold, Monitor, Witness) - W
de96aae3-fa74-5321-b644-152adf7f0cc6 | note | Detail - Apply tack coat
f1e82e9c-9921-5fc0-987b-a3e4b94f61c1 | note | Frequency - Prior to asphalt
65c166ff-da05-5192-a3be-d745c0bd3b09 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
dfdfa26e-31c2-5362-a2cd-01b22ab5fef2 | note | Conformance Criteria - TNZ M/10 2020 - Section 9.3.1
fdd832de-a714-5dc5-a3eb-86e8a3680632 | note | Records - Spray sheet, QA records
| checkpoint | 3.5 - Production Property Test - Grading
460b1db4-451c-52d0-a8d5-64c6598c86ea | note | ACTION (Hold, Monitor, Witness) - W
3b47d7c4-1ab0-5743-97a0-bad139d2db17 | note | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
5ed5061c-9a5c-574d-ad1a-7cee4ee59e11 | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
69188654-6cdf-5801-b103-4e91f57b3c0c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
40405b4f-f7c8-5799-9c04-9b8ae7bdd815 | note | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
d927f8d2-c27b-5d38-949f-f95d2d247769 | note | Records - IANZ Report, QA Records
| checkpoint | 3.6 - Production Property Test - Binder Content
1b217baf-8640-5742-921b-1c62f796a86a | note | ACTION (Hold, Monitor, Witness) - W
9315ba01-b05b-5934-9195-294fa842c24a | note | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
7785ef8b-c4be-58e6-bd82-3ccd5f785a51 | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
01fc5ef8-7080-5254-9cd7-4c105a763d6e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
93a201a6-5879-5ecb-a0c9-73fdf47c6611 | note | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
772cb7a2-982e-584a-9cae-d20a142abbdf | note | Records - IANZ Report, QA Records
| checkpoint | 3.7 - Production Property Test - Maximum Specific Gravity
9f4aff70-cb52-549f-b15c-729c99910425 | note | ACTION (Hold, Monitor, Witness) - W
09a98b0c-d2d0-5a6c-9d32-38932ae6ca70 | note | Detail - To comply with TNZ TM6002:2006
f7041634-f276-57bb-9336-7dd37bf3e112 | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
b69e76b1-a03f-53c0-a0a5-ba95fe060831 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
6c26b0d8-a29a-5697-b2b5-39e220600720 | note | Conformance Criteria - TNZ TM6002:2006 Report Value
3e0a5524-83d2-5e17-8e02-2ed048084278 | note | Records - IANZ Report, QA Records
| checkpoint | 3.8 - Production Property Test - Avg Temperature
7285886a-23c7-5b06-8019-341f7d9f2549 | note | ACTION (Hold, Monitor, Witness) - W
071cf91d-0303-599f-8614-2eea761c2604 | note | Detail - Check temperature of Asphalt for every truck entering the paver.
ad454e0f-28d1-58e8-ae3b-084911c8619f | note | Frequency - Any truck load
482f5eb4-6cb6-5017-9ae6-593105364fd1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
f1624867-e727-57f1-9ca8-bc089b67f30e | note | Conformance Criteria - TNZ P11: 2007
ecb1893f-5395-5832-9697-820727c0a134 | note | ○ ±10 oC from recommended mixing temperature
dbc24c32-dd06-5fee-9497-482c322b1588 | note | Records - IANZ Report, QA Records
| checkpoint | 3.9 - Asphalt Construction - Layer Thickness
6cfaba1f-3e66-555f-81ce-0e2fc6792d5b | note | ACTION (Hold, Monitor, Witness) - M
585f5061-23e6-51cb-bca4-0b20dafd395d | note | Detail - Ensure asphalt is laid at correct thickness of 50mm to comply with SPC-2171902a-PVT-PV3006-H-01.
45dac390-6fe2-553b-ac9b-8269f239aad8 | note | Frequency - During paving operation
81e6e95a-984a-574b-849f-3504a363d89f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
70f7684d-2449-52e2-9cda-4b27a63954bc | note | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
b3f69ae2-8794-5ce5-8765-ac832f2fc42a | note | Records - IANZ Report, QA Records
| checkpoint | 3.1 - Asphalt Construction - Surface Shape
1e4be2b2-893c-56e7-9614-72c8febcd205 | note | ACTION (Hold, Monitor, Witness) - M
cea514f0-ba0a-5a12-ac4a-ff1c545dd3ed | note | Detail - Ensure asphalt is laid to correct shape to comply with SPC-2171902a-PVT-PV3006-H-01.
2ab70f32-be8d-5b54-b588-66479e6a9217 | note | Frequency - During paving operation
546ad15e-ca84-5a41-a134-3b42d0a2793e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - 5m straight edge
09c0133d-5215-5d74-ab8c-bf4668ee3d50 | note | Conformance Criteria - SPC-2171902a-PVT-PV3006-H-01.
9b20401c-7f25-5d12-bc7d-aa26c24e0c22 | note | ○ ≤5mm (Visual Inspection)
54f3d20b-c13a-5a2b-8f46-f4c90e4106f8 | note | Records - QA Records
| checkpoint | 3.11 - Asphalt Construction - Surface Texture
8ad24679-0c9c-5e0f-9d09-d1034ce5df3b | note | ACTION (Hold, Monitor, Witness) - M
a3279356-20ae-54f5-abd5-cbd4114c181d | note | Detail - To comply with NZTA M10: 2023
fe225e84-b5e9-58a2-8da9-3f93e84440b2 | note | Frequency - Every 10 metres
031bf56b-4f26-5ba8-af09-4a2ce482aace | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Laser Profilometer
ea40e03e-8111-5aa2-9534-1a41850f0d58 | note | Conformance Criteria - NZTA M10: 2023 Table 3
4e2d037e-57a1-5ab4-b01e-6cd696e847f8 | note | Records - IANZ Report, QA Records
| checkpoint | 3.12 - Asphalt Construction - Compaction
9c3cbf70-c9f4-5fca-aff2-e0f663181a94 | note | ACTION (Hold, Monitor, Witness) - W
a0c28b5a-6321-5940-9113-395c06e3841e | note | Detail - To comply with NZTA M10: 2023
1cbbd1be-4191-56ae-9f3b-62035bbf9580 | note | Frequency - One test per 50m2
1d012bbb-6c57-58c6-97ce-731d2bcb9b55 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
49aa3f1f-f1c4-5ee9-b4d6-8db005a3e3a3 | note | Conformance Criteria - NZTA M/10: 2020 - section 9.9.3
b32916b0-aa67-5421-a675-62a7288764e1 | note | Records - IANZ Report, QA Records
| checkpoint | 3.13 - Ride quality
4c56552a-b278-5bf6-ac67-3d89353d8886 | note | ACTION (Hold, Monitor, Witness) - M
df688d69-3d61-55a2-8a07-5f0b68fe0038 | note | Detail - Upon 100% completion of OGPA layer and at expiry of defects liability period
a0020189-3bd1-5874-99c4-0c5c3a733952 | note | Frequency - Prior to Opening to Traffic
acfabbe7-930e-5123-b8a0-5547a8ca41b1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NAASRA
61e7df59-39e5-5267-954b-7051e4659e86 | note | Conformance Criteria - 10. Appendices to Principal's Requirement: 50 NAASRA count as a 95%tile for every 100m rolling section
efd6a033-fb1d-5300-af67-de15267f4fbf | note | Records - IANZ Report, QA Records
| checkpoint | 3.14 - Surface finish visual inspection
275baf9c-ba1c-58ea-9782-b31e6ab8fc72 | note | ACTION (Hold, Monitor, Witness) - H
76ac8f13-0a6c-555a-b4dc-b97c0b80f10a | note | Detail - Site walk over
00b0b2cc-fdde-5d88-b5df-6abc93dcb144 | note | Frequency - Post Construction
841ab86d-af8b-5e57-952a-56ad7440fa92 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bd6ca1c9-d1e9-51fa-a621-4b0d0d42e874 | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
4c8626cc-52a1-5dc3-ad27-d5be7f89754c | note | Records - QA Records, COR
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Post-Construction Closeout
| checkpoint | 4.1 - Final Walkover (Snags)
c9fb9d67-ed81-5ed4-b221-a9fb396f8b71 | note | ACTION (Hold, Monitor, Witness) - H
df72ad0b-a682-5c8a-ad64-e59f77f521a0 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
f77a8488-2e2c-5789-9d7d-ea718c4ee5cf | note | Frequency - At the completion of the Lot of work
47f0a676-274d-5552-a003-dd7caf8af0a2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
14dd018f-d376-53a6-9fea-ab165ef2b0e1 | note | Conformance Criteria - Completed report
1d430b0b-f558-51c1-96ae-4bc039c62156 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Survey As-builts
892ca46f-8eae-540e-8bdd-1a144e23129e | note | ACTION (Hold, Monitor, Witness) - H
fe301b49-c8ec-51ee-a30d-c6a3018e6bd2 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
0e111037-d804-5a11-a283-6c256202e9da | note | ○ A survey as-built of completed work must be provided
6e615034-34df-54fb-b6bc-86d9bf83d4f0 | note | Frequency - At the completion of the CWP of work
1747552d-a5c9-54b4-9584-4ae1a00ccc21 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
86fc6063-ebe4-5a9d-b40c-98078203d58a | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
e281ea92-70c8-524d-b5cd-8ae6f8bc2d1a | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Quality Assurance Deliverables
502b8a9c-d2fe-5102-adc6-3cf1adb98691 | note | ACTION (Hold, Monitor, Witness) - W
f5835484-1943-59a5-82aa-9fd5e7d135cd | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
7b84dfe1-fded-57a8-ac56-2eebb67f908b | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
fd74244b-b5c5-56e1-9990-fc4b81ff3c93 | note | Frequency - At the completion of the CWP
35417a3c-39f2-57db-8fed-d59b4fd6cf71 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
35185a1c-995d-51ad-a0e7-c11a9d331cf4 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
d97d1df7-263c-5d1f-b3b2-7a575914ebde | note | Records - As-builts, NCR's and RFI's
| checkpoint | 4.4 - Final Approvals
d1e93a99-0ffb-5bc8-acc6-6829e48a6872 | note | ACTION (Hold, Monitor, Witness) - H
28e41e73-2310-57b7-b3b3-d469a6d060ad | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
211dcfba-4e22-5804-9254-d36f4d7f509c | note | Frequency - At the completion of the CWP
d772f37d-07d0-50bb-b465-6af7182dd533 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
2ed54d51-0bc2-5b90-85ae-5592662976cf | note | Conformance Criteria - Ensure all parties have signed and approved ITP
42446ec0-d601-5d93-8a77-55642f34c129 | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - B1101A - Te Ngarue Bridge - Scours Guardrail | itp | ITP - B1101A - Te Ngarue Bridge - Scours Guardrail |  | 47e22689-6e4c-4976-917a-2a7184bdf356
| section | 1 - Setout & Checks
| checkpoint | Project Site reps.
df63d33f-1780-5e92-8afd-5894e5150f86 | textbox | CPS Eng.
bddb543d-16ff-5604-8f4e-c85e540d3f58 | textbox | Site Engineer
1a0d9cb3-e7fc-507b-aa98-7ee489c3f38a | textbox | Quality Eng.
| checkpoint | 1.1 - Design Check
a92d7390-7e68-58de-9e35-a67fadcc08ad | note | ACTION (Hold, Monitor, Witness) - M
abb86e8a-ecb3-51b7-a0e6-fe2ec7631d08 | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
e2ec5d5a-6d69-587e-9e6c-2eea6e9f3ae7 | note | Frequency - Prior to commencement
2305c7c2-615e-55ab-9fa1-1c165d1c1cef | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
16078782-cb0e-5e5f-9195-1d31eb57fa5f | note | Conformance Criteria - National Standard for Traffic Signal
03dfd91b-89fa-599c-953f-98cb7e6b44d6 | note | Records - COR, Photos
| checkpoint | 1.2 - Survey Setout
d15d7d31-0ce5-542f-b1b8-438a4f690162 | note | ACTION (Hold, Monitor, Witness) - W
41742240-24eb-541d-b505-020b3db429cf | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
9c999763-b265-526d-a646-c4896f5e8a56 | note | Frequency - Prior to commencement
ec5f74e4-c447-5ce9-acc3-0abfbf6d7966 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
2e0f86f6-cda7-506a-b0b8-9203a5e80b0e | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
a3d2b69e-1a12-50af-8b04-320a66246a76 | note | Records - Approved Construction Drawing.
| checkpoint | 1.3 - Survey Setout - Bridge
3ab24797-e357-5c9d-bb52-ebfb35d2a6b6 | note | ACTION (Hold, Monitor, Witness) - H
5eca4527-ced2-5053-8221-1e25acf7a5f3 | note | Detail - At transitions and on bridge deck, surveyor to mark each post position.
8724b8ac-78b0-5ae4-9584-c484dbeb6a9b | note | Frequency - Prior to commencement
3c9eb030-f261-5ed2-9b18-248e285ce22d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
96fe5459-49e8-5f85-9dd2-7c7aaf3125f2 | note | Conformance Criteria - Section 1.8 of specification (Te Ngarue Bridge)
961c322a-4a74-5274-93f8-c918f65cab51 | note | Records - Approved Construction Drawing.
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Material Compliance
| checkpoint | 2.1 - Barrier Compliance
5e6aa583-4dd2-5fba-94b8-94451a569993 | note | ACTION (Hold, Monitor, Witness) - H
58c3a0d9-e983-5ebc-ac51-0d8b6df5750c | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
f6560d04-4a3c-5e3f-af13-8f0b63784a1c | note | Frequency - Prior to commencement
63a13353-04a2-5e9a-87b3-6d88b4ac195a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
fbe9720c-0d79-5cda-a45a-3445bd2176d6 | note | Conformance Criteria - TNZ M/23:2009
386240c1-2fba-5677-9646-7b6373eace01 | note | Records - Manufacturing certificates and delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Material Suppliers
133ead95-5754-5a69-bcce-26159a0359b1 | note | ACTION (Hold, Monitor, Witness) - M
32dfb13e-7941-5421-af7a-64b1186ceee5 | note | Detail - All materials to be sourced from registered suppliers
8248e26b-e317-59e7-9ab0-6e5fd0576df9 | note | Frequency - Prior to commencement
65f2a788-b925-5f3d-bacb-1879f390a55c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
2bc5bcf0-4a7b-55d9-8fee-8e745cb2402a | note | Conformance Criteria - Registered suppliers
3e6cd783-cb35-54ac-a175-fcd756912ff5 | note | Records - Materials register
| checkpoint | 2.3 - Galvanising Repair Methodology Approval
464e99bd-54eb-5b03-b683-74298a528156 | note | ACTION (Hold, Monitor, Witness) - H
4df47340-6611-5cfe-9f67-5f5a089fb9aa | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
4c3aafba-7f9b-5bcb-93f2-744300fd6a27 | note | Frequency - Prior to commencement
bc26e13d-e81b-5008-b874-9e10a03c63d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
606cb49e-c060-5aa3-b4f7-6d7b5397e014 | note | Conformance Criteria - Best practice
b035d37e-cbb7-5c1a-8490-4ef73379b4be | note | Records - Approved / Signature
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Installer Certification
a1336d50-6ad7-5d90-b963-c0d6c54893de | note | ACTION (Hold, Monitor, Witness) - W
195dc503-f69d-57c9-b541-966407851a39 | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
e095c82e-dfb7-5ce9-95a4-2c7b27f10e0a | note | Frequency - On Procurement of installer
29ba95e7-917a-53a5-937c-6b120eb96814 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
bbfea415-9cf5-5c94-9e16-df181f53372a | note | Conformance Criteria - ASHTAS operative and installer course
de2c9483-7299-5555-8efb-78fc40d9504c | note | Records - Attendance Certificate
| section | 3 - Guardrail Installation
| checkpoint | 3.1 - Guardrail Installation Locations
541ae052-b6ef-568d-a2a7-ecac1a92956b | note | ACTION (Hold, Monitor, Witness) - W
312704dd-1fd2-5dfa-97ca-fa2904a738cd | note | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
54e84847-212d-533c-b2a1-688dee8b8928 | note | Frequency - During installation and on completion
391c5e17-27a6-5396-89e4-36047b2f060a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
085a683d-3faa-518a-be5c-5a4e58c02a2e | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
f4c09870-c7b8-5d8f-af3f-beb0535dfbaf | note | Records - Installation Checksheet
| checkpoint | 3.2 - W-Beam Guardrail Installation
168c86bd-2ab9-5a19-8285-18e7a279c3c5 | note | ACTION (Hold, Monitor, Witness) - M
66c57784-2381-53f4-9fa2-7b23c93099c5 | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
650b9375-47a0-5689-9b4c-4a43c5864719 | note | Frequency - During installation and on completion
f0f5a783-dd47-5429-bf9e-f89103884a00 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
aba9e79a-9689-568e-aaef-9ae6aabd43e5 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
f177b5e7-6160-5be3-8434-e41ce4f29103 | note | Records - Installation Checklist
| checkpoint | 3.3 - Chemset Anchors on bridge structures
9eef5f2a-48ad-5c0b-9638-b24c472eb57e | note | ACTION (Hold, Monitor, Witness) - H
e973ca96-8462-5c77-807e-05252bff2c09 | note | Detail - Location for post to be scanned for rebar position. Contact Engineer if clashes
ac913dfc-346c-5614-9b23-070539734bdd | note | Frequency - Each post
ef40abd4-5ec4-5c61-8e1e-8eb626e433e2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
c9eeac05-f008-5431-83bb-bff9481dac33 | note | Conformance Criteria - Absence of rebar at bar location
80f0569d-1b23-56b3-b3db-c62817235c6b | note | Records - Installation Checksheet, COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Chemset Anchors on bridge structures
2c915bf0-b1ce-5001-b434-e11c392190af | note | ACTION (Hold, Monitor, Witness) - W
0a216f8f-bfd6-52fb-a83e-1bf2ed4bdf26 | note | Detail - Treaded bar to be installed in accordance with the adhesives installation manual
b463e41b-f0b3-5e20-8592-c8037853b727 | note | Frequency - Each post
97df6734-af92-52a0-b7c6-77df4853e3de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
c7cb8fe0-c0a8-5bba-b5d7-53731c55977c | note | Conformance Criteria - Comply with specification
a43bf602-093d-5191-8781-e6480a72b809 | note | Records - Installation Checksheet
| checkpoint | 3.5 - Concrete spall repairs
afe3ba7a-6c72-5a4e-b51c-557daae16f52 | note | ACTION (Hold, Monitor, Witness) - H
c677a8fb-2d1e-5055-8922-66f4efc0f9ac | note | Detail - Engineer to be given opportunity to inspect cleaned off spall repair areas
548ac4f1-d890-5157-a883-90279b5a6dba | note | Frequency - Each repair
abdf04a6-878e-5bdd-91e4-8454726204ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
21d58964-ab1e-547b-afbe-53fd5a08465a | note | Conformance Criteria - Best practice
a1dc6933-f6c6-51ca-8776-efe0a66fa90e | note | Records - COR / Signature
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Leading & Trailing End Terminal Installation
8202cff3-9cbb-557d-a335-06f9f91dd547 | note | ACTION (Hold, Monitor, Witness) - W
d3f99238-f9e2-516b-89b6-cc1a565b5536 | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
146c93cd-f02c-58c8-b0b9-72f45f246a1f | note | Frequency - During installation and on completion
935fbe57-ba53-5f87-b366-c41d39a3c56a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
0f9407ab-fa3c-5e36-a75e-755c821857fa | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
09c27fe4-bae4-5529-ad7f-ae6e20187177 | note | Records - Installation Checklist
| checkpoint | 3.7 - Fit for purpose Inspection
3a183654-3228-502f-b7a5-abb545b66468 | note | ACTION (Hold, Monitor, Witness) - H
7453d163-b8a3-5d63-a567-ca1ed5c98532 | note | Detail - Barrier to undergo fit for purpose inspection by competent person
f385b3bc-3229-5051-9e0c-6d54fe151374 | note | ○ System checklists to be completed and co signed by contractor and CPS.
1782b563-604c-579d-a991-9c45da732a2b | note | ○ All faults to be rectified before acceptance into network maintenance and RAMM
a9b9a4c8-01a6-5106-bcf6-99ef7c84a6d9 | note | Frequency - Prior to trafficking,
4bb0e007-cd4d-5a3e-93f8-58362989f08d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
94b80745-a4d0-5cce-8e34-212a07d18333 | note | Conformance Criteria - Pass inspection RSHDS 4
33c2b9c0-9839-5afb-85d2-7b5a7a74ca60 | note | Records - Confirmation from inspector
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Post-Construction Closeout
| checkpoint | 4.1 - Final Walkover (Snags)
2915ce6e-3620-5941-81b4-d9dda78282a4 | note | ACTION (Hold, Monitor, Witness) - H
2e3819e9-7760-56f0-8e89-53fa99980add | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
ee2c17ec-0a80-5e9c-868a-954f7697e910 | note | Frequency - At the completion of the Lot of work
059f85c1-0143-56db-a590-caf369404ca2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
1b0c180b-c756-563d-97f9-4d63d384def3 | note | Conformance Criteria - Completed report with Snag List
2ef4f54f-37c9-5eb3-b583-db5648268347 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Survey As-builts
69e4c338-3eff-5288-828b-d7111e7238eb | note | ACTION (Hold, Monitor, Witness) - H
4859764c-861d-5a8c-9c79-a4820173a1d4 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
2d0582ff-6117-546c-8087-f42f08be2bbd | note | ○ A survey as-built of completed work must be provided
c0f02049-ada2-52a3-9975-822093921b02 | note | Frequency - At the completion of the Lot of work
faca1f02-81d3-56f1-a1b5-bea4e286821d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
f304e857-f453-54e8-aaa8-584a2a23baa3 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
ae5467b2-5772-5b64-b64e-57e0e573480b | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Quality Assurance Deliverables
ecfd483e-069c-5c1a-a47f-56a1afb86ebe | note | ACTION (Hold, Monitor, Witness) - W
8aafc7f2-182e-57b1-9530-5b6a44b294b0 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
c5683fbf-e556-5103-bcc0-f65b4873d8f3 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
04ae412f-5875-5cb0-b02c-c8260ebaf0d6 | note | Frequency - At the completion of the Lot of work
92221dc7-27d7-58ca-9482-f5a6c913e37c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1e82b80c-d8da-5f73-85c5-cb7dcd4feaa0 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
439b3132-3e7a-5477-8885-7330384d117e | note | Records - As-builts, NCR's and RFI's
| checkpoint | 4.4 - Final Approvals
b1219d9f-13d5-5c23-9ae2-527155621b3b | note | ACTION (Hold, Monitor, Witness) - H
a8006a42-efa9-59fa-b250-3858f067811d | note | Detail - Signoffs by Project Manager, Quality Manager, CPS Manager
ab11b9d8-1b1e-5f1d-9861-c79914cdd9a3 | note | Frequency - At the completion of the Lot of work
2c565c0e-b3d8-50cf-a2ca-270de2d9a8f7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
e0712485-e2ee-5ce6-8fb3-5e5e506b244d | note | Conformance Criteria - Ensure all parties have signed and approved ITP
34d395b7-c72d-5bc6-99da-12cbdb5c529c | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill | itp | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill |  | 0934ada7-6fab-45c4-ac41-de41d91a6b78
| checkpoint | Project Site reps.
84d68b54-0866-5aae-8dab-379e5ebf82fe | textbox | CPS Eng.
4fec42b5-dcc8-56a3-84b3-3343c942f492 | textbox | Site Engineer
d1f39e12-657f-58bb-a259-fa26c7a31eff | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
8a405b45-f783-53c4-a704-1eb47c3d51bd | note | ACTION (Hold, Monitor, Witness) - W
749c5afe-aa40-507e-b4b0-b6643969008a | note | Detail - Set out extents of fill and check against design drawings
b4495282-05ce-5dca-866f-12689186972e | note | Frequency - Prior to commencement
30fa9dc2-0bd2-5dd7-9a05-ec24551ce554 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
420ec524-d358-53e1-851d-7c11449e0738 | note | Conformance Criteria - Consistency with Construction Drawing
eb8a0e1d-e7c4-55ad-b850-a0ee69480ce6 | note | Records - Survey receipt
| checkpoint | 2 - Topsoil Strip
766419bd-70df-52fd-b108-9892b744a068 | note | ACTION (Hold, Monitor, Witness) - W
13878f56-1fb0-5fc1-912a-01724209e684 | note | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
2fce38ea-a4e9-57e0-8970-7ae7d01f0aa0 | note | Frequency - Prior to commencement
dd320576-be72-5546-86d9-e00b8adc3e6a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
9d162547-63b4-54aa-9d99-0209a13210d8 | note | Records - QA-6002 Process Control PlanTree Felling &Vegn Clearance Check Sheet
| checkpoint | 3 -
0af8e15b-0631-56b1-8173-f8bad7f87005 | note | ACTION (Hold, Monitor, Witness) - W
e7a935d3-b0db-5c3b-b686-1580b0fcad75 | note | Detail - Topsoil to be stockpile in an area approved by designer
dd44380f-288b-52b5-bdae-ffbb126d5de0 | note | Frequency - Prior to commencement
| checkpoint | 4 -
c8d53881-d981-56e2-a22d-debf8938f0c1 | note | ACTION (Hold, Monitor, Witness) - H
9f34bd36-4292-563c-9ee6-eaa7143c60a6 | note | Detail - Inspect fill foundation
c618fc08-3abe-5660-8aa3-fee7b92f1fe5 | note | Frequency - At completion of topsoil strip, before Toe construction
2028e762-4e77-5c43-9d8f-551a93b85bf9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
02f4564e-69a4-5956-bef3-d31933d56dc9 | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
bc624d85-1084-5429-9e20-383a206df263 | note | Records - CS-4100 Subgrade Approval Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Ground Improvements
3a33f4eb-4f70-57e0-9d7c-7f386a8d7cec | note | ACTION (Hold, Monitor, Witness) - W
e4da011b-6b67-530a-a101-940f7a886924 | note | Detail - Any area that requires Ground Improvements must be completed as per ACE-CS-6003 and be signed off and closed before bulk earthwork operations commence
dbc9e669-245c-5c1c-a72d-52865ae22d49 | note | Frequency - Prior to commencement
ac4ab536-c0f8-515f-a672-a05fa919f5c7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
5e9669c5-1241-5ddc-9117-1ecdf73635a6 | note | Records - QA-6003 Process Control Plan Ground Improvmts (Wick Drains) Check Sheet
| checkpoint | 6 - Fill Material Compliance Testing
69e9b3bf-f7df-5e4e-84a9-376e1258d05c | note | ACTION (Hold, Monitor, Witness) - W
35373171-7078-56e5-8096-2028eb947754 | note | Detail - Material to meet specifications dependant on material type selected
ced4a600-c411-5b83-bc1a-4141906f432d | note | Frequency - Each material used
5b5fc94f-9597-5589-9882-bdbe657f6af9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0b36e3d1-6a92-5b22-97b1-31b523b5967f | note | Conformance Criteria - Rock of GAP65, 100, or 150, GAP65 specifically within top 1.2m of buttress
20b48e16-36eb-544f-83a1-f86ecb289068 | note | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt
| checkpoint | 7 -
d1a4e612-5cab-5a03-9751-78fd47ec7ad0 | note | ACTION (Hold, Monitor, Witness) - W
6d33c8f1-353f-5613-a58c-23d98b59e494 | note | Detail - Fill Construction Material
5f1d67f3-2206-5b56-88e2-d270b94cb338 | note | Frequency - Prior to commencement
9198f6b8-9052-51c2-9461-697690c7eaf6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
3aef27bd-ca45-5f21-bc92-b67669678a78 | note | Conformance Criteria - Granular aggregate with broken faces
3a358ff2-b134-50c8-8fcd-3734dfdf2d28 | note | Records - Lab Test Report
| checkpoint | 8 - Filling Operation
cf4e7721-7211-54c7-9df1-4e1aa9b074de | note | ACTION (Hold, Monitor, Witness) - W
8492744a-9c25-5c99-90b5-b85705b3621c | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
4cbb8dfb-0201-5c69-83aa-c407c692f852 | note | Frequency - Daily
9fcb1007-4403-573b-b352-ebd4c0d0fc57 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
| checkpoint | 10 -
e07024bc-1493-5443-9553-747ad88117f3 | note | ACTION (Hold, Monitor, Witness) - W
e0a87bbe-2129-52f8-b156-f77077a59b44 | note | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
16db879a-787a-516e-98be-f460a77e5bcf | note | Frequency - Daily visual survey check
11a84453-0654-5755-8db4-5d18c448228c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
852f2d94-960f-5e51-95c6-3617f833584f | note | Conformance Criteria - As built drawings
cc7d0b06-57f9-5587-9dfd-a14dac7e5fdd | note | Records - Survey receipt
| checkpoint | 11 - Filling Testing Requirements
fd533b34-844d-5eb5-90db-aa678442401f | note | ACTION (Hold, Monitor, Witness) - W
f22e22b2-2a42-52ba-a3b7-e493f02107d2 | note | Detail - Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing
f5b46185-34bd-5169-b435-cf991110fbab | note | Frequency - 1 test per layer of fill
eb118f33-2791-5667-87f6-5e998964801d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
2c830bdb-381f-53d8-be12-e32e44d1d98b | note | Conformance Criteria - Fill shall be compacted in accordance with NZ4431: 2022
6171dc6a-bd1f-5ff9-9e24-693cd49a3123 | note | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet
| checkpoint | 12 - Survey As Built
21957959-bd9d-55a1-bcdd-c85bbf11212c | note | ACTION (Hold, Monitor, Witness) - W
f9339d8b-652a-5a29-835a-4159c0c1adf3 | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
eff9a66f-6751-51c5-8f51-4ea79fc2031b | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
5c09beea-9f24-52d8-9156-92101aa3f68d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
6c4a4064-83b7-55ed-9f4e-f70302d56be6 | note | Records - Survey receipt
| checkpoint | 13 - Confirm testing requirements met
13a339f0-1b8b-535a-81d5-3645879299c3 | note | ACTION (Hold, Monitor, Witness) - W
faad2d07-a86c-5e72-b17d-e6e4e7c44b4c | note | Detail - Ensure correct no. of test sets performed for fill testing
20cf8b15-d713-5857-8678-e013f7eac0ad | note | Frequency - At completion of Lot
10c07b54-d6df-51f4-a4b7-dc1c11ca0d7d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
2ba59505-d613-5c3f-9145-950a89565cbd | note | Conformance Criteria - GAP65 testing, Compaction testing
c8176cb6-ec36-5863-b5bb-8bd484b4249a | note | Records - Test results and calculations of fill volume
| checkpoint | 14 - Lot Number QA File
42712020-a79f-5ec3-a096-133c60b766d0 | note | ACTION (Hold, Monitor, Witness) - W
d044671d-1a1b-5d7d-a555-7305d76e4a8d | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
82a9f730-ad15-55a3-a049-712018733876 | note | Frequency - At completion of Lot
5ede5a98-a68e-5bcb-9da1-c6b7c6ac9946 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
12c8d129-397a-55e6-85c8-2925781f2f82 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
10880ce2-35aa-5c3e-9947-93c67d39e04b | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 15 - As-builts
00050ef5-fbcb-587d-8c60-9f624d5fb537 | note | ACTION (Hold, Monitor, Witness) - H
9cb3a5fd-5bf3-5c47-9fde-acdac88636e0 | note | Detail - Red pen mark up drawings to be included in QA file
aea053b5-4686-5fc7-a372-d7ed34b439ea | note | Frequency - At the completion of the Lot of work
5cb96b6e-fc7d-5979-bf12-b7a56c10b34c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
d145a3d5-0f76-59a3-8bdc-fdf9b10b74df | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement | itp | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement |  | 745f8f0f-997e-4616-9b85-c20e3d9cef3b
| checkpoint | Project Site reps.
ca4aeeb9-c451-5241-9bb7-14d6ab37912e | textbox | CPS Eng.
b646ee30-a66f-5564-b993-89a418e95dbc | textbox | Site Engineer
f11267eb-da48-5bca-aa59-504622ca9d3b | textbox | Quality Eng.
| checkpoint | 1 - Prerequisites
48ebec50-d948-537d-ab0d-b63359df5d33 | note | ACTION (Hold, Monitor, Witness) - W
c7dfb2c6-e570-5709-bac3-73dbed5e2c62 | note | Detail - Testing of underlined layer is compliant
920de338-19d4-5318-a228-0b4ff2837b7b | note | Frequency - Prior to commencement
b03f455d-ed26-50e3-babc-eeb78cf0ad4e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Field Test reports review
e18b5d3a-1b48-505e-bae4-90c975adcf0d | note | Conformance Criteria - All minimum requirements for each fill unit is detailed in the Earthworks Specification
bf8a8412-0365-5896-a773-5d858387445c | note | Records - This ITP signed
| checkpoint | 2 -
d5db54bc-33c3-5182-aca1-bb1d6fa8cb78 | note | ACTION (Hold, Monitor, Witness) - W
c5e05982-338a-5d3f-b805-8bafb1ff80d6 | note | Detail - Proof roll of foundation surface passed
f2e8bed9-2cb3-59c9-9b3a-9af1ca617a80 | note | Frequency - Prior to commencement
2500bfb0-a452-5629-985c-d090582790e2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3bd22ac5-7fad-5e2d-945b-82f582bfeb0f | note | Conformance Criteria - Proof roll completed with a fully loaded load truck with 8 tonnes per axle or equivalent.
f2a3470d-b197-5e2a-bdb2-4aa4ad20bcb3 | note | Records - COR
| checkpoint | 3 - Survey Setout
9c6af25d-0fe2-55c5-92a0-4f43fb4f1e20 | note | ACTION (Hold, Monitor, Witness) - H
fb680438-3449-58ce-b792-852becaf692d | note | Detail - Geogrid or geofabric set out - Set out as per Earthworks and Ground Improvement Layout Plans
4455edbf-c033-5cd8-8ba9-dbf6ed729827 | note | Frequency - Prior to commencement
ba0adf24-26d7-5766-9b4c-ad6cb5d64df2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - GPS
a08ca3e8-9aeb-5703-a200-317e7fb20fc2 | note | Conformance Criteria - Site engineer to confirm
1587c618-2778-51eb-8b6d-8c3d36dcf40b | note | Records - This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Material Conformance
2194b22a-ca3f-539d-b0f0-2d83b3bffaf4 | note | ACTION (Hold, Monitor, Witness) - M
9abb9fe4-6395-59ee-83eb-9ef36e9b25a2 | note | Detail - Ensure fill material compliance
cdc7aac7-dd4d-59cd-b563-eef0b5ecad9c | note | Frequency - Prior to commencement
b67a773c-67d0-55b8-954d-0f6fa87512b3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e742b20c-7eb5-53d2-af04-dada8bb874e4 | note | Conformance Criteria - Site engineer to confirm GAP65
903eb7bf-4f5f-5a0d-9835-eff1375406ed | note | Records - COR or Photos
| checkpoint | 5 -
ba41b82e-1763-5515-bd82-2bf0041a4585 | note | ACTION (Hold, Monitor, Witness) - M
f9a4984c-b326-50ce-a89a-9b44b39941b5 | note | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
fa331af9-613c-5635-8dc2-52fc6b080657 | note | Frequency - Prior to commencement
aed36c00-5642-588d-ab6e-65ad021f16bc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
122b30cd-4077-5f19-997e-9f211a8c56db | note | Conformance Criteria - Delivery dockets with roll details. Bidim A19 (class B) placed at backand base of cut.
71545b87-f7d6-546f-9126-c464e22e0bde | note | Records - Delivery docket
| checkpoint | -
5c9d0b9b-2f61-5494-b838-030911e2cc04 | note | ACTION (Hold, Monitor, Witness) - M
505bb32b-6759-5458-8bf4-86977ae9097f | note | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
c50fe64d-0d03-53f6-98fd-e69581bb1698 | note | Frequency - Prior to commencement
b63e6293-4e6b-5375-a0c8-d05c3ad46e31 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8b685ad4-89c9-5933-8a19-e7c928fb97cb | note | Conformance Criteria - Delivery dockets with roll details. Bidim A49 placed between rock armour and slope face.
5cc75f56-000b-5c05-b702-5df5c01edbb8 | note | Records - Delivery docket
| checkpoint | 7 - Placement of Geogrid/Geofabric
0690c08f-58bb-55eb-ab36-2226d30ccb55 | note | ACTION (Hold, Monitor, Witness) - W
9ea1c7c7-0594-5fc5-abde-1e84ddb8a1bf | note | Detail - Installation and inspection of geogrids and geofabrics: Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged.
187ced89-ce59-52ee-98d8-0b4a0d877c0f | note | Frequency - Prior to backfill
bd67586a-5aa1-51cf-ac5b-d247f0b7077d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
f58bf21e-9f82-5494-a8bf-87a803f831fb | note | Conformance Criteria - Completed and signed Check sheet.
4afeec70-fb73-53ec-bf2b-37e6d3d0a0aa | note | Records - No log or checksheet for this, will create and update
| checkpoint | 9 - Filling Operation
1854f6b2-cf43-5765-9267-660229d26f06 | note | ACTION (Hold, Monitor, Witness) - W
06f8e5d2-e4a5-5836-ade6-9d0dbef5a3c5 | note | Detail - Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced
ca77a99b-8224-5bee-8637-4781c4fa86c0 | note | Frequency - Daily
981fed8f-f98d-52b7-9216-1028b9fd60db | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c5ce028c-2548-514f-810c-34ef0f39867a | note | Conformance Criteria - Construction Observation reports and Photos
5d44cd2b-09a6-51b1-aeb7-d7d05077ddcb | note | Records - COR or photos
| checkpoint | 10 - Lot Number QA File
d75dae01-4308-5506-8dfb-0a9ecb98df34 | note | ACTION (Hold, Monitor, Witness) - W
7ca09bbb-4ed6-5644-9ee2-6dea2cde150d | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
1b399324-8488-5dc4-aa37-c06f3c3a0fe0 | note | Frequency - At completion of Lot
6490e87e-8197-5d46-960c-687f82a2f5a8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
ef556b4f-62cc-55f8-9711-4097eec4ac8f | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
fbcc9885-f3e5-5e2a-845d-eeaa6a29abdb | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 11 - As-builts
8fc1329b-4ba9-52c4-87b1-1730aa8cbce7 | note | ACTION (Hold, Monitor, Witness) - H
599b3750-6a3e-541e-b995-7035a4feb031 | note | Detail - Red pen mark up drawings to be included in QA file
093b1738-9452-5c00-84aa-153e731e14f8 | note | Frequency - At the completion of the Lot of work
3bd2de3b-a4ac-5643-9956-8fa201cfff37 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
bf646638-46be-5576-a6b5-2bfa07b618cd | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - C1503B - Mautaua Under Slip - Master ITP | itp | ITP - C1503B - Mautaua Under Slip - Master ITP |  | 93595409-952c-49ef-8efe-670682e8335e
| section | Details
| checkpoint | Project Site reps.
08c14d68-237d-5677-8fb5-9e9c90cedd25 | textbox | CPS Eng.
45c74036-bf5d-5c59-b582-6d4dd5ad90f9 | textbox | Site Engineer
19ce8c05-7451-5dff-a71f-71396b0b4a09 | textbox | Quality Eng.
| checkpoint | 1 - Confirm Solution is Appropriate for the Site
6c6a6f1d-756b-5e12-bf84-803a9786e0fc | note | ACTION (Hold, Monitor, Witness) - H
77f73635-b550-5cde-a994-5d0e965fe1f7 | note | Detail - Confirm the applicability of the solution for the site
8329c7ad-96d5-5324-b4c7-e16fd5189004 | note | Frequency - Prior to commencement of construction
da1b64f3-69da-5509-8ddd-0501fb81b130 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f7baebdd-4e88-5aaa-92cb-6b52fa0db148 | note | Conformance Criteria - To be confirmed by the CPS Engineer/Geotechnical Engineer
e9a020c1-b856-5afa-880a-a4b2f1c42bf2 | note | Records - Photos, COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Topsoil Strip
c48a9414-2a49-5578-947c-761e181afd97 | note | ACTION (Hold, Monitor, Witness) - W
ee188a7c-4b61-52bf-ab00-eb820020f7cf | note | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
3f886a48-b0e5-5c3a-9592-e0b371b78c85 | note | Frequency - Prior to commencement
a2c04c7a-8b57-5891-be16-2da55ec7c077 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
9639ebb4-01ff-5a42-a25b-19925b44c2e4 | note | Records - Photos, log
| checkpoint | 3 - Topsoil Strip
e46fc4e1-7b4d-5e46-aa41-f1bab7e8593a | note | ACTION (Hold, Monitor, Witness) - H
b68bbcd5-33f5-5d59-8ce1-4e5f3aaf1ac5 | note | Detail - Confirm buttress extents and rock armouring toe extents
df92cd3d-6fc7-56df-81c5-f67f5f7f5695 | note | Frequency - At completion of topsoil strip, before Toe construction
8ef1c077-e702-5d3e-961c-9bc9374e30e8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
fa7f480c-4204-596c-a9f1-d6a24e3c6b97 | note | Conformance Criteria - Buttress dimensions to be confirmed by CPS Engineer, including toe dimensions and placement.
761fee7d-010a-5692-a9b0-96107a962c31 | note | Records - Photos, log/sketch, COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Topsoil Strip
04de48c2-f700-5259-8c40-ce5957efbf6c | note | ACTION (Hold, Monitor, Witness) - H
c8cdcf4a-dc0c-5775-8243-91345b558f6f | note | Detail - Confirm Buttress foundation to be on suitable natural ground
e4db3c86-d098-573e-8459-1e9e4bee495d | note | Frequency - At completion of site clearing and foundation excavation
0109c46a-835a-5ca2-b2c9-8baa4769d823 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the CPS Engineer
1a69641e-808e-5e67-9c95-26dfb9d33804 | note | Conformance Criteria - Foundation to be suitable natural ground
b57876e4-298e-5bf7-b099-4edf7a387341 | note | Records - Photo's, Scala, COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Topsoil Strip
7586caae-c537-5d7b-8865-b5e95b4312f2 | note | ACTION (Hold, Monitor, Witness) - H
82e96f6e-2c3c-58b6-8bdf-0a85cb4e1b04 | note | Detail - Confirm Slope face is 2H:1V if its required to be as steep as 1.5H:1V CPS Engineer approval is required
d91f1bdd-9717-5c89-8a2d-273a2d4322fe | note | Frequency - At completion of clearing and foundation excavation
2bfd5fab-5698-5c61-b378-743c12be818d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the CPS Engineer
91e5045d-679f-5fd1-8d8f-df25140cb93d | note | Conformance Criteria - Slope 2H:1V - proceed
8328cc5c-44be-584b-985d-9a1fe5b684cb | note | ○ Slope >2H:1V CPS Engineer Approval required
92b8fcaf-eb98-5132-8b47-04bf79689e75 | note | Records - Photo's and COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Materials
345aed39-d5a6-587a-88b0-4efd00e4bb02 | note | ACTION (Hold, Monitor, Witness) - H
d1e69ce8-0425-5a45-88ca-ea0c8ce13a25 | note | Detail - Bulk fill to be approved by the Engineer
6006c287-a161-5372-8db2-ff7395fae410 | note | Frequency - Prior to commencement
e48318ed-627a-5283-a497-83e2796ba205 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
815b1ddb-077a-5bd3-ac1e-6a3e15a77e79 | note | Conformance Criteria - Rock of GAP65, 100, or 150 grading. Broken faces.
bef7fe3a-dcaf-598e-9d37-8867cf2bb632 | note | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Materials
b225e137-75db-5af6-a856-7da3a38157b9 | note | ACTION (Hold, Monitor, Witness) - H
8a942d22-9c9d-5569-94ae-e3e9f85a7d39 | note | Detail - Rock Armour to be approved by the Engineer
6ef673e8-99b9-5da0-83c8-7631b9ecf8e8 | note | Frequency - Prior to commencement
0cb82983-3e07-5575-bc33-d8695ed7af7d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
fc36c396-063f-58cb-b10f-b35a8a0eb53c | note | Conformance Criteria - Rock armour shall be hard, durable, crushed, quarried or natural stone free from dust, clay, organic matter and other deleterious material. the stone shall be free from laminations and cleavages and shall not disintegrate on exposure to weathering.
780cbdd7-ca5a-5fe2-9dcc-cefbb991f056 | note | ○ Rock to be SG 2,350kg with a D50 of 450mm
889d2698-e963-5e05-8532-fb18f734c446 | note | Rock size to be:
8022ba40-d7f5-56bf-a89d-6a65d90e125d | note | A. Gradation D85/15 = 1.9
d36ad47d-6931-5f02-8e2f-1574a8d0b7b1 | note | B. D85 max 690 (max) and 590 (min)
24fddc87-3b6b-57a8-b970-781158c9000f | note | C. D15 390 (max) and 275 (min)
f031ff95-78a1-584a-9d64-0b9fd81910be | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Mega Flow Strip Drain or Drainage Blanket
d29f96c0-38ee-52f9-84e5-1d65547af78c | note | ACTION (Hold, Monitor, Witness) - W
5475843e-601d-51fa-ae27-8313bfb9995d | note | Detail - If seepage is present in the slip scarp mega flow strip drain or a drainage blanket is required.
65e2c1b7-1b12-5c51-a3f6-9df148d67c79 | note | Frequency - Prior to commencement
21a26e5e-cabb-5a9a-921c-4d37d4e65136 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a0f23d40-c42c-5d14-a1e2-8d758275ce01 | note | Conformance Criteria - Ensure Bidim complies with specification
8a35b490-f483-536c-90eb-ea7ee17358b3 | note | Records - Photos
| checkpoint | 9 - Geofabric
8236c5e9-0148-5771-a904-32d2b8d89dca | note | ACTION (Hold, Monitor, Witness) - W
7d5a6874-2a43-5b70-bb34-25f63b156373 | note | Detail - Lay Bidim A39 geofabric over the slip between the existing ground and the bulk fill. Lay Bidim A49 between the bulk fill and the rock armouring.
dc0483dc-4ae4-5007-86dd-4cbeb93f2479 | note | Frequency - Prior to commencement
28e4f73a-726f-5a82-a0fc-300851eb30cf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
058554c0-cfd9-5d89-8a06-a5e129ab9769 | note | Conformance Criteria - Ensure Bidim complies with specification
47f26b63-a44a-5899-b2c7-bb651156474a | note | Records - Photos
| checkpoint | 10 - Geofabric
7712da06-31e7-50e3-861b-1b6196c79200 | note | ACTION (Hold, Monitor, Witness) - M
3eba0a87-681e-5fe3-8dc6-2130051983c4 | note | Detail - Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres
3df4df01-fa69-5b8b-a7bc-c62be008382f | note | Frequency - On completion of geofabric installation before fill is placed
60070e13-402a-5d60-a502-c00fa8d6bdbc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d711d07f-2292-5264-a342-0c7c65850fdc | note | Conformance Criteria - Manufacturers specification
054df029-edec-5718-b02c-60db9703aeb4 | note | Records - Photo's and Site Diary
| checkpoint | 11 - Geofabric
7bca3424-95f2-563a-b1ee-75ee1674ab94 | note | ACTION (Hold, Monitor, Witness) - M
27647efb-c9b1-5840-a043-5919cfbab810 | note | Detail - Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings.
066649bf-14d1-58c8-92ce-b7c187497c57 | note | Frequency - Prior to commencement
f694858b-5349-556b-9db3-ebb275845495 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d36530ab-52c5-582d-80e6-6d29a7d55c03 | note | Conformance Criteria - Delivery dockets with roll details. Class D placed at back and base of cut.
713a7601-1156-5029-9407-58e7229f50aa | note | Records - Delivery docket
| checkpoint | 12 - Filling Operation
1b1b74c0-82a5-5eb4-8e5d-7950fe1acddd | note | ACTION (Hold, Monitor, Witness) - W
1eecc0fc-78fd-5f14-96ae-6ab53f385a11 | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
3b3a0e63-498b-50bb-a3aa-d1d146c1ac6e | note | Frequency - Daily
a73a625f-114f-5bd3-bb7f-977ebed5e176 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
43797d6b-e25f-5715-927f-152c712af518 | note | Conformance Criteria - Fully drained conditions
85b6a2d2-641e-57fa-9eaa-78dcdffd5686 | note | Records - Photos
| checkpoint | 13 - Filling Operation
d2d034ce-48c5-5ab5-8b48-d58ee01f57c4 | note | ACTION (Hold, Monitor, Witness) - W
6d4acec0-91ff-54e9-92ff-494247400eef | note | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
f1c39e48-551a-5102-81ef-abb8137b001d | note | Frequency - Daily visual survey check
c4ad24d1-e7be-546c-8855-b33636014362 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
bc7a4b7c-60a2-56b9-af57-a4f8d70e84ed | note | Conformance Criteria - Line and level to be worked through with CPS throughout layer installation
29b0ca06-9f83-5a0c-9ffb-962c445e2d4f | note | Records - Photos, Site log
| checkpoint | 14 - Filling Testing Requirements
6e56eebf-74f7-5166-a881-a20c93ca84f5 | note | ACTION (Hold, Monitor, Witness) - W
671ca6ba-29e0-55cb-a625-0f8805a9c1ef | note | Detail - Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing
824093b7-cddf-590c-81e7-f9efaf258821 | note | Frequency - testing low middle and top of buttress
1c483823-59c5-5940-a1a4-bc10897d8595 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and NDM Testing
a5808135-5ebc-5b67-8b3c-70d8be12f07b | note | Conformance Criteria - Fill shall be compacted in accordance with NZ4431: 2022
4bdd6194-2841-5ea9-a797-0ccd25692490 | note | Records - NDM testing report
| checkpoint | 15 - Filling Testing Requirements
f4675b19-152f-5810-8c44-0b15ebdc214a | note | ACTION (Hold, Monitor, Witness) - M
0229f8ea-18c5-519a-859d-97d2c460478d | note | Detail - Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings.
be7c2a64-f497-5fbe-92fe-9744c43a0cbb | note | Frequency - Prior to commencement
3be34958-f877-5ea1-b601-337e0f4771ba | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
44e628c7-4294-55c4-8aa9-b483efc9398f | note | Conformance Criteria - Delivery dockets with roll details. Class D placed at back and base of cut.
ba305d18-ffcb-54a3-b872-d0615ef47aa7 | note | Records - Delivery docket
| checkpoint | 16 - Filling Testing Requirements
315c4be4-6336-5c3c-83fe-c1d21b51fe9a | note | ACTION (Hold, Monitor, Witness) - M
2baa5cfa-6ec5-575d-ab8e-d7502430a549 | note | Detail - Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres
aa953b3e-554f-5bf9-836c-f2a0b134b760 | note | Frequency - On completion of geofabric installation before fill is placed
74891f9b-503b-5f8a-ad80-8b1486866b1f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d670c441-024a-5467-b2ea-c01c21bc1251 | note | Conformance Criteria - Manufacturers specification
8b41881c-4ca3-55a2-bf57-4e0be0dd9266 | note | Records - Photo's and Site Diary
| checkpoint | 17 - Filling Testing Requirements
fc567c33-ddd3-55dd-b1fb-fa90fd5982b8 | note | ACTION (Hold, Monitor, Witness) - M
2439427a-f450-573b-a620-5f23fe117f02 | note | Detail - Use of the correct geogrid between slope face and rock armour- Check information on the delivery docket against the requirements indicated on the Drawings.
85d66cf0-b7a8-54c8-94b3-534bf4ec452b | note | Frequency - Prior to commencement
6df61c83-e139-5dd5-9c8a-c3844b481028 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
68b626e9-5f4d-5903-a43f-bfd5412be65b | note | Conformance Criteria - Delivery dockets with roll details. Bidim A49 placed between rock armour and slope face.
ff3e9842-c708-5b87-ade7-deaa2e1d2200 | note | Records - Delivery docket
| checkpoint | 18 - Riprap Placement
cc091761-df42-504f-942e-bdcf057c243d | note | ACTION (Hold, Monitor, Witness) - W
bfa700e5-96eb-55f2-8bfe-bdc000474e43 | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
82ecbdfc-82d2-5203-ae69-b969794fcc92 | note | Frequency - Daily visual check
37edc961-1956-57c2-97c3-efb5bf7e616d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e4cd16b7-2cd8-5c5b-9cc0-41fe228b3ec8 | note | Conformance Criteria - Specification
5c9d6437-7f8f-5604-8858-e3e32274094c | note | Records - Photo's
| checkpoint | 19 - Trenching
e85518dc-712b-5f48-9147-c0599f51f4b4 | note | ACTION (Hold, Monitor, Witness) - H
3095a933-a9e7-5e89-bbc6-cace234fd425 | note | Detail - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
431a476f-ff45-52c5-a352-79880b03c65c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
086d0454-5ac0-5214-aadc-f52557edb09c | note | Conformance Criteria - CPS Engineer to instruct action
410f3702-8519-559b-9784-4d35b3652006 | note | Records - RFI
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 20 - Trenching
81bd8c95-272c-58cb-a877-d79d794aa286 | note | ACTION (Hold, Monitor, Witness) - H
2ba54ef9-ea28-5c97-a383-d33ce4ee27cd | note | Detail - Location to be determined by CPS Engineer
b880c47b-cd1a-5579-a28e-25bfb7e83fd4 | note | Frequency - Prior to install
40135429-b334-567c-bf27-2dd8c1dd4143 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
05210e2f-3cec-551c-9ef4-1252aaa6fd49 | note | Conformance Criteria - Trenching location and direction to be confirmed by CPS Engineer
20f6f45f-384a-5345-a0bf-050af22db31c | note | Records - Photos, Log TBD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 21 - Drainage
2384ddb2-5634-54c6-869a-5c5341684bc1 | note | ACTION (Hold, Monitor, Witness) - W
00ce6ee9-aabb-5a4d-91a8-79ed35f73856 | note | Detail - Ensure drainage outlet from pavement connects to buttress fill if required
0d6f9b52-2987-5816-aad7-cd2f77b8621d | note | Frequency - Prior to pavement commencement
9e076c6c-66c5-570f-85b9-3989165bd464 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
368b2ce6-ab76-5d25-a586-75e96032f1b9 | note | Conformance Criteria - Confirm drainage connection if required
8db3efbd-9535-5568-ae75-c1744b22ff8c | note | Records - Photos, Log TBD
| checkpoint | 22 - Road reinstatement
554faf58-cdf6-5667-8b3d-ae6766a23e3d | note | ACTION (Hold, Monitor, Witness) - W
6af42992-5470-535b-8e8c-02c17fd6ff97 | note | Detail - Refer to Pavement and Surfacing ITP's
e59e75a9-6d17-52cf-9c64-5dbcec707c88 | note | Records - Pavement and Surfacing ITP
| checkpoint | 23 - Survey As Built
5cab7663-4b4a-5078-9b1c-aa8592d1f466 | note | ACTION (Hold, Monitor, Witness) - H
635a3861-e8c6-5913-9a50-2221f5be3145 | note | Detail - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
3e706729-4be0-50c0-a1b2-d6caad5b2d64 | note | Frequency - At completion of sub soil drainage line
0f26a82b-42e4-5d1e-a7c1-0e8aef2505f6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
546d8075-6744-5ab8-932d-c4f6a340dc78 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 24 - Lot Number QA File
b65cac74-0b93-5965-bddd-eab65eff199e | note | ACTION (Hold, Monitor, Witness) - W
e457ab5b-f70d-5e01-8f00-d1fce23bffbe | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
463be53b-578c-527a-8f18-28cfd7cc1f08 | note | Frequency - At completion of Lot
0388a153-c860-5ac0-8627-d53b1169fa45 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
968a7d38-2203-5ef8-8aea-2204ef5c45d6 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
8d2e211b-d02f-53e2-a25b-26f85c70a585 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 25 - As-builts
ba792bee-c866-5c69-a1a2-846099870dc9 | note | ACTION (Hold, Monitor, Witness) - H
7bdaddea-0811-5221-9525-deb6e6703709 | note | Detail - Red pen mark up drawings to be included in QA file
cb616503-0378-5b0c-b1ce-12d0fe413751 | note | Frequency - At the completion of the Lot of work
e3a3e096-0e25-5861-827f-32e5fea5c398 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
7afcc781-8c09-5e10-84df-c92793e102ea | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - C1503B - Mautaua Under Slip - Rock Armouring | itp | ITP - C1503B - Mautaua Under Slip - Rock Armouring |  | a50cb28c-1f87-4b06-8391-ffc4e21a6c87
| checkpoint | Project Site reps.
61468ce6-4c44-5ebd-9dac-7e238c15384d | textbox | CPS Eng.
1740bafa-2d94-5ccf-ab77-09aa8f74fc43 | textbox | Site Engineer
2f7d1ac9-0d40-5246-a8da-91540c5338ff | textbox | Quality Eng.
| checkpoint | 1 - Foundation Inspection
39415dc7-880b-524c-b613-6540c7be0b94 | note | ACTION (Hold, Monitor, Witness) - W
d6db8628-fc48-5b1d-a17b-d8a616ac26b0 | note | Detail - Inspect fill foundation
572345d2-590c-5eab-a844-da37a2e370dd | note | Frequency - Per area as required
5509d1f8-e47c-5bcb-8b13-8ae76a17c373 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
c9bd2484-f8cf-5c5f-bf68-e13e94070404 | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
5fc5c201-c4be-5d07-b817-db2446884bac | note | Records - CS-4100 Subgrade Approval Checksheet
| checkpoint | 2 - Material Compliance Testing
f9e0c859-7068-5e40-91a1-423b00ca489c | note | ACTION (Hold, Monitor, Witness) - W
ae0d972c-d654-5bea-b598-15036956369d | note | Detail - Material to meet specifications dependant on material type selected
b40a210f-4813-501a-a2d0-55d38e0049f8 | note | Frequency - Each material used
02357632-3c07-5e41-a522-be55fa50b360 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d4897cae-c3fc-5cb8-8308-ff84c2b53abb | note | Conformance Criteria - ROCK ARMOUR SHALL HAVE A D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
a702920b-ba03-5809-88ce-2315660239b8 | note | Records - Lab Test Report, delivery docket
| checkpoint | 3 -
9745ce43-07d4-5013-968b-ef3df36ffcac | note | ACTION (Hold, Monitor, Witness) - W
7f6b1a3e-0905-50ed-888a-16b0d2945fa0 | note | Detail - Rock Construction Material
23aa24dc-744c-540e-b4c6-7b0fbde39c7a | note | Frequency - 1 test per batch purchase
1ed3a967-bdf6-5a74-acb8-6d683a8c9098 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
c0937a14-91c5-550e-8373-ab5be234010c | note | Conformance Criteria - ROCK ARMOUR SHALL BE HARD, DURABLE, CRUSHED, QUARRIED OR NATURAL STONE FREE FROM DUST, CLAY, ORGANIC MATTER AND OTHER DELETERIOUS MATERIAL. THE STONE SHALL BE FREE FROM LAMINATIONS AND CLEAVAGES AND SHALL NOT DISINTEGRATE ON EXPOSURE TO WEATHERING
31b6985c-4591-52fa-98c1-ebd0714a470a | note | Records - Lab Test Report
| checkpoint | 4 -
9f71d66e-3a6a-5cf7-9a73-fb98a9295769 | note | ACTION (Hold, Monitor, Witness) - W
6f391fcc-54f9-5bdb-8c1c-c07f3c99e3ec | note | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 and Tencate PES 1000/Tencate PES 2000
02ce2f53-0913-5d14-9ae8-fcf8add05083 | note | Frequency - Prior to commencement of placement
1a011959-6acb-5792-92cd-ecfc7b0bfd70 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bf895ec4-c4e7-5955-b9cd-092e28c4cffe | note | Conformance Criteria - Conformance with Specification
3df19563-818c-5147-862a-ebd484dc429a | note | Records - Delivery Dockets
| checkpoint | 5 - Construction of Engineered Fill Embankment
4ed914af-d11c-5e9e-a6ec-9aa0774e8000 | note | ACTION (Hold, Monitor, Witness) - W
a17ee469-b647-55ee-ae7a-9a5d7c613e5e | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
536b35bb-f5e0-5435-a134-3bfb6e4ad4c6 | note | Frequency - Prior to commencement
f543687b-0b25-599b-8652-85058c441b63 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bb386fc3-3cd7-53c8-904b-23e3b1576bc3 | note | Conformance Criteria - Intake Earthworks ITP completed
bdd51e3f-d87f-55e7-96e3-9d4ee6630995 | note | Records - Backfill ITP
| checkpoint | 6 - Geotextile Placement
46041add-393a-5ef6-a4ad-0224f377450f | note | ACTION (Hold, Monitor, Witness) - H
aae3a285-3f7c-50e7-810c-4367dccd8b70 | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
cce0c0f6-9eb7-5acf-a595-96561d97c695 | note | Frequency - Daily visual check
b3b0c80b-fe55-5056-8ef6-5c0fc8afd7a4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
270a93b7-46d6-5b1c-8b05-3ac69dc7c80f | note | Conformance Criteria - Installed in 0.5m trench laid back, as outlined in drawing
e54c9c50-bb19-5b0a-bc0a-c20942afa398 | note | Records - Photo's, insepction log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Riprap Placement
7f1d3f90-a066-5111-a849-b57702305a3c | note | ACTION (Hold, Monitor, Witness) - W
ebb2699c-c34b-5f2a-86e2-5d23562b9250 | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
7d9542c5-448e-5733-a292-b35072a8ece1 | note | Frequency - Daily visual check
a8a0b1e7-fb2c-549e-b853-d2b0082ad5d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
db5f232c-5824-5117-a1b5-719a4f6a0a87 | note | Conformance Criteria - Specification
c9bf1525-736a-5153-8082-ce28e4e2e403 | note | Records - Photo's
| checkpoint | 8 - Survey As Built
9f6d5382-bd89-5157-8b53-193b7f9c7af0 | note | ACTION (Hold, Monitor, Witness) - W
8ff0233b-0f76-5474-8908-a42f2cd6bfd8 | note | Detail - Ensure rock slopes comply with design prior to next process taking place
7900975b-d635-5533-9a0e-b56f6a36857c | note | Frequency - At completion of Lot
6d51d184-e406-57e1-bcc0-33a7b54cda4b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
84a63fa4-0b11-5817-abf4-c0a2ea219b0f | note | Records - Survey receipt
| checkpoint | 9 - Lot Number QA File
705717ce-e384-5ea5-a74d-aec32b93e073 | note | ACTION (Hold, Monitor, Witness) - W
bcd6d59e-2e58-5e2d-880f-7dcec90244b9 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
d4aecc9b-a74b-5312-9050-ab20d1f4f7f6 | note | Frequency - At completion of Lot
db9bc96a-d501-524c-abb1-8515fd7777af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
21d8a015-8aa4-5973-b012-6aa99c01df6d | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
dabc297a-ef6c-5627-8be8-34e8e68256d9 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 10 - As-builts
669a768f-e9d7-53a3-afca-83984504f6e4 | note | ACTION (Hold, Monitor, Witness) - W
f9b87baa-375d-553f-8816-7c11e778a734 | note | Detail - Red pen mark up drawings to be included in QA file
4701edb3-c6e7-5915-906c-0c6240cad0be | note | Frequency - At the completion of the Lot of work
ae96f9a4-b653-5734-9367-ab079286a6d0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
fb9a593f-4419-5715-ace8-18e63c82248c | note | Records - As-built Drawing
| checklist | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage | itp | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage |  | 250b0a90-79df-40ce-ad7b-f9574acb0824
| checkpoint | Project Site reps.
518547c4-4814-5532-9f94-bf9bcd80a4d1 | textbox | CPS Eng.
14cc70c9-af48-592a-ac79-388f0865b3c9 | textbox | Site Engineer
d530125b-909f-542e-8997-ee009cf70568 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
d9e383c2-7a71-5945-836d-d65cf5b0dca8 | note | ACTION (Hold, Monitor, Witness) - W
3c45f520-d40f-59df-b59f-448aaf27e4d7 | note | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
56d42fee-019d-566c-bc60-70322f054d89 | note | Frequency - Prior to commencement
8adef0d4-10e4-5aec-b187-d55713795500 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
af6c91bf-10fc-5210-8537-4a4a13adf5e3 | note | Conformance Criteria - Consistency with Construction Drawing
7d5803b0-5ba7-5f94-b7be-5e11e8eb5114 | note | Records - Survey receipt
| checkpoint | 2 - Material Compliance
24278092-7420-5f84-9c36-df3679a03255 | note | ACTION (Hold, Monitor, Witness) - W
23485923-cb56-5e81-81da-e14fe316768f | note | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
83a8555b-fdd8-5fd2-87d1-c6593f5d6fcd | note | Frequency - Upon delivery to site
40db272d-fadd-5ac5-a7e1-64da1e1f0aa6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
f58c3047-d14a-567c-8ee5-962d9e279a35 | note | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
400162e9-6fd5-57e5-94eb-82ef602b0060 | note | Records - Delivery docket
| checkpoint | 3 -
e553f369-b132-5ef5-8188-54eeaaf4ec70 | note | ACTION (Hold, Monitor, Witness) - W
25dac27e-b01f-558b-a8ea-2fe1aa10b90d | note | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
58c757c3-6e69-5894-b356-10554df7497a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
9b45b5c2-149c-545a-9ad8-08514e80798d | note | Conformance Criteria - In accordance with TNZ F/2
2bee2370-0a69-5dac-aaf4-76a03ca43c83 | note | Records - Delivery docket
| checkpoint | 4 -
c46c962b-fd08-506d-9ec2-d4c64b4802bb | note | ACTION (Hold, Monitor, Witness) - W
ba9b76dd-b925-5098-a9f6-8ac90a4ca626 | note | Detail - Ensure the bidim material is A19, Class B.
1ce9d3f9-7cea-5db4-899b-d07bdf23356c | note | Frequency - Upon delivery to site
f0409eea-2499-56f0-a51a-ca34b1b8ee84 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
9e08d9f1-9663-572c-b976-e964399d5f81 | note | Conformance Criteria - Ensure geotextile is approved for use
db0ad907-1ecf-574a-9c6f-cb238f6786fd | note | Records - Delivery docket
| checkpoint | 5 - Trenching
146eb9a2-9600-5591-affe-51de8dec9f17 | note | ACTION (Hold, Monitor, Witness) - H
72ef3bdf-db4c-5f77-b086-811702c92cf7 | note | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
406724a7-3366-5801-8ac0-81ded2b6db70 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d5de1f84-d252-59ef-8444-56e640f6c13a | note | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
337c658d-9011-5cea-bc75-4f7e63d95bf4 | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Bedding, pipe installation and Backfill.
60cf15bd-56e7-58b6-9b46-faf04a95b11c | note | ACTION (Hold, Monitor, Witness) - H
35311b4d-9b36-5224-97e0-24d6dd2ee99a | note | Detail - Upon completion of trenching approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
749b3153-a047-55a9-8b10-7999ef7cb388 | note | Frequency - 10m intervals
47e42812-bacc-577d-9acc-611543b27711 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
bb928e98-b21a-527a-b0b4-97d721aab1aa | note | Conformance Criteria - Ensure material covers the trench and is pinned in place
a754a727-9563-5995-8672-1231513a6d39 | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
6e9aaad7-c0d4-507a-bf84-6bad0d3c1b50 | note | ACTION (Hold, Monitor, Witness) - W
a4aa2e7a-4778-5e36-ad89-bf4e51002550 | note | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
1d05e76a-2bcd-5426-a504-4c7be23d94d3 | note | Frequency - 10m intervals
1c006e6f-fbda-5982-a9c0-de85efb0a362 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d122e852-db4d-5b64-8248-3b723e472c4d | note | Conformance Criteria - Record levels of top of bedding on dip sheet
c9c22caa-a5fa-574a-9e30-f9315de49c20 | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
| checkpoint | 8 -
87f750ff-02e6-5476-8297-7b172ced93df | note | ACTION (Hold, Monitor, Witness) - W
3ef662a4-785e-580a-8fca-7ccbd186c09a | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
5cc7eaf1-e44e-5f94-a021-598df3a041d0 | note | Frequency - 10m intervals
5f08a244-589f-5ce9-a946-ea88d750c4ad | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
06cb943a-fbc4-5dff-b610-92abddd40a0f | note | Conformance Criteria - Consistency with Subsoil Details
69305cf7-8f4d-59b8-93a8-94d99aee8903 | note | Records - Photos
| checkpoint | 9 -
98a42d01-d10d-5184-b310-4ca1e06151aa | note | ACTION (Hold, Monitor, Witness) - W
3b869e05-519e-53a3-9a57-a997e842ca8f | note | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
98e34fd7-ad81-541f-b0d9-9c89d2525357 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
08a2822d-a396-58ae-9fc6-6389ed86add6 | note | Conformance Criteria - Ensure good coverage
d3bac1bc-1e40-5eb7-9458-498530c27b74 | note | Records - Photos
| checkpoint | 10 -
f2607903-bfb5-5d4c-9a07-bcb6bc34c8a8 | note | ACTION (Hold, Monitor, Witness) - W
caa0e245-b89b-5de3-bc19-8d99ded0a535 | note | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
5f17e6ce-7594-5d2b-acd0-57f6d5e56eb8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
| checkpoint | 11 - Outlet to any open areas
5306d9d9-200c-5108-99f0-63583c6f2238 | note | ACTION (Hold, Monitor, Witness) - H
05d45edc-f5d1-57ad-8910-23ba4ada99e0 | note | Detail - If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately
fb6e68a7-e0e9-5203-8839-81c1042147af | note | Frequency - As required
5587b5c8-65d2-5bcc-98f9-eca2fdf57a58 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
de777e7d-b2a6-5684-b4fc-c554edcab8de | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Survey As Built
8b715dc8-8c01-561f-802e-bed3198a7163 | note | ACTION (Hold, Monitor, Witness) - H
b45a30de-5a5d-50d9-94e8-d6b3d2fa828d | note | Detail - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
c3588d61-1ae5-5dd7-a010-9307620e9912 | note | Frequency - At completion of sub soil drainage line
031eea27-445d-5187-8878-26d5ecf3e790 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
5c6215ae-2e16-540e-b5fa-204c314efbdd | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Lot Number QA File
b1551c7a-afa9-5c3f-925e-d4c81fe66374 | note | ACTION (Hold, Monitor, Witness) - W
d5a4576e-3b2d-50e0-88e5-489ddc2b6715 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
541978a6-27d1-5e71-9ba8-a51a9d5a1e1b | note | Frequency - At completion of Lot
d93a94b4-8263-5275-9213-73cf251ca389 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
978a7468-025f-5a47-85ee-d89ef795f6fe | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
0af46dec-3912-5497-b2e3-3b8c51dd0087 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 14 - As-builts
7fc82291-ed8c-5a47-9f7c-1d07622a4843 | note | ACTION (Hold, Monitor, Witness) - H
175d8fc6-c4bb-504b-816d-1f7092b4ee23 | note | Detail - Red pen mark up drawings to be included in QA file
2c360225-4a26-5239-9d7c-3de4f1dd7a21 | note | Frequency - At the completion of the Lot of work
400c4195-91fe-50d4-b299-5d34fe459c05 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
5a3af319-0613-5621-a0f8-4c4b1f64936c | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction | itp | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction |  | f2874e3e-d6e4-4b93-9b52-60e0c58a929c
| section | Details
| checkpoint | Project Site reps.
8a1bf955-012d-56db-96ce-6e95f9578ef0 | textbox | CPS Eng.
dc9bc617-d02f-5aa2-b92a-595fbe4102af | textbox | Site Engineer
b7c9aa30-a42d-51c8-b820-41ef4e8a0883 | textbox | Quality Eng.
| checkpoint | 1 - Sub Base Signed off
2668510f-631d-5368-9c61-69fde62311e3 | note | ACTION (Hold, Monitor, Witness) - H
f5994546-4acf-54e5-b893-3d79058b2fcd | note | Detail - All previous Activities completed & signed off before Placing base course
a4d55f60-43f5-5759-a068-80ef7cc7727d | note | Frequency - Prior to commencement
99b3a2cf-6cc8-5666-a422-16725d4ed881 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
535c8374-0c83-5556-bd4b-5617e6dedaf5 | note | Conformance Criteria - Previous ITP completed
eed39c70-777e-5118-b587-ddecd81ab565 | note | Records - ITP - Subbase Construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
4f9d36ac-0a5b-55df-9a30-6ddd9665bbcc | note | ACTION (Hold, Monitor, Witness) - H
970e644d-a0d2-51a5-a327-ab8ccb79fe4f | note | Detail - Cross Fall and levels to tie in with pre-existing carriageway
798a1fc5-ef98-5267-83fc-bd4db4f6a116 | note | Frequency - Prior to commencement
59af329b-ba23-5899-add1-626fd6b00025 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
a58b6133-8a39-5327-b07c-60952ed3b3f4 | note | Conformance Criteria - Set out and levels agreed with CPS Engineer on site
15df0b4d-c336-566c-90ff-cebea009cb5b | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance
43b39d8e-c592-530e-94c4-d79582f05b4c | note | ACTION (Hold, Monitor, Witness) - M
98dcdad6-863b-5148-9133-f23cd6ad2e9d | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile.
ea658786-3ce5-5759-8e14-6d078b3b0a27 | note | Frequency - During construction, traceability of all materials delivered to site
64233547-a811-5072-83a1-1579b8453865 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check, document review
180c1c08-79f4-5126-9562-9fe3bb3cd94e | note | Conformance Criteria - Conforms to TNZ M/4 specification
5028fc67-ac0c-5696-b9d3-0f983732f0ff | note | Records - Delivery Dockets / Records
| checkpoint | 4 - Basecourse Construction
b8d0ffed-9f79-5ade-b7db-8a9acae4f700 | note | ACTION (Hold, Monitor, Witness) - M
49400f2e-1e8c-5412-a6aa-69d9093cbd93 | note | Detail - Basecourse Aggregate
36f7dd26-7718-511b-acbd-b12ec416884e | note | Frequency - 1 sample/10,000M3 or 1 per source stockpile.
e0267267-2c58-5ee0-9699-2cb8e3c3dd80 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - PSD, Atterberg Limits, MDD, OMC and CBR
64033c3d-b289-55e0-9135-3be2de4dd93c | note | Conformance Criteria - Comply with TNZ M/4 specification
20eb7018-d96a-5d88-8712-ec5288f2a6a3 | note | Records - Lab test result
| checkpoint | 5 - Basecourse Construction
a0cf2fb8-f697-56a5-b58b-fc78a80dca7b | note | ACTION (Hold, Monitor, Witness) - H
020b629b-0f45-5075-8487-d76ddf3cd549 | note | Detail - Degree of Compaction
aba17465-446d-57d9-964f-7f4e6bdae2ec | note | Frequency - 1 per 1000m2 staggered
64255000-1bcc-597b-8d3b-e835a9416646 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
c181b696-68fe-5270-a8a9-c38c912429e1 | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
381336ca-d351-50dc-87e1-91ee82c840a0 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Survey checks
81b3e9d2-d4a3-51da-99b3-8c56876d50b4 | note | ACTION (Hold, Monitor, Witness) - H
9510d273-b871-5158-851e-bff06a361d95 | note | Detail - Cross fall check. Surface shape check.
a06a8942-34d1-55d5-92cb-06c83e963257 | note | Frequency - 1 per 20m staggered
9d480a0c-fac6-57c4-8303-e46ce260178e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check & Measurement
42a7003b-b390-53ad-ac47-11a1e1135014 | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
ff9229f0-7da1-5178-8e79-0f09524c0fdb | note | Records - Photo's / QA records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Surface finish visual inspection
a3d3f94c-93c0-56b8-90dc-78caf0838085 | note | ACTION (Hold, Monitor, Witness) - H
11dcd8f1-ec59-55c4-aa7b-4f661bbedcef | note | Detail - Surface finish check
9169b6cc-619a-5443-897b-2a62c5d870de | note | Frequency - Prior to sealing
d5c8edb3-a99b-5234-ad54-845bb2b8446d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
877a337c-63ff-5c33-8bfe-a48c41105592 | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
93619291-382e-5455-828e-6b3a275b2e78 | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway | itp | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway |  | b2a4f3ca-28dc-473a-93ab-0a0e4511bb8c
| section | Details
| checkpoint | Project Site reps.
cc9e2a19-dfbe-5067-8541-babcabc9b119 | textbox | CPS Eng.
c6adeb89-a90c-51cb-aefe-f016a511a92e | textbox | Site Engineer
178ac339-3abc-599c-82e3-24dea4c618f2 | textbox | Quality Eng.
| checkpoint | 1 - Seal Design
5913534d-9c8c-5d11-9386-0bfc4a5699a8 | note | ACTION (Hold, Monitor, Witness) - H
0f0f11dc-d672-587c-9022-6a5a2156b091 | note | Detail - Seal Design to be submitted by Contractor for review and approval by CPS
d5f8bb21-87f5-5b1e-8c71-3d31c899de28 | note | Frequency - Prior to commencement
6415f021-0073-5cc9-a9f0-59417c8f7e5f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c2ba6fb2-0529-563f-94a0-73ad356aea42 | note | Conformance Criteria - Approval by CPS Engineer prior to activities commencing on site
68e58b5d-a64f-5cdf-aee1-b65a26a3f484 | note | Records - Seal Design
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Previous Lots Completed
ec357bce-55d5-55c2-8eba-263fd6e420f0 | note | ACTION (Hold, Monitor, Witness) - H
94431e3d-14b9-5661-bdad-549663634ad3 | note | Detail - All previous Lot ITPs - Basecourse Construction and/or Modified Basecourse completed & signed off before Chip sealing laying commences
c8bdb10a-45fd-50b0-9ef8-ddfaf21596af | note | Frequency - Prior to commencement
2815540d-5407-5f7a-8d50-8ad0923bc7b6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
156911de-a0a5-558f-9b05-b298eb9402e4 | note | Conformance Criteria - Previous ITP completed
4f5eaed1-05ed-5d93-a09b-05abca92ed53 | note | Records - ITPs - Basecourse Construction and/or Modified Basecourse
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout
ba04b947-73ab-53cd-99a8-66a538ddb53e | note | ACTION (Hold, Monitor, Witness) - H
2f70dd47-d228-5a31-931e-0b95253b3014 | note | Detail - Mark out the extent of the seal if not working to a kerb line. Square off edges to tie-in to existing pavement if encroachment is into wheel path.
3499b3c1-4a88-5bf3-9527-82411b24a468 | note | Frequency - Prior to commencement
30d18d5e-3b2e-5399-b4d9-e072811a6602 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
44c46191-1a90-5a57-aae3-421e9f899dcd | note | Conformance Criteria - Spray paint edge of seal lines
cf8899c4-2242-5f9f-8d66-37e6f791de2c | note | Records - Sketch / Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout - spray runs
51d3f590-b61f-5441-8811-c810b8a2ac17 | note | ACTION (Hold, Monitor, Witness) - W
307b3828-b275-5164-b61e-9deaba28d4e5 | note | Detail - Determine spraying runs start/stop locations
81f7c621-c4c3-538c-9093-cc565a9c6329 | note | Frequency - Prior to commencement
e976479d-ca42-5c2b-927e-d5b943b2d061 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
2e4ecbb5-0943-5879-ad37-1d867687a60b | note | Conformance Criteria - Mark out on site
d97ccd4d-8d1f-5142-a5a6-135c5ee67131 | note | Records - Sketch / Photo's
| checkpoint | 5 - Material Compliance Bitumen
c9a66b8a-d178-553d-849a-25b7a8343078 | note | ACTION (Hold, Monitor, Witness) - H
1a8ab85d-3bce-5c6e-8a9a-95e6661cd011 | note | Detail - 1st or 2nd Coat Chip seal - Bitumen (Design dependent on season)
dd40fb1d-9186-56b5-81e7-892fd8d7183c | note | Frequency - 1 test per bulk shipment or grade
89719395-371d-5593-8163-ef175129a7da | note | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab Testing
80251b1e-2a0f-544f-9f0c-54b82abd6830 | note | Conformance Criteria - NZTA M01:2020
c1c4766a-58fb-5eb5-85ed-8966e3984627 | note | Records - Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance Sealing Chip
feeed439-0b53-5586-bef6-2fdb05c0f66f | note | ACTION (Hold, Monitor, Witness) - H
f52e5415-c1fa-5550-ba36-81b4f67b8cce | note | Detail - Sealing Chip Source Properties as per seal design
a0d3d9ca-79d8-5d89-9765-2b27a455ab04 | note | Frequency - Prior to Delivery
28df58b5-ad94-5c40-9faf-0830623c5d75 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab testing NZTA M/6
724a0e44-4f95-5fea-8879-cf6e6c99d7af | note | Conformance Criteria - NZTA M/6:2019
5028ce68-cacf-5166-9859-d2180dbb0cc3 | note | Records - Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Chip seal - pre-seal Inspection
bc0a46a8-ab25-5061-af1b-f2561ab4b770 | note | ACTION (Hold, Monitor, Witness) - H
517375eb-64c0-523c-92e3-f5cff79554bc | note | Detail - Pre-seal inspection
ee64957c-4b3f-577a-aa00-40669438984f | note | Frequency - Each site
d0bbc522-35fb-5e01-9239-1aa85b7c7aa6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
9b4bd75a-cdfa-5f64-9ae4-3afa624b9e24 | note | Conformance Criteria - Walk over site
27f38d67-a29f-541b-b7f3-f465211a8675 | note | Records - CS-4060 Pre-Seal Checksheet, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Chip seal - bitumen temp
7a84c697-6029-5ab2-9d3d-a05f4c39d194 | note | ACTION (Hold, Monitor, Witness) - W
5dc077d7-f377-5864-b9b4-ab61d7b26221 | note | Detail - Record Bitumen temperature at time of spraying
b6fc4e9d-760d-5c16-9476-86dbf1e19d0b | note | Frequency - Each sprayer load
55015d0a-5b71-5bd8-9cfe-6d25311d2abb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature of load using sprayer calibrated temperature probe.
ecae2803-af46-5c7c-929d-7adad3f7e7dd | note | Conformance Criteria - Temp. appropriate to base emulsion and +/-5 degrees. IANZ calibrated probe
760fac91-7439-5085-8141-0dcb7e01ea52 | note | Records - Subcontractor QA Records
| checkpoint | 9 - Chip seal - bitume app rate
97c48499-a800-5f6b-8080-5b297a09b476 | note | ACTION (Hold, Monitor, Witness) - W
f37c6213-1790-57f8-a6cc-462d5a3659c4 | note | Detail - Bitumen application rate each spray run to be determined on the day dependent on conditions by sealing supervisor
c260bee0-1745-5ee7-b8d0-4821292456f7 | note | Frequency - Each spray run
6db5224c-441d-5ef3-9e3b-5ac12c9d464a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure by calibrated dipstick reading
f408065e-f816-54ad-aa03-0688865e9765 | note | Conformance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
74f8df16-d943-50bf-80ff-8dfe9621b13c | note | Records - Subcontractor QA Records
| checkpoint | 10 - Trafficking/Rolling
ce11ba9b-8332-5334-bb5c-f29734257564 | note | ACTION (Hold, Monitor, Witness) - W
48fb630d-5e86-55b5-9e6f-5b21c78a75f7 | note | Detail - Details of roller type, etc please
45e77a81-016e-5cb2-b5f6-d586d55a0164 | note | Frequency - After completion of sealing, rolling. 24 hour trafficking post rolling
b7b4191a-323a-5032-967c-4953f7507adc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
5373891e-fffb-5b57-b7cc-f3fce6e275a1 | note | Conformance Criteria - Walk over site
1686f1b2-065d-51c9-bffe-63f251b61bff | note | Records - Photo's
| checkpoint | 11 - Post sealing inspection
b3513e3d-4e8a-5e5e-838a-10f20f452fdf | note | ACTION (Hold, Monitor, Witness) - H
1e1a982e-9562-55af-b666-f13a520fb28f | note | Detail - CPS Engineer to carry out inspection and check the bitumen is completely bonded to the sealing chips. (No stripping)
74924378-34aa-5e9d-9d58-1dace024be67 | note | Frequency - At Completion of Chip sealing, for each site
10ee90ca-5230-5913-91eb-16147cfda61b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6ba4b40b-2d84-5f0f-8858-a325dd424cd8 | note | Conformance Criteria - Walk over site
7be59156-b51a-583c-a201-99cd162fcfbb | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Lot Number QA File
a4fe7684-37b7-5cf1-a9a4-5913a368ee07 | note | ACTION (Hold, Monitor, Witness) - W
e2d46813-74c2-5f9c-90c9-f6d9a26b8f45 | note | Detail - Ensure all NCRs are closed and included within QA file, Lab Testing Test Reports to be included in QA File
4d15ec21-4b7a-5bf4-bc9f-1dc5e2ed5c07 | note | Frequency - At completion of Lot
01976745-f850-59c5-80f3-bf4b9ff739cd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1cfe620c-17d1-521b-865e-1ec6fab25884 | note | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
37ed715f-a61d-53e0-90b0-dfa7534863ab | note | Records - Test Reports, Lab Tests
| checkpoint | 13 -
f48bd43b-49ed-5047-834f-76b70d434615 | note | ACTION (Hold, Monitor, Witness) - W
a07f26c2-60d1-5a53-9e6e-ea6fee3ffa12 | note | Detail - A complete set of subcontractors QA to be included in QA file
b8c1f7f9-328b-5fbe-8651-d8d3647a20b5 | note | Frequency - At completion of Lot
68c63f70-6349-5b91-8bec-aea7d5eaebd9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d736d731-131b-579b-8a66-dfb649982bce | note | Conformance Criteria - Check all subcontractor QA records
d56efbb4-c4a6-5b5d-a52e-1f187c7acb45 | note | Records - Subcontractor QA Records
| checklist | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail | itp | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail |  | 8873c421-178e-4696-a70a-6d584cec4636
| section | 1 - Preliminary
| checkpoint | Project Site reps.
d1329917-ab2d-59ff-91e7-ce3c8ad49bb9 | textbox | CPS Eng.
2670618f-526b-5da5-94ae-f3ab577f4289 | textbox | Site Engineer
c04a7f37-6065-55ff-818e-29a520fe4865 | textbox | Quality Eng.
| checkpoint | 1.1 - Alternative Detailed Construction/ Installation Methodology
0556865c-a122-512d-a0ab-56f31b5f415d | note | ACTION (Hold, Monitor, Witness) - H
87caa383-9358-5b9a-a85b-e05c95edf470 | note | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
dea3660a-d95a-5001-9c72-f2b3bb799de9 | note | Frequency - Prior to commencement
9b09f885-6972-580e-b28e-bd4c6a06b6f8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4a8670ca-c8fb-5d80-b517-81dfd7de5c51 | note | Conformance Criteria - Section 5 of the Project Specification
b88c5555-b56e-5eba-baa3-81dfe05fdd63 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Earthworks and Pavement Works
36a595b8-803b-5998-a86d-8f5ebf6a6e75 | note | ACTION (Hold, Monitor, Witness) - H
817ec378-3b06-57c2-b5b9-a750295c2b60 | note | Detail - Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation.
46c27f3c-5156-562c-8abe-b0bdd7a80b8a | note | Frequency - Prior to commencement
4334b27a-17ae-5167-b998-3b8cdb5d39a0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
31a83ee3-c034-54b9-8b52-16747d7e1277 | note | Conformance Criteria - Previous ITP's approved
6e73de46-4268-5d90-abe5-e32d42e6ee1e | note | Records - Previous ITP's
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Material Compliance
| checkpoint | 2.1 - Reinforcement Steel Compliance
67b71111-e73c-5d04-8df3-894d9d637c23 | note | ACTION (Hold, Monitor, Witness) - W
b1d73887-9aa1-5eb6-a2cf-e0130b34262e | note | Detail - All reinforcing steel to comply with AS/NZS 4671 Grade 500E
63f87062-6b37-5c92-a81f-38a140405b1b | note | Frequency - Prior to commencement
b7269fe4-1926-54a7-a1d9-cfdce5fe21b8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
df86bad9-75fc-548e-b544-768c8cb2a451 | note | Conformance Criteria - DH16, DH12, RH12 reinforcing steel delivered and dockets collected
19bbbc36-6d57-5388-a979-2f3c58b046bc | note | Records - Delivery dockets, packing slips, invoices
| checkpoint | 2.2 - Concrete Mix Compliance
c64d16ac-de84-5563-a76b-44938bb61fdd | note | ACTION (Hold, Monitor, Witness) - W
e0c997c9-95e4-52a7-92e9-dcb7d49192c2 | note | Detail - Concrete mix to meet required strength
bf1db101-9820-54ac-9882-d0c64df731a7 | note | Frequency - Three weeks prior to placement of concrete
fd953b46-711d-5c0b-b63a-5c14c88b4c3d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
c0b5885e-61ae-57cd-b36c-8cfb33222347 | note | Conformance Criteria - Minimum concrete compressive strength to be 30 MPa at 28 days
154fa6e0-1027-56c4-9a7a-9c2c6f874718 | note | Records - Mix design, delivery dockets
| checkpoint | 2.3 - Geogrid Compliance
1f9a9807-72e0-5d38-910c-e3f957473776 | note | ACTION (Hold, Monitor, Witness) - W
a80489bd-7df2-52cf-b710-daf00b71be35 | note | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
153b607c-87c2-5e2d-bfd7-047a9d825fc4 | note | Frequency - Prior to commencement
c7fdf94d-664c-5d95-8e9f-6f5e4db8f8f1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1bb75949-941a-59b3-b860-ce5f289d56cd | note | Conformance Criteria - Compliant with Tensar Triax TX160 or equivalent
97fadf55-4ddc-5b35-a13e-9432ac59e1c8 | note | Records - Delivery dockets, packing slips, invoices
| checkpoint | 2.4 - Safety Barrier Compliance
9be1937f-b06d-5492-8526-16250101bda7 | note | ACTION (Hold, Monitor, Witness) - H
54ec98e2-8f46-5b51-b19f-d45e18f59f8d | note | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
13e76bbf-9684-5541-95d7-7cf0b9951f89 | note | Frequency - Prior to commencement
e31e7012-4b6b-598c-9f91-03a08d55d258 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
393e36b0-0d58-536e-8211-d09130df4b6d | note | Conformance Criteria - Section 5 of the Project Specification
3101145c-8d44-5d3a-bb97-a8f5224126be | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Ground Beam Construction
| checkpoint | 3.2 - Install Reinforcement Steel
87797773-7e11-5d6d-b132-a25a9468018b | note | ACTION (Hold, Monitor, Witness) - H
e96b45dc-256d-579b-939c-929a2cd77ba6 | note | Detail - Reinforcing steel to have minimum 50mm cover
8f1a7f4d-cff1-5c6d-bae8-7d275c7711d2 | note | Frequency - During construction
6dc782f0-1569-5072-96b9-7c39d5b170bf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
977163e1-197b-5fb7-a0d3-2c728e454b0a | note | Conformance Criteria - Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer
b9c461c6-277e-5fb9-9dcb-94060e5ece0f | note | Records - CS-4040 Concrete Inspection Record, Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Pouring
9d7363ac-7404-5b0e-99a6-ab253471b2a4 | note | ACTION (Hold, Monitor, Witness) - H
b9509732-9e15-5873-a157-481ab183f200 | note | Detail - Cast-in bracket as per NZTA B5
fb6a2a4f-a308-5fe4-a229-8d8414387aa2 | note | Frequency - During construction
ed42170e-b7dd-509c-b508-6162502e420c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
75df6793-2a86-5b9c-9add-b4468aa9c28b | note | Conformance Criteria - As per design, Concrete dispatch dockets
0f6501d1-ba97-554c-ab3e-4268bce85c76 | note | Records - CS-4040. Concrete Inspection Record, Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Concrete Testing
d477f10f-d033-5536-9af9-b0cf4ec2bbd9 | note | ACTION (Hold, Monitor, Witness) - H
e7f6f563-d05b-531d-ab25-810d922c2537 | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores. Concrete slump and spread test reports.
1ffb37c6-b41f-5587-8537-cbb28eee41cf | note | Frequency - After Construction
e73ced51-e40d-5de2-b1a7-7db264938cf0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
ee857aac-f524-5ec2-bbff-b63fb6ead987 | note | Conformance Criteria -
89ff1823-35a4-5519-878a-fa185dce591d | note | Records - Test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Geogrid
b973aeb9-682e-5b10-80d6-d407ed1f2d1e | note | ACTION (Hold, Monitor, Witness) - W
442103e1-5e57-52f9-a72b-38d40409b693 | note | Detail - 1.9m wide strip laid evenly across beam and adjacent ground
8e9bb300-c345-5425-b162-fb052f5a48a2 | note | Frequency - During construction
88d5c86d-d55b-5566-9a0e-8b759f4ca267 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
51a66eab-3c4d-5d95-b2d9-0b6c853effb3 | note | Conformance Criteria - Geogrid at minimum 65mm above top of ground beam
6adc35ec-0d4f-5ba3-be6a-23a6d27fa786 | note | Records - Photos
| section | 4 - Barrier Construction
| checkpoint | 4.1 - Guardrail Installation
e10197ea-2b06-5095-add8-bc85ebc7e63b | note | ACTION (Hold, Monitor, Witness) - W
df60fd46-10d7-532c-954d-5b7e282640cc | note | Detail - Install guardrail as per contractors methodology
a59a5396-88fd-54d9-9a4f-722566ea7534 | note | Frequency - During installation
b340d40d-b0a4-5347-aceb-a89ea0e4f583 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
76e28e13-4b50-55b3-ab7e-0d21a5c5ccbe | note | Conformance Criteria - Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor.
b68949ab-c64c-5329-b06c-0c3e290c172d | note | Records - Photos
| checkpoint | 4.2 - RSHDS Inspection
8c8b30d0-a886-5582-872d-f4a78fbd374d | note | ACTION (Hold, Monitor, Witness) - H
2a5bc6c0-4b85-5dd2-a40a-065f230d8d85 | note | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
426e4140-4bc6-58ca-9132-9d6b8857f62d | note | Frequency - At completion of Safety Barrier Installation
d1bd57f0-650e-5072-9342-1640a19cbbd8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
87808cfb-b95f-5c41-9ce1-d7edd6ebfb9b | note | Conformance Criteria -
fcb7aa1d-7bd0-588d-9642-5fa56f1b181d | note | Records - RSHDS Audit Form
| signoff | AUTHORITY HOLDPOINT
| section | 5 - Post-Construction Closeout
| checkpoint | 5.1 - Final Walkover (Snags)
1ec01b00-f506-5d7b-9a46-6e8106b4749a | note | ACTION (Hold, Monitor, Witness) - H
1583b1b1-5afc-5be2-be31-342bb4a25f4c | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
ec9d3ee8-adf0-5cf5-8faf-cc055de75af2 | note | Frequency - At the completion of the Lot of work
acbb8d84-893c-550d-91a1-a5abfdd49e0d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
8925842e-f0cc-5a3d-ad99-54a8a72ca936 | note | Conformance Criteria - Completed report with Snag List
8fce97f2-50d3-5a16-87c7-8fb3a6a7a4d4 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Survey As-builts
805417a1-c248-5d7e-bfe9-1d34d5cc49be | note | ACTION (Hold, Monitor, Witness) - H
5ddefbe6-b388-5a15-b654-c1b6f656b058 | note | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided.
8471dba5-9a59-516c-bfa9-d54f95cdd854 | note | Frequency - At the completion of the Lot of work
6fb89fe4-7c5e-525b-bd73-426306a69dfc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
9d1f7821-674f-563b-8c07-e3ee1d5a9ec9 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
65d9eabe-4f76-58f9-aaee-de534e04fe69 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Quality Assurance Deliverables
cc827e45-5de3-5f90-9358-46b72efc8c99 | note | ACTION (Hold, Monitor, Witness) - W
17a266d8-48f4-51e0-94b9-e67bd0cfa444 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
4f5ad46a-f4e9-5e06-b47a-061baef6ecde | note | Frequency - At the completion of the Lot of work
c0a38b7b-ecd0-5610-961c-a4497f7773f4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1c8a90ad-da53-50d0-b67e-5b0184bccc9a | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
765d1ab1-b61d-51e2-986f-3e412df62c1c | note | Records - As-builts, NCR's and RFI's
| checkpoint | 5.4 - Final Approvals
73a122dd-dfd0-56a2-b641-d4deefe9940f | note | ACTION (Hold, Monitor, Witness) - H
bc858959-1e65-564c-b4d0-786ffe1654d5 | note | Detail - Signoffs by Project Manager, Quality Manager, CPS Manager
dd9ac091-4419-523a-86b3-f21ef6d2c24e | note | Frequency - At the completion of the Lot of work
20128416-f935-56b1-b42f-9a06a929fbff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
14bf7d46-06c0-5fb5-aa55-b7fa86580df5 | note | Conformance Criteria - Ensure all parties have signed and approved ITP
552b9390-306e-5593-ba47-e4082b05059e | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair | itp | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair |  | 603ba293-9bd7-4ac8-9b04-134dbc4a3749
| section | Details
| checkpoint | Project Site reps.
7182dd8a-0886-5d49-ade2-c008734e248b | textbox | CPS Eng.
1dd6ece5-4abc-5d36-b67e-897c724ca1f4 | textbox | Site Engineer
65e9486a-f8f2-55ba-bda7-27c74468d785 | textbox | Quality Eng.
| checkpoint | 1 - Dimensions and Setting Out
ec54b638-347f-5941-a439-649f21a09400 | note | ACTION (Hold, Monitor, Witness) - H
e0e4d00d-be6f-5446-a318-064e7b1ef53d | note | Detail - Dimensions of concrete breakout on bridge deck must be agreed with the CPS Engineer
11282eed-a28a-5690-836d-425cbd0f117c | note | Frequency - Prior to commencement
035aa413-3bb8-5fd0-a9e6-da0ec47833de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7e34a8b1-79fb-5dc9-9225-cb4892fde711 | note | Conformance Criteria - Dimensions at top deck and deck soffit agreed upon
aa8f5481-34d6-5636-927f-728d9bf6bafb | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Materials
600ba5aa-7417-5f43-bd2a-6d71102a16c6 | note | ACTION (Hold, Monitor, Witness) - H
f865baa3-4ae2-5459-908e-7fc59d2aa9bc | note | Detail - Contractor must provide a list of all proposed repair construction materials with any technical data sheets available for each material for CPS Engineer approval.
ebfd6d25-5f51-593a-9ddb-ecb65e7830de | note | Frequency - Prior to commencement
6dc78a3f-465d-5118-964c-785b295cdab0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
04dc720a-9022-5cb8-a66f-611a117143d1 | note | Conformance Criteria - List of all materials and technical data sheets
fd3a4412-cac4-5852-a92a-93561152ba23 | note | Records - Materials list, Data sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Concrete break out
6f3924da-8fe7-5773-b1ab-3636692af6ab | note | ACTION (Hold, Monitor, Witness) - H
591fa236-3137-5362-b635-6ffd9d5e5704 | note | Detail - CPS Engineer to inspect the areas broken out to inspect surface edge preparation
68cc52f1-ac77-541a-af05-11912f7e8d17 | note | Frequency - During construction
c16529f0-2688-567e-a425-7707207c3d5d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a3fddfff-c1d8-5725-82c6-0229b1d5e9c8 | note | Conformance Criteria - 45° taper cut on all 4 edges, no damage to existing reinforcement and shear cleat.
9a0b4c48-d8ec-5c5e-a5e6-afd228348295 | note | Records - Photos, Site visit record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Concrete break out
4d7a0704-d703-5a48-a1ce-9866774012c0 | note | ACTION (Hold, Monitor, Witness) - H
545d954e-6023-5aa3-92a7-ace6ed4e7d57 | note | Detail - Exposed and accessible (top and bottom) reinforcing steel must be power tool cleaned to SSPC SP3 standard. Other areas cleaned to SSPC SP2 standard
9769319a-5b67-5092-9534-e9fa03567e44 | note | Frequency - During construction
a4d05ebd-51bc-5d45-b9e1-18506a4445f2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
60131695-c6c9-5619-ba7a-2ac4f04e502d | note | Conformance Criteria - SSPC SP3 and SP2 standard.
852f38f5-e0ef-5f4a-94c3-e742fb01bf96 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Reinforcing bars
81bcb288-c111-5ea3-8546-30518996686f | note | ACTION (Hold, Monitor, Witness) - M
7c4eaa49-3f42-5160-9391-f2beb404832e | note | Detail - HD10 longitudinal bars to comply to design
1b655471-9ac7-597d-a972-857c9c56d12c | note | Frequency - During construction
1a1812d3-3b0a-5c9d-aac9-cd30ce73ae40 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
ffdfd2c3-c9a4-5d70-8cda-3adae251427d | note | Conformance Criteria - Ensure all new and existing reinforcement bars are coated with a cement-based polymer modified coating material containing silica fume. Ensure all surfaces are fully coated
1e4596f1-fb63-5ea3-acfd-bfd12a004e8f | note | Records - Photos
| checkpoint | 6 - Reinforcing bars
2d01fb72-bd7f-5c00-a6d5-dec4cb0eafc6 | note | ACTION (Hold, Monitor, Witness) - M
c00eb49e-9e6b-5c65-917a-6de50eee923e | note | Detail - Straight bars
3d2c6d9c-4dab-59be-8c8a-7c751559e849 | note | Frequency - During construction
3dbad1a7-959d-5f2e-9d1f-796162ad3111 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3715e333-6b34-5665-ae06-ffb9986a7026 | note | Conformance Criteria - HD10 hooked straight bars, crs 150mm, to form closed loop with hooked bent bar, embedded minimum 150mm, distance between 45° breakout face to be between 20-30mm
f6c425f0-1e39-500a-8ea2-e89ba0bc809a | note | Records - Photos
| checkpoint | 7 - Reinforcing bars
734c4ff9-5b64-5817-8248-7dfbde63644b | note | ACTION (Hold, Monitor, Witness) - M
cfe0e5f6-1ba7-5f35-a7d4-b6432f78cc74 | note | Detail - Bent bars
95900161-f9c9-5f05-8f3b-5c9d56706c1b | note | Frequency - During construction
1bc3735b-497e-5933-89e1-0c78ce25bccd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7002ac85-f0b2-55cd-867f-87b170af30b0 | note | Conformance Criteria - HD10 hooked bent bars, crs 150mm, to form closed loop with hooked straight bar, embedded minimum 150mm with chemset, distance between 45° breakout face to be between 20-30mm
504a71de-1a11-57fd-a1df-ec48d14ff35f | note | Records - Photos
| checkpoint | 8 - Reinforcing bars
e57235a2-c2bd-508d-aaa6-099a4e9021f2 | note | ACTION (Hold, Monitor, Witness) - H
1dc519a1-7944-5102-a079-08d10e430620 | note | Detail - CPS Engineer to inspect placement of reinforcing steel after it is fixed in position
04282662-5410-590c-94b2-3b07a24f23ec | note | Frequency - During construction
7338548b-5e18-571d-b4fe-18861df0d871 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
947482b2-8b4c-5f94-aa10-56358c0ad6a6 | note | Conformance Criteria - Hooked bars tied with 2mm wire as per construction drawings
932ae344-75bd-58de-ab52-980b8ad0b1f0 | note | Records - CS-4040 Concrete Inspection Record & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Concrete casting
185dd50f-9013-5f69-8195-a816a3a7a14c | note | ACTION (Hold, Monitor, Witness) - H
4ba1426c-8c16-5d63-b351-0d2e88f666d5 | note | Detail - CPS Engineer to inspect formwork before casting
d276271c-72e3-5f8f-a37b-495d35fa51f5 | note | Frequency - During Construction
35c5bd93-2a6d-5fd4-83e8-81bd9655ebf7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
50f0aa93-d706-5c90-8446-da0923466578 | note | Conformance Criteria - Forms must have sufficient rigidity and strength to prevent distortion due to pressure from the concrete. Formwork to remain in place until concrete reaches a compressive strength of 30MPa
d500bbed-09e6-540b-846a-4a0150a2e2fb | note | Records - CS-4040 Concrete Inspection Record & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concrete casting
8d367dd6-e203-59cc-a183-6f0823f63535 | note | ACTION (Hold, Monitor, Witness) - H
9ddde7cd-a3a1-5d97-b393-d9471fc42e8a | note | Detail - CPS Pre-pour inspection
62b15874-17c0-509e-83e6-771c574dbe8c | note | Frequency - During construction
822b9a35-04ce-57cd-9dd0-6b28f2d624e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
07b4757c-c269-57bf-be1d-caccddadd6c8 | note | Conformance Criteria - Ensure exposed concrete edges are free from dust and loose particles
c04b654b-419c-53d4-82de-fc99fc074930 | note | Records - Concrete pre-pour checklist, Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Concrete casting
c4947249-e5b8-5c36-a25e-f107369d224c | note | ACTION (Hold, Monitor, Witness) - W
135c2738-eb42-5e2e-9ec2-2ee30d68bf5c | note | Detail - Site Engineer to witness casting of concrete deck repair
83561413-1b3c-5f2c-81a3-4905306cad65 | note | Frequency - During construction
d53a2a5a-3f57-55f6-ba55-62b8bb199eab | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7f79cc53-339f-577f-844f-bbeb4caa6b4c | note | Conformance Criteria - All concrete used in deck repair must be in compliance with T-CES 101. Surface finish in accordance with NZS 3114. Deck top surface - U3. Exposed soffit of deck - F5.
ddd4f9f6-b023-55c1-b0ee-36d5609e2925 | note | Records - Concrete pre-pour checklist, Photos
| checkpoint | 12 - Concrete casting
d23bac96-63e1-59ad-9436-ac0cd796c0c3 | note | ACTION (Hold, Monitor, Witness) - H
df7b0875-eafc-51e6-b769-554b1639f7bd | note | Detail - Contractor to provide minimum of 9 concrete cubes for laboratory material compressive testing
effd5925-a427-5c86-b698-27b60c6dc5b1 | note | Frequency - During construction
b9abe3d0-9632-5c4f-9b73-082bee5e04c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
471f495c-4251-502d-8580-dbee5bc47765 | note | Conformance Criteria - Minimum compressive strength of:
cc989eb6-8fb6-5dd5-8f02-b2f80d488008 | note | ○ 25MPa (1 days)
a40e537f-d7de-53d0-b219-3cc7e270bff6 | note | ○ 50MPa (28 days)
63b2b4f9-c6e6-588c-8e47-f4436a2cda9a | note | – Patchroc C (Fosroc) or equivalent should be used.
e9bf172f-e83c-59cc-b137-e519b418e202 | note | – All concrete supplied shall comply with NZS 3109
28200b1d-c25b-5dc0-a926-ab93e3567ec7 | note | Records -
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Concrete curing
6bfe44f0-1ff9-5e91-a878-37e2bbe1d583 | note | ACTION (Hold, Monitor, Witness) - H
8c26c577-53e0-52d2-b950-753930ddb204 | note | Detail - Curing
94f3c1ad-7733-5a60-8bb4-7ce6fc5ab27c | note | Frequency - During construction
f3be1c6f-1130-5c6e-88e9-4c237f9dfd4b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
d9e43337-24f9-5d3b-a6b1-408fc620dcfc | note | Conformance Criteria - Contractor to provide details of the proposed measures intended to protect the concrete during curing
9063b20d-1c22-541b-9bbc-da9abaa21692 | note | Records - Proposed Methods
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Concrete curing
c1d5c589-5db6-5a28-ba1d-6cc302c7bdb9 | note | ACTION (Hold, Monitor, Witness) - H
1b535b4a-6299-5fe2-92a7-1ef85a90a338 | note | Detail - Prior to resurfacing, CPS Engineer to inspect the newly cast deck repair and make the decision whether crack injection is required
d7ba1673-688b-5e56-ad86-e3873a725ca8 | note | Frequency - During construction
61abc09e-8c07-53ab-91b7-ca05c00dd0b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8e752cd8-28c3-5594-86b4-a0929d3c2cb4 | note | Conformance Criteria - Crack injection required if crack between newly cast concrete and existing deck exceeds 0.3mm. Sealant strip will be applied instead of crack injection
7deeccbc-111b-57e7-a490-19e87492ec99 | note | Records - Photos prior and after sealant
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Reinstate surfacing
bb515f94-9253-5162-8225-e99a8a098df7 | note | ACTION (Hold, Monitor, Witness) - H
8503f52b-1c54-5b2d-b99b-e038f8d09841 | note | Detail - Road surfacing reinstated to be consistent with rest of deck surfacing (Grade 3/5 racked in Chipseal). Contractor to provide methodology for resurfacing
317de8ef-a82f-5f80-b12d-acdede16ec28 | note | Frequency - During construction
d05c2379-dd8f-515e-936e-9c99cb5d2924 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
212b0f10-a071-5689-b790-429693fee310 | note | Records - Methodology, Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - Completion Sign-off
bbcc5ae7-6947-557e-8391-319730a3f83b | note | ACTION (Hold, Monitor, Witness) - H
778f142c-3abd-5f40-96e0-ee4b4e481def | note | Detail - Upon completion of works, Site Engineer to inspect works to confirm it is completed to required standard for sign off
12f41545-6796-50df-bf67-deb956e06efa | note | Frequency - At completion of works
d2cf42d2-d9b0-5c4f-a16e-2b52b6b5e771 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e656ae5e-3db7-549c-a885-de983cb33ca7 | note | Conformance Criteria - Signatures from Site and CPS Engineers
89a28d01-e80b-5a13-8be6-a4784c5f8315 | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - Quality Assurance deliverables
74bbbdc6-5207-5981-aaaa-b0adc8436648 | note | ACTION (Hold, Monitor, Witness) - W
0e8c5f17-6f42-5ad8-9267-75daf32f0f63 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
3b3af966-7c58-594e-b29e-c3ef04adac43 | note | Frequency - At completion of Lot
fdae4f78-191f-5e1c-9902-fc775220d1ae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c468a4e2-ec16-5e20-8d20-4d50192916f0 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
39bed653-72dc-5bbb-b3a0-555451d73f32 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 18 - Completion Sign Off From Fields Below
ab3e990f-12f2-587b-bd8d-5e7ce5b9705c | note | Records - Completion Sign Off From Fields Below
| checklist | ITP - D1603B - ID587B - Otoko Flats Underslip | itp | ITP - D1603B - ID587B - Otoko Flats Underslip |  | f08233bc-12f7-4efc-8321-92d9e17a472f
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
d0a4b0c4-2d59-53d6-b82c-1c3a502cc6e8 | textbox | CPS Eng.
640c2b6a-3389-5421-ba2e-c43315181886 | textbox | Site Engineer
e5591bdd-dbd4-567d-8fec-0c8b4288d644 | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour (D50=600)
07cf68c7-8e9c-5192-8cc9-266b04f1ad3f | note | ACTION (Hold, Monitor, Witness) - H
bb64b39a-9bc1-56eb-a043-fd9c43faac04 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
b38ddd73-2f1e-5cbe-8a63-d9007646b6fd | note | Frequency - Prior to commencement
2e3c6909-4b64-50b8-a1ba-d8311ff1d3eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
629ba05e-6f1e-5e9b-9849-45c77c06fb73 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3.
f7bad2c9-7509-5955-b25b-87ed4e032f4a | note | Records - Material source test results, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
0ead98b4-a138-5c97-a61e-dc24252cfeb1 | note | ACTION (Hold, Monitor, Witness) - H
31708954-544d-5db7-93a7-eb017325ced0 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
c707215a-1a6c-53a7-bb19-fd2d2c8c930a | note | Frequency - Prior to commencement
5c590bd7-dbda-5d0b-bcda-e1cc5d8adbb5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
5c513e90-0c9e-564b-a2b4-c305389d939a | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
3b895cf1-b122-57ec-ac62-c795f1bfd979 | note | ○ Material source testing
48603bf2-c0ff-513f-9601-94d009240ac0 | note | Records - Material source test results, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Class D A39 Geotextile
76be5439-fc7b-5a49-9a5d-6bc042fc5804 | note | ACTION (Hold, Monitor, Witness) - W
58bf3d70-0564-5e1a-939a-0cb0315401e4 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7
aaa64b86-e044-5759-abd1-31b0163df075 | note | Frequency - Prior to commencement
13cfe51a-4956-5a9c-bcaf-e05b7642f03c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
3e820097-2ecc-549d-bf95-eab17434ef38 | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
3a728f12-220d-547a-b160-a0b01e08032e | note | Records - Material certificate(s)
| checkpoint | 1.4 - Class E A49 Geotextile
0ddd966a-8134-53f6-bd78-12b2dc037fae | note | ACTION (Hold, Monitor, Witness) - W
c50c61aa-aef5-5244-a28c-8f84fd2da8cf | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7
e6b644ac-e675-5426-82c4-6c501e031ef0 | note | Frequency - Prior to commencement
2f6e83cc-aa8c-5bfd-9c4b-a9710ef0ca6a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
6a47b1c4-a243-5041-9393-85df3f76e53b | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
11471221-ec42-52cb-8a09-e02c77b4b57e | note | Records - Material certificate(s)
| checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
342c0437-c034-5ca4-9362-85a094706f7d | note | ACTION (Hold, Monitor, Witness) - W
9c3dcdc1-cec6-576b-8c59-107abc05308f | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
a04c400a-e989-514a-aa88-e9e97d5c61ce | note | Frequency - Prior to commencement
51257ea8-4bdb-5a72-9c8e-b028467e3151 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
e2ed87ef-a2da-5303-9b7c-8d6630c4eb6e | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
961373b9-792b-58a6-92ca-61c4ba55aff0 | note | Records - Material certificate(s)
| checkpoint | 1.6 - Top Buttress and surface water drain rock D50=150mm
c008f964-9753-5263-ab25-2343ac995e46 | note | ACTION (Hold, Monitor, Witness) - W
f8a26446-8af4-5604-a8cf-4cce31f307b0 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
9cede806-8546-5248-a764-dc654fadc989 | note | Frequency - Prior to commencement
993825ac-1735-5357-9b7e-90a0e1b4d9ef | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Source test reports
ed9529d6-301d-511b-913f-88ffdc211c9a | note | Conformance Criteria - D50=150mm rock with minimum specific gravity (SG) of2350kg/m3
6cd3e68a-a5f5-5ba3-aef1-85b567074b99 | note | Records - Material source test results, Delivery Dockets
| section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
| checkpoint | 2.1 - Survey Setout
a73e536d-02c3-5f72-8a3d-24a1c7e5abcf | note | ACTION (Hold, Monitor, Witness) - H
5d9e0dff-beed-5418-999d-31cadb400d45 | note | Specification/Drawings Reference - Consistency with Construction Drawing
42106f1d-de1e-5bdc-9458-4a39d0bef5f6 | note | Frequency - Prior to commencement
d1934c9f-7846-5da8-8e1a-812980ff2423 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
f926665d-7019-52cc-82f0-9171146ef564 | note | Conformance Criteria - Set out extents of fill and check against design drawings
0341067f-fef8-568c-8b59-bbc667bd73dd | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
59ad444a-cf31-544f-8bf7-a55128caca6b | note | ACTION (Hold, Monitor, Witness) - W
ee437ed9-4520-5d74-bfc3-e9bac0bc4d1a | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
e54bc3d7-19fb-524b-ae78-5a27a283a14a | note | Frequency - Prior to commencement
c65df24d-7345-5dc7-b4ae-37d78d06f1a3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
7b8acf47-e836-55f2-9c70-5b11ac62f7e5 | note | Conformance Criteria - Remove and clear the vegetation
0fafd3a9-edc5-5582-88c2-ca409684edd2 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Excavation
8699af9e-0797-582a-801c-9a1baca64cf1 | note | ACTION (Hold, Monitor, Witness) - H
ba89d294-9c3d-571b-8339-d376d604d0e2 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
be33e8ff-bc0a-5057-b296-5e1ccaaed6f3 | note | Frequency - During Construction
2949ae17-4f3c-5a6b-81f8-ce4c12db44d3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
99d0e3ef-ac33-5d38-ad47-c71a20e71936 | note | Conformance Criteria - Engineer to assess foundation material suitability
247572b3-bae4-59ee-913c-ca54934132bf | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Subgrade Inspection
b90769ce-9bad-50d8-ad76-b7506d1a42e7 | note | ACTION (Hold, Monitor, Witness) - H
7103cdd3-e2df-54ec-887f-f5a8768b7ae5 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
a9c72c03-104d-5df3-91cb-dfbc709a1b3a | note | Frequency - Per area as required
bb0891b0-74d3-51e0-82ad-327407f7156e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
3fcd46a8-c969-561e-abb2-7bcb055e98f4 | note | Conformance Criteria - Inspect fill foundation.
dc03fa11-a6e6-5691-8f0e-3bc999e52458 | note | ○ Fill foundation must be approved, in writing, before filling commences
4129c859-842b-5a88-a096-05bf0656c79c | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Ground Improvements
c128f040-136c-5adc-97c9-9feb36e63c62 | note | ACTION (Hold, Monitor, Witness) - H
1ceef1f4-037f-56c6-b097-14d83c1adb5e | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
7ce4b197-fec8-52eb-bc5d-30bc7ef9e0ad | note | Frequency - Prior to commencement
d98953fa-1838-5d2c-9671-697d2faf5d73 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d405f476-fbbe-5416-b14f-999d0971d7c9 | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
e33d33bc-6fbb-520f-a5f3-60f5112afe4b | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Class D (A39) Geotextile installation on the excavated face
2a90ff42-0964-57bd-93e1-d8228f64bcd8 | note | ACTION (Hold, Monitor, Witness) - W
31c99359-7046-5f18-9bae-48562c68631e | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
10f1f4c3-3efd-5f7f-b85d-f0f3ddb7822d | note | Frequency - During Construction
8924e778-ecea-58bc-b5d0-a393bd11799b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4bd04732-1567-5ad8-93e0-10508958c798 | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill
db2e6580-a64e-50b7-b70d-585dff1aa0ee | note | Records - Photo's
| checkpoint | 2.7 - Megaflow strip or drainage blanket installation or 110mm Novaflow in 300x300mm trench for seepage if Encountered
388e9175-f4cf-510a-a01c-1820709c4bf3 | note | ACTION (Hold, Monitor, Witness) - H
b3d1d38f-a638-5ef0-af84-a036f26e344d | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
ed505663-86cf-59ae-afc3-4b37be449267 | note | Frequency - During Construction
6f8d936a-5f42-54f9-9e2c-ee659475450f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8c891a36-396b-55b1-8ca0-6f800122cbf0 | note | Conformance Criteria - Engineer to assess suitable drainage location.
b29c5a33-1899-59e7-9fee-0d0b4bbd1840 | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
472e6966-31b9-5b1c-bed3-7ac1dc3a1f5f | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Bulk Fill placement
ecc1f6cd-7dec-53da-9fb6-d309d76db644 | note | ACTION (Hold, Monitor, Witness) - M
3ad16f9b-03a0-58e5-9777-a05e0c1714eb | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZS4431:2022
235c74d9-bd9f-5337-bbd8-41327a6a9949 | note | Frequency - During Construction
167ff4e8-592b-5ebe-ac3c-ca08807a79d7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
06eceeb0-83c4-52ab-890f-bdbc66e13c59 | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
7abd16a8-69db-596f-bdd4-95aaae524efc | note | ○ Fill should be placed on dry subgrade.
664f3078-c8ce-5cd3-abb2-690ae786f2a9 | note | Records - Photo's
| checkpoint | 2.9 - Bulk Fill Compaction
eceff239-be61-59f4-ae39-b886ed8a712d | note | ACTION (Hold, Monitor, Witness) - W
057ffa41-9701-5735-b624-68bd38421f09 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
a64a9020-0c3c-5e70-bad3-dbd4d6f88ef8 | note | Frequency - During Construction
49ade9f1-88a6-5771-a455-8b16e10a6a41 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
6e28ab32-8355-5af3-abc1-f3029bc52514 | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
29e68b04-2b8d-565e-97b1-8120349e6ded | note | ○ Nuclear densometer testing (NDM), by an IANZ accredited laboratory, will be required to confirm the engineered fill has achieved the required level of compaction
81cd3bb9-6c6c-5220-868c-c2695812721a | note | Records - Compaction test reports, Photo's
| checkpoint | 2.10 - Form and cut fill batter as per design 2.5H:1V
e2c85e42-e213-5f74-9520-91676ba8c5c8 | note | ACTION (Hold, Monitor, Witness) - H
a471ffa7-f369-5285-a522-07f12711ccc7 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
d3183490-1108-5175-9e72-0e4bdce1572a | note | Frequency - During Construction
df8dde18-6825-59c9-a5a4-a499742d585e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9dfc6c5c-5d76-5697-9dfd-61b1dbe3654d | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
6094a647-0d16-5e09-bfd2-fd04fbed97d2 | note | ○ Slope angle of buttress is to not exceed 2.5H:1V
f2eecfff-4d45-592f-b65a-41e532fc040b | note | Records - Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Class E (A49) Geotextile placement along the face of fill batter
6dcf9a01-f460-59a8-b252-9f494d01388b | note | ACTION (Hold, Monitor, Witness) - W
9414b357-948b-5227-a05f-dbfc9e24964e | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
affd7acc-e11c-5dc2-818f-dea1267a162b | note | Frequency - During Construction
c010fe47-4c02-5004-b0f0-2936309d5cbe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
92e0caef-4576-524a-a5b1-252050548e33 | note | Conformance Criteria - Class E (A49) geotextile to be placed between the rock armour and bulk fill
fc1ff568-cba2-5fbf-b7af-dedcaf0a347b | note | Records - Photo's
| checkpoint | 2.12 - Rock Armour placement along the face of fill embankment
4a962155-0cfd-5a83-beaf-7895085480cf | note | ACTION (Hold, Monitor, Witness) - W
b950dbc0-b457-573c-8686-086f8f5315c1 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
57bdba66-7bc2-57c0-8e50-6aef56811fd0 | note | Frequency - During Construction
59fc2f18-a662-5814-ac23-91e36a65b351 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
c29a9f09-b701-516f-8280-883420eb2737 | note | Conformance Criteria - 2 x Layers of Rock riprap D50=600mm diameter)
9678b4da-c415-5206-95c2-13a0f138e44b | note | Records - Photo's, Survey As builts
| checkpoint | 2.13 - Rock Armour key into ground
32e43943-bdfc-512d-844c-7dd21d95ace6 | note | ACTION (Hold, Monitor, Witness) - H
946970ba-7b6b-5f61-ab68-3ede9aff20ff | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
025042a9-59c3-5d35-8546-e1faab176bf8 | note | Frequency - During Construction
a4ce3254-afed-55ed-a44a-e1e35c9e6e27 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
5b41b1c8-806f-579f-8efe-e3adc6c433ff | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing.
aeb7660e-be25-5664-973a-b97429a7bc8f | note | Records - CPS COR report and survey as built
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.14 - Buttress Crest
972b1364-7920-54bf-937e-2231c5d281fa | note | ACTION (Hold, Monitor, Witness) - H
d954c1dd-c3e4-5f94-90bc-8d00445b7ae9 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
afef67ba-d73a-56b1-adb0-6280f5c063dc | note | Frequency - During Construction
bc4047cb-3c5b-5d07-916e-df92508c4888 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
f7ee2cac-4e76-5605-882c-0472f44e0f8c | note | Conformance Criteria - The crest of the buttress slope shall extend to a width of 2m beyond the current fence line alignment. The drain and top of the buttress and secondary flow path shall be lined with rock (approx. d50 = 150mm diameter)
a717bcf8-a364-5da2-9150-ac0818271f8d | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.15 - As-built Survey
60711ec1-f055-5df9-8422-240114db505c | note | ACTION (Hold, Monitor, Witness) - H
c255d6c6-77fd-5f55-9172-5df326cc31cb | note | Frequency - At completion of Lot
96331e58-404f-5dcb-bb12-8438b36ce81e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
bf8434ed-3086-5dea-a0c2-17ffa3f2ec3b | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
d1f7da35-8906-5c83-8cfa-1d5097a8fb53 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.16 - Fence installation
a2c751d8-7e67-5f4f-a717-c668877862ba | note | ACTION (Hold, Monitor, Witness) - W
609d0d88-fe7a-5a85-b6ad-c41b237618f9 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
c034d96b-26c6-5139-b7c0-e4f2754ed15a | note | Frequency - During Construction
5070eb9a-84d6-5cae-a555-4d90775e87e8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b3836fa1-f4cb-55f1-a2eb-37352b19e1af | note | Conformance Criteria - Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line
31c92313-2c83-5af5-a4cb-b40ac244e2c7 | note | Records - Photos
| section | Section 3: Final Inspection and Handover
| checkpoint | 3.1 - Quality Assurance deliverables
385d4ac6-ed80-50d1-a2bc-e46a85147969 | note | ACTION (Hold, Monitor, Witness) - W
03614316-af17-55bf-9ac8-c5de922058a1 | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
0647edae-469f-54e0-a827-b9794191d844 | note | Frequency - At completion of Lot
1f1828b1-5e8d-5084-9764-de39f7e94974 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0a278d4b-5c47-52df-a6c0-a4d56323dc57 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
06122f0e-8ece-51f6-afa8-ba167231a91c | note | Records - As-builts, NCR's and RFI's
| checkpoint | 3.2 - Completion Sign Off From Fields Below
5fd8387a-d79d-55ae-b855-4f68619bc226 | note | Records - Signatures
| checklist | ITP - D2004A - ID173 - Tauwhatinui Bridge (BSN4593) | itp | ITP - D2004A - ID173 - Tauwhatinui Bridge (BSN4593) |  | f5bb144c-54bc-4ad1-9c2e-d2c05e70c550
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
b993a132-8c2e-5295-8034-c20fb8737c31 | textbox | CPS Eng.
09f2fa67-a944-5fd5-9376-199708a8254d | textbox | Site Engineer
962e0022-e747-5105-9f47-a1077ed54885 | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour (D50=600)
786c077e-d4da-590e-994c-1e34ad5c0918 | note | ACTION (Hold, Monitor, Witness) - H
ad49f15b-8fb4-59a6-a441-1eeed7f4cb3c | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
df7daefe-4982-5063-ba5e-51cad1103ec9 | note | Frequency - Prior to commencement
01dfbabc-bef0-5469-9a0b-b02046c38541 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Visual inspection
05226156-64c9-56ac-bbb2-cc83b925b3a8 | note | Conformance Criteria - Traceability of material required.
c0cb3714-ea39-5123-aea0-9056d7555d91 | note | ○ Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3.
1a2fb17f-0d34-5699-9e62-7863df6d6bba | note | Records - Material source test results, Delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Bulk Fill (AP65 or approved site won material) or similar
c31881da-7e78-591f-ae65-aae8c1d32f6a | note | ACTION (Hold, Monitor, Witness) - H
af5fa72b-7d52-5ce0-8025-0377f87ec442 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202, Technical specification sheet 1 of 3
cc423387-12bb-501b-9914-a81e2746749b | note | Frequency - Prior to commencement
89b9b059-ca03-5ac1-aabb-54c732f1f793 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Visual inspection
407c84fb-6ffb-5d8f-8136-39eb7cc21d50 | note | Conformance Criteria - Traceability of material required.
90c4f049-e5d1-52fd-a101-ea930f954e38 | note | ○ Should comprise clean granular aggregate and have broken faces.
b6999123-0097-56a5-9e22-3792eaba9b3e | note | ○ Comply with Sampling & testing in accordance with item 2.2.2 Sampling of materials & 2.2.3 Testing Requirements listed in Technical Spec sheet 1 of 3
b07f7cac-829e-589c-9d76-face669c9914 | note | ○ Maximum particle size of 65mm and not more than 5% by mass passing a percentage passing 75 micron sieve dry density water content relationship to NZS 4402 4.1.1 STD Compaction
db5b23a9-3f09-5554-a073-21829724e66a | note | Records - Material source test results, Delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Unaxial Geogrid RE540 or approved equivalent
c98c2a0e-c32d-51bc-b615-4c65e48a35dc | note | ACTION (Hold, Monitor, Witness) - W
614d4439-bce9-5feb-bd40-49bd863de1a3 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3
895c21bc-dc7c-57c5-9322-883423d04c84 | note | Frequency - Prior to commencement
c6e4fabc-0977-52ef-a116-defe7bb9da70 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a8ab80c3-ed22-541e-a965-f29016f93f55 | note | Conformance Criteria - Traceability of material required.
173450c0-1725-5cd9-ae89-8b74566a56c9 | note | ○ All rolls of Geogrid are to be inspected & bar codes collected/photographed. Geogrid to remain in their protective wrappers until required for use. Any defective rolls shall be returned to the supplier immediately
d8bf9936-c743-5b22-8105-ab4f2aa4b7ec | note | Records - Delivery Dockets/ Storage photos, Material compliance cert
| checkpoint | 1.4 - Geotextile Filter Fabric, Filter Class 1, Strength Class C
bec8ca27-c0fb-550e-8e6b-6fb26c63b030 | note | ACTION (Hold, Monitor, Witness) - W
bbd0bb14-12ee-5698-9fb4-368b3ca72bc4 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details, NZTA F/7: 2003
11726ad6-8c0f-5fe3-afad-523f599dd03a | note | Frequency - Prior to commencement
2efe51f9-fe6d-594a-a106-2bc845af9a57 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1477f344-e254-53cc-ac47-da475985c874 | note | Conformance Criteria - Class 1, Strength class C in accordance with NZTA F/7:2003
e983156f-163f-52d9-91c5-31a2b8477bd0 | note | Records - Delivery Dockets, Material compliance cert
| checkpoint | 1.5 - Green Terramesh
3d409cd5-f0c9-57b7-9d39-5f8cae5c4d87 | note | ACTION (Hold, Monitor, Witness) - H
98099b19-9e52-52dd-83b7-4dcdcc5116e9 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
b8719d9b-7de4-52d8-8834-ce580a0d6fed | note | Frequency - Prior to backfill
5b3c6619-4a9b-5a8d-9141-9a65e610d0b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
c4294c38-2d82-5021-897b-22ddf9ac81c6 | note | Conformance Criteria - Terramesh shall be manufactured from steel wire coated with a protective coating of zinc-aluminium alloy and a plastic erosion protective coating. Construction observation reports on cutting and approval
a76986b5-b267-5201-b7c1-d0f7cb225137 | note | Records - Material compliance cert, Delivery dockets, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Megaflow Strip Drain Or Drainage Blanket For Seepage If Encountered
f4f8cf89-3781-50b4-ada9-7b6b113fab82 | note | ACTION (Hold, Monitor, Witness) - W
3f05be75-8b18-5079-9e42-ce803b99af8a | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
c1a7fee6-b300-5014-9ad6-2e4ac2ff6fe0 | note | Frequency - Prior to commencement
2704ff59-d91a-5df7-812e-111da19153ef | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
a1691813-86e7-5a79-a1c4-ca99068366f8 | note | Conformance Criteria - Subsoil drain shall be in accordance with tnz f/2 (geofabrics enkadrain 5006h/2-2s/t110pp or similar). 110mm diameter novaflo subsoil drain, or similar approved.
e60b882f-caef-59fe-b8a1-a1bb014d44fb | note | Records - Material compliance cert, Delivery dockets
| checkpoint | 1.7 - Subsoil Drain Pipe
74e8b824-4135-5e56-9a77-fe717dd9b69c | note | ACTION (Hold, Monitor, Witness) - W
7a0850cd-2bc5-5934-ab9d-b47edf15a246 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3, typical section and details
66ef63be-e94b-5570-8da6-602faaf9df7d | note | Frequency - Prior to commencement
71123442-7881-5863-bac5-4c29a5a84948 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
b92b5911-c118-5a2c-b69d-ed83bfeac144 | note | Conformance Criteria - 110mm Iplex smooth-Bore pre-wrapped Hi-way drain or similar approved
e21b2a2b-34e2-57a9-9808-a4e6e5235023 | note | Records - Material compliance cert, Delivery dockets, Photo's
| checkpoint | 1.8 - Subsoil Drainage Material
291d05dc-e38a-50db-b831-e7be2dea54ce | note | ACTION (Hold, Monitor, Witness) - W
5ad93c24-6cd3-517e-bdfb-c8bfec5555c0 | note | Detail - Ensure Material for Bedding, Side support and backfill are as per NZTA F/5:2013
593414a7-a20f-52d6-b2bf-84b5668acdbc | note | Frequency - Prior to commencement
74ec9a52-3a90-568b-b4f5-83007684631f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
85181bb3-fb10-5aed-804e-150ec47047c2 | note | Conformance Criteria - Traceability of material required. Comply with NZTA F/5:2013. Ensure clean drainage chip.
616b31e8-2126-5e84-9d1c-9a71c31746da | note | Records - Material source test results, Delivery dockets
| section | Section 3: IN PROGRESS INSPECTIONS (Earthworks and Terramesh wall)
| checkpoint | 3.1 - Survey Setout
880e9e2e-1677-5269-b63b-90028d27fa8e | note | ACTION (Hold, Monitor, Witness) - H
0ceb2be2-bbbd-5de8-8060-30aa1baaa59c | note | Detail - Consistency with Construction Drawing
b40c6955-890d-553f-a761-dd87c8732fd5 | note | Frequency - Prior to commencement
c8c4af77-a555-5d77-b0f2-96342c464f81 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
1161c833-338f-5422-b5a4-13c31333e91d | note | Conformance Criteria - Set out extents of fill and check against design drawings
b46bf265-e832-5812-b45a-d2daf1362df5 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Vegetation Clearance And Removal Of Loose Debris
64604e64-b89e-5dd9-839c-2eebaf0d18f4 | note | ACTION (Hold, Monitor, Witness) - M
53decfad-5868-5002-a15b-6cf209ce3942 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
8bddb085-a6be-5ca0-b920-d57e812f57a3 | note | Frequency - Prior to commencement
ade9eee8-08f9-5ab4-99e2-dd6f52276a7d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
28ed5b30-f699-5e91-b784-2c6267f11799 | note | Conformance Criteria - Remove and clear the vegetation
add3fda6-3eb6-58e2-94cd-48cb50b95934 | note | Records - Photos
| checkpoint | 3.3 - Subgrade Excavation
f3b62d18-34d1-588c-994f-14da539271b3 | note | ACTION (Hold, Monitor, Witness) - H
da06bb8d-c0f0-5565-9323-49c0b7b6f30f | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
f61a5428-6309-5c02-a757-c021c951d296 | note | Frequency - During Construction
e87eb8ce-21af-5a61-835c-bab68e5cb30d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, testing
0cac93bb-9847-57b8-af57-d3c15c4cca14 | note | Conformance Criteria - Engineer to assess foundation material suitability
15d2cd11-ff86-587e-931d-3504aca87277 | note | ○ Hold point when excavation is 400mm above proposed level to do scala penetrometer testing to 1.5m below - minimum ultimate bearing pressure of 300 kpa i.e., readings of greater than 3 blows /100 mm
069fe956-a50e-5a17-abff-63f89cc0d436 | note | ○ Hold point when excavation is at level
f21786f5-2666-57a9-b344-b168b3ba7161 | note | Records - CPS COR report, 1M Scala check sheet, Scala test reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Subgrade Inspection
2cd48003-300d-538e-b60f-79731e7e89f5 | note | ACTION (Hold, Monitor, Witness) - H
b6f95a02-ca0a-5a84-9cd4-35f5c81f7bab | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
7e54f28b-b8d4-5819-b584-68a3d8f69017 | note | Frequency - Per area as required
b9893e57-2772-5f6a-8c38-11b68d0e1b3d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
424c0d36-3023-51fa-8875-509474acf190 | note | Conformance Criteria - Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences.
7b117a68-5e87-5e66-9899-f3c584c4eea1 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Megaflow Strip Or Drainage Blanket Installation Or 110Mm Novaflo In 300X300Mm Trench For Seepage If Encountered
49b13c12-f11c-5d8c-9ccf-464cc43cd1e5 | note | ACTION (Hold, Monitor, Witness) - H
9da0a674-a4e7-5c19-8e36-dce75c8a4309 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
00f46be2-3981-5acd-bc89-1bb499bc33f9 | note | Frequency - During Construction
35e7611a-f8b9-5c67-a9f5-b0cf7079328d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f20ac08e-8780-5322-bd28-74c4b8579313 | note | Conformance Criteria - CPS Engineer to assess suitable drainage location(s) and confirm on site. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
ae60d379-7269-50be-917b-64608a16476a | note | Records - Photos, COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Bulk Fill Placement
583359ae-fac9-5453-b1f7-e3776761bafb | note | ACTION (Hold, Monitor, Witness) - W,M
887a15f8-612d-5fcf-a446-6e3ff523bd81 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
de9ea40e-accd-5597-b42c-89bf71a13097 | note | Frequency - During Construction
deb01888-48f5-5a96-96b2-870bf4a77893 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d7dd063d-2ffd-5457-8fd5-fc64908199a4 | note | Conformance Criteria - Granular backfill to be placed in layers of maximum 200mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade.
928306b2-b9a7-5996-952e-c6107c615948 | note | Records - Photos
| checkpoint | 3.7 - Bulk Fill Compaction
18e22c4c-f992-54a3-af6b-eaebd5fe0e1a | note | ACTION (Hold, Monitor, Witness) - W
762c9a2f-26e8-5fa9-a643-d29002a2b361 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
adda284b-b2b1-50a1-b084-0953e5dcd299 | note | Frequency - During Construction
47e814a6-b9a5-5a3f-916a-41cb3d2376e3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
bfe941f3-59aa-50f7-959a-b0c11a75654c | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.1.
41015099-031b-53aa-82aa-636dcf1332d8 | note | ○ 5 x Clegg hammer readings shall be taken for each terramesh unit lift of 0.6m with the addition of 5 x NDM tests evey 1.2m lift (i.e every second terramesh unit)
c3cab5b7-0447-5d02-8d3a-1e3fa3b4c0fe | note | ○ NDM Testing to be carried out by IANZ accredited lab and results witnessed by CPS Engineer as they become available
7bb7446c-8f46-569e-80b7-8a07c1024ead | note | Records - Clegg and NDM test reports, Clegg calibration certificate
| checkpoint | 3.8 - Form And Cut Fill Batter As Per Design 70 And 50Degr.
ee9e9b26-b3c1-5de3-a6a6-f324da05845e | note | ACTION (Hold, Monitor, Witness) - H
b0ef2ab6-81df-5f7b-811b-48883db6e486 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
9d9087f5-56bd-5e97-b67a-687d6cd54d07 | note | Frequency - During Construction
95cc422f-5a73-567d-8621-e73843a8d8b3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
6f287e05-b38a-5c33-8312-7ee760a49972 | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 70 and 50degr. Respectively.
ea64b642-b987-5dd8-ba74-8a1a1dd2a297 | note | Records - Survey as built
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Placement Of Geogrid / Geofabric / Terramesh
7353a0d8-018d-5ec2-9830-e5f2463fc8a0 | note | ACTION (Hold, Monitor, Witness) - H
a7cef716-e0a0-5d5a-926a-0c37e351617a | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
6bd8cf9e-83b0-5d0f-84ab-bbcd4248a517 | note | Frequency - During Construction
872aaca0-62ae-542d-86aa-11a54bc41854 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
b2edd2be-a960-5a6c-8f03-bde2b8aeba72 | note | Conformance Criteria - Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged.
cfc9c8cb-80e2-5863-9825-a2c1799264a5 | note | Records - COR or photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Filling Operation
3ff74e00-b96e-5137-9c72-1723153495ef | note | ACTION (Hold, Monitor, Witness) - M
2ef38b96-f548-544a-bce2-f1803d29a94b | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
edb69fa3-b03e-5019-a609-3209c8d59ce5 | note | Frequency - Daily
f6544185-bdc3-5e68-a74e-762cb5e60a5b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
37cfa254-6b83-5c5c-9b21-9fed2cf9c91d | note | Conformance Criteria - Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced
96c15e50-5853-58dc-be9c-5f5db1bf1178 | note | Records - COR or photos
| checkpoint | 3.11 - Fill Material Placement
7fd277c4-de41-5a50-9057-9680668bd8e9 | note | ACTION (Hold, Monitor, Witness) - H
4ef0c31d-d278-5e6f-a364-aef3ef24e129 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
30796a0c-a390-56d5-9ecb-c8fdcf80db20 | note | Frequency - During Construction
8d339513-a463-5b00-9d54-0cf561d50863 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a13aeb7f-5962-5cc0-bebe-48411821be41 | note | Conformance Criteria - During placing of the initial layers of the facing and geogrid reinforcement, the engineer shall be given the opportunity to inspect the onsite construction methodology.
d26ede5d-1294-5ce4-bb82-1b1174192848 | note | Records - COR or photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.12 - Terramesh And Geogrid Inspection
3ab94700-b98b-5910-babf-d866234ee547 | note | ACTION (Hold, Monitor, Witness) - H
d397d610-6696-5f24-a70c-c67f26154d0d | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
36cafaaf-a262-5889-9df2-250539542001 | note | Frequency - During Construction
fc12e459-cb27-5e99-82b9-772820bebfab | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d367a046-d984-5f87-b518-2d7cbd5a5fb5 | note | Conformance Criteria - Once the installation of the terramesh green and the geogrid reinforcement have been completed, the engineer shall offered the opportunity to inspect the completed works.
85da3cda-f38c-56d1-ba14-18807b511cd5 | note | Records - COR or photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Foundation Rock Riprap Placement
b5e44063-f935-567e-b7aa-0d6453112088 | note | ACTION (Hold, Monitor, Witness) - H
99e11f95-ca9e-5f8c-9f1b-a3f00c4e9ef0 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
f3e4a5a9-e9c9-5519-a040-684db87bf192 | note | Frequency - Daily visual check
a3682e22-78d1-5ebc-a7f7-6c50ea1c8dfe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
3cb068d4-d905-52a8-be7d-6a1a3b00bfbe | note | Conformance Criteria - Ensure that placement of rock material is done in such a manner to minimise segregation and avoid displacement of underlying materials.
3b45c2aa-84ae-51a2-9499-019f462eb859 | note | ○ Oversize rock to be placed such to minimise voids.
3d1f2966-3ff6-5e67-9ea8-f22e01ab2a88 | note | ○ Design Engineer given notice to visually inspect initial placement of riprap material.
de85cfc2-1735-5af3-a495-6a7d562f0b44 | note | ○ Rock riprap foundation thickness 1.20m and 3.70m wide
1ea05dd7-df62-5d13-9cc3-8a4f0c1cdb55 | note | Records - COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.14 - Riprap Key Into Ground
c1cdfacb-6892-5aeb-8e38-f2eac52f6440 | note | ACTION (Hold, Monitor, Witness) - H
20965829-0fc5-5f2f-9b61-bae557667610 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
5e3652f1-a545-5a70-8dd3-0e7a52dfb613 | note | Frequency - During Construction
31bc5e45-bd06-58f3-993f-2a4a9121b3e3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
1ba67256-c2e2-53fe-bf4b-00e908382f6a | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing.
6ab59b61-521c-5840-a8a8-89564681b0e4 | note | Records - COR, Survey as-built
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.15 - Subsoil Drainage
861ec790-b0fe-51d3-b6f0-8e4571b666f9 | note | ACTION (Hold, Monitor, Witness) - M
911aae8b-0738-59ed-8962-5f2efcf80e83 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
0d1308cd-9f03-59ec-a3ac-5edce2834184 | note | Frequency - During Construction
87389ed4-5f7d-58cb-bb78-e0864512a4ea | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
5540a01c-c93e-5906-8f98-bd1b406c3cc0 | note | Conformance Criteria - Shall be installed as per manufacturers specifications & recommendations
cabc965d-08d2-572e-bf0a-c555c621eafe | note | ○ Drainage blanket shall be placed between the compacted fill and the excavated face to terminate at the subsoil pipe. 110mm smooth bore perforated top side subsoil piping and 110mm non-perforated HDPE outlet pipe with minimum pressure rating of 3.2 bar is required.
63398945-2735-5c75-bd68-1288a9e95654 | note | Records - Photos, Survey as-built
| checkpoint | 3.16 - Subsoil Trenching
09e58d30-e0cb-5a2f-b2ca-a29d5062b140 | note | ACTION (Hold, Monitor, Witness) - M
a6ce695e-95d2-5962-a5e9-56d5b736e4e5 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details
0f111f0a-46bf-530c-b610-234edb064916 | note | Frequency - 10m intervals
6a997cd9-ce72-5148-bd44-14e54f2dd4f8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
bd7813ea-f536-58e0-a40c-419b7f2fbb24 | note | Conformance Criteria - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
eb4b072d-aab5-5128-9ebc-db3eb97c0c9f | note | Records - Photos with measurements
| checkpoint | 3.17 - Subsoil Trenching
efc20360-68fb-5e91-900f-a7c92967d192 | note | ACTION (Hold, Monitor, Witness) - M
d196c6f8-977b-5c58-bacc-73e4c703f802 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details
aaaccc7c-8bf1-5369-a52b-1c204de881f8 | note | Frequency - 10m intervals
9e7058de-e71f-51c0-a007-d87df2c48d68 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
4e7ca109-8b91-57e2-bb2d-c6e78fa9bcc7 | note | Conformance Criteria - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
0e82f39d-6301-5fbb-b31f-b25960237c70 | note | Records - Photo / CS-4001 Subsoil Dip sheet Check Sheet
| checkpoint | 3.18 - Subsoil
956dec9a-2e00-5d4d-9100-73972d249f82 | note | ACTION (Hold, Monitor, Witness) - H
ed558e4c-fefe-5d11-83bd-422acdd0e539 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
c852da83-fa4d-5f16-acc2-e4366e2340b4 | note | Frequency - As required
bc88fbfa-2898-5bbc-8d6f-b8c64f816aae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
990b6148-0ac5-516f-9af5-f5de30a5b81f | note | Conformance Criteria - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
900d6d01-5786-57a5-8d89-70731751927e | note | Records - COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Bedding, Pipe Installation And Backfill.
e8346ac5-a210-57bc-876c-90ee5fa0adac | note | ACTION (Hold, Monitor, Witness) - M
f4d706d7-d489-507a-87cb-7d23fc341be5 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
405abaaf-bd58-5cef-a34a-cb693042c8aa | note | Frequency - 10m intervals
ffc9c373-45db-584e-ae69-3b75545dde5d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8ff2d7f5-5142-5c06-9fdc-d0e15842d11c | note | Conformance Criteria - Upon completion of trenching Class C or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
bf1ca02a-70cb-59c9-b3bc-fc41bbe5c3d1 | note | Records - Photo
| checkpoint | 3.20 - Bedding, Pipe Installation And Backfill.
63830962-d91b-5753-9156-e436d761b7df | note | ACTION (Hold, Monitor, Witness) - M
0698575c-dc18-596c-b44d-24e0360dbd61 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
78968be7-2bae-572d-8c2e-bb9025ca114b | note | Frequency - 10m intervals
c42a08b9-5ccf-5778-8d6b-78f04a009952 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - 10m intervals
2c34f94a-13cb-570f-92c6-8e0a2b963694 | note | Conformance Criteria - Comply with NZTA F/5:2013
88dbbd69-7f6f-545b-83d4-26f3b4df99d7 | note | Records - Photo, survey as-built
| checkpoint | 3.21 - Bedding, Pipe Installation And Backfill.
b1a4c6eb-f9aa-5bf0-95d3-f18676cc71f8 | note | ACTION (Hold, Monitor, Witness) - W
4dcfe16d-8a14-527f-9dbc-a44742f60f79 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
5228e9d5-5fe0-50ca-83e4-aee25b198d8b | note | Frequency - 10m intervals
04f2f99a-883e-51fd-b933-9277b2201330 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
4dc5f20a-390f-5f0a-a3cb-869ba85ba89c | note | Conformance Criteria - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
7bc6b002-186a-5be8-949b-7e8f3f8426fd | note | Records - Photos
| checkpoint | 3.22 - Bedding, Pipe Installation And Backfill.
c76f3d4e-b73f-530c-bc05-fa6e1faeebb0 | note | ACTION (Hold, Monitor, Witness) - W
8342cddb-04c3-54df-9139-6ecd7e0f6fc2 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
30bf7f10-f865-5611-b269-e5500eee7b0d | note | Frequency - 10m intervals
00b56c66-80bc-5a02-afdc-051891a620bb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
c246e9b3-f40a-597b-b883-48c51520c8b3 | note | Conformance Criteria - As built Survey the Pipe before backfill
4174ba12-1551-5ad1-969f-0f0bae75f23f | note | Records - As-built receipt
| checkpoint | 3.23 - Construct Terramesh Wall
974100ad-2356-5847-a8a5-2c1fe91b7ad7 | note | ACTION (Hold, Monitor, Witness) - H
f9f6b32f-9f78-5460-89bb-b1bce0259885 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
9fbbc84b-9147-5ac3-bffc-c354b9e8f910 | note | Frequency - As required
389a0df3-08ed-5cee-9723-717836c09f04 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
bddba460-7f74-519d-8f18-fb2da55f5bd3 | note | Conformance Criteria - Install grid layers as per drawings and have Design Engineer signs off each layer.
957b9ca0-e453-5d15-bbae-9c3f7c936199 | note | Records - Survey Receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.24 - Construct Terramesh Wall
38e0c2a0-7f17-539f-bb27-76e3be698f5e | note | ACTION (Hold, Monitor, Witness) - H
cbd8da1d-10d1-5e01-ad3f-f5aa57111890 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
6b714461-1b65-5524-8a12-dd8036b04d60 | note | Frequency - As required
ebab8958-4d04-5c54-9440-a650f112d0d4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
a07c802a-7f2c-5049-945d-c0edbdbaf491 | note | Conformance Criteria - Install Tenax Rivel / Maccaferri Green Terramesh cages as per Manufacturers specs along the front face of layers to ensure correct line and level.
9165f205-36b5-5fcd-89dc-8309e3ec3da6 | note | Records - Photo's and COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.25 - Construct Terramesh Wall
0b8e1269-0575-52ee-9d5f-f62a16d135a7 | note | ACTION (Hold, Monitor, Witness) - M
b9d7cc37-b060-5b5e-82a6-90c3b54580d5 | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
50784016-4e5c-5b66-b9e5-9cfe6313c525 | note | Frequency - Each Lift
84afb209-a865-5f2d-9d04-873562025b09 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
9181a345-568f-5e95-9bb3-bd66d9b9568e | note | Conformance Criteria - Ensure line and level of front face is as per design
118e55df-365b-5f59-a9f5-801cff189504 | note | Records - Photos, Survey as built
| checkpoint | 3.26 - Rock Facing
75913ec7-68e2-541f-89f6-ba1ac8392fde | note | ACTION (Hold, Monitor, Witness) - H
87e08d4e-a5de-5b8a-a8e6-2dbc5f858f34 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
fe6817de-1928-519c-a2f0-ffd7ea7228dc | note | Frequency - During Construction
3ad4f771-e246-54b1-8eb4-84f90d0f9f4b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
8f336803-494c-5119-ab06-f0fd74db8f90 | note | Conformance Criteria - Boulders to be placed in front of the terramesh wall. The extent to be confirmed with the CPS engineer.
3614a115-510c-56a7-93e6-e2b79fa14162 | note | Records - Photos, Survey as built
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Rock Facing
425b9895-4778-5c53-bb3c-77e6aec1ab39 | note | ACTION (Hold, Monitor, Witness) - M
d195ca5a-f5c1-562a-a6f0-a187082baee2 | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
081fab49-4acf-5ddb-8d5d-dc445351bc1b | note | Frequency - During Construction
fb463930-1e4f-55aa-a212-0d0238689990 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
98fd09d3-290f-5614-9414-6b5e50c8aa38 | note | Conformance Criteria - All Rock Shall Be Placed In A Stable Secure Position Utilising Three Point Bearing On The Underlying Rocks. Bearing On Smaller Rocks Which May Be Used For Chinking Voids Will Not Be Accepted.
fc19273b-4958-53a7-8270-a170ad60f7ad | note | ○ Local Surface Irregularities Of The Rip Rap Protection Shall Not Vary From The Planned Slope By More Than 300 Mm Measured At Right Angles To The Slope.
ea9e5575-7127-5c15-a2c7-9114e3ee76ba | note | Records - Photos, Survey as built
| checkpoint | 3.27 - As-Built Survey
32d83b69-2d5c-5253-ab57-11b580c8cb95 | note | ACTION (Hold, Monitor, Witness) - H
dd5fc96f-4398-5022-9cd6-f991144a2c19 | note | Frequency - At completion of Lot
b851404c-ccd1-5249-af6d-7fdfd46b7b5d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
46b4f5ae-42b6-598e-9e43-7e6ed054e8eb | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
e823785c-3355-5b1e-8631-554bd70da03b | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 4: Final Inspection and Handover
| checkpoint | 4.1 - Quality Assurance deliverables
c0ad5ee2-8a04-5c5b-913f-638f28960d04 | note | ACTION (Hold, Monitor, Witness) - W
4615ed41-5d2b-54c3-8537-33ca4c290921 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
835c7171-51ab-59b6-a542-e2cde082b5e0 | note | Frequency - At completion of Lot
59999a2a-4372-513e-bc96-3594d8a22e3f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
8d96ba58-039a-5f57-b5b2-86c18826f99f | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
53312613-c377-545c-b66e-ebf59cf477cd | note | Records - As-builts, NCR's and RFI's
| checkpoint | 4.2 - Completion Sign Off From Fields Below
6c05bc33-ad66-5629-aa68-1a30afb1e06c | note | Records - Signatures
| checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket |  | 4691bc5c-891f-4887-aec2-a2dbd86e25da
| checkpoint | Project Site reps.
88038049-386e-5235-ad1b-16cfd9267b0d | textbox | CPS Eng.
6bf43416-0a02-5aa5-8b89-57c19b956e19 | textbox | Site Engineer
15889b4c-22ce-59a1-b238-8df09be77574 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
5c8049c2-f071-54ab-9108-8575c9cf4172 | note | ACTION (Hold, Monitor, Witness) - W
158b0a3d-d62a-57f3-ae28-c24c58730302 | note | Detail - Set out the base of the Gabion basket
46b8bd94-a1b1-5f23-ad96-4eddd38dd67e | note | Frequency - Prior to commencement
349dd400-1b48-5944-a942-13ef676616a1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
2d2282e0-9422-56b8-8d1d-1d8769d6155a | note | Conformance Criteria - Consistency with Construction Drawing
99536bd5-2113-553a-8d14-be6bd0ef4aa5 | note | Records - Photos
| checkpoint | 2 - Procure Gabion Baskets Materials
fc512c57-614a-5e73-ae26-9ebafc3c9a42 | note | ACTION (Hold, Monitor, Witness) - W
15f8e314-785d-5c97-8d81-c2bce7e0a499 | note | Detail - As per Project Specification
5750a604-a004-5c3f-8971-3463198eeabf | note | Frequency - Procurement
182b68be-2da9-5ab9-b6c2-f95513018b98 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
9642bbc0-9e9c-5df8-9503-c7f5a3c8f296 | note | Conformance Criteria - Zinc aluminium, plastic coating mesh size, selvedge wire Stainless steel rings
30b4a683-cb2d-534e-a8a9-9b01072c0363 | note | Records - Product spec sheet
| checkpoint | 3 - Gabion Baskets
84905685-7d6d-598d-b5e2-d67a842c3de1 | note | ACTION (Hold, Monitor, Witness) - W
136b89fb-bd9f-51bc-a975-b1c3140ce45f | note | Detail - 2.0m x1.0m x1.0m Gabion baskets
b00336e7-160c-5461-901b-2f9bb8968ec8 | note | Frequency - Prior to commencement
c890f85b-f63e-5180-92c0-d73139ffa9e9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
4af74f12-fb4a-54f9-b597-bbea846793d6 | note | Conformance Criteria - Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately
cfd71625-516c-5cc0-a974-bf6ab58dcc35 | note | Records - Delivery Dockets
| checkpoint | 4 - Gabion Rock Material Diameter
71c2601b-fd8b-5794-b51e-0b64cc8dd171 | note | ACTION (Hold, Monitor, Witness) - H
5ce8739c-c5ce-5e78-a891-a7aceaedb549 | note | Detail - Rock Infill shall be 100mm minimum and 250mm maximum particle size based diameter
5bab5ed9-f907-5399-83da-d494fc5bb060 | note | Frequency - All material used
339f5c44-836f-57dc-96a0-5d4f8386429d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
4c39975a-8501-55ad-9a6d-601b97704bfc | note | Conformance Criteria - Compliance with requirements noted on bulk fill checksheet
57b1a05e-f399-55aa-98b7-34be7c6d7999 | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Excavate Base of Wall
6296eea2-015e-557c-9028-50f8a1e54ae6 | note | ACTION (Hold, Monitor, Witness) - H
56b863db-78c9-51ff-83a0-62485b32e0f3 | note | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
a4e62e38-3266-5530-8151-b0caf50f4804 | note | Frequency - As required
b0e1e4dd-311c-5e93-80fc-2113d5570afc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9a03ada4-0569-5ccd-9be1-a784a7b4007a | note | Conformance Criteria - Consistency with Construction Drawing
953ad28b-e67f-5b3b-9442-925f1d0e6213 | note | Records - Survey Receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 -
4a27e0c1-173f-5c77-b8f5-f016bb1ddbb2 | note | ACTION (Hold, Monitor, Witness) - H
f8433124-4fba-575a-bd32-5d40b762a3ee | note | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
2085a4ce-8fc4-5de2-a509-31157df6f7e9 | note | Frequency - After excavation
e27d4ce9-82e1-566e-9ccb-9b8a91ff223f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
51708661-e814-5b76-b8a7-188b506e4b33 | note | Conformance Criteria - Confirmation from the Engineer
379c70a7-b381-561f-a2a3-1dc1de66e290 | note | Records - Site visits, Photos emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
adc9ba18-aa73-5d9f-b0fe-c1723ebba26f | note | ACTION (Hold, Monitor, Witness) - H
beb51646-5392-52b3-935a-3cfc073eb511 | note | Detail - Clegg Test the base of the excavation after placing 250mm AP65.
390c2346-1988-5999-a654-3d360d9c25bf | note | Frequency - Prior to construction of wall
ab1c2c8f-4058-58bb-a0ca-bd372727eef4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
528f72d7-1e93-5656-9f96-3d613f36a8a8 | note | Conformance Criteria - Confirmation from the Engineer
40aadb68-a255-5f1f-8c35-9541d1b19b50 | note | Records - Lab test result
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Subsoil Drainage
231b1c49-c619-5976-b8e0-a0dc8042a5aa | note | ACTION (Hold, Monitor, Witness) - H
e9b2ea33-d19c-5b8f-8a2f-c5b43fd03485 | note | Detail - Subsoil drainage is required for this wall construction then follow the ITP for Subsoil Drainage
6ccaf676-2f40-5c70-8979-b5beacfac806 | note | Frequency - Prior to construction of wall
7a330f9d-24e0-5693-93de-5a66fd6426af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
b46eceec-b4d1-52df-b0c9-6fde0a0003b9 | note | Records - ITP Subsoil Drainage
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Construct Wall
b1849d0f-bd14-5308-a62f-4c2adbee2239 | note | ACTION (Hold, Monitor, Witness) - W
f9ed5fd2-ac68-577e-9e2e-a2d4c71253e5 | note | Detail - Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level.
63f20618-9a4c-5455-8e4b-98e0cb51ffa5 | note | Frequency - As required
df5a02df-016f-5da1-8950-e46f1a2b8786 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
fdb5f37d-90d7-5c50-86ca-5ba344df11a8 | note | Records - Photo's
| checkpoint | 10 -
02cffe05-5f77-5cc7-a189-7e1416d3721c | note | ACTION (Hold, Monitor, Witness) - W
7841951a-f8d3-5ea8-a566-3f95c6338f4b | note | Detail - Tie the first layer of baskets together using Manufacturers specs for tying baskets
4c96a861-2409-59fc-8dfa-4db69d630274 | note | Frequency - As required
20a32742-3ebd-5245-9d0f-41c7e20f26ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
df5c5bce-ceb1-5bc9-8b13-5511730fee43 | note | Records - Photo's
| checkpoint | 11 -
2e49c378-998a-5b42-8993-77963177a921 | note | ACTION (Hold, Monitor, Witness) - W
adcfb548-c0b1-5384-a292-d0cfa5631d0a | note | Detail - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square
c5422e21-26a4-5eca-8678-9dcaa678dfbf | note | Frequency - Every basket
8566bbea-9248-5163-8720-62182e9bac90 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
cc40c03f-4f4b-5a47-b257-64b597953b2a | note | Records - Photo's
| checkpoint | 12 -
589a2719-0f76-5fc8-8ac4-b0c525e42fe3 | note | ACTION (Hold, Monitor, Witness) - W
1046e7d6-3534-5b65-bfcb-5ed6a0d70eb7 | note | Detail - Tip Gabion material slowly into the baskets to fill the voids as much as possible
71a9c15d-ce82-512a-9f1f-8e6110fa756f | note | Frequency - Every basket
1249575f-a386-50ce-9c2c-840c97d72714 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
| checkpoint | 13 -
740353d8-a1e9-5da7-a2a6-c034561dc361 | note | ACTION (Hold, Monitor, Witness) - W
4e94aded-9ff1-5b50-9802-8249043a2e4c | note | Detail - Ensure line and level of front face is as per design
cedcd934-4e27-5fe5-9bd0-0d2171b21a26 | note | Frequency - Each Lift
a7d4fa53-d1de-5884-9c59-d5921a972ac3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
| checkpoint | 14 -
8bb2b955-c0ef-5977-b1e8-4d8cdae686dc | note | ACTION (Hold, Monitor, Witness) - W
2c21d2eb-b356-5975-ac0f-3e83b44c5b6d | note | Detail - Tie next layers of bottom to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again
5900e065-b9e3-5121-8a9d-22f36fcdfbee | note | Frequency - Every basket
5a9f4fec-ab25-5ba4-9838-0a9d3444d589 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
| checkpoint | 15 - As-builts
5a12d48d-92d6-56cd-946c-f89cc86463c1 | note | ACTION (Hold, Monitor, Witness) - H
527768ab-2f84-581b-8ce6-9166770a5d79 | note | Detail - Red pen mark up drawings to be included in QA file
94761c58-872b-50bd-907b-80127912bd97 | note | Frequency - At the completion of the Lot of work
5121cab5-2b3c-568b-be5b-13e7ad97bf71 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
15546a3f-096d-5aa5-af66-c617be8d5709 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers |  | f2a2ecde-fa69-4c4d-ae22-46fb3e016e3f
| checkpoint | Project Site reps.
7e67311a-f7a4-56dc-a430-4880f64d5e55 | textbox | CPS Eng.
fe0201d9-2854-5104-b9b0-0558b48943f3 | textbox | Site Engineer
6aa0d848-06d5-5906-aa92-961f16379f1b | textbox | Quality Eng.
| checkpoint | 1 -
fd480884-d911-5456-bb80-b4c9a5d6bbae | note | ACTION (Hold, Monitor, Witness) - H
5fc2b66c-9504-592b-8202-2839548e9a9b | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
305b9e25-517d-5726-83c6-b46b3fb5ffbb | note | Frequency - Prior to commencement
af903e71-99f6-5e0f-9d34-a9f75d57f10f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
938d62ef-dcde-5dcd-81f9-37a43e43c87c | note | Conformance Criteria - National Standard for Traffic Signal
118ad260-5bdd-58c3-9ad1-b1c6e76368fa | note | Records - OFI or NTD/NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
80dfe984-7aad-5251-ad78-09ed4d8e6e00 | note | ACTION (Hold, Monitor, Witness) - H
0fb77631-0e73-5809-9666-6f4f0c0f3e6c | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
b242d87a-5cbb-5563-8839-2c772098fa43 | note | Frequency - Prior to commencement
5089a9a2-488a-559e-bf42-c415298bc264 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
201311ab-a705-5795-b5bf-1517bffbfb9f | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
0edf1ffc-cda0-59eb-8c1a-94964f4c949a | note | Records - Approved Construction Drawing.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance
881f70ad-47c3-506b-8dcd-8f637996a9ad | note | ACTION (Hold, Monitor, Witness) - H
fd3ad304-2ae5-5dce-81c2-03204bc5e63e | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
f07137a9-744b-5fc7-9665-f1b53d8df1d4 | note | Frequency - Prior to commencement
84d69baf-5f87-5121-b551-9b4feef9739a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
54f56f49-6363-54eb-baea-0914a729c071 | note | Conformance Criteria - TNZ M/23:2009
73f1450e-1f93-5421-8803-fd84fbdea634 | note | Records - Manufacturing certificates and delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
620ed9bc-bb12-5026-b516-c89dba658d4f | note | ACTION (Hold, Monitor, Witness) - H
b20ff2a8-e908-5fd0-a044-be42e575e070 | note | Detail - All materials to be sourced from registered suppliers
3fd2cfd0-88de-551f-bfe5-2b3bbd099980 | note | Frequency - Prior to commencement
dc9849ec-806c-5af2-8770-7fa621658f80 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
bedc839f-0031-529c-981c-91d2551d28a0 | note | Conformance Criteria - Registered suppliers
6894c0a7-dc89-501c-b85d-4149e5e4b8f1 | note | Records - Materials register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 -
7e780dfb-055a-50a9-97aa-e938da42a94b | note | ACTION (Hold, Monitor, Witness) - H
05e0ba92-2fea-52d6-baf4-03612a021803 | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
922f6925-941c-5181-a1a3-e0d0a5e614ce | note | Frequency - Prior to commencement
c57123d7-99a5-5a39-9aae-6030cd0c56fe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1f336ca6-0966-505d-ada0-cacae8251b79 | note | Conformance Criteria - Best practice
7fbeb7b7-b52c-5aa3-84d8-c5eaf0409d3f | note | Records - Approved / Signature
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Guardrail Installation
cb5f2e74-1213-5ef4-9f6a-e52f2754d4fc | note | ACTION (Hold, Monitor, Witness) - H
49f8c806-ee18-5e95-aa88-52b34e0cf209 | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
b08eddb3-c307-59e9-9edd-e18c04b8d045 | note | Frequency - On Procurement of installer
16e346d7-f373-5646-bac0-8aa11e83add3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
de40ea62-f0a1-5dc1-86ae-f74888781545 | note | Conformance Criteria - ASHTAS operative and installer course
273fb345-2de7-59cf-a67f-008abeae1e29 | note | Records - Attendance Certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
2186d151-9c42-5db6-ae17-6154f3912a38 | note | ACTION (Hold, Monitor, Witness) - W
b7d0d6b8-25ce-505b-aeca-10ff3d36fba9 | note | Detail - Nu-Guard 31 shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
afce9aae-c89a-5766-baa6-8472cde71ad5 | note | Frequency - During installation and on completion
ea025653-a263-5613-a9c7-6674e06497c4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
09d9d9ba-687f-54ab-af8e-20acca29c691 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
4b09ae37-e6ef-5084-9c42-e8f904dda42f | note | Records - CS-4117 Guardrail Installation Checksheet
| checkpoint | 8 -
65d15aa5-6688-51e3-bfc6-d8be45aadaf4 | note | ACTION (Hold, Monitor, Witness) - W
0d419b3b-c2fe-5405-8699-a2cb0d107c9a | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
8c1b78f6-8e71-54bc-94b7-dd2706f49ae4 | note | Frequency - During installation and on completion
3daaedbf-b5d4-5110-ae3f-81bd5bb7e6dc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
2ff353b9-86aa-52ea-aa86-b0883e077a8b | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
884a50fa-c003-5cd1-bf2d-5356c594ee27 | note | Records - Installation Checklist
| checkpoint | 9 -
a411f0f0-26b4-58b3-8e36-e38953c96d89 | note | ACTION (Hold, Monitor, Witness) - W
a83596ec-2d9b-593e-9354-71b09d9fc5a6 | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
6469b66f-def1-531f-bd76-1118454f736d | note | Frequency - During installation and on completion
2422f282-3fac-5e19-999d-4d8277ebef11 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
1dc493b1-c6c1-5577-8941-270c9f082865 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
| checkpoint | 10 - Fit for purpose Inspection
692ed231-6daf-5432-b987-e403e18a6d23 | note | ACTION (Hold, Monitor, Witness) - H
4adac4aa-3b9d-57a2-b321-df6d5ad9c295 | note | Detail - Barrier to undergo fit for purpose inspection by competent person
301e402a-5b2f-5ba4-ac26-061692e988f0 | note | Frequency - Prior to trafficking,
387cdafe-7344-5f76-a986-362b09e35ea4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
1d35634a-5140-5240-83bc-09f152424411 | note | Conformance Criteria - Pass inspection
b9c9f1c0-116f-5a6e-bbcc-7e8cf40298d6 | note | Records - Confirmation from inspector
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Lot Number QA File
1303552c-89d8-50f1-83fb-ed8d78e92ce6 | note | ACTION (Hold, Monitor, Witness) - W
7e2bbe81-d910-52aa-a934-5e401e32379c | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
b5884c68-96f4-5ca6-bfc2-7e73dd4df044 | note | Frequency - At completion of Lot
67d12a49-1915-5fdf-bb14-a80f6273059a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6867b06c-bd18-5d4d-bcb7-1fcf763134d4 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
0170d500-fbda-5ab3-9b4e-5f71338ddc7d | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 12 - As-builts
395d48e3-5558-56cb-b728-6aa53ffaac45 | note | Detail - Red pen mark up drawings to be included in QA file
a25a7940-1ef0-5e8c-a86e-28569095421e | note | Frequency - At the completion of the Lot of work
908b537d-134b-5486-9a9e-627681caa28f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
d9ae161c-1343-5637-9bc8-401b56aabe67 | note | Records - As-built Drawing
| checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel |  | 78d668af-78db-490b-a9f1-3bcf1df2fffb
| checkpoint | Project Site reps.
64f134d5-b535-5d93-947e-ecd64ce5cb8e | textbox | CPS Eng.
32ee191e-f093-5a74-9d3f-dcda8115363c | textbox | Site Engineer
26928e2b-e061-575d-a6a4-76d7b4b6999b | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
0ab5d813-0e49-5b0a-9121-e82bc7a033d0 | note | ACTION (Hold, Monitor, Witness) - H
b975853d-6446-5408-8155-37d8320bec5b | note | Detail - Set out kerb line and level at 1m offset to EOS
0ab47cdc-b261-5874-a82f-4825f8a4ff7f | note | Frequency - Prior to commencement
00b4238c-b69c-5997-929b-2e6b95414f3c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
80963869-d6c8-5d22-a7f1-61a6cb885a29 | note | Conformance Criteria - Consistency with Construction Drawing
faea7cbb-fa89-56a5-9276-4035f8cfc080 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Material Compliance
a83101e1-5942-5774-a8a4-b4dcbc3a1349 | note | ACTION (Hold, Monitor, Witness) - H
54f00d4a-ca46-5dce-b557-61903f7d6a4e | note | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
251b3a08-f206-558f-8f43-3c621f0c921d | note | Frequency - 1/600m3, minimum of 1 per source (but make three cylinders)
c9868559-725f-515a-ad17-fcdadc26eb9d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
cd28ffa7-2f6d-5a8e-9db3-6707da10d896 | note | Conformance Criteria - 20MPa at 28 days
6357fade-7e9a-58ec-9594-f76bd5870aef | note | Records - Concrete Delivery Dockets and lab test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 -
c6b6b98d-aede-5043-a73d-ce8458cbfa50 | note | ACTION (Hold, Monitor, Witness) - H
4b3ce800-2184-5141-955b-d13bdc6c69e3 | note | Detail - Ensure the slip form moulds match the dimensions of the design kerb
3cd1363a-cb11-5db4-89e5-893360aadfa4 | note | Frequency - Prior to commencement
4919a36c-054e-5670-b9c3-f771c41758b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
80385d36-fcaa-5eb4-a0fa-07e330ecd19e | note | Conformance Criteria - Measurements match the design kerb dimensions
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Kerb Foundation
73659c18-3121-54af-bd33-230c59e94716 | note | ACTION (Hold, Monitor, Witness) - H
46391509-2607-5424-90d2-8bdeb2c0916e | note | Detail - Ensure Sub base construction is completed
9630daba-6a5e-5d80-88c3-4ecd2328c5ac | note | Frequency - Prior to commencement
8dbe3ece-a044-5c67-841d-256d8db2768d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
2113d818-c4c0-57ad-95e7-aeb2be42e041 | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
8c0b8fd9-3c4c-59fe-8e2c-b56558ce20c0 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Stringing
ae9be5cf-b637-5663-9769-bc7582373d13 | note | ACTION (Hold, Monitor, Witness) - H
18b62a52-2ff4-59e3-a57b-da50bec80763 | note | Detail - Check weather forecast and avoid adverse conditions
eeab87dd-0b14-5873-9778-b5a52200663c | note | Frequency - Prior to commencement
6b836bad-b3e6-59ad-9c34-f50a5be04f40 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
61fa1116-8203-5b37-af23-2466358a01dc | note | Conformance Criteria - No concrete to be placed in adverse weather conditions
5067cecc-12a0-5cbb-b102-9258341700f7 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 -
a3e26f5f-4d49-51b2-aa19-5db08c804f9f | note | ACTION (Hold, Monitor, Witness) - W
ac8a5276-2f12-5986-bfbe-a4a3da6bb833 | note | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
2c68da22-2e9b-5a4b-b126-768cd223b526 | note | Frequency - Prior to commencement
a79c64f5-7f18-5e06-a9ca-5c7d0233d69e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
8259d28a-28ff-5847-b4dd-ae7a48c8f629 | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
a27c6490-05f8-580d-ad3b-0b8a56d6bdf7 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 7 -
f77b2f46-ad03-5586-9e1a-bc52a166b222 | note | ACTION (Hold, Monitor, Witness) - H
05c71122-3c7e-5efd-a6eb-fb7842ee0a8e | note | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
bd8dccbb-dbba-5bc6-819d-c35dc04bce85 | note | Frequency - Prior to commencement
685f3c59-c558-5e0f-b9c5-d606538a2feb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
e50eb134-4305-5e83-90ab-fe24501069a3 | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
7423c794-81c0-52e6-852c-b1de83d92d66 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Slip forming
e6181475-22d5-5a0e-9742-5cc64bd91d1b | note | ACTION (Hold, Monitor, Witness) - H
561eaf32-5e37-505b-8f34-52f7146b91b4 | note | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
dfac2347-5082-5b15-9eaf-0156b8d7672c | note | Frequency - Prior to slip forming
3c4637ea-bb75-5bdf-80d4-70c2a83d5aa8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
1f46fe61-83f7-598b-8377-7d0fbdbe5a86 | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
4d9c34ad-f82f-526c-bff5-8839efb5d832 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 -
e4a5e10e-8c25-5c80-8127-ae7553b12310 | note | ACTION (Hold, Monitor, Witness) - W
944d88a0-2209-5a39-bb54-079a4a4ce8ad | note | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
f91a4db8-77a8-521f-b142-c34b2978b417 | note | Frequency - During Slip forming
85d6f421-4609-5af4-8ffd-c8ce06b23a18 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
80cb0fff-448f-5a20-829d-aa462df56229 | note | Conformance Criteria - To ensure the correct concrete mix is delivered
e7c5deb4-b5a4-53af-8d72-e75d1cdbf190 | note | Records - Concrete Delivery Dockets and lab test results
| checkpoint | 12 -
f6763fc8-7cdd-5242-8d2d-2c57d054bc86 | note | ACTION (Hold, Monitor, Witness) - W
74fdf6c5-1a99-50c8-b4a0-dee39bb3d890 | note | Detail - Expansion joints to be formed at 5m centres
3d81d4b3-59d6-5ee9-a71a-ba2d60da90c0 | note | Frequency - During Slip forming
ca41b970-7c91-598c-ab84-e8153da58e88 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d05e73f9-6edf-5da6-9aeb-c754f0e17271 | note | Conformance Criteria - Kerbing Specification
0f92f39d-492d-54d8-bda2-4b08cd231053 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 13 - Tie-in with pre-cast components
7b3fe8c2-c69e-5a37-ad8b-7af1ebc13b9b | note | ACTION (Hold, Monitor, Witness) - H
fac39dbe-2013-5933-961f-187f53fadfe6 | note | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
33fe506e-732e-578b-b81b-c513aadad00e | note | Frequency - During Slip forming
ab64f61c-f365-51af-b980-ac7c84928ea0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
69a1ad86-1290-50b6-9402-87c1e19ee997 | note | Conformance Criteria - Consistency with Work Instruction
bb21ae84-43bb-5635-b6dd-859e63684ca2 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - Protection
35df2f4b-55dc-510c-867c-4efe80897351 | note | ACTION (Hold, Monitor, Witness) - H
162d8a10-cbe2-5e94-aaf8-2472824caa6d | note | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
61c029f0-c9f8-5e99-af26-e5037c1f0990 | note | Frequency - Prior to backfilling
ece8ace3-763b-55e0-9454-e94df44a8fd6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a19140e7-6a9e-5fd4-b09a-18a57dfe56b8 | note | Conformance Criteria - Backfilling to commence only after 72 hours
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 20 - As-builts
482d3c34-05ab-5857-bce8-eb644d8e2dc3 | note | ACTION (Hold, Monitor, Witness) - H
aa0fdad0-aa00-5e1b-a93d-ecc91d97c595 | note | Detail - Red pen mark up drawings to be included in QA file
6c357053-ee9e-5d51-a71e-5d27cf034f5a | note | Frequency - At the completion of the Lot of work
22429908-f6cc-52a8-9d8f-c03d7f3d0830 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
bb057957-8458-5907-93c9-45b348e79906 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP V2 | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP |  | 0fb9dcb8-e398-4018-a935-65ebe47e4c8d
| section | Master ITP
| checkpoint | Project Site reps.
45a7ccc8-e61d-549f-8435-0bea0ee8046a | textbox | CPS Eng.
a13a82e2-0df4-5be7-bee5-d69fd66c5ed6 | textbox | Engineer
c40e70d9-166d-5e14-825f-753d2c701b14 | textbox | Quality Eng.
| checkpoint | 1 - Debris Clearance
34a13748-e9dd-5aec-8529-a7af52c5958c | note | ACTION (Hold, Monitor, Witness) - H
b0cac6cb-db32-5c11-9c04-1d4d87147de2 | note | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
53d2a460-a098-571a-9018-319a9fe8b356 | note | Frequency - After clearing debris
e17b2271-9c8f-5568-a32d-e0194d7cfb33 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
0065ae33-7499-591b-9ad1-ea14aafadabe | note | Conformance Criteria - Confirmation from the Engineer
f9e9b8ea-3244-5bfe-87aa-4cc9077c4b0f | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Stream and Bank Regrade
3db1529c-5502-53c7-89ca-4b8593b40c74 | note | ACTION (Hold, Monitor, Witness) - H
ceaf7680-c884-5f9d-9712-07fa4ae8da5f | note | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
91f55be9-565b-5e2b-a4cb-71b3b192b7a9 | note | Frequency - After clearing debris
a4b29d48-debf-5806-a3ae-cd555777f84c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
1dd1de15-2bd9-50f4-be1c-6315b95a4f61 | note | Conformance Criteria - Confirmation from the Engineer
e76f5034-3e14-5c26-874e-3568bb414d3f | note | Records - Site visits,Photos emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Stream training
ad3be08b-f60f-5d73-8c25-831576cf9f00 | note | ACTION (Hold, Monitor, Witness) - H
e09c1d36-cdc7-5374-90a7-7a00a6458f68 | note | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
24011bd8-ac24-579e-9f11-299401e9fa11 | note | Frequency - After clearing debris
f00a3093-db58-5a2c-a070-7860fd62523c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
2d278b0b-50e2-5944-aa25-0a20bc4bd2e0 | note | Conformance Criteria - Confirmation from the Engineer
d1e511f1-c589-5627-91bf-42d6aacd3ea1 | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Gabion basket installation
f3306661-b424-5bc0-a9f5-26859b912fc7 | note | ACTION (Hold, Monitor, Witness) -
4322dedb-e00f-5081-b746-53dafa4fba06 | note | Detail - separate ITP provided
8dfeec16-2c05-5cec-ac6c-0cfd8ae47012 | note | Frequency -
8dfc4d70-0f77-51f2-98bd-371de36c2a78 | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
13d545da-5c39-5fbb-b4a1-b24b5cda390f | note | Conformance Criteria -
d51cb77f-eeaa-59d1-886a-5bb1c3a8ce54 | note | Records -
| checkpoint | 5 - Rock Armourt installation
8f9b3a8f-1b95-5744-870d-3d0891788598 | note | ACTION (Hold, Monitor, Witness) -
5cfd2908-c6b3-5c66-9918-9febcddab383 | note | Detail - separate ITP provided
69fcd58f-0aa4-5e51-811c-f0a6217f0c7e | note | Frequency -
8d74b5a5-84e5-5c09-9b8c-2da113568787 | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
e744d34d-b824-5a97-b378-d3c4fe327ff1 | note | Conformance Criteria -
d11308c6-4a15-593d-8278-3a5362c66e05 | note | Records -
| checkpoint | 6 - Subsoil Drain
dbce5a0c-8afb-5ec4-9cc0-9e73b64b20b8 | note | ACTION (Hold, Monitor, Witness) -
f086a508-53c0-569c-a844-1ae6550120cf | note | Detail - separate ITP provided
8d3b951e-3093-50ae-b1b7-9521c4cfe67b | note | Frequency -
834e62f6-8567-5d65-a133-bbb27ae0996c | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
773af2ca-74cc-55d9-aa13-2d19b6927962 | note | Conformance Criteria -
f588f401-3bbe-5d22-8bf6-e3e8ae629b3d | note | Records -
| checkpoint | 7 - Parking bay construction
e9a88361-1958-5b9b-aee2-7da9756c7f6c | note | ACTION (Hold, Monitor, Witness) -
2d48dcce-af3d-5dc0-9ae6-220724e56ccd | note | Detail - separate ITP provided
eae8a39c-8eb7-5bf0-8e2b-209a79231a42 | note | Frequency -
a8010d11-9a07-5945-af4a-3364d70fbcc7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
9c90cd21-674d-5dcf-8509-9e015fe623e8 | note | Conformance Criteria -
1849c986-8d46-5dc4-a8f0-4823de2b47fb | note | Records -
| checkpoint | 8 - Kerb and Channel
c919f4eb-1865-52d7-ac18-c43bac6d60ff | note | ACTION (Hold, Monitor, Witness) -
ab6a7419-90ff-5f08-a0c5-0b4b3b3514da | note | Detail - separate ITP provided
047b0d76-826a-5f88-9c11-31b311ba5df1 | note | Frequency -
f7be5fe0-7516-56d3-9c74-82a7137114c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
f7857ebf-34f6-5f78-989b-71a572f041f6 | note | Conformance Criteria -
f12b247d-fec9-5632-8f80-b0eec7ed40ad | note | Records -
| checkpoint | 9 - GuardRail
491578a8-d276-5757-9b71-f2e08c266ea8 | note | ACTION (Hold, Monitor, Witness) -
b42ff3ce-92f2-516d-8e28-fda0423d2bc0 | note | Detail - separate ITP provided
e6a32fa4-8156-5337-874c-67d2de2fe214 | note | Frequency -
bda2f8d0-0c58-58b2-9a75-d9bc8d8aa459 | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
2f53dc5d-55fc-5e59-a342-d6fac4a4f33c | note | Conformance Criteria -
56199acb-f451-5149-9f19-68d9deb08d6c | note | Records -
| checkpoint | 10 - Swale Inspection
58427056-b1c9-53cc-8252-fc3ac1322b25 | note | ACTION (Hold, Monitor, Witness) - H
2c85c73d-40a6-5b9e-ba14-6fe08f888c5d | note | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
3b969a28-2e3a-5c6f-97df-d8e398f18ae8 | note | Frequency - Once the swale is set out.
96b02e05-c5d5-53ce-a910-376a1f9927b7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
33b542f6-8179-50cb-9b16-9fed5ae2aba1 | note | Conformance Criteria - Engineer acceptance
f6ff9854-0160-54f8-a197-6ecf150c644b | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Berm Demolising
f63ef5a4-4981-551d-93d0-865e678bc212 | note | ACTION (Hold, Monitor, Witness) - H
f9e8d03f-6361-5abc-ab4e-3429c64dff48 | note | Detail - Final inspection to be done before berm demolision
0966a4a2-a3f8-59f5-8e4d-1bd4e4ae869e | note | Frequency - Before Diverting back the River
415febc2-d024-5d0d-b909-56cbffa84e46 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
32582daa-5490-58bd-9430-1379218e8636 | note | Conformance Criteria - Engineer acceptance
10710ceb-3e27-5866-a9b3-f51294bde6bc | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Planting Process
88bddaa5-f0e5-5e1d-b0f9-9670a9ef730f | note | ACTION (Hold, Monitor, Witness) - H
31ae583e-7788-54fd-9eb4-a9cbc5342828 | note | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
4cb43045-4cda-5f40-b09c-d38faadbf05d | note | Frequency - During planting
d78f73a2-b03b-5402-a6a2-74ba5b048caa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f6935acb-2c6b-5075-868d-b82c7a9aefec | note | Conformance Criteria - Engineer acceptance
128af767-6a43-598a-b706-0a814d5d9fbb | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| section | Post-Construction Closeout
| checkpoint | 13 - Final Walkover (Snags)
ac506f7a-c09e-5d42-b8cb-99db25075e56 | note | ACTION (Hold, Monitor, Witness) - H
d55501f9-002f-5288-aac5-736fdde3d96d | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
66451397-1198-5a56-a429-d1b189b62343 | note | Frequency - At the completion of the Lot of work
d30b7d07-baba-512a-a4c3-0d0bc5833df5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
3865c2f9-4239-50a5-8357-9031551568a6 | note | Conformance Criteria - Completed report
f08ad7a9-a41b-53c8-818c-3bd940022a1f | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Survey As-builts
7bacf22e-e052-54ee-86d5-08feb7b1e49f | note | ACTION (Hold, Monitor, Witness) - H
af013ef9-f970-5c7a-9936-9a7455ff8887 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
87f683e1-f808-506c-9291-c002a7f6cd96 | note | ○ A survey as-built of completed work must be provided
7651c91d-6e6a-5ea2-b009-27b7ce3e5ba8 | note | Frequency - At the completion of the CWP of work
ff1bb492-ec96-59f6-a8ba-cfd7f1c96018 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
2f87e3a4-7e5d-5056-a9e8-273f520e431f | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
40f02686-eee3-5af3-9282-c9c31a4e5d90 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Quality Assurance Deliverables
f3894fda-17bb-5aca-b4d8-4d79b9a28722 | note | ACTION (Hold, Monitor, Witness) - W
3eda4559-5a0f-54b4-815a-71c2c89497b4 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
990cc14a-7e38-5fe4-a7cf-d23bde764fa4 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
7c839158-0c67-56cb-ad43-34e431040a77 | note | Frequency - At the completion of the CWP
c3eb1ad8-5c89-5917-a846-72c76eeed2a9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
68eb9c51-618f-53fb-b1d5-cc83fe6a848d | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
57d559f2-69c2-550c-8abf-a265b16543ea | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Parking bay Construction | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Parking bay Construction |  | b91c12cd-11d6-4fc8-b33c-5bcb92aab5bf
| section | Setout
| checkpoint | Project Site reps.
ceb1c1e9-1856-51a6-9b6d-418c1684447a | textbox | CPS Eng.
a60cba7c-2e1e-5d16-a9f4-2a7b95d02c7e | textbox | Site Engineer
ebda585a-0903-5687-a04b-5ba5c83e22bb | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
212763a5-0c5f-5fae-928f-a1e4f35454ac | note | ACTION (Hold, Monitor, Witness) - H
45a57b27-f2d0-5066-a330-e9fdd2d0b902 | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
93273dfb-94cb-53f4-9697-ce374561d75a | note | Frequency - Prior to commencement
09c5fc60-ec88-58be-92ca-47114db252b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
31783811-7f32-5057-933f-4a0cc199dca6 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Proof Roll of subgrade
2ed52153-b982-59e5-a8c3-f31ae8e21ef5 | note | ACTION (Hold, Monitor, Witness) - H
c203fb28-b7fb-58e1-8cb9-13fb0bdc7a2b | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
cfae26cf-75b9-5c15-ba78-771ad1cf15ce | note | Frequency - Prior to Sub Base Construction
60b862ef-62ef-5c5a-8ec8-1392d7ff52ba | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c9ac3c63-ad9b-5ef3-ad2f-a073523112a2 | note | Conformance Criteria - Engineers Acceptance
2348cdbc-1362-5f4f-bd2d-c295b9f8d558 | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| section | Sub base
| checkpoint | 3 - Material Compliance
8087f501-0214-56b3-8b65-8f830a854f3a | note | ACTION (Hold, Monitor, Witness) - H
e5cdd21c-f7de-58f1-a5da-283c3de1bf7b | note | Detail - Aggregate material compliance for Subbase stockpiles
c8b99a80-d15a-5d43-b1d4-64c7c477fd5b | note | Frequency - Prior to commencement
31bfa694-f21d-5648-b460-170733696e58 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
2245adc3-dcdf-51ee-8d08-e3cf9826e82e | note | Conformance Criteria - Crushed AP65 with 30% Crushed face. Lab test for MDD at OWC
28cce37b-42e4-58f6-b682-7875f9e77211 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
e9f8e870-9ddb-5bea-88c7-6a0e12204b81 | note | ACTION (Hold, Monitor, Witness) - H
4a51e39c-24f4-57c8-8700-60c563ea4eb3 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
fb205668-e000-5d78-9397-d9206ac7b78e | note | Frequency - During construction
a4e0a07d-c830-5892-8b80-c32e208ac177 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
7b9aba9c-60c1-5f11-b590-74faa0c726b3 | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site
4bbd5f70-332c-5021-bec1-857a4fbb60d4 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Sub Base Construction
233ca137-22db-5fb8-81f4-669e086721d5 | note | ACTION (Hold, Monitor, Witness) - W
1dc4985d-17e7-5997-b784-91869c3b730a | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
adac4c1d-15a1-59ea-aa33-b3f9fafcd404 | note | Frequency - During construction
8c0b4743-7710-5434-85bc-dad070c906cd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bf6c4ed9-631e-5929-a3ed-979f5b261c55 | note | Records - Photos
| checkpoint | 6 -
9694fe49-bf19-5cbc-b268-7fa3ed010325 | note | ACTION (Hold, Monitor, Witness) - H
6acf8cef-859c-591a-aac2-cd5b4f82cd2c | note | Detail - Carry out a Level Check on the trimmed Basecourse
6f6be30e-49fa-55fb-bc2a-0f232becd24e | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
f1514366-323a-5de0-a0b1-66480376e69e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
b3ef84e5-dc26-57f8-aa4d-cdac88eb48fd | note | Conformance Criteria - Tolerance = -5mm/+15mm
c086a417-7078-58f9-b0bf-744014e95f92 | note | Records - QA measurement Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
d4ef6132-f8ce-50af-a26a-e60a3f98b7ac | note | ACTION (Hold, Monitor, Witness) - H
74d8d24f-a126-51b9-9346-ffeab15498b2 | note | Detail - Degree of Compaction
d2f6d690-19c5-575d-a1db-d7e37fdf58c5 | note | Frequency - 5 per Lot
598df6bc-12ea-5e0b-9290-c5c919920d8a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
fdf0c47b-be49-5e67-aaca-d489f4d2dd75 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
cee8562d-2f3c-58c3-b396-21e74944cfe7 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 -
f5c0a594-3734-5369-adaf-3b0b39e2e224 | note | ACTION (Hold, Monitor, Witness) - H
9ff3ffb0-c117-5265-8f0a-2918f3aaad18 | note | Detail - Surface shape check
aa71dc6c-be3e-5ffe-9611-077d05d8e69f | note | Frequency - Prior to base course Construction
e822b3ac-5eac-5b04-b86a-53d4031b5378 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
17392b6c-ee71-5708-99aa-b6bf45a1babc | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
ce183eab-6664-57e2-8448-92ffd416ee1a | note | Records - QA measurement Sheet
| signoff | AUTHORITY HOLDPOINT
| section | Base Course Construction
| checkpoint | 9 - Material Compliance
e055c6c1-1b3c-5215-b488-a6b3218d0040 | note | ACTION (Hold, Monitor, Witness) - H
6f65e327-c81e-54cd-b090-5c68dad172c5 | note | Detail - Aggregate material compliance for base Course stockpiles
14a38f51-dda3-55e8-bae8-4dd8d5030cc5 | note | Frequency - Prior to commencement
58cad80f-8f29-5abe-af6c-8b6a981f4987 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
a279cfee-b023-510b-acb3-76b50c20cc80 | note | Conformance Criteria - Aggreate shall comply with TNZ M/4
b0e75ff2-7f22-5df3-8ee6-74572ab5550f | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 -
1e2416dc-58c1-55e4-821d-e1e04ca3a27a | note | ACTION (Hold, Monitor, Witness) - H
bec6f2d5-6540-5aa6-ae83-167d92da04bf | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
78b97c41-5ef8-51fc-9a70-bb6a56225203 | note | Frequency - During construction
da1a8f4f-f094-5ae8-b0f4-92c660573281 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
fcfe2d2c-c224-5f5d-8367-25b410c92a55 | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site
1fc76703-e212-5ea0-aab5-381e6ba6f58f | note | Records - Delivery Dockets, Aggregate Deliveries Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Base Course Construction
9eb0f2e5-cbb3-5e19-888d-d2208ae8b0cf | note | ACTION (Hold, Monitor, Witness) - H
8a94034e-7f81-59b5-9bbb-a3d1647056ee | note | Detail - Mat sampling of Basecourse Material
07e68a9a-e8f0-55cc-a2e6-c82692da8320 | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
a953f07f-97d2-5d3d-a9a9-306fbc52b72e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
6c0c080b-4187-5321-be22-f8c0803175ab | note | Conformance Criteria - Grading to comply with specification
84a059f0-a434-5743-aae1-6eea68119956 | note | Records - Mat sample lab test result
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 -
66a4b2d6-ad70-5382-a00c-3fc0cc8c337d | note | ACTION (Hold, Monitor, Witness) - W
9f9668f6-f09f-5cc0-8407-005218022ffb | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
78e1af79-193e-543c-878a-2eab3f4d1d31 | note | Frequency - During construction
70fe6f5a-a66d-592d-8ca9-653d6277605c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8210bdad-d62e-5a93-9983-089f81d8143b | note | Records - Photos
| checkpoint | 9 -
230d28bd-dae7-520c-8737-8e53b0fdc9d3 | note | ACTION (Hold, Monitor, Witness) - H
afa39e0a-828b-5167-95e1-76ee0235bfa8 | note | Detail - Carry out a Level Check on the trimmed Basecourse
f35b1c5c-fda7-51b5-a3d5-5c499b3b181b | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
3d7dfd3e-1803-5216-8828-f05b627dcf3f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
441a1e2e-91a7-53f5-b484-763f322fbbf5 | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
20ac5e2c-f7a9-5dde-9e65-52c5f8c7413a | note | Records - QA measurement Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 -
6152c7b6-57d1-5012-b68d-9c57ee56cbe4 | note | ACTION (Hold, Monitor, Witness) - H
2d124f8f-e608-516f-aa8a-dda751c85ecd | note | Detail - Degree of Compaction
a620f6ed-5677-58c4-9b46-bddbbe852e14 | note | Frequency - 5 per Lot
381aad5f-7daf-511f-b7b1-5d1fe47b9124 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
e8a4d1c0-2ada-5f1f-8d15-2a3dfb7b7f54 | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
2df809c9-1b32-5e87-aeaf-274c68f62345 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 -
608fce49-f222-5850-98ab-8fc1d292c7d8 | note | ACTION (Hold, Monitor, Witness) - H
802c8387-88f9-5a58-98fc-9d69c5c7af91 | note | Detail - Surface shape check
a8bdf62f-1bbc-528a-b437-10c0aaa2c267 | note | Frequency - Prior to sealing
7ba5b0b4-ae70-5c43-ab6f-eb496fb05ba4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
508ac4c9-a92b-5d61-90d4-204bdebb8bdb | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
b2b306a8-3dc1-55bd-8d9b-06af36a65008 | note | Records - QA measurement Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 -
09863528-ec79-57b1-8cad-a8fb2926b26e | note | ACTION (Hold, Monitor, Witness) - H
1e4d11af-dd9c-5b1f-9f19-ffa25f1e8034 | note | Detail - Surface finish check
dbc60e43-9104-5cb4-bbfa-1c3e440f163d | note | Frequency - Prior to sealing
96d52e5f-e26f-53bb-96d8-c402c2108391 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
71030b1a-91d3-504e-838f-de20cf6d37c9 | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
373a8be4-036e-5bed-89f4-89da5862b370 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | Sealing
| checkpoint | 13 - Seal design
ad39c149-3ca6-547b-8400-0717408b539b | note | ACTION (Hold, Monitor, Witness) - H
8115f3f7-6365-5737-9038-317f044d8c35 | note | Detail - Seal design to be reviewed prior to sealing
5ddf09c2-6339-52ae-ad9e-bbc21678c92c | note | Frequency - Prior to Sealing
e9df74b1-a029-5985-88a8-52ba1f59b38d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
432bd01b-34a2-5a27-8f30-aa589bd6caba | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Location/Size Confirmation
b359946d-224f-5d5c-9bd2-0bb7633e073f | note | ACTION (Hold, Monitor, Witness) - W
485661b6-3aff-5fba-8015-8045b180727a | note | Detail - Mark up extent of chipseal
3ee77a7b-11e4-5e4d-9bfb-53ac6175796b | note | Frequency - Prior to Sealing
02280ee2-9674-5f9d-848f-2c6d26490ebd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
6a154bd2-fecd-556a-81be-f0c13d699ad9 | note | Records - Photos
| checkpoint | 15 - Surface Cleanliness
38a8cffa-5c64-5d08-b700-59016737a967 | note | ACTION (Hold, Monitor, Witness) - W
23c48578-b4df-5d1e-bc0b-d1f594228825 | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
26fb3d07-3a30-5eea-b057-f8d169bf839e | note | Frequency - Prior to application of binder
2874f116-084b-510e-b7a3-4048f62cfbae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
2931bdc8-f659-5284-9646-4cd7a68e1da9 | note | Records - Photos
| checkpoint | 16 - Binder Application
636fcd3a-937d-59d8-a051-558dbb1405de | note | ACTION (Hold, Monitor, Witness) - W
27330b5e-79e9-585f-bd89-e4896001851e | note | Detail - Ensure the Binder application is according to the seal design
4c71d3d6-079d-546e-a1a3-af957bb51db1 | note | Frequency - During sealing
f74e14e4-9b62-5dd8-9a27-e6acd9686249 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
02dff363-c013-5cbf-9424-95a68c60387d | note | Conformance Criteria - According to seal design
071019b2-1840-5752-826c-d83983d4b9bd | note | Records - Sealing sheet
| checkpoint | 17 - Chip Application
6060fbc4-701c-501d-bab4-4836d52e3590 | note | ACTION (Hold, Monitor, Witness) - W
6e323dd8-4bd9-5470-be25-bd7a92c3b354 | note | Detail - Ensure the Chip application is according to the seal design
866675df-e7d4-5d95-8d32-36f0db1fc2d8 | note | Frequency - During sealing
9a043b31-a570-5900-9e62-b524acb6246d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
6e5a5804-1f2b-52d8-b130-9bb94704792e | note | Conformance Criteria - According to seal design
7ee75279-30f8-55e9-a60f-26b455ea13ed | note | Records - Sealing sheet
| checkpoint | 18 - Compaction
102000db-2e2a-590e-8d0a-ae4e02373726 | note | ACTION (Hold, Monitor, Witness) - W
7563fff2-3234-5d59-a25a-8f42892a4b5b | note | Detail - At completion of rolling
32f85830-575d-5432-9211-a5ed90b0e0a0 | note | Frequency - During sealing
eb6de82e-acdd-5ee4-812e-a0d6bc9dcad5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
0e15bc6d-2713-58d3-b8be-192da04592b8 | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
30e11b46-8e94-5d6b-89fc-7012f66b922b | note | Records - Photos,QA measurement Sheet
| checkpoint | 19 -
7da55e0f-30c5-55e0-80af-dee71565413a | note | ACTION (Hold, Monitor, Witness) - W
2e9a508f-e39b-5641-b4a0-c91f55514f5e | note | Detail - Removal of excess chip
a85f0e80-df11-586a-a8a4-d51bb5a7f920 | note | Frequency - Within 48 Hours of Sealing
9687a92b-a03a-5998-887c-03550625dc70 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
cd8c7c76-9775-53f1-9aa8-0b34340cc4bd | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
79ce4688-a624-52cd-a066-0994e25b19dc | note | Records - Photos, Site logs
| checkpoint | 20 -
1d512069-6da0-5eae-a91d-6328352f312e | note | ACTION (Hold, Monitor, Witness) - H
69819213-f331-5c17-9007-e5a2ae7cf179 | note | Detail - Surface finish check
455df514-f7ab-5405-94a5-174486db4165 | note | Frequency - After sealing
a26ae8cf-1dd7-591f-b9ed-5540123d0a2a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
84602eb7-57ac-5daf-9eb3-e2dc7f9eafb1 | note | Conformance Criteria - Engineers Acceptance
d7b2acfc-4ce5-5cf6-9a5d-5eaf901d091a | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 21 - As-builts
a203f543-ae86-5b9d-a67f-29c48cffab8e | note | ACTION (Hold, Monitor, Witness) - H
3fe5c3c8-b236-5617-a7e8-41b8c3f23992 | note | Detail - Red pen mark up drawings to be included in QA file
b0f60817-c727-596f-8d35-932c18c0f281 | note | Frequency - At the completion of the Lot of work
f5cadd40-8ded-550c-9155-34744cb09d25 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
0bd74447-db38-5c1a-9265-07beea54a51d | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Rock Armouring | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Rock Armouring |  | 7a9b9391-1d71-4fe3-b275-b40102e12acb
| checkpoint | Project Site reps.
b5a74fad-d0c9-5d5f-a435-8cf37bdcdba8 | textbox | CPS Eng.
35c3d663-a8c7-5999-99d1-333757bead77 | textbox | Site Engineer
d15a9e6c-ba17-5bd0-85b2-215e826f0fd5 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
92bcf7c7-280c-58f7-abcc-e74e735216f5 | note | ACTION (Hold, Monitor, Witness) - H
3c71d814-473d-597a-801f-00b14d7f39ec | note | Detail - Set out extents and check against design drawings
07bf40fe-54e2-5558-805c-258210a71367 | note | Frequency - Prior to commencement
57e36359-792b-558f-94f8-b6407b69cdaa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
c9aa3d75-fe7a-58c3-9fef-3800c4d3f7aa | note | Conformance Criteria - Consistency with Construction Drawing -
6f7209fe-7bb1-5da9-95d3-cc4791796810 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 -
92d0d6b2-71ce-5a3a-b671-8474fa27dc75 | note | ACTION (Hold, Monitor, Witness) - H (CPS)
feb535b8-0e6b-5055-9a8f-60c69494e571 | note | Detail - Engineer to confirm the extend with site conditions - Drawings C03, C04, C10
66a61b74-6925-5524-8866-88c130d6f04f | note | Frequency - Prior to commencement
25659552-2e67-513f-b74a-9ee51b7e3f28 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
1dc6a94e-1f55-5c95-b22e-7e325c166626 | note | Conformance Criteria - Engineers Acceptance
c8f144d6-a601-55db-8024-298f6ed5b5de | note | Records - Raise RFI on Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 -
2bd17ebe-7841-5f6a-8b4a-f2e1769b3d87 | note | ACTION (Hold, Monitor, Witness) - H (CPS)
d5a25bf5-36b3-5325-9013-ae58082bc89b | note | Detail - Inspect fill foundation
7298dbf9-bcbb-5f23-b38e-d95ddb5f37b0 | note | Frequency - Per area as required
467acd06-0846-58ab-b03c-f2ee38c39a5c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
88d63909-6ea6-5de3-b854-bfd2db731eeb | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
2ac273f4-9fec-5d3b-be17-36e51d3ee02a | note | Records - CS-4100 Subgrade Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance Testing
2d68bbf8-b06e-5090-b92d-f776156f0baf | note | ACTION (Hold, Monitor, Witness) - H
0e82d01d-f9ea-5195-9dc5-449414e241b7 | note | Detail - Material to meet specifications dependant (D50 of 125mm Class 1)
67fee3b8-6a1e-5634-965a-8dc53f7dcae5 | note | Frequency - Each material used
735d1edb-b73c-53ce-8f30-9b11123ba5e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 -
a798f406-274e-5327-a57d-f6ced0af4195 | note | ACTION (Hold, Monitor, Witness) - H
4bc9b03e-19cc-5fcf-b1f0-6d4edd672acb | note | Detail - Rock Construction Material
e158cd68-3a50-521d-a116-188e0b1e8d09 | note | Frequency - 1 test per Lot
121614f0-4442-5021-94ea-a97fc9f2772e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
d4443e08-6926-5f4d-aa88-e44d6c769968 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
fc578f3d-dbf5-53ad-b1dd-1fabcaa6efff | note | ACTION (Hold, Monitor, Witness) - H
4c33d978-6a3d-516f-9c8f-64e5684c3321 | note | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49
b48fa8ed-ea56-5755-aebc-1366fa55dfcb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
eae4312c-44d7-586d-b822-3d50c9f41b50 | note | Conformance Criteria - Conformance with Specification
a77180be-be15-58ec-abd2-17dcc7a72d3f | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Construction of Engineered Fill Embankment
01c25a28-1a48-5a76-a367-511672fbe6dd | note | ACTION (Hold, Monitor, Witness) - H (CPS)
955b60ba-c6c8-58c1-9be6-d6f2e48843fb | note | Detail - Location of bank regrading to be agreed with CPS Engineer - Drawing C10 item 3.2
fc027830-f2f6-5ba1-9c5a-b0baed5efb07 | note | Frequency - Prior to commencement
634ace84-30b7-5fa5-9450-ab27be907faf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f18d8949-8463-5419-951c-8c821bc5b586 | note | Conformance Criteria - Engineers Acceptance
99727bd0-5816-5f8b-b146-866ba106c28c | note | Records - Raise RFI on Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | -
d8f76015-8891-5bac-9b23-94159979de30 | note | ACTION (Hold, Monitor, Witness) - W
d08e1e22-d958-5405-984f-e8e64f437e44 | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
201ba140-3997-59a7-8d87-62bb463f9758 | note | Frequency - Prior to commencement
adbf0d80-3398-5de0-8700-9b2a776604cc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
77322fdf-cc5b-5615-beff-5e28a49fce66 | note | Conformance Criteria - Intake Earthworks ITP completed
| checkpoint | 9 - Geotextile Placement
0ad2a99d-1591-51f5-84cb-709cd9807110 | note | ACTION (Hold, Monitor, Witness) - W
26624183-e3c7-54b9-b81e-793f0b1389dd | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
897be73a-bc30-5927-806c-f538e04258b3 | note | Frequency - Daily visual check
b3d5c525-2d40-59df-b384-5c492542ceb1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ac22f77a-3d8d-535f-b9c9-dd7b5e145b09 | note | Records - Photo's
| checkpoint | 10 - Riprap Placement
1b86cd7a-e361-5e1b-8f61-c1413c56410b | note | ACTION (Hold, Monitor, Witness) - W (CPS)
213566b9-e237-5efa-b5b7-6d5da23ed82e | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
779a5472-f683-51c6-b50e-6a9c6115d359 | note | Frequency - Daily visual check
a4b6ad98-f276-53f0-9d8a-c4bb1b4eafa6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
379535f9-8154-5f8f-880a-8cf81e526812 | note | Conformance Criteria - Specification
d746f4c3-6916-5564-9a83-d30ba799c411 | note | Records - Photo's
| checkpoint | 13 - Survey As Built
0b2c5689-a8eb-57aa-8069-364ca4690be8 | note | ACTION (Hold, Monitor, Witness) - H
ec68d94c-1aef-5994-b16f-bf39891c95a6 | note | Detail - Ensure rock slopes comply with design prior to next process taking place
e0d261c4-5c86-551e-ac70-468be99517c8 | note | Frequency - At completion of Lot
bb1f359e-49f3-55f4-8299-10f0e3ed98b7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
170b55ed-c69b-5bd6-b7a9-853534f25a4b | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Lot Number QA File
d0290628-a0cf-5632-a891-360bd2a07180 | note | ACTION (Hold, Monitor, Witness) - W
7130a4b3-92a7-5721-a5b4-1f5aebb45ce8 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
3680421b-e26e-531a-a038-856e8f034ccd | note | Frequency - At completion of Lot
a7d9cdde-b66e-5065-bacb-662cfbd714be | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a9034e78-77df-5eae-980a-6ea86d3fd91e | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
54e7283e-ba15-5f40-9e80-9f1bbe22f755 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 15 - As-builts
45a13bd6-8218-5289-a252-207e23eb7b73 | note | ACTION (Hold, Monitor, Witness) - H
ad2ad162-dce7-50b0-bfec-b4c3df130a72 | note | Detail - Red pen mark up drawings to be included in QA file
49b0f0f9-3ca9-5a8e-a162-17523468880d | note | Frequency - At the completion of the Lot of work
0eddf604-32b3-5722-9377-3f097b507b0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
99f844a3-9ff4-5dc0-9ae8-37d050e6d2e2 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - Quality Assurance deliverables
6e3f782a-c4c2-548d-833a-4467c08b0a48 | note | ACTION (Hold, Monitor, Witness) - W
a7f40ca9-c724-5368-adb5-e157f74548f9 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
fe1611a8-26bf-5cb1-afe2-8c9a50da76f1 | note | Frequency - At completion of Lot
9523d355-656d-5fea-94be-9fbc2855641c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
bafefe6f-6622-5c0c-9e41-512c181157da | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
bf05fe0b-2528-533a-9117-ee40d616326e | note | Records - Asbuilts, NCR's and RFI's
| checkpoint | 18 - Completion Sign Off From Fields Below
9c4cb7da-b88d-5549-97aa-0e2812133b9a | note | Records - Signatures
| checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage |  | 75e8ab36-4838-4cce-a723-1c1edd15ebc7
| checkpoint | Project Site reps.
e2237771-6e5c-5960-a3ea-b80b5570a4a0 | textbox | CPS Eng.
7e54a6b3-f8ad-5c6e-865c-600bb193bd9c | textbox | Site Engineer
55689a6d-df15-5278-ab5e-19db4a45206c | textbox | Quality Eng.
| checkpoint | 1 - Setout
4b4cf16d-4273-5473-85d0-52f4d54f8584 | note | ACTION (Hold, Monitor, Witness) - H
9652d364-67a1-521b-bad7-04857dc17a9e | note | Detail - Engineer to confirm the extend of sub soil drain on site
4d1bbb12-1cd6-57f3-9f0d-bfb00a55cf55 | note | Frequency - Prior to commencement
1306f084-b451-55ef-a955-b51fbd0a1b1b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
b6ccca7d-dda6-5583-b5da-ab77a7f1c461 | note | Conformance Criteria - Engineer acceptance
6aa55eed-5116-55d0-9a23-aaa398186939 | note | Records - Site Visits, Emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Locate existing services by hand digging
34130c19-4624-552b-9e2d-9ce7b8a14e0f | note | ACTION (Hold, Monitor, Witness) - W
dd77fc3b-88d5-5bae-a755-188ad935d6b0 | note | Detail - Ensure all services in conflict with the line of trench are exposed by hand digging
22c69f8a-7bd9-5031-a28c-c7a795f2c7bd | note | Frequency - Prior to Installation
72118617-da5d-5df9-ae95-e97df3d97271 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
ee94eebc-e991-5cd8-a719-44fd5935f8c2 | note | Conformance Criteria - All conflicts have been located
d4c5161a-5bd7-58d6-84ee-c36c3c8f0202 | note | Records - Permit To Dig
| checkpoint | 3 - Material Compliance
9ec8ac48-5a3b-58b6-9e6a-e45e5added50 | note | ACTION (Hold, Monitor, Witness) - H
8f8353cd-5fa2-5169-bb44-dd21d0eabb87 | note | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110 Diameter
2fdae8ca-d188-57fa-bc85-d43cc9bc75a3 | note | Frequency - Upon delivery to site
2dd78fc8-5573-5162-bf40-93a4546da1c1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
29e11b42-ac5f-5343-91b5-db3bc98ce1ce | note | Conformance Criteria - 110mm diameter Drain flow TNZ F/2 Grade pipe
839a1023-39b1-58e5-b994-c5e64f79b721 | note | Records - Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
8cb9190d-9bcc-554e-8694-96c05efdfab5 | note | ACTION (Hold, Monitor, Witness) - H
59e2c3a4-6d15-5369-9b01-4b08aea57c4e | note | Detail - Free draining granular Fill Comply with NZTA F/5 2013
b3fdbb0a-e7e3-5b00-8bc3-bbe19d681ddc | note | Frequency - Upon delivery to site
b0b06983-f822-570a-bc26-c93d074e21bf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
4e2d2487-995c-56e4-b68d-c7f62ff8d9dd | note | Conformance Criteria - Ensure clean drainage chip
121a3349-7f80-5258-aab3-3ac42c45d626 | note | Records - Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 -
02a3cf18-499c-5119-99a4-7a86b545b3e0 | note | ACTION (Hold, Monitor, Witness) - H
2b092d3f-0c2e-5d72-a1f2-bd11ff1c5175 | note | Detail - Ensure the geotextile filter fabric,strenght Class D in Accordance with TNZ F/7 2003
572a137e-fe50-56da-ba2a-ab75c6355d8a | note | Frequency - Upon delivery to site
61a4a971-6176-5fc3-93af-d67496719384 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
4b7cce6e-c74f-50ee-8d90-fa5e9559c089 | note | Conformance Criteria - Strenght Class D in Accordance with TNZ F/7 2003
570cefc8-9e2f-5487-88d3-2f2f60073cb1 | note | Records - Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Trenching
30e93838-c58e-5af6-8bbf-c60bf0e954a5 | note | ACTION (Hold, Monitor, Witness) - H
b791da6a-d94b-5dd3-ac0c-06e197b7f124 | note | Detail - Inspect trench profile
3ed5f2d9-e270-5eec-b4f9-b0a6bc95f726 | note | Frequency - 10m intervals
6859158f-4d6b-5db9-8fbb-d0555c5cbc89 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
78635462-39cf-52c8-920f-456b74ddef36 | note | Conformance Criteria - Record levels of base of trench on dip sheet
fbec8335-9f8e-5320-81b1-3f4f133c8076 | note | Records - Photo & CS-4001 Subsoil Dipsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
8f335392-433f-5d31-88f5-c5f52cb41c15 | note | ACTION (Hold, Monitor, Witness) - H
8661598f-db35-59f8-aaeb-adea1542b119 | note | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
face15c5-e5b8-5ed6-89b8-b97d38593444 | note | Frequency - 10m intervals
cb60aa28-c2d2-5cfa-85de-270461453164 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
be04c72f-43c1-597c-85c7-676fb9bc6857 | note | Conformance Criteria - Ensure trench line and levels match the design drawings
e7c91aa7-0671-5d1b-b410-1745bc30387a | note | Records - Photo & CS-4001 Subsoil Dipsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 -
75941425-7241-53ae-a226-e0cd8552b461 | note | ACTION (Hold, Monitor, Witness) - H
5db267a8-fcec-543d-b55c-1ee57f66f761 | note | Detail - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
59b650aa-ff19-5942-8588-d606e842c3f8 | note | Frequency - As required
977a9265-7f3e-52ed-bd73-66b9e7f4eeff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4b931163-9425-5af9-9936-31a54aec4382 | note | Conformance Criteria - CPS Engineer to instruct action and record on dip sheet and as built drawing
2be598b5-d10f-5e99-9c78-553037b5e7f0 | note | Records - Photo, Emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Bedding, pipe installation and Backfill.
c0134d86-f837-585b-9676-b6bd4ec4c3e9 | note | ACTION (Hold, Monitor, Witness) - H
0452a891-3eaa-5f2b-a644-fde02d83d21a | note | Detail - Upon completion of trenching Geotextile Filter fabricto be placed into the trench. Accordance with with TNZ F/7 :2003
03c35507-deb5-5c2c-b9d8-7a1f77eb3bd9 | note | Frequency - 10m intervals
ac6aa259-b428-5886-bdad-c9a7c8566959 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
03112fa8-9f46-5c2d-a151-5d02fa20ade2 | note | Conformance Criteria - Ensure material covers the trench and is pinned in place
22765af2-8c71-54c3-a8bd-5f57af652f1d | note | Records - Photo & CS-4001 Subsoil Dipsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 -
3ed29aad-e78f-5c8b-badc-74f3f3c6269f | note | ACTION (Hold, Monitor, Witness) - W
b03fe4c0-d49d-55e5-bb0a-4a28536ca2e0 | note | Detail - Ensure 100mm thick Free draining granular Fill bedding is placed in base of trench.
2a865518-c1fd-52f4-a002-5f695a94839f | note | Frequency - 10m intervals
28f8df20-497b-56b3-b195-682541955474 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
953705ee-651c-5caa-8dcd-1d56371d8f83 | note | Conformance Criteria - Record levels of top of bedding on dip sheet
7210e0f7-ef43-5e7a-9a5e-9263c6321129 | note | Records - Photo & CS-4001 Subsoil Dipsheet
| checkpoint | 11 -
232713dd-028b-5437-a15e-0b00e33b1af2 | note | ACTION (Hold, Monitor, Witness) - W
47e37887-ed7c-5d29-828d-6ab6ee7fe7bc | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
20081d8d-00fa-5318-a442-413dd9435dd7 | note | Frequency - 10m intervals
b1bbc584-4614-5634-8b05-9eb36af956f1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d10ed794-e961-511c-8333-e06406d08227 | note | Conformance Criteria - Consistency with Subsoil Details
659258e8-0512-5d35-960c-d06614d1bac3 | note | Records - Photos
| checkpoint | 12 -
5252882c-f91d-554a-9d10-203dc06d51ea | note | ACTION (Hold, Monitor, Witness) - H
42c1f5b0-ab4e-5dcf-bbf2-27d4705b9f62 | note | Detail - As built Survey the Pipe before backfill
55c3d484-e45f-52d4-98fc-64c8879f276b | note | Frequency - 10m intervals
cd0d3da5-7f9d-52c4-82ed-f74aef5b4e1d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
5aa6c5cb-39a4-550a-9991-9ce17c2b291d | note | Conformance Criteria - Consistency with Subsoil Details
c3a1bb98-2f64-5087-9863-08eba49bb418 | note | Records - As-built receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 -
b5aaf815-b0c5-590d-a966-74c9c35b5586 | note | ACTION (Hold, Monitor, Witness) - W
e64a206b-186e-57ba-ae7e-eb725b0a8cc9 | note | Detail - Free draining granular Fill into the trench
fba9fd8c-0e52-50ef-9266-650b0a348e1d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
67c139c2-eedd-52d4-8dfd-83c1f5a04c58 | note | Conformance Criteria - Ensure good coverage
bd0b7524-a677-57ff-a74d-2f9ba281b31d | note | Records - Photos
| checkpoint | 14 -
f693e248-eede-5f1b-a238-03ba49d7f0f0 | note | ACTION (Hold, Monitor, Witness) - W
0624373d-e7b8-5051-ad8c-c8ba82fff4f9 | note | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
35fc3472-78b1-528e-90fb-29ce96122255 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
| checkpoint | 15 - SubSoil Flushing eye
5f346ec4-4126-542b-aaa8-6f68e9c01e32 | note | ACTION (Hold, Monitor, Witness) - W
7a24fc91-b09d-5bfd-be1f-68029364fb79 | note | Detail - Hynds Round 250mmm Lamphole cover and frame or simislar approved
0065a723-d360-5afa-aa7f-96eee2af2e25 | note | Frequency - Upon delivery to site
16a406d4-5c45-5770-b046-ec8209a43c2b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
4b30f687-e514-599f-939b-675b6dab47ea | note | Conformance Criteria - Consistency with Subsoil Details
560fc0db-c2cb-529e-8c1a-178bd46fb62a | note | Records - Delivery docket
| checkpoint | 16 - Final Inspection
563cf71d-2bd2-5ea4-8fd2-8d1151c86fee | note | ACTION (Hold, Monitor, Witness) - H
954d484e-e40b-59a5-998b-6353359d4a13 | note | Detail - The Engineer needs to inspect the subsoil drain installed
8892f8ba-79e2-5256-80e1-c0a23b5bb53a | note | Frequency - After subsoil drain has been installed
fdec0952-0152-5f2b-a1f5-04cf105a2f5f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e56c1e2d-bc32-564b-9e90-0fd0acb1d990 | note | Conformance Criteria - Engineer acceptance
fcd74e31-7033-50ff-8f49-961b62eea5a1 | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - As-builts
9cde5b56-c3bf-5b0e-8c86-c12d4b969de1 | note | ACTION (Hold, Monitor, Witness) - H
ad5aca4b-22e8-5a02-902b-dfe365296f07 | note | Detail - Red pen mark up drawings to be included in QA file
6648132a-3a47-5c97-9988-f137eb73db68 | note | Frequency - At the completion of the Lot of work
68d1c488-2bb2-5f33-98fa-c184dcfa9e64 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
7761ee2c-1cba-5ac7-8398-a5d2cd5e499c | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - E3001 - SH05 SIP Generic - Guardrail V2 | itp | ITP - E3001 - SH05 SIP Generic - Guardrail |  | 1200b33f-c809-4ab4-8059-f814df22456c
| section | 1 - Setout & Checks
| checkpoint | Project Site reps.
cced162c-64d2-5efc-90aa-3b044f641676 | textbox | CPS Eng.
aef69642-1706-53cd-a2f5-9e37b3acdbf7 | textbox | Site Engineer
1d5b771b-c7ac-5204-a1ca-3e64f12ab04e | textbox | Quality Eng.
| checkpoint | 1.1 - Design Check
f55b1984-6d0d-588a-8054-762a33dece0c | note | ACTION (Hold, Monitor, Witness) - M
177051a1-3506-595f-bb5b-b27b189c278d | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
f52bb312-076b-561b-bfcd-7ce0dc5287a8 | note | Frequency - Prior to commencement
04c50c9c-b709-55ad-93f2-9fbdcc77cdc0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
3c9d089b-9c8d-5e1b-b82c-6c13d495c85d | note | Conformance Criteria - National Standard for Traffic Signal
abc6a079-aa01-55ea-b05e-b202cbfc7c2d | note | Records - OFI or NTD/NTC
| checkpoint | 1.2 - Survey Setout
d58a41be-0d8e-55e0-83f7-9dddfd91717d | note | ACTION (Hold, Monitor, Witness) - W
0fa7bbb5-4b90-51d6-9e71-d4f13369826e | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
32bd05f5-da2b-52dc-8829-fa1d931f0471 | note | Frequency - Prior to commencement
a4ab71c4-fbac-586f-9fa2-c32656d81bde | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
4cc17b83-43ed-53b1-b84a-28c1c0984790 | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
3976877d-188b-5908-8651-baae92e7a860 | note | Records - Approved Construction Drawing.
| section | 2 - Material Compliance
| checkpoint | 2.1 - Barrier Compliance
6642b0ee-467b-5a79-b2a4-165f8d013434 | note | ACTION (Hold, Monitor, Witness) - H
fb6250fd-1021-55f6-bd8b-467bc46d4ea0 | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
c11b72d7-da09-52de-9f79-6cfe258be655 | note | Frequency - Prior to commencement
80e3d451-773d-565c-92a1-6ebf55337f2a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
dd9cbfe3-8e0d-5bdb-bb77-dd3f896ed60c | note | Conformance Criteria - TNZ M/23:2009
62a4186d-cfbb-5db6-bf4f-401d19092eab | note | Records - Manufacturing certificates and delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Material Suppliers
ae7a70d1-5226-5090-b448-de63d47187e6 | note | ACTION (Hold, Monitor, Witness) - M
074215fa-0917-5d71-8332-b2a18eceff3b | note | Detail - All materials to be sourced from registered suppliers
3acaba4a-ec2b-5741-935f-d6a5ece44544 | note | Frequency - Prior to commencement
16dcfb4e-b048-559b-a5de-9ecaaa0e1726 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7a66365a-7d74-52ff-823d-bc9d5c2c99bb | note | Conformance Criteria - Registered suppliers
5e9394b5-2f67-525e-93ac-2696134895b5 | note | Records - Materials register
| checkpoint | 2.3 - Galvanising Repair Methodology Approval
5458f4ef-8ad2-55b6-97b9-80b56a22293d | note | ACTION (Hold, Monitor, Witness) - H
bb45e8f6-e4bf-53e8-8973-777656f5dc08 | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
09fe0ce7-c87d-5515-8e8f-a1864b11daa8 | note | Frequency - Prior to commencement
b344cd9d-507f-5320-b1fc-5f693ae0dcb7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
43c2e41c-6eed-505a-a8a0-f48d823f4f96 | note | Conformance Criteria - Best practice
b45f1bcf-f0ad-5ad5-b313-cc5361b57092 | note | Records - Approved / Signature
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Installer Certification
2bf988d0-e6d7-57db-b0f5-da2c54c4ff86 | note | ACTION (Hold, Monitor, Witness) - M
38f4f582-aae9-5588-b09f-83aa42c6f346 | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
8407d565-4f9f-5c6d-9b8a-1a78020da663 | note | Frequency - On Procurement of installer
2ed6ab0f-f8f9-5cc1-ab08-dd3b93aa0e57 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
5043f194-ba45-5b63-a66a-70b1adac55f2 | note | Conformance Criteria - ASHTAS operative and installer course
1d8c40ac-340a-534e-b0be-2bee538bf51a | note | Records - Attendance Certificate
| section | 3 - Guardrail Installation
| checkpoint | 3.1 - Guardrail Installation Locations
9ab11576-eb0b-5230-a01f-7412ca3ac547 | note | ACTION (Hold, Monitor, Witness) - W
125dda90-41e1-568a-9db9-1d408fec3e67 | note | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
f3c68533-2408-5ee2-bdfa-1bd9bb994b67 | note | Frequency - During installation and on completion
31f05e85-4b2d-5ca3-99fe-642ca022de65 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
3b221de2-71c4-5602-92a9-bcd83e09ae7f | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
339a93f5-74e7-5661-8ec2-9455ec461a03 | note | Records - CS-4117 Guardrail Installation Checksheet
| checkpoint | 3.2 - W-Beam Guardrail Installation
2ae331d7-3bdf-5227-adde-9dbb5562585a | note | ACTION (Hold, Monitor, Witness) - M
749e98f3-4830-55db-9df0-906d7dbdf65f | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
47ea6e08-30c2-5a18-8c43-a78322f1d499 | note | Frequency - During installation and on completion
25607303-c40d-5d31-a16b-c65d1e8b4665 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
8f916022-66f2-5fff-a690-f8f718dac095 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
ab67f5a5-59ed-5e53-9389-0085ce9fa182 | note | Records - Installation Checklist
| checkpoint | 3.3 - Leading & Trailing End Terminal Installation
db2bc873-2ab8-5b4d-92e7-54851c13b655 | note | ACTION (Hold, Monitor, Witness) - W
a9780095-b39c-5e2e-af4c-8f2e599c733b | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
e26f156e-2adb-5df8-b083-f513698e407e | note | Frequency - During installation and on completion
e7b375a6-5b2e-54db-b01b-75c6289def34 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
db187f75-ba9f-55ac-a3be-92ae9db66293 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
3fdc85c9-6642-5868-8c20-64faa03b69d5 | note | Records - Installation Checklist
| checkpoint | 3.4 - Fit for purpose Inspection
81653748-fe4e-59e2-aa85-5dfc65f7dc96 | note | ACTION (Hold, Monitor, Witness) - H
be809af1-7a0f-58b6-8ec2-efe97bb63f7d | note | Detail - Barrier to undergo fit for purpose inspection by competent person
e0a8a8b5-b7c5-51fe-8b09-94786272a958 | note | ○ System checklists to be completed and co signed by contractor and CPS.
548e6c03-e4be-5f98-85af-0d482162e159 | note | ○ All faults to be rectified before acceptance into network maintenance and RAMM
c9a8501b-fc6b-5a2e-9861-00a41da50ed1 | note | Frequency - Prior to trafficking,
5179012d-de5f-565c-bdd5-94a972918e03 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a381182b-331f-5750-b3d7-7dfac60abac9 | note | Conformance Criteria - Pass inspection
09644748-d44f-5832-94fc-b603568c2796 | note | Records - Confirmation from inspector
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Post-Construction Closeout
| checkpoint | 4.1 - Final Walkover (Snags)
8c9cc89a-ee3c-5480-a10b-b52368125ce3 | note | ACTION (Hold, Monitor, Witness) - H
7b5aa7e1-c4df-53f0-848d-64b165c388c5 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
3f42e5a5-ab83-53fb-a8a1-ae5b977036d6 | note | Frequency - At the completion of the Lot of work
b29a55f9-ada7-5b9b-9ad5-ceba13309e12 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
0942803a-602b-55a6-8105-80bcd1fa1e8e | note | Conformance Criteria - Completed report
075d5e1e-2747-5f49-8170-a5cfcdd9e534 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Survey As-builts
8744d8c5-e4f7-59d9-83d0-16eea6296b51 | note | ACTION (Hold, Monitor, Witness) - H
d1236711-7d5f-517a-a9a5-0e80155ed85d | note | Detail - Red pen mark-up drawings are to be included in the QA file.
0c4f8a64-be53-5a7c-90d6-fc4a1ff4265e | note | ○ A survey as-built of completed work must be provided
f8a58bd6-76e1-5bab-a6f0-b5bb914dbeef | note | Frequency - At the completion of the CWP of work
2edc01ab-4bee-530e-b917-115d1732a6a1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
1ff12ee5-faf1-59d0-a6e7-eb36c2ee8b9c | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
333266ae-9282-5075-b672-5a6d8dcd3924 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Quality Assurance Deliverables
efc5e96e-0a34-593d-921a-dab98da168f5 | note | ACTION (Hold, Monitor, Witness) - W
edaf7a61-3df7-50ee-b512-d960651f7eb1 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
c4c767a3-1621-5e88-9529-deba8b5fcd1b | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
e2f731c1-645c-5c19-a342-4c0d792eed25 | note | Frequency - At the completion of the CWP
e7a22da3-7d7b-53a1-b926-29f2578c58bc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c8cfbc51-4c54-5975-bb9d-04442f404870 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
f46dc4c1-27eb-5cfa-a51b-2023a17405bb | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn V2 | itp | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn |  | 466f43bf-47cf-454d-8ff3-ce59a4db76b9
| section | 1 - Setout & Saw Cutting
| checkpoint | Project Site reps.
5eaf96ef-4314-51c3-9f83-46a410df3f49 | textbox | CPS Eng.
eb8a8ba7-f086-5223-9612-7ac0edbff6f1 | textbox | Site Engineer
9a84afa8-eced-5584-ada9-eca26ae76aff | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout
a327c703-085e-5291-8f76-e7375d4857be | note | ACTION (Hold, Monitor, Witness) - M
2e934403-7ebd-51ae-afea-f103c9f552e4 | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
e9ff245b-7286-5d4b-9839-bb9cc1e28c0b | note | Frequency - Prior to commencement
479d5542-d8cb-56ee-a74b-93ed89cd546b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
aaff4b60-b2b0-5ec2-a86e-65984f21282c | note | Records - Survey receipt
| checkpoint | 1.2 - Saw cutting
af8e8bf1-aee7-5314-84ec-67565e76df60 | note | ACTION (Hold, Monitor, Witness) - H
a17ca7eb-a599-5e81-aed6-08c529d3ce7d | note | Detail - Proposed Sawcut line to be inspected by the engineer
bb0712ce-9ca7-52a5-84db-48293a9c2f69 | note | Frequency - During construction
39cbab90-9b5f-5d75-bac9-3714bbad40c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
264e3216-1680-5f8e-9fb8-6573a7657f9b | note | Conformance Criteria - Project Specification 6.6
49fd88d4-3a20-5afd-a98a-abddfef0b226 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Material Compliance
| checkpoint | 2.1 - Sub Base Material Compliance
2a8c3ff1-c437-52b2-bfed-50738f176076 | note | ACTION (Hold, Monitor, Witness) - W
f0af23a2-65bf-504d-977d-dcf88525ee1f | note | Detail - Aggregate material compliance for Sub Base stockpiles
43f666e3-039a-553b-9866-faaec8eb0f49 | note | Frequency - Prior to commencement
b90dc7f4-d876-5911-9d1c-e3b513dbce91 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
7944c8b5-35d8-5348-8436-7fb5dd10acc7 | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
e720a913-2a22-55b7-ba62-8f8870e5ef32 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.2 - Base Course Material Compliance
6b6260c8-7793-5168-b343-7f9539bd4124 | note | ACTION (Hold, Monitor, Witness) - W
14a42186-465c-5eb5-a26b-f33498e0e989 | note | Detail - Aggregate material compliance for Base Course stockpiles
ed3c1cb2-3569-56cc-aa60-2f611febf9a8 | note | Frequency - Prior to commencement
32f9fcf6-1e06-5390-b6d6-6a946444b21f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
d5ee02ab-6a30-51d8-bd3b-03e9eae098ef | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
dc94aa75-d136-503c-86bd-264aa84ff144 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.3 - Concrete Pipes
e18f87a3-ee2d-5531-9690-8c38700cf570 | note | ACTION (Hold, Monitor, Witness) - W
12c6dbe7-22e4-5d41-8f7e-151478f73434 | note | Detail - Specification Compliance
c3398cf4-48d3-53cf-bbea-dd08600a5a85 | note | Frequency - Each delivery to site
94e12109-2f98-54a3-b1ac-afe2e119dd95 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
f4a57f3f-30b3-5a09-ba4d-1791ac9a6980 | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
fb7e03e4-3874-568c-9c50-1f7f1f7bd425 | note | Records - Delivery Dockets
| checkpoint | 2.4 - Pipe Bedding Material Compliance
45c2faaa-1cc5-5c8f-8d2e-f5075d861d90 | note | ACTION (Hold, Monitor, Witness) - W
97f80f13-4bc9-50cd-9bb0-6cf77668d9d2 | note | Detail - Material to meet specifications dependant on material type selected
5c7b252a-7c35-5ff5-bc78-9fcc54b5ab2c | note | Frequency - Each material used
77456db3-b046-553c-996d-94d7cd62810b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
14f0c562-51bc-5f3d-8b48-55f4e8fb144a | note | Conformance Criteria - Compliance with requirements from Specifications
dcb5452b-0c64-5900-b8ee-47fe2c628d2b | note | Records - Lab Test Report
| checkpoint | 2.5 - Pipe Backfill Compliance
bd71a89c-0d9c-50f1-a142-0f251eb51d48 | note | ACTION (Hold, Monitor, Witness) - W
81c61c7b-7b32-5881-8b31-85985c49a6ee | note | Detail - Material to meet specifications dependant on material type selected
6924d00f-d2c6-5b6e-935b-c07aa745c786 | note | Frequency - Each material used
8c1aab0d-c47a-54ad-93c4-02391d673db7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
bba74deb-b5ee-5e58-b330-cdf1bd3a0fa0 | note | Conformance Criteria - Comply with grading specification
ba8afc2f-e634-517a-9faa-6719cebb1e9a | note | Records - Lab Test Report
| checkpoint | 2.6 - Chip Seal design
7141d653-f61e-5e65-8ee1-e4c6cf2f8e7e | note | ACTION (Hold, Monitor, Witness) - H
daba90c3-9c1d-5493-adc7-0aa6c541e2e7 | note | Detail - Seal design to be reviewed prior to sealing.
d615fe85-08f2-578b-b97f-10ba6a61eff0 | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
0c531b49-e418-5649-aafb-165f41a25c52 | note | Frequency - Prior to Sealing
5948742b-e801-502d-823d-0030621557d8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
5b6b7248-0e3e-576c-9780-d7ea1662327d | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
8b778e6c-0702-535b-97fa-c9b87151ca2a | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Sub Grade Construction
| checkpoint | 3.1 - Sub Grade Strength
6da4f943-ed44-5248-b125-a8138ae14835 | note | ACTION (Hold, Monitor, Witness) - H
7ae36348-7b5b-5809-84a6-ad818a7b53e5 | note | Detail - Determine Bearing strength of Sub Grade
9f3df29c-d1a6-50e8-b30f-cd6a8c38ade9 | note | Frequency - After Dig out, every 10m
a6c2692a-a6d5-5048-8e7b-358d61167c0e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
0669672d-7551-55d5-b87a-73cedecc637d | note | Conformance Criteria - Min. 2 blows /100mm
77774cb8-1dbe-51e2-8491-6b21972f37e7 | note | ○ 2 blows = 4 CBR
ad96bdd9-c4d7-56d9-a5cc-c249aef9a2cd | note | Records - QA measurement Sheet, CS-4000 1m Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Proof Roll of subgrade
02a6fab6-b897-5ef0-8131-7f9b29a90f71 | note | ACTION (Hold, Monitor, Witness) - H
6848d3a6-7bd7-5433-9f5e-ca343e66a3a7 | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
2050be43-53f0-50f0-a944-1241417d1979 | note | Frequency - Prior to Sub Base Construction
ff5f84f7-d1f8-562b-b0e1-dc5e4e478fd1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c8cf295b-8a28-5e8a-82fd-fe210e1c815c | note | Conformance Criteria - Engineers Acceptance
ac640f9f-79e0-57be-ac63-2111bdb40728 | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Sub Base Construction
| checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
750ebec3-5826-5019-bdd2-76bb74fcc738 | note | ACTION (Hold, Monitor, Witness) - M
16825082-e306-5463-9e9b-738179d634d7 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
dc5d245e-72b8-5809-8cab-518892dde74a | note | Frequency - During construction
7976a289-eecd-5b93-bfb2-7d8cf7823d4f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
e0443362-6eb8-560e-84d1-b500d80a6fab | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
9e82593e-ae23-5c5b-a87d-f11825e3818e | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 4.2 - Sub Base Material Contamination Checks
d2478fe4-5000-5dbb-9d0f-479195678693 | note | ACTION (Hold, Monitor, Witness) - M
f49750e8-8e08-5afd-93c2-a41ef5eaff95 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
0cf51bfe-a5a9-5961-b227-5a72f6ab9705 | note | Frequency - During construction
2494f8f1-f3a1-55fb-8672-6b81acc3a31b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c34fd02a-e77c-5f8f-b6f1-970f9f27c8de | note | Records - Photos
| checkpoint | 4.3 - Sub Base Trimmed Level Checks
bbb7fe81-b8a9-5137-8051-029aecbd9146 | note | ACTION (Hold, Monitor, Witness) - H
e20dd6ef-75da-5e34-811b-c8b15907e95b | note | Detail - Carry out a Level Check on the trimmed Sub base
c7a22507-4e88-5871-a565-92f8fc1f3047 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
e84acccc-ceee-50b3-ad3b-11c28a142a25 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
ba4b7aa9-4117-554c-8fd0-faed860d4946 | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
8deaceaf-cf49-55d0-88fa-8e0fedfcf84d | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Sub Base Compaction Lower
1a2a17e2-01d1-5e4d-96e4-ea4dc2192782 | note | ACTION (Hold, Monitor, Witness) - H
7822b78a-b01b-5af9-a3e1-77c5b247d3c4 | note | Detail - Degree of Compaction.
9aa73e5e-813b-5307-804c-23f7b6b1995a | note | ○ The subbase shall be constructed in two layers.
6fd37884-d8f4-53fc-a590-0c091e8faf3c | note | ○ Lower subbase results must be approved before construction of upper layer.
36c0306e-f542-51bc-b547-d92addeb1de6 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
2caf7788-df59-5bd3-82fa-b0b35bbc5775 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
754ec960-82dd-588c-8a08-c007e6a39b30 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
daf1d0f2-95cb-5f14-83d9-4556cc5e577d | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Sub Base Compaction Upper
492a1cca-0cb8-5ef1-855c-34c84ec92dc9 | note | ACTION (Hold, Monitor, Witness) - H
444f0157-c8ad-5d14-a257-2c7004bcbeba | note | Detail - Degree of Compaction.
3f95f327-68f0-5374-8e20-69baa4fb9510 | note | ○ The subbase shall be constructed in two layers.
4011a8e7-e723-58ca-84fe-b429afa87a4e | note | ○ Upper subbase results must be approved before construction of basecourse.
6e712283-22db-5cfb-9a1f-a1d627dc73c1 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
0aa83a10-ed8d-5b91-8882-7036d07a7b67 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
2f606761-eac4-581a-8029-71cb66dfa5d1 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
81ca589f-fa8e-5310-88ca-71a77ec549eb | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| section | 5 - Base Course Construction
| checkpoint | 5.1 - Base Course Aggregate Delivery Checks
0772191b-7f19-58d2-94fa-6d90443d2b76 | note | ACTION (Hold, Monitor, Witness) - M
f2d64243-230f-5e6e-85b3-2c3ca5bf1582 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
ac23a20c-d36d-5e1f-9dd3-f8c0f59da4d2 | note | Frequency - During construction
cc812f2d-cd46-5b53-80f8-ba78ed98564f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
efd5e964-acc1-58fc-bfde-bf2c7c47fabb | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
e012b8ab-c0fa-568c-a74a-2e5d991fa9a9 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 5.2 - Base Course Material Contamination Checks
00924602-560d-56d4-a2db-b7d452d599c1 | note | ACTION (Hold, Monitor, Witness) - M
1d7e339e-0819-5061-a6b0-dd0e71fe9a1e | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
56708092-193b-5039-a5af-5d1d71ae2fca | note | Frequency - During construction
9b9b8925-2062-59b3-8e3b-09fb2864f924 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c5076003-747e-577e-bfdf-190979f5172c | note | Records - Photos
| checkpoint | 5.3 - Base Course Trimmed Level Checks
dfe83787-9637-5c75-991a-d25b77dbe45b | note | ACTION (Hold, Monitor, Witness) - H
1c28a6cd-7ea8-52ee-9330-ceabb6ae0325 | note | Detail - Carry out a Level Check on the trimmed Basecourse
f584e00d-55e7-51e4-af82-78a4a20431a8 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
b3a249c6-d695-59aa-a5c7-cc6006f6aa19 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
ed407575-8c65-556b-9e1f-564b0c09adaa | note | Conformance Criteria - Tolerance = -5mm/+15mm
8ffc541d-8b9f-5390-b2ac-d9168fbf9852 | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
cde82869-37d8-57da-b71f-4e40ac9c477d | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Base Course Compaction
a0ada81b-16b1-5e14-9d23-7ad45b9845ef | note | ACTION (Hold, Monitor, Witness) - H
f9641131-5270-5435-8310-f616117a381d | note | Detail - Degree of Compaction
1573ccad-0a0f-5da4-a6f5-8690af76728f | note | Frequency - 5 per Lot
8d475302-e142-584b-a85b-1de3ad4cb850 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
14ded284-de5f-5657-88af-0f64908b785f | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
3c812792-602e-5392-bca9-45820752b78c | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Base Course Surface shape check
960b0fb5-cad2-5880-b8a7-f32323baea14 | note | ACTION (Hold, Monitor, Witness) - H
8a919f01-7cce-5a87-b390-0e44d9ef3fdb | note | Detail - Surface shape check
0052f421-f971-5292-bd73-fdf22a7ef3c4 | note | Frequency - Prior to sealing
203cfeb6-cb7d-5e6a-b5de-e7f8239b01a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
f7bd6331-a35e-5fd6-9e35-7934927ca97b | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
52c6be31-0f19-5580-9c91-533e3160d1cb | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Base Course Surface finish check
f9b075ae-23a5-550b-84c4-664fa5ad8ccc | note | ACTION (Hold, Monitor, Witness) - H
2dcc09d6-2fbc-5364-9e42-4485b5b88a58 | note | Detail - Surface finish check
6fffd42b-c3b6-5c80-bf40-775f44f2b679 | note | Frequency - Prior to sealing
3f00703f-b254-5468-af17-b05e0384f2bf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
3b0260df-6d16-54ba-8f96-06af05ac97fc | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
c4718534-551a-547a-891a-3d199aa89730 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | 6 - Extension of Culvert
| checkpoint | 6.1 - Foundation Compliance
45be92dc-8806-5427-8e2d-a61bb1a803a3 | note | ACTION (Hold, Monitor, Witness) - H
b27544d3-1dc4-581c-986d-97f3f6c4d77d | note | Detail - Test formation level on completion of excavation to check if undercut required
797a5bab-64ed-5ebd-b1a6-d550e665a434 | note | Frequency - One test per 5 linear metres
c7b969e6-eaf2-52df-a98c-14a744769917 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
aef78195-05bc-5d9f-8e8a-9bd0c23c2d46 | note | Conformance Criteria - Min. 2 blows /100mm
98cdcf13-72b3-53bc-bb1f-137930572c63 | note | ○ 2 blows = 4 CBR
889981e6-d9a9-565f-8fca-5bc6e70dcf22 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Levels Compliance
0e2b22cb-6aef-5430-b39a-5a96de8d206f | note | ACTION (Hold, Monitor, Witness) - H
6059d5df-b1a6-5ee1-bef0-1a05ae073aa9 | note | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
f562a4f2-6922-5d86-8de6-961416598880 | note | Frequency - As stated
ae8b43c7-1d00-519f-b37c-25dab3bcf642 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
608cd521-7adc-52ae-a207-f12c90b70182 | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
da79f9b2-1ded-5f99-91cd-3d12e814d437 | note | Records - Photos, Visual
| signoff | AUTHORITY HOLDPOINT
| section | 7 - Sealing
| checkpoint | 7.1 - Location/Size Confirmation
55e08f24-1e4b-5d9c-be07-45d63498b79b | note | ACTION (Hold, Monitor, Witness) - W
9ecb35f0-62f4-50f8-9937-62d87be0acf9 | note | Detail - Mark up extent of Chipseal
68db4614-41ac-53dc-a59b-50603435e345 | note | Frequency - Prior to Sealing
49ed456f-5ee1-5ec2-839b-93fd0b4509fc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
606927db-485d-576b-84a1-99605c8ad3f0 | note | Records - Photos
| checkpoint | 7.2 - Surface Cleanliness
1bcf7106-ce4b-5321-98b3-26d13274b4f6 | note | ACTION (Hold, Monitor, Witness) - W
6b72b169-48d4-5935-a1f0-a6d9a1e5dfce | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
630628cf-6b4c-5690-82bf-7ddba21ca546 | note | Frequency - Prior to application of binder
e3244862-29af-5af8-935e-3048754b079c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
2fe5ae57-bfb7-52f5-b56d-f1bf26b8e8cd | note | Records - Photos
| checkpoint | 7.3 - Binder Application
8fc402e7-21cf-502b-9e5c-150d090f97b1 | note | ACTION (Hold, Monitor, Witness) - W
aca03926-84bb-5f6e-b782-e646503ae1fe | note | Detail - Ensure the Binder application is according to the seal design
6654e618-64cb-5483-a29d-c43214056299 | note | Frequency - During sealing
b2aba300-f0b7-5f09-a1b5-aaa16153b7f2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
7289c1c3-55fb-55fe-8f86-ef8340775f63 | note | Conformance Criteria - According to seal design
f62cabb9-28a2-5a13-bac4-69086d8820f2 | note | Records - Sealing sheet
| checkpoint | 7.4 - Chip Application
c59768f7-979c-571a-911c-7d8177946b91 | note | ACTION (Hold, Monitor, Witness) - W
1cde60dd-1b29-59ad-849d-7466a299c173 | note | Detail - Ensure the Chip application is according to the seal design
24668de1-5505-55d6-9021-9099a8de0441 | note | Frequency - During sealing
da92bd03-998a-5a39-8230-894cb3f44542 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
bf968687-d8a1-578c-b698-5f8df0dd1f42 | note | Conformance Criteria - According to seal design
02d6a1aa-bb79-5ec0-9e8d-a0cc5916f006 | note | Records - Sealing sheet
| checkpoint | 7.5 - Compaction
a239f1d7-efaa-5ab2-b804-52788389a8a4 | note | ACTION (Hold, Monitor, Witness) - W
a389fb1b-0761-5cf4-a645-7055cd1806d3 | note | Detail - At completion of rolling
fa1cbf5d-98f5-5ad9-be59-95901da3904b | note | Frequency - During sealing
8e557790-feac-5f84-b8e2-4e53412f0a5d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
f03ac157-d2c7-51e5-8d8f-d6fbdded7dc3 | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
bf719e1b-6fcf-5636-afd2-54c82a6259f6 | note | Records - Photos, QA measurement Sheet
| checkpoint | 7.6 - Removal of excess chip
4834dd61-983c-5bed-8f13-b10937d9dba0 | note | ACTION (Hold, Monitor, Witness) - M
1407b561-6856-5e0a-9d85-113220284617 | note | Detail - Removal of excess chip
8dd17909-414e-534c-8936-334525b8f346 | note | Frequency - Within 48 Hours of Sealing
e2c30be3-b24f-56c9-9612-1f85bf8d09d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
905bd7bc-c118-5c94-8005-a6401a5b5100 | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
82ff8530-8763-5d12-b66f-782aa3c6c8a7 | note | Records - Photos, Site logs
| checkpoint | 7.7 - Surface finish check
2dea07ed-a233-5107-a8d2-320baf3d9ca7 | note | ACTION (Hold, Monitor, Witness) - H
82156e54-aeb5-57a7-97c7-55bfe1f39781 | note | Detail - Surface finish check
b641dec9-2a5f-5cfe-a0e1-2a0fd9b89d0a | note | Frequency - After sealing
c2e31100-0f81-5b00-9a39-69146fb84c0d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
26806c68-067d-5216-bcb7-b3268a370267 | note | Conformance Criteria - Engineers Acceptance
e1a7bfdf-97bd-527f-b3db-d12009b1b569 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 8 - Road Marking
| checkpoint | 8.1 - Road Marking
7948cc8f-6d46-5536-b77a-8a3956ce71e5 | note | ACTION (Hold, Monitor, Witness) - H
bd5a1ede-71e5-59b7-9294-4bd1851cbc80 | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
eb713895-21a2-5c41-ab4e-9bb0c40bc96c | note | Frequency - Prior to the final line marking
19ab4798-0e0f-58d5-89ed-1c3c095b43c9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
19c31483-9a4e-56e2-ac94-03a703cb092a | note | Conformance Criteria - Engineers Acceptance
49c95b7a-cd66-54d5-ae1c-5ceb4d26aa17 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 9 - Hydroseeding
| checkpoint | 9.1 - Hydroseeding
fcf8aaef-026e-5b9f-97e4-253efba6fc98 | note | ACTION (Hold, Monitor, Witness) - H
d7cea0e9-ef80-5992-824c-85b2b44e012c | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
bf1d6a3c-9f59-5a8f-a2e8-69c9e5dbab22 | note | Frequency - At the completion of the Lot of work
407258fe-f443-52ff-b1f2-7fe5993c18c6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
e00d4925-9bf1-5fba-a9c7-6e8c63ff19d6 | note | Conformance Criteria - Engineers Acceptance
8dc2e0f2-b37c-5cc0-abfd-9ea5abf664be | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 10 - Post-Construction Closeout
| checkpoint | 10.1 - Final Walkover (Snags)
982ff868-c2dc-5490-8bc2-67f7bad93854 | note | ACTION (Hold, Monitor, Witness) - H
654640ab-95c1-53b3-b22e-df1313e2a73e | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
1ea94dee-7077-5903-bd4e-ad811867b177 | note | Frequency - At the completion of the Lot of work
6aea82d3-d905-56eb-beb2-fb213708a934 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
bd2deeb8-ece0-59ea-a3aa-cdc98ff854c9 | note | Conformance Criteria - Completed report
1a35418b-9150-5fd0-afe9-1c25026c59ad | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 - Survey As-builts
5fa849e6-ff29-5444-a20c-1d6c6b055be9 | note | ACTION (Hold, Monitor, Witness) - H
9f3f221b-0d43-5f59-852a-e6be3f9a04d7 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
70bcab5e-2444-50a1-8c5a-9309b58e50b1 | note | ○ A survey as-built of completed work must be provided
a61a8f18-38b3-56c7-b898-2fbb816415da | note | Frequency - At the completion of the CWP of work
6696f226-c05e-5b52-996c-7c6cb8ef6788 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
cfdffd97-8bc8-5110-9bf4-51bd7c641ce8 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
b6896e51-ee19-577f-9d69-28578241d0cd | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.3 - Quality Assurance Deliverables
2b200a92-58ff-531c-82bc-864915f65f49 | note | ACTION (Hold, Monitor, Witness) - W
6d9a762f-49ad-5f0d-b927-6c501348f290 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
6dc7d01b-418b-535a-b225-a18817c22999 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
72e06a66-74d4-50e9-93f9-667a3483d7f5 | note | Frequency - At the completion of the CWP
c216d9a2-e74b-5efb-83bc-dcc963c463ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
28497fbf-1038-50e0-a395-6e4fbad63998 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
8b89c2d8-45c4-5a79-9258-621c7893e9aa | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction V2 | itp | ITP - E3001 - SH05 SIP Generic - Pavement Construction |  | 3bc16a59-7963-4a6a-b5e7-809f99a8c25f
| section | 1 - Setout & Saw Cutting
| checkpoint | Project Site reps.
5da27e37-9227-5bb1-a724-fbf532403a4f | textbox | CPS Eng.
dc9e46fd-eb2b-5473-9946-dd1dfb0a1aba | textbox | Site Engineer
5a919999-991e-5160-9912-a294362d2c67 | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout
3ef15018-6208-511e-8c82-d1183059d622 | note | ACTION (Hold, Monitor, Witness) - M
b8960be2-03b2-59ff-b4d8-752ba989392b | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
4ebf3757-7862-55c8-99b3-72880d3f1c73 | note | Frequency - Prior to commencement
ecb94d98-9750-599d-b303-158d244625de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
f269f329-a54a-5df0-9660-2e4daacc3c5d | note | Records - Survey receipt
| checkpoint | 1.2 - Saw cutting
16ea99d8-ef40-59bd-8c5a-5f5ad20a5110 | note | ACTION (Hold, Monitor, Witness) - H
ea533cdd-56ad-522d-9021-e49d7662d1f0 | note | Detail - Proposed Sawcut line to be inspected by the engineer
f3e10b10-6dab-5347-8aeb-febbad767d01 | note | Frequency - During construction
286319d0-553d-54c1-b317-04b282f99c2e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e5809d11-6015-5a46-bcff-54894ea5223c | note | Conformance Criteria - Project Specification 6.6
187f0fd6-12c9-5321-acd6-623c638caa1b | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Material Compliance
| checkpoint | 2.1 - Sub Base Material Compliance
afc0c0bd-da12-554d-aa42-a96305fe4320 | note | ACTION (Hold, Monitor, Witness) - W
ae94212e-d0a2-59dc-a902-db67d176c2f7 | note | Detail - Aggregate material compliance for Sub Base stockpiles
6021f4f4-d3c6-5bea-9179-9aaeb88b902d | note | Frequency - Prior to commencement
9e64e8a1-0a37-5bd4-b685-b822f88f00e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
ab7b2e55-1551-5fd8-985d-9094acab4a8b | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
ac9a0812-9c04-5ce7-90ec-c76cb17e20d1 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.2 - Base Course Material Compliance
5f00bf43-8d7d-585a-8daf-f14e112b6230 | note | ACTION (Hold, Monitor, Witness) - W
94e8cb67-85e3-5453-ae90-b5beacb67bba | note | Detail - Aggregate material compliance for Base Course stockpiles
910048a7-84d0-5605-91f3-e55d0427aec9 | note | Frequency - Prior to commencement
34a94167-7f5f-5aae-965a-1157570982d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
825117ee-e282-5ce8-a2fe-678e108c0a09 | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
df1c5b79-8441-528f-b877-ea5baba299a1 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.3 - Chip Seal design
6242664b-32ed-53b6-a3ed-aeea5c5b0f3b | note | ACTION (Hold, Monitor, Witness) - H
b74310c5-c1c0-599c-a570-596cfd8df162 | note | Detail - Seal design to be reviewed prior to sealing.
951e56e0-2725-5124-8564-95ff58370f78 | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
b57dd01e-989d-5b53-9e8e-9640c2257bdb | note | Frequency - Prior to Sealing
31f6ccb1-de06-5196-b51a-defa7f1c713f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
47d962ce-af5a-5dfb-b1af-3e3e5b1eddcc | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
1eaa35da-0f38-5de4-ac2b-ad95d8797e05 | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Sub Grade Construction
| checkpoint | 3.1 - Sub Grade Strength
9f98b8e7-cf56-5bfa-8271-39c4f3aa8879 | note | ACTION (Hold, Monitor, Witness) - H
0243efe6-bd17-557b-88c8-845a3db28e60 | note | Detail - Determine Bearing strength of Sub Grade
ad87a623-204d-5161-aa18-282647c27b6b | note | Frequency - After Dig out, every 10m
d087639e-cdc1-5423-a4b4-332b524dee89 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
38629ae5-8331-582f-ac1d-83875c734bce | note | Conformance Criteria - Min. 2 blows /100mm
68cf7310-e3a2-5b71-a125-73c6ac686c21 | note | ○ 2 blows = 4 CBR
9a668e70-3dfc-56e3-895d-cd70e2854daa | note | Records - QA measurement Sheet, CS-4000 1m Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Proof Roll of subgrade
8dda20b6-e36b-530d-9288-89ffc93618d8 | note | ACTION (Hold, Monitor, Witness) - H
b71fb06d-af66-5baf-8773-10b17ae2bed3 | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
c954ded2-96e7-5af8-85c6-8a899101aa05 | note | Frequency - Prior to Sub Base Construction
2d8a8f02-51f6-5430-8d53-686192d4fbed | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
9cd4191b-ab63-5b8a-a832-2be3f7bd5e7b | note | Conformance Criteria - Engineers Acceptance
37b503a9-dd84-5465-8229-af1577b39778 | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Sub Base Construction
| checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
4040404c-e33a-57ab-8e0c-9e510ca0b66e | note | ACTION (Hold, Monitor, Witness) - M
07c4f95a-1c8e-5117-909c-c59c6a29b847 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
9ee68f3d-4159-505e-8cf5-17f39abb6bd6 | note | Frequency - During construction
507c5590-3f67-519d-a544-d0a37cb4d8f9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
ca92ccb4-644a-5403-91f7-21d24a95bb8b | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
29d4a6ff-41e0-5fa1-8b27-5444a7254413 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 4.2 - Sub Base Material Contamination Checks
2ac3f7fa-7af8-549c-885b-b7c883addb17 | note | ACTION (Hold, Monitor, Witness) - M
c5d860c0-cc62-5398-a05e-06d3246cc065 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
cfcab3c5-c985-5dee-8a44-ab6c6b8d3113 | note | Frequency - During construction
e8d8dc0d-e5e9-54d5-9409-2c1fde4103f4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
adaad07c-7bcc-5635-9a28-c76b5c0fb511 | note | Records - Photos
| checkpoint | 4.3 - Sub Base Trimmed Level Checks
74e426b2-2e49-5a32-873e-090e01d9080a | note | ACTION (Hold, Monitor, Witness) - H
a1d707ab-01c3-5683-80ba-d304fcecafb2 | note | Detail - Carry out a Level Check on the trimmed Sub base
c51c1567-cc37-5801-86a0-1474c7db4695 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
28b40f97-5488-5e87-b9cd-4b8b51db9930 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
4320d227-1631-5656-bedb-032176d4b5a9 | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
f0aa8f9e-aa5f-55ab-b00d-a02d9e9f5cd5 | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Sub Base Compaction Lower
83156ea3-8204-5ebc-b059-aa6bb2996063 | note | ACTION (Hold, Monitor, Witness) - H
5cf1ad09-96c1-54e1-a81f-cb6583e36f79 | note | Detail - Degree of Compaction.
88f560c6-a8b5-5eba-a0cd-5c23834c6362 | note | ○ The subbase shall be constructed in two layers.
3ff8a5fd-7a5e-5a0c-a9a4-9dbaa34fb280 | note | ○ Lower subbase results must be approved before construction of upper layer.
451fe181-7218-5d50-82ec-456548e3a1fa | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
2b8674bf-18fa-526c-b779-32b2192e5da8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
eb3be03a-56a6-55f3-bec0-41400956e24b | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
1c3e1863-2578-5f19-a036-3815db278bc5 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Sub Base Compaction Upper
39a2f529-fb2d-5734-aa4d-0612ea21993c | note | ACTION (Hold, Monitor, Witness) - H
4301bd6b-0072-5bf8-ae06-5ac2fdd6a9ec | note | Detail - Degree of Compaction.
96688400-c1d3-599f-8f72-4655db3c738e | note | ○ The subbase shall be constructed in two layers.
e811e220-aaf9-5719-84cd-08e13f2ad804 | note | ○ Upper subbase results must be approved before construction of basecourse.
492b1a19-728f-5cea-bf6e-20ea2fd3f6e0 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
96d81701-9dd5-5363-8751-83268f9630c1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
2eac3e29-6dc2-57c4-b553-03fa86a1cadb | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
aab71665-6f34-5ecc-885e-4c778e3defd0 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| section | 5 - Base Course Construction
| checkpoint | 5.1 - Base Course Aggregate Delivery Checks
a9505cc9-d657-5d0d-9013-ab2f18821ed1 | note | ACTION (Hold, Monitor, Witness) - M
92f48eee-05e8-53ad-9199-c0d3493a373a | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
f8f8a5b1-41bf-5770-8fd5-c14e3ba0c648 | note | Frequency - During construction
7f7168e5-a0aa-5225-a5bd-6a94acad8ae6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
9aef1535-8d7f-5449-aa05-9416ce4d817d | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
26fa8e8f-9ca2-5996-9859-30d768f362c7 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 5.2 - Base Course Material Contamination Checks
455a7bb4-2877-5879-befd-447ff47cd683 | note | ACTION (Hold, Monitor, Witness) - M
52b87140-99ed-5def-af1b-ba5836871a5d | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
83da7bc3-9eb5-5c40-9bf6-3a79c0c93442 | note | Frequency - During construction
db3561ae-16a3-5252-a5ec-07ab24948e07 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
abc8c789-c8ba-50cc-86fd-aa83851b6d93 | note | Records - Photos
| checkpoint | 5.3 - Base Course Trimmed Level Checks
ea7aabec-c7af-5eff-a2e7-ac1944cb3274 | note | ACTION (Hold, Monitor, Witness) - H
57681b45-f5f1-588d-a790-719b9037e9b9 | note | Detail - Carry out a Level Check on the trimmed Basecourse
f78a7bfe-40a0-54de-9eac-0d311f9fd842 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
1c1e8ac0-6dfd-5aab-b8ed-327fa25a1e0a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
02636fff-f1ea-529f-b67a-8da418d46658 | note | Conformance Criteria - Tolerance = -5mm/+15mm
2e4aa163-4cf7-5182-936f-0c1190506a7a | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
2fe400b7-361e-5c15-a881-79134691646e | note | Records - QA measurement Sheet CS-4100b Basecourse Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Base Course Compaction
7adbab00-8d87-5485-a1e0-2117e1b5f871 | note | ACTION (Hold, Monitor, Witness) - H
5defd46b-293a-5b8c-bd17-9b32d463b084 | note | Detail - Degree of Compaction
803620d0-d4d1-57f8-b00d-f3109f415968 | note | Frequency - 5 per Lot
68bb47d5-4232-5f81-81a6-cab7c53e3021 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
ba7c8fbf-4ee6-5b05-82a7-9de90837f882 | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
3f67cbb6-3129-55f2-b9b7-16b96c08926c | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Base Course Surface shape check
624b10ac-6c8b-5771-a808-dc7ef81602d5 | note | ACTION (Hold, Monitor, Witness) - H
de94c82c-f275-5889-b2e7-7e1897299fd4 | note | Detail - Surface shape check
77d1f411-78ec-5059-8591-3bdd0d36c8a9 | note | Frequency - Prior to sealing
8bbe0891-aff3-589e-93af-f3ab94f1b2e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
85cda516-e41d-52b1-b739-7f0886a73f15 | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
05ed5353-ec27-5be9-835d-bba72c42a0b6 | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Base Course Surface finish check
0220ad22-0840-56d5-919f-a0c33498fc4c | note | ACTION (Hold, Monitor, Witness) - H
aebf525d-4ed8-5718-a98f-1ea627e85d36 | note | Detail - Surface finish check
b079aa92-77d3-5094-8b1b-a86b322adfa9 | note | Frequency - Prior to sealing
d9ac9732-5dea-5224-9f27-fa763908fb54 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
3fa7dc4e-60bf-50a9-aeb4-217f1cf68970 | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
12abd0a8-cb91-58b9-a8f9-e11618432643 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | 6 - Sealing
| checkpoint | 6.1 - Location/Size Confirmation
7485f261-d4f9-536b-8fdf-561601de76c2 | note | ACTION (Hold, Monitor, Witness) - W
c8d48b6d-db97-53fb-9758-4d4866adcbd6 | note | Detail - Mark up extent of Chipseal
cb8b1442-c99f-5f49-b1bd-e623891b21e3 | note | Frequency - Prior to Sealing
739f9ab4-98f4-5175-a391-f34c4115690c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
0948da8f-3868-588d-ab60-cc56197caa0a | note | Records - Photos
| checkpoint | 6.2 - Surface Cleanliness
fb17b9dd-3a9c-5ae0-8483-0f7f73c208aa | note | ACTION (Hold, Monitor, Witness) - W
79aa985f-289a-5c62-a926-0b250674f747 | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
1f2a42d5-f130-5ef4-9d62-f4e07e20dfda | note | Frequency - Prior to application of binder
88900a8e-f43c-5a99-8559-6dd471a283da | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e6f8d306-45a8-5ad4-9639-9b6595ca4370 | note | Records - Photos
| checkpoint | 6.3 - Binder Application
1422a60d-cd8d-5f49-b41b-d465972ef4fe | note | ACTION (Hold, Monitor, Witness) - W
1b4621f4-d8a0-53f2-bb18-1f9b358d2953 | note | Detail - Ensure the Binder application is according to the seal design
2f077953-4c36-5d05-9d9c-a0db80e18ea9 | note | Frequency - During sealing
9ba2946e-59bc-5470-9365-d7e27ce2acd7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
b6e772c4-0363-505a-8e8f-1239054c41bb | note | Conformance Criteria - According to seal design
f8648227-b271-5c91-ab7e-90f3439745a5 | note | Records - Sealing sheet
| checkpoint | 6.4 - Chip Application
b5a208fd-40f2-52e3-9cca-56711f730bed | note | ACTION (Hold, Monitor, Witness) - W
e72e3bf2-bda1-5f1a-b021-dbba356b5902 | note | Detail - Ensure the Chip application is according to the seal design
911e46fa-d246-5b30-82b5-a6ce46568fe6 | note | Frequency - During sealing
d66906f6-16a5-57c8-89a7-4ce475e38332 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
e8882c91-dcb9-5df7-bf00-d8de68422cfd | note | Conformance Criteria - According to seal design
baa65324-b804-5379-a4b8-95d634b02604 | note | Records - Sealing sheet
| checkpoint | 6.5 - Compaction
e20e83ee-4700-5b84-802b-eb87a3f87c4d | note | ACTION (Hold, Monitor, Witness) - W
c87001d6-cc7e-513d-a15d-023ce0485788 | note | Detail - At completion of rolling
7073d984-be08-5ff7-83e0-9f902fc2f7a3 | note | Frequency - During sealing
6a86c290-5f38-581b-99d8-e986fb728f94 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
84ae9be8-6762-521b-97a6-13b1d5623ac0 | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
6721c5da-b99d-5168-8f75-73e0995eec47 | note | Records - Photos, QA measurement Sheet
| checkpoint | 6.6 - Removal of excess chip
d5c18bd0-667a-5346-a137-b810d639eb7b | note | ACTION (Hold, Monitor, Witness) - M
b5f3dfb8-3b48-5cbf-b61b-fa48d09663a0 | note | Detail - Removal of excess chip
77e27586-729d-519b-a8f7-e5fb020fe37d | note | Frequency - Within 48 Hours of Sealing
56722817-c9fa-5f36-b249-fd18e5ac83d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
964a8ccb-f1d8-574d-8f28-e2cccbb0be65 | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
4b248657-8678-5a28-bb34-5addfc697508 | note | Records - Photos, Site logs
| checkpoint | 6.7 - Surface finish check
3f1b6df4-7b44-57d2-b3a9-15fa76642587 | note | ACTION (Hold, Monitor, Witness) - H
533c4c79-b617-5caf-bc14-d023edd661b3 | note | Detail - Surface finish check
90dcc6c4-eade-54e3-9bc4-961129dbbf46 | note | Frequency - After sealing
369264ef-d533-5e7f-9b79-c0a4cd5c456a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
a23abaf5-bf8e-5fdc-b686-71d39175140b | note | Conformance Criteria - Engineers Acceptance
bf63a106-238e-5a4b-9fb7-b25a2792b89f | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 7 - Road Marking
| checkpoint | 7.1 - Road Marking
0ef3fc74-de5c-5ac1-a095-308ca8073025 | note | ACTION (Hold, Monitor, Witness) - H
51b9f79e-12a5-56c6-af31-7a848ff256ea | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
00cc6976-2ce6-555f-aaf9-a95542f79ff7 | note | Frequency - Prior to the final line marking
d8b2e7a1-ce8f-5cfc-b218-85635199b90e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
255b4cce-c383-5c84-9b14-da016543a7db | note | Conformance Criteria - Engineers Acceptance
b5bd9f51-4f6b-5269-968a-7e0689ca743f | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 8 - Hydroseeding
| checkpoint | 8.1 - Hydroseeding
b61e720a-f746-5e99-8c22-f0c969116f0b | note | ACTION (Hold, Monitor, Witness) - H
2c7c1bd4-2667-5e03-9979-0d3697094659 | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
0caf40e2-08fb-555c-8523-339f007b31a8 | note | Frequency - At the completion of the Lot of work
fa40d2df-0afb-558f-aad4-1237ac808457 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
39b44a5b-4b7d-5c2d-805f-d8d09fa4f680 | note | Conformance Criteria - Engineers Acceptance
f62e2122-ad8e-5238-92f4-0e05ec2196bc | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 9 - Post-Construction Closeout
| checkpoint | 9.1 - Final Walkover (Snags)
7de9238b-1a82-5161-8d51-098bf31828ad | note | ACTION (Hold, Monitor, Witness) - H
0b7ef239-9499-5d42-b9b4-cc1a63f23e6d | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
7e6937b9-79a1-51e7-8579-eab1f02ac151 | note | Frequency - At the completion of the Lot of work
5a2bc79f-d0cb-5cd9-a680-9673075515a5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
bbbc28a7-af8a-5ec5-a7d1-06a900682b58 | note | Conformance Criteria - Completed report
719704c9-1130-5a5d-acac-368e46c466ff | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9.2 - Survey As-builts
734e3d95-654f-5b81-82f8-b9d64a879923 | note | ACTION (Hold, Monitor, Witness) - H
ef15707e-fe22-56e7-87c8-34a64ac4757c | note | Detail - Red pen mark-up drawings are to be included in the QA file.
82d4a511-2815-5af5-8da5-d1c508bb0a13 | note | ○ A survey as-built of completed work must be provided
f5b03f3f-1e8b-55ae-9d2f-4b1ce0d7d12b | note | Frequency - At the completion of the CWP of work
b993bd80-b41b-55d8-8f97-c5031b30e84b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
2438aa1b-a84c-5a31-a735-61f723bafcbd | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
8a8d5207-5b2f-586d-a02b-2e19065886d9 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9.3 - Quality Assurance Deliverables
ed06dd4d-f370-5f63-8ac9-aae4f6a5ef1b | note | ACTION (Hold, Monitor, Witness) - W
d8df4bc2-80b4-560d-b9bc-42e1479f532e | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
771cd758-4ead-5454-88a8-d990b48dbda0 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
531faa74-5e4e-5f16-bddc-c3798b50ab54 | note | Frequency - At the completion of the CWP
31bfad75-8b62-5423-a0c3-50940d0d7582 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0755f4d6-f60e-566c-ae3b-09bfc793a11b | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
7c069f27-d304-5884-9994-f289940a2f88 | note | Records - As-builts, NCR's and RFI's
| checklist | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers | itp | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers |  | 9f633b7a-3c5c-4843-94a3-aa84728eea43
| section | Guardrail & Wire Rope Barriers
| checkpoint | Project Site reps.
758eb6ad-2873-5e7b-b204-28da6b6bfbb8 | textbox | CPS Eng.
bc09aa80-d789-5b2e-9ada-1385248cfba4 | textbox | Site Engineer
21cc7cc8-edc4-5855-93b2-8ad8815b53da | textbox | Quality Eng.
| checkpoint | 1 - Design Check
1828de01-e90f-5ff8-907c-23774ae62ff0 | note | ACTION (Hold, Monitor, Witness) - M
032db625-53ee-506a-9191-82c441d61a1f | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
d0d9b12f-4fe7-5443-a69c-8e14cdec1434 | note | Frequency - Prior to commencement
03579d6e-9b73-58cb-bfad-aa270a5b2021 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
99d5de9d-6452-530a-9b29-822df37a1628 | note | Conformance Criteria - National Standard for Traffic Signal
6f0c5e2a-519f-531d-a0a3-96c003eef7e4 | note | Records - OFI or NTD/NTC
| checkpoint | 2 - Survey Setout
7144c113-46d7-596b-9d54-9b10611bd483 | note | ACTION (Hold, Monitor, Witness) - W
504afca7-5d28-5476-8605-4d039317ea25 | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
a730970f-7705-5c63-84a3-a6dd45b36a98 | note | Frequency - Prior to commencement
28f47454-07de-592c-b726-58f3528c4e6d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
a9535095-c4e2-5219-9f30-97c383244cc6 | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
95910492-aa8e-5704-84aa-34a53d57689f | note | Records - Approved Construction Drawing.
| checkpoint | 3 - Material Compliance
1de6bc03-a39f-5e40-a98c-7c07d46156b8 | note | ACTION (Hold, Monitor, Witness) - H
dc5ea69d-64a3-5798-8883-777a9672ac91 | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
7c41ca5d-b7fd-5d01-9890-1f620ca890b0 | note | Frequency - Prior to commencement
7400d344-5a39-5d82-8e22-93f7e7cb1009 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
e1f1f435-bca8-5ba5-b12b-a1ee4e0af043 | note | Conformance Criteria - TNZ M/23:2009
4c5d73f8-4012-5cfc-a61f-8592efebb882 | note | Records - Manufacturing certificates and delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Material Compliance
187d790b-47cb-596d-a198-927bba673fc2 | note | ACTION (Hold, Monitor, Witness) - M
06613769-514b-5562-9576-e997de19fc62 | note | Detail - All materials to be sourced from registered suppliers
1451a7f4-197a-55f9-8a4b-0f19b25e8798 | note | Frequency - Prior to commencement
89a0a243-45ea-576b-85a6-f1ddd6aa80de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6e4e0bcc-354d-53b1-897a-37172532e8db | note | Conformance Criteria - Registered suppliers
50dd5561-ed78-5e5c-b35c-f61928050176 | note | Records - Materials register
| checkpoint | 5 - Material Compliance
5dbe622d-7071-5dbd-a7fb-e06535b0105b | note | ACTION (Hold, Monitor, Witness) - H
d5622037-b6f3-5e86-8d06-60503c8bd0e2 | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
7cd29671-4771-58e0-a342-5f4ca2b5fe6a | note | Frequency - Prior to commencement
2f3785c8-5b5b-5944-ba4b-ec65a2eeb978 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
895b6383-1974-5552-adef-c8e534cc9245 | note | Conformance Criteria - Best practice
48387041-fc19-5901-82a0-f60fe2b42344 | note | Records - Approved / Signature
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Guardrail Installation
81bca486-28c0-5488-93c0-71e8559955cc | note | ACTION (Hold, Monitor, Witness) - M
d3f7622c-50c6-526b-8634-e60ce45e8a0d | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
2354c452-fac9-5e02-a655-5d4364dd4811 | note | Frequency - On Procurement of installer
dd2dab29-a83c-519d-85ad-602dac92a1a9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
64c1e163-318f-54d6-aca5-b3135734ba4d | note | Conformance Criteria - ASHTAS operative and installer course
ad32f265-36ea-5a32-878b-5372b6a0aa24 | note | Records - Attendance Certificate
| checkpoint | 7 - Guardrail Installation
d7748823-3fb3-5d76-b290-18d3496ccdb1 | note | ACTION (Hold, Monitor, Witness) - W
a4636cb8-d0d9-5d3d-b11d-697bee5ddbce | note | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
563b2e60-9713-5475-97f4-b32a029f0add | note | Frequency - During installation and on completion
b8e5a8f6-f9be-55a7-97fd-40429ab03259 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
5548a4ee-1f7b-5d7f-bed4-d08893a9c104 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
82cb35af-2f7c-5824-be58-98a071fec757 | note | Records - CS-4117 Guardrail Installation Checksheet
| checkpoint | 8 - Guardrail Installation
d58c5529-e050-5cd0-8b62-daedbc5a2913 | note | ACTION (Hold, Monitor, Witness) - M
3f5b6f11-7096-5c56-beed-0ff73897d113 | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
ba1501f6-67d0-520c-8ac8-5a5b83fc1ace | note | Frequency - During installation and on completion
1b550293-e414-5bfb-a39f-6d27fc6a9e26 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
efdf288b-53bc-56a4-9ba1-d6b9df8237b3 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
accc7b8e-d26c-5871-9206-ec81465d9961 | note | Records - Installation Checklist
| checkpoint | 9 - Guardrail Installation
e3847334-0311-59f8-aee2-a1b98704956f | note | ACTION (Hold, Monitor, Witness) - W
d4193ee1-9da5-5344-bc84-da08dff87eb5 | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
95ec324e-2a29-5287-a41d-782a30ad05df | note | Frequency - During installation and on completion
50ba4034-ed93-5670-810c-2fccac864637 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
081051d0-aed3-53ff-b27a-00c5f581fa0a | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
e7d8a766-36ce-5ea9-b2ff-4c0adfa8e529 | note | Records - Installation Checklist
| checkpoint | 10 - Fit for purpose Inspection
4b2dba2b-1e04-5918-b73f-3c291a4f8032 | note | ACTION (Hold, Monitor, Witness) - H
e5b6e777-3067-5a57-b43a-6a3dfaed1384 | note | Detail - Barrier to undergo fit for purpose inspection by competent person. System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM.
fab7481e-e2fa-5c85-9a45-8bf66e7b72a2 | note | Frequency - Prior to trafficking,
81ae9a3d-f56c-58c1-9037-2d275e25c4d8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
824fdb24-8ff0-57d1-9778-762e0981da75 | note | Conformance Criteria - Pass inspection
bcb8d528-3209-5489-a274-6e0ee6ade9d0 | note | Records - Confirmation from inspector
| signoff | AUTHORITY HOLDPOINT
| section | Final Inspection and Handover
| checkpoint | 11 - Quality Assurance deliverables
19fa0a23-d736-55db-a23c-7014f38121ec | note | ACTION (Hold, Monitor, Witness) - W
36648b68-29f7-566e-b53a-44423610372f | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
926c0adc-9a24-50c4-a4d2-c4c43ee66be3 | note | Frequency - At completion of Lot
3ba9d05c-4cb2-53ca-b9d5-17b1a4b38cb1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
237c8c65-8236-51b2-b2d5-927643e35a2c | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
1f1dd3b5-c5c0-5ce3-9883-ed9f11904e0b | note | Records - As-builts, CPS COR Report, NCR's and RFI's
| checkpoint | 12 - Completion Sign Off From Fields Below
781d06b1-13d8-5cd3-b2f7-8de786d574d6 | note | Records - Signatures
| checklist | ITP - E3002A - SH05 SIP Site 5a - Pavement Construction | itp | ITP - E3002A - SH05 SIP Site 5a - Pavement Construction |  | d3134165-423e-447f-83a0-9464e8829c1f
| section | 1 - Survey Setout
| checkpoint | Project Site reps.
c0515ac9-cd01-5a92-9e05-d3905d4b1ac9 | textbox | CPS Eng.
f91e604b-b660-5d16-938a-d8040501375e | textbox | Site Engineer
5f886a28-a60c-5bb5-b2b2-332bd5d3ac62 | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout
31691b3e-5ab0-5e74-8aba-47140c79c5f5 | note | ACTION (Hold, Monitor, Witness) - M
e5e21bc0-fc0e-5e2d-bb39-0da026cc3f13 | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
e5c4ab05-9dee-5b3e-ac37-dfa02a95893d | note | Frequency - Prior to commencement
cd2824ec-1240-540d-af26-be95e3031da9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
dfb80265-c343-5f26-8761-d7e58d85f6fe | note | Records - Survey receipt
| section | 2 - Material Compliance
| checkpoint | 2.1 - Sub Base Material Compliance
ebc9d69e-0196-5be6-a7f5-2bd39e807869 | note | ACTION (Hold, Monitor, Witness) - W
d2551835-3fe0-5e49-a8ef-dd140c31a336 | note | Detail - Aggregate material compliance for Sub Base stockpiles
ac2961bd-51a8-5eb2-8f16-2ce6dfe3d5f9 | note | Frequency - Prior to commencement
90fa0fa8-09ca-5ae3-943f-808bbcee341e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
49cfe294-df10-5d09-9d7a-3e3524d1891f | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC
57a69a95-ec21-5eaf-87dd-9cc8407072a6 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.2 - Base Course Material Compliance
40999254-4b48-59e2-ae5c-e67d26f2e78b | note | ACTION (Hold, Monitor, Witness) - W
566b2b1e-6cef-501e-ab53-70cf80e475fa | note | Detail - Aggregate material compliance for Base Course stockpiles
c7324156-c90b-5ba8-a928-b31602c71427 | note | Frequency - Prior to commencement
6e55217c-0140-51f7-b7a7-6593375473f4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
2976fe6a-7299-5308-b68b-707f8125fea1 | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
cc3f6a50-1499-5b81-8337-aadebc01710c | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.3 - Concrete Pipes
8a644a99-5055-5fc6-b8cc-68bad78c7ead | note | ACTION (Hold, Monitor, Witness) - W
ef3bf306-aa41-51ac-a3ee-d73802ddf096 | note | Detail - Specification Compliance
880d4e06-e386-5091-8e56-db5807498047 | note | Frequency - Each delivery to site
015b5296-f8f3-5ca3-b97d-98c81f2045c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
6a0603e8-2868-55cc-8273-742232ac470e | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
6492c547-d5ea-5659-b673-dbf70fc934c0 | note | Records - Delivery Dockets
| checkpoint | 2.4 - Pipe Bedding Material Compliance
b202d822-6037-5396-be74-ff6f65098a2e | note | ACTION (Hold, Monitor, Witness) - W
949e44df-b200-5477-be82-6b3ceeffe6e1 | note | Detail - Material to meet specifications dependant on material type selected
ac75e243-b1af-5159-90a8-471ceeca4930 | note | Frequency - Each material used
9b6d4ba0-737f-582b-83af-92b5d14ab7b8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3bfcd1a0-30ca-5e29-858d-09a0740ebece | note | Conformance Criteria - Compliance with requirements from Specifications
f92c15c7-6e62-566b-9d4f-bf5293177e9e | note | Records - Lab Test Report
| checkpoint | 2.5 - Pipe Backfill Compliance
a4edb0d5-89a7-59a0-bf37-8bc133481135 | note | ACTION (Hold, Monitor, Witness) - W
1091db44-008a-5719-9d8c-a72759491c0d | note | Detail - Material to meet specifications dependant on material type selected
c6d712d5-a278-5cb0-955e-3d902c053b88 | note | Frequency - Each material used
e0058b42-e656-5e94-8086-cc7ef1aef753 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
aa38a29c-67d0-573b-a271-4093fb63885d | note | Conformance Criteria - Comply with grading specification
a8842ce7-c31a-544b-8aff-ff99f47a0772 | note | Records - Lab Test Report
| checkpoint | 2.6 - Chip Seal design
7467503b-d98e-57d0-a974-b3106989e6b9 | note | ACTION (Hold, Monitor, Witness) - H
87557249-494b-5cf0-9000-3e1f0370774b | note | Detail - Seal design to be reviewed prior to sealing.
206398a5-5f44-5fe8-ab41-9943f4060d11 | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
af47fc05-934e-5b83-8e01-cdc3822784ae | note | Frequency - Prior to Sealing
20bd58c0-03d3-5526-b5e1-ae30fd1d8d5a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
31f833ec-b415-5e1c-a3af-8c0c5ff43ebc | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
dc755240-c491-5a6c-85d1-3d003e07c8a7 | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Sub Grade Construction
| checkpoint | 3.1 - Sub Grade Strength
00e2b83a-1a82-5ed5-a517-fdb04986273b | note | ACTION (Hold, Monitor, Witness) - H
b6184de0-ff22-5381-9813-d2aa2bceec41 | note | Detail - Determine Bearing strength of Sub Grade
0632bd81-0c35-5dd6-af05-8f59f7c7d296 | note | Frequency - After Dig out, every 10m
f2ffc15a-7ca4-55ca-b46e-d69809703aa4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
32fefad6-72ff-5c5a-b03f-f26eb7dc6fe7 | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
b852df96-5eed-5798-8990-203e6d1abaad | note | Records - QA measurement Sheet, CS-4000 1m Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Sub Grade Proof Roll
d9913091-3262-5aeb-b4e3-c4eae1cc0147 | note | ACTION (Hold, Monitor, Witness) - H
b079e331-1f24-5235-9ddd-2522c0a3dbb2 | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
33e5eb4a-6bc2-56a6-b0d8-d29694b5a98e | note | Frequency - Prior to Sub Base Construction
87eaeeb6-d93d-50e6-a847-b3a8fca3bfd7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4fe4276f-a3c9-5def-855d-0e109cba275a | note | Conformance Criteria - Engineers Acceptance
773a9a7f-fc94-51fb-a05c-c7294947191e | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Sub Grade Survey
f145ba22-289d-55e1-92d2-fd6fbab20f50 | note | ACTION (Hold, Monitor, Witness) - H
a5eb5e11-d509-59e3-a83e-dd977c84e1c6 | note | Detail - Survey the full subgrade surface
0e1fd4cf-276c-5a2e-9549-7091f70d157b | note | Frequency - Prior to Sub Base Construction
e650b860-7da3-57f2-afb4-879f13d4101f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
ec24b1fb-94ff-5c8c-8243-24ade08561db | note | Conformance Criteria - Whole surface
71c6c9db-7e1d-5ac9-a12e-38325e91a69a | note | Records - Survey Data
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Sub Base Construction
| checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
e556e9e0-588b-5521-9c58-c0e5c8574547 | note | ACTION (Hold, Monitor, Witness) - M
b9bc938c-352e-545d-994a-aa4a0ccf2727 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
33dce71a-7146-5b4f-bf2f-84bded2cb708 | note | Frequency - During construction
b6d076c7-ac71-5305-b0e2-e024ba737dc0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
723d4cf1-486e-5f0a-8e1d-d959aa2a92e1 | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
367304b3-18d0-5ee8-96aa-1bc8a2baa547 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 4.2 - Sub Base Material Contamination Checks
7401305d-1756-571b-9659-7541acddf194 | note | ACTION (Hold, Monitor, Witness) - M
1ebfcefa-5e3b-5b70-b09b-44972bbe9356 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
93e97a9b-be79-5844-945c-14899d9d2ccb | note | Frequency - During construction
3d9fc794-4e5a-504c-9541-7dfb64494cae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
ed4541e7-c592-5593-a88f-3b1eb919164f | note | Records - Photos
| checkpoint | 4.3 - Sub Base Compaction Lower
02cfbfe2-669e-5e6b-a7eb-46ddba96c01a | note | ACTION (Hold, Monitor, Witness) - H
86b4247a-d6f0-5ae4-8195-593fddcbaee7 | note | Detail - Degree of Compaction.
88793569-0fa5-5a93-bc84-dfc952238fc0 | note | ○ The subbase shall be constructed in two layers.
a6d0092c-e350-58b4-be9e-bb8771c90023 | note | ○ Lower subbase results must be approved before construction of upper layer.
b6d6d0bf-7410-591d-a039-e99a03f257f8 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
a8da3463-d166-5ff3-b3bd-ad7b585668d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
308eb868-458f-55e0-846c-dd08490c499d | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
da56c722-07fd-53ab-9054-294852f7aec0 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Sub Base Compaction Upper
aec03155-5b99-5cd7-bf06-5b17f6759395 | note | ACTION (Hold, Monitor, Witness) - H
a00c1bc3-9b77-5dea-a713-7f262249ebe4 | note | Detail - Degree of Compaction.
50ce0fc1-9bc8-55ff-bf12-f0630367ca3f | note | ○ The subbase shall be constructed in two layers.
49c00ea8-3be4-5cb7-83a3-62479f732f5a | note | ○ Upper subbase results must be approved before construction of basecourse.
c4e06f37-a7c9-54c5-9e7f-5ecbd7a1ccc3 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
9b573d6c-2507-5d21-8fa8-17be22161067 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
079793f0-1c75-5062-a9ce-8ada73718646 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
f75f9e1d-3f5c-541c-8b7c-38ba9e703a04 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Sub Base Trimmed Level Checks
21e2c2d1-73da-5f4d-91f6-96b2c250a61e | note | ACTION (Hold, Monitor, Witness) - H
5a678929-b811-5ea5-ab94-8659945bac9f | note | Detail - Carry out a Level Check on the trimmed Sub base
4b59b0b2-d3c0-5d5e-9c9b-1981fc4de32e | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
294cc88a-3724-5e3f-a77c-7f09b22943e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
a803e526-ba0e-5d44-bce6-3860496e2085 | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
e29ebbc1-53b1-53e7-a94d-36256558a259 | note | Records - QA measurement Sheet. CS-4100a Subbase Approval.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6 - Sub Base Survey
523cfb48-e08d-5246-ab02-05fff006c9d1 | note | ACTION (Hold, Monitor, Witness) - H
0ee95852-e174-56b4-af6a-64853065b087 | note | Detail - Survey top of Sub Base Surface
92a805cb-a26f-5f4f-b780-796984bab36f | note | Frequency - Random 10 spot checks per lot prior to basecourse construction
6620bd47-0411-544e-9376-c6bea7547b28 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
43368fcb-effa-58ec-b78f-880768b0eb93 | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
eb2a82c3-6838-577a-ac37-f971016fa659 | note | Records - Survey Data
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.7 - Saw cutting
7e3c2a8a-b508-539f-ab40-c84e567d787b | note | ACTION (Hold, Monitor, Witness) - H
67961899-296f-5e40-b36c-c84ebfcde902 | note | Detail - Proposed Sawcut line to be inspected by the engineer
5df8fddb-301d-5f48-a828-f918889a37bb | note | Frequency - During construction
d02128f4-2d42-5666-a53e-acfa33448cbc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3a2861e2-c3e4-5eb6-a4ce-2138e16bfb17 | note | Conformance Criteria - Project Specification 6.6
cf9f6146-303a-5d98-88e0-0c791291d544 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| section | 5 - Base Course Construction
| checkpoint | 5.1 - Base Course Aggregate Delivery Checks
fca1f198-1dd1-5492-86c7-6bfd35a6f92b | note | ACTION (Hold, Monitor, Witness) - M
dd0fa73e-0666-5fae-8327-8a6b5ddc7f6f | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
0eb76670-151b-5110-9ba9-494562735b4f | note | Frequency - During construction
822db8d1-8c50-581e-bcb7-f84076efab7a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
c8f1926e-d4c1-5d91-b54e-3165eb32fe2b | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
2702e6dd-1149-55c5-8227-28b690169b62 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 5.2 - Base Course Material Contamination Checks
af29ef3c-7958-5e55-945a-4e4712007468 | note | ACTION (Hold, Monitor, Witness) - M
384c0076-e091-5e91-9937-513e29620c54 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
230f181c-77b7-502f-97a7-d33543d784d5 | note | Frequency - During construction
221dea4c-d804-538b-9803-d207afd175c0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
fd8ce33d-70ef-5db9-b2da-210867fee991 | note | Records - Photos
| checkpoint | 5.3 - Base Course Compaction
6d24e34b-1d6c-5e74-8256-5b2f16a167a1 | note | ACTION (Hold, Monitor, Witness) - H
1f1bcfe6-4459-5a3f-9103-cab743c21bfd | note | Detail - Degree of Compaction
21d66408-1b4a-5790-a4b8-b7ee2ff1e48a | note | Frequency - 5 per Lot
204b6922-d41b-5ef7-b20a-994f053fe962 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
c21b90b0-379b-5de3-a9cd-525662dad646 | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
cfb60a08-85b9-597c-9cf8-df510efd8225 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Base Course Trimmed Level Checks
c0c4772a-30d2-5786-8fca-fd85f543e441 | note | ACTION (Hold, Monitor, Witness) - H
43cf6506-dd20-58a3-844f-07e22b3df447 | note | Detail - Carry out a Level Check on the trimmed Basecourse
266ce1da-8ffc-5517-bfa0-a4736e3ad9f8 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
f3c05036-d375-5a1d-a39b-4bee94d66e9a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
40f17334-b05c-5b33-b680-6d62771c2fe1 | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
61d75327-80d4-5c7d-9de2-feb2d74a839f | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Basecourse Survey
c8a6999a-9894-52a8-8a8a-8e3b006443ad | note | ACTION (Hold, Monitor, Witness) - H
5ded7299-cd63-5603-83fa-65fa643a4900 | note | Detail - Survey top of Basecourse Surface
fb7c1323-df80-5a30-80c2-f3e4ded35f71 | note | Frequency - Random 10 spot checks per lot prior to sealing
84015079-96d4-5661-8bd0-7eae461377ca | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
ae91cb3e-5c7a-5ead-9579-f4573cdc8810 | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
3bca6710-c54a-5a85-b524-ead310dcbe04 | note | Records - Survey Data
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Base Course Surface shape check
7452ba28-7890-51f0-b793-e21ce7300d37 | note | ACTION (Hold, Monitor, Witness) - H
2c6c357f-eb70-54ec-86aa-9fe96e38b44c | note | Detail - Surface shape check
8eb7c2a5-4e73-5d26-a482-75d91ea2d23f | note | Frequency - Prior to sealing
37a8d220-8ca5-5c5f-89b4-78aaa88342c0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
447d9740-581b-5025-bc7d-972fc9123862 | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
0cc2441d-8198-5e92-a484-76cbadaf449c | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 - Base Course Surface finish check
5c457520-044a-5aba-9f8d-6bf68f4afdb6 | note | ACTION (Hold, Monitor, Witness) - H
75c03d18-11f8-54d5-888f-1fcf6e8e5ec0 | note | Detail - Surface finish check
5e963668-0371-5671-bbbc-2ec8401f9721 | note | Frequency - Prior to sealing
53ef57bb-689c-5327-8542-5de122bdb0c9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
74e6452a-a530-5265-9718-023e4474e8e4 | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
ece140f8-4d95-5689-adc4-505dee74d03f | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | 6 - Extension of Culvert
| checkpoint | 6.1 - Foundation Compliance
bff08b5f-be51-5dfb-a714-0a705e15fd78 | note | ACTION (Hold, Monitor, Witness) - H
11e88e2c-aa7f-5d9c-967a-14a1c93894fe | note | Detail - Test formation level on completion of excavation to check if undercut required
8e4c7925-e38d-5832-a482-971cb78cf700 | note | Frequency - One test per 5 linear metres
3fc2af45-db57-58b4-8e37-ebb2f4e9f1ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
5875be77-5b92-5b31-8e60-64fb30e5dcf9 | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
a1707b6b-98ec-5f6b-8846-71ee759125b4 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Levels Compliance
540f36c9-264d-5a1a-8f60-b470dcce2151 | note | ACTION (Hold, Monitor, Witness) - H
cc6786d2-fb58-5a31-8c0f-4599f89e4414 | note | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
30b02e5c-53ee-51b0-bbb3-89b91a9f1197 | note | Frequency - As stated
6997ed46-3d2b-5364-be4e-41efd9f3fcc1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
b04104a4-6509-5ffb-bc06-c4e4061d5213 | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
2a8125d2-8f0f-5ac6-983d-35c29748bb3a | note | Records - Photos, Visual
| signoff | AUTHORITY HOLDPOINT
| section | 7 - Sealing
| checkpoint | 7.1 - Location/Size Confirmation
299efc87-332a-5579-b051-a6d4e622829a | note | ACTION (Hold, Monitor, Witness) - W
668e08d4-d4e6-5a90-8d46-aa49f8b329ec | note | Detail - Mark up extent of Chipseal
4f49f31a-d819-5eba-a856-8f78d0b85c37 | note | Frequency - Prior to Sealing
557cc8d6-68b6-5a13-9a43-f6f9d8f9a17f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
dd812849-bd3e-5a06-992e-6ca9cc78a094 | note | Records - Photos
| checkpoint | 7.2 - Surface Cleanliness
9f1e286d-2042-5951-a6bb-13cfab438b02 | note | ACTION (Hold, Monitor, Witness) - W
ad952383-30a2-5d0c-a3e7-3d1e81c1323f | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
486c0aa5-4ec4-523f-91ed-3e46171dacb5 | note | Frequency - Prior to application of binder
f3e13543-7372-56db-80b7-06c2c68a2966 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
dff662f1-d055-58be-85f2-948851ccd28e | note | Records - Photos
| checkpoint | 7.3 - Binder Application
99925b67-5405-5791-8d8f-48c06f6f0773 | note | ACTION (Hold, Monitor, Witness) - W
635af93a-957c-553b-ad53-606a2e0ba855 | note | Detail - Ensure the Binder application is according to the seal design
ba1e1de6-7cfe-5ddd-a088-387529e231ba | note | Frequency - During sealing
5c6807d8-c6d5-5cc6-88a4-e7bdb0d9e7c3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
283f3567-800f-5eaa-9e4c-4bf175eb709f | note | Conformance Criteria - According to seal design
a05099ba-a0f8-5e56-9087-9dddb177d3a9 | note | Records - Sealing sheet
| checkpoint | 7.4 - Chip Application
a1181e4d-9280-57f2-8de8-1feecab8caac | note | ACTION (Hold, Monitor, Witness) - W
f3ba3a97-8243-50dd-a275-8b03e1801cfd | note | Detail - Ensure the Chip application is according to the seal design
e56cc3fd-179c-5744-90e4-02bbeb98c416 | note | Frequency - During sealing
04d52846-3499-58a3-aa4a-a7ac6d73e805 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
677e396d-64af-56be-8db8-33493f60905c | note | Conformance Criteria - According to seal design
dfac4eaa-219b-5a10-8c86-96876a14d97d | note | Records - Sealing sheet
| checkpoint | 7.5 - Compaction
3a1f5f21-7699-523d-9176-f91383c2ec60 | note | ACTION (Hold, Monitor, Witness) - W
0a683a63-ccde-5209-91c4-0832ff144513 | note | Detail - At completion of rolling
daedaa82-33c0-5056-9c82-89d881cb1231 | note | Frequency - During sealing
752f8153-6549-5645-97fc-64114a77cdf2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
75f689c6-f774-5049-9a8d-0a24ed3768d2 | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
64d3021c-54c7-51e6-8af4-22b1a5ededc2 | note | Records - Photos, QA measurement Sheet
| checkpoint | 7.6 - Removal of excess chip
4939778b-d040-58a1-aef6-e4feb9424643 | note | ACTION (Hold, Monitor, Witness) - M
5245c22e-877f-5e32-9a53-68aac3633075 | note | Detail - Removal of excess chip
3571a5a0-05e2-500e-b153-924767928e1b | note | Frequency - Within 48 Hours of Sealing
10453f31-8cb6-5f76-b40a-3c3891ac4598 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
f94b027a-2d99-50a2-897b-bb69cb034374 | note | Conformance Criteria - Ensure all excess chip removed from site.
db556e63-31dd-55a2-b26d-cb2fc322123d | note | ○ No chip windrows left on site in Shoulders.
0ffd4905-0be0-53a4-9202-eb0ece7f4c0e | note | Records - Photos, Site logs
| checkpoint | 7.7 - Surface finish check
fa01dc67-5469-57b7-93da-b123a41d93ee | note | ACTION (Hold, Monitor, Witness) - H
4673f079-fd9c-515d-a5eb-f8c7136b0de7 | note | Detail - Surface finish check
e96c0cb2-3e1f-55c0-b424-d588f82f0250 | note | Frequency - After sealing
90be8435-33df-569d-934a-b9ee6f2e5883 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
9a12d256-3346-570e-853a-d398883b57ec | note | Conformance Criteria - Engineers Acceptance
b49f131e-cd42-5559-abbc-1e2854645486 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 8 - Road Marking
| checkpoint | 8.1 - Road Marking Setout
a6e5f3e8-1e71-5699-a8a1-85764320d781 | note | ACTION (Hold, Monitor, Witness) - H
c3a149f6-0f60-521f-a286-74633e9e853a | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
c1bda6b7-2a67-5edf-a24b-36d313097d7c | note | Frequency - Prior to the final line marking
e636f903-6a2b-55d5-a31b-9de439f8e40a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
b9106f7e-e093-5674-a589-c9405247e346 | note | Conformance Criteria - Engineers Acceptance
f8c7591c-4529-527d-bc88-34b0fd5fb162 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 9 - Hydroseeding
| checkpoint | 9.1 - Hydroseeding
0afdfca5-6835-5361-8881-aa8271ad7805 | note | ACTION (Hold, Monitor, Witness) - H
31060b99-997f-552c-8f7c-03bb68f20f16 | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
b6512bec-3bfb-5f7c-872e-3ea6714cda69 | note | Frequency - At the completion of the Lot of work
5a13e2e4-096e-5535-b788-ad934ba47dbf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
cdeff05b-5d19-5f3a-b779-920504b6a6cf | note | Conformance Criteria - Engineers Acceptance
535b567e-5bb6-5e5a-a8df-25f962985b6c | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 10 - Post-Construction Closeout
| checkpoint | 10.1 - Final Walkover (Snags)
2e3f7f01-5c03-5408-bf66-8f82e20c5ea1 | note | ACTION (Hold, Monitor, Witness) - H
8bc36f1d-4b9b-570e-995c-cf02828832f5 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
5bde4e6c-d9d5-5772-88b6-f62a76fb052b | note | Frequency - At the completion of the Lot of work
47520585-f5d9-5a7f-a53c-5b84be71a15e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
8e246fc9-f2af-5851-97a6-53c95183eaca | note | Conformance Criteria - Completed report
45325b4e-2cbb-5005-b7de-8150fbeeb743 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 - Survey As-builts
d97d78a8-d187-5418-a885-c6ad93f93d0f | note | ACTION (Hold, Monitor, Witness) - H
838e0cd9-52c3-52bd-b81b-10484900dd7f | note | Detail - Red pen mark-up drawings are to be included in the QA file.
85147e2d-3685-5791-ba07-d6d63ff99b21 | note | ○ A survey as-built of completed work must be provided
14ac0ad3-35f3-57ce-8beb-b681ffc55519 | note | Frequency - At the completion of the CWP of work
d5e15747-0744-5b90-9292-79c57b5a4223 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
8880a717-c1de-54c4-891c-209f0127659d | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
9828de73-baa2-50fd-9e14-0e312c061c81 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.3 - Quality Assurance Deliverables
168392f9-039b-5b8d-ae87-43eeff61e917 | note | ACTION (Hold, Monitor, Witness) - W
87dddae0-06f4-5b12-b4b5-06b8ddbc4fd9 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
763f6ec9-5ba4-5076-b6b5-2ffa46fa8614 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
978a4276-febf-51ec-ad0b-a47fa479cc8c | note | Frequency - At the completion of the CWP
c7cf75e2-168e-5831-ae2e-d22832559bda | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7de4c597-67ec-5944-9311-21d1fda21aad | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
f4d8f68a-cc04-539b-abbb-6ca38cd8e5cc | note | Records - As-builts, NCR's and RFI's
| checkpoint | 10.4 - Final Approvals
cf7432c4-8cd0-5ced-a533-2437d419665c | note | ACTION (Hold, Monitor, Witness) - H
e9ddb9d4-a71b-5cae-b4e4-a3a7d612679c | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
fcb92487-30a1-52dc-b826-e92cf90afabd | note | Frequency - At the completion of the CWP
bf65e1f8-a343-5cbf-9195-f944fc1c74b1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
dcba420f-f3db-5f49-b089-325a08e8ce57 | note | Conformance Criteria - Ensure all parties have signed and approved ITP
e8bd3cf7-6109-5ef4-a0fc-01e17cc7cc6a | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - E3002BCD - SH05 SIP Site 8, 9, 14 - Pavement incl Culvert Extn | itp | ITP - E3002BCD - SH05 SIP Site 8, 9, 14 - Pavement incl Culvert Extn |  | 357a2c98-2397-44f3-918f-f22648e6a289
| section | 1 - Survey Setout
| checkpoint | Project Site reps.
ee1a23ab-be67-5903-bc24-e8284093dd9a | textbox | CPS Eng.
049ae183-2464-5eab-80be-41cdf86abe99 | textbox | Site Engineer
f72edf6f-e992-5014-9b52-700cba73382c | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout
6907e981-f3b3-5827-bab9-77ccd121a351 | note | ACTION (Hold, Monitor, Witness) - M
2b8334d1-11ac-58c5-8b20-57a0b8522f95 | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
bba36c2d-c8a3-5c16-b107-cc15921a1105 | note | Frequency - Prior to commencement
f8cb683a-7434-525a-a342-e4901ab232ba | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
b22179ca-c017-55b4-9dd7-24efc4f2b359 | note | Conformance Criteria -
f5c7b5a5-4b4d-5aa7-a2f7-556d84dd389b | note | Records - Survey receipt
| section | 2 - Material Compliance
| checkpoint | 2.1 - Sub Base Material Compliance
ebd8efb4-d353-5b10-a415-30d70a4e5295 | note | ACTION (Hold, Monitor, Witness) - W
21e90c78-562b-55c6-bf4a-3bb6c2d9058f | note | Detail - Aggregate material compliance for Sub Base stockpiles
0a13351e-1764-5866-bc04-9d6fc69630ad | note | Frequency - Prior to commencement
1183c6c7-b369-5e88-a1d6-da5899e5e598 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
efbbe4f3-ad32-5fc2-99bb-2e35da8d26b4 | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
5c8e147e-e426-5905-ab0a-626874e5e00e | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.2 - Base Course Material Compliance
1bde9524-8530-50fc-90d8-af8b5994a252 | note | ACTION (Hold, Monitor, Witness) - W
dc99e203-3402-54ef-bb56-2d86229a81d4 | note | Detail - Aggregate material compliance for Base Course stockpiles
d7d7d756-9a72-59d9-8ba3-010ff6234ed9 | note | Frequency - Prior to commencement
28840db7-c199-5f5d-b0b2-3521057331a8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
18b05787-e1be-58b7-a350-fbb139dde46b | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
67038c9e-ecd2-5fec-afbe-d066ebca4144 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 2.3 - Concrete Pipes
4d67241f-c5ed-53a2-a4e1-18acd20fd265 | note | ACTION (Hold, Monitor, Witness) - W
c5a98c76-5c96-5edc-ab31-194c58f1fc6b | note | Detail - Specification Compliance
660a25cc-4e50-5440-bf34-65c05b86383b | note | Frequency - Each delivery to site
a331b3d8-f412-54dd-8e85-4c3b3e40f4a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
800ad4b9-710d-5940-9e8f-6ef7a006cee9 | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
40ca76c5-79e7-557e-a1d1-f17a12c297d9 | note | Records - Delivery Dockets
| checkpoint | 2.4 - Pipe Bedding Material Compliance
bc5fc9e6-a232-5b84-8db7-9f4cad716bea | note | ACTION (Hold, Monitor, Witness) - W
57f53d04-c4c6-59c9-95e3-365b6143d01b | note | Detail - Material to meet specifications dependant on material type selected
f155fe0c-2397-569c-9200-ed6b6e24f2cb | note | Frequency - Each material used
1dc122d4-ac9c-5898-b852-ac30c010fca3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
dd842495-c091-5c58-a89a-66da9e993834 | note | Conformance Criteria - Compliance with requirements from Specifications
a8e0f772-204f-5047-bb45-ec27b9531a77 | note | Records - Lab Test Report
| checkpoint | 2.5 - Pipe Backfill Compliance
7ccc4329-b0cd-5c7e-bbba-a4518ed13fad | note | ACTION (Hold, Monitor, Witness) - W
adeea588-acdb-57de-bfbf-3aa7a64df790 | note | Detail - Material to meet specifications dependant on material type selected
f98896eb-8040-5103-a973-9b5ff25ad186 | note | Frequency - Each material used
5dd2785d-35fd-5ac8-9e73-5a7b7b33678d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a991cb82-56e3-5e12-999f-5a6df3e5f4e0 | note | Conformance Criteria - Comply with grading specification
a95dc6db-073a-5656-bb49-c984560dd960 | note | Records - Lab Test Report
| checkpoint | 2.6 - Chip Seal design
da881361-2901-555c-a6af-cba67c88ac7a | note | ACTION (Hold, Monitor, Witness) - H
323bd58d-ea36-5815-bdf8-dbdccce6990c | note | Detail - Seal design to be reviewed prior to sealing.
0f7e9cd3-8a0a-5a27-b001-59458c31a94b | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
615392c4-eee9-50f6-86bb-6060f48670e4 | note | Frequency - Prior to Sealing
83344722-5f89-5691-9a9d-277a094dfb53 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
5f9c19e6-4abf-5689-8fbc-2749eedc9555 | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
70318b24-a9d3-56a4-ad66-34295c87ab1b | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Sub Grade Construction
| checkpoint | 3.1 - Sub Grade Strength
34b8c3bb-13b6-5bac-9515-c6b4ade94668 | note | ACTION (Hold, Monitor, Witness) - H
da69e99b-3bf4-5ca0-8d1a-26d69d6d59cd | note | Detail - Determine Bearing strength of Sub Grade
9e357a8b-19b9-55fd-b81d-4ced4050c871 | note | Frequency - After Dig out, every 10m
93f4970c-5c09-5e0c-aa53-fd080018c69c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
30b0ce7c-e3bc-561f-b19c-681f86fdaf5f | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
9eeb9138-e8be-590e-9511-82a7b7002369 | note | Records - QA measurement Sheet. CS-4000 1m Scala.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Sub Grade Proof Roll
55a7bb0a-1d70-547a-be2f-8703c72bb70d | note | ACTION (Hold, Monitor, Witness) - H
7ee34545-49a7-5c82-bef2-5f7996d61f4b | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
86050918-3c3e-532f-b5f3-9a15d281f9b8 | note | Frequency - Prior to Sub Base Construction
15c9e234-33a8-509f-a88c-5965b49e85f6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
54c7e2eb-7c09-5d2d-8e07-903f0c2aefa4 | note | Conformance Criteria - Engineers Acceptance
4b8e9266-ba67-5b15-88c7-db106add3320 | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Sub Grade Survey
00f81ab3-3f89-55ba-81de-694e90ec6558 | note | ACTION (Hold, Monitor, Witness) - H
f7d482b2-0971-57fb-b8ca-ec06cdd61474 | note | Detail - Survey the full subgrade surface
4417f2e8-a388-5095-9faf-78fa60bf1d24 | note | Frequency - Prior to Sub Base Construction
8f736763-3959-58bd-b856-a170c9f03740 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9733ce04-be94-57b4-a333-406b55f51d4c | note | Conformance Criteria - Whole surface
01bd8dfc-b632-5382-aeaa-704d0aeccc45 | note | Records - Survey Data
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Sub Base Construction
| checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
fcccd52b-c2d2-5fa9-a164-6d7beae2587b | note | ACTION (Hold, Monitor, Witness) - M
b91806ff-95bf-5343-b542-f3b76bb3e0a8 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
73ef0ada-6d62-52f3-b3e9-b370f576be8b | note | Frequency - During construction
f0a65ffb-76d4-5d98-92f6-bdcd0dd4ac6d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
ab712513-94fe-505d-87ea-466f4b3907d7 | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
2d4db383-bf2b-591a-acd3-ccd67953dd54 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 4.2 - Sub Base Material Contamination Checks
9e94ac90-a5f8-525b-ae85-9e4ab086159a | note | ACTION (Hold, Monitor, Witness) - M
ff395a41-f860-5016-b093-8b70bc326447 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
f307f898-4082-5d9d-b516-037341295567 | note | Frequency - During construction
acf24461-f075-5d63-a7a9-e4f5c8b650c6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4bab1501-73b1-506e-aff4-8bab3953d533 | note | Conformance Criteria -
c215c7cd-3c93-5869-9a9a-5a50324d2a8f | note | Records - Photos
| checkpoint | 4.3 - Sub Base Compaction Lower
99cfdeac-3783-59c7-8af0-7d0a845ca8f1 | note | ACTION (Hold, Monitor, Witness) - H
9cf1b763-3821-5cbf-8426-733672094838 | note | Detail - Degree of Compaction.
114fdc83-400d-52a9-a65d-35dd210551e9 | note | ○ The subbase shall be constructed in two layers.
86da690b-e12e-5158-8bee-836020efd3a4 | note | ○ Lower subbase results must be approved before construction of upper layer.
6acc21c5-db89-5e28-9be3-d3a9019b7e77 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
6cb8069b-0b80-5184-93d7-68621052b413 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
08cb37d7-910e-5bb5-8916-e1f20fa559a0 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
d7560041-56f4-5dd0-b4e8-aed07b59816e | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Sub Base Compaction Upper
49123423-1eab-5417-b67e-498db23c7fc8 | note | ACTION (Hold, Monitor, Witness) - H
e388c80e-7375-5e83-a866-29494ec011b5 | note | Detail - Degree of Compaction.
9fdd3dac-f5df-58c0-a9d4-8730bf5f2085 | note | ○ The subbase shall be constructed in two layers.
df31a700-1e3f-521a-936c-579a2a324cc2 | note | ○ Upper subbase results must be approved before construction of basecourse.
3cd1df53-7376-5bd5-8088-72996597522d | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
f6725cf2-608a-5390-8799-645e9121466a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
6cb6ba5b-e564-5a8a-a4c2-56416f37a8ca | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
43c754d0-c6af-5a75-88cc-a67a27e989bf | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Sub Base Trimmed Level Checks
816ede2f-c26e-5a45-a3be-e89f59529b2b | note | ACTION (Hold, Monitor, Witness) - H
f7ab4143-2643-54c0-b193-c40e3e10f7e9 | note | Detail - Carry out a Level Check on the trimmed Sub base
f745c0d3-8812-53b3-b879-6a8671a933da | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
b8609b23-a3bf-531a-9923-ad75ef8da29d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
30f94b38-8239-54c7-8a11-17effd63f5f7 | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
3ec2d75d-dc59-5a1e-a0a9-44f6091ea21b | note | Records - QA measurement Sheet. CS-4100a Subbase Approval.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6 - Sub Base Survey
3693b2a9-f1e2-5464-82e8-c9534560ee46 | note | ACTION (Hold, Monitor, Witness) - H
ea4aa0d3-6b07-516d-88f7-2f030bcdb19d | note | Detail - Survey top of Sub Base Surface
b64732f8-860e-5bf6-8f90-f34068ded6c7 | note | Frequency - Random 10 spot checks per lot prior to basecourse construction
61ad312e-5f72-5e6f-80b8-63137d5c5042 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
3bd8adeb-51fe-5143-9f90-73e4b0a7552a | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
733a0a2e-2c97-5184-bf7b-ce0afeddf960 | note | Records - Survey Data
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.7 - Saw cutting
26c9e0d2-86db-5302-9a18-3d34c468c9a4 | note | ACTION (Hold, Monitor, Witness) - H
1a665449-3f58-5cda-a185-f2007301ab86 | note | Detail - Proposed Sawcut line to be inspected by the engineer
af40aed8-dd44-5cfb-9648-8b531f94c633 | note | Frequency - During construction
081862c1-4d1f-523f-aee3-83200a4f1ef9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
90725048-da7d-54a2-b687-eded22eee762 | note | Conformance Criteria - Project Specification 6.6
5ed69861-fe04-5c37-8e96-f596e463a04a | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| section | 5 - Base Course Construction
| checkpoint | 5.1 - Base Course Aggregate Delivery Checks
93239102-d997-52af-87c2-409e4f2d5615 | note | ACTION (Hold, Monitor, Witness) - M
c108a4d3-b740-5129-9379-2faf6f0e6044 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
5bebeb0d-6485-5379-a986-b42b82fa2823 | note | Frequency - During construction
0c398cfb-109b-5e89-88a6-3fc241144ef7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
f17e7f54-d74c-5e8d-824e-06552f8ead13 | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
bce5d683-0271-5843-b11a-981368150dea | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 5.2 - Base Course Material Contamination Checks
d9226edb-acc6-5df5-b17c-e18bca50cc72 | note | ACTION (Hold, Monitor, Witness) - M
d7cd23c2-5272-568f-abd1-b1ad6bdf223d | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
95e414a9-37cc-5fc1-a497-7accd078d00d | note | Frequency - During construction
8a0399f0-a2c5-5464-8e0c-39d3ee57a7d0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
32ec1452-3e23-5dcf-87c5-194306d18f09 | note | Conformance Criteria -
a23a589e-3b67-5d70-ad50-677daef25432 | note | Records - Photos
| checkpoint | 5.3 - Base Course Compaction
45e35f09-d9a1-5345-9a2b-7737fec23b2b | note | ACTION (Hold, Monitor, Witness) - H
c59db112-277d-593f-95de-2b4add7aa71d | note | Detail - Degree of Compaction
63fd6d96-21a7-57cf-b480-88c529fa64d5 | note | Frequency - 5 per Lot
a65f56de-c045-5384-905d-cb9bf9ff9755 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
a0cbe965-c2c4-57d1-92d2-2327f6c8ebd9 | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
d489d04b-2db6-524f-a5c3-7fa7744f45ca | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Base Course Trimmed Level Checks
bb975718-5d5b-5da3-9121-7d251f72557d | note | ACTION (Hold, Monitor, Witness) - H
9fb63695-0f6b-5cc4-9501-992f81c93643 | note | Detail - Carry out a Level Check on the trimmed Basecourse
76eb1149-f51a-5a50-875f-38a97516393a | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
3d792ee5-384c-5574-b4e9-af39cd0d4dc0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
f92480b2-cfab-58a9-8021-c855602fdeeb | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
83f40c06-b08a-5f54-91fd-d63121416be5 | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Basecourse Survey
77e0b51b-79cd-5d45-83d6-2b89aa5edd51 | note | ACTION (Hold, Monitor, Witness) - H
9636f020-2f7f-51e4-aa67-89577e051792 | note | Detail - Survey top of Basecourse Surface
6326fe80-16d1-5742-871c-fed9995fd6f5 | note | Frequency - Random 10 spot checks per lot prior to sealing
d63f2498-0f53-5e3c-875c-5864ae8fe350 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
936953b8-8d56-592a-b616-8c538db255d2 | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
40337637-81de-5853-a2c7-c2ce357a591a | note | Records - Survey Data
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Base Course Surface shape check
504720de-e082-5b80-be9f-a9b84b832f3c | note | ACTION (Hold, Monitor, Witness) - H
f713eaf5-b684-5659-8f88-7f693cae893c | note | Detail - Surface shape check
af385aeb-a6c7-50e0-9fae-9693fc20518b | note | Frequency - Prior to sealing
7d7c02a1-83d9-5e13-b6c9-ebd62d5d8b55 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
7db9f6d9-c9ad-5443-a4f2-eb641424d62f | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
a9921015-5b82-5486-9e95-2a14045136dc | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 - Base Course Surface finish check
04c58ee6-3c67-5700-a5d2-753edd46e395 | note | ACTION (Hold, Monitor, Witness) - H
adf9503f-020f-5704-8017-d0a16186eff4 | note | Detail - Surface finish check
9e2a5d25-6576-519d-9e18-bf313b648f6c | note | Frequency - Prior to sealing
9568bb22-7517-5598-9a62-058d4ac90534 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
2cb16601-bbb5-53c7-99fb-ce05ec09bc46 | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
326a59da-13e3-5202-bd0d-d62cffe1c770 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | 6 - Extension of Culvert
| checkpoint | 6.1 - Foundation Compliance
6e3d8503-f3d7-5e92-b182-24570e9abdc0 | note | ACTION (Hold, Monitor, Witness) - H
f730a8cd-c5f7-5257-acaf-77da46221440 | note | Detail - Test formation level on completion of excavation to check if undercut required
b8edf7f1-8201-5468-8cc1-5be4cbe7c60c | note | Frequency - One test per 5 linear metres
3e6ae74f-2c49-51c1-9da0-f2eacfc94179 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
2107d4b6-bec4-5273-b60d-152a282847ee | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
45e2ed68-c56e-5651-88dc-dbb5f0dff581 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Levels Compliance
0af6b545-3fb1-51ef-936a-b112510cf956 | note | ACTION (Hold, Monitor, Witness) - H
8bd6ea7d-5026-59f9-8c4e-3376ecd2dcd1 | note | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
7a833145-ab37-52ec-8225-02b4a262a970 | note | Frequency - As stated
07653e10-3355-5f7f-961f-83b1d199c98f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
6c1a2400-f15f-5743-b766-ccfeb298d091 | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
3aeecaad-c9d3-5361-93c1-acd0d7126130 | note | Records - Photos, Visual
| signoff | AUTHORITY HOLDPOINT
| section | 7 - Sealing
| checkpoint | 7.1 - Location/Size Confirmation
1a53d99b-6abc-54b0-98be-278a98805bfb | note | ACTION (Hold, Monitor, Witness) - W
3b3aa8af-c6d5-5b1b-a9d3-1253faf77784 | note | Detail - Mark up extent of Chipseal
a2bb04ca-c742-542a-8a38-4aa8a834dfed | note | Frequency - Prior to Sealing
86aa64ca-bfe7-5cc1-a6d4-76fab9bb93e7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
a61c251e-c9e6-5b8a-8d76-cce119f7e375 | note | Conformance Criteria -
ace594a4-41f3-5d0d-8cc3-108fb228bd7a | note | Records - Photos
| checkpoint | 7.2 - Surface Cleanliness
94dc2f32-1287-5c52-9ad4-93fbf4d3ed79 | note | ACTION (Hold, Monitor, Witness) - W
74fb5c53-1c3d-5cc7-8014-266c1f42dfe3 | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
e8a74dd4-f1d9-55f2-97c3-5e4ea6cc3a92 | note | Frequency - Prior to application of binder
d8d88610-966d-54c9-86e8-e3224394b90f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
1efc0f68-e461-5e3a-abdf-0266cfa91d34 | note | Conformance Criteria -
2e214aa0-eabb-5629-9e25-d639ddd2f464 | note | Records - Photos
| checkpoint | 7.3 - Binder Application
8b149d88-bfda-54ef-9350-56f3bfbf0bba | note | ACTION (Hold, Monitor, Witness) - W
e9ea2939-76be-5e22-a5c0-e3b546648e96 | note | Detail - Ensure the Binder application is according to the seal design
a54f4f33-522d-5668-8652-a6b8b6948541 | note | Frequency - During sealing
9416a6d7-975a-5ced-a28b-1987d8e6ad67 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
bb70fffe-cdfc-51d3-8005-efcc79819a76 | note | Conformance Criteria - According to seal design
a7d45692-cc96-5395-9b96-062f50ebb570 | note | Records - Sealing sheet
| checkpoint | 7.4 - Chip Application
9b11cc38-c96f-5b81-820a-6fd289d83106 | note | ACTION (Hold, Monitor, Witness) - W
34287822-3160-57e5-a13c-086c78b6c6ba | note | Detail - Ensure the Chip application is according to the seal design
8c26174c-f9e7-5b73-a7de-9b31787873cb | note | Frequency - During sealing
917b977d-af4b-5f8e-9532-51867a8a4816 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
b39cd932-cda0-547c-818d-e4402f8b7188 | note | Conformance Criteria - According to seal design
9d997e6a-cf1b-533d-b067-0adfb8be6be3 | note | Records - Sealing sheet
| checkpoint | 7.5 - Compaction
0ce37c26-7fd3-5510-bfef-a6695b19d120 | note | ACTION (Hold, Monitor, Witness) - W
5c21d8be-eb8b-5cec-bcdf-616af17bc4a4 | note | Detail - At completion of rolling
5d33128b-ed1d-50ce-9cee-f1c324ce732e | note | Frequency - During sealing
eaf77675-fe38-537e-9651-28a92e13704a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
eb38c069-4352-5aed-bd8c-a5200e78c61d | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
117cd5fe-f125-5eb9-be00-f4417689bfd7 | note | Records - Photos, QA measurement Sheet
| checkpoint | 7.6 - Removal of excess chip
3eb7fa2e-9ecc-5a7c-b8c1-fcafdad81a72 | note | ACTION (Hold, Monitor, Witness) - M
0f4594aa-c6ff-5c06-80b4-20685bba1382 | note | Detail - Removal of excess chip
ca19b25a-171a-5945-9af1-6f9d577e7583 | note | Frequency - Within 48 Hours of Sealing
e2c0b5fe-5132-58c9-be4e-76c780bc88d0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
e513ffab-aea7-52a7-ac4b-3c33ce962f65 | note | Conformance Criteria - Ensure all excess chip removed from site.
7ddef8d5-6a99-5935-8d50-2468de38e793 | note | ○ No chip windrows left on site in Shoulders.
f8489c8f-c44a-51c2-8b18-a6c2a6b3369c | note | Records - Photos, Site logs
| checkpoint | 7.7 - Surface finish check
b670f9c0-1817-559b-8a43-de9e6ce9187c | note | ACTION (Hold, Monitor, Witness) - H
5eb0bf35-96d0-5c78-afc1-eedca6a6e3ee | note | Detail - Surface finish check
27f99051-be39-5355-b4f8-47691953520f | note | Frequency - After sealing
58a7d7de-b14c-5468-baf7-d1d9ef0fc440 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
c97cf200-68f1-5972-8375-589815bea978 | note | Conformance Criteria - Engineers Acceptance
69be2015-d683-5898-b155-d80d39dff986 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 8 - Road Marking
| checkpoint | 8.1 - Road Marking Setout
8c90febb-fe67-569c-aaf7-0d18a935fe36 | note | ACTION (Hold, Monitor, Witness) - H
c59e6f5a-4c20-5526-a8a8-63cc7fef22ed | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
fcbaf42b-ac2c-5f43-8f4f-15a9e2de3f6a | note | Frequency - Prior to the final line marking
b77e6afc-d19a-59c6-8749-53289b675c20 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
85afebef-a1f1-5440-a67d-aae08789d5ad | note | Conformance Criteria - Engineers Acceptance
afae688c-b8a0-575d-aae8-1718bff383ad | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 9 - Hydroseeding
| checkpoint | 9.1 - Hydroseeding
23ea6780-27f1-5ebb-b951-36c41bee4158 | note | ACTION (Hold, Monitor, Witness) - H
28d0ff9a-ac29-58c7-8dd0-82810c03e137 | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
20b802ff-471e-5a2d-a6e2-3a7b790ea037 | note | Frequency - At the completion of the Lot of work
89217211-9d98-5cdf-98e9-4abb1e3b7d33 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
29a7e17e-34a3-5e6f-a96b-e6ab718585c1 | note | Conformance Criteria - Engineers Acceptance
37294cf9-d883-5ad7-99c3-0c4fb6dd1d5d | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 10 - Post-Construction Closeout
| checkpoint | 10.1 - Final Walkover (Snags)
f7a5fba1-11c1-58dd-a329-252c4e5e130c | note | ACTION (Hold, Monitor, Witness) - H
1a334285-657b-532f-a9ed-c47451c140f9 | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
26821f9b-b139-5d3f-900c-eaa7f3c4870a | note | Frequency - At the completion of the Lot of work
e98605ec-7db6-58a6-a46b-17d2990021d8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
71d903ea-30ab-5c66-9b0b-5d4f62041f46 | note | Conformance Criteria - Completed report
2c2f5e2d-a027-5027-bee9-e0d130c9e075 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 - Survey As-builts
a351bc08-4bf6-5e2e-bf81-25bc7dd27bb4 | note | ACTION (Hold, Monitor, Witness) - H
b0766f34-2f92-50d5-be43-bba48a01b5e4 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
0adaced8-2375-58cd-8b7a-349a9f15a046 | note | ○ A survey as-built of completed work must be provided.
492405e9-33c1-535c-97ae-1ea289815e18 | note | Frequency - At the completion of the CWP of work
3f8cb4d5-c539-5703-a6c4-9e845fc893ae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
c4106abe-74cb-558a-8d17-4c2945591979 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
7d238d6d-ba63-5f0a-952e-fbaf6bc5a606 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.3 - Quality Assurance Deliverables
5b9d8a97-8ef0-5986-a5f5-ff14aa1d672f | note | ACTION (Hold, Monitor, Witness) - W
70d71417-04aa-58a3-aa54-bf3a26d20794 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
2b92b5e5-5329-5b65-940d-2d86805f200f | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
533af868-5e5c-5782-bc04-ef875b8c2668 | note | Frequency - At the completion of the CWP
8bb1e7f0-e2be-55ff-9b4c-ae300e453b06 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
db3c18bf-e476-535f-8d12-320f58357966 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
e59d771c-b02c-583d-978e-1955faae53bc | note | Records - As-builts, NCR's and RFI's
| checkpoint | 10.4 - Final Approvals
b172694f-09b0-57c4-ab3b-54fca8255ada | note | ACTION (Hold, Monitor, Witness) - H
4611bc21-1431-54b8-bdef-2052bd85dd23 | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
1b21e170-d6ab-569b-b9e9-d05f0634a862 | note | Frequency - At the completion of the CWP
f5ee7300-606e-5f3b-bf38-b486bde184d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
77052014-943f-5b16-a302-038a22eb059a | note | Conformance Criteria - Ensure all parties have signed and approved ITP
f33ee95f-a61b-52b9-a7dc-428266e147ce | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - F2501A-ID460 - D9 Gully Underslip | itp | ITP - F2501A-ID460 - D9 Gully Underslip |  | ea7851d6-da70-4bfc-9305-881dc286549d
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
79593a82-6448-5d46-b205-71bd59a3579c | textbox | CPS Eng.
01e04ef5-326a-5945-a46e-cb58253be3ec | textbox | Site Engineer
ac7b8a5e-e585-5aec-81d7-92c42fcf1c0b | textbox | Quality Eng.
| checkpoint | 1.1 - Bulk Fill (GAP65/GAP100) or similar
bcb67f85-629b-520a-be24-f6f1058685cf | note | ACTION (Hold, Monitor, Witness) - H
fe9e16ee-170e-5359-84f9-4c26c67c261a | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
c539ee73-fdea-58a6-91f7-53d5f03cd825 | note | Frequency - Prior to commencement
6fcd712e-aed7-5aa4-9890-19c4b56012f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
0f4c5072-770c-5f4c-8c88-23715d455047 | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
f579305d-05ac-5694-bc38-a38be4091561 | note | ○ Material source testing
7d7e07b9-cc4e-5ab0-9113-dba528a805d9 | note | Records - Material source test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Class C A29 Geotextile
4c500886-5616-5b29-976a-d3aacbddb01e | note | ACTION (Hold, Monitor, Witness) - W
e0c315de-bc5d-5543-8e18-a15fc27ab028 | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
43642500-6938-5f58-a160-4b3a0cafde76 | note | Frequency - Prior to commencement
a9f5922c-67b7-5ee5-a214-397cd805eb16 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
14bac9b2-4c87-51d1-a779-01552fdef079 | note | Conformance Criteria - before placing foundation material and engineered hardfill
d014664b-0401-5ecc-8dac-922b3ad09325 | note | Records - Material certificate(s)
| checkpoint | 1.3 - Drainage blanket (AP65 or approved material)
ae50977b-48b5-53e6-bea4-34594cbee6f3 | note | ACTION (Hold, Monitor, Witness) - W
1b15d9d5-6728-5e3a-82af-3d1934918afb | note | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
5ea96361-ecc0-511c-bef2-0a9537e633de | note | Frequency - Prior to commencement
4421785c-aff0-59d1-84ab-e4cceaa94348 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
6b65e326-76b2-5f94-9519-e05c5023bd1b | note | Conformance Criteria - Material source testing
8bbf3199-c1a9-55fa-bb08-04e5b67b8652 | note | Records - Material source test results
| checkpoint | 1.4 - AP40 (Basecourse)
db955d16-530f-5033-bb73-3ba5d7d9ec87 | note | ACTION (Hold, Monitor, Witness) - W
d67c5092-8886-5b43-bce2-0a762b2ab1cc | note | Specification/Drawings Reference - TNZ M/4
6516e45a-47e3-50f2-a473-3d0d6dabf48e | note | Frequency - Prior to commencement
38db5660-763b-50e2-9150-5243df5ec6b4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
edc5f169-9d2a-540c-ab69-a46856913203 | note | Conformance Criteria - Source property testing
5ddeefa7-c627-57b7-aea4-0338ff90370f | note | ○ Traceability of all materials delivered to site
7d6bfcff-92f0-55c4-b320-370313f60779 | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.5 - Geogrid/Geotextile
5087926f-22fa-5886-9af8-158002c0b4d5 | note | ACTION (Hold, Monitor, Witness) - W
2bee1034-712b-5ab8-a60a-8eab9830f192 | note | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
331c4260-a241-5438-96f3-2da77be6a2e8 | note | Frequency - Prior to commencement
270dd5c2-5d7d-5deb-96c8-ffdc7881f80f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
22bbd409-6751-5b54-be4f-cfde360aa6d7 | note | Conformance Criteria - Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings.
8f32d773-4854-5412-8e27-a1b0dca57d5f | note | Records - Delivery docket
| checkpoint | 1.6 - AP65 (Sub-base)
227972cb-05a4-51c9-9132-3d87759fd795 | note | ACTION (Hold, Monitor, Witness) - W
39febf7b-c108-594c-a7a1-517ee9f5cac1 | note | Frequency - Prior to commencement
d58843af-8ce8-52fc-b1a0-868f1dfd2b75 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
967bcda7-1cae-520e-9cf7-3175b92323e7 | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
f2656b2f-95ff-5446-a54f-da75a24f5e48 | note | Records - Lab test reports
| checkpoint | 1.7 - Grade 3/5 Chip
8bce78bc-f43f-53a8-8b4b-8a0671dac7e7 | note | ACTION (Hold, Monitor, Witness) - W
59003c17-3df4-5a68-a855-d1a09e0ef497 | note | Specification/Drawings Reference - NZTA M/6
f9695cb1-cd9f-5964-9b39-e559087f0019 | note | Frequency - Prior to commencement
d56ad5d0-0b14-54e8-a439-d1891be9a568 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
f84a7e55-5aaf-5b19-b7d5-b311115ad8f5 | note | Conformance Criteria - Source property testing
9d0d42f4-9fc8-57a9-9e6a-ae5fafcf58a5 | note | ○ Traceability of all materials delivered to site
b0bcf333-65b9-5300-9072-355e6b018a47 | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.8 - Cement Material cert
b760c934-7c79-59c7-a0ba-80421ca47a27 | note | ACTION (Hold, Monitor, Witness) - W
8ca3e3fb-1151-5f5a-9632-28c9805f1eed | note | Frequency - Prior to commencement
1eec91ba-4606-531c-94dc-9af3cca4e507 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
17825815-1b52-5bde-9814-63d545f42e3b | note | Records - Material certificate(s)
| checkpoint | 1.9 - Enkamat 7018 (or similar approved)
3b904bdf-eb85-535b-8bd1-3400ebecefc5 | note | ACTION (Hold, Monitor, Witness) - W
47481378-eed6-5923-b02b-6d4445be0a7b | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
1be117b7-47fa-5c8d-80bd-978e8022b6be | note | Frequency - Prior to commencement
b8ba4485-948b-525c-83f9-679b8da73fe0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
42159eca-19cc-5372-847d-eaa229f3dbde | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
8056458e-7321-5f77-93a2-dd6b27f832c6 | note | Records - Material certificate(s)
| checkpoint | 1.10 - Bitumen
bb6c50a2-8c6d-5a17-86f5-b64b308f3baa | note | ACTION (Hold, Monitor, Witness) - W
02c58db7-20e9-5b2a-8dfd-6c121f6b55a9 | note | Specification/Drawings Reference - TNZ M/1
fb8a00c4-c65a-547a-8a73-b89697719028 | note | Frequency - Prior to commencement
d4a10c1b-465c-51c5-8f1b-6a9e35867c1f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4537019d-9d09-5e63-98c6-82fb74670b97 | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
3a2080b0-1a48-5a98-8b0d-2f15053cc0db | note | Records - E2 Certificate
| section | Section 2: IN PROGRESS INSPECTIONS
| checkpoint | 2.1 - Survey Setout
fed335ca-2fb2-57f5-9ba3-05258d726d33 | note | ACTION (Hold, Monitor, Witness) - H
fec84958-d488-59d4-a621-29c9a1adadfe | note | Specification/Drawings Reference - Consistency with Construction Drawing
135751a0-9515-5ab1-9035-50d5f5d044f8 | note | Frequency - Prior to commencement
4ee333a7-6172-5abd-b9a2-b54c05d61e38 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
4d0fb0e6-e8f4-54fa-9f97-858f0ca82c48 | note | Conformance Criteria - Set out extents of fill and check against design drawings. Subcontractor to arrange survey
235115d2-6cc9-506e-bc89-0c5c29fe601a | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of fence & loose debris
12622f30-4f31-5ed1-b993-f7884c69f31b | note | ACTION (Hold, Monitor, Witness) - W
925f365f-affb-530a-ada0-0d5c398125fa | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
aec5c7a4-bda9-5dd7-9907-d82fc8a1be6b | note | Frequency - Prior to commencement
eacb7928-830a-5ac5-a020-fd3b88d0ff0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
61a105e9-4953-550f-b2a2-eafab87e1e36 | note | Conformance Criteria - Remove and clear the vegetation & fence
37cfa2b6-8ac8-555c-9b1c-edfdd7c929be | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Inspection
d2441fb0-dc63-529a-886f-312c76ab514c | note | ACTION (Hold, Monitor, Witness) - H
7757c630-0b06-5668-9e79-a598f796ef50 | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
8e22e228-7461-5d3a-8d2c-2eede1a5f655 | note | Frequency - Per area as required
dd79439d-0887-5e8e-9bf4-298b38e9ce78 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
edf6ad55-4e22-59ce-af55-fd879a4a37e3 | note | Conformance Criteria - Inspect fill foundation.
1b8caa08-a737-5c44-8963-5584239d1bf9 | note | ○ Fill foundation must be approved, in writing, before filling commences
69877691-9f0e-5786-81ac-cf8ba35bc7d6 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Ground Improvements
fa04603d-f016-5057-9ec4-c780ad9ec62f | note | ACTION (Hold, Monitor, Witness) - H
4a912f19-7b87-52a6-ae60-470cc5212802 | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
5f3ba6cd-41c5-50e5-920e-1639285dc9d4 | note | Frequency - Prior to commencement
ed2be660-d149-55b8-8c52-77ef3f4bfed6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d6630ae5-be22-59a2-be41-0b1db21f8b2c | note | Conformance Criteria - Any area that requires Ground Improvements (i.e undercut) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence
78de86dc-1dbf-57aa-adf5-8cd0be83a5ad | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Class C (A29) Geotextile installation on the excavated face
1651861b-4001-5b06-b460-372bd498c97f | note | ACTION (Hold, Monitor, Witness) - H
5b302b67-3052-5212-8c18-97dcb1709a5a | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
0674e93a-1649-5495-8096-085548e4b314 | note | Frequency - During Construction
0d97242b-2ebc-56a2-8b84-77ed08830f06 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
988141c7-4924-5e22-a6d5-46234b8a8b4a | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A29 or similar approved before placing drainage gravel material & and engineered fill.
117fa03e-21af-5c4e-836a-478a69abf908 | note | Records - Photo's, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Drainage blanket/material installation (AP65 or approved material)
bfc8d66c-dbc9-560d-b9a3-8fbfd9413b92 | note | ACTION (Hold, Monitor, Witness) - H
3ef5a68c-c334-5ebb-895c-b5038ae6b828 | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
535676e3-f95b-568d-af47-4ea28b980296 | note | Frequency - During Construction
e0a30c31-9648-5655-b56d-3f037177d807 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
842b2411-9e44-5870-8a9a-63970c0c246b | note | Conformance Criteria - CPS Engineer to assess suitable drainage location & extent.
ff9a4beb-f08c-5a09-b1ae-5db6bbeefced | note | Records - Photo's, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Bulk Fill placement
95d86604-376b-54cf-a089-95c165cdcbd4 | note | ACTION (Hold, Monitor, Witness) - M
1fbbc4c1-bda7-5b05-8437-f32f459931c6 | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003, NZS4431:2022, NZS 4402:1986
63df2b6c-6b19-58a0-a115-784432abe101 | note | Frequency - During Construction
e668654d-10f4-5040-ace3-18a350956ca3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b4a611ed-f6ac-5598-b0c7-f5b63109663d | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022.
de6517cb-f789-591d-8937-1a927fdf03c0 | note | ○ Fill should be placed on dry subgrade.
2e8e4eac-8c06-5ffa-9e3f-c2fbfdd82ea5 | note | Records - Bulk Fill Earthworks checksheet (CS-4100), Photo's
| checkpoint | 2.8 - Placement of Geogrid/Geofabric
04114585-6c9e-5dfb-b713-d70916c25663 | note | ACTION (Hold, Monitor, Witness) - H
3592ddb2-7c38-5de7-b170-1880020b8045 | note | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
03f7d541-056d-5b7a-b9a3-a14bde184424 | note | Frequency - Prior to backfill
cbff8ebb-b055-56dc-b723-0f6370431c99 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
17123964-02ce-5126-993d-858c8c2574de | note | Conformance Criteria - Placement to be sighted & approved by CPS Engineer
801eabec-74a9-5a74-97cc-23ff51d36892 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.9 - Cutting of Geogrid/Geotextile
05d72e18-f01a-5ee6-a623-5e07a1aefa48 | note | ACTION (Hold, Monitor, Witness) - W
90b5a91b-f859-574c-bba6-396cb3387d2a | note | Specification/Drawings Reference - Cuts shall be limited to 0.5m and only made along the weak axis.
243d461c-f49d-5ad9-9967-1650d29c8840 | note | Frequency - Prior to backfill
f121fd78-3d25-5cb0-8d3b-f2e3a48b6247 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
3b66f0f7-7ebf-5ab3-bdf2-b311658564e0 | note | Conformance Criteria - Geotextile/Geogrid cuts shall be undertaken if pre-approved and inspected by Engineer as per photographic evidence
33c8c425-b18a-595e-9dad-8fae4ad50ce1 | note | Records - Photo's
| checkpoint | 2.10 - Bulk Fill Compaction
ead58b58-f430-5654-8b50-f6beb00c975c | note | ACTION (Hold, Monitor, Witness) - H
5a97d800-e7ed-513f-b466-55018741c01f | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
9def9c38-a0c8-5dc9-b054-40752c035ee3 | note | Frequency - During Construction
915cbc55-5f00-583f-9234-7b44754adb89 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
9a80b594-7d73-58c1-b36e-0b643cf85b2e | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3.
cd412b59-bf03-58e6-90b2-a97923c79625 | note | ○ Completed and signed COR per 1000m2 with a minimum of 3 checksheets for area covered. Scala results to determine CBR and required lap widths.
631d2ae5-0768-5588-8ff5-7ca009071252 | note | Records - Compaction test reports, 1M Scala check sheet (CS-4000)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Form and cut fill batter as per design 2H:1V
48f61314-2d14-555d-b731-2f50cf672017 | note | ACTION (Hold, Monitor, Witness) - H
f9d0de3e-f8ef-5c7e-bf02-aa84dfe3b61a | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
f22a816f-62ee-5e2b-8b64-cffb8a87c7b7 | note | Frequency - During Construction
3ad72981-69a4-584a-b437-ca37c46d31de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
6d9b05a9-c19f-55ea-9def-0ab10f15af45 | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
27757f25-8903-58ea-8bd0-c44a27d02143 | note | ○ Slope angle of buttress is to not exceed 2H:1V
41950e0c-a575-5761-8378-48ead053fe82 | note | Records - Survey as builts
| signoff | AUTHORITY HOLDPOINT
| section | Section 3: IN PROGRESS INSPECTIONS (Pavement)
| checkpoint | 3.1 - Saw cut existing pavement
6db4c396-b249-5d16-ab08-10a89d828133 | note | ACTION (Hold, Monitor, Witness) - W
25c3e3e4-6184-5aa4-ac7f-cae00deed48b | note | Frequency - Prior to pavement construction
46ab9f68-4326-5489-9331-ad18af2570fb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
1d673398-6eee-5c92-97ec-c24677ad0e0e | note | Conformance Criteria - Smooth and straight saw cut
6485a148-e986-55e1-9fae-53ee0be7d9c3 | note | Records - Photo's
| checkpoint | 3.2 - Subgrade construction
56e4574e-bbef-5e30-8ce7-d08184401867 | note | ACTION (Hold, Monitor, Witness) - W
436c6663-04c7-56e3-9747-c19bfca875ea | note | Specification/Drawings Reference - TNZ B2
8b4eebce-ae02-5923-ab98-0eca2a615a7b | note | Frequency - Every 20m
ac9027de-0253-5400-a073-92f54e48de77 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
76332d06-b763-5ea4-8e9a-dc83857817eb | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
1d2cefc9-8218-5800-ba6e-a220e126870a | note | Records - Test reports
| checkpoint | 3.3 - Subgrade Cement Application rate
a5173348-18bd-5b35-abd8-beda3d7c1477 | note | ACTION (Hold, Monitor, Witness) - W
869e0d7f-fbd1-5971-ac55-bbe1b68feb4b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
6a876534-c63e-50ce-a744-d9c2c6b95990 | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
4303f717-6eb6-5135-846a-9cc287020a9a | note | Records - Bag test records
| checkpoint | 3.4 - Sub-base construction
19ebaf4d-f805-5bcd-9f1a-05f822e7964d | note | ACTION (Hold, Monitor, Witness) - W
ba9072dc-3ec3-5132-b6c1-1d2bde7690d2 | note | Specification/Drawings Reference - TNZ B2
1f3d5e69-cedb-5aad-9b9c-a43d42b2d2ba | note | Frequency - Every 20m
02d7a108-8b3a-5f8c-a577-53542755fd84 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
da506688-dda7-5faf-9a79-f8d8941deb23 | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
8ccc9012-65b2-5e62-adf5-32bba0970cfd | note | ○ Average 95% of MDD with nothing less than 92%
3b9966b8-8218-5a82-9f47-b012bd4b2693 | note | Records - Test reports
| checkpoint | 3.5 - Sub-base construction
bcbcc9bd-ba42-59ef-b1cd-544d94de33fb | note | ACTION (Hold, Monitor, Witness) - W
dcad67dd-4f6b-5466-9b30-8fc5ca480f49 | note | Specification/Drawings Reference - TNZ B2
98afa033-dc89-5320-9535-d460d723f3c2 | note | Frequency - Every 20m
3baedc51-cf81-58a8-980c-43f54163b9b1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
bcaba973-e0f1-5197-9766-4822fdd99f19 | note | Conformance Criteria - CIV>=25
bc46b977-4057-5d91-b78e-b0d5627804a8 | note | Records - Test reports
| checkpoint | 3.6 - Sub-base construction
b8c5019d-4c74-5866-8073-45ff6a5ae170 | note | ACTION (Hold, Monitor, Witness) - W
f47988b7-06f9-5721-9fc4-8dddd09b102d | note | Specification/Drawings Reference - TNZ B2
ec5367fc-26f7-58b0-b294-9a6acc398141 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
377ce7ee-e391-5e33-9cbf-b5177a49f122 | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
f2961e80-ea7a-505d-8bd6-34f34e1d1910 | note | Records - Survey as builts
| checkpoint | 3.7 - Basecourse construction
e721120e-e529-53fd-96df-c67ea95f2a99 | note | ACTION (Hold, Monitor, Witness) - W
613d8e40-aa0d-5981-a596-b99322485945 | note | Specification/Drawings Reference - TNZ B2
b89e7222-1da9-5d94-86d8-67125acec2e6 | note | Frequency - Every 20m
d1f6e00c-b37e-5a09-81c4-3f25715149ac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
8c587a75-4b8e-5eab-8fd4-2b7537d1235a | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
f032ca4c-331f-5d5a-ae8f-cf20f046660d | note | ○ Average 98% of MDD with nothing less than 95%
0f8c0272-8c5e-5f04-8a50-dedd81dca62d | note | Records - Test reports, Photo's
| checkpoint | 3.8 - Basecourse Cement application rate
2e92a789-3fe6-5763-abd9-74b37ac9a91c | note | ACTION (Hold, Monitor, Witness) - W
1c0a35d6-e2ac-5082-a398-3d6441798e18 | note | Specification/Drawings Reference - TNZ B/5
5e10de9d-3551-5e38-bda3-36ae1f87ab68 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
0a1884de-f1e6-5232-a4f4-c8a48a3a7fd6 | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
f06a96ff-6010-5f76-8357-87110201102b | note | Records - Material specs, Photo's
| checkpoint | 3.9 - Basecourse construction
a45b4a71-3b21-5d7a-8cff-22e837bfd867 | note | ACTION (Hold, Monitor, Witness) - W
5370112d-5a2f-5ccc-ac41-c2460194d835 | note | Specification/Drawings Reference - TNZ B2
91007fec-2e58-5c4e-8b4a-391decc81a91 | note | Frequency - Every 20m
9a7f04c8-c4ef-5ec3-a5a4-53f5a3e6b78e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
efa7ac4b-9cf7-5621-a90e-2de9e9e3a716 | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
d9714f52-c982-5480-aeab-31c8f352af3d | note | Records - Survey as builts
| checkpoint | 3.10 - Basecourse construction
a8c490b9-66dc-5d05-a50e-1b6b1b0b6b60 | note | ACTION (Hold, Monitor, Witness) - W
4ea2263e-2593-516b-ba4d-ada616c33163 | note | Specification/Drawings Reference - TNZ B2
3e3409e0-1dbd-55c7-9ead-34e16c0c5383 | note | Frequency - Every 20m
03227d5c-d804-5bfb-ba56-ec425cb26151 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
86f9698f-83ff-5d59-9579-07ff53373224 | note | Conformance Criteria - CIV>=25
f823ce89-108e-59e4-a3e6-14e39bcc7bdb | note | Records - Test reports, Photo's
| checkpoint | 3.11 - Basecourse construction
27e97157-0ec5-5a8d-89e0-ea167ed829a4 | note | ACTION (Hold, Monitor, Witness) - H
1bcaf79c-9c11-5c7e-9f41-2cfe24624e3c | note | Specification/Drawings Reference - TNZ B2
c64fb4e9-6c51-5eba-873f-e2652fe69160 | note | Frequency - Before sealing
1d9c6734-1069-5670-971d-3b8eeed9db1f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
3179474f-cae7-55b3-b9d9-a0b2d4c28681 | note | Conformance Criteria - Mosaic surface
4dbe1879-f74e-5847-a5d5-64362a406aaa | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.12 - Applying Bitumen
9ccff7a5-af5e-5a12-8a17-67c87ae26a71 | note | ACTION (Hold, Monitor, Witness) - W
cadf0e62-5791-5026-a453-26e1d85c08b0 | note | Specification/Drawings Reference - NZTA M/6
0a148a6a-0d1a-5151-bffe-cf398badfb49 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
7e26ede5-5018-546f-aebd-128f1cc6eec2 | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
368a9a67-145f-5d89-b7c3-c2efba7ffbe9 | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| checkpoint | 3.13 - Degree of saturation
53fed0c5-13e3-54a9-a4b2-fee745b308e9 | note | ACTION (Hold, Monitor, Witness) - W
61f422ac-79fd-54d9-94ab-dffacf9ad989 | note | Frequency - Before sealing
8a1d91e3-c0f5-50d2-9a99-7da5925dde8d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
8d936735-d644-5076-ae80-3f01fd90baf8 | note | Conformance Criteria - Degree of saturation should not exceed 80%
6f276759-bfe7-594d-b5c5-f0b65dcaf861 | note | Records - Pre-seal checksheet (CS-4060)
| checkpoint | 3.14 - Chip seal laying
108d5f81-b8fa-54d2-b9f3-e3028cb2c370 | note | ACTION (Hold, Monitor, Witness) - W
3d6d5284-042d-5624-9efc-6323b0fe063c | note | Specification/Drawings Reference - NZTA M/6
4683ab54-98dd-5674-850d-502eadd90f2f | note | Frequency - During Construction
5e31aaa5-9c4d-56e4-b192-8b3a707df70a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
235d39e5-42ac-548a-be56-7962b303cb9c | note | Conformance Criteria - grade 3 and 5 chip seal
7e9b9caf-85d6-5db5-a5f1-2e235873d112 | note | Records - Material certificate(s), Photo's
| checkpoint | 3.15 - Sweep & Line mark new chip seal road
f653e592-308c-5635-90bc-97b9d98ffb06 | note | ACTION (Hold, Monitor, Witness) - W
62d7dca9-38bc-59a1-8973-a1281cac654a | note | Specification/Drawings Reference - TNZ P/12:2000
8c92ca16-d369-5afe-8e3d-0233c730327a | note | Frequency - During Construction
e899b782-cd3e-5568-be15-f43e690bfdd9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
df09c25a-6b6b-5e5e-91b0-a8058a4f87ed | note | Conformance Criteria - As per TNZ P/12:2000
88ddd69b-48b3-5c60-b3e6-a7c8b70bbc61 | note | Records - Photo's
| checkpoint | 3.16 - As-built Survey
5b8ca600-77aa-54a1-bc6b-0d6d4009a169 | note | ACTION (Hold, Monitor, Witness) - H
85f42fc8-0a93-57b4-b21d-fe9c72d14b6c | note | Frequency - At completion of Lot
b2aeeeaa-d8d7-56ff-b6dc-67763838b43a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
dfd17e65-ebb5-5a20-b41e-3f250e47a947 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
f16cacc7-c7de-5aaa-aecd-c9c93cf592df | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 4: Final Inspection and Handover
| checkpoint | 4.1 - Quality Assurance deliverables
8a0eb5ba-f9e8-51bd-bc59-62fc16898792 | note | ACTION (Hold, Monitor, Witness) - W
ba8197df-b613-54b0-87f3-1fcb6f8d4c8d | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
5459a453-144c-53ba-8544-eee4bb42a29a | note | Frequency - At completion of Lot
236bb8b4-8297-5014-ada2-540911848bfd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
35623637-b9c8-5329-8bb5-e570e0fff161 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
4f73cfaa-f970-5e51-a4f8-a4349c5c3a00 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 4.2 - Completion Sign Off From Fields Below
4ab39cd5-0c79-5f72-882c-ee376fb24c57 | note | Records - Signatures
| checklist | ITP - F3001B - Te Puia Dropout V2 | itp | ITP - F3001B - Te Puia Dropout |  | d6eca4ab-a250-43f8-b33d-7c027e0b5123
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
d5886eb3-a0de-5c61-921b-d30af2fbf729 | textbox | CPS Eng.
bae783f7-d269-5d23-999c-b42af6f08699 | textbox | Site Engineer
7ca7109d-b0ca-5f9e-b2e6-fd77ddc4d7ff | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour (D50=450)
2efad191-92e2-5f3a-a888-fe001effe14f | note | ACTION (Hold, Monitor, Witness) - W
a93e5f66-7e0d-52d5-971a-0822c653d1c0 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
65236aa0-90e6-5f1f-9c88-dcbb1f2b88a1 | note | Frequency - Prior to commencement
b072a4ad-2c07-548a-9499-b644f49b6ecb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
706525fc-135b-5755-89fe-535780952c20 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
9f9414e7-179e-50c9-89b9-cfafea24efe7 | note | ○ Traceability of materials is required
8735c40e-d22e-5a8c-a712-559b9c81298b | note | Records - Material source test results, Delivery dockets
| checkpoint | 1.2 - BulkFill AP65 or GAP65/GAP100
4831e455-3774-531c-9c51-7e18c56eeec1 | note | ACTION (Hold, Monitor, Witness) - H
94c285c2-727e-5b2f-8fad-06be49e5c555 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
2c6406b0-8b8d-515c-afa3-ded7b052d44f | note | Frequency - Prior to commencement
a57aae86-37a1-551d-9d97-38dacf1d0f74 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
31b99d8f-4b28-5650-a06b-f069550175f9 | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
654f126e-4009-5869-82e7-0639a4c005cc | note | ○ Material source testing
e8da746e-fca7-57a0-b041-592acf263bdf | note | ○ Traceability of materials is required
ce03e7b2-888f-537d-85a9-dfe8f262ecc3 | note | Records - Material source test results, Delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Class D A39 Geotextile
eb3c85d5-c7cd-51cc-93c6-9780893699a5 | note | ACTION (Hold, Monitor, Witness) - W
32293d84-98aa-5f8e-9b4a-5a415ed2c725 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
41279df7-1183-575c-9791-c38fb7460287 | note | Frequency - Prior to commencement
075c13cb-d0a8-516a-bbc5-4d898c6ef833 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
1edfa198-df8f-55e5-9d3f-746e9ce35216 | note | Conformance Criteria - On dry bed below fill
e77e60a7-4a5d-51fe-8474-336ffa92a226 | note | ○ Comply with NZTA F/7
702d1850-5ec5-52c0-935e-57cbdb07b409 | note | Records - Material certificate(s), Delivery dockets
| checkpoint | 1.4 - TNZ F/2 drainage material
2b3b2145-ccef-5ef0-87cb-197976fd1cfc | note | ACTION (Hold, Monitor, Witness) - W
6460b965-ab28-5b06-a43c-143553b14fda | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2
a48b02be-73fc-5b30-88c8-9d47a9b9d41d | note | Frequency - Prior to commencement
77b7796a-640b-5aae-80df-60d2c0abd7e5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
f2c36c2e-b630-5d08-b702-133405225cd7 | note | Conformance Criteria - Comply with TNZ F/2
6e2cb734-6e63-5fab-aac6-4a271d08cb2c | note | ○ Traceability of materials is required
631dd9f5-cd29-54fd-b325-030f2100f413 | note | Records - Material source test results, Delivery dockets
| checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
24043b29-1917-5891-9cb0-ee2dc9bd1d8c | note | ACTION (Hold, Monitor, Witness) - W
a5c320ff-ce1a-5d03-9f13-0e662a8fc012 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
8d3d2cbd-ed40-5c36-a9a2-f479ea3bf373 | note | Frequency - Prior to commencement
189e2faf-74c6-5ca8-ae7b-de70bc0dd7e9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
5e8385b9-49e4-58ba-ae6d-eb68c2cb5c52 | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
74fa60f2-83d5-5f74-a5f0-4c8e6140caa8 | note | Records - Material certificate(s), Delivery dockets
| checkpoint | 1.6 - 110mm Novaflo drainage pipe
fb978551-3cea-5a47-baa0-37a7969f6304 | note | ACTION (Hold, Monitor, Witness) - W
bd71725a-1d6e-54ba-abe0-916860cca927 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
85819755-63f1-5a4f-9cd5-b03ca8f11403 | note | Frequency - Prior to commencement
79400abf-ebbf-5468-bbdc-e18f3b6e8de5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
85744991-173d-5f9c-be99-0e1ef7746d02 | note | Conformance Criteria - Comply with TNZ F/2
d8a4f37f-faed-5968-8f79-21e2aab3cc76 | note | Records - Material certificate, Delivery dockets
| checkpoint | 1.7 - Biocore erosion control matting
040045b0-3555-5cb8-bee8-929356def80e | note | ACTION (Hold, Monitor, Witness) - W
f5597053-1948-535f-bb09-69cfc6ed04b1 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
c35dd2fc-6ae9-5bc1-bc8a-ee736cba8beb | note | Frequency - Prior to commencement
959e8c3d-75fc-5981-b574-a4992a8f1d3e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
86c98595-dc53-5d6b-b75c-3c38537766bb | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
5d593ebe-0950-58d7-b9f1-132628f737de | note | Records - Material certificate(s), Delivery dockets
| checkpoint | 1.8 - Enkamat 7018
ce9c48a5-f190-561e-93b8-4d8fddbaa380 | note | ACTION (Hold, Monitor, Witness) - W
b49111c6-049e-5580-be46-14d8ef5ca081 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
b30aa0f8-92d5-54a4-b866-123efde2a14e | note | Frequency - Prior to commencement
5cc3c0ef-ce25-583a-9412-fb94494f0aa6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
5923c629-5560-5cdd-9bcc-f572c2b98a76 | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
0c1be551-040c-5285-a5d9-e3c4bb88cf19 | note | Records - Material certificate(s), Delivery dockets
| section | Section 2: IN PROGRESS INSPECTIONS
| checkpoint | 2.1 - Survey Setout
2c6af61c-4d7c-5922-84d9-fc97da36b0a4 | note | ACTION (Hold, Monitor, Witness) - H
a44540ac-8d79-58b2-b082-2dfb9ee70b16 | note | Specification/Drawings Reference - Consistency with Construction Drawing
245f2761-65e2-5c6e-9ebb-21bfbc36818b | note | Frequency - Prior to commencement
0834b667-0b05-55d6-a8b3-71b3f4e134ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
ee72cd15-fbe1-5c15-9c36-6c0a716cdfe2 | note | Conformance Criteria - Set out extents of fill and check against design drawings
dba849cd-216c-5f96-96c7-e1c3c0dd7d59 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
d00fdfb6-9470-511d-93fe-39a5ecb142d6 | note | ACTION (Hold, Monitor, Witness) - W
154733fc-f4c4-5789-8c09-3c6975db5845 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
eeaf5627-81de-5dd1-a8c2-812e497665f1 | note | Frequency - During Construction
00f602ae-01dc-543f-b8ae-6495b87a3379 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7925ccb3-df6c-5cd9-96fd-da53d14f930a | note | Conformance Criteria - Remove and clear the vegetation
ce65565f-9801-5688-8401-48398d39d8e2 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Inspection
3f34c1a7-c4df-5732-a75a-fdf70427b9be | note | ACTION (Hold, Monitor, Witness) - H
1d798224-c504-56cf-81bb-f1fad579d0a9 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
4b1df22b-5ff4-5af6-ae72-7eb4c7175274 | note | Frequency - Per area as required
886aab3e-c0b3-5594-bf1d-7ebd2ce80550 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager or representative
cbc261ef-2982-5449-a38b-67daa049bc7d | note | Conformance Criteria - Inspect fill foundation.
834627b1-ad12-5926-ac77-33db0059bbfb | note | ○ Fill foundation must be approved, in writing, before filling commences
2afa4c7d-76fb-52ce-8f53-f0aaa9102eb7 | note | ○ CPS Engineer - to determine any testing requirements here
decbc955-c5ff-5e7b-bef5-b6f6b4d66938 | note | Records - 1M Scala checksheet, CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Ground Improvements
6feb87ae-c63a-5727-bb51-c66d3c25b74e | note | ACTION (Hold, Monitor, Witness) - H
86300ed6-823d-57bb-a36d-b1cd271134d7 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
2145d0c3-0e3b-5ddf-b72a-cc1d9613cb19 | note | Frequency - During Construction
7581ced4-6d66-59d5-ad4b-e796d7ff7bfe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d15431b8-2fd9-536e-b35b-c9f72f58bb79 | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
1346da4e-c4cf-54fa-86e4-57b9095bf8d0 | note | Records - Photo's, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Class D (A39) Geotextile installation on the excavated face
b8486f92-3009-5058-acb7-a876885d2465 | note | ACTION (Hold, Monitor, Witness) - W
8b50b391-8ed2-5679-8ca8-9eea19b66010 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
83a3b3d7-ece8-5088-bd61-18b7ab017617 | note | Frequency - During Construction
c5c2a0fd-fc43-52de-9d48-9fb7e9da15cd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
11c55e9c-31a1-5cb6-a699-3c42919f412b | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
26b1cb0b-d88c-5440-b1b0-377f9ac001ac | note | Records - Photo's
| checkpoint | 2.6 - Sub soil drainage
615e52b0-3922-511c-9d54-1e733d4c2b0c | note | ACTION (Hold, Monitor, Witness) - H
d3ec1b92-8253-596b-852f-6cc562b69a1b | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent. CPS requested a 110mm diameter nova flow drain around the perimeter of the works
0e37120b-6d1c-5e53-aeb0-6fdc6bf2eacc | note | Frequency - As works progress in agreement with the CPS Engineer
f45807c4-7a1b-5e05-8f4c-824f65b047c1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
81f9706f-ebfb-526d-97b0-9f4ee8d77af1 | note | Conformance Criteria - Engineer to assess suitable drainage location and confirm drainage positions on site.
69edf05d-78db-5be7-b05a-9d4f490e7481 | note | Records - Photo's, Drainage Line Record check sheet (CS-4025)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
95cd155a-340f-5289-8ed1-5e003d53145d | note | ACTION (Hold, Monitor, Witness) - W
7051c6bf-6253-5d2d-bb8a-573a7f5d23f6 | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
15fbf63b-0dcd-5146-bf02-941bedf24121 | note | Frequency - During Construction
3d2d5f62-85e3-58ff-a110-0cd7ccd9df15 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
498dca08-2c80-55ef-8875-b1bb70730803 | note | Conformance Criteria - Installed in accordance with manufacturers recommendations
2d9df7f3-ed6b-58be-a86f-86e717266224 | note | Records - Photo's
| checkpoint | 2.8 - Bulk Fill Placement
85dee485-46b8-5991-a1f5-53a9488e65d0 | note | ACTION (Hold, Monitor, Witness) - M
95e787ff-46fb-5a2e-abe1-3d4e743b273c | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
1e9ad25f-d1a4-51ff-a869-c143a9f61c3e | note | Frequency - During Construction
05bb11a1-4e92-5b25-8bb7-8d7ae16d3e01 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b8df0f9a-cf1c-5d82-8282-0b067f607b70 | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade
647cad54-1dd3-53d7-8d56-e4b8b7a184c1 | note | Records - Photo's, Bulk Fill Earthworks Check Sheet (CS-4020)
| checkpoint | 2.9 - Bulk Fill Compaction
e457a3c1-23c6-51f6-be4a-499e86d85de2 | note | ACTION (Hold, Monitor, Witness) - M
294b20c1-fefa-5294-8f74-696dc4619651 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
dd254345-2283-5c8a-8ab3-c79b3b2a9e81 | note | Frequency - During Construction
8b13bce4-ab62-5ea8-b0c1-756a9c07673b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
05240f67-5347-55e2-8605-1e1fa296115b | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 CPS Engineer to confirm number of tests / lifts to be completed
5336a973-78cd-5d12-8d58-4f0741eb977f | note | Records - NDM test report
| checkpoint | -
0c068ee2-a4dc-5daa-bee5-15fa1fb845a3 | note | ACTION (Hold, Monitor, Witness) - M
1178116a-e1d0-5574-a6b4-7132a6b93781 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
c49587a8-aab8-5a68-8655-9b3f44b74339 | note | Frequency - Every lift/layer
5e72fab6-53b0-5b6b-9101-df39325e5212 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
5dc78e36-9e65-5e50-b8ed-204f404a21f8 | note | Conformance Criteria - CIV>=25
ec942465-645a-506e-9748-b98f054956e7 | note | ○ Shall be carried out for each lift/layer and recorded
842ffe63-6ae8-5a0c-98d4-da0476004c90 | note | Records - Clegg Record test sheet (CS-4037c), Clegg calibration certificate, Photos
| checkpoint | 2.1 - Form and cut fill batter as per design 2H:1V
e3b6bcb3-e47c-58a4-bb67-9cbb98f71c5a | note | ACTION (Hold, Monitor, Witness) - H
13adac06-f0e2-5b3a-9cb8-4dfcffddd604 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
3a1555a9-80e6-54ee-a1a4-855b985dd024 | note | Frequency - During Construction
27a2186b-9bd0-597e-ab46-b8ca46d3e300 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b509a875-62a4-5e5a-b17f-14d437dd914e | note | Conformance Criteria - Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations
2f986d59-913c-5cf8-8c22-81062e7e4257 | note | Records - Site inspection on completion, Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Rock Armour (50-450dia) placed on the toe of the slope
56f83237-cb9d-5aff-8c37-de868fdb41db | note | ACTION (Hold, Monitor, Witness) - W
e6e173cf-b4d4-5314-8fa1-b6ff7ab0dc8a | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
024d45d0-84a8-505d-8034-ea5259813bf9 | note | Frequency - During Construction
52090ee9-1a05-5e30-a027-af6c505f3700 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
932aef3a-6a2b-51d9-b2fa-4cc43a8dbdbb | note | Conformance Criteria - The buttress to be keyed in to natural ground as required and agreed with the CPS Engineer. Rock armour to be added to the toe as required
1d6f2f26-d1af-55d1-8858-1df7cc567b5d | note | Records - Photo's
| checkpoint | 2.12 - Verge & Fence Reinstatement
c0704f72-b43a-586f-8d8b-6ead4fc33fd7 | note | ACTION (Hold, Monitor, Witness) - M
9d7ce1a4-d9bf-51e5-b2ed-354b3deb27e0 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
542efebe-36cc-511e-9f0d-67c1ce42fb09 | note | Frequency - During Construction
e2392eea-d2c3-518c-a10b-8e6f4396cf0c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f2ebe251-a82f-5b9f-af93-751d7289968a | note | Conformance Criteria - Verge reinstatement as per site instruction by Engineer
1c602820-e49e-5789-88f1-f4b1867f523c | note | ○ Fence reinstalled to match existing
bfff5779-5d2e-54e6-80fa-d566e1b638d9 | note | Records - Photo's
| checkpoint | 2.13 - As-built Survey
defd746c-a0d4-5b34-8d91-d9e0a19ba431 | note | ACTION (Hold, Monitor, Witness) - H
67256af9-139d-5610-b747-cacc1e585581 | note | Frequency - At completion of Lot
62ca4e0c-31b7-599f-a367-41e2ebfbbbc3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
535da349-2897-5f6f-8f59-ca4c8c334842 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
c5585b2f-58e4-58a6-9986-aaba2fcaa541 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 3 : Final Inspection and Handover
| checkpoint | 3.1 - Final Walkover (Snags)
3133cf79-6721-5e85-a47b-81b912a70b7c | note | ACTION (Hold, Monitor, Witness) - H
ad7f4a42-bb8c-555b-9bed-cf4000415f9c | note | Specification/Drawings Reference - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
507f2a2a-24da-53dd-8ca1-b122a6147ed5 | note | Frequency - At the completion of the Lot of work
06f98d94-449d-5978-a3bc-6acbae604c2b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover/Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
a9463427-7da7-5a1b-8093-d2d596a6aa35 | note | Conformance Criteria - Completed report
ddfc20e8-8aa1-5a00-a6a9-7850a8cf227a | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Quality Assurance deliverables
1ccc7a01-cf9c-52a7-ab7e-ac2839d347b6 | note | ACTION (Hold, Monitor, Witness) - W
a2830549-4943-5fd2-b4f7-d3f43438f7ec | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
75148702-9349-5372-813b-dd525415c2ac | note | Frequency - At completion of Lot
5d910072-3ca1-534a-9289-0c76f705dcc8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
cfc21ccb-55e1-5bfb-9dcd-4b65b2c0f2dc | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
a956c156-6659-5642-9bc5-112ecb6e77f7 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 3.3 - Completion Sign Off From Fields Below
730f35aa-6dd0-5e99-b0c8-2865c67758e2 | note | Records - Signatures
| checklist | ITP - F3002D - Mangahuini Long Drop Site - Guard Railing | itp | ITP - F3002D - Mangahuini Long Drop Site - Guard Railing |  | 4db5d008-47c7-4541-93a2-e3491da36cc1
| section | Inspection & Test Plan / Checklist
| checkpoint | Project Site reps.
07a6729d-3354-5ae8-89c7-ecc01cf58b18 | textbox | CPS Eng.
2f595288-c6fd-52e2-8d20-cca647d4056e | textbox | Site Engineer
829a885f-2d1b-5e55-af1c-167e81d6ad20 | textbox | Quality Eng.
| checkpoint | 1 -
4e6c1dc4-d073-59bf-8b34-328eff7f1b11 | note | ACTION (Hold, Monitor, Witness) - H
f669b5c0-712f-5cbe-900e-16d3f57097ed | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
71b319ad-ddfd-5b10-a656-196edd0d3a51 | note | Frequency - Prior to commencement
85826c6c-e534-59e5-97fc-8b875c2fa2bd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
b89b421b-9fc4-55ec-891a-eae14e182b60 | note | Conformance Criteria - National Standard for Traffic Signal
4bc90ce3-a993-5ac9-ba87-b388e99a693c | note | Records - Site pics, NTE/NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
be4ce099-9316-563f-8098-707e68d1c379 | note | ACTION (Hold, Monitor, Witness) - H
90f6732b-e65a-5ba2-880e-b6788a6f74b6 | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
f66824e8-b6c9-5c26-a11b-f68cebfa1762 | note | Frequency - Prior to commencement
a7330349-2659-5676-acd1-fcf3e26be2db | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9bf7b259-243e-5727-8f04-10ee9d4ac4bb | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
b593c1e7-5926-5e84-ac03-3e7fc17ea298 | note | Records - Approved Construction Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance
922a4fb9-0e18-5856-91a4-d455bd3d9944 | note | ACTION (Hold, Monitor, Witness) - W
34c00366-d726-5cb1-9c36-b7a91b8a9220 | note | Detail - All roadside barriers shall comply with TNZ M/23:2009. Only NZTA mash TL3 approved systems to be installed as specified in the specification & guidelines for road safety hardware and devices, Appendix A: permanent road safety hardware.
15493f96-ad48-5d9e-8d89-d8a96270eefb | note | Frequency - Prior to commencement
599e79eb-8058-5a72-b4bf-50016c38cb1e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
bd15e27c-d53b-567c-b402-de4dd7d6af4a | note | Conformance Criteria - Comply with TNZ M/23:2009. NZTA mash TL3 approved systems only
8beecbc3-02b6-5774-bd21-de71e55ce68f | note | Records - Manufacturing certificates, delivery dockets
| checkpoint | 4 - Guardrail Installation
7251bb61-9ef5-5928-b9a8-844da40500e2 | note | ACTION (Hold, Monitor, Witness) - W
4ea47c23-93b4-5902-b5b0-afa072354fc6 | note | Detail - Guard railing shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. Laps to be in direction of traffic
79dc4a94-8885-5e19-a5c4-f7d08ad2b6c0 | note | Frequency - During installation and on completion
eade38ee-2737-5585-9ae3-345370f9ba53 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
6dae757d-7734-5f09-b1ef-9a5212750d88 | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
9380abed-ffe9-5f18-8d40-e95f917cbec8 | note | Records - Guardrail Installation Record (CS-4117), Photo's
| checkpoint | 5 -
14cc0fe4-ce0e-51b3-a60f-bd7b816e3444 | note | ACTION (Hold, Monitor, Witness) - W
979b79e7-e5ed-5d41-aa8e-79fe3958f4d6 | note | Detail - Hazard markers to be installed at terminal ends. Edge markers posts to be secured to the guard rail. Guardrail to be a minimum of 1.2m from white line. Engineer to confirm min of 1m support width behind the barrier
41d775a3-910c-545a-9cd2-db93f5ab0980 | note | Frequency - During installation and on completion
8caf8533-a031-510b-be7d-5f4c019e384d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
ee1fb88d-25f9-5253-b45d-5170556e2680 | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
f6752a78-a87f-55d9-b864-b054fbceb26f | note | Records - Guardrail Installation Record (CS-4117), Photo's
| checkpoint | 6 -
9362a151-fde6-5bdb-b055-f177deca18de | note | ACTION (Hold, Monitor, Witness) - W
e04302e3-1e7a-520a-a14f-66ef1c7a6d60 | note | Detail - Barrier face to be max clearance of 200mm from kerb face where kerbed. Design speed 100Km/hr AADT <1000 V/D run out length 64m. Existing signs to be placed behind the barrier. Offset of fence is to be confirmed to ensure there is sufficient room for barrier installation
7fbb6aca-dc56-50e4-890b-35975bd57688 | note | Frequency - During installation and on completion
9b00fb02-4ff7-5cba-963a-870f49ec5be1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
e8724f78-286f-574b-8872-1f76b027dbbd | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
62581f40-4214-5abd-a2c5-e042a45b3280 | note | Records - Guardrail Installation Record (CS-4117), Photo's
| checkpoint | 7 - As-built Survey
9c6ff1e7-e9d3-5e5d-80ab-9297b281419b | note | ACTION (Hold, Monitor, Witness) - H
08086838-913b-5ba1-b213-d8a7d9a01e22 | note | Frequency - At completion of Lot
9a3af4d5-fd0e-5f0c-8429-222290592161 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
cf5d4669-d962-5806-b36c-79e8d6a4508c | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
fd97d86a-9e41-555d-bb98-5a6158d1f04d | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Final Inspection and Handover
| checkpoint | 8 - Quality Assurance deliverables
8cb59d57-1730-5047-9df3-3c48da8e6fbc | note | ACTION (Hold, Monitor, Witness) - W
f13bae89-03e7-5567-ad7a-8c0916e316bb | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
c5f09f82-70db-5323-905c-4e8aab4c5b73 | note | Frequency - At completion of Lot
3a61c0b8-cbc1-520b-9487-a4e88ca16cb2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
bee2b8ec-ace0-56a8-a2e7-f1c66d935dd9 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
e4a32095-9132-59ad-a6a6-3631acdd12d5 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 9 - Completion Sign Off From Fields Below
3ae7ef04-75c0-5bdc-99d2-9c98e01b087c | note | Records - Signatures
| checklist | ITP - F3002D - Mangahuini Long Drop Site - ITP for works REV 1 | itp | ITP - F3002D - Mangahuini Long Drop Site - ITP for works |  | c5f2bb34-e766-4f47-a09e-75e6088ceda2
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
69ba1670-d957-5bf0-aab6-a05b34916406 | textbox | CPS Eng.
8c1f7a61-58b7-54cc-985b-9d091d0caa12 | textbox | Site Engineer
77331545-1f61-5d64-86b1-70c1c05c6353 | textbox | Quality Eng.
| checkpoint | 1.1 - Buttress Rock Armour (D50=800mm)
77a1b739-aa7d-52af-873f-8fea8d11d5f0 | note | ACTION (Hold, Monitor, Witness) - W
c00b327c-0b7d-55f3-8a4e-94cd541a9503 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
38104185-906c-5367-bb72-f1624cd0c436 | note | Frequency - Prior to commencement
0345be39-11ca-56cb-a012-bd64752adead | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
37043cb7-64ff-53c9-a037-eff6e5916412 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 800mm with a minimum specific Gravity SG of 2350kg/m3.
63e617f4-6f33-584a-8c0f-23e714aa66dd | note | Records - Material source test results, Delivery dockets, Photo's
| checkpoint | 1.2 - Culvert Rip rap rock (D50 = 500mm)
cbb5e7b4-aee7-54a5-9db8-f2133086a8d3 | note | ACTION (Hold, Monitor, Witness) - W
a5d0924d-c932-5dec-9668-c2ab2dc2c891 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
147b2162-95d4-59bd-aa36-caa7c047e1b3 | note | Frequency - Prior to commencement
4d1cde87-9a24-5ee6-891a-fe000445b504 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
e86ac567-be0a-57ff-8535-eadfe4166e36 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 500mm with a minimum specific Gravity SG of 2350kg/m
cbd6ea1e-10bd-5ddc-b1a7-a1b0ebcd524a | note | Records - Material source test results, Delivery dockets, Photo's
| checkpoint | 1.3 - Drainage material
aca1b633-ca8c-5e14-a0a3-91b599b2cf37 | note | ACTION (Hold, Monitor, Witness) - W
0b226452-4dd7-52ae-9c5a-3cc6e5bee58e | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
12864a85-e69f-5cb8-bc9a-0fa19845ccd2 | note | Frequency - Prior to commencement
a3b42221-b1c2-50d1-a6bc-06f01c20a0c7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
06f86aa8-369a-5c49-9c4f-ec4c106d0de2 | note | Conformance Criteria - Comply with TNZ F/2 or approved equivalent.
86a71b0d-58b8-585c-9914-f3579c766ce0 | note | Records - Material source test results, Delivery dockets
| checkpoint | 1.4 - AP65 Granular fill
81656688-a056-5b33-bcea-1f01a771a750 | note | ACTION (Hold, Monitor, Witness) - W
4bdae82d-30d9-58a3-8361-04931f16a23a | note | Specification/Drawings Reference - F3002D 2-U3436.BM
979eea29-ffbc-573b-a8a5-780d1813811e | note | Frequency - Prior to commencement
2b3e77d0-9b52-5237-ab18-263603d9d2b0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Particle size distribution test
75bdec89-211c-508b-b6c9-d5d14e57ecda | note | Conformance Criteria - Test results from a representative general fill sample tested in an independent accredited laboratory
d55bd3b5-a234-5c65-a02b-8762d25d8b55 | note | Records - Material compliance cert, delivery dockets
| checkpoint | 1.5 - Geogrid: Miragrid 80/20 Biaxial Grid or Similar Approved
91bb69ac-64d5-52b1-a6da-7340bf460ccd | note | ACTION (Hold, Monitor, Witness) - W
307e4e13-bea8-5f07-bb23-742da2ab9dbc | note | Specification/Drawings Reference - Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final
6b4056aa-a48e-5642-926e-c73d49bce54b | note | Frequency - Prior to installation
e3345105-59eb-5e15-9c12-0f21546c8b10 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
3fdd3c05-1843-5866-93b3-8889d1237307 | note | Conformance Criteria - Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings.
b3a20d44-55b7-588e-9dc4-d43f2539ab8f | note | Records - Material compliance cert, delivery dockets
| checkpoint | 1.6 - Class D A49 Geotextile
3e88f360-590e-566c-b998-430c6c1e2296 | note | ACTION (Hold, Monitor, Witness) - W
0721bf09-a894-5c53-9878-3215d6accd88 | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA F/7
f8ed2091-ed7b-5511-9b3d-190772d28f39 | note | Frequency - Prior to commencement
93f77f79-9d09-5bac-a2f4-f5c3f34d2a8f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
007fd651-2825-5d3d-9224-6ad73a0eed39 | note | Conformance Criteria - Non-woven & NZTA F/7 compliant On dry bed below fill
61602227-dab1-57e2-829d-06fcbb4f9853 | note | Records - Material compliance cert, photo's, delivery dockets
| checkpoint | 1.7 - Perforated lateral drains
b61e6e97-3878-5994-bc6f-8219890ecdf7 | note | ACTION (Hold, Monitor, Witness) - W
ac6bd562-86fe-56fc-958b-a5ab06b05628 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
22373b6a-52c9-5722-bce0-343bbedcab13 | note | Frequency - Prior to commencement
5a2cfc61-174d-5810-9f4a-6458a6a3a0d7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
3bbaa945-929b-5765-8731-993eac9c9a77 | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved.
4ff021b4-a716-5d7d-9a3e-2854f222e565 | note | Records - Material compliance cert, photo's, delivery dockets
| checkpoint | 1.11 - AP40 (Basecourse)
cf0b8a31-c159-5e3e-8093-337c41592bfb | note | ACTION (Hold, Monitor, Witness) - W
215115cd-2af9-58e6-93ba-8eb51d9731db | note | Specification/Drawings Reference - TNZ M/4
9b7574c2-5927-527d-9f54-cefa95d853e5 | note | Frequency - Prior to commencement
1e984488-a525-54ec-98c6-521b044cad1f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
1f0438b5-ec5d-5177-9bd6-dabbc262042e | note | Conformance Criteria - Source property testing
c057982e-e6f8-5883-8091-e712b47b3d41 | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.12 - AP65 (Sub-base)
19bad9ec-6394-5b2f-8bc3-ff8f93dfa23a | note | ACTION (Hold, Monitor, Witness) - W
7b0fa3cd-7cbe-5425-bcc1-af691c1c4b2b | note | Frequency - Prior to commencement
58d3418d-3265-5a7e-9f8c-54978e7d2c51 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
a4fc5c80-af03-57e3-82d5-b91bc42a8f95 | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
52456a5a-6278-583c-a8ff-90b515c1d9cc | note | Records - Lab test report, Delivery dockets
| checkpoint | 1.13 - Grade 2/4 Chip
713ae944-f691-501f-b2b3-aa37889a90c6 | note | ACTION (Hold, Monitor, Witness) - W
81f2c5cd-6d1c-5947-b7e6-33f5d32b2bb1 | note | Specification/Drawings Reference - NZTA M/6
baacf0dc-3a17-52a4-93e0-fa642ba86f26 | note | Frequency - Prior to commencement
edd2a852-1b29-5250-a868-661a5a84154a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
13b6c27e-af8c-5629-833a-a6c23777fbcb | note | Conformance Criteria - Source property testing
fe4e9545-21fa-564e-822b-621ecda0f051 | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.14 - Cement Material cert
187b79f7-a78e-584e-8ecd-e31951799b00 | note | ACTION (Hold, Monitor, Witness) - W
01f01242-bdc2-55a7-bd4c-180ee1d34136 | note | Frequency - Prior to commencement
abb65add-a615-5900-8b02-475699c7c0ed | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
870d7da7-872c-5f0b-9316-62752b762745 | note | Records - Material certificate(s)
| checkpoint | 1.15 - Bitumen
e774e17d-5d65-5475-a031-b8c571c34639 | note | ACTION (Hold, Monitor, Witness) - W
a7687c65-8b09-5572-b7ca-cb2ec4e61d22 | note | Specification/Drawings Reference - TNZ M/1
30934812-4a16-57b8-830a-25658fb405d1 | note | Frequency - Prior to commencement
5e896a46-fe5e-5bca-8da9-3625898c8ab1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
851b358b-f1b1-559d-8f03-fbe7dee87474 | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
07254412-94a2-58dd-b1be-6bb4b52f1f5f | note | Records - E2 Certificate
| section | Section 2: REVETMENT & BACKFILL INSPECTIONS
| checkpoint | 2.1 - Survey Setout
77243461-0405-5401-b865-7c94cc5422ce | note | ACTION (Hold, Monitor, Witness) - H
5462632e-00fb-5c00-8aa1-6133221795d6 | note | Specification/Drawings Reference - Consistency with Construction Drawing
77c11763-b412-598f-9074-76f7bd4ea803 | note | Frequency - Prior to commencement
68448adb-6031-5c27-a369-ca09ea462244 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
b9931fc1-f327-53c8-a357-5edd7aaa0492 | note | Conformance Criteria - Set out extents of fill and check against design drawings
9519d962-d180-50a2-9da2-13654bcda9e8 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Unsuitable loose material and vegetation
e17bbec4-b120-5755-91e8-041e3a842e4f | note | ACTION (Hold, Monitor, Witness) - W
d73b5d0e-f59c-5a56-8595-2da4f162e89d | note | Specification/Drawings Reference - F3002D 2-U3436.BM
1f764354-1045-50f3-a5ef-5af7767258a3 | note | Frequency - During Construction
a40660a0-0c17-5d04-8777-439a001d6cb7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b37b6f9b-46d2-525d-beff-2446d3fac350 | note | Conformance Criteria - Remove and clear any vegetation, trees and unsuitable material
662e07a7-deb1-5865-8663-a864df0f2880 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Inspection
1b73dbf1-4e95-5edd-bfe7-20812ba5f68a | note | ACTION (Hold, Monitor, Witness) - H
ed5216f2-91e3-5fb6-8004-c6ceeef73475 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
4095da97-1525-5c47-a84f-6b90b7ca096f | note | Frequency - Per area as required
b16f65aa-22fa-5e62-b78d-09afdbae9592 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
5522a425-5a6d-5692-ba9e-b8330d9a85a1 | note | Conformance Criteria - Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences.
65db3e2d-382a-5a49-8da8-5805d36eb4b0 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Class D (A49) Geotextile placement
366c7b76-67c4-594d-8c94-24ac9cc27afe | note | ACTION (Hold, Monitor, Witness) - M
a6c3967f-ca4e-54a7-bc58-453a1d18e291 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
58de8393-4019-5c37-b418-6833605779b8 | note | Frequency - During Construction
51cbc4a5-2cfd-5a1e-ac57-4c1074b475c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f4ce3702-28a7-5023-ade6-34b0d123ec40 | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A49 or similar approved before placing granular fill. Bidim layer required between granular fill and rock armour.
9ef26a1f-daea-5171-8e03-17e9afa40833 | note | Records - Photo's
| checkpoint | 2.5 - Sub soil drainage
bf12397b-2030-5353-84da-4965698066e3 | note | ACTION (Hold, Monitor, Witness) - H
de08250f-01c0-5e3f-85ca-787fc2e1909e | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
0ebcebef-8d19-54d3-8c4f-355aa1b026a5 | note | Frequency - At lower bench level and mid bench prior to placing granular fill.
90ee9db3-26e2-562d-aa44-588375753c5d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
9f927b06-fa36-5846-86d8-1dee158aa795 | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. To be inspected and approved by CPS Engineer prior to install.
531837d0-3b74-55d3-948a-fbee43382917 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Imported Granular Fill Placement
732b3b5f-e0d1-53f4-8e48-a9bf00296c6f | note | ACTION (Hold, Monitor, Witness) - H
6436c7d9-837b-5d54-aa8b-b0a1caf8e548 | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS4431:2022
6b02f525-f74f-5e9e-a978-81f2b996c94a | note | Frequency - During Construction
b544d24e-3511-5dbb-a33a-2023ae38bb56 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
1624f3d2-4ed1-53ec-b06d-20f90f4dbc5b | note | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
c6502f86-fd87-5379-9582-98d134354f6e | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Imported Granular Fill Compaction
6d14a2ea-9b2c-5f9f-92ae-ca122ab0b323 | note | ACTION (Hold, Monitor, Witness) - H
03661876-f6ed-5c8f-beab-78cac80c4719 | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS 4402:1986, Test 4.1.3
7dfa6c83-1fc1-55ab-a11d-065dce8e550a | note | Frequency - During Construction
cf0a0ed0-f9d7-5e82-b47c-58b66054572b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM & Clegg hammer testing
ab9b46bf-bd68-579e-b02d-c36213cb9256 | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Testing done as per Site Instruction by CPS Engineer.
10597727-27f6-54d0-b91e-5601fed515f1 | note | Records - Test results, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Geogrid Placement
71a9322d-065d-5203-aba6-2673b1a221eb | note | ACTION (Hold, Monitor, Witness) - H
d958f2e6-ab7c-511e-a2cb-7bf786661d28 | note | Specification/Drawings Reference - Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final
d6ddd0c0-6107-5153-bb2c-5be25ccdf127 | note | Frequency - During Construction
884e212d-fd3f-56cc-a38d-b063e4f71172 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
eb956fbd-9b5a-5f67-a96d-7caaa20d5d0e | note | Conformance Criteria - Geogrid to be placed in engineered fill 300mm thick between geogrid layers. Geogrid to be wrapped with a minimum overlap of 2.0m. Panel overlap on geogrid layers to be minimum 0.5m or manufacturers minimum.
1f9a3541-9511-503d-ae6b-b36dd5e8af33 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.9 - Form and cut fill batter as per design 1.5H:1V
61252a02-4800-5d33-b00c-c7d4ba723fc3 | note | ACTION (Hold, Monitor, Witness) - H
a5770630-99c6-54e8-bbcd-d61657489c80 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
8d5591c7-1ea7-553f-b832-cf39d8a8c8f8 | note | Frequency - During Construction
a8ba870b-c554-5783-90b3-f56cfe32d638 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
da3fdaa7-8770-5515-b4ff-2d250a603179 | note | Conformance Criteria - Benches to be cut and profiled to suit slope profile
a3706d50-7949-573f-bf52-ea0957c273df | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Rock Armour (50-800dia) to form revetment
5bf79f7e-dcda-59bb-94c3-1f19f1979fdb | note | ACTION (Hold, Monitor, Witness) - M
880d5199-68b6-5f7a-8dfe-c0a9b205523e | note | Specification/Drawings Reference - F3002D 2-U3436.BM
1c85ac03-a6c6-5ddc-8e97-eb900bfae1b2 | note | Frequency - During Construction
4972af42-8c66-5246-802c-179c1883cea6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
544f5f91-b24e-5240-974e-8ab8608bd848 | note | Conformance Criteria - The buttress is to be keyed in to ground directly behind existing displaced reno mattresses and existing railway line timber panel retaining wall
22e0777b-ef4b-5a57-9bf3-1398f12f387a | note | Records - Photo's
| section | Section 3: FISH PASSAGE INSPECTIONS
| checkpoint | 3.1 - Survey Setout
5d084ca1-c657-5a90-8342-72273b53dbcf | note | ACTION (Hold, Monitor, Witness) - H
07c391a5-109c-5fd1-b33c-83730d13a857 | note | Specification/Drawings Reference - NTC F3002 D
63710ad7-547b-52a7-a4b0-c173d8131809 | note | Frequency - During Construction
3cf3b01e-2436-5c8a-92f8-44c1642fbedc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
94b71ae2-1a24-5f45-a62e-247a56006e82 | note | Conformance Criteria - Set out extents of fill and check against design drawings
6b19af11-661c-5833-9e98-eb843a5b46ee | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Void Fillings
61c9f388-b059-548e-919b-0a0c4a20cb76 | note | ACTION (Hold, Monitor, Witness) - H
ab3eea29-6be5-5d41-83ed-6f10f6fe8492 | note | Specification/Drawings Reference - NTC F3002 D
f0b77a74-192c-51d4-afd3-7e78d8bece84 | note | Frequency - During Construction
5f84243d-6781-5f16-9640-214a829a36d6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
9ce95f60-291d-5ce4-a467-966a4d488148 | note | Conformance Criteria - Measurements of Materials
088e556e-739e-53a7-8c7b-1909cf4fca16 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Gradient of the fish passage
27faf134-ee3f-5d9d-bc90-484c7144689f | note | ACTION (Hold, Monitor, Witness) - H
6955f498-b90e-5f8b-8bd1-e4579049095a | note | Specification/Drawings Reference - NTC F3002 D
c661b9ea-bd52-558a-beef-da89998ebbea | note | Frequency - During Construction
6574d70d-96f8-542e-b0bd-1405da94d0ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f5abfa32-1bed-596b-9c47-bd0c1334cbf5 | note | Conformance Criteria - Set out extents of fill and check against design drawings
f2419f99-43ea-5ae5-ae31-fb607d04e078 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Clear, reshape & apply rip rap to culvert inlet
ca073347-b1aa-5580-9e8b-27e587454f24 | note | ACTION (Hold, Monitor, Witness) - H
566ab8fc-34d7-52ee-b3a6-1e2114ccc74d | note | Frequency - During Construction
d1044034-9e45-529f-ae75-f06a619993b5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
984648b4-15be-59d2-ae5b-c6a66651b2a8 | note | Conformance Criteria - As agreed on site with CPS Engineer
27d636a1-7246-5f91-a136-156c813d798a | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| section | Section 4: PAVEMENT INSPECTIONS
| checkpoint | 4.1 - Saw cut existing pavement
e3ae9fe2-d9d7-5b3c-8e87-6c33a5594485 | note | ACTION (Hold, Monitor, Witness) - W
69f866f3-5564-5809-9830-64869c8d22b2 | note | Frequency - Prior to pavement construction
d8b4bbf7-6894-5014-80d5-fceb9816f462 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8fddf259-83e2-5239-ab1a-507660d5f143 | note | Conformance Criteria - Smooth and straight saw cut
ec85849f-19ec-5b41-9167-3db26ced296d | note | Records - Photo's
| checkpoint | 4.2 - Subgrade construction
8a78d471-4505-5de9-9d75-5b3d9dca3871 | note | ACTION (Hold, Monitor, Witness) - W
c659d7fd-1148-514b-b560-41aea63bdf53 | note | Specification/Drawings Reference - TNZ B2
6ee9f9da-bbe9-5134-a21d-8c4b98c7b2b7 | note | Frequency - Every 20m and/or at random
6f721878-33aa-5093-b58b-0165bf708462 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
17496a70-f1d1-522f-aff8-00ff70ff25e8 | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
09fefa71-1164-5a2a-91dc-66ae39e81cb3 | note | Records - Subgrade Approval Check sheet, Test (CS-4100) reports
| checkpoint | 4.3 - Subgrade Cement Application rate
73b3f88d-d1cf-5570-9923-ce47bc149d0d | note | ACTION (Hold, Monitor, Witness) - W
36e174b4-6f93-55ea-8068-0ec45de986d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
f2bc55d7-74a4-5d11-a37e-888744e0e95c | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
d1da49ae-186a-56ff-b180-999619d3b293 | note | Records - Bag test records
| checkpoint | 4.4 - Pavement construction: Sub base and base course
7fcf9c73-9ac2-5ec7-87d6-aad027db7a4d | note | ACTION (Hold, Monitor, Witness) - M
caf1d79d-9fb4-545a-985d-16b9a8339133 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
14ba1bc4-e16f-5671-8317-ff422c97caca | note | Frequency - During Construction
710c2693-2418-5438-9ef1-1674e46df538 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
03ec83f2-73ed-530b-b079-5c4e2aff29fb | note | Conformance Criteria - Sub base and base course to be placed in accordance with TNZ B2. Compaction required in accordance with NZS 4407:2015. Cement supplied to NZS3122 and stabilised in accordance with TNZ B/5.
57d2a0d9-7303-51ae-b926-0b79349b88ab | note | Records - Photo's
| checkpoint | 4.5 - Sub-base construction
a922f33f-5424-5091-90b3-e476b86d8983 | note | ACTION (Hold, Monitor, Witness) - W
28e9b5e2-65cc-5967-bb9d-887adcd93b10 | note | Specification/Drawings Reference - TNZ B2
fc27ada3-350c-5358-9314-0eac7b0aa95e | note | Frequency - Every 20m and/or at random
f4475cc5-3870-5581-8aad-a2fd217f52ce | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
873f65af-5b16-5ac4-a75c-065812de0155 | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%. Average 95% of MDD with nothing less than 92%.
d5255fc9-41ae-5d3c-9d81-7b56b8c80e51 | note | Records - Test reports
| checkpoint | 4.6 - Sub-base construction
94210b9c-2b05-56f0-ac19-991fa81ebab3 | note | ACTION (Hold, Monitor, Witness) - W
ace5074a-1705-5ca4-95fe-de98e9761845 | note | Specification/Drawings Reference - TNZ B2
d5e69c2c-6ab1-5397-a858-277275b218f0 | note | Frequency - Every 20m and/or at random
d983ea52-b33e-5e67-9702-513fc54e3597 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
cbd37141-8c2e-5dad-acc4-828f44a3960d | note | Conformance Criteria - CIV>=25
53fbd93f-8de9-56e5-9450-5cfbed7c11f8 | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
| checkpoint | 4.7 - Sub-base construction
73ca106a-8345-5539-8b01-bd9d554a4201 | note | ACTION (Hold, Monitor, Witness) - W
5e5377f3-d0e6-5421-8250-cb15db8b47db | note | Specification/Drawings Reference - TNZ B2
598d6281-ca43-5eb2-b503-6dbc13c14b56 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
69d41c07-e05c-50d3-9c0f-8fdd6754a999 | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
8d3c3826-1225-59cd-9faa-f5c882927bda | note | Records - Survey as-builts
| checkpoint | 4.8 - Basecourse construction
1babbece-6e2d-5b6b-9995-d18a660f29f0 | note | ACTION (Hold, Monitor, Witness) - W
3c05a4a1-e58f-5e12-a674-a70beace4fcc | note | Specification/Drawings Reference - TNZ B2
d7be59e4-8cb4-52cd-b8ef-7689cd1300a2 | note | Frequency - Every 20m and/or at random
54ba58bf-5af0-5007-9f4c-906154cf3e08 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
c13516f4-c684-526f-b0ad-b90992a4fdab | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%. Average 98% of MDD with nothing less than 95%.
cc84b23a-7814-5d99-b7eb-4a5f9a6c248f | note | Records - Test reports, Photo's
| checkpoint | 4.9 - Basecourse Cement application rate
8cc691fe-6701-5bec-b1e3-33f0414ce5de | note | ACTION (Hold, Monitor, Witness) - W
456bb4b5-2e36-5cc6-b679-31a375a52c1d | note | Specification/Drawings Reference - TNZ B/5
c3423cb9-8d48-574b-97fa-48687d0a35ce | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
03940fb6-1936-5c84-8a58-843fab5ba2f4 | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
a3fa84e9-6cf0-5694-8a76-9a824686655a | note | Records - Photo's
| checkpoint | 4.10 - Basecourse construction
6ff3dd56-ac1d-5f23-8088-092372b9d5a3 | note | ACTION (Hold, Monitor, Witness) - W
5abe17a8-ee53-52f0-9939-18a6dd34002f | note | Specification/Drawings Reference - TNZ B2
5a0ea1e0-47aa-5039-ac88-c0e0ab356f48 | note | Frequency - Every 20m
35d67124-04ef-52f3-8866-ad8900187bac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
6405343b-bdf9-5a65-8cf9-f8c0dcff6e74 | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
71473fc3-30c9-5590-bef3-f9fd80eba79c | note | Records - Survey as-builts
| checkpoint | 4.11 - Basecourse construction
2913bcb9-a245-5945-913e-089c5debc8a3 | note | ACTION (Hold, Monitor, Witness) - W
ac7cda92-e8e5-5898-95c4-b49a90b66755 | note | Specification/Drawings Reference - TNZ B2
f5d7089a-9846-57b7-8679-474b7f240099 | note | Frequency - Every 20m and/or at random
aa313e2c-d2fb-514e-ac0a-4999f46b8e43 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
65f3b842-4d8a-53a5-8aed-888e602fcd7e | note | Conformance Criteria - CIV>=25
a2d2d79c-f5b7-5013-8af8-814b4a1f3e37 | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
| checkpoint | 4.12 - Basecourse construction
f843ddba-0355-5072-ab3e-8271b35a7ae3 | note | ACTION (Hold, Monitor, Witness) - W
1815ae73-b8ca-540a-8ef3-0dcdb1ebac4d | note | Specification/Drawings Reference - TNZ B2
f606d52c-63f3-5484-bebd-74872d11e5d1 | note | Frequency - Before sealing
c1818244-e088-50e9-bff5-614479e20b79 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
8197e20c-1192-5c84-9f3b-2bfe92a97281 | note | Conformance Criteria - Mosaic surface
72d1e3dd-8881-5065-9d48-ac6bd252741e | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| checkpoint | 4.13 - Applying Bitumen
32f8ab63-a791-54a0-8b3a-b7674cd2fef9 | note | ACTION (Hold, Monitor, Witness) - W
b8cd8ca5-8aac-5112-a313-4e13922acab8 | note | Specification/Drawings Reference - NZTA M/6
5244362d-05eb-5e37-ac16-e7af59156ddc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f871c2c9-444a-5a18-96b2-7521996de80b | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
191aca1e-0629-5ce1-b488-0b5a8c188f1b | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| checkpoint | 4.14 - Degree of saturation
9f484139-7754-5d2f-9f64-8f6a9d75501f | note | ACTION (Hold, Monitor, Witness) - W
e9b475d5-531d-5cba-a1f1-75c64497e7e3 | note | Frequency - Before sealing
8c2c0399-b533-5a54-aaeb-c8bed1be3abb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
899338fd-bd25-5daf-90f8-53d293bab74e | note | Conformance Criteria - Degree of saturation should not exceed 80%
08537d5f-4a0c-573a-a3c1-d39f09e519c3 | note | Records - Pre-seal checksheet (CS-4060)
| checkpoint | 4.15 - Chip seal laying
d8fb7d51-db7f-59ac-8eb4-72d89aea975a | note | ACTION (Hold, Monitor, Witness) - M
4eda1095-4a39-5e97-9396-dc14660e75b1 | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA M/6
756d26d9-b79b-565a-b282-396208cc5b49 | note | Frequency - During Construction
0051120d-4222-590a-b9a5-c9b671e0f618 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a0d2c8c2-86a0-5a7e-af94-7ba01bf0fe45 | note | Conformance Criteria - Chip seal will match existing seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
a228eca9-bb26-5144-92a7-241f48e01d72 | note | Records - Photo's
| checkpoint | 4.16 - Verge
f17a5978-f022-5980-aefd-a21fe408f485 | note | ACTION (Hold, Monitor, Witness) - M
831a439a-f6d3-5880-bd53-2ca39bbc3142 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
178ce6d7-0b4d-5033-b2ce-deddf9904c1a | note | Frequency - During Construction
1c1d93c0-b2a9-5d94-8eae-f88e4e909016 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
171f9219-b694-5de1-9eba-b4baff33d4a1 | note | Conformance Criteria - Verge reinstatement to match existing
bab5eba6-b22b-57d3-896c-c21f10141478 | note | Records - Photo's
| checkpoint | 4.17 - Sweep & Line mark new chip seal road
d7ec98cf-1d78-533f-9658-fb694cdfd56a | note | ACTION (Hold, Monitor, Witness) - W
70362e1f-b03d-5c3b-9ac0-2fec1751085b | note | Specification/Drawings Reference - TNZ P/12:2000
d6ac6e36-b352-5525-9104-a4a62a49cfe1 | note | Frequency - During Construction
1dd2d797-4310-59a2-b5fc-8af5b460ae47 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
615e77f3-90fe-5221-a653-04ba4a2ee7e3 | note | Conformance Criteria - As per TNZ P/12:2000
b9ea0ed8-6d8a-561a-8079-8da3ee899d55 | note | Records - Photo's
| checkpoint | 4.18 - Install Traffic services
a5515068-2261-5479-b4f0-3cb3b7182bf9 | note | ACTION (Hold, Monitor, Witness) - W
c6fcb241-e371-5f18-9dad-2376c68dc9c5 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
7bbd97b3-4f5a-583c-b99f-d3b24e4c8102 | note | Frequency - During Construction
d5a6f097-efa5-5774-965b-52f1f379737f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c05f1cad-f858-5fac-89de-bbd2771f85c7 | note | Conformance Criteria - Traffic services including signs and edge marker posts to be supplied and placed in accordance with TNZ C/20
bc41fc26-2540-5ded-8b67-612583f44bee | note | Records - Photo's
| checkpoint | 4.19 - As-built Survey
fa744596-59ef-5f9c-8e91-e92a908c91f9 | note | ACTION (Hold, Monitor, Witness) - H
26261f5f-7784-5943-9e0c-502c678934bf | note | Frequency - At completion of Lot
bf1072e0-d007-52af-b1e7-313347889819 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
966f64d8-5bfa-550c-9258-25c8bd5cfad0 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
bfa7950b-a82e-5e8e-9c24-b9198fa22823 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 5: FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Quality Assurance deliverables
85680821-106c-5ad5-b2f1-c0dfabac1e00 | note | ACTION (Hold, Monitor, Witness) - W
bcc20ede-d4bb-5724-afa1-da6d53ffd737 | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
1a6c4c76-f022-57ea-b64d-961adac549bc | note | Frequency - At completion of Lot
fc90df9e-2dfa-5850-ad45-4e516892bd5c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
034f5d3b-3de3-56ed-9d17-38d29c4a2620 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
1112bc04-6f45-5d1c-a430-f29279f287a4 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 5.2 - Completion Sign Off From Fields Below
6dff8cb4-a725-545c-b9a9-aff3fe9787fb | note | Records - Signatures
| checklist | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress | itp | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress |  | 16d67872-34dc-46d5-abd6-75d9f8e815e1
| section | Details
| checkpoint | Project Site reps.
b83b48a3-7df1-5d0d-afd3-d9b4ffe2c781 | textbox | CPS Eng.
a7fa664f-c6da-5edc-9061-190b7182fffe | textbox | Site Engineer
4c1950af-ad1c-5e56-88ab-a2664afc00e2 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
4c1edf87-11fb-511c-9dac-b41434318ae0 | note | ACTION (Hold, Monitor, Witness) - H
9795616a-7b9a-59ef-9385-2dc7bb73db61 | note | Detail - Set out line of pile as per contract drawings and specification.
45d83aec-5e11-5cb0-803f-98553899211d | note | Frequency - Prior to commencement
2cb56425-4431-5a3f-a00d-2bacf87fbe11 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
00419cc6-2628-5442-bc22-2add6594ddfd | note | Conformance Criteria - Consistency with Construction Drawing
ea382de3-2719-522c-a8c2-dd61556f361d | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 -
5b4b8db4-f585-5ea6-8a07-cd5467a88e1f | note | ACTION (Hold, Monitor, Witness) - W
b63f25e0-26fb-5b08-aae3-861ace5d3093 | note | Detail - Any services in the area are to be clearly marked before any work commences and to be potholed to confirm their location
6af9e722-921e-5946-aec6-0879beb73edc | note | Frequency - Prior to commencement
c7672b76-6802-5254-a7c4-f1d70dc3fb73 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
93e488a8-5e38-51eb-a3ae-c3c3886681aa | note | Records - Site record sheet/Daily diary
| checkpoint | 3 - Material Compliance
63f18d8b-7adf-54e0-9be8-5909fba258cf | note | ACTION (Hold, Monitor, Witness) - H
0164a95f-3e7c-5138-9acc-302583d546a5 | note | Detail - Driven piles to be 310UC137
14d7108b-c0c1-5be3-a2de-c2d7803cb4fa | note | Frequency - Prior to commencement
121c1fa7-fd7c-5329-882d-b8ce26ad77c6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
bb66e546-d918-5182-9951-4594a49b6b4a | note | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
2763e0ca-7038-56b1-adaf-3d6a4985f89b | note | Records - Data sheets and mill certificates
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
4d9b4479-baed-5fe3-b7f1-98508bcdde0d | note | ACTION (Hold, Monitor, Witness) - H
e4eceb23-3cb0-5000-b225-88534f8c7b20 | note | Detail - Walers to be 200UC52.2
e5e77908-9cf6-530a-bbfa-c9ce6f8c8dd5 | note | Frequency - Prior to commencement
50b7d8f6-c2a0-5dd5-be4d-2f8fbc8d91d4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
292d2729-8a76-562e-b0d6-9146c2e5d803 | note | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
ba50b2f5-ce12-56ee-9ec2-d52f698e6bbf | note | Records - Data sheets and mill certificates
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 -
050bb266-aae9-56ae-990b-3e5eb69313ea | note | ACTION (Hold, Monitor, Witness) - H
e0c519ce-7b2e-56de-87f5-bd636c879b1c | note | Detail - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade 300 as shown on the drawings
d68d46fc-69ee-53d6-88e2-f7bdaed39d95 | note | Frequency - Prior to ordering steel
ac8114a7-68e4-5b60-9bfa-bdfb81d03018 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
2839fc17-743e-5a92-9659-f2be9b1b384e | note | Conformance Criteria - AS/NZS4671&NZS3109
bdb8bfd9-5e5c-516c-aac3-efd17849984b | note | Records - Detail Sheets and Mill Certificates
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 -
be0e4ae3-3d30-59c6-b8b3-4ba581853b40 | note | ACTION (Hold, Monitor, Witness) - H
70e126ed-2f22-5ad1-a821-2d2241add272 | note | Detail - Any welding or mechanical splicing to be approved in writing by the CPS Engineer
697d9d95-238e-5a79-a817-7e0e830efed5 | note | Frequency - Prior to welding or splicing
a8c75b7d-878e-5119-862a-3f0948b1499a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
78240f4d-a604-57bb-8a92-8caa35c33292 | note | Conformance Criteria - AS/NZS1554 part 3
4f288608-d45d-5042-a324-bbc31203f6b6 | note | Records - Mark Up As Built Drawings
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
ad9ffd7e-cf8e-5577-b74b-6218dd53e956 | note | ACTION (Hold, Monitor, Witness) - H
e56014cf-f442-5fd3-9a8d-a90f5d72d769 | note | Detail - Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer
d4028933-0996-5806-bcf1-e38ff6982e34 | note | Frequency - Prior to cutting or bending on site
32359a3e-5f5f-5db7-8ac5-86e44e25ee7f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
acc50786-ec71-56ad-9e1d-6b9e3e56c426 | note | Conformance Criteria - NZS3109;1997
f0d7ad2c-7902-5f29-aa69-5cb44c976268 | note | Records - Mark Up As Built Drawings
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Pile Line
c265c885-d832-5792-8c5f-ada1a5f7ccea | note | ACTION (Hold, Monitor, Witness) - H
514b539e-57df-5e1b-b541-6c2dedab05c6 | note | Detail - Check if the bench has been excavated/filled can accommodate the entire pile line
77eceded-ef0e-5861-8b27-7ee3a7a9cc9f | note | Frequency - Prior to Commencement
b8bc6884-0008-5297-a8ba-ab52f9d76b31 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f415db86-b807-5b3b-b7e7-8ddcd30ae6ef | note | Conformance Criteria - Relevant Drawing & Survey set Out
14718fdc-de16-5e6c-89d9-00af409f75dd | note | Records - Site visit agreement
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Driving Operations
ce761580-9ede-53d2-9f71-a2d951cfb30f | note | ACTION (Hold, Monitor, Witness) - W
57c2d411-bb2d-591b-875f-2fd90db788ea | note | Detail - Check driving performance, verticality and position
67479033-5940-5c62-99d1-0344e75337ac | note | Frequency - Each Pile
32926d4d-c7da-5b60-b005-f2601706ca96 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6cbfb8a1-a9e2-5851-8153-720320124aa4 | note | Conformance Criteria - Piles to be drive vertical checked with a spirit level
77d9fac7-c4a5-5b5d-8044-1db5bfb0dbfd | note | Records - Piling Specification, Relevant Drawings, Pile Card
| checkpoint | 10 - Testing
2bd8d1fa-f9f7-5006-9022-6c9edca9e45f | note | ACTION (Hold, Monitor, Witness) - H
7b0d71f4-4833-50ae-91aa-63b686337871 | note | Detail - Ensure penetration depth of 3.8m is achieved
7b9da82f-c327-55ff-99a5-e513f8b07b8b | note | Frequency - Each pile
7ce687c7-bfc1-575a-bc24-1a189856fc87 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - measurement/visual inspection
1ddda249-ab24-5eb6-8c1c-64de161e1584 | note | Conformance Criteria - 3.8m embedment in river bed in acordance with Design Depth
72136b54-bf8c-5876-a7f0-ef02be9413cc | note | Records - Pile Card record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Reinforcement Cage
1b336a26-ded0-5d41-b189-b6e811edb999 | note | ACTION (Hold, Monitor, Witness) - W
ee223243-2d0b-543d-8481-65563eefa8e7 | note | Detail - Check supply and installation of reinforcement cage
9a31dd6e-86ad-5299-a8a9-ac369355a1df | note | Frequency - Each cage
47640df9-bcd5-5d45-b64a-afcca28aa09c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
005cb709-f6df-5c7e-8908-8973669b8d3b | note | Conformance Criteria - NZS 3109 and being in accordance with the drawings, ensure cover of 50mm from face of formwork
77e02181-0546-55b1-bc6c-f3d00c73a2f5 | note | Records - Reinforce cage record and site photographs
| checkpoint | 12 -
c6f87830-798a-5894-827a-01f04ef4d6a8 | note | ACTION (Hold, Monitor, Witness) - H
98c60a6c-ae95-5a44-bf51-8df557b8b063 | note | Detail - Arrange for inspection of installed reinforcement cage
8072c07e-7e94-5d47-bee0-0be089585c1a | note | Frequency - Prior to placing concrete
d6d57f61-b71c-5be1-8047-f2d7fd831d7b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
deaddb39-94da-5d58-9e8d-ab9e118aa30c | note | Conformance Criteria - In accordance with the drawings ensure cover of 50mm to formwork and 40mm cover to piles and waler
54e624a9-29e9-52ea-9e66-d333655e5528 | note | Records - site photographs/ inspection report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Formwork
15d2a0b3-b8fe-5db8-a1df-7f3a748fd8c7 | note | ACTION (Hold, Monitor, Witness) - W
9ce47331-ecac-50c7-847e-b0edcd4dc1f9 | note | Detail - Ensure formwork is competent to contain the required volume of concrete
28f1d376-0b76-53d7-9794-206d711f839e | note | Frequency - Prior to placing concrete
51454960-4e03-5502-a793-4c6b6f2840b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3ecc90ce-c71b-527e-a5a1-627a3ebd2b1b | note | Conformance Criteria - 50mm cover to reinforcing. Formwork is straight and true
62648827-de6c-5fc1-a5d6-34c4bc985cdd | note | Records - site photographs/ inspection report
| checkpoint | 14 - Concrete Pumping Operations
b6eb8fd4-d073-5953-a81f-5a6fb89ada31 | note | ACTION (Hold, Monitor, Witness) - H
ca9d3b58-a5f7-52b0-aa78-2c3e1e68f63e | note | Detail - Concrete required is a 30Mpa mix design required for a pump mix is 13mm aggregate for pumping
f99ed9e6-317c-5653-a068-801c58152a3a | note | Frequency - Prior to commencement
7113ef0b-734c-5449-9c16-89caa11090c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
d42376b8-45a5-5128-a503-0b342e030d2c | note | Conformance Criteria - Concrete Mix design acceptance
77d37329-54f6-5411-b101-5a61923ef78a | note | Records - concrete mix design approval prior to comencement
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Concreting
f88e8def-645f-59c6-b031-117fbc8f4fcb | note | ACTION (Hold, Monitor, Witness) - H
c9c054fe-09a0-5e7d-b992-f3f1f51bc894 | note | Detail - Pre-pour inspection and check sheet is required prior to comencement
31539dbf-229c-52af-8188-9a5e643a14a0 | note | Frequency - Prior to concrete pour
6ce53a33-402e-5fb9-90ef-04c5ecbbcf69 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
11b84f34-fca4-58de-a1a8-7d104eda2c26 | note | Conformance Criteria - Concrete Inspection check sheet sign of
f7c60a78-de74-529c-94f9-a79b2145eadc | note | Records - Concrete check sheet signed off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 -
6b71a992-0f89-5fde-b9b3-8e272f5bb19c | note | ACTION (Hold, Monitor, Witness) - H
fd2d5ee9-1d7c-5c66-9705-8753c9d3f8ac | note | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets
83fb1eba-783b-502b-93f7-4faa36944f3d | note | Frequency - Prior to concrete pour
b85967ea-8a15-55dd-a879-9f504bfa192a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
7aa6c9c9-bc7b-5e44-b3a0-0f97bfe6c940 | note | Conformance Criteria - NZS 3104
f13a9e4b-d7f4-5c2b-b5f9-5219c48ab0bf | note | Records - Concrete docket & Concrete test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 -
cf20a106-4b21-5289-9cb3-1446db16c311 | note | ACTION (Hold, Monitor, Witness) - H
9ee2979d-5b97-5fc6-bba5-29779474aad2 | note | Detail - Post-pour inspection and Check sheet for concrete placement method and finish
43c0e116-affc-5785-b1be-26e249a53434 | note | Frequency - At completion of pour
6135e4cd-fd60-527d-85dd-adfad8db71d5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
e9c433f0-956c-5870-aba5-9c6204953368 | note | Conformance Criteria - Concrete Inspection Record
6c46f996-1179-5d6b-8c24-d83fda4d2716 | note | Records - Concrete check sheet signed off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - As-builts
76e9ca74-a2e5-5d7d-9386-52a5d53a837d | note | ACTION (Hold, Monitor, Witness) - H
4e7a11f1-f795-5939-a0c3-c7353c5826b9 | note | Detail - Red pen mark up drawings to be included in QA file
05427f48-a7f8-5a06-85de-4d974aa84720 | note | Frequency - At the completion of the Lot of work
66ba4f71-c521-56fa-ab3c-3d54c4e14329 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
4f504f53-2dc4-5a82-93ba-60c4c19adcef | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 19 - Quality Assurance deliverables
2e588117-a59c-5115-8248-49af172aa03a | note | ACTION (Hold, Monitor, Witness) - W
621757a6-cbae-574f-a206-76c60108518d | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
ac858838-1557-561e-9bc7-cf096c8c5920 | note | Frequency - At completion of Lot
5f117cea-5b38-514f-b12c-7d32d067e8cc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3bca6603-a25a-50aa-9f52-14a7de144f01 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
2cd137c8-ae57-57c1-85a2-a865dd536304 | note | Records - Asbuilts, NCR's and RFI's
| checkpoint | 20 - Completion Sign Off From Fields Below
970acaf9-ceb8-50d0-9fe0-0e6572edfd46 | note | ACTION (Hold, Monitor, Witness) - H
b8293da3-1477-5297-9e66-3885aab032ac | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - F3202A - Culvert ID 614 | itp | ITP - F3202A - Culvert ID 614 |  | 198da203-19c9-4d91-875e-d1d8e191d2d4
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
f1c0b22f-bf16-5f5a-81ba-adf0948edef9 | textbox | CPS Eng.
3e1ad4e6-bf4c-575d-9c2f-e926f7251ccf | textbox | Site Engineer
a4c2b72e-98e5-54a9-a612-23a0a9a345c8 | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour (D50=450)
6c39692b-6961-5fbe-8572-d5d85ad6169b | note | ACTION (Hold, Monitor, Witness) - H
6120b79a-254c-542a-9e08-0eee147e83f1 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
8e5a7e23-f3bd-599a-8ab1-f925d09dc4c2 | note | Frequency - Prior to commencement
9ec585a5-5910-5e58-bb0c-c346ea58cc39 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
b2e6de74-3d6e-574d-80a0-dd5be51e2b9f | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material.
7596ca68-bfb8-519a-9b5a-6ed7e5d2356d | note | ○ Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
fae7f3ce-bfd7-5c5a-8296-f839bc095dba | note | ○ Rock size to be confirmed by CPS Engineer
c9667aa7-84e0-5cd3-9812-85d57406e8a5 | note | Records - Material source test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
82f33349-0f17-561a-95e5-5424abeebe3a | note | ACTION (Hold, Monitor, Witness) - H
3ad961b3-435f-5829-aedb-2d7252d900e0 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
414cfcb9-86bd-5619-8040-7f16682cab7b | note | Frequency - Prior to commencement
41b068d9-5d8a-5a33-aa2a-9bc9cb2f16b7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
b23ba344-d198-5250-9fc2-b249012a68dd | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
19c36cc1-565a-5723-ab43-3197e2bd35a4 | note | ○ Material source testing
dcccfe01-d031-5ba0-8057-4dfa09eccd71 | note | Records - Material source test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Class D A39 Geotextile
dcad168a-067e-5371-9d7a-988c3a1c13b7 | note | ACTION (Hold, Monitor, Witness) - W
c4cb42ca-7bf1-5d4d-9c34-df63438f0273 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7
83b2cb8c-5ee5-5c0f-b525-991c04d67923 | note | Frequency - Prior to commencement
40d12321-9574-5975-a0af-0bd071e1dad7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
da647e4f-eebd-5f8c-b5c1-34647f895649 | note | Conformance Criteria - Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill
dfd37a2b-10a5-584e-87c9-6eeb93ceaf7c | note | Records - Material certificate(s)
| checkpoint | 1.4 - Class E A49 Geotextile
a2fb517d-e009-5c1d-a6e6-c683689ba8c4 | note | ACTION (Hold, Monitor, Witness) - W
df719271-d7fe-5622-8ddd-d75c79e49879 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7
4b93207f-2635-525e-9271-1941e918aa11 | note | Frequency - Prior to commencement
0fa11052-d5ce-567f-9332-48e55301c5d0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
8d3d3dbd-0fba-5a18-8cd6-d461a102fbfc | note | Conformance Criteria - Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill
ee07ec4a-62b9-571c-9088-1aa0e1fca755 | note | Records - Material certificate(s)
| checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
e8c4a53d-e969-5abf-a3d8-c35d0e359798 | note | ACTION (Hold, Monitor, Witness) - W
cfb284ea-d555-5825-bd0e-acc2ded61ee1 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
fa5347b0-5792-5f61-9f6c-8e8d828bfec1 | note | Frequency - Prior to commencement
2b561ff5-c7f4-5015-93d7-e2b01eddf5ff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
9c99aa59-f10f-521e-8356-8272055b51b0 | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
3a6079a7-8a75-5d84-a036-9f5db52f5100 | note | Records - Material certificate(s)
| checkpoint | 1.6 - AP40 (Basecourse)
fa2a4822-bdda-5f61-bd01-7aebd39615b1 | note | ACTION (Hold, Monitor, Witness) - W
5b729a51-0086-5e04-95a0-2003af210767 | note | Specification/Drawings Reference - TNZ M/4
7161d828-a3a4-57bd-8a8f-ef8448fb7149 | note | Frequency - Prior to commencement
13213340-a379-539f-b909-f82ab45452b8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
5ab66b82-57e3-513d-bb27-3e3c1afdf249 | note | Conformance Criteria - Comply with TNZ M/4 specification
5c375363-44fa-5294-962f-01fe32a13c09 | note | ○ Source property testing
087ec782-cb70-5bad-ba25-0cdd5812da19 | note | ○ Traceability of all materials delivered to site
d4edb520-edd5-5708-b900-f0893362c00d | note | Records - Lab test reports, Delivery Dockets
| checkpoint | 1.7 - AP65 (Sub-base)
262396ef-681d-5a8e-aed6-c85ebcafcb9d | note | ACTION (Hold, Monitor, Witness) - H
464babcf-17c6-53c8-955e-4d2122679599 | note | Frequency - Prior to commencement
43b8ed77-9274-596d-8054-57da8da9b888 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
e74ef82b-cd20-5278-9f6a-c23898ecc9e4 | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
cc3c9ef9-6508-5d38-8027-daf63f3cb1b8 | note | ○ All fill material to approved by CPS Engineer
fed5a7ff-59df-57c2-baf9-073447a33533 | note | Records - Lab test reports, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 - Grade 3/5 Chip
2c275679-8a69-57cb-8ed7-bc34cb7e2ab3 | note | ACTION (Hold, Monitor, Witness) - W
d8676812-5959-5fa1-949b-56595589a287 | note | Specification/Drawings Reference - NZTA M/6
fb645473-11bd-5d38-a952-28f8ce4729b0 | note | Frequency - Prior to commencement
0aa99ca2-e06d-53e6-929a-b4f2ab02923d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
bb71ae60-c34c-5927-8de7-d350ff18989c | note | Conformance Criteria - Comply with NZTA M/6 specification
c6fcd170-77bc-5399-8b4f-46082412a0f5 | note | ○ Source property testing
738ed4ee-ba3f-5447-bdd4-fadb3282ffb3 | note | ○ Traceability of all materials delivered to site
a97abd68-1197-5cee-b5ae-a7abfe799e24 | note | Records - Lab test reports, Delivery Dockets
| checkpoint | 1.9 - Cement Material cert
8a33b583-550e-5bd9-81e1-d401f06fa6cb | note | ACTION (Hold, Monitor, Witness) - W
1af6248c-61cb-5288-a81c-b8e181defc92 | note | Frequency - Prior to commencement
22d6e878-dc90-5ad0-a9be-9532c6d3e93c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
936f45eb-ff43-5d3b-8fd1-ac4516763db8 | note | Records - Material certificate(s)
| checkpoint | 1.10 - Bitumen
7c31e1f6-9287-5eb9-b92c-90e95cad4fe6 | note | ACTION (Hold, Monitor, Witness) - W
4ded7682-4281-53d2-ba41-6d96436548ec | note | Specification/Drawings Reference - TNZ M/1
e4429fb0-3a61-54f5-94f6-00229a8b0d11 | note | Frequency - Prior to commencement
2a5be107-a666-53df-b947-7d1a8529b913 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
5ea3a2ea-c82f-571f-94a8-2a6261b1ae62 | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
6b336a7e-4ef0-5c1e-a197-fb4b46a6052d | note | Records - E2 Certificate
| checkpoint | 1.11 - Galvanised Traversable grate
ae6672e0-0ef8-5481-a46c-f2230441c640 | note | ACTION (Hold, Monitor, Witness) - W
4e6d05b8-c105-53f1-8438-9c9015420321 | note | Specification/Drawings Reference - F3202A-Culvert ID 614
e471f33e-f114-566f-8bbf-f727c659818e | note | Frequency - Prior to commencement
06941cb3-f26a-5526-acdd-4c0e84fb7051 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
a8eec299-82fc-5b7f-8384-32244c8a2f2d | note | Conformance Criteria - Galvanised Traversable grate mounted on headwall
deca79b7-e91e-5f18-9688-00798f0bf39e | note | Records - Manufacturer cert, Delivery dockets
| checkpoint | 1.12 - Precast Headwall
b253cc31-bffe-57e3-9082-bdc2d47f65cc | note | ACTION (Hold, Monitor, Witness) - W
0cb7f161-0746-589f-81d4-15b0ed125083 | note | Specification/Drawings Reference - F3202A-Culvert ID 614
d0094357-0399-577a-8d33-312cb334d22f | note | Frequency - Prior to commencement
a93ded59-5f15-55bd-8610-df2959012d56 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4d63e31f-84d4-5ad7-8fc0-e1d24bfe633f | note | Conformance Criteria - Delivery Dockets are collected and signed before precast headwall materials are removed from the truck.
cefb5932-5f3b-53da-aed1-712aab064357 | note | Records - Manufacturer cert, Delivery dockets
| checkpoint | 1.13 - Precast RCRRJ 1050 pipe
f6e2dadb-150f-5c86-805e-9f0edafc0ea5 | note | ACTION (Hold, Monitor, Witness) - W
355e22cc-1463-5d01-a1cf-72e7c421299b | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614, AS/NZS 4058
030b2504-e114-55ed-b56b-c9f08432b945 | note | Frequency - Prior to commencement
479f7a08-f921-5f8f-a892-421c553ab422 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
0f791c90-b6bf-5eef-a2c6-6dc06d253667 | note | Conformance Criteria - Delivery Dockets are collected and signed before precast pipe materials are removed from the truck.
6e68e986-ab89-5214-95e1-a161a323bfc9 | note | ○ Class 4 RCRRJ 1050 pipe to comply with AS/NZS 4058
e832370a-bafe-5fcb-b3a7-e5a7c4c0e2c2 | note | Records - Manufacturer cert, Delivery dockets
| checkpoint | 1.14 - Precast materials
432333d3-1491-5972-a27c-bdd3bccbd3f5 | note | ACTION (Hold, Monitor, Witness) - H
1afa993a-981d-57f7-95cf-404865155fec | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
efb0c5e5-c7d1-57c9-b13e-615d9e3b3057 | note | Frequency - Prior to unloading
e9f70c07-265d-5053-a9e2-ddcc538c5ef8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
97dc428c-98ab-5798-be98-cb769b7cb5a8 | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
b02685d1-a4e3-55d7-a1a4-3f00cbdd72cb | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.15 - Rock Rip-Rap
83eeecec-7fea-5bea-92a6-87f6806428a8 | note | ACTION (Hold, Monitor, Witness) - H
f2ecc357-15dd-5180-9b9f-da53c558c393 | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
831c62e7-4237-53c6-bd48-7f3e978a0176 | note | Frequency - Prior to commencement
c7a573cc-7e6e-5138-8a12-034cf20d13f2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e409e545-8253-5150-907a-ef1e3534ab0e | note | Conformance Criteria - D50=150mm Rock
bafb839e-3f86-588f-9cb9-bcd4985be2f2 | note | ○ Rock size to be confirmed by CPS Engineer
81f42940-9b1d-5797-9cd9-dcf5e790b1c3 | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.16 - Hydroseed
f337f0dd-db70-5988-aa81-e8bc58a97640 | note | ACTION (Hold, Monitor, Witness) - W
745a1e82-7e74-53ff-bc1a-0b3a77aa2f1a | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
d274d7de-e95a-53b3-a6b6-e59b3f5044f5 | note | Frequency - Prior to hydroseeding commencing
05e6efaa-6e96-56e0-a68d-6d54f02d2ff5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
a337dbb4-7b4b-5059-bf4b-fd21b3b164eb | note | Records - Delivery dockets
| checkpoint | 1.17 - 35 Mpa Concrete
564cdc50-2f87-5f92-b723-dc061cc42015 | note | ACTION (Hold, Monitor, Witness) - W
59e49571-7cca-5cac-b1fa-d17ce2b1748d | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
62027ade-fe7e-5d38-aadd-42055dd1cb70 | note | Frequency - Prior to commencement
a7154dee-842c-5bdb-9aa0-c9c59de4c428 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
47abff10-9abc-5c9a-9238-12fbd03b09ea | note | Conformance Criteria - Mix design 35 Mpa concrete @ 28 days for haunching
dae89020-d6b1-5387-879a-b4324bd9b62e | note | Records - Mix design cert, dockets
| checkpoint | 1.18 - AP20 (Bedding material)
ac506038-c7bd-5826-a53b-f34500417369 | note | ACTION (Hold, Monitor, Witness) - W
bc24ed6a-e0ca-5df9-99f1-70d1772b4029 | note | Frequency - Prior to commencement
7792eab8-180b-5d3d-9a3f-340459391041 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
7bc7ec80-adc8-593d-905c-706393c00d09 | note | Conformance Criteria - Source property testing
04a9f3e1-1d96-5c24-9e82-b267884083a9 | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.19 - D16 Rebar
d2f8f8d8-1d68-50ab-91c0-759a42abbcd6 | note | ACTION (Hold, Monitor, Witness) - W
28220890-27dd-5912-9346-c5f46b86034c | note | Specification/Drawings Reference - AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001
1d66e574-4676-5f13-aa3b-55299809d45f | note | Frequency - Prior to commencement
7f2a7525-e3d2-5408-b74b-6ee5dc20a796 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
eec4fae9-bb1f-51e1-ba5b-75bb6cfd6083 | note | Conformance Criteria - Comply with AS/NZS 4671 & NZS3109
93856b51-abe4-5653-8112-5e672324e152 | note | ○ Shall be D16 rebar for concrete pipe haunching as per design
1a90154e-589b-5368-adcd-d022da94d2a7 | note | Records - Mill Cert, Delivery dockets
| checkpoint | 1.20 -
551a028b-2d81-51f9-b193-4311dce17a1e | note | ACTION (Hold, Monitor, Witness) - H
8de447fb-8d14-596b-aded-bcf51a884ac0 | note | Specification/Drawings Reference - AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001
db511828-e355-5548-abcd-dfd51b6cb1f7 | note | Frequency - Prior to cutting or bending on site
3a2ca515-4ce1-58f0-9863-23a33fc8faab | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
3d0e0103-231a-594e-b3d7-05b2b62fa3ad | note | Conformance Criteria - Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer
6108c261-bb38-55f2-ba54-8de210bee954 | note | Records - Photo's, CPS COR report
| signoff | AUTHORITY HOLDPOINT
| section | Section 2: IN PROGRESS INSPECTIONS
| checkpoint | 2.1 - Survey Setout
1f24fd03-c0e3-508f-a4e5-9535614c03f6 | note | ACTION (Hold, Monitor, Witness) - H
b06f3ac8-71fc-50c8-be85-bd88695ebff1 | note | Specification/Drawings Reference - Consistency with Construction Drawing
5a821973-8f71-57a0-9b96-e030d4b25ddd | note | Frequency - Prior to commencement
ad505b60-f4b3-57f7-8d58-3162c69547fe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
98d1bc48-7a58-5fe6-8fc9-60f80a5e6564 | note | Conformance Criteria - Set out extents of fill and check against design drawings
a39e34a7-24ca-5ab1-b5b1-2afb2452ff4e | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
cf6aaef6-1638-5d29-b855-2d76b8ac1719 | note | ACTION (Hold, Monitor, Witness) - W
ef34c6a4-c1cd-52fb-a669-eaca24ec3aa9 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
b6ef889a-66c6-51cb-862d-eb2e2f5e7478 | note | Frequency - Prior to commencement
a9660176-3622-534a-b3a7-6980e135bead | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8a74b099-5192-538d-b01e-6a6bbed7ca39 | note | Conformance Criteria - Remove and clear the vegetation
dc03ea5b-3741-59ad-86a9-fd501773841b | note | Records - Photo's
| section | Section 3: CULVERT OUTLET EXTENSION
| checkpoint | 3.1 - Foundation compliance
ea98b308-fb78-5677-a07d-d95923dc3f90 | note | ACTION (Hold, Monitor, Witness) - W
45cbc0ef-f096-5859-b030-4c6b7089b224 | note | Specification/Drawings Reference - F3202A-Culvert ID 614
dc77bcb0-a11f-5b74-84df-48dbf4fc6c6c | note | Frequency - During Construction
962efecd-221e-5193-83f9-3fa5e4259107 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
b448d67e-06b0-557d-a7ee-f3abddf88123 | note | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
7e06cf6c-c400-583e-ab49-18fb06b629ea | note | Records - 1M Scala check sheet (CS-4000), Scala test results
| checkpoint | 3.2 - Foundation compliance
7fbb4f93-1672-52a7-a04b-26be1e7beaf0 | note | ACTION (Hold, Monitor, Witness) - H
d6542715-e108-5beb-be06-75353a4386f0 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
9a4d94ff-a984-59dc-a6ab-b0cba8dfc96f | note | Frequency - During Construction
4025bdd5-4512-5eee-9118-b06825d34aca | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a7504bdf-c94b-546f-a23d-5bab68227b25 | note | Conformance Criteria - CPS to inspect and approve formation level at outlet
dcf50019-403b-53ce-8074-0972b2adac40 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Trenching and Excavation
d87fae9f-d82c-5d35-9744-e39674f773e3 | note | ACTION (Hold, Monitor, Witness) - W
8ade21d8-c371-5e48-b06a-a66bf36b59a5 | note | Frequency - During Construction
519a4b0d-9b14-52cf-8fb6-c615fe8b733a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
9dfc7d74-29f9-500b-9512-0f9503f9bf69 | note | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
21c54a9b-2df7-54f8-beb5-d23c58a11590 | note | Records - Photo's
| checkpoint | 3.4 - Trenching and Excavation
86924117-55f4-51d9-9284-02309ab8cd96 | note | ACTION (Hold, Monitor, Witness) - W
2ed7cc73-9859-5654-9fc0-83fcc3f695a3 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001
ff95c829-efad-58b1-9b36-d62cefe3eccd | note | Frequency - During Construction
aeb32840-76e2-5f8f-aae4-c0649031a6f2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
0d114f7e-3485-5f39-bff1-466e25d409be | note | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
336c473e-cefd-5e2b-be70-1a8f6e34bb04 | note | Records - Survey As-Builts
| checkpoint | 3.5 - Pipe and headwall Bedding (AP20)
cf0eeb1c-0b2e-5d6c-891e-fc73b662c4bd | note | ACTION (Hold, Monitor, Witness) - W
eca14051-2d6f-58cb-891e-4df54afa0c17 | note | Specification/Drawings Reference - AS/NZS 3725:2007
4e996f9a-cd0d-55b0-8071-d8f850569362 | note | Frequency - During Construction
9f8b4806-c199-5aa1-afe8-d2fab144c19d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
05b9ab78-2f30-50b5-9b81-34ea6f93dd86 | note | Conformance Criteria - Comply with AS/NZS 3725:2007
658b96ff-391b-5720-be4e-ba18a85b847e | note | ○ Ensure correct thickness of bedding is placed and compacted.
6f4e6212-4aba-51fb-b5e3-7c6ebcd99868 | note | ○ 100mm thick bedding for <1500mm dia pipe
7fc98fe6-ae04-58df-8f0a-ffb4357b882f | note | Records - Photo's
| checkpoint | 3.6 - Pipe and headwall Bedding
64ec5ec1-a821-5371-8765-4fa726e8621e | note | ACTION (Hold, Monitor, Witness) - H
6b311e66-531f-5113-98c8-cf67c2170f18 | note | Specification/Drawings Reference - NZTA F3
94629ad1-8e46-570b-8800-caf5c741f5a6 | note | Frequency - During Construction
eff703ba-babe-56c3-af40-ae3fb7eb14eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
361a38c0-23e8-597d-b791-2c023872689d | note | Conformance Criteria - Ensure bedding material is compacted by Clegg (TBC by CPS on-site)
c69448c6-3114-55c1-9fa9-96838fa1ade6 | note | Records - Test report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Pipe and headwall laying
f162f493-6cf5-56ba-8760-49f409a100f8 | note | ACTION (Hold, Monitor, Witness) - W
970c8a4c-8c1b-51c9-aaad-f06ebd07929a | note | Frequency - During Construction
6ba0cfbb-3f49-5745-a6dd-b3d9e1fe5cf9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e9dfad7f-21dd-5e88-964d-d4166cab984b | note | Conformance Criteria - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm
357a3a9e-1bdc-5b36-be17-b68736e07ead | note | Records - Survey As-Builts, Photo's
| checkpoint | 3.8 - Pre-Backfill inspection
8a6e96da-1b76-5ed8-ace7-eea995f0db3a | note | ACTION (Hold, Monitor, Witness) - H
51714a7c-f155-543d-8890-ad18bbdf41d6 | note | Specification/Drawings Reference - NZTA F3
7866d8ec-e7d4-5174-ba00-403bbf35c083 | note | Frequency - During Construction
9ca221e0-928c-5ed3-9e37-740e60fb7784 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
b30c1815-b10c-595c-b23c-b0deb7e9062d | note | Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface. Check for gaps and/or defects and check pipe alignment for straightness
a3d2dd75-6e18-58cf-ab1a-dc2f2fe3a8a8 | note | Records - Photo's, CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Backfilling (Haunching AP65)
28380f48-ec4f-5961-b42a-c84aa4bb88b6 | note | ACTION (Hold, Monitor, Witness) - W
02c0e60d-c77e-59b5-afe3-029b78f5fa14 | note | Specification/Drawings Reference - NZS 4402:1986, Test 4.1.3
0d5d7292-9a37-5577-b952-717ea2d7a8dc | note | Frequency - During Construction
0c664014-f0f9-5727-84dc-294dc711b060 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
7177fa42-af0b-5eef-9cad-17ba6ab4da46 | note | Conformance Criteria - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms.
ee6dde5a-57d7-5654-8a20-564232b47dc1 | note | ○ Remainder of backfill to be done with excavated material.
25fed3eb-03e6-553c-a11b-52073fa6c172 | note | ○ 95% of MDD shall be achieved
ffd8555d-ff89-57be-8be2-84563f413b65 | note | Records - NDM test reports
| checkpoint | 3.10 - Existing road side Swale
f8fa7fb4-3aa7-5c88-afcb-ba22da79f1d8 | note | ACTION (Hold, Monitor, Witness) - W
932ad419-199b-58c5-8261-8332a28002c0 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
a92f71e2-01d3-5539-90e2-126a59f250ab | note | Frequency - During Construction
18d5c32a-4ded-5eb4-a29c-b61a50fffc94 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8ea8dd47-3444-5a3e-8f9e-2012f5c5a0c3 | note | Conformance Criteria - Reshape and form both ends of road side swale to match the rock chute invert.
ac1c0420-20f4-5d83-b7ca-93bfa58d0496 | note | Records - Photo's
| checkpoint | 3.11 - Swale geotextile installation
8ac743b5-71e7-52b2-ae5f-9639a59e59a1 | note | ACTION (Hold, Monitor, Witness) - W
2af00e94-f6e4-53b1-9fba-2e932b6c68cc | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
633a1e16-5115-5327-b4ac-db6822103fad | note | Frequency - During Construction
fdb1379d-fbe1-5613-bcdd-ae84d11824bb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
118b0c9e-342c-589b-abf9-00b09a8633ed | note | Conformance Criteria - Class D geotextile to be placed in the swale prior to rock placement and be laid/overlapped as per manufacturers recommendations
71bf46ec-6549-5de7-8826-cc13befe3172 | note | Records - Photo's
| checkpoint | 3.12 - Swale rock line
30a56a00-628f-5d37-8a65-bd85e3dcaeb2 | note | ACTION (Hold, Monitor, Witness) - W
b15728ab-4835-5d03-bde4-bcaf1ffae7a0 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
e003d582-d1f9-50b1-b75b-5d336654bf32 | note | Frequency - During Construction
3a6d6fef-9ac5-5a4b-96ad-0fdc59703acf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8b802f0c-b898-5780-8d14-b3ad62fcc176 | note | Conformance Criteria - >1:50 slope rock line D50=150mm, 300mm minimum thickness over Class D geotextile to be placed
9bd4ad5f-ce0d-565e-89e2-8e114538ca54 | note | Records - Photo's
| checkpoint | 3.13 - Swale rock line alignment
372f802a-f681-59dd-a80c-bb64f143487a | note | ACTION (Hold, Monitor, Witness) - H
cd250c76-0876-54ea-b7cb-eb0101d6a673 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
9a02f913-5b0d-53d7-89cb-d8f221152736 | note | Frequency - At completion
d7141539-1e31-52eb-8956-4723cbfd0bbf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
70ff1c02-ed5f-5e53-8c37-4e37954ccce5 | note | Conformance Criteria - Slope rock line should be >1:50 slope
e4516aec-57ce-5911-a173-0c50e9961e24 | note | Records - Survey As-Builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.14 - Outlet rock chute
b7b7e192-defb-5407-adc2-bae4abd5b18c | note | ACTION (Hold, Monitor, Witness) - W
a842527b-5a90-5647-aa12-47c61afd2347 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
212352a0-6f16-5f6c-bcba-4a946f5e9523 | note | Frequency - During Construction
bb11fa29-f4c3-5b64-bf05-9aa12c82d8d4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
2a2c025a-edb2-5bf7-bac9-01583f927b23 | note | Conformance Criteria - Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Rocks should be placed to a length of 1800mm in front of the headwall.
088d7114-5de2-5eae-827c-f7ac84d951ea | note | Records - Photo's
| checkpoint | 3.15 - Geotextile installation
c2e8d620-d84c-5fa9-9509-942912720d1e | note | ACTION (Hold, Monitor, Witness) - W
fc44896e-f8db-56d6-8b7c-2eb8926b1f55 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
637665d4-52f7-5ae2-9b78-4f0f06bea35a | note | Frequency - During Construction
5517d667-de39-5e25-80e0-37248b6fe30d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6e79032a-db58-519c-b4af-09f8a669b72e | note | Conformance Criteria - Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations
cb4c537a-baf1-5afc-84de-d1aeaddc2eee | note | Records - Photo's
| checkpoint | 3.16 - Rock Riffle
8ec1a5c2-e19b-508c-88ba-35c8af268731 | note | ACTION (Hold, Monitor, Witness) - W
ec7185b1-c7c5-5972-9c15-f312ade0ba0c | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
224767d6-9aae-58b9-858f-cf66dfee93e1 | note | Frequency - During Construction
557fabd2-7596-5961-833a-9c910612f39a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
c9ce0c6e-90b8-5268-b934-97a05a6ebf8e | note | Conformance Criteria - Largest rocks 900mm to be installed closely to form an arc shape facing upstream.
dee7ee81-1edd-5a31-a686-ecaae350c45d | note | ○ Reduce grading of rocks towards the toe of the slope.
89304abe-5564-5ef0-a206-8a34a9e5d6a0 | note | ○ Wash gravel/grit over to fill all voids.
4f377e5a-dd0f-5aae-9ae1-bce271d10ec2 | note | ○ Rock riffle to be installed to approx. 1V:5H slope and tie into existing streambed minimum 200mm
e4d8c0d0-ea03-51e2-8a3f-aa23ba21d8a0 | note | Records - Photo's, Survey As-Builts
| checkpoint | 3.17 - Slope above the rock chute
e8bf6cd2-c0fb-571e-9c4d-598ed923f569 | note | ACTION (Hold, Monitor, Witness) - W
d28141ac-51cf-5f41-ac89-8c15bcb91e9e | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
a0ae3a9c-2d53-528b-b621-d5d0b427c044 | note | Frequency - During Construction
7e97da32-f5e9-54c7-9cb0-7fe2ccb445a1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
f9e34b29-aa77-5f5b-b378-949ea512278c | note | Conformance Criteria - Daylight at maximum 1:2 existing ground and hydroseed / cover with pinned biodegradable erosion control mattting
354c0575-af96-522c-9690-f20576f23ca1 | note | Records - Photo's, Survey As-Builts
| checkpoint | 3.18 - Galvanised Traversable grate installation
daa144da-c470-51e0-b23c-ed9ee3ddfe15 | note | ACTION (Hold, Monitor, Witness) - W
83fc432a-d74b-5d75-beeb-603602453cf2 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
237fdc0c-2cc9-5fc0-b5d4-1f4cc7a5a1f7 | note | Frequency - During Construction
721d5b24-b4f8-57c1-8d7f-25ec6f7d38d7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
5e10f704-3c76-593d-a78f-8999d46311a8 | note | Conformance Criteria - Grate mounted on headwall in accordance with manufacturer's recommendation
d7db07b4-63a7-54a1-9085-78328a70c8c2 | note | Records - Photo's
| section | Section 4: BUTTRESS TYPE A
| checkpoint | 4.1 - Class D (A39) Geotextile installation on the excavated face
de581656-a551-58fd-b7c2-c2c3661ae225 | note | ACTION (Hold, Monitor, Witness) - W
a7318a93-f505-5cba-a4ba-8f3758f8e9c7 | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
b5c0405d-d85f-54ac-8d77-590317965227 | note | Frequency - During Construction
5d0ede96-dc6d-5f07-b09c-c87fae6989f4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
52c60ed0-0558-5404-992e-899a10852e31 | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
2c5af6a5-13bf-57ba-a373-94df7f8f3980 | note | Records - Photo's
| checkpoint | 4.2 - Megaflow strip or drainage blanket installation for seepage if Encountered
09bfd8e9-89af-5cb2-a7d5-cb11a796a3d9 | note | ACTION (Hold, Monitor, Witness) - H
6f9b3ae4-0b1d-5f83-b342-9840a4448688 | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
ff309149-9c14-5b02-aa1a-df00bd8ae534 | note | Frequency - During Construction
ac112e18-f6f3-52cd-bede-3d6816352bc6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d0354f39-5fba-50ba-9bdb-c8b264b9d523 | note | Conformance Criteria - Engineer to assess drainage location suitability.
3a94f429-a4c4-5222-aee2-82f9754d9cd5 | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
4f10e92b-4228-5c1a-b151-4d26964acc2b | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Bulk Fill placement
0b938f3b-4d5b-5289-b2fb-1cc62cfa2f1a | note | ACTION (Hold, Monitor, Witness) - M
8da35694-c34b-5b31-9df7-d4e5c43d72e5 | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
791da686-9e53-51e1-ac08-9dd5245b48ed | note | Frequency - During Construction
333bf4ee-766e-5979-8f58-36cb6199a63d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
1308d5e9-a449-5eaf-95ea-56f90804b0b3 | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
e16bda47-aaea-50fe-a935-8a9fb32d937b | note | ○ Fill should be placed on dry subgrade.
4d0a74c4-e4e8-53c4-9c4c-a405d2e70d41 | note | Records - Photo's
| checkpoint | 4.4 - Bulk Fill Compaction
c788d06c-aecf-57e5-9f26-3246a1f21a3f | note | ACTION (Hold, Monitor, Witness) - M
f92e235e-b2e0-5167-96ba-0c4f3da4c1af | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
a1a8b684-7f10-5457-b567-4a7c6dfded86 | note | Frequency - During Construction
9ac242e0-b22e-5b6b-aa76-a782d9b99a76 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
a8447ae9-b812-503a-9bd5-7e2a03e58b48 | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
8ef0169a-843e-56a6-9618-4ced7436e7d8 | note | Records - Compaction test reports
| checkpoint | 4.5 - Form and cut fill batter as per design 2H:1V
d9971979-c750-50c6-bcdb-5a8cba8399d5 | note | ACTION (Hold, Monitor, Witness) - H
0e2c7c86-022f-5c1f-87e3-808936839aea | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
9582448f-d18d-5e81-ac5e-57dfcf0686be | note | Frequency - During Construction
b58e890f-c26e-5db9-8330-3e1368775cea | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
93bf8771-a602-5187-9e8d-cf5c2c0901f0 | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
b1857b78-bd75-5643-949e-0ab318718d0d | note | ○ Slope angle of buttress is to not exceed 2H:1V
94c4a85d-70ca-518c-be60-0e56be400116 | note | Records - Photo's, Survey As-Builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6 - Rock Armour Placement
05c32811-6ed2-581b-ab82-d5a4151bb7b6 | note | ACTION (Hold, Monitor, Witness) - W
9076a82a-a16c-54e9-806b-268f0bddca05 | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
49594781-c711-56e9-87f2-3fe4f1c62e6b | note | Frequency - During Construction
dea90abd-b012-5bdc-b00a-d2f74e43226e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
8fbfe8d3-8da9-595b-9f31-03329a507497 | note | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
2dad5ffa-3e7f-527e-b0a4-ff39b875a7e6 | note | Records - Photo's, Survey As-Builts
| checkpoint | 4.7 - Rock Armour key into ground
b72b383a-8738-5813-ba95-49392af416ce | note | ACTION (Hold, Monitor, Witness) - H
4de48aff-2c9f-558f-a3a6-083249689356 | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
336845af-1fd5-576a-96d5-3176d2cdaa40 | note | Frequency - During Construction
72efed0a-e1df-502d-b7f0-38e61165de30 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
7e78fba7-d5d8-558e-8bee-2b433516adc0 | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
74bceb56-41fc-53bb-a25d-06b6c3c6312a | note | Records - Photo's, Survey As-Builts
| signoff | AUTHORITY HOLDPOINT
| section | Section 5: CULVERT INLET EXTENSION
| checkpoint | 5.1 - Foundation compliance
b5f8b102-fa00-5d2b-ae60-cc6119e7fb5a | note | ACTION (Hold, Monitor, Witness) - W
cbabf044-469f-5c26-8f23-8e41c69cbd69 | note | Specification/Drawings Reference - F3202A-Culvert ID 614
e061ae29-1433-50f3-a518-a9f74158f8db | note | Frequency - During Construction
b1326f39-1101-5dbb-a6b6-d704a8558cb7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
b2c8a284-31f7-5cda-81d8-917ba5d80890 | note | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
13324ffc-aeb3-5758-9c06-61f6cdb23dab | note | Records - 1M Scala check sheet (CS-4000), Scala test results
| checkpoint | 5.2 - Foundation compliance
15a6996d-21d5-5a62-a8da-6c5edd878efb | note | ACTION (Hold, Monitor, Witness) - H
18a76a60-002e-56d8-a935-09f91664d7d1 | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
bae720a8-5fbc-5802-a680-6567475d15af | note | Frequency - During Construction
9dd896d5-da34-55c9-9f6a-c7fbc3d3e5e3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
11ae6c19-2ea1-5ecc-a1e6-3bc16bab0f22 | note | Conformance Criteria - CPS to inspect formation level at outlet
d23d9203-e8bc-5618-99ac-faad58daf9ca | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Trenching and Excavation
0339ec87-257e-5317-a832-3ee75ea9bef9 | note | ACTION (Hold, Monitor, Witness) - W
14cfbcd5-3a3d-5982-b456-848474fee8ad | note | Frequency - During Construction
b2c2b34e-b06d-5b47-b7ee-3773d2df25d6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
bdfddba9-035a-5c79-9ed5-00bd154f7568 | note | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
e63432f6-d214-5c43-bb80-ce23ee956110 | note | Records - Photo's
| checkpoint | 5.4 - Trenching and Excavation
01e684a3-2e23-5581-875c-34d3d9798728 | note | ACTION (Hold, Monitor, Witness) - W
764e46e7-49eb-5012-b6d8-e67384983afd | note | Frequency - During Construction
210616ec-96e8-5256-be8e-967bd8996ea1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
07a449ab-e06b-55ee-9dc0-1a4c3773a00a | note | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
d7915013-9802-5c39-a1a5-bc5124cbb5db | note | Records - Survey As-Builts
| checkpoint | 5.5 - Pipe and Bedding (AP20)
72dd8861-25c9-5584-ae8c-403b93e089a9 | note | ACTION (Hold, Monitor, Witness) - W
acf9b0d3-a12b-5136-a91a-97119c643af3 | note | Specification/Drawings Reference - AS/NZS 3725:2007
97bbf516-1340-52cf-abea-c812685858b0 | note | Frequency - During Construction
4e2ee1ec-d521-5318-b61d-aaa6fb6b36a7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
686283af-b9ba-5a9e-b3e4-a0e56b34432a | note | Conformance Criteria - Comply with AS/NZS 3725:2007
2cb2c166-ba51-5eb5-b247-d693327e4a77 | note | ○ Ensure correct thickness of bedding is placed and compacted.
2a9457e0-890a-53f6-946c-612889122495 | note | ○ 100mm thick bedding for <1500mm dia pipe
dd9cc8b7-576b-5494-9c77-d8b5b72179ae | note | Records - Photo's
| checkpoint | 5.6 - Pipe and Bedding (AP20)
c7c2828f-3711-5359-bd76-d6f9e2c1f246 | note | ACTION (Hold, Monitor, Witness) - H
7d285644-1238-5e93-a26d-805dd0ed1536 | note | Specification/Drawings Reference - NZTA F3
891c5364-7bf2-567e-b76c-c22ed8812149 | note | Frequency - During Construction
5d495be7-9a97-5e18-9f50-d6b34b6bc229 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
afe47449-70ed-517c-9dc6-914a49c91964 | note | Conformance Criteria - Ensure bedding material is compacted by Clegg (TBC by CPS on-site)
1ab11dfd-dfb5-5d21-b66a-583503bf6119 | note | Records - Test report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 - Pipe laying
16147e83-2117-54e8-a155-7f84a2bcfca2 | note | ACTION (Hold, Monitor, Witness) - W
8c9e7e91-39dc-5710-bff2-0a28b6b0677b | note | Specification/Drawings Reference - NZTA F3
b0a39fab-4de2-5d6a-ab3b-1d11aa57ddc7 | note | Frequency - During Construction
b80250f4-50db-5783-995a-9e88197617af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
94b8fa21-2e0a-5a91-823e-8d68a026afe3 | note | Conformance Criteria - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm
b8aff680-10b9-5b27-9339-cfcab6044189 | note | Records - Photo's, Survey As-Builts
| checkpoint | 5.8 - Pre-Backfill inspection
3bcf7eaf-98b3-5228-be37-2fc33347a536 | note | ACTION (Hold, Monitor, Witness) - H
6677ff43-a889-5aa4-8eaf-e4df73f78ce7 | note | Specification/Drawings Reference - NZTA F3
e6d16257-95ea-5aaa-8649-fda822618a5e | note | Frequency - During Construction
ee88121a-98c7-5267-b172-69c1f9dc992a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
fa208e19-22d3-5d94-be32-dac95d75517c | note | Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface.
e45ce26f-4ae2-5027-9494-f20ef8176c72 | note | ○ Check for gaps and/or defects and check pipe alignment for straightness
d9499017-12e6-52ec-a0c6-34f4833a32dc | note | Records - CPS COR report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Backfilling (Haunching AP65)
e6301a9a-8ef7-5a3e-accd-1ff1c270b378 | note | ACTION (Hold, Monitor, Witness) - W
2363a7ca-0ba3-54ed-a4a8-41e752d0ec34 | note | Specification/Drawings Reference - NZS 4402:1986, Test 4.1.3
ed4911c5-bdc3-5d1b-8de8-b3782fc8b2a1 | note | Frequency - During Construction
3144c195-062b-5029-b335-beb544da5312 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
2fd73cd6-6415-58bf-913a-2f6e91667676 | note | Conformance Criteria - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms.
617d6251-6ffa-5ea6-9d60-700480198fe5 | note | ○ Remainder of backfill to be done with excavated material.
7996001f-feae-5a50-ba1a-a99063b66690 | note | ○ 95% of MDD shall be achieved
bb33acae-96ad-5f52-8e20-f79435fb3ccd | note | Records - NDM test reports
| checkpoint | 5.10 - Concrete haunch around inlet
8ffa810a-fbe5-55e8-9c4e-c1f5b1d98744 | note | ACTION (Hold, Monitor, Witness) - H
268797c3-3f22-5ff6-9050-92903527410a | note | Specification/Drawings Reference - F3202 Stormwater inlet details, NZS 3109
f16f482a-2455-5bc3-806a-7b10a5a168b2 | note | Frequency - During Construction
b4790978-c554-5da5-a8e4-11d958ca2e96 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing and visual inpsection
daa77120-f135-51e8-bc30-1f7a64c8b602 | note | Conformance Criteria - 300mm concrete apron to be poured around the inlet. 35MPa concrete @ 28Days.
3b5b6001-701a-5f33-bb0f-34a8b80beec8 | note | Records - Concrete compression test results and Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.11 - Concrete haunch around inlet
f7dfaf14-d323-5362-a810-4271fde26159 | note | ACTION (Hold, Monitor, Witness) - H
d702f6f4-0940-5108-b2d8-aa14cc88b6e6 | note | Specification/Drawings Reference - F3202 Stormwater inlet details, NZS 3109
f22e90cd-4bc1-54e1-a361-86ade67bf34f | note | Frequency - During Construction
1af33502-fbbf-5f57-997e-c0358e958360 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
44b55ab6-c92f-5d18-9a79-c2b2509eba27 | note | Conformance Criteria - 300mm concrete apron around the inlet with D16 reinforcing bar centrally, 50mm NOM. Cover.
fd1a4196-939b-5f8e-b1c5-bf64b9ce59bb | note | Records - CPS COR report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.12 - Inlet pipe cut
91e9ba1f-22b1-57a0-9bb4-771442ac0614 | note | ACTION (Hold, Monitor, Witness) - H
eaf8eb18-4456-5f34-a352-e010cf2ea1c3 | note | Specification/Drawings Reference - F3202 Stormwater inlet details
94b65a1a-8aa8-5874-8193-8d9c83363302 | note | Frequency - During Construction
5a75aec7-23ea-588d-8524-95612adabd05 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
588b38bf-97ee-522f-a407-7cd4493c284e | note | Conformance Criteria - Mitre pipe at 1V:2H. Grind back exposed steel 20mm and place bead of epoxy mortar on cut surface
961a8887-ecd7-5057-8fd7-043e683d2bfe | note | Records - CPS COR report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.13 - Rock chute and rocks around inlet
d930776e-84fc-5d6b-bca9-ff3b4326282e | note | ACTION (Hold, Monitor, Witness) - W
857802f1-966d-5b0f-8e7f-e06ce5d36d0e | note | Specification/Drawings Reference - F3202 Stormwater inlet details
baa6869d-6473-5fd3-9929-088167db1dad | note | Frequency - During Construction
00f798fc-1a98-531e-a648-773f5f0f516a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
163e9414-bef3-5b58-9224-fd8744b26773 | note | Conformance Criteria - Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Extend rocks to top of the embankment.
3c341d77-42ff-5816-b489-8242cedb0ded | note | Records - Photo's
| checkpoint | 5.14 - Geotextile installation
9e8514c9-cb5a-544d-a7fd-516004b8ad7f | note | ACTION (Hold, Monitor, Witness) - W
2f67b0ce-1acf-5fe1-bf4b-6a6a0de14a0f | note | Specification/Drawings Reference - F3202 Stormwater inlet details
8c4388f8-c679-55a2-8244-800563458505 | note | Frequency - During Construction
9a71cd9c-3fd8-5ed7-b043-5bcafcba823c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6decc480-42b0-5727-a5f6-ebe0d90dd379 | note | Conformance Criteria - Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations
4ebff999-f5dd-53e8-8b31-78443f0a3230 | note | Records - Photo's
| section | Section 6: BUTTRESS TYPE C
| checkpoint | 6.1 - Class D (A39) Geotextile installation on the excavated face
be0f2c7b-ab61-571c-a4ad-cf682ce72548 | note | ACTION (Hold, Monitor, Witness) - W
d87a950c-5f03-54a8-b249-8b195b3504f2 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
1df3f2df-61ef-5d02-91fc-1c39ccc41a8f | note | Frequency - During Construction
b6108af1-809f-531e-ae24-5af5abfdd1fe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
36748f2b-a8f3-579f-ab47-1c281e4f2bed | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
efc87a2a-d842-5cd3-96c9-b06b9e0c3c1c | note | Records - Photo's
| checkpoint | 6.2 - Megaflow strip or drainage blanket installation for seepage if Encountered
69f1bc7f-8781-5da1-9105-c877001fd89d | note | ACTION (Hold, Monitor, Witness) - H
44ab7121-5ab3-5106-a41f-f393a5c7038f | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
110dd5be-06d3-5bbd-aca1-641c5f539e57 | note | Frequency - During Construction
eccbb473-7e44-5e11-85de-707b2bbbdffb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
142a3a8d-cc79-5c8c-a8c4-86321c2dd0cc | note | Conformance Criteria - Engineer to assess suitable drainage location suitability.
f2a8782d-0959-5e2e-b1ce-258003c1c9df | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
96ebb8d5-e689-50b0-bed7-378f352ee36e | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Bulk Fill placement
68750eb1-8f88-5773-bcf8-8cd17fd90b41 | note | ACTION (Hold, Monitor, Witness) - M
5a642488-876e-5a99-9e89-8fb1cda6c0a6 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
0ec160f8-5a52-56ac-a42d-aba51090c8bc | note | Frequency - During Construction
1e6188c2-e1cd-50ff-939a-9d93503bb8ad | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
11057674-ddfc-50e0-a8f0-f6a0e5ff0c35 | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
32a60fbb-6b88-5410-861f-a584bd3ace75 | note | ○ Fill should be placed on dry subgrade.
d68a3bfc-7906-5ffd-a9be-f7771e96c2eb | note | Records - Photo's
| checkpoint | 6.4 - Bulk Fill Compaction
c6f20b86-9eef-5f4b-b726-67f08f8a4f63 | note | ACTION (Hold, Monitor, Witness) - M
e650e379-54f6-51b8-857e-99cf053c12ce | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
e02c87e2-7597-59a4-bc8c-d87cd5dd854c | note | Frequency - During Construction
f13babc8-68a2-5593-bb1e-841f105e58de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
9f194ab2-1098-54ce-a8e5-5acc683c56dd | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
ef93eb74-faf7-5de1-a350-02915c3d6519 | note | Records - Compaction test reports
| checkpoint | 6.5 - Form and cut fill batter as per design 2H:1V
abaff27a-d560-5c60-abfd-e3f45a5afce1 | note | ACTION (Hold, Monitor, Witness) - H
439bc721-de61-5a28-8b06-a22649aecba8 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
763e690d-0f2a-5774-9508-5b7fa350d009 | note | Frequency - During Construction
9bacbed1-81a3-595d-8b40-2a005f77c0d8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
6c3af3b1-cdec-53ff-a54b-8c0724c7bf40 | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
e49868bd-0bd3-50ce-9bed-2b8e034fe042 | note | ○ Slope angle of buttress is to not exceed 2H:1V
9dba6b7e-3ad9-5e2c-9330-5c8cf7409a99 | note | Records - Survey As-Builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.6 - ClassE (A49) Geotextile placement along the face of fill batter
4200f698-3912-580d-b43d-38ef1fdaa0e5 | note | ACTION (Hold, Monitor, Witness) - W
69faecb3-91a3-53d4-ae4c-2a10e9fd5bb9 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
51f17acf-c224-5c58-b697-6f7f9903d311 | note | Frequency - During Construction
7b1dc968-58e8-5859-abfb-2e2a99c1619d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
47f41dc4-d9fa-54da-be88-7c47e150951a | note | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill and be laid/overlapped as per manufacturers recommendations
2920c35e-5ebc-5d51-8ef9-4ac1bc92a248 | note | Records - Photo's
| checkpoint | 6.7 - Rock Armour placement along the face of fill embankment
c4d22971-afc5-57a8-bb03-bb3e868156b7 | note | ACTION (Hold, Monitor, Witness) - W
e7c3a6e5-a3d6-5696-8aa7-9405992bf2cb | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
edf57464-6137-5c85-9c17-ddd47fa00c12 | note | Frequency - During Construction
a9e20cf1-ce8d-5924-9415-389a70979b35 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Survey
483c1724-a521-5863-8295-41ad00df24c3 | note | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
225f7095-cf38-5def-a3d5-49acefd3abf5 | note | Records - Photo's, Survey As-Builts
| checkpoint | 6.8 - Rock Armour key into ground
c320ad12-2d15-51a5-a8d5-c653a6c77bae | note | ACTION (Hold, Monitor, Witness) - H
aaa0eed7-5fe1-5049-ab3a-412635dc39a1 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
db4fa21d-2545-518f-ba32-b0f2aeb8c211 | note | Frequency - During Construction
a60383ec-acbf-562a-bc42-c49cb8ce4117 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Survey
0dc90d7f-3c83-5753-beb7-8ed894007826 | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
ab57cfb7-8b5c-5d1c-9938-04165ff2924e | note | Records - CPS COR report, Survey As-Builts
| signoff | AUTHORITY HOLDPOINT
| section | Section 7: IN PROGRESS INSPECTIONS (Pavement)
| checkpoint | 7.1 - Saw cut existing pavement
4f480534-25eb-52b3-8f84-48bc3e9743b9 | note | ACTION (Hold, Monitor, Witness) - W
ab3e2226-d077-5e82-8e03-a54d6fdce8e8 | note | Frequency - Prior to pavement construction
1a90bf2b-f47d-5054-8499-80f1c439045c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
607f8d4c-4e55-5664-b4da-e498ae7d0ff7 | note | Conformance Criteria - Smooth and straight saw cut
7c3a0eed-b28f-5beb-bed5-83b717ad9ad2 | note | Records - Photo's
| checkpoint | 7.2 - Subgrade construction
949a9cb7-2349-5de3-a3ad-3d024331c68f | note | ACTION (Hold, Monitor, Witness) - W
cdf3fa5e-b3f3-53a6-a10d-5e2645e6476c | note | Specification/Drawings Reference - TNZ B2
6794ab67-7c36-5039-a6d8-f7c2bae182a1 | note | Frequency - Every 20m
e4483e53-c344-5bf3-8c9a-1d95e2f6f3af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
6cc72c2f-9271-5d91-8b17-c8ef392a751e | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
160ce483-89b9-5546-9fc3-99dd29d51487 | note | Records - Test reports
| checkpoint | 7.3 - Subgrade Cement Application rate
72747d9d-8635-569b-ab29-e19649b49910 | note | ACTION (Hold, Monitor, Witness) - W
b19ee6d9-0a6e-572f-8089-d3b172272178 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
7049826a-7160-5095-81af-b5dff7800003 | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
a4a8de2c-91eb-59e5-9e92-24b4be0dd305 | note | Records - Bag test records
| checkpoint | 7.4 - Sub-base construction
f707e496-3da3-5606-93d3-507da4100260 | note | ACTION (Hold, Monitor, Witness) - W
ee4e14fb-b1d2-54c6-9908-6de571b83725 | note | Specification/Drawings Reference - TNZ B2
46f80a4b-7af8-5c81-84c2-1632f78f2acb | note | Frequency - Every 20m
c316399a-c3c6-5f4c-ae36-06ffc153667e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
86db5103-9748-5f82-a593-4df384eb6cb1 | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
8fae2177-ee99-532c-9584-8151b59ce854 | note | ○ Average 95% of MDD with nothing less than 92%
f3cd88ae-57e7-5f8b-9d7c-f4e0f9bcc82b | note | Records - Test reports
| checkpoint | 7.5 - Sub-base construction
0fa267e7-ab53-510d-9d7c-7909d4666123 | note | ACTION (Hold, Monitor, Witness) - W
86ed813f-b79b-532a-aa97-8fba5572d2b0 | note | Specification/Drawings Reference - TNZ B2
ba44fdbb-96dc-5199-a5e5-b766f2146b28 | note | Frequency - Every 20m
fe182b8d-a685-5f86-9ff4-43928ba470a9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
2e2ec6c7-3d52-5e61-a4fe-3cb22cc29384 | note | Conformance Criteria - CIV>=25
447be51e-4d03-534f-9a2d-c5f8bbf90d3a | note | Records - Test reports
| checkpoint | 7.6 - Sub-base construction
89a4583c-f980-5077-a060-82f9193c78de | note | ACTION (Hold, Monitor, Witness) - H
b46ca745-a92f-5b09-96bc-4e0857f24d59 | note | Specification/Drawings Reference - TNZ B2
03eff594-a6d3-5386-876f-cdd7c484a75b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
b1409b13-4bbc-5019-8f19-ae305c96987d | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
e4060828-3b85-59bc-a0d7-71f905e1dc90 | note | Records - Survey As-Builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.7 - Basecourse construction
8824e1ef-db2b-5411-9d0b-1b395f9180ef | note | ACTION (Hold, Monitor, Witness) - W
3014f08f-a566-5cf4-b922-330473a0c5da | note | Specification/Drawings Reference - TNZ B2
80199d07-3c97-5216-9550-1fee977348e3 | note | Frequency - Every 20m
b3c1c2fa-80da-5ea6-bdd3-4dd1f049fe7b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
13519bd7-14f7-5c60-9eb9-89fc1dbbcd3b | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
6d34c2c4-684c-5ee4-aa04-89e4e027ccb3 | note | ○ Average 98% of MDD with nothing less than 95%
24b9995b-a739-5a8e-a059-1bad2f1d64cf | note | Records - Test reports, Photo's
| checkpoint | 7.8 - Basecourse Cement application rate
d26a9460-0755-5ccb-b5b4-b992dcb6b8f1 | note | ACTION (Hold, Monitor, Witness) - W
41ecbab9-2643-56d3-abda-d28fe780ae91 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
290d9d52-0fc0-55c8-866d-355476d67c20 | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
6fa3e494-3aa4-5bdf-9f3d-0e71773fdbed | note | Records - Bag test records
| checkpoint | 7.9 - Basecourse construction
5e17f39b-29a5-5174-bb23-a94754af75e8 | note | ACTION (Hold, Monitor, Witness) - W
7229e932-eae5-523f-8fa2-6e183374b022 | note | Specification/Drawings Reference - TNZ B2
06ea7982-986d-5098-9c47-36417f5dd34d | note | Frequency - Every 20m
54566d0b-5c10-5984-982e-8cf7188deea9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
f2a89ef0-39af-548b-b8ad-fa41419e8998 | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
949186bd-3e0c-5552-8041-62db422c8b06 | note | Records - Survey As-Builts
| checkpoint | 7.10 - Basecourse construction
2680036a-598d-53e7-a24a-e3c0f27485d2 | note | ACTION (Hold, Monitor, Witness) - W
7368d677-6c52-50e3-9d1d-d05ba396b253 | note | Specification/Drawings Reference - TNZ B2
fc3fe1d1-3685-5b22-8599-ab0e4c4b91bf | note | Frequency - Every 20m
1d305976-e556-59f5-a0a1-4ab44332d6fe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
cc26249c-cc92-51ee-bc0d-276048fff722 | note | Conformance Criteria - CIV>=25
9e81b123-d7e5-50b5-a294-57be0f4421b6 | note | Records - Test reports, Photo's
| checkpoint | 7.11 - Basecourse construction
49944b97-6ef9-597e-a318-3c1aa4231425 | note | ACTION (Hold, Monitor, Witness) - H
3d440818-006b-5cf0-ac9d-dcb28eb461d9 | note | Specification/Drawings Reference - TNZ B2
226b1c68-becf-5cb1-bb45-bdd2f4685b97 | note | Frequency - Before sealing
f5d0a4ae-e879-575e-becf-12a0ec9b503f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
95430ea2-915d-516d-a72d-ee02d2727da2 | note | Conformance Criteria - Mosaic surface
7e9a560a-a4ea-52ac-b153-039f9dd38b81 | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.12 - Applying Bitumen
34eee98d-ec9e-5b41-b516-28e1605ad71a | note | ACTION (Hold, Monitor, Witness) - W
46cb6354-86ed-51c1-8a1a-ac7aae56dc31 | note | Specification/Drawings Reference - NZTA M/6
d9d661e1-9a34-5a8b-9c52-576ed47f6623 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6f0057f7-5649-56b0-816a-9fde36473ead | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
5875de6f-d0e3-5a1a-96d6-babb7377f56c | note | Records - Spray report, Pre-seal checksheet (CS-4060), Photo's
| checkpoint | 7.13 - Degree of saturation
f1a1c7d5-1766-5072-b90d-3065b6d0abb7 | note | ACTION (Hold, Monitor, Witness) - W
c04bc189-ffc4-592c-88e9-25591e05d676 | note | Specification/Drawings Reference - NZTA M/6
64e1ccea-c33f-5655-8b4d-1aeebac2160d | note | Frequency - Before sealing
6280fc10-c30a-5e60-b0b9-80fbfc972c86 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
22853b31-6807-5c92-841b-d1bdffeb8fee | note | Conformance Criteria - Degree of saturation should not exceed 80%
9f8a8b3b-8432-520e-8e9e-3d787711fd2d | note | Records - Pre-seal checksheet (CS-4060)
| checkpoint | 7.14 - Chip seal laying
b511c933-f31f-561a-8a91-470c488d8fda | note | ACTION (Hold, Monitor, Witness) - W
eb6075de-ec36-53a0-85da-9b5d2d16a6c4 | note | Specification/Drawings Reference - NZTA M/6
70e7436a-b746-52c3-b010-b215e2149cd9 | note | Frequency - During Construction
95ec2f71-3a75-54f6-9bda-1f3c9b643d0d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
161fe68b-9ccb-532c-a74b-82309f523a94 | note | Conformance Criteria - Grade 3 and 5 chip seal
a67e8de9-5a5a-5103-92fd-a7e63a3758d3 | note | Records - Material certificate(s), Photo's
| section | Section 8: FINAL INSPECTION & HANDOVER
| checkpoint | 8.1 - As-built Survey
8cc4d18d-cc1d-5a59-99b1-73fab7162354 | note | ACTION (Hold, Monitor, Witness) - H
99bbfbf7-f5f8-557a-9b09-a9fee1d4dd0a | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
3bab04bf-7dd5-5505-9c7d-be687155deb5 | note | Frequency - At completion of Lot
66b0ba7c-e096-58b4-91b4-bd54bb4cd06c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
ce500299-2f7e-5078-8d11-bdcaba21f9fa | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
40f65eb6-4e81-52af-adc1-729a1b92adf3 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 - CCTV inspections of culverts
c569861a-2043-58ac-9965-637b5a4b5f34 | note | ACTION (Hold, Monitor, Witness) - H
2ebf936c-daba-5a70-a7f3-b3c54999bd6b | note | Frequency - At completion
293318be-541e-5894-9927-c15106fe2570 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - CCTV inspection
2abe161f-d954-5f64-9ec6-e91e8f2443e5 | note | Conformance Criteria - CCTV to inspect the alignment, no defects, joints are sealed properly
cd9b6bee-c5c9-5b2b-bdaf-2d06cd234622 | note | Records - CCTV footage
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 - Quality Assurance deliverables
4016d3d9-2006-5f8b-9c32-996a62424071 | note | ACTION (Hold, Monitor, Witness) - W
6b8c23a1-309b-5b8b-84bc-c302b0f125d7 | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
024398d1-3e06-5761-8520-137563706e96 | note | Frequency - At completion of Lot
a6afb4b0-8c59-57c9-b8ea-b420c6e9efb0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4331519f-e908-5925-a3c6-e7e738f00722 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
9f0b6605-474a-5fb8-b396-4160c1bf901e | note | Records - As-builts, NCR's and RFI's
| checkpoint | 8.4 - Completion Sign Off From Fields Below
8aeb759a-3655-5e47-9192-0ebd6e08dc36 | note | Records - Signatures
| checklist | ITP - F3202B - Earthworks Mangatuna River Buttress | itp | ITP - F3202B - Earthworks Mangatuna River Buttress |  | a186a86a-03fd-426f-90c4-e10ceef55c74
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
3d7c1d9f-5c85-55ef-a48a-2d9580d45035 | textbox | CPS Eng.
5c1b453e-4b8f-5e9c-a8bc-c8df3ae99bcd | textbox | Site Engineer
b97fca2a-d94d-57ab-8ecb-3837af0ee861 | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour (D50=450)
b00f8af2-f079-5b7f-ab9e-6310bdaa85c2 | note | ACTION (Hold, Monitor, Witness) - H
8befd2ba-2da4-5530-a680-22d1f8947345 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
27c29eca-e287-5231-ad62-d5e1ba349b9e | note | Frequency - Prior to commencement
0f20889c-51b7-5f67-a84b-c22aa052027c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
c7a1bbb1-dfc3-526a-a1a7-c35084577642 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
136e042a-f0f7-5a48-84c0-051e96d153b7 | note | Records - Material source test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
680257d4-0e81-55cf-a714-3072c550a966 | note | ACTION (Hold, Monitor, Witness) - H
b9992734-21be-51e3-b722-8e316082be78 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
2152777b-98b5-5769-b7ba-867f4e1c0317 | note | Frequency - Prior to commencement
7da5b836-ea72-5151-8941-67379f1c254a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
9fcec33e-52d9-5851-ab1d-a8be944053df | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
b4f02d22-66c7-522a-8409-464b56a6b5d9 | note | ○ Material source testing
fbbbd757-c4df-5b35-9eee-f7fe2783e505 | note | Records - Material source test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Class D A39 Geotextile
7ce55843-bce5-5f48-b0b9-1a3079e364ec | note | ACTION (Hold, Monitor, Witness) - W
2a681a28-74d1-53a2-ac03-88e0939f9604 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant
dbbb33da-12b5-587f-8a8c-a0e532388a49 | note | Frequency - Prior to commencement
05203b0d-81f9-5713-b109-c24486951430 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
813dc71e-5d49-5952-a36e-2168d9f99b7f | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
ce1cd929-bf90-5161-bb5f-47d29975d37f | note | Records - Material certificate(s)
| checkpoint | 1.4 - Class E A49 Geotextile
0767e3ab-c632-5e49-bd98-67c699caa77a | note | ACTION (Hold, Monitor, Witness) - W
6a482b2e-5935-5d5f-8e54-17f4747a9585 | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant
dc145734-9009-550d-a343-84f5c3f0806d | note | Frequency - Prior to commencement
6460516a-3c76-527e-8a6e-9ff2912d3acf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
6f78b780-df08-5b0f-971a-73b2ef4f83e3 | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
43f8edb8-5902-5e28-9a0b-82cd67c4384a | note | Records - Material certificate(s)
| checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
07f36520-c2ee-5128-af71-6b3d74bb539b | note | ACTION (Hold, Monitor, Witness) - W
9973be82-d622-5270-88e9-565a40f39b1d | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
21c6d585-d824-506f-b140-4dacea588efe | note | Frequency - Prior to commencement
2cf5a38e-9322-501c-bf81-8895cf9e2d84 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
20310bcd-6455-560d-9990-3dbfb65cbb75 | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
8bf89a32-8214-5c57-8c22-5e7e96fda505 | note | Records - Material certificate(s)
| checkpoint | 1.6 - AP40 (Basecourse)
3f3ee13f-1f28-5611-a3c5-31e243f64609 | note | ACTION (Hold, Monitor, Witness) - W
7af918f9-ea37-51a8-a71a-67c9308eba41 | note | Specification/Drawings Reference - TNZ M/4
0519996c-e15a-57c2-9755-b007c4f4b1c6 | note | Frequency - Prior to commencement
b77a741f-2fae-5bdc-804e-0f4d1e2b00ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
38052fc3-5cf1-5193-bcf2-12848615d78f | note | Conformance Criteria - Comply with TNZ M/4 specification
7d76500e-05e0-50dd-bf3f-bb3a6ea38247 | note | ○ Source property testing
461c865f-4852-5ad3-876c-276a44afe553 | note | ○ Traceability of all materials delivered to site
f9028564-8aa8-5dc5-89f6-d97ada6b1200 | note | Records - Lab test reports, Delivery Dockets
| checkpoint | 1.7 - AP65 (Sub-base)
c204980c-2ac8-5007-bb8d-6c4f8c3c4c6f | note | ACTION (Hold, Monitor, Witness) - W
6d9fa096-e2d8-57e5-a2d3-0e84c084d0fe | note | Frequency - Prior to commencement
a8c52fda-c8c7-5e0c-b704-70263e3fa920 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
7cd40b0e-6936-5daa-b853-2bba1150dea7 | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
14b83719-42c2-5b70-96c0-c64ef0be9235 | note | Records - Lab test reports
| checkpoint | 1.8 - Grade 3/5 Chip
f52df208-4a2d-5e67-ae7b-43d8ac9c704d | note | ACTION (Hold, Monitor, Witness) - W
50a8b36b-360b-5535-962b-a43cbd9b9d02 | note | Specification/Drawings Reference - NZTA M/6
f58bcf40-2052-5f8e-9b4e-da1b66a5331b | note | Frequency - Prior to commencement
08b5465c-7f7c-5608-8f4f-aaf730b86ded | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
dc5d071c-fccd-5f97-a169-2f05fbb46e23 | note | Conformance Criteria - Comply with NZTA M/6 specification
f0629f67-5ccd-5006-9891-1fa9e93eb42a | note | ○ Source property testing
656a3022-1e15-562e-b5c2-2986f961a8a6 | note | ○ Traceability of all materials delivered to site
5d9a672b-d6f7-584a-bf0c-3fef2702d28c | note | Records - Lab test reports, Delivery Dockets
| checkpoint | 1.9 - Cement Material cert
ca75a6b3-f237-5210-b085-7cd3a1ee4d86 | note | ACTION (Hold, Monitor, Witness) - W
7dd82d59-98b2-5d2a-bbeb-c1562e869be2 | note | Frequency - Prior to commencement
96ac36b4-121c-5b36-8909-e595482d26a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
0bb48d40-3935-5d64-bcd0-005a492e834b | note | Records - Material certificate(s)
| checkpoint | 1.10 - Bitumen
698c226c-404e-54cf-a040-8779ce4736cc | note | ACTION (Hold, Monitor, Witness) - W
677dd4d0-2678-590b-b9b3-d890aa1fb45c | note | Specification/Drawings Reference - TNZ M/1
29befbed-4754-5fc8-9269-621b215bfde4 | note | Frequency - Prior to commencement
c3254eaf-6b4d-5c1b-b59e-fac4f151ef9f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4970f541-c2e3-5cfe-8a16-3a139e62f2ff | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
aa577a09-1202-536c-b628-ead433a040a3 | note | Records - E2 Certificate
| section | Section 2: IN PROGRESS INSPECTIONS
| checkpoint | 2.1 - Survey Setout
542f2082-647c-5236-b608-ef31d1e4a2e8 | note | ACTION (Hold, Monitor, Witness) - H
84636dde-d7bd-5c39-b076-9f9c43d7c2e2 | note | Specification/Drawings Reference - Consistency with Construction Drawing
b8c466f6-a0eb-5216-b46f-732a3a666d7c | note | Frequency - Prior to commencement
0c54ce75-bc03-5bce-a46d-117ba2764462 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
6a8e6dde-26e0-5285-86c9-ee44ea6d915e | note | Conformance Criteria - Set out extents of fill and check against design drawings
d955f81a-8c4e-5136-97cc-f7a9441f416f | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
76c3e1b1-5136-555b-b030-f20052bdf3de | note | ACTION (Hold, Monitor, Witness) - W
bb53824c-b923-5d23-a63b-065d03f06fa7 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
7469758a-a608-513f-82db-219261b54d0a | note | Frequency - Prior to commencement
88c8594a-3741-5630-8870-8cb5b217baa8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
0813a297-e691-5992-bf95-00bfefa5c3e6 | note | Conformance Criteria - Remove and clear the vegetation
e12c85e2-93f3-5228-a998-74db516e0a29 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Excavation
bb6aba83-3f04-562f-9df4-62b2fa513b66 | note | ACTION (Hold, Monitor, Witness) - H
f70d0d8b-9600-5f36-88ac-6be2af596b59 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
27dca832-2785-54ef-9131-88adb93688fd | note | Frequency - During Construction
1aabf870-6dd6-509f-b016-62a13c127795 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection During Construction
1fa691a7-ed17-5068-8593-f9c2c8057a23 | note | Conformance Criteria - Engineer to assess foundation material suitability
6a4af242-6d59-5ced-a5cb-d7fac7799483 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Subgrade Inspection
648f509b-f386-5834-8772-ec6a014c2509 | note | ACTION (Hold, Monitor, Witness) - H
6aef5cb7-bb2e-5a9d-84b7-2d8ee34ad9d7 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
cb744bee-8930-5bd5-a389-b2c36a993826 | note | Frequency - Per area as required
78e490b5-659f-5844-a93e-3ad899756c12 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
3d173007-afae-5e31-bc08-c84874b1f7b4 | note | Conformance Criteria - Inspect fill foundation.
f1cda49b-4f22-5482-a138-02564a48c337 | note | ○ Fill foundation must be approved, in writing, before filling commences
eadb1661-dd59-5ab5-9f2d-daceb9c89f22 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Ground Improvements
82da808d-a6e9-509c-b1ef-c44e62862daf | note | ACTION (Hold, Monitor, Witness) - H
e16d32f6-8f9b-597f-a35a-338941673659 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
6acc7daa-206c-5c84-b7ae-1ed6b0154be7 | note | Frequency - Prior to commencement
640d38b7-26f8-53ad-aa15-162bd7b59e10 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
aa4eee53-d14b-57cd-8474-49516914cdd5 | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
8ab4b7da-203c-5d3e-9878-5ddd6f67cc54 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Class D (A39) Geotextile installation on the excavated face
7a70d917-86a8-5b25-90ac-6347a80c696d | note | ACTION (Hold, Monitor, Witness) - W
5ec8eb08-d906-57a5-a02b-00d1cb74cb86 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
683006d6-f046-5508-9d2c-f347f588ba1b | note | Frequency - During Construction
5cfa5334-e7e3-58cf-9554-617b6560ed4e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3f8a5e9c-3990-5695-abcf-7c52062156b2 | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
4c70292e-2cfe-5fd0-b01f-dc62b08b2670 | note | Records - Photo's
| checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
1ce34d9c-889a-5559-b5de-1c057578050e | note | ACTION (Hold, Monitor, Witness) - H
7f7d8e7f-6f58-5ed0-813b-fd56d8261f64 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
9edadbc9-b6dd-5b09-bfb2-57ae82d66900 | note | Frequency - During Construction
eeb80f6b-c46e-5201-aca1-a07667b95fcd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
23d2a3d7-1ded-57c0-a124-72928072442d | note | Conformance Criteria - Engineer to assess suitable drainage location.
b78ad7f9-49d5-5800-b43a-83a1135688d6 | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
9c85a504-eadb-54a5-a08c-ff5271a5bd1f | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Bulk Fill placement
55859e77-ad8f-56a6-9568-78bc91a7459a | note | ACTION (Hold, Monitor, Witness) - M
09388e0c-ba09-5f55-a263-a01af0cdcaae | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
825d3590-ff3d-5753-8cb6-8927ef74ec96 | note | Frequency - During Construction
130c02da-1530-5544-ac76-3abac2533208 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6e8b59b2-9f17-56a4-b804-50c2aad9290d | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
5f60c18b-8990-5199-9fb1-8988bb79c697 | note | ○ Fill should be placed on dry subgrade.
62efdfb3-e662-5fab-8e8b-a5262a9eba00 | note | Records - Photo's
| checkpoint | 2.9 - Bulk Fill Compaction
a1bb71b0-6d6c-5974-b797-31646af81fc5 | note | ACTION (Hold, Monitor, Witness) - M
1c0ce3d3-fe73-544b-81dc-fa760fe4c5d5 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
726461c1-10e8-5561-9033-fecf183728f9 | note | Frequency - During Construction
6fd17e7d-8670-5aa4-826f-e1a099313f7b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
9f8ab8f2-12a3-564d-a661-ac73a9b6f97f | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
33c3a105-8533-566e-9522-c24021fdd28a | note | Records - Compaction test reports
| checkpoint | 2.10 - Form and cut fill batter as per design 2H:1V
c1447588-bcb1-5138-8c2e-5acb45348eef | note | ACTION (Hold, Monitor, Witness) - H
b2852862-03f6-592b-bc89-6485e050994e | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
9abab4f5-92b3-53c9-9b09-3ab6adaee9d9 | note | Frequency - During Construction
ee9db302-4d8a-560a-86b4-c09b6f0eb93a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
46083da9-b8b9-598f-a6e1-2919719d344c | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
45ada656-c772-5e8d-8511-50bdc4a9d9c9 | note | ○ Slope angle of buttress is to not exceed 2H:1V
f8e46bc7-537e-55c1-b39b-3abd12758fd1 | note | Records - Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - ClassE (A49) Geotextile placement along the face of fill batter
33a098a7-f7fa-5c48-8484-df5ddaf79e19 | note | ACTION (Hold, Monitor, Witness) - W
f1c04c40-b704-5772-98e6-9b6458d79198 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
b6e4ab50-e4e8-5e72-ada2-84ec3c4c81e5 | note | Frequency - During Construction
f55d5f83-f183-57a9-80db-1f91607bd4a9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
5cd3c0c3-ddf4-5075-b6c8-bced2a03d6ef | note | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill
9ca5f7e3-444a-5233-b14f-be8ea28e2bfb | note | Records - Photo's
| checkpoint | 2.12 - Rock Armour placement along the face of fill embankment
c0bad696-8b13-5779-9c9d-8943af8d1fe5 | note | ACTION (Hold, Monitor, Witness) - W
af348cff-e741-5f40-b59b-3dac75926440 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
a7cacb3d-5b00-572e-b33d-5862ce6fe59d | note | Frequency - During Construction
6b9290a1-c439-5271-bb6e-9f5916d9f88e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
15c4a07d-7edb-544e-8acf-ff8be93be4d7 | note | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
fdc58580-1827-5f14-8ad6-d1919a214dff | note | Records - Photo's, Survey as builts
| checkpoint | 2.13 - Rock Armour key into ground
d7647abc-d16e-5735-a101-09ab95d62cde | note | ACTION (Hold, Monitor, Witness) - H
6c69ad48-3728-5f00-9d79-a0bdc844a3e3 | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
5fcdbeb7-2e12-5eb7-8cb5-fc487539391a | note | Frequency - During Construction
e5718869-eb2d-5bc5-89ae-cf871f5aa24e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
5a4c0d3c-26b7-55f6-8983-2a4fbf1dbb3a | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
5ce8fbfb-38d7-5539-b1e7-e55fbe2a1178 | note | Records - CPS COR report and survey as built
| signoff | AUTHORITY HOLDPOINT
| section | Section 3: IN PROGRESS INSPECTIONS (Pavement)
| checkpoint | 3.1 - Saw cut existing pavement
ec26ab9c-f6eb-5f36-b29b-685aec8879fa | note | ACTION (Hold, Monitor, Witness) - W
88d315e5-41be-5a64-8c80-494ea869b685 | note | Frequency - Prior to pavement construction
da79f036-9eb4-5cdc-a08a-68c9d2003f29 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
bb5b1dda-0fd2-5859-89b0-561010fd51dc | note | Conformance Criteria - Smooth and straight saw cut
ea1fd34c-cbd9-5059-8e60-43945f389adc | note | Records - Photo's
| checkpoint | 3.2 - Subgrade construction
59c5d923-a8e6-5cd2-8c41-5e7cf7be6141 | note | ACTION (Hold, Monitor, Witness) - W
f947924e-7b5e-512f-8d92-3415d70f999d | note | Specification/Drawings Reference - TNZ B2
ed4c1fb5-61df-50b8-81a8-9722afe0612b | note | Frequency - Every 20m
bb66882a-f8ae-5990-a305-e3dd93ed1ca3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
a212ea49-90f4-5d80-bd89-8fceaa319bbc | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
31f13429-a713-5eea-a23e-1f0e112345de | note | Records - Test reports
| checkpoint | 3.3 - Subgrade Cement Application rate
e577e1cc-aa18-5a72-9094-2c78569fbc22 | note | ACTION (Hold, Monitor, Witness) - W
167a3b3e-602b-5a95-acfc-f426130a0964 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
b6925712-2da2-5dc2-ac66-5ea4c24c808e | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
6f479d70-8c21-5b8f-994e-a5321da1be26 | note | Records - Bag test records
| checkpoint | 3.4 - Sub-base construction
ba15115a-e11b-5bc5-b4d0-bf70fefb6b20 | note | ACTION (Hold, Monitor, Witness) - W
edb9bc33-7068-5834-99c3-e7394ab7a04d | note | Specification/Drawings Reference - TNZ B2
92f4ae29-af5d-59df-a759-2e92dd9763e5 | note | Frequency - Every 20m
0a13e1f6-d5cf-5cdf-96d2-d5049e0e88e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
c3b77605-7677-5d19-9d88-391c5e30fefc | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
542e96ad-2928-55a2-922f-6d707724c8ae | note | ○ Average 95% of MDD with nothing less than 92%
44a0171c-b1c7-546e-a655-d72c16982039 | note | Records - Test reports
| checkpoint | 3.5 - Sub-base construction
33035d97-49bc-5e9c-b4df-70ae6cc415a3 | note | ACTION (Hold, Monitor, Witness) - W
22fea1ee-404d-5b6d-8dd8-24544ba62b39 | note | Specification/Drawings Reference - TNZ B2
ddce049e-ec81-5288-ae64-a482c545153f | note | Frequency - Every 20m
54bfb7ce-c633-50fa-8959-d7af9cb1fb28 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
935c7ef6-b31b-50c5-a363-366199973242 | note | Conformance Criteria - CIV>=25
8ef13e17-8de3-5b3f-a904-db7323709cd3 | note | Records - Test reports
| checkpoint | 3.6 - Sub-base construction
224fa1a8-9a43-5793-8264-4c6bbdf307f2 | note | ACTION (Hold, Monitor, Witness) - H
98931da3-83d1-542d-b92a-02cc441ed142 | note | Specification/Drawings Reference - TNZ B2
56aa2af6-125e-537c-9ccb-173340490250 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey as-builts
0438a408-0410-52be-96a6-6e743de45d38 | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
84b6b003-4157-58a5-a5b7-a9572de8e18e | note | Records - Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Basecourse construction
27833f22-b022-56c1-be48-4251b3cbf8b4 | note | ACTION (Hold, Monitor, Witness) - W
42c1b2b1-0797-5253-83b0-13bf261e42b5 | note | Specification/Drawings Reference - TNZ B2
34928bc4-a8a0-542b-9372-0e0da6ff5610 | note | Frequency - Every 20m
3e320a1c-a791-5dff-943e-cbad4fa0db0c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
2f4a381f-a4ff-5771-a4b7-991ae5fa873d | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
40b30b88-a2b9-5afb-b071-e9b423048012 | note | ○ Average 98% of MDD with nothing less than 95%
8761add4-8b3f-5062-a24f-1304349040a2 | note | Records - Test reports, Photo's
| checkpoint | 3.8 - Basecourse Cement application rate
1fa8ae3d-718a-5150-a3cc-da6c24ec991f | note | ACTION (Hold, Monitor, Witness) - W
bb3d312d-0628-5808-a2e1-88557cefc52d | note | Specification/Drawings Reference - TNZ B/5
0e071a12-de0c-5b7c-9209-217bd5953e56 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
4373e81c-929a-55b8-b90b-4dfe50fea19b | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
d003697d-f7bd-5e72-9499-8c4352170753 | note | Records - Material specs, Photo's
| checkpoint | 3.9 - Basecourse construction
b8890d7a-3841-543d-9446-e9d7109bf58a | note | ACTION (Hold, Monitor, Witness) - W
d56c1b13-6537-5914-8b15-7ee7965ce103 | note | Specification/Drawings Reference - TNZ B2
a3cd02cb-e8a5-5299-afff-9fbda0e80bd2 | note | Frequency - Every 20m
a70b5b19-a388-56e5-adb0-e3af6df4a5e7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
52370be1-8e29-5738-a5b3-f535ad85f216 | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
7713d8af-334e-573d-a9a5-f8f478a41259 | note | Records - Survey as builts
| checkpoint | 3.10 - Basecourse construction
ee4f6a9d-922d-55c4-899c-aea300a00385 | note | ACTION (Hold, Monitor, Witness) - W
b343250a-186b-521f-ba10-ae42fd5309ca | note | Specification/Drawings Reference - TNZ B2
c208e9b8-f0f5-5e3a-991c-46155cb970b8 | note | Frequency - Every 20m
898df548-2eea-53dd-972a-8cf848c0292a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
7ddf0d1e-b5d6-50e1-8913-67048251a3ff | note | Conformance Criteria - CIV>=25
12d4e996-ea15-516c-afc5-a8514aa1e730 | note | Records - Test reports, Photo's
| checkpoint | 3.11 - Basecourse construction
355d14ba-d90e-57cd-a82c-e45ce559983e | note | ACTION (Hold, Monitor, Witness) - H
5ab01e68-8180-508a-9fe5-024aea400c2e | note | Specification/Drawings Reference - TNZ B2
cae5a6fd-1c0f-5097-900f-60e036a4b2ca | note | Frequency - Before sealing
0739e501-cf0d-5c88-926f-5109c4869a5f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
615793be-f992-566e-9f8d-3392a0f7160e | note | Conformance Criteria - Mosaic surface
fb804712-9a83-5d71-a72f-04dd2c9a4020 | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.12 - Applying Bitumen
14b04779-8899-5f3c-8dd5-c2f94a6c43b9 | note | ACTION (Hold, Monitor, Witness) - W
c8ad93ec-8b13-511c-a91e-056715c9baca | note | Specification/Drawings Reference - NZTA M/6
bc8f4b1c-2f1a-557e-b850-0ec20e4eae16 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e46f6a88-c3f9-51ff-9a07-dac7ef9cba7e | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
8b97e749-8551-55cd-9f5f-7249b9f66106 | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| checkpoint | 3.13 - Degree of saturation
9eb30f4d-9c42-52e4-a481-3023c92b54ee | note | ACTION (Hold, Monitor, Witness) - W
30542b94-b336-5c5c-b3c0-9b311be92f17 | note | Frequency - Before sealing
a076e980-9d73-57f6-af04-8b78b87e809e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
f3debbbd-a937-5f75-9df6-dea338fae89b | note | Conformance Criteria - Degree of saturation should not exceed 80%
343d839e-0a81-5eb7-8377-bd87504ea81a | note | Records - Pre-seal checksheet (CS-4060)
| checkpoint | 3.14 - Chip seal laying
36a0cdc8-39ad-5630-b175-0b6ca085fddb | note | ACTION (Hold, Monitor, Witness) - W
8a8f7375-559a-5799-8c7f-1d36bbede43c | note | Specification/Drawings Reference - NZTA M/6
01f6c1aa-51ec-5f01-87ac-8652e0023a88 | note | Frequency - During Construction
65dbce93-d542-5c49-8f87-bb38c8d3134d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
c02f9e9e-ee7b-5ddd-8880-0a2d1d020ef1 | note | Conformance Criteria - Grade 3 and 5 chip seal
45531bcd-71ac-5fe9-8e90-ffa5460c973f | note | Records - Material certificate(s), Photo's
| checkpoint | 3.15 - As-built Survey
50804e25-fddd-5a4a-9491-d5b420eaf227 | note | ACTION (Hold, Monitor, Witness) - H
f70e1beb-b5d1-5262-8c99-f6d355a931b8 | note | Frequency - At completion of Lot
09f3d00e-b94b-5c9a-bc7a-998586c9a62f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
88ce1934-31d3-5685-b5b3-bc4479ce21e0 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
072b3f7a-d820-5e48-a889-f574a91a250e | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 4: Final Inspection and Handover
| checkpoint | 4.1 - Quality Assurance deliverables
81176b79-9ef0-5143-98dd-5530f59a372a | note | ACTION (Hold, Monitor, Witness) - W
dc35f08e-1abb-548f-870b-c75856ce7ca4 | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
1094fc3c-2de7-5e2c-b8ab-4a4265a05c99 | note | Frequency - At completion of Lot
06301faf-674b-51b0-95e4-fed016502ea9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
2618d148-cea5-5564-af6b-381c5f8d1e64 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
ef2afa73-b1df-5b6d-b891-373b76d35837 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 4.2 - Completion Sign Off From Fields Below
7277d007-af50-5af1-88bf-9209083f0d19 | note | Records - Signatures
| checklist | ITP - F5001A - Hicks Bay Slip Repair - Guardrail | itp | ITP - F5001A - Hicks Bay Slip Repair - Guardrail |  | a7b98b4a-fa4b-4bd8-ae67-7d152c96fbf4
| section | Guard Railing
| checkpoint | Project Site reps.
4b70e3c0-cfa8-59bc-80d9-9e291f6f6e15 | textbox | CPS Eng.
e5bf1f80-bb44-5291-b9c5-5914eed2727c | textbox | Site Engineer
f24d9f01-de9d-55ef-9f30-a411c6ab4067 | textbox | Quality Eng.
| checkpoint | 1 - Guardrail Posts Installation
a942fc10-2d03-5a38-91a1-34afea684d79 | note | ACTION (Hold, Monitor, Witness) - H
1f3f6076-7834-588e-a156-b067e4ae0970 | note | Specifications/Drawing Reference - Design check locations of posts and check for any clashes with underground services or similar.
3da9985a-c2c5-5c8b-adb4-185f8c839540 | note | Frequency - Prior to commencement
28639fa7-b187-5b99-b205-bf698ca0be56 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
63c9e628-f4bc-57d3-be79-56a14f074bd1 | note | Conformance Criteria - Contractor to confirm that installation of posts avoids culvert clash
adef905a-97f2-530a-82b0-5862eae7a562 | note | Records - Site pics, NTE/NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
a243c6a6-df95-5fac-b7c6-4a4e324b0c87 | note | ACTION (Hold, Monitor, Witness) - H
3618c143-2cff-5c10-b73a-2db9a9b48130 | note | Specifications/Drawing Reference - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
f290a01d-a475-5af2-bb0f-f6d738a54a93 | note | Frequency - Prior to commencement
927ca9a4-40cf-50e7-9ca7-8c98282e6e65 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
ba97c57b-40f9-5439-a220-64ccafdee70c | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
b1e0bad6-54be-5f32-9ae6-2f3b261ed5c8 | note | Records - Approved Construction Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance
80751b05-1d77-5095-bb36-4172197e78fd | note | ACTION (Hold, Monitor, Witness) - W
ffa797bc-1f61-580f-b757-d444dbe2f13d | note | Specifications/Drawing Reference - All roadside barriers shall comply with NZTA M/23:2023. Only MASH TL3 approved systems to be installed as specified in the specification & guidelines for road safety hardware and devices, Appendix A: permanent road safety hardware.
c04d5b10-6e05-56db-ab22-1cab1a9aa69c | note | Frequency - Prior to commencement
485d9cb2-e51d-5da6-beca-21bf1b85b429 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
175a022b-0171-5cf8-997f-e740e364aec4 | note | Conformance Criteria - Comply with NZTA M/23:2023. MASH TL3 approved systems only
788478a5-7b4b-53d2-b6c1-ad8f610aafd4 | note | Records - Manufacturing certificates, delivery dockets, Photo's
| checkpoint | 4 - Guardrail Installation
79cc6213-8f38-5234-bda0-eb296117b96b | note | ACTION (Hold, Monitor, Witness) - W
6ae8e769-9b87-597c-8f5d-86746957f9be | note | Specifications/Drawing Reference - Guard railing shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. All Guardrail laps are to be lapped in the traffic direction
e9c9f644-c1b4-51b8-9de7-7a081e00fc8c | note | Frequency - During installation and on completion
c1afa3eb-f35d-55cd-85ae-703132d2bbed | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
f1f1c3c0-aa95-5bf2-91b4-c6ae464db8d7 | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
cd5cd24a-dbcf-5970-a338-e9bc4da7d6df | note | Records - Guardrail Installation Record (CS-4117), Photo's
| checkpoint | 5 -
9040ad6f-9925-5015-b624-2272029b476e | note | ACTION (Hold, Monitor, Witness) - W
50bd3935-2270-50ad-bfc9-32ca99174c79 | note | Specifications/Drawing Reference - Hazard markers to be installed on all terminal ends. Edge markers posts to be secure to the guard rail face. Face of Guardrail to be a minimum of 1.2m from edge line. Engineer to confirm min of 1m support width behind the barrier at a desirable grade of 10:1
4086cd3d-0f3b-5102-a826-21fe7fb42a21 | note | Frequency - During installation and on completion
89357190-1c3a-5816-9d04-8a438dbccaac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
ceec723a-2d0d-59c0-a227-79f11f3588ae | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
4bb2b504-033b-5133-bf83-560bdc767903 | note | Records - Guardrail Installation Record (CS-4117), Photo's
| checkpoint | 5 -
1fed0805-c529-5919-9778-f791172b53e8 | note | ACTION (Hold, Monitor, Witness) - H
5e50f481-5873-5ee0-8ceb-54f7ab9b1a84 | note | Specifications/Drawing Reference - Terminal anchor points ground conditions assessed and confirmed as being adequate based on barrier manufacturer requirements.
5b8a87f9-9d46-52cc-a083-aee5097babd0 | note | Frequency - During installation and on completion
15bc4814-2566-5ad9-b261-21ea83d2769d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
38175823-83e8-591f-ad53-0623f128d5f4 | note | Conformance Criteria - As per manufacturers specifications
3bdbb742-ce84-5325-95cd-197bcad4e4a6 | note | Records - GHD COR, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 -
2b383ddd-217c-5228-9948-1b589a1dfd02 | note | ACTION (Hold, Monitor, Witness) - W
202e328f-dcff-5e5f-9d79-16f2f04f158a | note | Specifications/Drawing Reference - Hazard markers to be installed at terminal ends. Edge markers posts to be secure to the guard rail face. Face of guardrail to be a minimum of 1.2m from edge line. Engineer to confirm min of 1m support width behind the barrier at a desirable grade of 10:1
50e0a133-cfc2-5eda-be97-aef347ed444b | note | Frequency - During installation and on completion
f214deb7-e485-507e-9347-6fc25a257b4d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
8d28ce60-7f31-5ed0-85f5-211c135c9fb5 | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
e0115a5b-b30d-5e36-b05c-adcff1fdb11c | note | Records - Guardrail Installation Record (CS-4117), Photo's
| checkpoint | 7 -
e780e90f-764c-5121-891d-71fe79c50c36 | note | ACTION (Hold, Monitor, Witness) - W
f6fc848b-452f-52ba-b6b0-9bd464138455 | note | Specifications/Drawing Reference - Barrier face is to be a maximum clearance of 200mm from the kerb face in the location where there is kerbing. Design speed 100Km/hr AADT <1000 V/D run out length 64m. Existing single post signs are to be repositioned behind the barrier. Offset of fence is to be confirmed to ensure that there is sufficient room for barrier installation
f6b9f9db-a8d9-54cf-900b-de3a86f31ef8 | note | Frequency - During installation and on completion
ad4d8d39-a277-58ae-8443-691250f59627 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
cd02edea-9e07-51e9-b741-00ebf45ff0e1 | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
ca6396c3-0ff4-5e40-8f8b-d0421120b7ca | note | Records - Guardrail Installation Record (CS-4117), Photo's
| checkpoint | 8 - Fit for purpose Inspection
28da455d-f2b2-51f3-9789-a783c9373e2d | note | ACTION (Hold, Monitor, Witness) - H
26ad1898-f942-553a-ae7c-9d21e8030be6 | note | Specifications/Drawing Reference - Barrier to undergo fit for purpose inspection by competent person
aaa97180-9c9d-5ee9-99d1-4efdd2777df6 | note | ○ System checklists to be completed and co signed by contractor and CPS.
29bda815-aac4-5e7f-8df5-c018c9839c9c | note | ○ All faults to be rectified before acceptance into network maintenance and RAMM by contractor
018627ca-5cf0-5692-9f7c-5dd8c76fa9be | note | Frequency - Prior to trafficking,
dfac64ea-54b8-5a20-990b-b3c11536633f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
5c763779-6ac7-5468-885f-9c2931aeb8d2 | note | Conformance Criteria - Pass inspection
81ee6aaf-9941-5c80-bc3a-db5c3609109a | note | Records - Written Confirmation from NZTA IMI qualified inspector
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - As-built Survey
52c9ef1d-06b4-538a-bed7-c3f418d9671c | note | ACTION (Hold, Monitor, Witness) - H
8159c396-228c-50b1-ad72-ec48ed9029ff | note | Specifications/Drawing Reference -
ab6594a6-b83f-5868-bbcc-b30a9ab3a80c | note | Frequency - At completion of Lot
2fcf2074-cb0a-5e45-afff-f3f2a8b8843b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
346ed996-0dd7-5bed-b8d6-c55c4160af6a | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
812c4f4b-b39b-5470-b2fc-4e09f8081821 | note | Records - As-builts, GHD COR
| signoff | AUTHORITY HOLDPOINT
| section | Section 4 : Final Inspection and Handover
| checkpoint | 11 - Quality Assurance deliverables
5e786bba-a2e3-5098-9cd3-af60c0c0df85 | note | ACTION (Hold, Monitor, Witness) - W
0b950c01-cabf-5bab-9eb8-959ea1f4ea55 | note | Specifications/Drawing Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
4b1f0cd7-ba5a-5941-97fa-878b0d368a45 | note | Frequency - At completion of Lot
2faa3775-d0cd-599c-9480-7e207864a0a3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
835a8b56-8d85-5278-bc88-7a1893428af3 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
be56291e-153e-5cc2-937d-57b0739d3da2 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 12 - Completion Sign Off From Fields Below
df9c28b4-2060-5e96-a325-6b2d04e0b0b5 | note | ACTION (Hold, Monitor, Witness) - H
d95dddf8-7031-5b5e-9fc1-dfd2eac04621 | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - F5001A - Hicks Bay Slip Repair - ITP for works | itp | ITP - F5001A - Hicks Bay Slip Repair - ITP for works |  | f1ac2565-6c2b-4a96-baa6-00b453de60ff
| section | Section 1: Materials Compliance - RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
ba7e57d0-75c3-5132-9109-e7f7f4217e61 | textbox | GHD Eng.
25aafb23-dbf1-587a-9d78-ae062011aec0 | textbox | Site Engineer
ed4a5ebe-47e2-54de-b0f4-dc803832b1b9 | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour, 2 tonne rock class (D0.7m to 1.5m)
786f645d-1e3e-5f38-8e5e-c8f72c10be86 | note | ACTION (Hold, Monitor, Witness) - W
77e16301-8dc4-53f0-91ec-dc894d000dc8 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-1253342-Q002
f1473d90-41c0-5b31-8549-18795847cd01 | note | Frequency - Prior to commencement
1afd8d2a-25ff-5d97-b6ad-e6773f1db683 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
ab17d09d-58d4-5de3-b9cc-7db8712b3706 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D700 to 1500 with a minimum specific Gravity SG of 2350kg/m3.
079e806d-be9c-511d-8b29-32f50e560c79 | note | Records - Material source test results, Delivery dockets
| checkpoint | 1.2 - Granular Backfill - AP65 (1)
1073a260-844b-5be0-945e-d034293ba329 | note | ACTION (Hold, Monitor, Witness) - H
81f9fa33-3f63-56bd-9350-ea1410b1fcca | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
bcb515b2-92ed-5a38-99c7-a3b49cc991a7 | note | Frequency - Prior to commencement
8eb52025-b62c-5adc-9f6d-0eca6b1bc8eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
d21a73e3-6484-5acb-bb75-456c1a15b5fe | note | Conformance Criteria - Shall be free draining, hard, durable, well graded, crushed granular material such as AP65 with a fines content <5% with more than 2 broken faces. It shall be free from organic and vegetative material and compacted to achieve 90%MDD. Compaction maybe checked by clegg hammer.
39aedeec-f922-5f14-a210-5f297434705f | note | Records - Material source test results, Delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Granular Backfill - AP65 (2)
a9342567-ef5a-565a-a755-3abf7c8af8a3 | note | ACTION (Hold, Monitor, Witness) - H
5127c2b3-46a3-5297-b54b-ea62a2975fb2 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
5abd01ac-0dd1-543c-8b92-f784eeb262e6 | note | Frequency - Prior to commencement
770e95bb-ab15-5cce-b733-2547f812d642 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
19db35eb-9f16-59ce-bb2b-7c8807eb184e | note | Conformance Criteria - Address of the source quarry. The geological description of the parent material. Particle Size Distribution (PSD) Test, Compaction Test and Broken Face Percentage Test Results from a Representative, General Fill Sample Tested in an independent and accredited Laboratory
59d83fe0-eb41-558a-8c1b-d786a206c173 | note | Records - Laboratory Test Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Granular Backfill - AP65 (3)
0ca72c48-6a4e-570e-bf2d-9c8f86e10157 | note | ACTION (Hold, Monitor, Witness) - H
450528b5-d01c-505a-891d-89ce3f4491d4 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
f210f35c-6ed5-5467-b728-38721ca26039 | note | Frequency - Prior to commencement
a5ce139f-4a52-5e6c-ab7c-6ee61de8fd36 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
29fcff46-66fd-5f44-b811-a900cc2bae14 | note | Conformance Criteria - Results of Compaction Tests as Specified in NZS 4402:1988 - Test 4.1.1 or Test 4.1.3 are to be carried out on the proposed backfill and the results presented to the engineer for agreement prior to construction. These are to clearly show the Optimum Moisture Content and Maximum Dry Density Achieved
8d9240fa-3d5a-5900-85c2-ab5038925311 | note | Records - Laboratory Test Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Geotextile Filter Fabric Bidim A64 (or under Rock Rip-Rap on Culvert Outlet Scour protection
0ed90c4b-86f9-5e72-b227-fbeb34a1e8f5 | note | ACTION (Hold, Monitor, Witness) - W
a504e602-dd7f-59d9-8528-fd80ffd09e44 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
5a440ab3-7fb2-5402-a0c3-2ca62c6b6365 | note | Frequency - Prior to commencement
8980ddc9-e196-5d20-a7ca-c768c4729352 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
86d7d972-2fa4-5c78-b5e5-fdd1883f054a | note | Conformance Criteria - NZTA Strength Class C. Filtration Class 1 - Bidim A64 Geotextile or an approved equivalent - compliant placed under Rock Rip-Rap
4801fee7-5e78-5049-8790-cc4735a4b3b8 | note | Records - Material compliance cert, Photo's
| checkpoint | 1.4 - Deep Rock Rip-Rap (300mm-500mm dia.)
bfe3922f-e352-5458-89e2-b954a8e94dac | note | ACTION (Hold, Monitor, Witness) - W
d66555f3-a4ea-5950-b05c-ed72273eaeff | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
bcaf8729-73ff-5c2e-96fa-acf7453150b6 | note | Frequency - Prior to commencement
87ff15dc-cb6f-58ca-af46-1777d5db6f8c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
674996d0-0349-506a-8ef4-825b49cb369c | note | Conformance Criteria - Apron for Scour Protection at Culvert Outlet
9a8304fa-0d02-56aa-ab78-2ad88987e808 | note | Records - Material source test results, Delivery dockets
| checkpoint | 1.5 - Guard railing
48bfd126-b35b-59bc-b002-b61ae8334b2c | note | ACTION (Hold, Monitor, Witness) - W
c8a435a6-c6f4-580d-9880-4c81fd152854 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
4d3bb00c-0283-5041-8184-80eb5112036d | note | Frequency - Prior to commencement
fe3bd8de-d849-51da-86a8-10644b986d15 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
df1d45e9-9c0c-5383-a899-415b90e9b67f | note | Conformance Criteria - Guard railing system to be installed to manufacturers specification. see ITP for Guard Rail
2b52e970-74a4-5089-95f3-4589cd7e9281 | note | Records - Manufacturers spec, Delivery dockets
| checkpoint | 1.6 - Precast RCRRJ 525 dia. Pipe
d128f6d1-56bf-5415-9154-2a1af6c37806 | note | ACTION (Hold, Monitor, Witness) - H
d9887691-4f1f-5d23-a2ed-71eb9b632a72 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
90633ec5-e87c-576b-b9d7-78c487afb459 | note | Frequency - Prior to commencement
153a783f-6783-51c6-a2eb-e41f9148c5e9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
cf92b2c3-a959-5171-b5bf-8ced8ee07fdb | note | Conformance Criteria - Delivery Dockets are collected and signed before precast pipe materials are removed from the truck.
a8a647bf-1d66-5d9f-b759-ba9a0540f835 | note | ○ Class 4 RCRRJ 525 pipe to comply with AS/NZS 4058
db8fe520-30c9-5fa0-8849-8d0077e43fb6 | note | Records - Manufacturer cert, Delivery dockets, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.7 - Precast materials
ab7cab42-c02c-5363-8a0d-ed2160b9c4ad | note | ACTION (Hold, Monitor, Witness) - H
ec76aceb-1c47-58d0-a05f-4ffd11352837 | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
d0fcfd8a-8b7c-5f1d-a85b-2d8a54b75747 | note | Frequency - Prior to unloading
f7dad77a-2c38-5a22-851c-644c68e0c632 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
9a06d241-5c02-5fc6-9139-ab7f60520535 | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
24c61288-adf1-583e-951c-eb8206951456 | note | Records - Manufacturer cert, Delivery dockets, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 - Hynds Mountable Wingwall for Culvert Inlet or similar approved by Engineer
fe948366-b8bd-5e30-93ac-864bf862e4b4 | note | ACTION (Hold, Monitor, Witness) - H
35e2bcaf-3ec7-5f04-b64c-b55927a3a8e0 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
da73fdc9-c1f1-549b-b09f-be9bf26830e8 | note | Frequency - Prior to unloading
2e89d27b-9eea-5bc3-9e40-86222bd31e6a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
72601a65-0808-5f96-b0df-2b1a5e5fc637 | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
9aede700-1f17-54f8-8c91-dce586e957fa | note | Records - Manufacturer cert, Delivery dockets, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.9 - D1050mm Concrete Pre-cast Manhole with concrete lid
b16b1a1d-236f-557f-87dc-dbe8399aad61 | note | ACTION (Hold, Monitor, Witness) - H
93d04a23-80e1-5f5b-9b08-45ce15c88fb9 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
65498fc5-d63a-54f1-bec4-4502521b3b74 | note | Frequency - Prior to unloading
c75ceb4b-f172-55a0-a7e1-e7aecfaecf8b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
7e54bf4b-0c7c-5b1f-b2db-9ed02070a0ab | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
31453115-2341-56d5-b3cc-855a6630bfaa | note | Records - Manufacturer cert, Delivery dockets, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.10 - AP40 (Basecourse) or approved basecourse modification
08c3b89c-77c3-5802-8576-263abe4ec3e2 | note | ACTION (Hold, Monitor, Witness) - H
d155378b-c160-558f-b6ab-e5d89e012640 | note | Specification/Drawings Reference - TNZ M/4 Section 3.2 & 3.3
024eb254-564f-53ed-ba9f-1e94793ec411 | note | Frequency - 1/source and at least 1/3 months
6b24b15e-8ea4-53f8-b828-c52327ca9f3d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
8dd12409-e64c-5862-96ba-c3457a3aabbc | note | Conformance Criteria - Particle Size Distribution, Plasticity Index, Soak CBR, Crushing & weathering resistance, Clay Index, Sand equivalent
2041fcaf-6f18-5365-9b22-7fe4c6843066 | note | Records - Material Source testing and approval, Delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.11 - AP65 (Sub-base)
844df46d-f13b-5c72-b6ed-38f4c39ccf3b | note | ACTION (Hold, Monitor, Witness) - W
b5e94ee2-c691-5fd6-ad7d-2325c687ed27 | note | Specification/Drawings Reference - NZTA
03c7659c-f35e-5889-bc90-39845a7db075 | note | Frequency - 1/source and at least 1/3 months
6db84737-e842-5ba3-8eec-7608c544ad54 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
9b1c2c94-e134-51a4-8606-11a67844ac92 | note | Conformance Criteria - Particle Size Distribution, Maximum Dry Density, Plasticity Index, Soak CBR, Crushing & weathering resistance, Sand equivalent
6a924ccc-d802-5cc1-802a-334f842e7b71 | note | Records - Material Source testing and approval, Delivery dockets
| checkpoint | 1.12 - Grade 3/5 Chip
c5149dce-0442-5137-b2c4-d52b4d928acb | note | ACTION (Hold, Monitor, Witness) - W
49f6ddba-ecf8-5af5-a860-69b719104bc2 | note | Specification/Drawings Reference - NZTA M/6
e346fb44-f599-569e-8d64-1e9dfb682d20 | note | Frequency - Prior to commencement
0e84e7ed-1071-5b7b-a407-a55e5562bad5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
912309b6-250e-510d-8448-e00410cf21c0 | note | Conformance Criteria - Source property testing
a7a578de-9204-580c-8efc-01af0caafecb | note | ○ Traceability of all materials delivered to site
a7fc42df-b8b1-5bae-a5b7-7a8e9d27ed92 | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.13 - Cement
e837a6e8-6364-5428-bb8d-f3b25a1065c4 | note | ACTION (Hold, Monitor, Witness) - W
2b265a18-a2bc-5382-a434-6d16fab748e1 | note | Specification/Drawings Reference -
435bc650-01b1-59e9-b0da-1889b5d99ebc | note | Frequency - Prior to commencement
14383c16-6629-5d4e-a0a8-c43159aea2da | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
5256ec22-a6de-5e90-913f-eeaa4737e74d | note | Conformance Criteria - Material compliance Certificate - Portland
269239a3-bf4c-580f-bfd7-a92612adff35 | note | Records - Material certificate(s)
| checkpoint | 1.14 - Bitumen
f187616f-3423-57d4-9729-2c325bbc9c0e | note | ACTION (Hold, Monitor, Witness) - W
d5137789-3adb-522e-b84e-738532333312 | note | Specification/Drawings Reference - TNZ M/1
2e0e36a6-7b7c-52bf-ad1f-06c6c6c6f66d | note | Frequency - Prior to commencement
2c54861d-f688-51f9-b69a-acdc32002216 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
9228b84d-2bb9-5be2-9f47-6c4396c388f6 | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
0ae0805b-796b-5dde-82c2-993022f1fb5a | note | Records - E2 Certificate
| checkpoint | 1.15 - Review contractor's materials supplier QA documentation
9352b6cb-194d-5129-915e-54eaa90ed4f7 | note | ACTION (Hold, Monitor, Witness) - H
ce0f23bb-5177-5efb-a120-ef15a264ca3e | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
1d9a887f-c7b0-5320-9e5a-87a104a9ddd9 | note | Frequency - Prior to commencement
4c7c9f05-ab2a-5985-ac57-dfb5f5db0d42 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
8d2d21b4-7e1f-5108-a413-88cb829aaeae | note | Conformance Criteria - Review contractor's materials supplier QA documentation
e5a669fe-1884-5195-84d1-e7824b9acb7a | note | Records - Lab test reports, Delivery dockets
| signoff | AUTHORITY HOLDPOINT
| section | Section 2: Construction QA/QC - SLIP REPAIR & CULVERT INSTALL INSPECTIONS
| checkpoint | 2.1 - Survey Setout
cc9c8254-5f5e-5c77-836f-97c35a20269a | note | ACTION (Hold, Monitor, Witness) - H
03762eac-e556-5181-b1a3-2a416f9f7706 | note | Specification/Drawings Reference - Consistency with Construction Drawing
bfdc8ec8-c0e9-577f-ab4f-3584c884b368 | note | Frequency - Prior to commencement
3457bd0f-6e40-51c6-8a86-51e995b94923 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
b867cef9-ba0e-5c7b-ac05-537be68aa822 | note | Conformance Criteria - Set out extents of works and check against design drawings
20e7aa7a-0cf9-5d9e-a3f8-646f2400a1a5 | note | Records - Email/COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
2d8ae9af-cac3-5a3d-bb71-e90d16b8a985 | note | ACTION (Hold, Monitor, Witness) - W
c72dc1e4-bcf5-5276-b037-e0dcb6ac6682 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
98a74745-3119-5321-be91-2bf98afa81f6 | note | Frequency - During Construction
9e999855-2220-5944-839f-39d128e8da84 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
ea0d1126-4f9a-5009-86ab-052e4ca0241c | note | Conformance Criteria - Remove and clear the vegetation
7785655b-5e92-5330-9686-ff00cd20ca20 | note | Records - Photo's
| checkpoint | 2.3 - Slope & Toe Subgrade Inspection
d08e5bfe-5dea-5aca-8910-93fc242b1b33 | note | ACTION (Hold, Monitor, Witness) - H
df0d37aa-ee3a-50fe-9deb-098c4d0f9217 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
03fe6d4d-bbb5-59b5-8bec-7306ca88c7eb | note | Frequency - Cut slope and toe of Revetment
772133f0-2457-592f-93c4-97ba54b87058 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
44a17048-c113-53bd-9656-71b99ab053e4 | note | Conformance Criteria - Subgrade Approval Check sheet, Bench slope and excavate toe key of the revetment key to the design formation level. Toe key subgrade to be a minimum ultimate bearing capacity of 300kpa and requires GHD Engineer to visual check inspection & approve
9f0bca76-fde6-59e8-830c-f20c44fcd2a3 | note | Records - Subgrade Approval Check sheet (CS-4100), GHD COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Ground Improvements
dcd128d3-27d5-52fa-bf10-0c086a5fa719 | note | ACTION (Hold, Monitor, Witness) - H
b510ba47-ce38-55ef-ba0f-53c2d453e26d | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
489eae8e-9d6a-5159-843c-1d811164837e | note | Frequency - During Construction
dcec5e25-7688-5fa6-ad46-4095e2165322 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
50c6375f-7751-512a-beaa-514bb23ce757 | note | Conformance Criteria - Any additional undercuts in U/S areas to be approved by GHD engineer
493e0484-0027-5f25-9a69-517af90e05d4 | note | Records - Photo's, GHD COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Form and cut fill batter in benches
1fd42dab-3b25-5984-911b-9b22fb96c049 | note | ACTION (Hold, Monitor, Witness) - H
f8dedd4b-b6f3-55fc-a123-b0c81686943c | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
35019eb7-6381-516e-b1bc-69464304fc41 | note | Frequency - During Construction
af7fd3e7-40f8-5d13-b811-d991bf0491da | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
061737da-4a8b-52c3-9a25-48b55abcd655 | note | Conformance Criteria - The final Bench configuration will be considered and agreed on site with the Engineer.
ae9e06f1-ea3e-5230-ad5f-025237e56e2d | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Bidim A64 Geotextile installation on the cut surface/faces
6355133a-0331-54d8-9b4c-54d9f74a6425 | note | ACTION (Hold, Monitor, Witness) - W
7561c5ad-1268-5d2a-88ef-8ac59c95945c | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G003
0bb3ff79-6bf9-51de-9b79-44843e607513 | note | Frequency - During Construction
ce53a0d2-adbb-5c2c-8efd-4d87d964ed1b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
2f6d1170-36e5-5bd2-9230-c753351aa623 | note | Conformance Criteria - Excavation undercut to be underlain and pinned with Bidim A64 or similar approved before placing rock and be laid/overlapped as per manufacturers recommendations
ab428bd4-ee94-50fa-867e-ce49b565c2a3 | note | Records - Photo's
| checkpoint | 2.7 - Rock Armour (700 to 1500dia) placed on the toe of the slope
02fa882c-e922-58c2-b8c2-8e4289ac6011 | note | ACTION (Hold, Monitor, Witness) - H
664b7ba0-96f2-54a9-a798-007624483cc1 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
a63c98a2-1cf2-524f-97ca-7444c4d3b7ca | note | Frequency - During Construction
926578ac-fb23-5fba-be02-119cb7539fc6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b550c8ce-1c67-5713-adff-166a92763426 | note | Conformance Criteria - 2t rock class 700 to 1500mm to be placed in toe and on benches to form revetment. Rock to be placed individually not dumped. Slope of the top face of each rock back towards the rockery/ revetment at an inclination of 5%. Any voids larger than 300mm shall be clinched with smaller rock and or infilled with granular aggregate (smaller rock).
123320b3-75e6-5a12-b8a9-1bd3fa3cc781 | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Rock placement
769f1152-a665-5412-83ea-e460a594e730 | note | ACTION (Hold, Monitor, Witness) - H
faa5bae1-f2fd-597c-a352-4912f4dbd10d | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12617302-01-G002
b597dd44-b841-5108-877d-1e1383236347 | note | Frequency - During Construction
7da0ef31-bd62-5e2d-835f-784bd1828251 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
9a8e367b-574d-5879-a3bf-ee5a6604961d | note | Conformance Criteria - Engineer confirmation during inspection and monitoring that the rock placement should be well placed block shaped rock,
8564e32f-7ed8-581a-b0c8-543d4ae197a5 | note | Records - GHD COR report, Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Verge
4a676475-cf11-5695-aece-4984689bce10 | note | ACTION (Hold, Monitor, Witness) - M
bcbf21bf-97e1-53cc-a642-c72d23c89de4 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
13e65308-7403-5ba0-9c66-47682b3c74db | note | Frequency - During Construction
8e5e64a1-c594-50f9-90ce-01bed6621750 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
5db463ef-9a24-59b8-9ebf-37778d58cd9b | note | Conformance Criteria - Verge reinstatement to match existing
8f3d20e2-be5a-54f6-8f81-6e5e7ffbc63b | note | Records - Photo's
| checkpoint | 2.9 - Replace existing culvert with new 525 diameter concrete culvert
3866932f-6448-5c19-80b6-5146189d3ceb | note | ACTION (Hold, Monitor, Witness) - H
065a1bdd-e118-51c5-86fe-9d8174023c95 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
ef47ee3f-f3b5-51fe-90f7-7298fea8d385 | note | Frequency - As works progress in agreement with the GHD engineer
3297b933-3e97-5167-bfe1-d62e536025e4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6236109d-eb93-5132-acdb-8767a002b6cd | note | Conformance Criteria - Exact location and alignment of the culvert as agreed on site with the engineer. Inlet and outlet areas to be shaped to be agreed on site with the engineer
4911f833-409f-5569-b4ab-00cf3615eb7e | note | Records - Drainage Line Record (CS-4025), Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.10 - Foundation compliance (Culvert)
04878e4d-bb44-5540-b862-2498613c549b | note | ACTION (Hold, Monitor, Witness) - H
b0f8a0a6-9113-512f-a435-1999711d75e3 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
2f576e37-fc81-54d5-9560-dd60a80e1b3c | note | Frequency - During Construction
ca40dc0b-6c16-54e5-9eba-d60436b0e339 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
7e314018-bfbd-57b5-afb2-a861f93d0214 | note | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
1516f1a4-2def-506a-b9e4-c45153f10521 | note | Records - 1M Scala check sheet (CS-4000), Scala test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 -
565732b9-71c3-54c4-b395-8fcb5ef4152d | note | ACTION (Hold, Monitor, Witness) - H
26c896ac-6f37-54e4-b8e7-f26b55c094c2 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C005
9423a2d3-64eb-5218-8ac1-a902b2fd82aa | note | Frequency - During Construction
c03e6ff1-1853-55b4-9d69-889f8939aa54 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
23635b0c-c51f-56be-b470-69cdf711de8f | note | Conformance Criteria - GHD to inspect and approve formation level at outlet of Culvert
f7390a16-0082-58b3-bf24-8c08db2b6f48 | note | Records - GHD COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.12 - Trenching and Excavation (Culvert)
31c7da60-d954-55bb-8e4a-fa2afe552bf7 | note | ACTION (Hold, Monitor, Witness) - W
4ba0c09f-f95a-5f2c-aaaf-a61e12084b08 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C006
a2ab2ada-2ea1-5aa6-a2a3-ed45ecac0b60 | note | Frequency - During Construction
59783e2e-252e-5e7e-8989-9854010a164c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
80af389b-7b02-546d-9085-c74107ad9539 | note | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
40d6f88f-5a18-5bcb-918f-38a749b157b4 | note | Records - Photo's
| checkpoint | 2.13 -
6a81172f-afb7-5fbb-9339-b292788c33b7 | note | ACTION (Hold, Monitor, Witness) - W
4c5defe2-050e-514b-b837-a8797e8ed6e0 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C007
6d082053-4ecc-5830-8558-47cf97f0c33b | note | Frequency - During Construction
118bf4ff-08ce-5149-8fbb-5fb347467875 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
913bf01b-9bec-5fa3-8b89-72f92024da70 | note | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
69fd984e-170d-5333-8001-8bb2437167e4 | note | Records - Survey As-Builts
| checkpoint | Inlet and outlet shaping
75e862d8-f86b-5748-95b8-8b4c2fe115c2 | note | ACTION (Hold, Monitor, Witness) - M
3ccb17e8-f0f7-581b-9851-26767b10b621 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
bdff2912-c1e4-5aea-a97f-44b525ab37f8 | note | Frequency - During Construction
e16da3a0-f309-5eeb-b9db-b9a5717feea7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4ac8f3b2-47e5-5dc9-8eab-8a2514d6cfef | note | Conformance Criteria - Inlet and outlet areas to be shaped in consultation and to be agreed on site with the Engineer.
8332e25f-68e4-54e2-b86a-43d4ac0af2cf | note | Records - GHD COR
| checkpoint | 2.14 - Bulk Fill on drainage trench and final bench
bebf1f2e-f48b-5c06-9091-0fcdb019f6d0 | note | ACTION (Hold, Monitor, Witness) - H
8a70afe9-0ec0-56a7-b34e-25a305690569 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
ee677248-6cc3-5ce6-98e9-46130cd7b089 | note | Frequency - During Construction
25c816e8-4e7c-59e0-ab97-3a3da5a352b5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
6f97e408-3297-53c3-9124-1f20b8388920 | note | Conformance Criteria - Bulk Fill Earthworks Record, Place AP65 in 150mm deep layers target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
162fc259-07cb-5eec-ae83-de8effee4b5d | note | Records - Bulk Fill Earthworks Record (CS-4020), Test reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.15 - Wingwall for Culvert Inlet and Concrete Pre-cast Manhole
f18dbfd0-2fe8-59bc-84bd-1a18f49d9883 | note | ACTION (Hold, Monitor, Witness) - H
5babf932-00d0-5a0e-9df0-0f88f8eafdc7 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
6e3cbf8c-b8e3-5c69-98fe-67c9fea63c68 | note | Frequency - During Construction
8cd4fdec-8cca-5392-9a72-d3d6157e4fcb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b996cf09-5d7a-59b3-a473-8d977c3d0b29 | note | Conformance Criteria - Install Hynds mountable wingwall or similar approved pointed towards approaching traffic tie in ground profile smoothly to match wingwall profile and to connect into 1050mm concrete pre-cast manhole with concrete lid. New culvert inlet pipe to have minimum 100mm drop from wingwall inverts.
6ef4b340-6b31-50bd-ad52-94822a65d53b | note | Records - GHD COR, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.16 - Culvert installation - new RCRRJ 525mm dia. Pipe
f1830254-6796-5ebe-a79f-80972762eca4 | note | ACTION (Hold, Monitor, Witness) - H
35dab34b-45f5-52d1-a209-37e63dc3263f | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
4a7343bf-262f-595b-b0cc-cc0a245eb554 | note | Frequency - During Construction
a57b4753-f6de-5b70-94c6-a689a2502493 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d6344577-b3ef-5820-b67f-eea4c78ee39b | note | Conformance Criteria - Installed in accordance with typical detail and manufacturers recommendations. Culvert construction and bedding to be as per NZTA F3 Specification. Consider using excavated river run as fill compacted to achieve 95% MDD
b515d3bd-56e7-5cc0-be9a-a3a6c8d8ed89 | note | Records - GHD COR, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.17 - Apron for Scour Protection at Culvert Outlet
ef226170-0e3b-5b4a-bc68-5252b5eb495c | note | ACTION (Hold, Monitor, Witness) - H
806c8a57-6da7-53cc-b743-17104f8ba6a3 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
1d8be51c-6a1f-5c26-9a97-4dedf26689ac | note | Frequency - During Construction
a2ea8d18-1d6c-5fd4-8958-401af6bc6011 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4cabc19d-6578-5427-aba2-27f04f6c8e36 | note | Conformance Criteria - Construct 2.1m long X 1.5m wide X 0.5m deep Rip-Rap (300mm-500mm dia.) apron for Scour protection at culvert outlet. Install Filter Fabric A64 or equivalent under rock Rip-Rap.
e8194478-ff3a-5641-9d0d-eb53a5591c76 | note | Records - GHD COR, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.18 - Fence installation
052db378-6a25-5895-9a24-830829aa65a9 | note | ACTION (Hold, Monitor, Witness) - M
ed102309-38e5-5c9c-8c8b-4edc9015ccb2 | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
d3a41696-9b2e-586d-be7e-b234e0cc08c7 | note | Frequency - During Construction
f5c8a831-75f0-534f-aedc-087a5dd92a3a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
cd78cdbe-c4d0-5187-88d7-d341ca19fe5c | note | Conformance Criteria - Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line
727a3678-b543-5865-bde6-cacd1e4fcc9d | note | Records - Photos
| checkpoint | 2.19 - Grass Seeding
835f8f2d-3445-5e05-890f-b6161d70c04f | note | ACTION (Hold, Monitor, Witness) - M
170b1910-aec9-5be8-8931-de1f3c504881 | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
cd8f635e-1870-57ec-8c0c-e9b3977ec3ef | note | Frequency - During Construction
ebb22050-0c2e-59cd-837e-7d0e6b0e3362 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f545c450-67af-503b-9fb0-d4b17394f3d3 | note | Conformance Criteria - All exposed earth to be grass seeded
f787e933-3ec9-5078-abea-2c04cb67cc96 | note | Records - Photos
| section | Section 3: CULVERT PAVEMENT INSPECTIONS
| checkpoint | 3.1 - Saw cut existing pavement
e3f05dc5-9946-5dad-8455-4038aeafb1c7 | note | ACTION (Hold, Monitor, Witness) - H
3b8e7e63-141e-5189-83db-9bd59c51e233 | note | Specification/Drawings Reference -
6f49d878-25d7-5783-87ab-0f5299fc30bb | note | Frequency - Prior to pavement construction
42f703e6-cf0a-525b-98c8-f0b32dc668d3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a6615936-83fd-508f-8dae-b90f85d742ef | note | Conformance Criteria - Smooth and straight saw cut
073956dd-9356-5b6e-96f8-27729dee1b1b | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Subgrade construction
820a7423-0164-5d16-8301-a6804fd2193d | note | ACTION (Hold, Monitor, Witness) - W
cd4b3709-945e-5709-ab2d-50f9f27bc55a | note | Specification/Drawings Reference - TNZ B2
dfc28fee-3ab5-5e84-a200-5af5dc099182 | note | Frequency - Every 200-300mm
8ee1c7e7-e757-5bde-8c9b-cf1751090340 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
de51802b-0ab3-54ce-a220-aa5f30e13cf5 | note | Conformance Criteria - Subgrade shall be AP65 compacted to average 95% MDD with nothing less than 92%, CIV>=25
dc1cf74b-155c-5c8b-ba26-8df6d31cbd5e | note | Records - Subgrade Approval Check sheet, Clegg Record Test Sheet, Test (CS-4100) reports
| checkpoint | 3.4 - Sub-base construction
881b7681-1792-597c-b2ee-cc10bf58f22a | note | ACTION (Hold, Monitor, Witness) - W
fafcdd8c-78af-5748-a0aa-f1a0f701ddfd | note | Specification/Drawings Reference - TNZ B2
488b074e-bca0-52c3-991a-e550d62e8cc8 | note | Frequency - Every lift
aba9bd0e-281c-5202-84e2-9931f0e91506 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
50e5cee3-28d4-5b53-833c-ce6134b96855 | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to Average 95% of MDD with nothing less than 92% CIV>=25
44970d8f-5ce5-5c76-9ec2-2a65adc365b9 | note | Records - Clegg record test sheet, Photos, Test reports
| checkpoint | 3.5 - Sub-base construction
1c99e405-a6ea-5443-99f4-2312be9fe2ce | note | ACTION (Hold, Monitor, Witness) - H
d1c30ae4-78e7-56bf-a68a-00b329b9d5d7 | note | Specification/Drawings Reference - TNZ B2
d1274894-7207-5f7a-8c5c-3a548b740ca2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
e04b068b-9c7a-5df3-b01e-2341f69f7c01 | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
b09345e5-4822-584a-bcbe-bd443ecad482 | note | Records - Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Basecourse construction
1fa943b2-dc58-5ad1-a1e3-8acd1e3416b3 | note | ACTION (Hold, Monitor, Witness) - W
7f5ba2de-27b8-5ff8-b26c-9a8ea18ffd22 | note | Specification/Drawings Reference - TNZ B2
1ff1d399-7fb1-5e22-9842-a6a1e79e68bd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
3391a213-947d-579d-ad67-827b4c3c0a06 | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
ed08f4fd-5016-5d5e-811e-1034aa10edd4 | note | ○ Average 98% of MDD with nothing less than 95%
f14999f0-e855-5cc4-acf3-d03f1d9a1999 | note | Records - Test reports, Photo's
| checkpoint | 3.7 - Basecourse Cement application rate
2cece770-a6dc-5cfc-a509-1692de721552 | note | ACTION (Hold, Monitor, Witness) - M
a54ea526-1f1f-57f1-96dd-2bc087e74982 | note | Specification/Drawings Reference - TNZ B/5
7eec204e-a31a-5fd5-9db8-7efe2e78c093 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
75d29dee-2a0f-5ad4-8884-da7924c6904c | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
d48a90f3-bb6a-5d03-82f3-4233b34bf78d | note | Records - Photo's
| checkpoint | 3.8 - Basecourse construction
75860352-26d5-555b-84e3-d754f26a43e3 | note | ACTION (Hold, Monitor, Witness) - H
ee24cac9-af32-5734-a685-38521b071ec6 | note | Specification/Drawings Reference - TNZ B2
527e7ba9-b37a-5346-a03e-383c7dd95cc7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
1552abd5-0913-5bdb-8c7d-8dfd75663cdf | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
809e53d3-2406-5416-9d8d-6953bc18bb86 | note | Records - Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Basecourse construction
904c9fff-f20c-59e3-8a19-74fe8a8e34bd | note | ACTION (Hold, Monitor, Witness) - W
d3c7a6c2-29b0-59c1-a308-5926ad0f40ff | note | Specification/Drawings Reference - TNZ B2
bce3d906-ccc0-5aff-9ed4-28de8a2cc3c4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
b455ee13-2b61-5c75-ad71-2e27b58e439d | note | Conformance Criteria - CIV>=25
66445809-7b48-57cc-a8d8-544d8caeb469 | note | Records - Test reports, Photo's
| checkpoint | 3.1 - Basecourse construction
593bc92f-2a37-5135-beac-6554c2e15a63 | note | ACTION (Hold, Monitor, Witness) - H
80765426-c388-5561-a7b0-3a138f17a4f0 | note | Specification/Drawings Reference - TNZ B2
8767bef9-a043-53f5-aae6-f90bf4bc64bb | note | Frequency - Before sealing
a448771b-0eeb-511b-a1cc-34fe900b4307 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
2d5b19ef-d7e9-5f34-9f50-f60ed0d24ba8 | note | Conformance Criteria - Mosaic surface
e4d65fd4-dcb1-55e5-887b-ae934b5f9c6d | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.11 - Applying Bitumen
9cb0f1d4-2a11-5049-b031-5ec39c96a857 | note | ACTION (Hold, Monitor, Witness) - W
db9ba2a9-ef25-5368-acd2-bae6715eab06 | note | Specification/Drawings Reference - NZTA M/6
fa2b8412-280f-5c1c-823f-deefc169fe0a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d2407a53-8761-5fb1-a9b2-2ab2448fef58 | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
a130ec71-0535-5221-aa54-3d6ce04ce2c5 | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| checkpoint | 3.12 - Degree of saturation
29a24789-b019-53e2-8ab2-d3a28ab8968f | note | ACTION (Hold, Monitor, Witness) - W
8e25cd6a-7625-5e6a-b344-396d7261cdc2 | note | Specification/Drawings Reference -
3ceabb78-541d-514e-8fe9-3f95f2b6a114 | note | Frequency - Before sealing
047733a5-a0dd-5636-9f07-cfa2835d8aab | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
5c8c3caa-21eb-5bbf-ab5d-b098c395a178 | note | Conformance Criteria - Degree of saturation should not exceed 80%
4799a418-526d-597d-a436-6d59e60ece7a | note | Records - Pre-seal checksheet (CS-4060)
| checkpoint | 3.13 - Chip seal laying
6a0ba525-2a2c-5c4d-a499-0c0cf754b151 | note | ACTION (Hold, Monitor, Witness) - W
7e4d681b-7d6e-581b-ae71-4ab99b82f64a | note | Specification/Drawings Reference - NZTA M/6
2615a5f3-6b6a-5290-9c74-bffe4efd8383 | note | Frequency - During Construction
a1e2ae64-2d1a-5806-ab6d-22e610527024 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
c3daa349-edd0-5b44-84f6-3d4c05d2c76c | note | Conformance Criteria - grade 3 and 5 chip seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
3759ec59-1751-5642-9ab1-0176646fccd9 | note | Records - Photo's
| checkpoint | 3.14 - Sweep & Line marking to new chip seal road
619cd07b-1ecf-5508-b27e-c602f073dc1a | note | ACTION (Hold, Monitor, Witness) - W
f4d601a2-d7d9-5a38-bcc5-d34b264d13d7 | note | Specification/Drawings Reference - TNZ P/12:2000
523cc3f2-11f3-50ef-8d14-de030a28f0b0 | note | Frequency - During Construction
d8c5d4a5-7801-5d9d-8e8c-25a32d9b226e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ec285ab7-a7bd-5169-968c-4a2608674fcc | note | Conformance Criteria - As per TNZ P/12:2000
de40ede8-f93b-5622-a119-8acdd1cddf19 | note | Records - Photo's
| section | Section 4: Post Construction - FINAL INSPECTION & HANDOVER
| checkpoint | 4.1 - As-built Survey
de3dd19c-1e4c-5d39-a5b3-fd14f52da74e | note | ACTION (Hold, Monitor, Witness) - H
7913f9b3-7faf-5406-9a6a-2b291a0c3731 | note | Specification/Drawings Reference -
0cee0d96-7cff-55f7-b906-0fc739ae20d5 | note | Frequency - At completion of Lot
9fbba6e7-6f40-5ccf-b2e2-a0b36afebe9d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
9a5d4416-3825-5873-8400-1e58cee22b23 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by GHD Engineer
1dd0bacf-f0c6-5a8f-a372-5f9e0e3de8b2 | note | Records - As-builts, GHD COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Inspection of site following completion of physical works
8a7b5465-536a-519b-afb8-6da74c978a98 | note | ACTION (Hold, Monitor, Witness) - H
e4a643a6-98ea-53e8-9cc8-92f3cc5b93da | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
0c8f83a7-2496-5ae8-ab31-cbd763ecdfda | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover/Visual Inspection
6bb50ab6-45b8-5428-b932-06c695e33a3c | note | Conformance Criteria - Inspection of site following completion of physical works
01be4d60-72ee-5289-8b70-e03142fdb9e9 | note | Records - GHD COR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Quality Assurance deliverables
24525758-4de0-5f88-bc1a-489b0a4c66ce | note | ACTION (Hold, Monitor, Witness) - W
14fe81ed-fbfd-55a8-804c-6b9a8b6bb5dd | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
c2900dfa-3b65-5a8b-8109-8ea0f2aeebbd | note | Frequency - At completion of Lot
55c23ded-4a83-526b-bf5d-5da8ae2bce44 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a1247148-3da7-5eaf-a792-e9f50b0349c9 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
c1910acf-6226-5f2d-8035-8e4a4d54bf4b | note | Records - As-builts, NCR's and RFI's
| checkpoint | 4.3 - Completion Sign Off From Fields Below
6a76a45a-b4c4-5845-9c11-3077f384f9dc | note | ACTION (Hold, Monitor, Witness) - H
2a333d35-6d53-53fd-8702-c8ba2dc42c48 | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - G1202A - Waikaretaheke Overslip #3 - Network Drainage | itp | ITP - G1202A - Waikaretaheke Overslip #3 - Network Drainage |  | 8b5fb8c7-215e-4f94-ab74-7c9c1c9a646a
| section | Details
| checkpoint | Project Site reps.
1fda3bc9-409b-537d-88a9-49b339b5c600 | textbox | CPS Eng.
a4c55642-a82f-5e18-b444-d59bb685fbc8 | textbox | Site Engineer
46cdcef9-5ed5-5837-b79f-bf96617a116e | textbox | Quality Eng.
| checkpoint | 1 - Locate existing services by hand digging/hydro excavation
cd2c6db2-15dc-5eae-b899-b9e19fdc4cfa | note | ACTION (Hold, Monitor, Witness) - W
8b95d867-c22b-537e-8593-f5bd83924ef8 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
5540c231-0984-5a22-a54c-6143e9589927 | note | Frequency - Prior to commencement
a4aa2c7f-c5f5-5bb8-a2b7-afbead17c450 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
7af0a82e-6370-5abf-9c40-27fddf11e52f | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
9623d5d3-772c-5b65-9be3-b7dbbb7f31a7 | note | Records - As-built Drawings Doc. Review
| checkpoint | 2 - Trenching and Excavation
692260d6-02f6-5190-87fe-88dc43ecbd15 | note | ACTION (Hold, Monitor, Witness) - W
787bd98d-b991-5df5-9ffe-ea12f2ccb966 | note | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
4c1162ee-0003-5371-b4b2-c7e80d826ce6 | note | Frequency - Daily
78d2d16b-689e-5c08-927e-8ea094b8039c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
a7ee3182-9052-5a7e-a96b-6d8132669962 | note | Conformance Criteria - Line and level is correct
5ae01b46-057e-52c3-8470-345a05d0cffa | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 3 - Trenching and Excavation
d12d8c9a-bfea-57f8-8df7-e70c130704db | note | ACTION (Hold, Monitor, Witness) - W
55f6e185-31b8-592e-bd80-fc8ecfad5146 | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
2d6098be-5621-5f75-9ee5-7c6ca34a9ce5 | note | Frequency - Daily
de948657-613c-5c17-9e28-077e580ac465 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
f80de7bd-162a-5817-87b6-85cd516802a4 | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
a813cddd-3dba-5870-8b07-7631f6b1cb11 | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 4 - Foundation Compliance
af79596d-3466-5bee-b499-63b0040fef15 | note | ACTION (Hold, Monitor, Witness) - H
52320a71-3bb0-5ff5-bbf7-dfa4930fc52f | note | Detail - Test formation level on completion of excavation to check if undercut required
3064f3f2-a357-5493-bef8-f6e3805d46da | note | Frequency - One test per 20 linear metres
876e493f-e6d3-5d53-8183-70c3d4e221df | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
1a31888e-f5fa-543d-890e-19d54e7363b8 | note | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
6073bcfb-a71f-5c96-b129-47b895c052b4 | note | Records - Scala Record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Pipe Bedding Material Compliance
5a1e06ad-8a31-5760-8cda-a8aa6947c289 | note | ACTION (Hold, Monitor, Witness) - H
0aa17af5-4296-53f5-af73-9a4a3ee4f64d | note | Detail - Material to meet specifications dependant on material type selected
b5d45428-141b-5c12-95d9-64182e4f57a5 | note | Frequency - Each material used
64a29b7c-b8ad-5bb8-ba03-1f078a30da76 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4c603003-80a1-587f-a513-6e66f2a77092 | note | Conformance Criteria - Bedding material
e95966a0-cf8e-5821-b497-fed510b1b82b | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Bedding
0923c592-8c9b-5c19-8ace-643c7bbc2e03 | note | ACTION (Hold, Monitor, Witness) - W
971b623d-ff52-58bb-877e-a15ea822fc70 | note | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
a0d5e98a-8120-5b8c-b47d-cd8d465ea61c | note | Frequency - Daily
2bd97e56-1331-5a98-abc1-af10be06afac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
23c99cbe-d646-5c5b-81b8-eb37bfb4f231 | note | Conformance Criteria - 150 mm thick bedding for all mm dia pipe
e4f664f8-cd7a-5bf4-a29c-aa43993c9105 | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 8 - Pipes and Precast Units
c8d7b0a8-aed9-5b76-9ab6-c639a0e611ca | note | ACTION (Hold, Monitor, Witness) - W
47442f82-6f98-5005-b3cd-618440e9783e | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
d56d6a65-2b8e-531e-a128-231f83098c42 | note | Frequency - Per pipe
7d3d1e4b-a863-5590-a434-3a6ebd2c7b5d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
077f1059-b4bc-53ab-9164-c2fb73543168 | note | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
cb8e96f7-5adc-5a44-96b6-806afeee879a | note | Records - Photos
| checkpoint | 9 - Pipe Laying
3330c6a0-1b96-5f7f-9cb2-d583921b9f01 | note | ACTION (Hold, Monitor, Witness) - W
6b3b8249-8ced-5be9-9277-6ae0c5bcbc3e | note | Detail - Pipe Laying - as only replacing section on outlet of existing pipe, grade is to follow existing levels
6ca009cc-e19f-566b-9e6e-f0358b0082c4 | note | Frequency - Prior to backfilling
c652ace6-ee73-5013-88d1-9f7bc1f62ad3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
f7d9663a-a5a6-5661-8563-3f375fd07b57 | note | Conformance Criteria - Invert level following pre-existing grade
2eda8e12-7885-54e1-a506-01b0f888d74a | note | Records - Photos
| checkpoint | 10 - Pipe Laying
a60fb744-3c14-544c-be60-e56b1754ceab | note | ACTION (Hold, Monitor, Witness) - H
b04b9d2b-aa0f-5eb1-917a-0418f0453bdd | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
e790ebcf-36ab-56cc-8a39-4dd55a4c8472 | note | Frequency - Prior to backfilling
b65eee45-d2dd-5987-bb67-263582ad3410 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
123f5ff3-fd23-546a-8492-9397c5305041 | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
2991f685-ce14-5b64-bda5-e77b55d6bdb5 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Pipe Backfill Compliance
2686a1a2-7d72-5a81-bb00-12d0dcfc184a | note | ACTION (Hold, Monitor, Witness) - H
34f14952-eb58-57f1-a668-86d57cc3703f | note | Detail - Material to meet specifications dependant on material type selected
8b54f006-9921-5fe3-8a21-e7df1503230a | note | Frequency - Each material used
b05cf48e-feb7-59d8-8286-d2b2aee46c1c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
bb23f186-77b2-58ff-b30c-4c2447f70943 | note | Conformance Criteria - Compliance with requirements from Specifications
634e2ddd-13c7-5ec7-9e59-b53431a598cd | note | Records - CS-4025 Drainage Line Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Pipe Backfill Compliance
d18fc675-2e61-5c68-9700-72cddc9e1dd0 | note | ACTION (Hold, Monitor, Witness) - W
5f72e963-f721-5e6c-972d-ba61bd451a4c | note | Detail - Backfill Construction Material
74221a0f-4255-5faa-85f1-67cb2a043d2f | note | Frequency - 1 test per 50m
85c48d26-8d69-5f8f-b58d-2623cf581b80 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
19cba11c-57b5-520f-8fe2-79023e92f412 | note | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
e12bfbcc-f9f6-5768-97a7-7f70c2fcd43a | note | Records - Lab Test Report
| checkpoint | 13 - Backfilling
2b48186c-3bd6-55f3-9296-d9e9b4b53ff0 | note | ACTION (Hold, Monitor, Witness) - W
c5bc1d40-fef6-5eb9-87ff-ed860cebb652 | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
87bfd999-ca7a-5527-8130-2a913ee0fa9a | note | Frequency - 1 test per 20 m length of trench per 300mm lift
8884610c-ccae-5374-949a-15ebb1e8cbdc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
d6c2f02b-9fd2-5c18-916e-4fa2c1e4ef47 | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
98e3c371-25c1-58e3-be0d-f0c6016857ae | note | Records - Clegg or NDM Test Results
| checkpoint | 14 - Quality Assurance deliverables
e867cee8-9be4-5e17-b347-8ffba9f87fbb | note | ACTION (Hold, Monitor, Witness) - W
ce0634ee-4c05-51c5-a2fb-80dc8ea80a78 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
8bb73d9c-9fe2-5d74-b086-a7f1110438b4 | note | Frequency - At completion of Lot
076100cb-fff6-53b2-bbe3-f82f5c44f1f2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1aa5aff7-319e-5f24-a6c7-d888c8c7fb65 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
ff026c5e-0ce2-5b01-bf53-ddd4ae239f73 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 15 - Completion Sign Off From Fields Below
d3f3075f-c66b-59a7-a44d-8b44645547f0 | note | Records - Signatures
| checklist | ITP - G1202A - Waikaretaheke Overslip #3 - Rock Armouring & Bulk Filling | itp | ITP - G1202A - Waikaretaheke Overslip #3 - Rock Armouring & Bulk Filling |  | 80b3e6ff-3356-4ff3-89a7-7e36524b8d3e
| section | Details
| checkpoint | Project Site reps.
1aaf5e02-b3e5-5804-a831-daadbfa324b0 | textbox | CPS Eng.
183729c4-a1d5-5d93-bf91-713a07508cc2 | textbox | Site Engineer
ab88cf91-d294-53d5-9fd3-5cee5568643a | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
e1f38f48-d12d-5f11-a62d-1ade130b87f9 | note | ACTION (Hold, Monitor, Witness) - H
5f72ff74-57f5-552e-9013-1c0d7b3c3cd5 | note | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
87b918eb-dc9b-5998-8f3b-373fb9a0a730 | note | Frequency - Prior to commencement
b5a5d8ea-34aa-5fe5-ae5f-9922c36d5b2b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
614d1c1d-85ba-5669-9c8d-2761e9600490 | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
2dae98ec-7d44-5de7-9d28-bd844b6a9b48 | note | Records - Survey receipt / sketch markup
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
5b9b2e17-8cc9-5794-8336-b62c1afd0d40 | note | ACTION (Hold, Monitor, Witness) - H
3bd4f410-2f93-5f9c-858d-90c3c6a6df4a | note | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, at Geotechnical Site Engineer's discretion
e48e1c45-8c3d-5f4f-8a11-91ee93d28e60 | note | Frequency - Prior to commencement
895a6605-6dc3-528e-8687-4781da5ef8b0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
1a5830e5-f57f-563f-94aa-d0d4b4fc8636 | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
0d8920ea-eaed-577f-9ba6-cd986618ab22 | note | Records - Sketch
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Excavate to Sub-Grade
95ffbeb8-cced-5019-8200-ff627322923f | note | ACTION (Hold, Monitor, Witness) - H
4355d788-40b2-5721-82be-13ce348bb41c | note | Detail - Excavation only to start once ESC in place as per ESC ITP. Inspect fill foundation.
4096fb2b-5d20-5155-b486-71dfd434a5f3 | note | Frequency - Per area as required
d7df1edc-5fd2-53fd-bf6f-0fe278ff1527 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
9790464a-fadd-5f26-8fd3-7a71f7aa4cce | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
eae83166-6566-52fe-acac-4c45f794c86d | note | Records - CS-4100 Subgrade Approval Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Excavate to Sub-Grade
11743bbc-58e4-5920-9b14-70207ec44141 | note | ACTION (Hold, Monitor, Witness) - W
f141e38c-a9ab-5199-85b7-19667c4b6af5 | note | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
ea9a4b06-3eac-593b-8113-31cdd5b681fb | note | Frequency - Per area as required
c2389461-c32a-5588-9d7f-fd1fa0716364 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
01961d33-4516-5265-a6da-0446c926244d | note | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
058d63da-0d78-5a4b-b184-e2e853e23ca6 | note | Records - Engineer or Lab Test Report
| checkpoint | 5 - Material Compliance Testing
dafb6580-16d3-5389-994b-cdc3d95de44a | note | ACTION (Hold, Monitor, Witness) - H
da0fd2d9-d67f-5f82-b51c-2710294d266b | note | Detail - Material to meet specifications dependant on material type selected
260736a5-7d2a-57ad-9a77-bb9a14358aec | note | Frequency - Each material used
314a69c0-be9a-5d63-8ab7-e0460e5957f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0255f467-0b6f-5049-b3fe-4308236ce5e0 | note | Conformance Criteria - a. GRADATION D85/D15 = 1.9
2cf9de52-99cf-5d33-aab0-65e299d11b8f | note | b. D85 690 (MAX) AND 590 (MIN)
d379fd8b-41ae-5266-869c-dc011e96eec4 | note | c. D15 390 (MAX) AND 275 (MIN)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance Testing
8cada2d1-c449-5925-89c0-7001f91b6363 | note | ACTION (Hold, Monitor, Witness) - W
419d723f-fb53-5f25-ab28-53a69fce9073 | note | Detail - Rock Construction Material
f14a50df-dde8-52d6-b4dc-298508248c7a | note | Frequency - 1 test per 1 000m3
d52778be-a38e-5af9-8ab4-2d50ec13ae0c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
9c8e34e1-534c-5004-9ef1-172c2ff65226 | note | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
d219826d-6b81-52c7-8d24-7905f6c5f9fa | note | Records - Lab Test Report
| checkpoint | 7 - Material Compliance Testing
63644ea4-3bfb-5e40-baeb-dc44882fba96 | note | ACTION (Hold, Monitor, Witness) - W
20e505f2-fa99-5afa-971c-bb2ce42ccdbd | note | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
86d0e016-9bc6-5f16-98af-085f989a31c3 | note | Frequency - Prior to commencement of placement
9ef19a43-ba9e-5b12-a64d-9660e78f288a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8fac69fa-e6bf-5ecf-a5d5-859a897a0e37 | note | Conformance Criteria - Conformance with Specification
e760a788-c035-5561-944a-85ce1f16a96e | note | Records - Delivery Dockets
| checkpoint | 8 - Material Compliance Testing
1fc3f692-df5c-58ba-b28b-daf307df49cb | note | ACTION (Hold, Monitor, Witness) - W
863a2978-07b4-514c-a260-82203134f971 | note | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
acfad55e-6d93-5e18-86c6-a1e65e909991 | note | Frequency - Prior to commencement of placement
7b4e40c9-dffb-5010-b656-5a2093eb511e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0afcb380-96d0-5421-a991-ae207a27c2af | note | Conformance Criteria - Conformance with Specification
1f404334-d3cf-589b-8ecd-d0a73155a15e | note | Records - Delivery Dockets
| checkpoint | 9 - Material Compliance Testing
00462b8f-5fe6-59a2-9315-2988a7370cbc | note | ACTION (Hold, Monitor, Witness) - H
63c74947-61c6-5c1f-a6da-65973eab6145 | note | Detail - Bulk Construction Material
ed65e90c-d88d-5f4b-9070-8b0a8ecb24ca | note | Frequency - 1 test SET per 1 000m3
f323973c-2ab4-5f2d-9e82-01bf211ef74a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet sieve)
b545d3f6-a5b6-5b88-a853-9687d08ae55f | note | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
6be51878-f401-5af4-8c2d-02efcae0336e | note | Records - Lab Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Geotextile Placement - Backface
4e5341e0-1006-52b6-9cae-f78a0f30ca6f | note | ACTION (Hold, Monitor, Witness) - W
0b4fb4f9-ce15-5a3d-8955-35deaebdedf1 | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
24d7f43f-22b0-571d-835c-23b76a447f5c | note | Frequency - Daily visual check
0ecfddcd-5ba8-584c-82b0-85582a73c402 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
72ac4623-1e29-5f68-b39d-7d55515c2a2f | note | Records - Photo's
| checkpoint | 11 - Backfilling of Engineered Fill Embankment
bf5495e2-1fd5-54e7-b38c-a1099b484206 | note | ACTION (Hold, Monitor, Witness) - W
5f38aa16-ec19-52a6-9f9d-7390a31d1dea | note | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
ca561128-7b23-514e-99ef-96d19b8df76a | note | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
781ff798-2fb1-5bcb-8ac1-c6343196eed1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
fb728b70-2fa0-5051-9020-47afe1a1439a | note | Conformance Criteria - 95% of MDD or clegg equivalent
dcf3f317-2f9c-5386-b0f9-adf74fbddb5a | note | Records - Lab Test Reports
| checkpoint | 12 - Construction of Engineered Fill Embankment
b8229fb2-01e1-5fbd-a902-2a691af077db | note | ACTION (Hold, Monitor, Witness) - H
e8a6d18c-8bfd-5a45-b4b5-9f2a94bace4b | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
21ad2db0-7f41-5b80-bf75-7fa48f24a036 | note | Frequency - Prior to commencement
451d4667-1e1f-50b8-baa2-2043147749f4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8f27dfc5-7f99-57bb-b42e-a783962f4ed0 | note | Conformance Criteria - ALL BULK FILL MATERIAL SHOULD COMPRISE CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65 OR SIMILAR MATERIAL.
a3bfbc33-d7b6-53e0-9230-f958503205e1 | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Geotextile Placement - Frontface
76b32109-022e-5be8-883e-f150f8d47df5 | note | ACTION (Hold, Monitor, Witness) - W
4a0f45ec-66cb-5136-9546-d9ad10e67caa | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
389f52fa-a1f0-55d0-aa39-332690c533dd | note | Frequency - Daily visual check
9263fcce-ec9e-537c-a97f-f66e7d8a6be5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e6d506ec-d6c6-5f95-9cbe-5f3b9aecfe9f | note | Records - Photo's
| checkpoint | 14 - Riprap Placement
9e1e5865-e114-57a6-a62d-4e377afa96a4 | note | ACTION (Hold, Monitor, Witness) - W
dd6f7817-f079-54fc-981c-358977c8158e | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
2661e7f8-edf2-5b5c-b05b-efcde4d2016c | note | Frequency - Daily visual check
5ea0d486-5aff-5a77-932c-ec8a474bd29d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ac069992-1004-5209-b475-81b0cf869b7c | note | Conformance Criteria - Specification
3524a439-6860-52a7-a31e-0d01d78e6860 | note | Records - Photo's
| checkpoint | 15 - Tie in to existin swales
664a9854-b170-516b-98fd-7957c4f52c07 | note | ACTION (Hold, Monitor, Witness) - W
398ae4fe-2bf3-5150-b157-4c77458ed43a | note | Detail - Ensure drainage swales are insatlled to tie in with existing swales to esnure drainage flows correctly
39f06ef9-638e-5714-9092-a51116eb3101 | note | Frequency - Daily visual check
e4ed5720-346f-52d0-a365-f02a2f0afd1a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
575eb873-b13b-5698-8730-609a7f948d17 | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
ffe7d7e0-eb99-5d2d-b5d1-6c78b69a19d3 | note | Records - Photos
| checkpoint | 16 - Quality Assurance deliverables
8f3d7360-ea79-5bc5-b122-615d6d505ef7 | note | ACTION (Hold, Monitor, Witness) - W
fd9da0f7-36a1-5056-be2d-fd88fdf9cce8 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
0d6b272e-d806-576b-ba88-a1120e9fe8ad | note | Frequency - At completion of Lot
f9f63fcc-7d81-5a1e-b0c1-2e04e9361f7e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review. Red line mark up notes of design plan.
abc021f8-80f0-5f5c-8d6f-5d220ca0cce8 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
b62d1345-1f75-56ff-b968-a827d3ef15ea | note | Records - As-builts, NCR's and RFI's
| checkpoint | 17 - Completion Sign Off From Fields Below
c021397a-3e64-50d2-97ca-2e84d8c4dc0c | note | Records - Signatures
| checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Compliance and Environmental | itp | ITP - G1202A - Waikaretaheke Riverbend Recovery - Compliance and Environmental |  | b01d59ef-d668-43e1-a1e5-39144e7bc786
| checkpoint | Project Site reps.
88e2a397-a2a8-57ce-bb59-f25c5eb450b4 | textbox | CPS Eng.
a7152f1a-2dff-5955-b3d5-720e372c19a9 | textbox | Site Engineer
ed542aa1-c975-52c9-b11d-9c4abcae4db4 | textbox | Quality Eng.
| checkpoint | 1 - Approved Consents
574850ff-6c80-5782-804c-a179caeeb9e3 | note | ACTION (Hold, Monitor, Witness) - M
8c6e7f5e-311f-5fef-88e4-7184f9533639 | note | Detail - Is a copy of approved consent(s) available on site
13b50fc9-8d46-501c-a0d9-f4ec2e0bb229 | note | Conformance Criteria - Check latest consents and SSESCP's are at each site office
a6330879-2007-5787-85b5-f0e821d04bd7 | note | Records - Copy of Consent
| checkpoint | 2 - Internal ESC Pre-Construction
42f4efc9-3d7c-50f6-987b-99581fc10757 | note | ACTION (Hold, Monitor, Witness) - H
e368b1f4-cf3e-5a60-9c4c-81b0ca97332f | note | Detail - Internal pre-construction meeting held with Environment Team
a42e9670-b074-55f2-ab33-69fc33a98514 | note | Conformance Criteria - Environmental Advisor to organise
b45716fe-cf10-5a2b-b0b5-7ed1a54463d7 | note | Records - Meeting minutes or similar record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Type and Location of Erosion & Sedimentation Control
059da8b9-d7bf-5085-afdf-f1c5d7825926 | note | ACTION (Hold, Monitor, Witness) - H
061b668b-b7e2-5610-8897-fb12c2f564c9 | note | Detail - Confirm type and location of erosion and sedimentation control, based on relevant drawing/s
47957109-37e4-520c-a156-311ad2c66ffe | note | Conformance Criteria - Relevant ESCP drawing
3b4222b7-de06-5df0-9dc8-73b7b807f54b | note | Records - Relevant ESCP drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Channel Bund (if required)
d8f9d0a0-7f53-59b6-b415-0a8d9a0e527d | note | ACTION (Hold, Monitor, Witness) - M
f8032a87-a737-5ab2-ae81-a1ce00295193 | note | Detail - Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted.
8684bed6-66df-59d3-bbfa-ace3967d7a42 | note | Conformance Criteria - Work Instruction, Drawings and Checklist
03a9bd65-d80d-53ea-8faa-a1b8ee3834d1 | note | Records - Photos and Checklist
| checkpoint | 5 - Silt Fence (SF) (if required)
63491a1a-cd90-58dc-98c8-8f9ff4c64ab5 | note | ACTION (Hold, Monitor, Witness) - M
e3eb192f-ee19-503f-bedc-ee07c161619a | note | Detail - Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings
d50b1efc-d80a-5c01-a930-43546deadb98 | note | Conformance Criteria - Work Instruction, Drawings and Checklist
432cffbb-ace7-5281-83dd-025e4bcb062a | note | Records - Photos and Checklist
| checkpoint | 7 - Maintenance Inspections
af1b48e1-e251-5044-9ee8-ae83fa6948ab | note | ACTION (Hold, Monitor, Witness) - W
370af2d4-2bc1-5ad7-ac21-26e21b1e8406 | note | Detail - Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance
b19140e3-a89c-5874-9009-95dea27f8301 | note | Conformance Criteria - Approved ESC Plan. Complete weekly and upload to ConQA / Procore
14debedd-6790-58b6-9e57-3e3eb364f28b | note | Records - Inspection Record
| checkpoint | 8 - Decommissioning of Erosion Sediment Controls
4be35db9-c330-56b8-a6d6-9543e0d6e029 | note | ACTION (Hold, Monitor, Witness) - H
b9fef797-6845-5fe6-8ee7-bfa7c318e0e8 | note | Detail - Decommissioning Plan submitted to HBRC for Approval
728afc50-3fd7-51f0-bd79-9ceccdcd5d49 | note | Records - Decommissioning Plan and Email record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Decommissioning of Erosion Sediment Controls
1a9e2774-7245-5bb2-9330-458268c0d2b2 | note | ACTION (Hold, Monitor, Witness) - H
2a4d7d2f-641a-55d7-8396-a72feae8c3e3 | note | Detail - HBRC to issue an approval document so that Decommissioning works can commence
c458b923-57aa-5cee-a0eb-4c08cad5e0c8 | note | Conformance Criteria - Approval for Decommissioning
f7b29347-56bf-5b07-b25e-d5791c8b4316 | note | Records - HBRC approval Doc
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Completion Sign Off From Fields Below
b6ebb761-d585-5493-97a5-9760ce7b4cf3 | note | Records - Signatures
| checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage | itp | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage |  | a237353b-2194-49c6-b9aa-762b2474f4bb
| checkpoint | Project Site reps.
7fbddc50-e153-537c-b301-3aefd19c37b4 | textbox | CPS Eng.
b89050fd-c618-5fff-9847-038b72e20eea | textbox | Site Engineer
64b83f64-e765-5ac6-b2bd-f5a5bc8ef4ec | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
2e57edb8-9554-5d89-b2d4-e135d311d621 | note | ACTION (Hold, Monitor, Witness) - W
67d7e0eb-3927-5068-9b49-86fea18c8b0c | note | Detail - Setout inlet & outlet points with inverts as required by Contractor to construct to design
e909b721-0b58-5beb-9edc-fe87de61d607 | note | Frequency - Prior to commencement
e9f8aaa1-8df2-500f-ad78-553217978fe7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
57f6de6f-09c8-5dd3-b90e-b0517be7f089 | note | Records - Survey receipt
| checkpoint | 2 - Locate existing services by hand digging/hydro excavation
00e93fb7-4f8f-5020-808a-d389ad869983 | note | ACTION (Hold, Monitor, Witness) - W
71739925-c04c-5b65-bffa-475a35c3cb8f | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
ded29cd8-df38-5728-8e6c-8d99bb830421 | note | Frequency - Prior to commencement
6b1ca492-8faa-5b93-99f2-bec14275bde2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
c005ee1d-e81e-5b91-9098-a83204413e86 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
ff27047a-17e2-5296-86aa-6a7a24792304 | note | Records - As-built Drawings Doc. Review
| checkpoint | 3 - Trenching and Excavation
01c1baff-6244-539c-a2c8-c453e5df57f1 | note | ACTION (Hold, Monitor, Witness) - W
84be7284-861c-54f8-a854-46f0e5be9470 | note | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
0c975529-3411-52b2-90f4-6b408ff56c17 | note | Frequency - Daily
697b7ba8-9aa5-5eba-aa85-4ab801ca8e79 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
40c2e924-07eb-53ae-a072-fcc784eb7efd | note | Conformance Criteria - Line and level is correct
10fd0aef-25ba-5aad-8db0-5db58a8f1624 | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| checkpoint | 4 - Trenching and Excavation
4f54e8f8-4522-5a4c-b600-c65c4614a9e5 | note | ACTION (Hold, Monitor, Witness) - W
dc9a9e5a-2018-5803-9838-c1a56de5cef1 | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
434a48c3-101f-564e-8b74-76d558524aa7 | note | Frequency - Daily
06d2fa9c-2eef-5e41-afe6-78aaac36e186 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
c7147289-a3a7-5661-927e-945b4373f524 | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
157f966a-1aac-5419-9165-912860d594f8 | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| checkpoint | 5 - Foundation Compliance
7c5404f6-c18c-5f90-be33-d4ef39d7e7cf | note | ACTION (Hold, Monitor, Witness) - H
44c6b0f4-553d-5564-af85-437d9528592c | note | Detail - Test formation level on completion of excavation to check if undercut required
d15c4f64-3419-5d57-8136-738022579b13 | note | Frequency - One test per 20 linear metres
468c2bb8-6d36-5038-8995-70de93f229b8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
34680943-5851-5855-a20a-25f158c4e333 | note | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
f3be3a46-787c-5d0d-859c-0ee33cef8358 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Pipe Bedding Material Compliance
a0297ffc-d5b4-5448-a980-df5b3588abc1 | note | ACTION (Hold, Monitor, Witness) - W
223b949c-f401-5295-bdaa-f01640bcbdc4 | note | Detail - Material to meet specifications dependant on material type selected
1f2e95b6-de68-5128-9dbe-474f42c4415e | note | Frequency - Each material used
eddf6694-03fd-524f-b8ac-05a152d35b95 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6398ce0c-f496-504a-8b72-14ceabb11d8f | note | Conformance Criteria - Reject chip 10-20mm
03038752-fe37-5361-945b-1035fcc56b5b | note | Records - Supplier Documentation / Lab Test Report
| checkpoint | 7 - Bedding
7cb6fb8e-5f40-54a4-99a6-52725d9eefb1 | note | ACTION (Hold, Monitor, Witness) - W
d8a0b1a5-ee4d-5da8-8cd1-37097d7fee45 | note | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
791c1f4f-8d38-5894-8819-5fc368bfe388 | note | Frequency - Daily
dbdd8854-4faf-5dc2-8839-49c493292675 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
a17a73bb-233a-5322-9492-756a88f084cf | note | Conformance Criteria - 100 mm thick bedding for all mm dia pipe
b52f4a88-73e7-50b0-9689-4f36cf9a9e9e | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| checkpoint | 8 - Pipes and Precast Units
d59db7be-1758-56f2-b997-40be14b371f0 | note | ACTION (Hold, Monitor, Witness) - W
c07132bd-22de-5eda-8f66-bcf29f4bcef3 | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
20c57cd5-4855-5913-a869-75b183314a06 | note | Frequency - Each delivery to site
bbc3d58c-70d5-57af-bdb1-a0b19755a341 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
0a49ea97-22ce-58d7-a53e-d66f504c7c23 | note | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
250d41ae-1418-54c5-b6b9-32497f33bdc1 | note | Records - Delivery Dockets
| checkpoint | 9 - Pipe Laying
4400a3b5-2530-581c-ad21-fcf7c902ec1b | note | ACTION (Hold, Monitor, Witness) - W
cd6fb686-cc99-5fb8-827d-1617ad9524eb | note | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
f26d4beb-12a2-542c-b8e6-3d4e19451be5 | note | Frequency - Daily
e3b9dbc3-b95d-5af3-8261-ca846a3a01de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
ffe8f492-0d46-5eb0-9ddb-233c691a9cdd | note | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
71b56eec-c0a0-5559-9194-100322d0fb8e | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| checkpoint | 10 - Pipe Laying
e5512f07-b9cd-5861-95db-dad2c1eccc61 | note | ACTION (Hold, Monitor, Witness) - W
ca632798-0337-582b-b470-d65030707d54 | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
e0c8e9d5-b329-5bc4-90a9-040f3e1fe97f | note | Frequency - Prior to backfilling
29f3f393-e23f-5c70-bed9-c8fc4adc1f59 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
6cf098c6-bab0-5bb1-b483-70d11ee27a98 | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
413c0741-a844-5745-9444-facfa24029ca | note | Records - Photos
| checkpoint | 11 - Pipe Laying
a7c896ad-9fb1-5293-920d-6405126b08c3 | note | ACTION (Hold, Monitor, Witness) - W
634a6ba0-f705-50cf-af46-8e9caf759ede | note | Detail - As-built survey of pipes installed
c47378e5-576c-5cba-9c66-29962c122a99 | note | Frequency - Once line is completed between 2 structures
f498b9c0-4ea3-563e-a3a9-6d21fe06d3f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
831f86e7-0fdd-5d61-9a11-45e52b8f0448 | note | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
55ebd781-9730-5a30-90d8-5184e3578835 | note | Records - Survey Receipt
| checkpoint | 12 - CPS Engineer Pre backfill Inspection
d3ece75b-2896-57da-addc-7628fc683272 | note | ACTION (Hold, Monitor, Witness) - H
1051376c-235b-559d-87e7-46ab0573abf6 | note | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
87b72960-801c-58ff-88a7-c4f23bd0888c | note | Frequency - Daily
666bd3af-9c07-5c82-877c-7a67e37f22b6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c3841fcf-900e-527e-9523-a61d69f351e8 | note | Conformance Criteria - Compliance with the Specification
976c8ff9-6f8e-5f6f-906b-7ab1199efcb3 | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - CPS Engineer Pre backfill Inspection
ababf02f-356d-5ce5-93eb-d20fe73bbea5 | note | ACTION (Hold, Monitor, Witness) - W
f11fa872-8cf4-57dc-9f73-3779d10cda9a | note | Detail - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
e2af7a5f-043b-5452-998b-f4844ca8b6d9 | note | Frequency - Prior to backfilling
2b6cf55e-7865-56ed-8288-da7e736dd78b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
c27cf77f-a47e-5d63-ae84-c1d8dd504dff | note | Conformance Criteria - Vertical tolerance +/- 5mm
1179710e-2219-55bc-8a98-a86e22e13252 | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| checkpoint | 14 - CPS Engineer Pre backfill Inspection
3055770b-c1e7-5d69-bf2f-f45aa53564ce | note | ACTION (Hold, Monitor, Witness) - W
b553426e-720f-571f-a31f-a7bfe021bf86 | note | Detail - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
0657d488-3f57-5247-83af-f9b7ecbda2a2 | note | Frequency - Prior to backfilling
bdf1b684-546a-54ba-aaa0-97ba368f86fa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9997fe47-7d5b-5a11-8480-017926690b8f | note | Conformance Criteria - Vertical tolerance +/- 5mm
aa1bd214-7038-52b6-9f57-87681c1cd104 | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| checkpoint | 15 - Pipe Backfill Compliance
5105f763-5abb-5a61-9eb7-e773c6a633c1 | note | ACTION (Hold, Monitor, Witness) - H
53270cea-1e1b-5130-a706-645d28a841f6 | note | Detail - Material to meet specifications dependant on material type selected
615ea508-0fdd-53d4-86b3-3556c6c9fad5 | note | Frequency - Each material used
0e913085-842a-5bbf-bdf5-861cbbca3ff8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3e27ab7d-04f4-5ade-a42f-9df87fc0f781 | note | Conformance Criteria - Compliance with requirements from Specifications
f2f1d136-d3ce-5faf-a365-e37eb0beb0c3 | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - Pipe Backfill Compliance
35e794a9-d920-5c5c-b6fe-a1a9a2f1dc48 | note | ACTION (Hold, Monitor, Witness) - H
869af08e-f726-512c-bf71-bffb782b9592 | note | Detail - Backfill Construction Material
36f5ea41-6f6c-546d-a949-84cda196e452 | note | Frequency - 1 test per 50m, or per 500m3 of source.
5b2e7cd3-25cb-5574-9017-2ae41202656a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction Curve; Grading Curve (wet or dry sieve)
27b1afb9-13af-5e4d-8d51-832295f35c0c | note | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
5f445352-26c9-5ef8-92f1-502b1c9c63f1 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - Backfilling
99419b45-6d78-575e-af0c-30400c7d5cdc | note | ACTION (Hold, Monitor, Witness) - W
8903c538-bba7-54a6-9ff8-e39e278229b5 | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
83ea7ac1-aafa-5829-9cd0-269d7eba35c2 | note | Frequency - 1 test per 20 m length of trench per 300mm lift
af647640-f0d5-50aa-83df-e9a92e97c128 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
696ae9a6-4dcf-508b-b23f-3a0fb2ad54b7 | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
4908f73e-6574-59b5-83e4-1da2a88b0dda | note | Records - Lab test results
| checkpoint | 18 - Structure installation (Manhole, Catchpit, Wingwall)
1ce4607f-9a33-568f-aae0-dbfee8e6d853 | note | ACTION (Hold, Monitor, Witness) - H
9245ef83-c1a9-5d58-b440-9590eceef0b1 | note | Detail - Structures to be installed to the design survey location and level
291e3823-303f-5e2c-821a-fa76103f4c9e | note | Frequency - During structure construction
6b8ab263-0384-565c-95cb-26086ba3dc9c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
dd478f29-5e8e-5d07-acad-71ea3a9ff994 | note | Conformance Criteria - As Built Survey
368b8f66-d41f-5d83-b8c7-27720e11d439 | note | Records - ACE-CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt (or equivalent)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 19 - Structure installation (Manhole, Catchpit, Wingwall)
85ea0e5d-ad8b-5c91-8cb3-45032039a7d5 | note | ACTION (Hold, Monitor, Witness) - W
b9e22f53-c70a-58be-a2bd-9d7af8041226 | note | Detail - All joints are to be sealed including rungs and lids
d4444d61-bab4-5780-b239-48f5fc9afebf | note | Frequency - During structure construction
79220d6a-1058-5699-9f99-7e735d42ccf5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
8be09cdb-ca94-5fee-a655-32b89e7510dc | note | Conformance Criteria - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
b64b187c-8721-5850-b63e-75e4762a2bbc | note | Records - CS-4006 Manhole Catchpit Board Check Sheet (or equivalent)
| checkpoint | 20 - Structure installation (Manhole, Catchpit, Wingwall)
22639be1-f2f9-5ae5-8c09-b805737a0a3e | note | ACTION (Hold, Monitor, Witness) - W
8da4f9f6-1bd6-5db4-aa1a-9681f21ecf8d | note | Detail - Arrange as-built survey of the structure and all invert levels
18711f92-0e4e-5c75-8bdd-82881747464f | note | Frequency - Once installed
1e055832-3ebc-5f26-b9da-e2439e0a4d6b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
2415fd7d-a718-5aa5-9836-49f35e0a421d | note | Conformance Criteria - As Built Survey
346dce77-b1f6-548a-88d3-af649a2e1624 | note | Records - Survey Receipt
| checkpoint | 21 - Survey As Built
9cbf6ff6-1a4c-5b6d-99fb-1bd134f21770 | note | ACTION (Hold, Monitor, Witness) - H
b10fb010-36f8-5788-a774-e8421c24e3c5 | note | Detail - Ensure all drainage lines comply with design prior to carrying on with next construction process
5a069e0d-4663-5247-8016-7279e0c585f0 | note | Frequency - At completion of drainage line
fed9e068-0ce6-58f3-8feb-ae06dca97f9f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
eddbf916-3aa2-5408-8bce-b414a4f9c8dc | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 22 - Lot Number QA File
06812f70-c3f0-5a0c-a61d-2b7fb2920305 | note | ACTION (Hold, Monitor, Witness) - W
e8d76b5b-474a-5fed-b77e-466e1e9d9eef | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
66a65d87-4ebe-5e70-94a8-9ce06a4941c7 | note | Frequency - At completion of Lot
f60f1878-fb55-5a28-b92b-5193250cda9b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6cfd0fea-22ed-53af-8169-380f93bda0bd | note | Conformance Criteria - 65
2e01aa85-e483-5e1e-976f-8244dceb95be | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 23 - As-builts
05e3385a-7370-50e8-8d58-5bc13840778a | note | ACTION (Hold, Monitor, Witness) - H
ac31e0f7-d1c9-5ca0-bde2-a50796f737ab | note | Detail - Red pen mark up drawings to be included in QA file
7ea5b51d-2dee-547f-acff-89679381c5e7 | note | Frequency - At the completion of the Lot of work
2ae9beb8-e6ab-5194-bca9-be5c155e8829 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
3d7b6c9d-c6f7-5bb0-8fdd-5b4e94027cd2 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 24 - Quality Assurance deliverables
5ee83a3e-4b7e-5d5f-9f22-2f1a3db045bf | note | ACTION (Hold, Monitor, Witness) - W
ff1cf9e5-5dbc-5fbe-86fa-ba8eb24b5ca7 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
b37f0cce-f721-5b65-a798-23868c26c466 | note | Frequency - At completion of Lot
904d7869-e7c1-5716-984a-7c7bf2fb1fe5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0a1bf5f1-0e21-5c3f-bb43-e56f6f68cd0d | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
b2bd1fa1-089c-5230-8ca0-f2b238a3b345 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 25 - Completion Sign Off From Fields Below
4a344c3b-31c7-587b-9cd4-c910667a49fd | note | Records - Signatures
| checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Rock Armouring / Bulk Fill | itp | ITP - G1202A - Waikaretaheke Riverbend Recovery - Rock Armouring / Bulk Fill |  | f787917b-d7d8-4d41-8a02-33791c141049
| checkpoint | Project Site reps.
d2a0936c-1361-5cc7-ad04-61798a8a96c7 | textbox | CPS Eng.
77830ba1-13b9-5061-8157-75144483b612 | textbox | Site Engineer
80805fb3-9a2f-502c-8e6d-2eac03919090 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
f13839b3-625e-5e9e-a18e-0d1e787ba921 | note | ACTION (Hold, Monitor, Witness) - H
6563edd2-254b-5ace-8d82-742a8ff93901 | note | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
e49df920-ed1b-5427-a974-4fbc3c0a6bdb | note | Frequency - Prior to commencement
57258033-502c-515c-9262-4dda11e037e4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
cd37160f-f724-57cc-925c-c2982155707e | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
5bdada54-7f0d-5730-b3ed-76595fb6f8bd | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
9e0d1e36-f6e4-51a1-8996-c6f0b685adad | note | ACTION (Hold, Monitor, Witness) - H
ea62ae68-78f5-5469-8986-a6e9fba091ec | note | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, this will need to be approved by the Geotechnical Site Engineer
fbe62728-362a-57b4-944e-0195bd310d0d | note | Frequency - Prior to commencement
418e96ad-a179-5654-9b12-1f3614d57634 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
7d938b50-0411-5510-8acd-5868444014c4 | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
43687502-dd4b-5bcf-922d-24024877a374 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Remove all loose materials
0ac8bc5c-3bb3-530d-a828-8ab4702bd6b8 | note | ACTION (Hold, Monitor, Witness) - W
349bb2dd-5216-5868-8905-0e00a6047cd9 | note | Detail - Once all ESC controls have been installed
bbccbaae-1f5e-55ba-9101-08a99d428e90 | note | Frequency - Prior to commencement
041df88f-e44f-5cdc-81f7-b2d4b7dea796 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
| checkpoint | 4 - Excavate to Sub-Grade
4907b1b8-39f6-5d20-8f3d-4b55756fcfee | note | ACTION (Hold, Monitor, Witness) - H
0003bc22-27a1-5507-b0d9-083b68f96305 | note | Detail - Inspect fill foundation
acacd9da-9f2f-5854-887b-5631366653ef | note | Frequency - Per area as required
3ef168ba-d3ee-5cdc-800d-ec4a9ac0fa57 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
f93077ec-dbc2-58ff-8241-bfec7a1cede5 | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
002ab2d4-7521-58a0-a580-355ccfa762b5 | note | Records - CS-4100 Subgrade Approval Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Excavate to Sub-Grade
9cfbe2aa-b06d-51f8-9131-40cceadbf525 | note | ACTION (Hold, Monitor, Witness) - W
8cac154c-ff61-52fe-918e-5f67ff2c2abc | note | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
ee9a5d69-5c13-5f82-8621-fd41d23c3164 | note | Frequency - Per area as required
3a01d25b-f976-5d6e-b81d-f469c01076aa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Per area as required
a9fe85fd-b964-5d22-9510-a9fe70901a9e | note | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
4fe77421-d047-5029-82c1-aafbfb8c576b | note | Records - Engineer or Lab Test Report
| checkpoint | 6 - Material Compliance Testing
c21fb40e-ecb6-53f0-b389-a7017aed39b8 | note | ACTION (Hold, Monitor, Witness) - W
62a72fd9-7657-5be7-8408-32aa3c4237c2 | note | Detail - Material to meet specifications dependant on material type selected
678d0ddb-9196-551e-9794-f25cf0b4ddba | note | Frequency - Each material used
ce7fecc0-d49d-5fda-a0f8-b8097c7663d7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
15b2703c-ab64-5c01-a2b7-c9a09dbf572f | note | Conformance Criteria - a. GRADATION D85/D15 = 1.9
20505638-2b1a-5cec-86fa-77427620cd09 | note | b. D85 690 (MAX) AND 590 (MIN)
ecfa3bda-9988-5a26-a118-dee885a7c083 | note | c. D15 390 (MAX) AND 275 (MIN)
49a8a889-a430-56c1-a137-ee846c664388 | note | Records - Supplier Record or Lab Test Report
| checkpoint | 7 - Material Compliance Testing
a9622b56-bff2-5a50-8b34-1743cc6fccdd | note | ACTION (Hold, Monitor, Witness) - W
923f6d74-21f6-5046-91d2-9ae0de8d2c9c | note | Detail - Rock Construction Material
fda6b4c9-bd8e-5ef3-a8ec-71323d1db986 | note | Frequency - 1 test per 1 000m3
ae87f384-8f40-59f9-bc6a-895b698dea98 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
69be5886-54be-5f78-ba5c-e2c1f6bafa6d | note | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
19d5ab7e-680b-59ae-8df7-529e4c7b2ab5 | note | Records - Lab Test Report
| checkpoint | 8 - Material Compliance Testing
fc419a85-8478-53f9-93df-d8678a1bde34 | note | ACTION (Hold, Monitor, Witness) - H
edaf621f-31e5-511f-8087-7edfcaf7c686 | note | Detail - Bulk Construction Material
2e725d94-1437-5cf7-8add-bc57a1c30ba5 | note | Frequency - 1 test SET per 1 000m3
f71d0027-5e36-5427-a51b-d156b405dcbf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet or dry sieve)
6de63a39-cf7b-599a-bed5-0f9c27defc49 | note | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
ed5b2e22-bec3-56ad-b1fa-5f5b402f204d | note | Records - Lab Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Material Compliance Testing
0881e1c6-1d28-58b3-b442-0338f8ebe58a | note | ACTION (Hold, Monitor, Witness) - M
e922d9d0-4c0e-5e4f-9ca3-c622d66b6bea | note | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
0cf4fd6a-58fb-5d8f-8c92-59121538445e | note | Frequency - Prior to commencement of placement
6ecd2e71-c900-5435-a5f3-45879cf5659c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
94988dbe-701c-5458-b3b3-e7767cc21b9e | note | Conformance Criteria - Conformance with Specification
470fd9f2-e8d5-504a-bfc1-de6649bbe861 | note | Records - Delivery Dockets
| checkpoint | 10 - Material Compliance Testing
de4d336e-40ce-53ad-b717-695932e27279 | note | ACTION (Hold, Monitor, Witness) - M
dab923b5-f745-5b26-bea3-925d44a00c68 | note | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
222ac956-8ee7-5c65-9ca5-18562efccb05 | note | Frequency - Prior to commencement of placement
bc58f48a-2422-5f8a-8204-b2cc88a49096 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7f2f8376-12ef-5d0e-9d81-f7ae73524f9d | note | Conformance Criteria - Conformance with Specification
c0a6f8ac-7abe-5bd9-953c-4ff4c880269d | note | Records - Delivery Dockets
| checkpoint | 11 - Geotextile Placement - Backface
fa3f4201-49f0-5fb0-b8a8-2888f3097055 | note | ACTION (Hold, Monitor, Witness) - W
c41198a8-428f-5c57-ac1f-aed8460e4d4a | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
eabdb306-8ac1-52be-9ba2-7bdf87164fd1 | note | Frequency - Daily visual check
50120ae6-8d6f-546a-9514-b6674220ef1c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8d6a348e-aec1-5f0c-ae42-e380da403203 | note | Records - Photo's
| checkpoint | 12 - Perforated Drainage Coils
7d9e4b26-790c-53ac-aaaa-3028f0ac2c7d | note | ACTION (Hold, Monitor, Witness) - W
762fce90-6017-5238-affc-7adf053b3035 | note | Detail - TAP ANY SEEPAGE OR GROUNDWATER FLOW WITH MEGA FLOW/ PERFORATED DRAINAGE COIL. THE OUTLET SHOULD BE AT THE TOE OF THE BUTTRESS.
82a3ea47-e4e0-5771-b470-5fd59161ed6d | note | Frequency - Daily visual check
105bdfc0-2b4f-530b-ad86-6304dbb661ad | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d03f971e-c121-528a-a694-e8a4af4ca93c | note | Records - Photo's
| checkpoint | 13 - Backfilling of Engineered Fill Embankment
1d50bb1c-efc0-5361-aa4a-83654b5b4d81 | note | ACTION (Hold, Monitor, Witness) - W
0009544e-40ce-5099-9b73-27969eff00c2 | note | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
2de22a9d-a3e8-59c3-9810-77f8bca163ea | note | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
79265aa0-9cf4-5abe-9e0c-de4a464c81d5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
908b5d17-82a2-57bb-a8df-dbe61e625c21 | note | Conformance Criteria - 95% of MDD or clegg equivalent
cdc53b12-22bd-5184-94d1-dfdba12e841e | note | Records - Lab Test Reports
| checkpoint | 14 - Backfilling of Engineered Fill Embankment
324dab97-bb41-50f4-bbf7-ee5adc382372 | note | ACTION (Hold, Monitor, Witness) - W
796aba56-3208-58a5-bc73-e02932a566d4 | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
a38d704b-953c-54b4-80f9-ffd9d941356a | note | Frequency - At completion of bulk filling
00eada8f-e51f-5bc9-bb04-4ae3f087d064 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a19dad3b-7d9b-5418-ac5d-8ddd101eff9f | note | Records - Photo's
| checkpoint | 15 - Geotextile Placement - front face
42131609-b110-5761-b2d6-c05ae6f8a68f | note | ACTION (Hold, Monitor, Witness) - W
bc1587ea-02da-5a12-bcab-697aa10fa47f | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
ca8cafe2-f36b-5490-b44f-487179c4c1ae | note | Frequency - At completion of bulk filling
9e58f22a-a5aa-5eb0-80f6-9a4942ce62ae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
c6073179-d230-5351-b0d6-1140a1419c09 | note | Records - Photo's
| checkpoint | 16 - Riprap Placement
1131da71-5aba-5b56-a2f5-d993598af579 | note | ACTION (Hold, Monitor, Witness) - W
512670ec-ff67-5dd4-830f-31c303974560 | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
5b5714ba-dcd4-50ce-bcf1-b9c2d2e8eba0 | note | Frequency - Daily visual check
564d08d0-ada6-5239-b080-3b9a716d9913 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6f9caeb5-1603-596f-8a30-a6bafbc7b1df | note | Conformance Criteria - Specification
725e91a1-d8e8-5fac-9cbc-9c75a9576a9b | note | Records - Photo's
| checkpoint | 17 - Survey As Built
ed5b144e-399f-5cf5-8f58-6cc396f12501 | note | ACTION (Hold, Monitor, Witness) - H
110ae3a7-bdbe-53a9-8c8e-cf1f9f5a74bc | note | Detail - Ensure rock slopes comply with design prior to next process taking place
0519734a-f154-5022-b918-154c4cba8d67 | note | Frequency - At completion of Lot
2bf8ba30-9e1a-5558-9384-e4f2d50f8f7b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
f204cdec-6de2-5c93-8203-3e1e72f4df7c | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - Lot Number QA File
3d28326a-5afc-58cb-a3fd-c84df00daea3 | note | ACTION (Hold, Monitor, Witness) - W
f8f61be5-81fe-5360-8ac2-eb4ef53d7e67 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
304db41c-fc8f-5cbd-a25c-8615316eafac | note | Frequency - At completion of Lot
bd11cdb2-100e-5425-bb0c-fc54dc0214f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6b37e9f1-55e2-5481-bc51-4786f2537454 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
40827fed-a49b-5b98-9fba-7681f3577a20 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 19 - As-builts
50950d3b-5cbe-539c-bb17-743587837b93 | note | ACTION (Hold, Monitor, Witness) - H
58c57be2-04c5-52a0-9926-2ccbe9ab2fc0 | note | Detail - Red pen mark up drawings to be included in QA file
d7312da9-8104-57d8-a980-526b16bebabc | note | Frequency - At the completion of the Lot of work
057410e7-f682-5fe0-8ce2-74e8ce7041ce | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
f062531c-3621-5a3b-b567-24aed46757a8 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 20 - Quality Assurance deliverables
5f709ebc-7653-59fa-91ee-74e465ec8793 | note | ACTION (Hold, Monitor, Witness) - W
0b149e25-b2a7-5483-8412-a8d09a4557a3 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file.
1a22fef4-3007-505a-aee1-c04d73c7e37d | note | Frequency - At completion of Lot
b908f2b7-6269-5a13-995d-5ccf1703351f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
bd2bede7-a71c-5627-b1f4-9946019f08b9 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
683eb719-18bc-5778-80cc-678c9c133835 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 21 - Completion Sign Off From Fields Below
e6e3a030-a362-5765-9bbf-182a8a4d11ab | note | Records - Signatures
| checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage | itp | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage |  | c831da04-a99c-4a80-8b82-3903692b5503
| checkpoint | Project Site reps.
9e35585a-2bf6-55d9-8a8d-c7b0ece18bcd | textbox | CPS Eng.
e462aca7-6062-5a76-89e6-cf76e6ae7462 | textbox | Site Engineer
73f99775-8a79-5a39-92c9-073d3486030f | textbox | Quality Eng.
| checkpoint | 1 - Survey As Built
a0793920-b5c0-535f-9a93-f8fac3b6c128 | note | ACTION (Hold, Monitor, Witness) - H
c696e729-63a2-5bee-b91a-313e831530c9 | note | Detail - Ensure cut/fill slopes comply with design prior to swale drain or over land drain construction
d3eb4eb3-b1f9-5585-af7c-5a943e7e950d | note | Frequency - Prior to commencement
bf675016-1051-5b3c-879d-04a8768da13a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
89045eb3-a6f1-52af-a576-5e641659f41d | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Previous Lots
64dd18eb-fc67-5b3e-baf5-87ddabde5090 | note | ACTION (Hold, Monitor, Witness) - H
5daf409e-9580-56cd-bed6-b0d0d33f97c8 | note | Detail - Are all previous Earthworks & Topsoil Respread ITP's are completed and signed off
64bd46ce-e93a-5de9-89aa-e1c42fe9783f | note | Frequency - Prior to commencement
65ca1878-c20e-5ad1-b3b9-b538ad39e23f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
9335feaa-f76d-511f-8060-cf2eed8ccedb | note | Records - Earthworks & Topsoil Respread ITP's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Previous Lots
54bef59d-6251-5d28-b635-647dbdab1819 | note | ACTION (Hold, Monitor, Witness) - H
32692ff9-3f40-5a99-94f8-babcb24da6f7 | note | Detail - ANY OTHER SITE WORKS THAT WILL CAUSE REWORK TO SWALES HAS BEEN COMPLETED
2f9b3215-6021-57c4-9382-45a2d359b48f | note | Frequency - Prior to commencement
f9265c26-3e81-5412-bc0c-c3ffaa796592 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3a2c04b4-870a-5b9b-b6bd-031be53e4d7f | note | Records - Snag Lists for previous Lots
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Excavation of Swale Drain
7bae49be-50f3-5e04-9c5a-9dfd54762887 | note | ACTION (Hold, Monitor, Witness) - H
cfcea117-caee-5d53-9d08-15cc44d51c0c | note | Detail - Swale drains shall be excavated, shaped and constructed to the dimensions and the types on the For Construction Drawings/ existing swales
92801c93-5fa7-53f0-9f9f-c1a932e8e6b2 | note | Frequency - During Construction
f2cba139-d8bd-5184-ab98-4b7fdc6909af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
da4e8e17-2f78-5fff-a52f-ec121b5924ae | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Profiling of Swales
da3b95e3-9c5b-5bd5-b917-58bbc5afa29d | note | ACTION (Hold, Monitor, Witness) - W
cdbe21f1-a1ea-500b-8236-9a00e90da762 | note | Detail - Level check prior to topsoiling
0dd8cea9-180d-5fd6-a557-85fe7ed7dddf | note | Frequency - During Construction
e64fcd91-ec99-5d7f-98de-727c95ed5043 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
e669ddcb-834a-5033-8ca6-c79b3cb948be | note | Records - Photos, measurement sheet
| checkpoint | 6 - Profiling of Swales
53d2920f-f05d-5e14-bb39-37930f86a3dc | note | ACTION (Hold, Monitor, Witness) - W
e152f914-3104-5c14-9284-23cbc9b20385 | note | Detail - Level shape upon completion of topsoiling by As Built survey
fbee2dcb-9ce2-5972-b0e3-75793eb34072 | note | Frequency - During Construction
a28e7f3c-e7b3-59f3-bf82-6d48f872aa2f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
aad95d6b-9621-5a57-86c2-5920e20bba3e | note | Records - Survey receipt
| checkpoint | 7 - Lot Number QA File
46dc9919-3cf4-50eb-9351-1503fff08492 | note | ACTION (Hold, Monitor, Witness) - W
b5422c95-4082-51b7-9a3e-c1fca8e769e5 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
eb4af9df-93e5-52f8-9be1-f7e746db25d3 | note | Frequency - At completion of Lot
24b4f3c8-8db7-56f5-b7c8-5be18d463e34 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
b8620c47-fd82-5137-b7d2-5020f04a5eae | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
aebc79a6-c88b-5f84-ac23-578ba0c2ddde | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 8 - As-builts
18bea5c4-9dd4-56fe-a168-46928c1e9956 | note | ACTION (Hold, Monitor, Witness) - H
9d034dc6-6068-5d7a-91b0-35561f2a5770 | note | Detail - Red pen mark up drawings to be included in QA file
eb818c67-ec9a-5f17-a6ce-703b81f3e1c9 | note | Frequency - At the completion of the Lot of work
e42804f2-799a-52df-b2ea-b02711a834f7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
84fbe299-fa50-59ed-8920-bb367caeda0f | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Quality Assurance deliverables
a81ec121-503c-56e5-8757-a5b844538c2e | note | ACTION (Hold, Monitor, Witness) - W
6d7af1fb-8243-5d8a-92bd-2d23aa5b75e5 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
0f61cf24-33e0-5d8e-8c6b-91a1939758a3 | note | Frequency - At completion of Lot
82c336ea-7af1-5b90-a385-e5a0a63f0814 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
edf5adad-3463-5b96-b584-3d5851d1d845 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
76192795-528e-5e93-afca-6dc43e7ea2d8 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 10 - Completion Sign Off From Fields Below
9d1bdc22-7a6f-5f15-83b6-fa132042a4a3 | note | Records - Signatures
| checklist | ITP - G1202B - Waikare Riverbend SH38 - Network Drainage | itp | ITP - G1202B - Waikare Riverbend SH38 - Network Drainage |  | 278c81bb-4d4f-4adb-b710-ac401c0efb8c
| section | Details
| checkpoint | Project Site reps.
83c2b61b-686d-541e-a752-93d5dd1e620b | textbox | CPS Eng.
7ffc959e-cc33-5539-aa45-55a0a462c9fb | textbox | Site Engineer
98ece4f7-f3f5-547b-8410-80cd2bbc285c | textbox | Quality Eng.
| checkpoint | 1 - Locate existing services by hand digging/hydro excavation
e0bb53ac-6a34-56ec-99ed-7399258a248a | note | ACTION (Hold, Monitor, Witness) - W
dd593447-0195-5452-a2ec-264b31a5e049 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
dbc5a343-ec37-5256-908a-be4f9be831b7 | note | Frequency - Prior to commencement
ace2912c-3aaa-518a-bb61-3cb36b6ce7e9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
f5e7c0b0-d176-519b-b422-cbddb4cffeff | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
63dbcabe-26dc-5d39-8533-ec97087a30fb | note | Records - As-built Drawings Doc. Review
| checkpoint | 2 - Trenching and Excavation
bd2ea02d-b559-54fa-8295-d9334b6e459b | note | ACTION (Hold, Monitor, Witness) - W
1c032eeb-2753-5c27-a192-731761584cd8 | note | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
a4ef3a7d-177e-5538-9bee-8fab350513fb | note | Frequency - Daily
ab07cf42-9530-5bda-a983-7608ca30700a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
f60406fa-744e-5c6b-80e0-c01c6ca415b8 | note | Conformance Criteria - Line and level is correct
4ba7939d-e82f-52b0-a6f4-e08d3e7bc51b | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 3 - Trenching and Excavation
2e0e08e3-7139-5b14-b539-38dd38a702d0 | note | ACTION (Hold, Monitor, Witness) - W
3d130484-cc91-5bd0-832b-e745a0081ef2 | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
46aee52e-cb5c-593a-97ad-ac45dce59c16 | note | Frequency - Daily
d89ff2a8-5a24-5d48-b26a-02085f166d63 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
29ef5f9b-d714-58c3-90c2-6745c53150e1 | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
5454c43c-d6b7-5b30-a1b1-f3e2bf763fa0 | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 4 - Foundation Compliance
9b0d3f93-9a98-57eb-8ebc-7179b81600eb | note | ACTION (Hold, Monitor, Witness) - H
8aa101af-1bdf-5b27-873b-18b97e305864 | note | Detail - Test formation level on completion of excavation to check if undercut required
03c373d3-833c-5afd-adb5-0b80f7c80039 | note | Frequency - One test per 20 linear metres
55568fca-c706-5a09-a1be-92f3ae57b1f3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
f0093bf0-338f-58d2-9c1b-750765d2d192 | note | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
85641b5d-43ca-5e16-a472-1c4358060127 | note | Records - Scala Record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Pipe Bedding Material Compliance
b5c9cbb1-b412-5c5b-8dd7-f126db27c542 | note | ACTION (Hold, Monitor, Witness) - H
d406634b-a818-5440-8b44-038cbc001bbc | note | Detail - Material to meet specifications dependant on material type selected
3b17e624-c25d-577f-a29b-65859a5f75af | note | Frequency - Each material used
74b89660-7344-522e-9bd2-08229a6f6ae0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
42000391-6509-52f6-bedb-5758ee09c215 | note | Conformance Criteria - Bedding material
78c0d71e-a951-5119-8417-0e1be5daee5b | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Bedding
fb0f3ec3-64f5-5f65-8cf2-f8dcdd4312dd | note | ACTION (Hold, Monitor, Witness) - W
362f5dcc-096f-578c-ba1c-1b6960d7c09b | note | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
e253a934-ead3-5b45-966a-b98bf10f9ef7 | note | Frequency - Daily
fd06c4aa-57c0-5874-a73d-15617dc7bf06 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
18cccd35-4a64-5085-b088-a8f166ee0474 | note | Conformance Criteria - 150 mm thick bedding for all mm dia pipe
f8998b60-ee9b-5a5c-9874-3b5c6c0c6038 | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 8 - Pipes and Precast Units
6d1069f1-641a-595b-8588-84691e1fc735 | note | ACTION (Hold, Monitor, Witness) - W
f8f6eab2-c956-54de-b76f-3bf6ecc4aba4 | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
e290701c-91ea-5711-9062-240851a9cfcf | note | Frequency - Per pipe
61b39941-9cd6-5b97-a155-77a277067949 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
857d40cd-1b19-57a6-bea1-a547211a0755 | note | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
c3b5e74d-24e5-5cf6-ba74-bd069998387e | note | Records - Photos
| checkpoint | 9 - Pipe Laying
7428c96a-bbfb-59d4-87a1-634d6a4748b7 | note | ACTION (Hold, Monitor, Witness) - W
73eb6ab4-5fcb-5f45-820f-4167d478cfbe | note | Detail - Pipe Laying - as only replacing section on outlet of existing pipe, grade is to follow existing levels
4d3e8a39-a125-5e63-aaf7-ec86d018d64b | note | Frequency - Prior to backfilling
4a182d4a-00ba-5019-baca-e48f7fbcefa4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
eafd7411-3fe9-5d41-b44f-f9bc248fe434 | note | Conformance Criteria - Invert level following pre-existing grade
ff4c4e26-6b29-5cf6-a080-42f73844e3a8 | note | Records - Photos
| checkpoint | 10 - Pipe Laying
eaa43e51-b6e5-5125-a7b0-7e8fd01beedf | note | ACTION (Hold, Monitor, Witness) - H
e608d849-5817-5fe1-9431-191dfb10e55e | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
db9736d6-bb83-5bf2-b6ad-47627472d83a | note | Frequency - Prior to backfilling
6e663473-c7ee-5e8f-8a4a-fb0bf9fac07e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
38fa2111-6242-56b1-bb01-d05f4620049c | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
85d586f6-78de-5fa5-9427-27583499fd3f | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Pipe Backfill Compliance
d5d584bb-4f73-57bd-b0e6-af47d9788885 | note | ACTION (Hold, Monitor, Witness) - H
913a7156-9e27-56c5-9df3-0eb67d2c6fee | note | Detail - Material to meet specifications dependant on material type selected
9da8a5e2-7ebf-59e8-bbd0-6ed85fcadb5d | note | Frequency - Each material used
dddf959a-0afd-5494-83b6-90f13f129e19 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
64e60532-d655-53ba-ba07-8f1f5c31b363 | note | Conformance Criteria - Compliance with requirements from Specifications
218eb4f3-6771-5626-9bb1-3656edb0a244 | note | Records - CS-4025 Drainage Line Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Pipe Backfill Compliance
99e00f60-91e0-53eb-b593-e4eb082cb77b | note | ACTION (Hold, Monitor, Witness) - W
8923c915-cdd8-580e-a467-52496ce4502d | note | Detail - Backfill Construction Material
c8d4c0da-24a8-52b7-b1c9-e76334edcd51 | note | Frequency - 1 test per 50m
072c4a07-48cb-5045-a513-a7033583977b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
db607949-0da1-5694-ad01-895b6a72a036 | note | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
d0db4f11-d1bd-53be-9755-aaf742fc24ff | note | Records - Lab Test Report
| checkpoint | 13 - Backfilling
211f895f-b24b-5c38-aea9-ca4cdf742d26 | note | ACTION (Hold, Monitor, Witness) - W
61e19ca4-1f71-5a09-9e2f-85a6632411a7 | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
67525203-5067-5956-a8ba-b9885809c1ed | note | Frequency - 1 test per 20 m length of trench per 300mm lift
4ea1ee7b-832b-5821-ba96-27ac6e2aaa59 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
6c1eb88a-2aac-5002-bef3-6a9e51ae2af2 | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
b44d0670-426c-590b-b52e-66b6deecd613 | note | Records - Clegg or NDM Test Results
| checkpoint | 14 - Quality Assurance deliverables
ff2cdf8e-86f2-52d2-a652-fa105709e91d | note | ACTION (Hold, Monitor, Witness) - W
a7011c74-7f91-50a4-b65d-1a32839fab8f | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
3c50f37c-7597-5cd2-a1f9-cfcafce1e8fc | note | Frequency - At completion of Lot
b096f740-1bc0-5af6-b206-679b095181a7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d641badf-38d8-52b7-a634-4014de9bf5a3 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
845ac51f-3d03-5559-8985-c378d52058b1 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 15 - Completion Sign Off From Fields Below
bbb86b69-867e-5408-89a1-54027189c114 | note | Records - Signatures
| checklist | ITP - G1202B - Waikare Riverbend SH38 - Rock Armouring & Bulk Filling | itp | ITP - G1202B - Waikare Riverbend SH38 - Rock Armouring & Bulk Filling |  | 1452590a-4bf6-413a-8120-de21fbe63380
| section | Details
| checkpoint | Project Site reps.
0c44dbcb-a284-5af2-a9e6-64ea7dcdd31c | textbox | CPS Eng.
0682470e-7f3c-533e-8647-de0deeee9a2e | textbox | Site Engineer
4158f4ab-b17a-5f3e-a32a-ff41e5cf5eb1 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
6e1d6436-ed72-5db4-8768-0eca50ce97fb | note | ACTION (Hold, Monitor, Witness) - H
06958738-b638-5c82-82f0-a32af27b3156 | note | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
b0978575-c6be-5546-b740-9cf3b50b8361 | note | Frequency - Prior to commencement
73ba85cf-3a32-58e1-b2a8-0ea1609b0a58 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
f6cc68db-78c6-56dd-b033-f1f2ab523874 | note | Conformance Criteria - Fault ID 529B - Underslip Recovery Remediation Design Report
a1415ee3-cf00-5ed4-8b5d-841a03746ffb | note | Records - Survey receipt / sketch markup
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
0a259225-36ce-576c-adf5-36b9ea187156 | note | ACTION (Hold, Monitor, Witness) - H
d8e3f95a-0de1-57a6-9e99-f036ddcda0aa | note | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, at Geotechnical Site Engineer's discretion
6fc4fb2a-005e-5d67-9505-9f0bdbad0d8f | note | Frequency - Prior to commencement
18c9fb5d-dc52-5297-a336-12d61487ce15 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
4893bab3-08ed-5261-90de-2403c05a66ab | note | Conformance Criteria - Fault ID 529B - Underslip Recovery Remediation Design Report
52fe9713-359c-58b3-85da-2427cd678b70 | note | Records - Sketch
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Excavate to Sub-Grade
911fea95-d1a5-550e-ad09-b80a3188e8a9 | note | ACTION (Hold, Monitor, Witness) - H
a1291362-35b2-5c46-b20e-b5a9c85f4ac1 | note | Detail - Excavation only to start once ESC in place as per ESC ITP. Inspect fill foundation.
dcc5e9a5-b8de-5608-a4f2-f5eccd3776ed | note | Frequency - Per area as required
20ba246c-976e-5b32-8f5d-a23abb08fb49 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
e2bc1ac1-0201-5dec-b7a9-1cda797ae55e | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
2691f704-d838-525a-9285-c299493767b2 | note | Records - CS-4100 Subgrade Approval Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Excavate to Sub-Grade
9b4b959f-8904-52f9-a367-1834abbe2d5b | note | ACTION (Hold, Monitor, Witness) - W
e92a244c-a231-590a-85dd-20f31a526ce8 | note | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
5ff8630e-2816-50e8-931c-8bec24628337 | note | Frequency - Per area as required
9d870814-0589-53c9-accf-d73af17400a8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
071229a1-b748-5a0d-84ca-db9a225d4bcf | note | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
1fc24bda-7466-50a3-98e1-070a3d7c3933 | note | Records - Engineer or Lab Test Report
| checkpoint | 5 - Material Compliance Testing
4bebe36e-231d-5645-baa3-34bb678f8443 | note | ACTION (Hold, Monitor, Witness) - H
52995b27-310b-52a4-8c31-ad45f1db3751 | note | Detail - Material to meet specifications dependant on material type selected
5d58ca03-d56d-5759-bdc8-9a6005411bdb | note | Frequency - Each material used
4200d30c-bec0-5601-8456-b61d7c58a0a3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
75949cf9-7bee-593b-b6de-cf6fe6d1036a | note | Conformance Criteria - a. GRADATION D85/D15 = 1.9
07a4f063-7a70-50ae-8e16-551f685369d5 | note | b. D85 690 (MAX) AND 590 (MIN)
46043b8b-e102-5798-af28-9a312653fa9c | note | c. D15 390 (MAX) AND 275 (MIN)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance Testing
e9b9da3c-ad84-58b5-96e6-fb1a1b110387 | note | ACTION (Hold, Monitor, Witness) - W
a74ae0d6-5a57-5801-92fb-a57038258bc0 | note | Detail - Rock Construction Material
0a8947a9-a53c-56f4-ab4f-0976fff3cba7 | note | Frequency - 1 test per 1 000m3
873bc116-db2c-5079-9f44-dae34fd6ca4d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
c8d06fb9-7275-532e-8ed0-21a47998a4d7 | note | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
386a978e-7a13-5919-9e26-efa07575ca31 | note | Records - Lab Test Report
| checkpoint | 7 - Material Compliance Testing
ce2dff68-90fc-5993-b3e7-6f0cbcfad31a | note | ACTION (Hold, Monitor, Witness) - W
8886ed75-609a-5616-9cba-19398bdbfdc1 | note | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
9228d9a2-928d-5ab0-ac69-30a740311bb7 | note | Frequency - Prior to commencement of placement
12c4a93c-1ad2-58c4-ac56-40475efc7993 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a22fd8d3-a192-51d9-a975-6a0b3f6d8d5a | note | Conformance Criteria - Conformance with Specification
2aa9fd0b-40c2-50cb-87a8-bc511c7ab58a | note | Records - Delivery Dockets
| checkpoint | 8 - Material Compliance Testing
dc1bd04b-6404-5bfe-8402-43b3e8f00b00 | note | ACTION (Hold, Monitor, Witness) - W
e5d40a2c-cce4-5ec5-9431-a4e3f24f5894 | note | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
17c3a3dd-7949-57e8-af80-83ea476bf2b3 | note | Frequency - Prior to commencement of placement
9f66f6d7-bbe7-57ee-8813-a416bf9016e3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
baebd6c6-0914-5e92-ba0b-6121f3b83492 | note | Conformance Criteria - Conformance with Specification
e72d98f9-682a-5079-b137-601905aa38b3 | note | Records - Delivery Dockets
| checkpoint | 9 - Material Compliance Testing
ad224f25-5185-5b59-ac12-4178991431f1 | note | ACTION (Hold, Monitor, Witness) - H
ff3f3e55-422b-5e3e-a39c-2baa8cb0ccea | note | Detail - Bulk Construction Material
7abf819e-bc0b-5a7a-9a5c-2a13c6a2d442 | note | Frequency - 1 test SET per 1 000m3
c8efebfd-bc40-56ee-a6fc-dc6fabc43a39 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet sieve)
53ed14cc-dd53-541f-9666-fd05d96acd84 | note | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
58322e43-87d6-5dbf-abe4-1af280455107 | note | Records - Lab Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Geotextile Placement - Backface
4df6e343-a6a0-57c1-93d5-7862f79a4629 | note | ACTION (Hold, Monitor, Witness) - W
852c2c8e-0eb4-5e7a-bfe2-e12a481397a6 | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
a7e3fc36-855e-5c67-a4f8-f5aae10dd21f | note | Frequency - Daily visual check
284f8e57-3293-5593-80be-1612a7c14a25 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
11c6ce00-568b-57eb-a46c-72b2b9296911 | note | Records - Photo's
| checkpoint | 11 - Backfilling of Engineered Fill Embankment
5026a80e-09c7-523a-9a70-ca258fccb183 | note | ACTION (Hold, Monitor, Witness) - W
b4243553-ca56-5f18-8647-cedf50375f5d | note | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
3a58dab4-44a8-5a79-8c8a-36ee722c28d8 | note | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
be4b94e1-aa98-520e-b594-34868aacf8e6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
88c98214-4caa-5ef3-92c5-8b14132dfa6e | note | Conformance Criteria - 95% of MDD or clegg equivalent
799bca98-57ab-586b-958f-b8e716f44d15 | note | Records - Lab Test Reports
| checkpoint | 12 - Construction of Engineered Fill Embankment
26165f01-da70-528f-b2c6-5467ff12efdf | note | ACTION (Hold, Monitor, Witness) - H
ade8082d-2f68-5f9e-b9a0-00cf38d88896 | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
455085a8-75e9-5976-88fe-f17bdb965e4c | note | Frequency - Prior to commencement
05a86ff5-4047-5e3a-a11e-37f972e3d772 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
ff715518-49b4-59d6-b3e4-34994946df36 | note | Conformance Criteria - ALL BULK FILL MATERIAL SHOULD COMPRISE CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65 OR SIMILAR MATERIAL.
73e52732-dcad-5b4a-b4f0-5eb3596f6bc4 | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Geotextile Placement - Frontface
5364dabc-b5d1-5dff-806f-0e9dd9b33afa | note | ACTION (Hold, Monitor, Witness) - W
21cc58de-fdcd-5a3f-893e-a61f6e9c9e0d | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
70eec4fe-9487-5d39-bb73-cb6d29519131 | note | Frequency - Daily visual check
f1e262c8-1a4a-5457-a126-51f22ac57bb2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f4fd5606-6907-511f-88f5-85a9600151f2 | note | Records - Photo's
| checkpoint | 14 - Riprap Placement
9cb2cad6-27b6-5705-ae85-7857b7048d3f | note | ACTION (Hold, Monitor, Witness) - W
8b1e479a-71f2-547d-8180-610022b1e858 | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
f1c53bf2-0323-5436-87ac-72de46b77398 | note | Frequency - Daily visual check
3d479750-866b-50d8-8fa2-6db77ded6560 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
696bd550-2ca0-5180-a302-19a3f5569241 | note | Conformance Criteria - Specification
656e9eb1-08c1-53ea-b306-484d6ddc12d5 | note | Records - Photo's
| checkpoint | 15 - Quality Assurance deliverables
44d2f1fc-b80d-541e-98c3-6406c8b3a5f2 | note | ACTION (Hold, Monitor, Witness) - W
c33608c3-442d-5872-80d0-a72ab3d976fc | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
6e2fa082-51c1-57d7-871b-a55f8a830f5d | note | Frequency - At completion of Lot
271baa8f-83b9-5751-8098-c59b02c0b9fc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review. Red line mark up notes of design plan.
0b649d11-3747-513e-88e1-ce0f86b47354 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
f929f53f-be5a-599c-9b23-8ea7cea16efe | note | Records - As-builts, NCR's and RFI's
| checkpoint | 16 - Completion Sign Off From Fields Below
35617f7a-73d8-5894-84d7-bc087b533e3d | note | Records - Signatures
| checklist | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental | itp | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental |  | 12e678d8-bc59-49b5-bf5f-7447a11f0a2f
| checkpoint | Project Site reps.
3f12448c-2050-5fba-a4fe-1b9ec272c02a | textbox | CPS Eng.
0d16a946-a623-52e0-8f9b-c80e32b69c9e | textbox | Site Engineer
54ff240a-43db-5134-b582-382379c04a23 | textbox | Quality Eng.
| checkpoint | 1 - Approved Consents
3f759ae4-b6c9-5154-9d50-88438b77ca17 | note | ACTION (Hold, Monitor, Witness) - M
2decdb38-689a-50da-9315-246e6abdb9b5 | note | Detail - Is a copy of approved consent(s) available on site
0075176c-78b5-5dbd-8cc8-2f6b874f8c78 | note | Conformance Criteria - Check latest consents and SSESCP's are at each site office
a9794e5c-440f-522f-9257-71d212106843 | note | Records - This ITP
| checkpoint | 2 - Internal ESC Pre-Construction
15ad64e6-2445-5b5c-a26e-f62613539706 | note | ACTION (Hold, Monitor, Witness) - H
ee572a2e-0768-5222-b550-1d3ae07d9860 | note | Detail - Internal pre-construction meeting held with E Team
c7ee2cac-ab33-5b04-ae81-456b04684d6f | note | Conformance Criteria - Environmental Advisor to organise
5b36d0ee-e683-585b-99a5-c870d49decc2 | note | Records - This ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Type and Location of Erosion & Sedimentation Control
83995358-ce2f-5735-b481-a596e0f47988 | note | ACTION (Hold, Monitor, Witness) - M
985dee99-0d37-5c15-9b0f-665735e27fc8 | note | Detail - Confirm type and location of erosion and sedimentation control, based on relevant drawing/s
9a3b59aa-2d2f-5d20-9d9e-768064f9a414 | note | Conformance Criteria - Relevant ESCP drawing
bfe88daf-3b8e-5011-95eb-6fb64f1c0c98 | note | Records - This ITP
| checkpoint | 4 - Channel Bund (if required)
022652a8-98cb-5f81-80e8-91cb95ff1db2 | note | ACTION (Hold, Monitor, Witness) - M
5bbf3fbc-310e-5ab6-b63b-e82015ae892e | note | Detail - Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted.
0fb4cee9-4517-5001-bdae-bab3047227fb | note | Conformance Criteria - Work Instruction, Drawings and Checklist
| checkpoint | 5 - Silt Fence (SF) (if required)
935be997-6950-5129-b0df-67c70b4fbd15 | note | ACTION (Hold, Monitor, Witness) - M
506a696e-f0bb-5cb8-98e9-b91037d23853 | note | Detail - Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings
ab983ae3-60bd-52d0-b1fa-ff366b42f024 | note | Conformance Criteria - Work Instruction, Drawings and Checklist
| checkpoint | 6 - As-Builts
ba768826-2b18-5df3-8b37-c623c173de04 | note | ACTION (Hold, Monitor, Witness) - H
67b3185f-101a-54ac-b175-2e43ed4cdc7c | note | Detail - Confirm as-built details of completed works
b93ac9d4-2500-5a20-b45b-cfaed0c19d5a | note | Conformance Criteria - Submit to Document Control/Environmental Advisor to issue to HRC within 24 Hours
bea21850-4785-5f93-96fc-eb0d0a662d17 | note | Records - This ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Maintenance Inspections
834d4d6e-e486-5575-af98-56696d0ad070 | note | ACTION (Hold, Monitor, Witness) - W
dffe944f-63de-50ef-866c-90d3abc052c9 | note | Detail - Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance
d6e26a25-0949-5587-b120-336fb034b60e | note | Conformance Criteria - Approved ESC Plan. Complete weekly and upload to ConQA / Procore
| checkpoint | 8 - Decommissioning of Erosion Sediment Controls
c4864943-93d6-540a-8953-b85834f228cc | note | ACTION (Hold, Monitor, Witness) - H
cab643ed-94b7-5ae6-a3f5-b37b0fc88d0d | note | Detail - Decommissioning Plan submitted to HRC for Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Decommissioning of Erosion Sediment Controls
6ea3e572-fdba-59a5-857a-5bbf374bf244 | note | ACTION (Hold, Monitor, Witness) - H
afebc491-6127-586d-933c-7ebf4651a36e | note | Detail - HRC to issue an approval document so that Decommissioning works can commence
5a26a986-ab35-55e1-864d-a482f1900e2c | note | Conformance Criteria - Approval for Decommissioning
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Lot Number QA File
7178b4c0-3d59-5251-b739-3e0efa40a616 | note | ACTION (Hold, Monitor, Witness) - W
a9f7d783-0c59-55e4-bd95-10ab54980bb9 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
8cf53f56-dbb1-5546-81b9-0006477bc19b | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
5331eeb2-c5ba-504d-8858-73fd25f445fd | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checklist | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Network Drainage | itp | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Network Drainage |  | 55b5d343-05dd-44a2-94d9-bc79056fcc1c
| checkpoint | Project Site reps.
f545cc4f-208b-5ca1-b5c1-0f2a9892027e | textbox | CPS Eng.
d213dc9b-a30c-59a4-a578-59a396b477e5 | textbox | Site Engineer
d079e68c-7e45-5cc1-a881-df73e498c343 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
16575ef2-04bd-54a0-a818-089de7556a73 | note | ACTION (Hold, Monitor, Witness) - H
dd57d66f-c7e4-54f7-bf38-895874e85954 | note | Detail - Setout inlet & outlet points with inverts as required by Contractor to construct to design
6ab8dad9-5700-5bea-a657-e29da4edcc96 | note | Frequency - Prior to commencement
776c3cec-8b42-5939-91b6-16fbb519c250 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey (As agreed with Engineer)
6e30d5d3-6be1-5c03-b906-e73e09ffa1cb | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Locate existing services by hand digging
e132ff9c-0ddd-5298-b124-c3096cd53f36 | note | ACTION (Hold, Monitor, Witness) - H
7038c967-e212-5c3d-bd9f-44e268bbfc67 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/hudro excavation
1f040c64-d850-5c95-a4d6-a86cef7d2fc7 | note | Frequency - Prior to commencement
dd0201ed-5184-58c4-9674-7d92e88cc33c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
76bfdf77-50fc-5fd5-b168-56f9a46c78b2 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
948cdb2c-9273-5583-8431-d25d395a4a91 | note | Records - As-built Drawings Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Trenching and Excavation
3e8b8de4-4ef9-5f56-b762-e202896a8fc8 | note | ACTION (Hold, Monitor, Witness) - W
d8d323f4-1741-536b-b6f8-089785e6d482 | note | Detail - Inspect trench profile and ensure it is correct to lines and levels to design
bbd9ba36-eeda-57d4-927d-4dbb3a377ebc | note | Frequency - Daily
06d75a3a-213b-51de-b797-317146870553 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
292a4ab0-c38d-5d2b-8a05-a6a3938f9e17 | note | Conformance Criteria - Line and level is correct
| checkpoint | 4 -
b682dee9-166b-5197-8ccd-c9ca01f3023c | note | ACTION (Hold, Monitor, Witness) - W
b46d3709-6546-5155-bc92-2bb0d097f9bd | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
4d067bbb-8c5b-577c-aeed-f3b603c7824c | note | Frequency - Daily
db8f8579-44d5-5e7b-9700-a395dc9cc665 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
d05ffd38-9e88-579c-9f3c-b0d0b89c5ca2 | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
| checkpoint | 5 - Foundation Compliance
3b22f58e-6031-51ce-98ed-a5ff19920cbc | note | ACTION (Hold, Monitor, Witness) - H
ec884a26-f836-593a-b7dd-ec159062ffb8 | note | Detail - Test formation level on completion of excavation to check if undercut required
69e8aaf1-4775-548f-9675-0571cced996a | note | Frequency - As stated
f210f1e7-33d0-5c20-95e1-27751f0307eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection by Designer
d2ba1132-1de0-5702-8da1-92d7b689add7 | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
e9f7ed52-bc43-5119-ae79-23357961d649 | note | Records - CS-4025 Drainage Line Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Pipe Bedding Material Compliance
6749cb88-5222-5e9f-9365-956f2c1f7c1b | note | ACTION (Hold, Monitor, Witness) - H
2b99929e-c842-52b8-bee3-00f1461861e0 | note | Detail - Material to meet specifications dependant on material type selected
211d8ccd-3d11-500b-8ca7-64929e545c0c | note | Frequency - Each material used
ed87da44-eddb-5dd3-88ad-40d72f88b5d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
243a642d-0d76-5f40-935c-dff226d80b4b | note | Conformance Criteria - Compliance with requirements from Specifications
5dfc7e30-7960-5af4-9a19-5677c0b1733e | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
39731e4c-883e-51f4-9068-65ff655ec998 | note | ACTION (Hold, Monitor, Witness) - H
80018f50-928d-5d24-b374-e9d4cac89a81 | note | Detail - Backfill Construction Material
8586469e-6bed-5594-8f4d-9f3a105644a6 | note | Frequency - 1 test per 50m
0bcbd37a-da05-5ff3-af89-5ea7300e3ad1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
e4c93179-8a29-52af-a83a-c5ab664377d8 | note | Conformance Criteria - Solid wall pipe – Pea Metal < 7mm
89076ff8-da2f-5207-ac75-be4adfe3f441 | note | Records - CS-4025 Drainage Line Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
78cc7594-88df-5de4-bda9-dffcd88ce87a | note | ACTION (Hold, Monitor, Witness) - W
4e78b5d0-ce13-5d5e-b3d2-33a842704068 | note | Detail - Bedding - Ensure correct thickness of bedding is placed
0652095b-b427-51c7-aed8-d5232dc1ece9 | note | Frequency - Daily
866f2b7f-7a30-5c7c-9547-28eb7935f31d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
7b351f5f-616f-543e-afd7-2b0c66eeb1fa | note | Conformance Criteria - Type 3 support as per drawing
c79feeb5-92b8-5309-9534-c669c6d39cd2 | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 9 - Pipes and Precast Units
653b9662-6453-56a3-808e-f64495548ffd | note | ACTION (Hold, Monitor, Witness) - H
7fb7ebe3-0c65-50f8-af51-7b9d7b6d56f8 | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
c733131e-844d-5745-8738-8b29cd65038d | note | Frequency - Each delivery to site
23f4bf35-09a1-51c3-b867-a0e40db7571c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
f5c7662a-95c0-5860-b5c8-d2d7ef269e0d | note | Conformance Criteria - Comply with Section 3 AS/NZS2566.2
48104b3d-615b-555c-8893-542327ef90a3 | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Pipe Laying
f1bb784b-41d4-5492-8f7f-5f635cc3c16b | note | ACTION (Hold, Monitor, Witness) - W
ef80c2f2-8547-5396-b24b-dc65b1e7a06a | note | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
9400ffc4-d8d7-50c6-8019-d2d6020e7de3 | note | Frequency - Daily
216a6b00-2293-5343-bc28-3b0a366670c4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
0b8a25d0-c28d-51c3-b81e-744f2f0c9ecd | note | Conformance Criteria - Line and level to follow existing pipe
025c67b7-7ca1-58c4-b33a-e9381dcfd029 | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 11 -
53c46a92-a0ac-5c7e-a19f-174f0f1b685d | note | ACTION (Hold, Monitor, Witness) - W
4a69946b-eeb4-5598-ace1-d59b2847534d | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
b31e3dd5-29ec-5b36-8320-e35dd24f7c2b | note | Frequency - Prior to backfilling
152ae4e1-3659-5c06-8f94-b0c5cc5d1d97 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
a9f4368e-61a8-5775-8179-2fe77702b67b | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
913d68bb-9dc3-54e4-8e1e-19608f29569c | note | Records - Photos
| checkpoint | 12 -
40aa9ccd-e19f-519c-bd20-48a893a3e5ae | note | ACTION (Hold, Monitor, Witness) - W
473af6a9-1e1a-5756-bde8-871fd662f0df | note | Detail - As-built survey of pipes installed
2b72b4e5-79b1-5bb2-9a60-02b57c0093f3 | note | Frequency - Once line is completed between 2 structures
7033a7f4-a514-5568-959a-e797b9e039ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
8a39abe4-8b42-5940-81be-a5e801482500 | note | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
160a218a-87b7-5ba4-8593-24647437f3e0 | note | Records - Survey Receipt
| checkpoint | 13 - Design Engineer Pre backfill Inspection
26b7c0e9-0d90-5e1e-b024-96e2ba39869d | note | ACTION (Hold, Monitor, Witness) - W
a0d9b730-bd3a-5d41-891f-7d76f67b1c4d | note | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
859de29f-8940-5d54-8f29-a082dc11c932 | note | Frequency - Daily
60398078-9ae3-5c47-9c50-b856e32742c6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f2516b49-da8b-5611-967d-95353bf191b9 | note | Conformance Criteria - Compliance with the Specification
3f9f6dc3-1ed2-5788-af25-8d9a355ae033 | note | Records - CS-4025 Drainage Line Record Check Sheet
| checkpoint | 14 - Pipe Backfill Compliance
bc7f84da-b4d3-58c5-8767-9ae369953dfa | note | ACTION (Hold, Monitor, Witness) - H
a79eb23a-ca54-51b4-897f-b544e398d70f | note | Detail - Material to meet specifications dependant on material type selected
9152e1c9-59c4-5d4e-9ba3-3f6d1476baf1 | note | Frequency - Each material used
72ed1fad-4145-5f3b-a842-66d8a1bd3458 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
e263650e-5638-51f4-a7f6-f367fee9c31b | note | Conformance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
f49a5256-1690-5c04-89a8-108f2f0241b2 | note | Records - CS-4025 Drainage Line Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 -
bfc5326e-f57f-5d19-847b-92ff09c5595d | note | ACTION (Hold, Monitor, Witness) - H
235822f5-df57-5fae-934d-ab3719476045 | note | Detail - Backfill Construction Material
79255d63-09ef-56e0-86e3-87464bb9478a | note | Frequency - 1 test per 100m
2ec54c99-d88d-5cd9-ba21-e2ec3a3fdd40 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
56ca5a48-f53c-59de-a66d-7cca267f888a | note | Conformance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
029c04a4-35a7-5b18-be88-74bcf208fe7e | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - Backfilling
d19ac24c-b231-5f5c-b815-654a11d50484 | note | ACTION (Hold, Monitor, Witness) - W
ce0c1df5-9f6c-5503-b408-88c7d83295dc | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
18c0f984-e5d5-5418-9f43-1aae0dbf4ad2 | note | Frequency - 1 test per 20 m length of trench per 300mm lift
b4224ab9-bb4d-5664-9933-23ccd6d04e82 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
3dc9bfbd-cdc4-5373-93ff-c2c99ea963b6 | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
370f1dac-2028-5096-ba84-0b5e0e78c3d3 | note | Records - Lab test results
| checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall)
5bc7a3df-dcd0-51c0-a34e-255795c4810f | note | ACTION (Hold, Monitor, Witness) - W
26c60ec5-f9b9-5a9e-999b-87282fa14255 | note | Detail - Structures to be installed to the design survey location and level
e13a2d5d-0926-5591-bc5a-6e42d30ee8d3 | note | Frequency - During structure construction
a43ca19c-90ab-59d2-8f67-32678118181c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
d3f1fbaa-58da-5ad8-bfc4-d7a17c5eab12 | note | Conformance Criteria - As Built Survey
44f5b7f5-75ce-5bba-9522-d2df10350614 | note | Records - CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt
| checkpoint | 18 - Survey As Built
5e635146-034b-5aef-8de6-ee4b2faff1af | note | ACTION (Hold, Monitor, Witness) - W
e5581a26-d7a5-529b-953f-5766b333d131 | note | Detail - Arrange as-built survey of the structure and all invert levels
87b87545-6273-5df8-afcf-7a16f28e4c57 | note | Frequency - Once installed
1f9a9c04-cd8e-5855-b040-70247e94edba | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
6a34a104-9bd9-5510-acf6-c12de56e9c07 | note | Conformance Criteria - As Built Survey
dcbad85a-a77f-5956-a1aa-8e25fbd5b5b6 | note | Records - Survey Receipt
| checkpoint | 20 - Lot Number QA File
1e42318d-35d2-5e5e-bb21-42f2c7b4c822 | note | ACTION (Hold, Monitor, Witness) - W
46beed26-57bd-5594-aec3-505907c734c4 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
7cd8e859-a5a9-5289-b029-884fb787e707 | note | Frequency - At completion of Lot
1a5843f7-02ab-56c0-a84f-d4db60150701 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
82d3381b-6694-505b-afcf-b24ecb6a6d88 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
787443a7-7bcf-53f1-a6d2-6e920577d6ce | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 21 - As-builts
e5d2c777-d5c4-5550-a904-ca7ae6f11a1d | note | ACTION (Hold, Monitor, Witness) - H
18aa13e9-d7d4-5205-9044-f4fb3fe63b22 | note | Detail - Red pen mark up drawings to be included in QA file
ddd07923-2f18-5bbd-9cae-225668548751 | note | Frequency - At the completion of the Lot of work
f5787a4a-27b6-5a75-a052-ed2e8a579c7c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
14333cb1-6589-5728-a2b9-8fb729b8c2de | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Ground Improvements (Wick Drains) C1001A - Concrete Pile Underslip TEST | itp | ITP - Ground Improvements (Wick Drains) C1001A - Concrete Pile Underslip |  | ce42f9af-1533-459c-b379-d391fbc3cacd
| checkpoint | 1 - Design
9527ea5d-4ad6-5f6e-a2dd-3b4a7cf2375c | note | ACTION (Hold, Monitor, Witness) - H
c184153a-d9c2-56e6-a0bf-7376efa6c9eb | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
a4fc8357-baee-57c1-8e82-7871f4833ccf | note | Frequency - Prior to commencement
c4ac5ec4-8846-5c24-a802-aa512432c6e8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
43bd6591-6e7a-5a7a-8319-7fa884c44fa3 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Survey Setout
53017645-38cb-5d02-87f2-de98e7aa55d2 | note | ACTION (Hold, Monitor, Witness) - H
77950b3b-d513-5355-bc76-fa23313335c8 | note | Detail - Setout locations of wicks in accordance with design
bdc6b090-27a2-5312-9541-c3c0d6ab2950 | note | Frequency - Prior to commencement
2abec7fc-2b22-5b5b-9b2d-de4cba2cace2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
486ad5e6-5617-5f84-b738-8a47d0981753 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Material Compliance
c13ebf17-e464-50f7-bf36-eb0918d0c45d | note | ACTION (Hold, Monitor, Witness) - H
e433c9ea-6bca-5943-8628-a39c8636b569 | note | Detail - Prefabricated wick drains shall consist of a 100mm wide drainage core
be039405-b8d5-5885-8464-7d466fc15d56 | note | Frequency - Each roll
8770c848-4a06-52ee-881a-3ad68f9384ea | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection / Certification
16bbcb3d-3792-5c91-9832-de9b8527d27c | note | Conformance Criteria - Vertical Wick Drains Specification
06e8bd55-3fca-545d-b6d9-2349e4b18d06 | note | Records - Manufacturer Certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
ff58c52f-acc7-5df8-83bd-1745fefc5f36 | note | ACTION (Hold, Monitor, Witness) - H
861259e7-6291-53c6-9c6b-d5ef2461689a | note | Detail - Ensure all wick drains are free from defects, rips, hole and flaws
545e08f3-b785-59d3-904e-dd7fa02dc655 | note | Frequency - Each roll
5dc2a9f4-5f94-5ea4-976a-7928aa461325 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection / Checksheet
5140a341-34a2-576f-a8c1-ccbeca761193 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Wick Drain Installation
6e1d5e57-8a6b-5c91-aef5-6cb4fc3fdc68 | note | ACTION (Hold, Monitor, Witness) - W
657b00fd-a624-5f24-a4ce-c9875cda286d | note | Detail - Wick drains shall be installed vertically, within a tolerance of not more than 20mm per 1000m.
fa7c1ffe-aad3-5ee0-a69d-3b34fef78afe | note | Frequency - Daily
abf87b5e-9e99-5f2c-abf8-7350a2f38942 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection / measurement
dcf186ab-7eaf-5162-872a-4b4fd77c233c | note | Conformance Criteria - Contractor to check for plumb as per Vertical Wick Drains Specification
ff1952c8-79b2-53e8-9ebc-1875a5b818e8 | note | Records - Sub-Contractor Records
| checkpoint | 6 -
93cecb21-311c-5d90-8b41-6936813d178e | note | Detail - Depth achieved. Min of 500mm wick protruding from the ground
22e2844c-5208-5e03-b99e-3e7d687128c0 | note | Frequency - Each Wick
8521b32c-2cc0-541b-ad21-fa1ab302fd7f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f86b2630-5f6b-5fdb-b51f-89d4a0d9cc5d | note | Records - Sub-Contractor Records
| checkpoint | 7 -
5657c4a7-66dd-5f55-acd1-5b6033dcef71 | note | ACTION (Hold, Monitor, Witness) - W
6ce37909-80bc-50c6-8552-be2cbf3ec7d4 | note | Detail - Splices or connections shall be done in a professional manner that ensures continuity of the drain without diminishing the flow characteristics of the wick material
98218840-4da8-5b39-a8ac-9c84e859485a | note | Frequency - Each joint
a9c75682-c601-5826-b056-bd5ec25a744c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a2af3e6b-c3ca-5a40-a7db-aab2213efda1 | note | Conformance Criteria - Vertical Wick Drains Specification
87a31c7c-8d90-5055-a118-1506cf3abf10 | note | Records - Sub-Contractor Records
| checkpoint | 8 -
e9698526-64a2-547c-aa87-ac98a68d5efa | note | ACTION (Hold, Monitor, Witness) - H
ac50ad11-fc32-56d0-9c47-108f2fd2247f | note | Detail - Design Engineer Inspection prior to backfilling
c0b4e08d-9a14-5667-9e1d-356bf3e99966 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Survey Asbuilt
d83a3285-8265-51c4-8716-b7f099e5e725 | note | ACTION (Hold, Monitor, Witness) - H
18df1158-48ae-5f57-aebf-685a7bd69813 | note | Detail - Extents of wick drain area to be As Built surveyed
b3bc1be0-c5a2-5785-857a-4cdc541c8a35 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
46d9e973-3a6d-5d46-b184-0908910a141b | note | Records - Survey Receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Lot Number QA File
9b3ace38-9dfc-509b-886e-8c78f68f88f7 | note | ACTION (Hold, Monitor, Witness) - W
4d7882e5-6fe0-583c-83b7-b1967c5451bc | note | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
d60ed3e6-e026-5276-87b3-b80d27ca18da | note | Frequency - At completion of Lot
5b8d88c7-d87c-58a2-93bb-6195df0b17b0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6b426933-7e77-5ab7-9994-27a71b0175f8 | note | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
d432231e-d981-5f2b-b9d1-73228d8c8189 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 11 - As-builts
fec78173-e144-5492-93f9-60ea63be52f4 | note | ACTION (Hold, Monitor, Witness) - H
78a1236c-e08f-56a3-9fd9-a855ed89e830 | note | Detail - Red pen mark up drawings to be included in QA file
247646c9-dcb0-5aed-8e13-8abdab9d3b1a | note | Frequency - At the completion of the Lot of work
35f599ea-31e8-5ca6-81b5-09ca5a767653 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
324b69cd-4147-5497-9a92-9c86eb8ca8c9 | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - H1501A - Tupiko Stream Bridge - Reinforced Slope (Rock Bolts, Soil Nails) | itp | ITP - H1501A - Tupiko Stream Bridge - Reinforced Slope (Rock Bolts, Soil Nails) |  | 2973051b-ac2f-47a6-b7ed-f70f24c0cc9f
| section | Details
| checkpoint | Project Site reps.
61b6dafa-db5c-5c0a-8ea7-d3b4295dc8f4 | textbox | CPS Eng.
b72b271c-7529-531e-a0d3-0800fb14a89d | textbox | Site Engineer
0f5c32b8-effb-52ee-bff0-f84024d16ef8 | textbox | Quality Eng.
| checkpoint | 1 - Dimensions and Set-out
a64dbdcf-6680-5a09-a682-ad9827df9c80 | note | ACTION (Hold, Monitor, Witness) - H
24397a8f-573b-57a4-ab34-2d63a3c6794f | note | Detail - Once on site the Contractor shall confirm the condition and dimensions of the structure.
b6db4162-af0b-58e3-bf05-fc7705857383 | note | Frequency - Prior to commencement
252c203c-f3e9-53eb-a7b9-3fcc41e8379e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4c4542d8-2ec0-55e3-959e-5c251291ddb1 | note | Conformance Criteria - The CPS Engineer shall be informed immediately if any conflicts in dimensions are encountered.
1df77485-8393-5487-952f-7c5fbb7be8e2 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Erosion and Sediment Control
b80758fe-6da6-558e-8bba-650cc8b60800 | note | ACTION (Hold, Monitor, Witness) - W
3afd3f18-4941-5d72-8ee6-8216a9c1a472 | note | Detail - ESC measures shall be designed and maintained by the contractor during the period of the works
9f52852b-a7d2-562b-991e-e64fee30ae73 | note | Frequency - Prior to commencement
adfd8738-3cd7-5509-ba22-18e36c3e506c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
73c7d4bb-25d5-542b-a918-761cc249fb46 | note | Conformance Criteria - Ensure no surface runoff flows over temporary excavations
5f7b9486-3f63-53d4-a1b1-a7531041c35f | note | Records - Photos
| checkpoint | 3 - Clearing & Earthworks
781513fb-81af-5f38-a451-f291795ccfcf | note | ACTION (Hold, Monitor, Witness) - W
93397ef7-f133-5acc-a7c7-36dabb31d356 | note | Detail - Before setout of the reinforced slope method the bank along the full length of the abutment shall be trimmed/excavated to remove all loose material.
03c43d5d-7dc8-5412-9188-592d1d9af36e | note | Frequency - Prior to commencement
c156eb21-74eb-5f77-81ea-44a0c6e47afd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b7ed888a-b0a7-588a-ad81-856e77571f28 | note | Conformance Criteria - Keep excavation to a minimum
b4fcda9f-7b71-5b3b-b7dd-8a64efbf3fae | note | Records - Photos
| checkpoint | 4 - Clearing & Earthworks
60086fd0-f7cc-52e1-8a04-1b449c84bcda | note | ACTION (Hold, Monitor, Witness) - H
20261151-393d-54f6-8f27-4c44037841ae | note | Detail - Founding materials shall be inspected and verified by a geotechnical Engineer on site
444c8c31-8068-57ed-a592-5a4b912a75ea | note | Frequency - Prior to commencement
c3ae8484-911b-5311-a047-1c6dd9bcc39e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
89b1dbff-9407-5f56-b146-83264ec1d8ca | note | Conformance Criteria - Any soft or unsuitable soil shall be excavated and replaced with lean concrete (minimum compression strength of 10MPa at 28 days)
59353310-c245-5436-9f0b-3c7627bdfbae | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Clearing & Earthworks
66336d1d-7309-5c0b-8625-232dfdd42436 | note | ACTION (Hold, Monitor, Witness) - H
8ddc0d9d-4c8c-540c-a5a2-eafb23a61977 | note | Detail - Contractor shall submit their construction methodology for the trial anchors to the CPS Engineer at least 3 days prior to anchor installation.
7db13927-56e3-5e02-bb92-40c43e3dd425 | note | Frequency - Prior to commencement
073d7f92-6238-5e53-b752-b6ec24ea841d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
026e6bcc-ffc2-5b72-a895-e1ecf52e517c | note | Records - Methodology
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Reinforcement Compliance
def812c9-2f61-56f6-8de6-1f0a06def7ce | note | ACTION (Hold, Monitor, Witness) - W
8e01e86f-5592-54a6-9892-89a57c92f15a | note | Detail - All reinforcement shall meet design specifications
c7ae2ed0-3ee4-5afe-8377-5733a4032111 | note | Frequency - Prior to commencement
6c96fb6b-095a-5e6b-a573-a9e06dfa7fc3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
bdb0cc7a-d610-5ba7-a200-4a48782b1181 | note | Conformance Criteria - Grade 500E and shall comply with AS/NZS 4671
477cca65-1307-50ab-84cd-3729fb625c02 | note | Records - Delivery Docket
| checkpoint | 7 - Anchor Ties Compliance
21723f27-2463-53b0-9146-81fbaa605c20 | note | ACTION (Hold, Monitor, Witness) - W
10b52d56-9b24-5f1b-bc58-772a890c5c4a | note | Detail - All steel solid bar anchor ties are to meet design specifications. Alternative anchor systems will be considered provided they achieve the intent of these works
24f62f80-bfd2-530b-9180-e826abd4ca77 | note | Frequency - Prior to commencement
9835f9ef-97c6-55cb-9655-bfb0b3100149 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3f7efbc9-8d0c-5614-a693-88e8673903cd | note | Conformance Criteria - 20mm diameter grade 500E Reidbar or similar approved, and hot dip galvanised in accordance with AS/NZS 4680:2006. Damaged bars are to be rejected.
76fda56b-0cbc-5a4f-a37b-d6b055efe231 | note | Records - Delivery Docket
| checkpoint | 8 - Bearing Plate Compliance
e57edbda-f8da-549c-adb8-380dc28313f6 | note | ACTION (Hold, Monitor, Witness) - W
e566b97a-ff8d-5d67-87eb-68e889d0c7a4 | note | Detail - Bearing plate steel, coupling hex nuts and other accessories must meet design specifications.
8350c2ec-c629-58ce-b5ca-077fb5543104 | note | Frequency - Prior to commencement
7f23538f-b2e7-53c4-8ee2-b427c59ea823 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c018fe2d-650a-586a-83bd-a12fb18ecebe | note | Conformance Criteria - Bearing plate steel: Minimum yield strength of 250MPa, min 200x200x12mm. All galvanised to HDG600
85830fd5-8832-53c0-a7a6-b7aaec418531 | note | Records - Delivery Docket
| checkpoint | 9 - Concrete Compliance
2d254a89-8a37-5b44-bb8a-f56cd6359bb1 | note | ACTION (Hold, Monitor, Witness) - W
d16d4bad-ec40-51b4-8a2a-d09b520c55f7 | note | Detail - All concrete to meet design specifications
22f46fbb-9eb3-535b-b489-65e110bec52e | note | Frequency - Prior to commencement
65d6fe1c-54fc-5423-bd50-7d29a84dced7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6bbb2e11-35bc-5459-b71a-8136f2ad7c78 | note | Conformance Criteria - Workmanship in accordance with NZS 3109 and meets minimum 28-day compressive strength of 30 Mpa
f9efd58c-6d6a-5b08-948b-dc87536cb37e | note | Records - Delivery Docket
| checkpoint | 10 - Grout Testing
aad260fd-5347-5664-8930-d5061c558508 | note | ACTION (Hold, Monitor, Witness) - H
1092d73e-839b-53bf-8548-3d6bd6dedeea | note | Detail - Contractor should employ an IANZ accredited laboratory to perform one compressive strength test for every anchor at 1,7, and 28 days in accordance with NZS 3112.4. Test results shall be supplied to the CPS Engineer within 24 hours of testing.
3d83061d-dcd6-5eea-9293-8297791ac0a6 | note | Frequency - Prior to commencement
36fcd6a1-35c9-5a3e-b777-30bd62917222 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
84fc82e0-fa32-5093-971d-b56ed7ab2841 | note | Conformance Criteria - Anchor grout shall be Sika grout 212 or similar as approved by the Engineer and is required to achieve minimum characteristic strength of 20MPa at 7 days and 30MPa at 28 days.
d46e8de0-f026-5200-b7a1-5e30d2cdcaf5 | note | Records - Lab test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Anchor testing
d9764a9c-c914-5265-909b-c9535d8648f9 | note | ACTION (Hold, Monitor, Witness) - H
5445173b-0ba5-5f8c-b2b5-250b0364b747 | note | Detail - Three sacrificial soil nail tests are required by the Engineer. Location will be agreed on site with CPS Engineer. Testing may only commence once the grout has reached 30MPa as confirmed by grout cylinder testing.
982055cc-744d-5a92-9a70-aadfbac59060 | note | Frequency - Prior to commencement
b699b075-0102-5ab6-bba6-fbb9de4da660 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
0e4e0231-c80b-583a-b44f-3b8e63fb1a80 | note | Conformance Criteria - Grout test results to be provided to the CPS Engineer prior to nail testing.
df63da1c-000f-59e6-a077-b8b65b9a33a4 | note | ○ Test equipment certificates and calibration certificates submitted to CPS Engineer prior to testing.
61feef2d-7986-55ef-8160-ef25a4e28c41 | note | ○ Sacrificial test anchors and production anchors shall comply with Section 3.4 Table 1.
ba358700-35fb-500e-903f-ebe1e465c1c4 | note | ○ Test results shall be provided to the CPS Engineer for approval within 24 hours of testing
e9d7c9fe-b882-504d-a552-131a3226cf68 | note | Records - Lab test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Anchor testing
d17221e0-7832-5af5-8670-5fa237035f06 | note | ACTION (Hold, Monitor, Witness) - H
08db4a33-1dbf-5bcf-8607-cd0bb41d1520 | note | Detail - Three production anchors shall be proof tested in a location agreed with the CPS Engineer. All remaining production anchors shall be acceptance tested.
d71e2fc7-2fe0-5731-888c-0b3ba7a3d928 | note | Frequency - Prior to commencement
abb72d86-fe12-5aab-b18a-95b566a3df01 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
8dbb96ea-7fc3-5844-a50a-b11a0b215ae5 | note | Conformance Criteria - Testing done in accordance with Section 3.5, test results provided to the CPS Engineer for approval within 24 hours of testing. Rejection of anchors in accordance with Section 3.6
43c7fa96-2d07-5106-8cf6-e74b77aef884 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Anchor Installation
f3e0b869-00ea-5d24-a4ce-ac66282555c1 | note | ACTION (Hold, Monitor, Witness) - W
765c15f8-1299-5ad0-a2b0-0391269069f3 | note | Detail - Anchors shall be installed in accordance with the lines, lengths and levels shown in drawings.
05d819fa-d9b7-51ce-99aa-0a9d8cb522ec | note | Frequency - During Construction
322a9ce4-7939-5f8d-ab89-5f2af1a5072a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
011c112d-cc8b-5b65-bf68-f7c59dbf486e | note | Conformance Criteria - Bonded length of anchors is minimum 4m. Upper row installed at 10 degrees downward from horizontal. Lower row installed at 35 degrees downward from horizontal.
54c2ca9a-9285-5601-9d5a-2fde766915e7 | note | ○ Anchor drilling, hole cleaning, anchor installation and grouting shall be completed within 24 hours of commencement. No holes are to be left open overnight.
7e7e2c5e-13d7-5382-a070-b22cb51b01d8 | note | Records - Photos identifying anchors and installed locations
| checkpoint | 14 - Anchor Installation
d5a21151-eaef-5a89-9e96-c0f91c30e1c8 | note | ACTION (Hold, Monitor, Witness) - W
9e77940a-66b8-5480-be58-78f1f7939801 | note | Detail - The contractor shall keep a record for each individual ground anchor and submit these to the CPS Engineer
1748fd55-1f84-530a-8552-a1edbd9ec9bf | note | Frequency - During Construction
2eef8604-4446-5c05-8edf-be3cfac5fea8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
9437a323-8cc9-52d1-b0a6-3386ceadf677 | note | Conformance Criteria - Record must include:
cbce56a1-c8f4-5e42-ab58-60573b0c0943 | note | – Type of drill bit
0a8f3082-debe-5e2c-a97a-8a191582ebfc | note | – Drilling rate
f22a5e78-5468-527d-9901-113951aacd0f | note | – Grout pressure
ec21193f-b3e3-59ac-ac18-6b6a96a4866d | note | – Grout volumes
3216220f-b3a1-5666-8b98-5cb9e72ff2cd | note | – Ground conditions encountered
d9bcc73c-b231-5672-b112-289bbf21e43e | note | – Unforeseen conditions
c32394fa-edb7-5dc2-bdb3-d4d11ac34908 | note | – Prestressing steel manufacturer's mill test reports for the solid bars incorporated in the installation
7af8ade8-4b73-588f-b6a9-f2021e154caa | note | Records - Subcontractor QA Records
| checkpoint | 15 - Anchor Installation
8e66edce-b332-586b-ae0e-c0088810b9e3 | note | ACTION (Hold, Monitor, Witness) - W
69025681-99c7-511d-a422-5fa9fb97529d | note | Detail - Install grout
ef4b95d6-86a9-567e-ae8a-641124987cbb | note | Frequency - During Construction
4604783e-c81c-58f6-ae35-24b6655557e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
26307d67-8eef-5327-ad5d-63fb809c95e2 | note | Conformance Criteria - The entire length of the nail should be grouted without voids, intrusion of soil, or gaps in the grouted column. Grouted columns are not to be leaded for at least 72 hours after grouting.
c8ed386a-b270-5371-9069-7503ea26aeb2 | note | Records - Photos
| checkpoint | 16 - Anchor Installation
76535ba0-9a2d-5a7b-b684-7eb0aad001f5 | note | ACTION (Hold, Monitor, Witness) - W
c38e9ba5-3ba2-55da-95c2-d6466bf81405 | note | Detail - Install bearing plates and washers/nuts
51af8499-08c8-561b-8c98-c870d8f110fd | note | Frequency - During Construction
33d4d4aa-4b82-5539-ac22-a84824418647 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d4b78b7e-0ce4-5562-9334-a4bb7b0238a1 | note | Conformance Criteria - Bearing plates (anchor heads) are required to be buried within the mass of the skirt concrete block.
d6fc4907-3444-5530-8407-c866b551b8af | note | ○ Tie rod nuts are to be snug tightened only to remove any slack.
e771364b-0420-54ee-aaad-09561866b6cd | note | Records - Photos
| checkpoint | 17 - Reinforced Steel
8029afe6-7bb5-5379-b37e-b1f21690032c | note | ACTION (Hold, Monitor, Witness) - H
2d353360-460b-51bc-931e-e1001c366c50 | note | Detail - Reinforcement shall be installed in accordance with Section 3.8.
fc04ed8d-b1a7-5592-8d70-22fb83fb6d2b | note | Frequency - During Construction
53142556-6ee7-589d-b7fa-4b114c8fdbad | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0dfa4a6d-f87c-5959-90c6-c33576acbea8 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - Drainage Installation
969ee0b6-8f95-5196-b798-8d3d07630e4f | note | ACTION (Hold, Monitor, Witness) - H
031f7c03-f1dc-5347-8ca5-d98698128237 | note | Detail - Sub horizontal filter wrapped slotted pipes to be installed as shown on design plan. Outlet pipes shall be installed along the front face of the concrete block to form weepholes as per construction drawings.
33802c43-ab8b-512e-b32b-4cbc31fa7975 | note | Frequency - During Construction
19e36804-cabe-5fa5-a5ee-57275f3626b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
988c57d2-de53-5aee-8e42-10808c8b9b12 | note | Conformance Criteria - Drains shall be installed in 65mm diameter drilled holes at 10 degrees upward from horizontal.
38d276c0-6984-547c-b1dc-b5418df348b8 | note | Records - Photos, Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 19 - Drainage Installation
12b73158-5559-5296-af2b-bcb75e44e9b5 | note | ACTION (Hold, Monitor, Witness) - H
5c8b86a0-c635-545e-84fd-2e3648d5e22a | note | Detail - When completed the subdrains shall be inspected by a geotechnical Engineer on site
c83d2ad0-2637-51c6-8820-c04d1c9d14e6 | note | Frequency - During Construction
fa0bfac0-5a4b-5608-b61e-62d9a29cae10 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3c298e1f-3d87-561d-a3cc-dc574fe04e42 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 20 - Concrete
91093201-4725-525e-89da-638586f6ac32 | note | ACTION (Hold, Monitor, Witness) - W
e2b2bd76-d773-5322-b09c-bc8985c612d0 | note | Detail - Ensure any cavities and surface is clean prior to application of concrete
ac34b36f-3831-5e4a-b245-d68544b62182 | note | Frequency - During Construction
475411af-e3c9-5e7f-a783-001274123c46 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
1b1f12bc-3024-5ab9-8847-6e9688b91e9e | note | Records - Photos
| checkpoint | 21 - Concrete
e395dad1-9179-5a1b-8a5e-6a1c260df19e | note | ACTION (Hold, Monitor, Witness) - W
7abf1e6e-8557-5d16-a72c-ed62fd802f3a | note | Detail - Apply concrete in specified locations
16c9234e-bd1e-5eb9-b2e1-54195c585d41 | note | Frequency - During Construction
9681c65e-9693-5d11-84bb-4950d5c363b4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
9935e282-1e28-5609-b30a-01eb037e44ae | note | Records - Photos
| checkpoint | 22 - Concrete
117f151e-ce76-558c-80af-957cfc6e7036 | note | ACTION (Hold, Monitor, Witness) - W
d22bac8c-7ab4-5844-aeaf-1f227f26f79b | note | Detail - All concrete shall be properly cured for a period of seven days or until specified strength is obtained.
bcd20ef1-2aad-5eab-8287-fd584da7af86 | note | Frequency - After Construction
7bc62d26-8340-5790-a13d-2d6bb5853283 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
72227e85-5b5b-5aa8-9cfb-94b5179bc9c6 | note | Records -
| checkpoint | 23 - Concrete
30aea42c-e6cf-5cd1-ae75-b686f2e96317 | note | ACTION (Hold, Monitor, Witness) - H
b8222e74-ce8f-5727-9b28-fbaaf69104e9 | note | Detail - Once the concrete block has been completed, the CPS Engineer must be offered the opportunity to inspect the completed works.
e0bd43b8-cf7d-57ba-81aa-f9f16a7c4048 | note | Frequency - After Construction
ef18d935-25f4-50d8-97a9-c0dca9fa076c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b715c0a0-889e-595e-9888-4a3bd314c092 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 24 - Bank Reshaping
d6d8fc20-083c-57b7-b7a2-ad89493b7223 | note | ACTION (Hold, Monitor, Witness) - W
02c9bf96-36ba-5e90-8980-13ed9f4fd695 | note | Detail - After completion of the works, the existing banks shall be shaped to match with the new bank.
21cc8ba6-92c3-50ed-b450-b161fb5ea979 | note | Frequency - After Construction
8221f9c3-6d17-51ac-a0a9-51a3b235c094 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c35b7438-0803-593f-a029-d5dddbcc1924 | note | Records - Photos
| checkpoint | 25 - Topsoiling and Grassing
845b5b09-bab6-5bf3-8e4b-4ee2e76aa4e1 | note | ACTION (Hold, Monitor, Witness) - W
b918ec27-386f-535b-8b8c-a5b6d4c6905e | note | Detail - All areas disturbed by the works shall be topsoiled and grassed except as noted.
1217ea96-e75b-5cdc-9153-844c6e28aee8 | note | Frequency - After Construction
28718e2c-42a5-5a0c-b086-20912c2a3efc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
2fbcc6ae-21cf-59d0-bb98-67a6ad4c7de7 | note | Conformance Criteria - Topsoil shall be spread at a nominal thickness of 100mm, but no less than 50mm and no more than 120mm. Batters steeper than 2:1 are not to be topsoiled. Topsoil is to be tamped down to a firm state (minor indentation when stepped on).
5ffa5832-f1f2-5c7f-8ebc-18a0b4a5e371 | note | Records - Photos
| checkpoint | 26 - Topsoiling and Grassing
643ae454-de7e-5b7d-b5b1-097774fb299d | note | ACTION (Hold, Monitor, Witness) - W
da758f87-28ac-5ae2-b497-f9eb95c4be83 | note | Detail - Grassing of topsoiled areas shall be a to a mix agreed with the CPS Engineer on site.
9b69f6a0-a894-5f0d-9b16-7786a891111c | note | Frequency - After Construction
5aa98177-acfa-5130-984c-973671d669d3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8cf03860-2b53-5a78-bc4f-ba49f3b7b583 | note | Conformance Criteria - Contractor shall apply 50 grams per square metre of superphosphate.
d8f19c5d-a34b-5e96-b162-252e447ed555 | note | ○ No seed is to be sown until preparation work has been approved by the Engineer.
23e0cb66-5b13-5637-8f67-9dfb369ecf59 | note | ○ The grass seed mixture shall be sown at a rate of 25 grams per square metre bare seed weight.
5c3808ba-1b19-5011-8926-e8eae3260394 | note | Records - Photos
| checkpoint | 27 - Lot Number QA File
3dbd762e-5c0f-59e7-bd56-dbc7d6667f47 | note | ACTION (Hold, Monitor, Witness) - W
c617aeff-6251-55d3-a359-05af650558ea | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
98b71dd0-2224-5f5c-84b1-125e46b9532a | note | Frequency - At completion of Lot
0ed8cf18-4273-5772-b24c-26af964c68ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
66622252-00de-5792-ba1f-f06202c90919 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
ddc770b3-acb3-5bcc-9797-889194bb1289 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register, Subcontractor QA Records
| checkpoint | 28 - As-built
54150ace-afc5-55cd-8b64-c138a33c86a8 | note | ACTION (Hold, Monitor, Witness) - H
73abac7b-9573-57a7-ba23-1c3098f0d81a | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red line mark up drawings to be included in QA file
4dfa45a8-9d5a-51ea-ac08-be0e790ec028 | note | Frequency - During and at completion of work.
e244ef21-8883-5d56-932e-7e610e554080 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
da39950c-a64f-5769-9fcf-0531968f5649 | note | Records - Survey receipts, As-built plans
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 29 - Completion Sign Off From Fields Below
aa5a6249-48bb-51bb-b813-600710e36c97 | note | ACTION (Hold, Monitor, Witness) - H
41c7b7b1-dca7-5357-90db-fae6897481b9 | note | Detail - Below sign-offs to be Captured in CONQA / Procore
6289426d-40cd-5c81-8565-e3963b0da183 | note | Records - Signatures
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Mangahauini Bridge Scour - F3002H ID501 | itp | ITP - Mangahauini Bridge Scour - F3002H ID501 |  | 11e4bafe-5e72-4b7c-b205-8f6b9e52ca4e
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
bb8acee6-7ac1-5cbe-bec1-9cd5819e2760 | textbox | CPS Eng.
e57d3f40-0fb9-5508-926c-a46b4bbb0c56 | textbox | Site Engineer
f2c3d17f-5e91-5d26-a59e-b2642d34dacd | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour
df0ecc16-1a4e-5489-8617-f5bc9bf6749a | note | ACTION (Hold, Monitor, Witness) - H
958bb8ea-8489-5c58-8d2d-9683bd4b5d2f | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
845a8118-47c1-550c-8cb9-5d97e56e5dde | note | Frequency - Prior to commencement
f7b9b0ac-06ed-522d-8e3c-cd8aeb18662e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
bbc86290-706b-5e9e-b4bf-52deea0b0a3b | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall comply with Grading as per design (Rock Rip Rap Grading table) with a minimum specific Gravity SG of 2350kg/m3.
55b0e522-b0e3-502e-862b-d08fd324e13f | note | Records - Material source test results, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Class E A49 Geotextile
69d584cc-0010-58a7-a822-4e55b7f941f4 | note | ACTION (Hold, Monitor, Witness) - W
f889611e-51e4-5c73-a1a9-38cb17b7a8a5 | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC, NZTA F/7
b2c4518c-f761-564a-a27d-dae357d48216 | note | Frequency - Prior to commencement
fd07b547-6b4a-5122-b274-182182f2c90c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
ef3e173b-0e75-5fee-966a-8b2aa7881d3c | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
bfbe614d-33b6-5c2a-9658-bfdba1eda367 | note | Records - Material certificate(s)
| section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
| checkpoint | 2.1 - Survey Setout
3f321a83-74cc-5182-bbe5-0dcb538339c6 | note | ACTION (Hold, Monitor, Witness) - H
d01a25b2-ff2c-5f8a-8d17-2b1fd03fe5fd | note | Specification/Drawings Reference - Consistency with Construction Drawing
195ff7b7-21aa-540f-8c69-9c77cf58a8e1 | note | Frequency - Prior to commencement
f59f2cbf-0267-5231-8d41-26c2bf92880e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
dbb0aee7-8743-5253-9d32-628f803cc277 | note | Conformance Criteria - Set out extents of fill and check against design drawings
de63e509-c45c-55e5-bc67-d0b84689a0ea | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
1e362743-c9ed-52f6-a1ed-51f8280717f7 | note | ACTION (Hold, Monitor, Witness) - W
8354aea2-4248-5e47-a749-f03ac32af9e7 | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
2851fd24-debb-5d31-8b7d-5af1f50e39ee | note | Frequency - Prior to commencement
ae6b7edc-31f3-53de-9d66-0aa154d74e11 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
390582f8-6cc0-5f5c-a34a-3b697361bbcb | note | Conformance Criteria - Remove and clear the vegetation
6715ba3e-d538-5bd8-8df4-712b6c20b482 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Excavation
15d55333-6e6f-5dff-b371-f4a65f99f3ed | note | ACTION (Hold, Monitor, Witness) - H
86322827-01e5-552b-a41b-a7a0781ada7c | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
17474d21-482d-54e0-ad4d-46a5c4dcc236 | note | Frequency - During Construction
5666076b-9777-5f97-9692-45986452cd4f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
682b5d02-9cc3-5536-ae16-6c0cceac1b56 | note | Conformance Criteria - Engineer to assess foundation material suitability
50babbd9-3a35-5df7-9f74-888be5a58f9d | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Subgrade Inspection
be4095f7-2492-566a-aa25-95ac6ba304b3 | note | ACTION (Hold, Monitor, Witness) - H
95d1b80c-8bde-5670-9d2b-38f114d4d9be | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
eed39a4b-f080-58ae-b7b4-2951b8c0cfc7 | note | Frequency - Per area as required
046e667d-8264-5d34-8fba-e22ff62a5b42 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
48b93d56-9fdc-5757-8729-59ddce38560e | note | Conformance Criteria - Inspect fill foundation.
ed457cf2-adf9-5990-be28-a1e81af2c089 | note | ○ Fill foundation must be approved, in writing, before filling commences
43e0fc25-dcc7-5a03-a68f-d612b16a44f2 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Form and cut fill batter as per design
716ea1fa-ee54-56d4-8f8b-921a8a5c5e6f | note | ACTION (Hold, Monitor, Witness) - H
0f096b9f-e54e-55f5-9e08-75f4718bf416 | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
2af48bf4-5d0d-5d9a-9787-d1974f3fac02 | note | Frequency - During Construction
2e44ef5a-d677-50df-b886-d1a65d1bd1bb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
06720ad0-d9d0-55a5-b0fa-9b3e68789828 | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
abcf48d6-328a-55e7-a301-9e659eb9ea2a | note | Records - Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Class E (A49) Geotextile placement along the face of fill batter
6d091d36-435e-5e70-bc5a-b1335edc540d | note | ACTION (Hold, Monitor, Witness) - W
802b3c2b-c3a3-5ad9-8385-ca2d5bf0b8b8 | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
00149a28-7064-584a-8961-f54ce1b48c00 | note | Frequency - During Construction
167cfbb4-6d90-5dbe-b196-e479b33ac277 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3629a763-f8f1-5471-bf1f-d40aec4178b7 | note | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill
114919e6-eca6-550d-9da1-d814a1ac0166 | note | Records - Photo's
| checkpoint | 2.7 - Rock Armour placement along the face of fill embankment
58eac124-111d-5ef1-8a0d-8d2afc9df245 | note | ACTION (Hold, Monitor, Witness) - W
3e6a3927-047c-5813-9c7e-463c48ba6d36 | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
9cc27e46-6e1b-5f45-b91b-a58e3d0eaa9b | note | Frequency - During Construction
4fe301d0-b230-592e-8acc-a5e93dcbe047 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
06625d57-ab86-5589-afb2-6ec9d79be780 | note | Conformance Criteria - Install Rock riprap as per design; material to comply with requirements set out in Rock Rip Rap Grading Table located in design documentation
524677c9-f8ee-51da-b8f4-d2e704bc42a9 | note | Records - Photos, Survey as builts
| checkpoint | 2.8 - Rock Armour key into ground
48a5849b-b913-58b1-9e15-4a060802daf8 | note | ACTION (Hold, Monitor, Witness) - H
e98e16e5-08a0-53e1-b7e0-a54a81dc919c | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
60c0939a-5b5e-59f6-9bc8-66506c05ca60 | note | Frequency - During Construction
7c5f234c-173e-5ca6-bd92-5ba66f943544 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
cd59ccc3-0673-58f5-b8a4-e543d5811fcf | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer.
46794dc9-2500-5568-8c89-2f33eac145ba | note | Records - CPS COR report and survey as built
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.9 - As-built Survey
4870ef4e-ad10-54fb-bc3d-17c85fa9e645 | note | ACTION (Hold, Monitor, Witness) - H
145110d5-9885-5f01-9cb8-4f2a58c2fdf9 | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
7ac32906-907a-5043-9e3e-6a23e27b5f6e | note | Frequency - At completion of Lot
addfc81a-56d8-528d-94c3-483177f961dd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
ceac6596-2bb9-5720-a7cc-bb2006b484a5 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
18f331b5-01af-55c8-9095-43b96827574b | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 3: FINAL INSPECTION & HANDOVER
| checkpoint | 3.1 - Quality Assurance deliverables
28e21f65-037e-5026-9482-7128ff3aaebf | note | ACTION (Hold, Monitor, Witness) - W
10863d2d-8922-53cc-9517-0d7950a1eb88 | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
0a4e591b-64eb-513d-9313-d534fd285d46 | note | Frequency - At completion of Lot
6f062dd5-be9b-56bc-91a9-2f8391f57828 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1a87ee9c-530a-5dcc-8b89-80797d3d7561 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
1ee59ac8-b506-51ee-b553-d9734ba9fc60 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 3.2 - Completion Sign Off From Fields Below
f1f1d7a0-2e81-5bcb-b269-0e5527cb3adc | note | Records - Signatures
| checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut | itp | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut |  | e960010f-82d1-4b8e-b659-ffb1fcc3dbc4
| checkpoint | Project Site reps.
f7eb4be8-0141-5220-a9bd-b6dc1240d70b | textbox | CPS Eng.
5f1e35c7-a05b-5bca-96a2-36e336cfb902 | textbox | Site Engineer
106042a6-bd71-5857-b6ae-53d4ef2f908e | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
54e656aa-b6e4-57c5-b6a3-2280c6d19067 | note | ACTION (Hold, Monitor, Witness) - H
d490be53-6bac-509b-b04d-d04ade180eb1 | note | Detail - Set out extents of fill and check against design drawings
5caa6f5d-0259-5132-9946-a9a185488a78 | note | Frequency - Prior to commencement
76c748ae-8ffc-51d4-9f7b-a82d9b652aec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
3adb0d78-c4cd-5b94-8c8d-ceb02c730d91 | note | Conformance Criteria - Consistency with Construction Drawing
bd5693a5-6693-5ca5-8e58-ff4f4abf1638 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Excavation (1)
620b8bec-88d6-542d-8095-eef0c61d5bb4 | note | ACTION (Hold, Monitor, Witness) - W
38818efb-c17b-5d40-9b3b-562eb2f14c5e | note | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions
bd77c310-c4d3-55f6-b6af-67564ac5c05d | note | Frequency - During construction
1de98e51-1ded-52ef-b0fb-01d2f3e21e7a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3bcb9200-d7a7-5dc5-a82e-b31bd80b0936 | note | Conformance Criteria - Consistency with Construction Drawing
6d16b584-890d-581b-9695-bd378a76a709 | note | Records - Photo's
| checkpoint | 2 - Excavation (2)
77aa6537-6194-5382-99cd-fe58ad53e2f1 | note | ACTION (Hold, Monitor, Witness) - H
ddfaefb6-53ea-5615-adf9-cb9b68f08b35 | note | Detail - Existing ground/bank & foundation for rock toe to be excavated/trimmed to remove any deleterious and loose material
70255cc2-0852-5231-a3ae-d573ad36bb0d | note | Frequency - During construction
dd5a9a59-0039-5dfe-9e0d-677033320e89 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
89f34932-d1b8-54f3-96c0-64f9b7454d5d | note | Conformance Criteria - CPS Engineer to inspect and approve trimmed surface & founding level material before proceeding further.
848fbb3f-f9ef-5f45-8dda-66010f8d21c6 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Geotechnical Inspection
39618f64-ead8-5905-9511-11baaa6bf042 | note | ACTION (Hold, Monitor, Witness) - H
03fb03ba-bc1f-5ed0-bbbb-18ac46909d3c | note | Detail - Any areas of concern with the face at any time, ensure the Geotechnical Engineer is involved and any changes that are required are documented
cf1720b0-1282-5ddb-bb24-ba53fbe6a119 | note | Frequency - During construction
259b541e-f4a4-5edc-81bb-57e6911ac0fc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e973c19f-a5e6-551f-94e3-2415067b4961 | note | Conformance Criteria - NTC/NFD
6f59361b-3e11-5d1b-b9f2-1ee0b19882f8 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 -
e4261c2b-640d-5848-9af8-4b6ae5b2b03d | note | ACTION (Hold, Monitor, Witness) - H
ae0dc4e4-efdb-5691-b026-b1ca3c2ccc7c | note | Detail - Any changes to the design (soil nails, rock bolts, shotcrete etc.) are to documented individually
5ed9949b-8a42-58c3-ae8f-25a70881c4e0 | note | Frequency - During construction
79f97b6e-38bd-5a8b-aba4-5facd09d9228 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
426310f3-f03b-50ef-abf2-9df9547f8422 | note | Conformance Criteria - NTC/NFD
2cca6452-dd9d-5dcc-8230-241aa59aa246 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Formation
ddd8ef40-563e-5d1e-957c-948031c85b62 | note | ACTION (Hold, Monitor, Witness) - H
6d89dd5d-d29e-5c1a-9688-8723aed46b8e | note | Detail - Once cut is down to Formation level complete Scala check sheet
78a3350a-6e62-517c-b6d7-b3255d94b255 | note | Frequency - At completion of section
c2994f46-c4f2-5b7e-9bc0-779eafddfb91 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7c9c1aae-a3ef-5f9e-a7bf-e34a04f471ae | note | Conformance Criteria - As per design/drawings
dabba7bd-1843-583a-87d8-6450027dfe45 | note | Records - CS-4000 1M Scala check sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - As-built Survey
766b3879-e3c0-5646-88b6-22f900b40ad0 | note | ACTION (Hold, Monitor, Witness) - H
c60e1edb-b1a6-56ee-800f-3928023f881a | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
8b0ec46e-7ccf-5afc-95ec-f66fdac9243f | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
672060c6-444e-505a-ac45-cf14c4757a36 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
dd9b1392-6182-5906-ba0e-1e7387b97d59 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
b0c7b74d-0ec2-5e46-b5fe-e9de94b3e94a | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Quality Assurance deliverables
fe445447-aeb7-5059-b06f-08596ca7df9b | note | ACTION (Hold, Monitor, Witness) - W
d09e44e8-d5e1-5151-8c31-28c04ae21732 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
c754de72-6f21-5d5d-a3e8-e0f6143af8e8 | note | Frequency - At completion of Lot
c1d25cf8-ec42-591f-b621-87336127da6a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
efbde662-39a2-5542-b1d1-761213540c59 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
f4129db3-4a0b-5f31-b5db-3f93d2cc0e5e | note | Records - As-builts, NCR's and RFI's
| checkpoint | 10 - Completion Sign Off From Fields Below
84cb292b-57ff-5318-84f7-45a293187a2e | note | Records - Signatures
| checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill | itp | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill |  | 53a7e31a-58e7-41f4-be59-b3a5b3b43ae8
| checkpoint | Project Site reps.
9767d015-034e-50b4-95bf-5cd9dd0fa1d8 | textbox | CPS Eng.
1f58d06f-615a-5451-898c-6bea68c80135 | textbox | Site Engineer
e3481929-0aab-5860-8677-a15b94fbbe9b | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
28a70587-8e08-5e9f-b0b8-dc9d5b37bd29 | note | ACTION (Hold, Monitor, Witness) - H
a39f5a16-a7fb-50ce-b60e-bf85ef3c13a7 | note | Detail - Set out extents of fill and check against design drawings
29df25c8-d1ec-5b59-9244-72f865510e69 | note | Frequency - Prior to commencement
0a89cfd5-f4ee-50cb-8bc9-91f03d6696c5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
57bef4bc-a651-50d9-b0e3-8c53b19a9708 | note | Conformance Criteria - Consistency with Construction Drawing
bc9e18cc-bc68-504c-bef3-2c8ab3091f28 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Ground Improvements
1437883b-e844-5ac2-8a16-8a24bd6769da | note | ACTION (Hold, Monitor, Witness) - H
c3490e56-6b3a-5705-a67a-ddd83ca62686 | note | Detail - Ground Improvements / Dig Outs for soft areas
60c620e5-2078-5abf-a242-07faa5168ee7 | note | Frequency - Prior to commencement
613e8a49-1e8c-50a1-89f8-16978bb839d7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7ac2f59a-bb00-58da-85c3-7c79fbf3ce2b | note | Conformance Criteria - Must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
9e3cdbed-71e1-51ca-a6ea-d20c13504756 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Granular Fill (AP65)
e0ac56ba-b8db-5f7a-aabb-83cf3fcfa4c3 | note | ACTION (Hold, Monitor, Witness) - W
d08c775e-8850-572a-9c32-8e0177c4f280 | note | Detail - Granular fill material to fill any voids in the batter slope shall be crushed AP65 material
222259b9-68fd-5d34-9575-0892ba663d37 | note | Frequency - Prior to receiving rock rip rap
4e1983bb-ebac-5f20-bb0c-a17100f7b6dc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
92b25a71-2777-5ab5-bcf2-edf4cfe0ce28 | note | Conformance Criteria - AP65 shall be a hard, durable, well graded, free draining material with a maximum particle size of 100mm and 65mm respectively and not more than 5% by mass passing a 75- micron sieve. The fill material shall be free of organic fines and vegetative matter.
bf9dacaa-9ddd-585a-956a-a8812c5413f6 | note | Records - Delivery Dockets, Material certificate(s)
| checkpoint | 4 - Subgrade Testing
80dfb72e-8d5d-5aee-86e6-02b0c01ad38a | note | ACTION (Hold, Monitor, Witness) - W
1fba8111-3e5d-5384-abe4-65b73d2e5a33 | note | Detail - Subgrade Cut and Fill Construction
21428e23-073c-5d2c-b9af-7bf6dc377baa | note | Frequency - During construction
c6716d1d-38e3-5aeb-a345-256d34b38559 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
30e33850-7fb0-5563-9201-cb62fb9d9650 | note | Conformance Criteria - Ensure clearing and topsoil stripping does not extend past survey & clear the site with organic material / unsuitable soils
c3725273-d242-57bc-8a24-d17aca91da99 | note | Records - CS-4100 Subgrade Approval Check Sheet
| checkpoint | 5 - Filling Operation
fe26c607-d10c-5617-ae45-93005c4fff45 | note | ACTION (Hold, Monitor, Witness) - W
aa95c2c2-7d92-5089-b2e8-6b1dac8be65d | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
ee14ea73-f12e-5e56-a032-0455aef34f81 | note | Frequency - During construction
3fc58e8b-ce7c-5281-8598-ab8f540e5966 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
9500c0d3-002f-5bf8-9aab-dfb2bda774cd | note | Conformance Criteria - Any voids larger than 300mm to be filled with 100 to 300mm diameter chinker rock
f7f67166-d5cf-582d-a2e9-b8e7ebc7eb9f | note | Records - Photo's
| checkpoint | 6 -
ee1a031e-de18-5a86-870c-db1c5e23819c | note | ACTION (Hold, Monitor, Witness) - H
63f13e77-0a9f-511b-b2f6-fb77daea4cc8 | note | Detail - Granular Fill (AP65) used in voids for batter slopes shall be placed in layers not exceeding 200mm loose thickness and be compacted
b8f804a9-48b3-5e86-a6c6-1711bb0bbb16 | note | Frequency - During construction
a07752c5-757f-59da-8878-66f3b32195c9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8829495c-42cf-5f48-9d6c-69ea21a41588 | note | Conformance Criteria - The material shall be compacted by using hand-held mechanical tampers achieving 95% of the maximum dry density as determined by NZS 4402 1986 Test 4.1.1.
f1cceb38-5ba5-5021-91b5-37df359a2321 | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - As-built Survey
f02dcad3-567a-581e-ad71-9a34945e27bb | note | ACTION (Hold, Monitor, Witness) - H
e5ae8868-f9e7-56e3-b3b6-d2317d076c9b | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
41392891-d43e-5db6-8f75-56bcdbacc36b | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
3360f140-f1e3-5ac0-a92f-999e77051176 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
51369fe1-c189-5c63-97db-a2f867b835b2 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
516ffe34-4144-5c58-997a-8d02b00c9783 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Quality Assurance deliverables
03d287d2-28a1-520f-86a9-4694c8cb02fb | note | ACTION (Hold, Monitor, Witness) - W
36de4ec3-a6d5-5177-878f-d3adfa90d729 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
095faf89-c219-5a19-9e65-035cd187839e | note | Frequency - At completion of Lot
0bf97d4a-03ca-5b03-940d-7b7814c091d7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
12ab9b67-ddc3-566f-aa5c-7d8f8683b705 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
979151bf-acb2-57b9-9ca0-5ec3d398f80e | note | Records - As-builts, NCR's and RFI's
| checkpoint | 10 - Completion Sign Off From Fields Below
84c43040-bd86-5bbd-a6e1-d7340582c311 | note | Records - Signatures
| checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation | itp | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation |  | c14bda9b-0f1c-4b37-b664-054c087e0a17
| checkpoint | Project Site reps.
b361f670-2dba-51ff-aab5-f5cf9699b5c2 | textbox | CPS Eng.
b0b5cd6d-eb61-5be4-bc3e-07d859425b14 | textbox | Site Engineer
96a52802-96d6-5dab-bb8b-7500140a7c5e | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
6fcd7122-16c2-5a42-9217-3aeffd5089fd | note | ACTION (Hold, Monitor, Witness) - H
c4201754-69a8-5739-9728-f159d2aa8631 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
acc1f260-9890-5f36-9013-9d65348c31fc | note | Frequency - Prior to commencement
2f0d38a7-72c6-58ee-a73c-16e5b9ab714e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
3438655d-7ea4-5aa7-b9cc-8d33ad73a432 | note | Conformance Criteria - Consistency with Construction Drawing
acc1d686-ec4b-5188-a20e-fecaaf22abc0 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Precast Installation
710f06c9-044a-541b-8f53-fd97e082087e | note | ACTION (Hold, Monitor, Witness) - W
d142d536-a34a-5a89-900a-c6cec0caf839 | note | Detail - Delivery Dockets are collected and signed before precast materials are removed from the truck
e7e58567-c46b-59b7-b12e-ebedaf82ae01 | note | Frequency - Prior to commencement
512d5a3b-9945-5c3d-a430-90b982bacd3d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
f71bc4f5-aa8d-5e3f-b911-f28e08998869 | note | Records - Delivery Dockets
| checkpoint | 3 -
cfe9cb73-635e-5102-ae4b-677302351e20 | note | ACTION (Hold, Monitor, Witness) - W
0aa0bfbf-d943-5ac2-9d10-e9401b306736 | note | Detail - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
0cac6042-734c-5be0-a6c3-9b83b65d830b | note | Frequency - Prior to unloading
497c3cab-27c0-5303-b12f-a69cc5ef5499 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a2e2dd6b-8c5a-55a2-b662-04363a8def84 | note | Records - Photo's
| checkpoint | 4 -
51f59ae6-5f93-5151-8502-0ae8e8c2a8ed | note | ACTION (Hold, Monitor, Witness) - H
6f7c6874-6c4e-5041-825a-90047c6da07c | note | Detail - All Steel brackets, bolts/nuts & steel wire ropes must be inspected on delivery. Any damaged items shall be isolated, repaired or replaced
867ce4bd-065a-51af-8cd9-fef44a3d6e5f | note | Frequency - Prior to commencement
27cabd83-5c5d-57b6-9792-ce988b4b9867 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Document review
e76414d0-2ed7-5b1a-b48b-6d4073b4b1a4 | note | Conformance Criteria - Comply with AS/NZS 5131. Brackets will be manufactured from 16mm thick 300 grade steel plate. Steel wire ropes shall be 20mm in diametre. Any welding required to be approved in writing by CPS Engineer
825ebf85-e701-5839-8b14-9479a2c86eba | note | Records - Photo's, CPS COR Report, Manufacturer Test Certificates, Welding tickets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 -
ca1eb944-aad6-52c7-9df1-58bf7e8fb0ab | note | ACTION (Hold, Monitor, Witness) - W
1e89c40b-fb9e-5871-bcd3-9c40028ac5d9 | note | Detail - Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the pre-start/OFI
c8bcdc95-7263-5f15-b0bd-0c47643b0285 | note | Frequency - Prior to commencement
28c4a49b-5185-585e-8fa0-515c44d41e94 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review, Visual inspection
eefb803e-3080-5eeb-8da3-924bc2e45a57 | note | Records - OFI, Photo's
| checkpoint | 6 -
528e4ea3-a1e1-5a12-8bdb-445fe765c2ac | note | ACTION (Hold, Monitor, Witness) - H
93279b0d-fb8f-5dbb-9375-968c76d32f87 | note | Detail - Precast Components are to be installed in accordance with the design/drawing. Each unit is to be butted tightly against the adjacent unit to present a coherent mass
aaafdde0-7b37-5f5e-b5a7-b19cdff292b1 | note | Frequency - Prior to commencement
2fca2821-352d-5cf6-bcb4-e94089df17a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
eae7edc8-94d5-54be-a420-ef80fee5dd9f | note | Conformance Criteria - The position of the dolos groynes will be set out and agreed to with the CPS Engineer
e754b700-f686-53b4-aae6-589facf50ef9 | note | Records - Photo's, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 -
2a42c47e-4dc6-5775-96be-76729bca4cf7 | note | ACTION (Hold, Monitor, Witness) - H
c952c7fe-eef6-523e-8614-bfd133f28c84 | note | Detail - Dolosse’s will be secured in position using 20mm diameter steel wire ropes passed through the lifting eyes of the Dolosse’s and secured to brackets welded onto the existing sheet pile wall.
530afb9a-c65c-5cf2-a630-7b674416fed6 | note | Frequency - Prior to commencement
8d807c06-2580-544e-855f-5287502c9ca1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
78bbd848-3279-53a0-9bde-8bd250c4201b | note | Conformance Criteria - As per design/drawings. Welding to be inspected and be approved in writing by CPS Engineer
a909d8de-9bd1-59e7-b7e1-b77aa26abc64 | note | Records - Photo's, CPS COR Report, Welding tickets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - As-built Survey
4aaff410-aaff-53fe-8a03-3bbaa1045954 | note | ACTION (Hold, Monitor, Witness) - H
2b073b31-5fba-504a-9198-288199bb8a77 | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
cab7c53a-0278-5ac6-97ec-73bf56fc38ed | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
73b0908c-2361-5cf1-8248-69ac2fd3d608 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
0f5b2c0a-709c-5908-bb25-29283e177875 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
76feba2c-877a-5a5e-bf9e-d17e9d53db51 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Quality Assurance deliverables
8ea93cba-65d5-5478-8fa7-c6d0af5f7c5d | note | ACTION (Hold, Monitor, Witness) - W
9b72ccbf-e087-52de-83fe-29b7b47d29b1 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
799e8dba-7f79-55bb-aa83-e6039effc78e | note | Frequency - At completion of Lot
bb12e4da-08d8-54b9-a823-a2ef485f0c66 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
f019f10c-1706-53f2-8b95-f1727901e8c2 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
6486f58f-ebcd-5bd3-bfca-c7d09713eb5b | note | Records - As-builts, NCR's and RFI's
| checkpoint | 10 - Completion Sign Off From Fields Below
3db71024-9154-54d5-9335-73285f4ffab8 | note | Records - Signatures
| checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring | itp | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring |  | 8df91791-bce1-4754-87d3-02e9ead54bc7
| checkpoint | Project Site reps.
4bef4597-7959-591f-8908-acef648caf0a | textbox | CPS Eng.
b4c5798e-1d4e-5313-be62-365318144750 | textbox | Site Engineer
6b073cb6-7cf8-5333-9f35-237e567de475 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
453387c9-be0d-5f93-8652-0103d677f030 | note | ACTION (Hold, Monitor, Witness) - H
1912eac5-97b3-578d-913c-7ed88814bb6b | note | Detail - Set out extents and check against design drawings
cdfb859c-4c04-5300-ad90-ad799e6252d8 | note | Frequency - Prior to commencement
0668ccf3-6712-5ff7-8b7b-1f0bef549313 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
7b9145e4-59b8-5cfc-a46d-fa9381aba409 | note | Conformance Criteria - Consistency with Construction Drawing
aace3aad-a4da-51bb-83f5-02e65a7eddbb | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Geotextile material
2c925392-a7e2-5f82-99b7-1d3ceb0d855c | note | ACTION (Hold, Monitor, Witness) - W
c85a242b-d81d-5c5b-8c65-048517d60a7c | note | Detail - Geotextile filter fabric to be compliant with Bidim A49 or similar approved
1ec1d88f-e134-597d-bb67-253be488cfa7 | note | Frequency - Prior to commencement of placement
de453872-89c9-507a-8a84-f469968af6c4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
71f56043-c40a-57c7-876e-843c190ac8c4 | note | Conformance Criteria - The material shall be non-woven geotextile and comply with TNZ F/7: 2003 meeting filtration class 1, strength class E requirements.
80eda5e2-bfa9-551f-bbef-1235115167c5 | note | Records - Material certificate(s), Photo's
| checkpoint | 3 - Rip Rap Grading
47ab396f-99bf-5c6f-9610-774c13e693d7 | note | ACTION (Hold, Monitor, Witness) - H
203dc1e5-b8d9-5e6b-b72c-4a3cc36d440b | note | Detail - Rock Armouring Construction Material compliant with Rock Rip Rap Grading tableas per Typical Sections Views sheet S03 Rev 1
7ecfae93-1a27-5cc4-864a-983d287fe000 | note | Frequency - 1 test per 75m3
48644135-abd0-5a37-894c-91960a8f37b8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing, Visual inspection
325ddbbe-c3ae-5491-9dbc-202c04471551 | note | Conformance Criteria - 100% smaller than 2400Kg, 20% greater than 1000Kgs,50% greater than 600kgs 80% greater than 175Kgs. Stone shape shall be as close as possible to cubical. Long, thin, slabby shapes are unacceptable.
843c1e74-a3ab-5568-a54f-b21fb9cc1a45 | note | Records - Lab Test Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Geotextile Filter fabric installation (1)
68d4745b-0e75-5608-b622-df12be94a0a4 | note | ACTION (Hold, Monitor, Witness) - W
40a06619-9311-50a6-a8bd-4e652ccec76c | note | Detail - Filter fabric shall be placed under rock and against the end faces of the excavation as per design/drawings
8b500198-fe37-5b32-8d46-bf7bfe2bcba3 | note | Frequency - Prior to placing rock fill
bbf91ec3-a66d-5f44-b274-6626fbebb8a7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d971a8a0-84c1-532b-9e5b-4ee3a55fa1ed | note | Conformance Criteria - Placement of fabric shall be as per design shown on Typical Sections Views sheet S03 Rev 1 and be laid/overlapped as per manufacturers recommendations
903f6017-d532-5203-9e3a-8e509aeb74b5 | note | Records - Photo's
| checkpoint | 4 - Geotextile Filter fabric installation (2)
6482a52b-f06e-5a78-9395-3219e7e50ef5 | note | ACTION (Hold, Monitor, Witness) - M
0b42fe91-7f74-5d1b-b65d-72252c42075a | note | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area
4a4a9f05-b98c-51e9-bd12-127ea70da7af | note | Frequency - Pre/ During install
b0f34020-e966-5dbe-84b7-f36fb8bbacfd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6d625eb9-dc2c-5eba-903b-467e88facb95 | note | Conformance Criteria - tears shall be repaired by contractor
b8de44ce-f607-5d4a-9c8c-b39a1c2783ed | note | Records - Photos
| checkpoint | 5 - Armour/Riprap Placement
47788299-6c60-58c3-890e-213c48844cac | note | ACTION (Hold, Monitor, Witness) - H
bfa23fae-95c9-5e69-a11a-49ebf31051a2 | note | Detail - Ensure that rock material is placed in such a manner to minimise segregation. Rock is not to be end dumped or allowed to fall from an appreciable height. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
340efce0-892c-5035-a2fa-d612c6989c8a | note | Frequency - Daily visual check
e90bff94-06cd-530d-8a52-a7f551449df2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
adc8b13b-8380-5047-b811-9d9ed2cae573 | note | Conformance Criteria - As per design/drawings. Rock toe construction to be sighted and approved by CPS Engineer
9f40ce74-5d2f-5791-98af-1c323bd499ca | note | Records - Photo's, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - As-built Survey
72a1ac89-f12d-56e9-8f1f-895cd507a1f3 | note | ACTION (Hold, Monitor, Witness) - H
0138de6a-0035-5822-b6d1-5ac12a37453f | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
d61373af-5602-58b1-85a8-f52e8c0cdee0 | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
626b657e-5a90-5787-a728-bd5b76e6463a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
e432ef22-b811-5c52-aa62-55c9a0873ce3 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
0af3194f-4691-558f-88e8-d35d643bcf6e | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Quality Assurance deliverables
0b7a2d63-5dce-5151-926f-86229e23e230 | note | ACTION (Hold, Monitor, Witness) - W
b8180eec-a38f-5653-a96a-0c4cb0e8b6a3 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
2ae03511-18e2-537c-890f-d4c90dfa7dfc | note | Frequency - At completion of Lot
4e7f8844-5a62-5432-b3bf-c2a9b867b80a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
cadaa7dc-e720-5ce2-8438-da690c074409 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
8997f693-a76c-5087-82d2-23cd839f9b5f | note | Records - As-builts, NCR's and RFI's
| checkpoint | 10 - Completion Sign Off From Fields Below
f64bc4b6-f807-502f-88ae-28b23cda1132 | note | Records - Signatures
| checklist | ITP - Maraetaha Bridge 5 - D2102A-ID1507 | itp | ITP - Maraetaha Bridge 5 - D2102A-ID1507 |  | 576460f8-072f-412f-bf4a-eb21bfd70cac
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
f88199f0-f6c1-51c4-a017-defc66b7e08c | textbox | CPS Eng.
316bd405-13e1-504d-ad54-34ab280d0ec5 | textbox | Site Engineer
a38f8463-b9d9-50e3-b778-65e744b5639a | textbox | Quality Eng.
| checkpoint | 1.1 - 2t Ecogreen/Kyowa bags
5265307e-b107-5e3c-8f03-8227cdd7d2cc | note | ACTION (Hold, Monitor, Witness) - W
1c2df015-5591-5721-9fac-84c9550a40fd | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03
9099b30c-04fb-5e55-8983-7cfe19b3e5b7 | note | Frequency - Prior to commencement
d6227ae5-e418-55be-899c-ad16311a97ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
b6349a32-d48d-57bb-be31-d38ffb3d57b9 | note | Conformance Criteria - Purchased from Bluemont or similar approved
309b8b80-5a8f-5bdc-a53a-bbcf604a8756 | note | Records - Material cert, delivery dockets
| checkpoint | 1.2 - Class D A39 Geotextile
7aeba7d8-1a02-52de-82eb-15b3d6e88258 | note | ACTION (Hold, Monitor, Witness) - W
f4a76730-ab63-5c4c-8519-180ed5fee44a | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03, TNZ F/7
f5a113ee-7bdb-55af-bb47-9b842542e214 | note | Frequency - Prior to commencement
ab890e93-1f8c-5a94-91e2-e646c0228f3c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
5b2a2d0c-da5b-5b49-97d6-fbd89b5f3682 | note | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D
1f30795a-3975-51a8-831a-3dbc5322fd40 | note | Records - Material cert, delivery dockets
| checkpoint | 1.3 - Granular Backfill AP65
da86400f-44a8-5d3b-96a0-da6680eacfb3 | note | ACTION (Hold, Monitor, Witness) - W
1340db44-4782-572c-bb24-4669e2ead6bd | note | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
cda9c819-d746-52fd-8c18-b9df0421556b | note | Frequency - Prior to commencement
74d141d7-7af2-5364-ba5d-33a971cf8688 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
402f5d66-2818-5053-8b94-2ca86734722b | note | Conformance Criteria - AP65 shall be hard, durable, well graded, free draining material with maximum particle size of 65mm and not more than 5% by mass passing a 75-micron sieve
b0b85316-24fe-5300-b748-a9ecc5465dad | note | Records - Material cert, delivery dockets
| checkpoint | 1.4 - Rock Infill for Eco-Green Rock Bags
26e5c963-9b29-570b-b8eb-58deb7295338 | note | ACTION (Hold, Monitor, Witness) - H
321b164e-4c7d-5eb5-a5d2-33177b588479 | note | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
5830bdf1-c4e1-570d-9f96-5b6e1fa1d7c9 | note | Frequency - Prior to commencement
b3b1cd16-9db9-5ac8-86ec-845a7c5ca975 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
a39b691b-730e-537b-a54b-926246f966e0 | note | Conformance Criteria - Sound, hard, durable rock resistant to weathering shall be used as rock bag infill material.
2b4d12b3-ceba-5551-a258-b56cb8c0b128 | note | ○ Sized from 50mm up to 175mm but not exceeding 200mm. Should be round in shape and not flat.
646f9e3e-a015-5c78-a7a5-3835eb9efdfd | note | Records - Material cert, delivery dockets
| signoff | AUTHORITY HOLDPOINT
| section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
| checkpoint | 2.1 - Survey Setout and joint site visit
4ae8d08b-c296-5851-a9b0-62075acef384 | note | ACTION (Hold, Monitor, Witness) - H
f2116009-de21-5f2d-b43c-ab8020092839 | note | Specification/Drawings Reference - Consistency with 2-U3436.BM(14) S01-S03
1982ed7f-fee5-5bbf-a86c-4d975c5e2e1f | note | Frequency - Prior to commencement
37f8af29-9cce-544d-9e30-7bee427ffa83 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
1205cbbf-fce4-5392-9e68-e04e8d2a631d | note | Conformance Criteria - CPS Engineer to confirm and agree the extent of works including rock bag placement and survey set-out
a004e19b-6129-5dfa-8b88-153144b63813 | note | Records - Survey receipt, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
cef717a0-2dd2-5ba3-9570-79709c643dfc | note | ACTION (Hold, Monitor, Witness) - W
92aac839-2d1f-517b-875f-3be508681daa | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
9dabdb08-45f1-5c31-bcbc-1c0f665d492e | note | Frequency - Prior to commencement
bc571fae-ca47-59e9-b448-a53af6cf760b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
5a6554d5-34a6-5450-b22e-3be8402da686 | note | Conformance Criteria - Remove and clear the vegetation
645ff52f-aa92-58d3-9370-b488dc25c307 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Excavation
0aa144ad-8a91-56dc-86c5-f60d53ce4d70 | note | ACTION (Hold, Monitor, Witness) - H
aa161853-bf8e-5e77-a95e-a917493f1c6a | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
991e8f47-58ec-530d-9d6f-f31f3f296db3 | note | Frequency - During Construction
7136d1dc-8373-5546-8033-50994e5480c7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
014af4a2-4a34-5757-a200-3f0a4847deab | note | Conformance Criteria - CPS Engineer to inspect foundation level when required depth has been met.
955487b2-62c2-56c4-9a5b-2123d1e9cfe9 | note | ○ Scala check sheet (to 1.5 metres)
b579a155-83de-50e1-9acc-1402b07180c6 | note | Records - Scala Check sheet (CS-4000), CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Ground Improvements
a3ca6e82-0033-5ea5-b7eb-0fcf87da93d0 | note | ACTION (Hold, Monitor, Witness) - H
78985c2b-67a1-54f3-8f55-727d0444a663 | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
b6be57ec-f261-5482-aaff-1b0756882226 | note | Frequency - Prior to commencement
be4f7dd4-cc4b-562e-b51b-de58b17579a7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0afdcb93-4452-58c2-982b-07baac6de572 | note | Conformance Criteria - Any area that requires Ground Improvements (i.e. additional undercuts) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence
0faf4ceb-dc81-5e90-b25b-71125162b2f0 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Granular Backfill AP65
764dee92-d5e8-5f83-ac98-c97db19d011b | note | ACTION (Hold, Monitor, Witness) - H
e778f6d5-e84a-5e2f-a7f0-589c7f5a4034 | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03, TNZ F/1
09c5ac0e-e09b-5577-9f30-4b5ad58dfe30 | note | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
ce9ddad8-b5d5-5dc4-ad2a-fbf5a66c4c08 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
d5a334d2-24b8-5230-b08c-9ff22dac5aca | note | Conformance Criteria - Comply with TNZ F/1.
3c6ca403-da9a-571d-ad37-b8fad2ad044f | note | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
bc6221a1-c2f4-524f-adfa-31d58a3d2be4 | note | Records - Test Reports, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Class D (A39) Geotextile
940b8c68-2440-56fb-ab8d-6abcd2857f92 | note | ACTION (Hold, Monitor, Witness) - W
b44980db-8c69-57ea-9b48-48e8e8702432 | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
bb22eb1d-8832-5c15-b3c0-39c9886d03dc | note | Frequency - During Construction
0f814ad9-73ec-54d1-936b-e0b7db134724 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
56f06f58-ea12-50db-bcbc-e0ceb3f44466 | note | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
6a2a0553-7a8d-52e4-be45-1ea9666237c9 | note | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
d7697ced-d7a6-58b2-a7ab-93f8e42a4a3d | note | Records - Photo's
| checkpoint | 2.7 - Rock Bag installation
964424b4-fcda-56ec-a419-13319fca90be | note | ACTION (Hold, Monitor, Witness) - H
91ef3d50-ade5-5ae4-8da4-4aac4c95074f | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
17ed43f4-a2c9-5a0b-b048-d3b8d2bac2ea | note | Frequency - During Construction
ba75ee0d-b2e2-519d-8fe3-6ec8980e7778 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b38a8ced-24a0-5693-b2e1-048262eac3b9 | note | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
c305703f-0797-54e7-bfb2-662cdc418dd5 | note | ○ The final layer will be determined by the CPS Engineer on site
4b93600f-5ab3-5b20-a2b8-f067f2eaf335 | note | Records - Photo's, CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Bulk Fill Placement access roads
47918e7c-4832-5d9c-93cd-f30ba3d8728a | note | ACTION (Hold, Monitor, Witness) - M
63970332-eda7-5b5c-8c86-02428f66982d | note | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3436.BM(14) S01-S03, NZS4431:2022, TNZ F/1
314b2502-e498-5adc-ae8f-2a485104ee02 | note | Frequency - During Construction
3ee204ce-53d1-5f6b-b01e-3ae7d5c61da6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
17d7d943-0407-50d0-ac02-b6d9e0410373 | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
e1564bdb-089f-575b-91bb-c48bab421037 | note | Records - Bulk Fill Earthworks check sheet (CS-4020), Photo's
| checkpoint | 2.9 - Topsoiling
71f813c5-059d-5874-985f-ca0280918f9f | note | ACTION (Hold, Monitor, Witness) - W
76f41463-eb51-50cc-b9c4-0a4b0cc4a8db | note | Specification/Drawings Reference - 2-U3436.BM(14)-S03
50a854cd-643e-59d8-b82c-8b6dcce840bb | note | Frequency - During Construction
2b9961bf-b6d3-5aaa-9db0-9997f9412da2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
42e14763-6e32-59b0-8c50-30674ad1c2fb | note | Conformance Criteria - Topsoil shall be spread out on the disturbed area at a nominal thickness of 100mm but not less than 50mm nor more than 120mm.
f0d3eff9-e7b3-57f5-91b1-db4b813ed57d | note | ○ Batter steeper than 2:1 are not to be topsoiled.
3a2ed85c-ac51-5244-b95d-6ddcbed47929 | note | Records - Photos
| checkpoint | 2.10 - As-built Survey
3a12d179-7e26-5acf-af0c-d00c412d5b15 | note | ACTION (Hold, Monitor, Witness) - H
4dec2ab3-057f-5eab-a379-e7223c1b259f | note | Frequency - At completion of Lot
c50109a0-53c6-5a12-b68d-e9c10802dcf6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
a0fc7970-40c8-5d20-a033-4cc287d693d5 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
26dd2d89-9de6-5931-b5bc-1d64f8bb3bfe | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Grassing
58f8c33a-30f1-5a0a-8770-f22ab3e4c1a0 | note | ACTION (Hold, Monitor, Witness) - W
78af3432-d58e-5201-b25b-76ef5f435254 | note | Specification/Drawings Reference - 2-U3436.BM(14)-S03
185557c2-c41a-5180-bc8d-423048378aa8 | note | Frequency - During Construction
a04d144f-830b-5a99-9158-56aebcc207d0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
363755af-9773-5049-9d3b-f0013d634d27 | note | Conformance Criteria - Grassing should be superphosphate at a rate 50grams per square meter, Grass seed shall be sown at the rate of 25 grams per square metre bare seed weight
7fb21fce-5334-51b5-9e18-7ed12fdf210b | note | Records - Photos
| section | Section 3: Final Inspection and Handover
| checkpoint | 3.1 - Quality Assurance deliverables
fa2f6bb6-152f-55a0-98bd-7d056c87ecd3 | note | ACTION (Hold, Monitor, Witness) - W
491d7a35-c203-5766-9de7-b34cd9b54d7a | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
96d26f3c-99b3-5ccb-85df-a950b87260a8 | note | Frequency - At completion of Lot
1ef120a1-6022-5095-bafb-9978029ba9a8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1fe0778c-e96d-5166-a639-cdeaaac832bb | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
de7ad251-6ede-5270-bf29-4f9c6b5424bb | note | Records - As-builts, NCR's and RFI's
| checkpoint | 3.2 - Completion Sign Off From Fields Below
6f76877a-f223-5691-adc4-e6d743f20ab0 | note | Records - Signatures
| checklist | ITP - Turitaka Slip Repair - F2601A - Works | itp | ITP - Turitaka Slip Repair - F2601A - Works |  | 72a85c26-6540-489f-9a57-5060ee8ac317
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
0f8957f3-1c53-54a2-af99-301424b6b604 | textbox | CPS Eng.
3230aea2-e686-5ea7-a3bc-e4eadd1769f7 | textbox | Site Engineer
8fade03e-fb5d-57f6-b176-74cc238804fe | textbox | Quality Eng.
| checkpoint | 1.1 - 4t Ecogreen/Kyowa bags
5b338e84-8c80-571f-b1e2-7f743d767013 | note | ACTION (Hold, Monitor, Witness) - W
d21dcba5-e15d-51ab-99f6-9090b8893379 | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
4dd1cf44-e8ee-53a7-adfc-ee6be373deea | note | Frequency - Prior to commencement
34dcaeec-b789-582b-9481-75cc0b7d9bb8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
23d80a28-ae35-531a-9846-2dbdba632d33 | note | Conformance Criteria - Purchased from Bluemont or similar approved
b1291bd3-111c-514e-9b9c-da437697bb50 | note | ○ Traceability of all materials delivered to site
ccac1cfc-65ca-5a2c-86cd-f89e854a2962 | note | Records - Material cert, delivery dockets
| checkpoint | 1.2 - Screen river run
7ec5ee1b-8661-5436-b229-d998cd5afd6f | note | ACTION (Hold, Monitor, Witness) - H
82e32fab-18f7-5a8a-8f7f-f37c0f67affd | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11/SH12
aecfd00d-4e7c-5d08-943c-e28abd0de468 | note | Frequency - Prior to commencement
63747b1b-d931-5f9c-bad2-d466845ff815 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
5bba963d-22a2-56c8-8102-b17dac2bc7ec | note | Conformance Criteria - River run to fill bags 50mm to 175mm screened rock < 2%fines
3d468c93-a7c2-5e24-ad13-72fc1f967e2b | note | ○ Provide written evidence of supply source to CPS Engineer prior to delivery
d1c59dc4-bc12-5608-a27c-ac0a70d81221 | note | Records - Material source test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Class D A39 Geotextile
0c6f2d99-7d9b-5ca5-86e2-f26aae589891 | note | ACTION (Hold, Monitor, Witness) - W
b6a77b61-7f53-573e-acc9-e7dd716f8af6 | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11 TNZ F/7
6b4b10f2-1a6c-5339-9b36-8405fcdce545 | note | Frequency - Prior to commencement
e45d16d9-295a-5f6b-a4a3-08517046b95f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
3885dd45-2a58-5d07-a5b1-5a5afd7acdb7 | note | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D Traceability of all materials delivered to site
222e7c0b-3595-5cf8-805d-daa60a2eb642 | note | Records -
| checkpoint | 1.4 - Granular fill AP65
0e8f6a61-0033-57dd-b9e7-16cbb8aa4eca | note | ACTION (Hold, Monitor, Witness) - W
816775d8-6568-5c68-b13e-806077560844 | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
5204626c-14d4-5d4c-8af8-efff62c5bb59 | note | Frequency - Prior to commencement
ce0b1fe7-6402-5b62-a8e6-9c5253fe70fb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Suppliers grading certificate
0b759737-e89d-557c-851c-46ce546270bd | note | Conformance Criteria - Hard durable well graded free draining material 65mm not more than 5% passing 75 micron screen free from organic fines and vegetive matter.
a4657c84-ea14-5c3f-888a-fe04b7c3569c | note | ○ Traceability of all materials delivered to site
f685051c-7993-5ef7-bada-5756fd013a5d | note | Records - Material cert, delivery dockets
| section | Section 2: IN PROGRESS INSPECTIONS
| checkpoint | 2.1 - Survey Setout
ef6e21ac-7167-535b-9b3b-e60d73ebeff0 | note | ACTION (Hold, Monitor, Witness) - H
85ba12a7-f760-5c96-9c3d-cbfcfbcba1c2 | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
812470f6-c058-5253-ab74-29495f44d73c | note | Frequency - Prior to commencement
83ccad1a-55e6-510f-9afc-1b59fe8bcd68 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
c95fcb1f-a22c-5017-bf58-a57eb2a253e9 | note | Conformance Criteria - Set out extents of works and check against design drawings. Check and agree on set-out and number of Ecogreen Rock bags required with CPS Engineer
ae5e378b-4215-5566-bf60-b9cbca143311 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Excavation
6c9ff44a-4a67-54ae-9af5-4443db84ca35 | note | ACTION (Hold, Monitor, Witness) - H
cb53598d-c562-53c9-a389-8039fb95c448 | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
95c93a96-b61a-548d-92f5-2cac1bca6593 | note | Frequency - During Construction
3fc05a6c-09d4-56c2-966d-84c7e7fef86a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e4d82910-7562-54c5-8cba-d51027431018 | note | Conformance Criteria - Comply with TNZ F/1.
eef994df-c389-5023-be5d-6ea97559fb8a | note | ○ Remove and clear deleterious material when excavating to formation level. Excavated material to be disposed of off-site. CPS engineer to inspect and approve the foundation level material
2530913a-bc8d-596b-93e7-2e6d6c94e859 | note | Records - Photo's, CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Granular Backfill AP65
3f6fa137-1a9a-5dc2-a8cd-45c2a95ba7f6 | note | ACTION (Hold, Monitor, Witness) - H
0d661a55-dd1a-5345-9c3f-8b8fa9324fa0 | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
f592547a-0030-5c0b-85f3-7397fb707875 | note | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
e8d5cd5d-fa91-5fb4-830a-f2632925d99b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
975c30dc-00de-564e-8302-17574e409825 | note | Conformance Criteria - Comply with TNZ F/1.
c860b3e9-526f-5bbc-97ab-5f8fc6d9e19c | note | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
c8f71978-cf13-5538-a062-ed0143a1c6a8 | note | Records - Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Rock Bag installation
5c3d2ff3-2167-55a9-ab8c-6137de7ec63b | note | ACTION (Hold, Monitor, Witness) - H
f9bba66a-fe7e-5bc9-8a4e-e5d3e92cceb5 | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
0e4e4f85-cc9d-5676-90a3-670430da6126 | note | Frequency - During Construction
0e6cddc5-a864-5dc9-b5d9-75facd090da7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
31a7f9aa-cc9e-5b66-87c3-60edaf2b840e | note | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
c1690b69-36b0-5f0d-abd8-52ab6f40a9fc | note | ○ The final layer will be determined by the CPS Engineer on site
8bd26fff-b2d3-5a71-b18b-4a280b61e6dc | note | Records - Photo's, CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Class D (A39) Geotextile
8307755f-f69b-5c89-8566-93e495a2040f | note | ACTION (Hold, Monitor, Witness) - W
ec56c58c-1b72-5ccc-95c4-19c26bd7483e | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
0af13aad-756a-5c7e-9189-4ff85a4a0d71 | note | Frequency - During Construction
99b894f4-bf5e-5bcd-b068-8f2ac9a43551 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a5d9bd61-5eb0-5d4a-aedb-6055272e59f4 | note | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
61c82b22-8750-50af-8d5f-83616c271b31 | note | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
321db55d-125c-506d-9b96-c761ef0be0ec | note | Records - Photo's
| checkpoint | 2.6 - Bulk Fill Placement access roads
b3b90f0a-fff2-5687-ae62-f919ed38ed3e | note | ACTION (Hold, Monitor, Witness) - M
c28fa545-e231-5541-8136-4ff275d606e4 | note | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3435.SM(6) SH13, NZS4431:2022, TNZ F/1
0fc9ed06-9e5f-50af-8c53-dc3c00dcee95 | note | Frequency - During Construction
64808a28-3f49-500e-abbe-f82014b24e7c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
2e342713-77d6-50cb-95e0-ffc5166a37c8 | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
3dc6f98b-4397-500b-a861-43372398621b | note | Records - Bulk Fill Earthworks checksheet (CS-4020), Photo's
| checkpoint | 2.7 - As-built Survey
cc7118d5-7dc1-53f8-b797-39c125dc7327 | note | ACTION (Hold, Monitor, Witness) - H
502050e2-4b45-582c-bb0c-cf53b4348738 | note | Frequency - At completion of Lot
02d64319-66da-5520-b291-05b90a9af28e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
e68140ce-71e8-550e-b2d3-c5f18c839e5b | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
cf521bdc-8329-5924-9a56-aa9b26abef49 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 3: Final Inspection and Handover
| checkpoint | 3.1 - Completion
1754d20e-357b-5afc-a2c4-9c9e79373b94 | note | ACTION (Hold, Monitor, Witness) - H
ce2c452e-9b3d-5029-9dcf-c7d0e68ceca3 | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
cd649d3c-0071-50f1-b96b-2ea2c842c7b1 | note | Frequency - At completion of Lot
232f250b-7509-5bda-893a-153408766341 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
3ccd95c4-ef15-58f2-b4ab-133d3cf9e021 | note | Conformance Criteria - Upon completion of the works the CPS engineer will be given the opportunity to inspect the works having been done to the required standard and sign it off for completion
f4ef162a-b3f3-529b-ba29-39a6cfdcd136 | note | Records - CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Quality Assurance deliverables
b25b0be9-1821-52d0-980a-d4ba40653593 | note | ACTION (Hold, Monitor, Witness) - W
b81aea6c-f9a0-5afb-8414-0c7c01d48808 | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
0a2b5ce4-065a-55c7-9d87-c0d0f0d1bb63 | note | Frequency - At completion of Lot
ab2cb3b2-a2d8-51c7-9ca1-7fe71f1bfd60 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
51affa96-3c4b-5647-9f2b-d6ea2e0aed45 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
5892188c-e05f-5e77-8613-84499d3accdf | note | Records - As-builts, NCR's and RFI's
| checkpoint | 3.3 - Completion Sign Off From Fields Below
6bb45ee2-fc5c-5915-89cb-c8433af2f215 | note | Records - Signatures
| checklist | ITP - Waikare Gorge Descent - C1603A - Bored Pile | itp | ITP - Waikare Gorge Descent - C1603A - Bored Pile |  | dfd895ab-e858-4f4a-96ce-1a1e1215b4e4
| checkpoint | Project Site reps.
c0f8c7c2-0f92-5ff4-a561-2fcf05075edb | textbox | CPS Eng.
cd831d9e-37d6-5ff8-8377-4d3f4c25ff1e | textbox | Site Engineer
a8b66195-d44a-5c8d-9f5e-8eb6430eb451 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
be193455-e28b-5cd3-96ef-ba0e185c9166 | note | ACTION (Hold, Monitor, Witness) - H
20d99eff-930e-5f29-871c-cc2bb7bef108 | note | Detail - Contractor to set out grid lines as per contract drawings and specification.
07f2bd98-80b9-580f-8b33-eb73d54c5891 | note | Frequency - Prior to commencement
42b55cf5-da05-5b27-87bd-0c340943e35a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
b2320059-c7f1-5971-8fe3-f95f08299cee | note | Conformance Criteria - Consistency with Construction Drawing
24c570fa-d276-542d-b811-bce2547a2984 | note | Records - Design Engineer Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 -
5c46e044-c976-53f2-bca4-5e205278667a | note | ACTION (Hold, Monitor, Witness) - M
6507584b-e308-585c-a209-82d6436dabc5 | note | Detail - Any services in the area are to be clearly marked before any work commence.
5446ad2c-272b-5ec6-9d23-5d3e3a1d58f0 | note | Frequency - Prior to commencement
1a1a532b-3cbc-58b0-921d-884f3f16b930 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
283cc7ab-5733-52a6-bf5a-1d88e874f134 | note | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
8f1d8d1c-c5aa-58a8-a86e-0a236ef016e1 | note | Records - Photos, log, site inspection
| checkpoint | 3 -
a546c0dd-120f-59bc-9bd8-e825e9f4460c | note | ACTION (Hold, Monitor, Witness) - H
1f130842-1de6-54b6-91ef-b6208ddf0a17 | note | Detail - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer
ffe6b519-90d1-5960-804e-8338cb72b514 | note | Frequency - Prior to commencement
5ca02a7e-721a-5319-b8c8-13407694ec98 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
5b4579d1-e92c-5f02-b019-97f671a963de | note | Conformance Criteria - If the set out is found to be incorrect, the works shall again be set out by the Contractor and re- checked by the Engineer.
268d0caa-a838-58de-8688-c62c7446bd6d | note | Records - Design Engineer Approval (RFI), ConQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
c511fbaa-acf5-5e65-9746-51c3f9ebc28b | note | ACTION (Hold, Monitor, Witness) - M
63fa3c53-4122-5bff-b136-00f5a663f594 | note | Detail - Timber post spacing and clearance to be in line with the drawing specifications. Set out should allow for clearance, angle and spacing of centres
61858a11-3a64-5a81-b9c1-ddd6448536af | note | Frequency - Prior to commencement
8a189b64-db83-553d-a83b-c4e05b908422 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
5801b3d2-78b5-560c-ba7c-b248e6fb8762 | note | Conformance Criteria - MAX 1.10m centres
530d6d38-35bf-5851-8a3e-d17b52fd4f32 | note | ○ set at 4 degrees from vertical
25215b6e-be33-51ad-bd3f-18568cc2724f | note | ○ 100mm of clearance on all sides of pile
057ba9fd-e0fb-524c-b192-814575d041aa | note | ○ 100mm minimum cover of concrete at base.
5c21b524-ffb8-5b31-950a-2e8368d46d51 | note | Records - Photos, log, site inspection
| checkpoint | 5 -
ea73bac1-8b72-5d57-b59a-0965ff9108f8 | note | ACTION (Hold, Monitor, Witness) - W
767cdcfe-7508-52ff-8075-dfe55d4a2d83 | note | Detail - Minimum Pole embedment to be as outlined in specifications
0e62367e-bd40-5045-87ee-e975a504d5ac | note | Frequency - Prior to commencement
bca3e34b-f082-596a-89f5-37576a9d9882 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
2109dbbe-bc16-5cfb-b4e3-ade00a168755 | note | Conformance Criteria - Pole minimum embedment to be be 3.25m, unless otherwise stated in the pole schedule on drawing C013
c4084f5a-9ecb-549b-a83e-e5ad28518864 | note | Records - Photos, log, site inspection, ConQA
| checkpoint | 6 - Pile Material Compliance - Timber Poles
41cbd10e-15c3-5e33-8ae8-69d1c7274b42 | note | ACTION (Hold, Monitor, Witness) - W
e1716da8-5749-596f-a36e-9e16f0f1b947 | note | Detail - The timber poles are to be radiata pine, high density selected in accordance with and complying with NZS 3605:2001 for cross-section, length, straightness, strength and branding. All materials used in the works shall be new unless otherwise specified.
86d19c38-b21b-5791-a76d-f2dc676ba3ba | note | Frequency - Prior to commencement
87eff655-c3ae-54ba-a5b2-f621f40aad89 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
732bce53-d396-532c-a090-d92053947447 | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance
aaf073f2-3d9a-5960-ab0e-54a766c4afe9 | note | Records - Document/ConQA
| checkpoint | 7 -
63e0df30-78cc-535c-a64d-8160e52d3abc | note | ACTION (Hold, Monitor, Witness) - M
e9b6c533-81fb-5ef9-89e8-0c1a6cef8d27 | note | Detail - The poles must be H5 treated in accordance with NZS 3640, H5.
ebb6f15c-31ec-54c9-b2aa-e54a54afc929 | note | Frequency - Prior to commencement
4a2b578f-e0bd-5be4-b713-4dc826cdc85e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
f391808d-f3e7-5d61-8128-c8024e438007 | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance that the poles have all been treated to NZS 3640, H5.
ac54c80f-f01b-5f1f-b879-1f40d327b53d | note | Records - Document/ ConQA
| checkpoint | 8 -
9df0690b-b75a-5db3-9b73-94fb7a8e5c8c | note | ACTION (Hold, Monitor, Witness) - W
77e6bde5-96e1-5b72-bd85-ac76ef5c4c05 | note | Detail - Poles are to be peeled and not machine shaved and not steam treated. All cut ends, notches or drill holes shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative before sealing with a bituminous sealer. Cut ends shall not be in contact with soil.
ce999cd9-cac4-57f2-b905-b0281997da75 | note | Frequency - Prior to commencement
f6f947c8-37a2-5b83-a2a6-3498ba9f30fb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
5ad89d19-c448-54d2-9c2f-9b207ad4f105 | note | Conformance Criteria - Engineer to inspect as accordance with specifications
6fb43252-2d3b-576a-8005-148bfd9b6e21 | note | Records - Photos, log
| checkpoint | 9 - Pile Material Compliance - Concrete
7b32a45b-05a4-512b-a9af-998803986d6b | note | ACTION (Hold, Monitor, Witness) - W
200da0c0-5684-52cd-8424-54860224acff | note | Detail - Concrete mix design(s) shall be submitted to the Engineer in writing prior to placing concrete and approved before placing concrete.
17ea213c-2184-52e8-82c3-576ebceb51ca | note | Frequency - Prior to commencement
d66fdf8e-3f1a-50e9-9599-b2da5e567896 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
b001da80-a4bc-5982-8155-4e18d0822202 | note | Conformance Criteria - Engineer to approve design prior to commencement
c69d2744-d2e8-522e-a2e2-430c1b144cd9 | note | Records - Design Engineer Approval
| checkpoint | 10 -
08860cd6-81d1-5696-b3f3-7af7bd59e6da | note | ACTION (Hold, Monitor, Witness) - M
f6568834-3ffe-5a16-a2d0-c2c751aeafe1 | note | Detail - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
4a8a2990-c4f6-5754-aa56-d9f86d3a0c20 | note | Frequency - Prior to pouring concrete
6bfc8592-42ca-5818-94cb-37998a299329 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
34bb0b2a-c3b5-5dcb-b8d9-fcda944dceef | note | Conformance Criteria - Site engineer to inspect delivery dockets
74dd2563-6e78-50ef-bb8f-50330b98d534 | note | Records - Concrete Delivery Dockets
| checkpoint | 11 -
b88c95d6-e00c-5d2f-84a8-9b51e0d4144f | note | ACTION (Hold, Monitor, Witness) - M
31f1af45-5eca-5792-b004-8efcbc7c9136 | note | Detail - The concrete used to backfill around the timber poles must have a minimum 28-day compressive strength of 20MPa. Concrete batch crush test supplied by concrete supplier for 28 days.
7a9e74b6-043b-5f78-acab-1ee25ba5e5a3 | note | Frequency - Each batch
81cfb03b-c060-5dba-a200-8540e0b5d117 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
2dbfe536-5d33-5b17-8439-93f5224ab976 | note | Conformance Criteria - 28 day strength of 20MPa
93fa166b-f24e-5dec-a4f2-6c1fe352026d | note | Records - Test Reports, Lab Testing Register
| checkpoint | 12 - Pile Line
23ff5523-b1e2-52b3-b006-1efdca492241 | note | ACTION (Hold, Monitor, Witness) - M
eeb9fb3d-1961-5256-9c82-d68a7772b7f4 | note | Detail - Check if the bench the has been excavated/filled can accommodate the entire pile line
00087894-e7ea-5d19-bb5c-e97b844d2d10 | note | Frequency - Prior to Commencement
6117e6d8-518e-50e9-a912-df519b588398 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6b7c1303-1f54-53dd-ab9b-feb105157d82 | note | Conformance Criteria - Site engineer to inspect against relevant drawings
7c8e93e9-506e-5717-86a4-66720e8bec18 | note | Records - CS-4011
| checkpoint | 13 -
82865199-8e1f-502b-b258-4ab485a03643 | note | ACTION (Hold, Monitor, Witness) - W
7c19f46b-fd2b-5a23-8e24-1037576ed295 | note | Detail - Drilling is to be carried out for every second pole, and poles shall be placed and concreted for at least 24 hours before any drilling for intermediate holes
1f81406e-0a71-5d78-b413-c6cce0c616bb | note | Frequency - Each Pile
c7095c7e-0872-595a-adef-348a88fd793f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d5a7dfe5-47f4-596e-a871-2e3a61f77dd6 | note | Conformance Criteria - CPS engineer to inspect
6ed8e71a-0d8d-50ba-a337-032821608a91 | note | Records - Photos, log
| checkpoint | 14 - Drill Rig Set Up
458cc103-0f33-5a7b-825a-ac2b9b12aa86 | note | ACTION (Hold, Monitor, Witness) - W
89880d59-bae6-54c4-a414-569c0c65cd8e | note | Detail - Check drilling performance, verticality and position using equipment of sufficient capacity for the ground conditions.
309d183f-9e9f-5349-befc-9955d0f5fbc3 | note | Frequency - Each Pile
808c6b97-9711-5440-9733-28b34b122cbf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e05770aa-42b5-509a-aa25-1f1eea175b58 | note | Conformance Criteria - Site supervisor to inspect
18f4ad27-33e2-5bca-be44-ab4d22de82a4 | note | Records - CS-4011 & CS-4083
| checkpoint | 15 -
100bed62-e56b-5a59-86eb-3717fd8f4618 | note | ACTION (Hold, Monitor, Witness) - W
a2b63a9c-75fa-5a89-ab82-46b730c93a66 | note | Detail - Timber poles are installed in pre-drilled holes to the dimensions and at the locations and batters shown on the drawings,
d8e6653c-7c2a-5cbe-8853-977e35949f31 | note | Frequency - Each Pile
bc77a84c-67ed-54c8-85e1-c2a11b1e654e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8d35eddd-d811-5e8e-9ad2-c55febcdd093 | note | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
aa923a38-0c76-5059-a041-9b144295041b | note | Records - Photos, log, site inspection
| checkpoint | 16 - Pile Bore Condition & Logs
ae67d3b3-ae21-573f-9e63-140528aab307 | note | ACTION (Hold, Monitor, Witness) - H
8021aa59-91d7-5995-a4bd-aec79a10a213 | note | Detail - Inspect pile bore condition, pile depth, rock socket length and toe level
adaca05a-17e2-5b17-a0e5-bdfa3b2e6c32 | note | Frequency - Each Pile
30f4febe-7691-5ed3-b7ca-7c6250ec0033 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
aeb31c5c-c146-5669-84a8-4ea763b71d51 | note | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
a0f637be-9ee6-5814-a40d-9cf78a1c8460 | note | Records - CS-4011 & CS-4083
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 -
e2ddfda9-25c7-5f28-a7f2-39735c11ea49 | note | ACTION (Hold, Monitor, Witness) - W
362584b8-7dd7-5990-ba35-60b14ea0a031 | note | Detail - The Contractor shall maintain a log describing the type of soil and rock, the ground water level and the general ground conditions encountered in each hole excavation; hole location, reference number, and total depth of hole below ground level.
a08b49e6-4e0e-53a1-938f-9c0911e6138e | note | Frequency - Each Pile
b1a2a91e-11d0-5452-bb39-3785ef4a2f1e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspection
0ef29b59-6f56-584e-b9e1-a480bdd47101 | note | Conformance Criteria - Information shall be provided to the Engineer at the end of each day's work.
ef598990-adcd-5ff9-bff0-83cc0a75a7b0 | note | Records - Document
| checkpoint | 18 -
580092b6-0633-5235-aead-7cd94f4c637f | note | ACTION (Hold, Monitor, Witness) - M
23ca0757-3432-56b2-a25c-441887259475 | note | Detail - The chosen method of excavation shall minimise overbreak and prevent collapse of ground outside the hole excavation. All loose material is to be removed from the base of the hole before post installation and concreting
f97a8dc3-0a74-50f0-b670-13bd5773c57d | note | Frequency - Each Pile
f0168f8b-cf99-5bee-b1d9-1bd90dc9c82d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
f7e31311-1c55-51e5-9985-36655bfaa698 | note | Conformance Criteria - Areas of overbreak are to be reinstated in an approved manner
aa66ec7b-0360-5e47-904e-12890e3bfb40 | note | Records - Monitor, inspect
| checkpoint | 19 -
bc145fe6-ca34-5bd8-b080-a9e4b8d310d1 | note | ACTION (Hold, Monitor, Witness) - M
f50ace83-29cb-5634-9419-80491fc41284 | note | Detail - The contactor must minimise the impact that the drilling has on the environment.All material collected from the drilling process will need to be removed from the site.
3d3d91e0-741f-5cd3-ae7a-b5c9f7dbe307 | note | Frequency - Each Pile
762f4d8a-0335-5b34-9ac1-fa57a4db7f3b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
0973d4fe-90b8-5d56-9a43-44542f3b7e33 | note | Conformance Criteria - All drilling must be in line with the EMP and other environmental protection documents
299118da-fc49-5d99-9a83-4a42dd56493b | note | Records - Monitor, review document with Environmental team
| checkpoint | 20 -
d7264ecf-b6ed-527b-aca6-05a3d36e7ed3 | note | ACTION (Hold, Monitor, Witness) - M
46070096-7058-58d7-8583-79a4742ea727 | note | Detail - Check that holes are not to be left open overnight.
bf63a037-3488-51fa-8425-808fd4020f4b | note | Frequency - Close of works each day
12acfe02-3b37-5910-afd2-e73c73f1043f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
66903b44-8ad0-5209-afce-0cfc5e87069c | note | Conformance Criteria - Site supervisor to check at close of works each day
57edfcd7-90d7-51c8-abde-0c931bf802c6 | note | Records - Visual check
| checkpoint | 21 - Pile Bore tolerances
6707aec3-f4b7-5c62-8e69-621098d0c89c | note | ACTION (Hold, Monitor, Witness) - H
8fa464c2-e4be-571c-8a0c-a79b4a4ef78f | note | Detail - The Contractor shall inform the Engineer for an inspection of the excavation by a suitably qualified geotechnical professional
94d6083a-cce9-51c6-8828-c170fdb42eac | note | Frequency - Completion of stage or bore drilling
60d6fa38-1a9a-5198-b69b-6d026f5284fd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
0cc1f5c4-606d-5e14-a98c-80d1b53d4d96 | note | Conformance Criteria - Contractor to notify engineer, Geotechnical Engineer to attend and approve excavation
77de0e13-1253-59a8-accb-e712cd5b51f8 | note | Records - Geotechnical Engineer Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 22 -
2020aaa2-3f74-5818-b9c9-2ae37391e865 | note | ACTION (Hold, Monitor, Witness) - H
61339f11-5d5e-575a-b8b8-130e2cc4d7b7 | note | Detail - The hole must be excavated to the tolerances outlined in the specifications
473ec2c1-3429-5f9c-8aa2-893f1072ddd5 | note | Frequency - Each Pile
70d0203d-f399-5d8a-9ece-f2304d595197 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
0292e4dc-0e7a-54cf-946f-2dd0e25efaf3 | note | Conformance Criteria - Pole hole diameter +50mm / -0mm
8aadc27a-b3af-51a9-9693-204ff88d8018 | note | ○ Hole plan position at all depths +/- 20mm
636d6b9b-0f76-5c8f-aa35-92ec44b13c52 | note | ○ The pole shall not vary any more than 2 degrees from 20 degrees
f9eed877-3790-5aba-b7ff-ac3aefc66fe4 | note | Records - Geotechnical Engineer Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 23 - Timber Pile tolerances
9409dc89-ef39-5302-a668-6060c7eb1bc9 | note | ACTION (Hold, Monitor, Witness) - H
24075fe3-f938-5a00-a0b1-b55d3499e874 | note | Detail - Timber poles shall then be set into the holes, complying with the tolerances outlined in the specifications
9123d3d8-bc3f-591b-b9e3-2285be540e18 | note | Frequency - Each Pile
ce48f5d4-9580-523b-ab4a-15014e838a80 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
69f4194e-5308-53fb-9dbd-5af30673efd4 | note | Conformance Criteria - Deviation of pole centre from line in plan +/- 10mm
4f2093bd-8e35-54d7-a481-a5d375478530 | note | ○ Pole top reduced level +/- 10mm
98bbd0d3-5a34-5e64-9ac0-b028dd5a98cd | note | ○ Pole base reduced level +/-50mm
1e1cdab8-8851-53fc-a835-ea555f14fe06 | note | Records - Geotechnical Engineer Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 24 - Concrete Pumping Operations
65c0f45f-feb5-5e72-aa09-99a4bbac44db | note | ACTION (Hold, Monitor, Witness) - M
d3f4776f-4c7e-5082-8494-ecff2456a336 | note | Detail - Ensure the Permit to Concrete Pump & Pump Operator Checksheet has been completed before concrete pumping commences
5519172b-2ab4-5744-8e86-441f24167fe5 | note | Frequency - Prior to commencement
4227f32b-55a5-5f04-bfb8-d42958973a46 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
fdb44cc3-f2fe-5650-b067-1f92368e2f68 | note | Conformance Criteria - Site Engineer to compete CP and PO checksheets
7789f216-cda0-5e0d-b0ee-9c5015b6c6de | note | Records - CS-4029 & CS-4002
| checkpoint | 25 - Concreting
b2c1139b-48bd-5988-9ac3-763e9b37fa90 | note | ACTION (Hold, Monitor, Witness) - M
946451ba-7f1f-53c4-8e9b-8c6b2e336554 | note | Detail - Concrete pre pour inspection
8888825a-a5a8-5bbd-95a0-c9681ce22a0f | note | Frequency - Prior to concrete pour
9fb2fa5b-9f25-54db-abe0-b2281663adf8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d7c05663-0391-57d0-9aa0-60d406d66257 | note | Conformance Criteria - A pre pour inspection checksheet to be completed outlining:
94fc241b-08cb-512c-bf0f-91d5fdb52c2d | note | – Pre pour inspection checksheet to be completed
5ec7cb45-fa0c-5740-a694-9fa30874c9c2 | note | Records - CS-4011/ TBD
| checkpoint | 26 -
41d8b3fa-9ef3-51ce-8b02-fc12bf9f1504 | note | ACTION (Hold, Monitor, Witness) - M
8abd268c-3f8b-578c-965b-ffacb4e95edd | note | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. Dockets to the Engineer and keep a record of the volume of concrete placed.
44eeefa4-f4f9-5213-b2aa-eb27c01f08e4 | note | Frequency - Prior to concrete pour
6958a507-f390-5d44-b15c-b6078ee76b85 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
3cef2173-e38d-5dcb-ac48-6a0d3f5e7016 | note | Conformance Criteria - NZS 3104 Concrete dockets match design
a0528c79-1abf-5d65-b2df-5bf91146f656 | note | Records - CS-4090
| checkpoint | 27 -
603356dd-f642-5f72-8cf5-92688bfeb308 | note | ACTION (Hold, Monitor, Witness) - M
7269f070-aa20-50af-a1a7-4b069df3f098 | note | Detail - The concrete in each hole shall be completed as one continuous operation
b7112cad-2c64-516b-add7-145917a046fe | note | Frequency - Each Pile
b9fd7a6d-f650-5325-b754-71969cdd2a42 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
79ddcb59-11de-52c3-a263-69e5c00190e1 | note | Conformance Criteria - Concrete Inspection Record
f647d7c8-6d33-5abe-8e57-5d8fea6916b7 | note | Records - Photos, log, site inspection, Document
| checkpoint | 28 -
9ea10b46-f5bc-54ee-ae8c-a92e70875f89 | note | ACTION (Hold, Monitor, Witness) - M
a4a01dcb-c215-53aa-be4b-884a10ca0b66 | note | Detail - Securing of poles in position, then the approved concrete mix shall be poured around the timber pole with concrete being tremmied if required
fe77ace9-752c-547d-af5e-a0c561cb1818 | note | Frequency - Each Pile
3b66de67-0ebf-5295-8278-59e944e1b8e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
2fa6e6e5-17b6-544d-a02f-74ace7928cee | note | Conformance Criteria - Concrete Inspection Record
ca2c3e62-a5e1-58a3-95f2-c1516a9a8024 | note | Records - Photos, log, site inspection, Document
| checkpoint | 29 -
c380e777-1ef7-50c5-b894-eb98cccc5021 | note | ACTION (Hold, Monitor, Witness) - M
119c3d92-3d7e-54d4-bdf5-cba839709db6 | note | Detail - Check concrete placement method and finish
f3e8666b-6ba5-5ba5-bd7f-5e79ae30f902 | note | Frequency - At completion of pour
bbb5f6b9-0ec8-5c7c-b411-973532253a54 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
99922070-ba2b-5920-934a-795c18b84d29 | note | Conformance Criteria - Concrete Inspection Record
e8760f80-6b1e-5308-a4d3-f541deb39482 | note | Records - CS-4011
| checkpoint | 30 - Survey As Built
fce2bc97-1068-56e0-bf9d-d6888841d75f | note | ACTION (Hold, Monitor, Witness) - M
d4947f35-a84d-5361-a62a-de30edc3e5e4 | note | Detail - Survey final position and R.L. of each pile, produce As-Built drawings
2081d59c-9e89-58af-ae44-36aca89e2318 | note | Frequency - Each Pile
8ccc5d34-eb9e-59cf-8eee-b9ef94268fc6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
2a51e531-7779-5d1b-a926-28a86c2c578e | note | Conformance Criteria - As-Built Drawing
26523812-96bc-5a2f-9bed-e9f2d6c6d697 | note | Records - Survey receipt
| checkpoint | 31 - Lot Number QA File
03b92a6e-5576-5638-bc14-fc0ec883132a | note | ACTION (Hold, Monitor, Witness) - M
a0a9fed7-a577-561a-a4ff-a28d811727ba | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
8a01c41f-06c2-5630-a963-f5a95d2b112a | note | Frequency - At completion of Lot
c999b3a7-7777-54e9-845b-c9522a33c62b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3f566e6f-5adf-542b-bee3-e3211c677995 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
fc523927-ac25-5585-9593-63e90e89f7f6 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 32 -
59c4c592-b0a7-5223-a9dc-5416044cb72c | note | ACTION (Hold, Monitor, Witness) - M
bf2c2042-a7dd-5230-b058-0eb12ee0a2d9 | note | Detail - Check all piling records are completed and signed by the relevant signatory.
4745cb1e-278d-5469-9ce2-5eb87197c471 | note | Frequency - At completion of Lot
7117c316-9c1d-5852-8908-d0876a5ec150 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
11f3d9f0-a03c-51f4-b4a6-eaa75bbe2249 | note | Records - All relevant documents
| checkpoint | 33 - As-builts
d8651c18-89ed-5754-9739-3c4e6474d829 | note | ACTION (Hold, Monitor, Witness) - M
d0424fc1-eb99-5e28-bc90-a86eb219d30d | note | Detail - Red pen mark up drawings to be included in QA file
68219caf-3fb6-5eb8-a4d7-ec0ac338cae8 | note | Frequency - At the completion of the Lot of work
9dc031ec-9953-542c-a768-15c2b749967a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
0f0a3b1c-7cd1-5bfc-b665-d84cdd3b4c08 | note | Records - Asbuilt Drawing
| checklist | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | itp | ITP - Waikare Gorge Descent - C1603A - Ground Anchor |  | 4c352ada-8bb8-4301-a3c3-d998d7d962f8
| checkpoint | Project Site reps.
23268b9b-9119-556b-8205-fa154e0babb6 | textbox | CPS Eng.
2190b7d2-d1c2-5b6e-996e-5888b338140f | textbox | Site Engineer
eebd02a7-5ea2-50bf-86a3-e0205dcf4236 | textbox | Quality Eng.
| checkpoint | 1 - Test Anchor Setout
bbb0f351-09aa-55f5-b634-687bccbbd8f1 | note | ACTION (Hold, Monitor, Witness) - H
821768a7-bd88-541d-8d0a-4c9e59ba6aa8 | note | Detail - Location of the tests (to be agreed with the Engineer, two tests shall be completed), and 1 pull test location.
af029eb6-fd67-5c83-99f0-f3809988b74d | note | Frequency - At least 1 week prior to Testing
3b1cd78e-4ee2-5970-9013-128c86e48335 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
6a06a246-44e1-5439-b551-acb0ae954fdf | note | Conformance Criteria - Consistency with Construction Drawing and agreed with Engineer
fc789738-5e33-5654-962c-5f075eedb04e | note | Records - Design Engineer Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 -
ffe2582b-c47d-5315-8e7c-03b47ca43a7f | note | ACTION (Hold, Monitor, Witness) - M
e3825050-d1a8-5750-b9ef-ffc1a2e04e9e | note | Detail - Any services in the area are to be clearly marked before any work commence.
28db5995-0e4b-5d4e-9e9d-d44915089874 | note | Frequency - At least 1 week prior to Testing
f58a6714-0d12-5d2b-8648-35f2b11593cb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Service location
b45f83ee-dcb1-5d22-8b23-75cbbec89485 | note | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
5da6e55d-f3e5-5e8d-a6ed-4a94b9b9d346 | note | Records - Asset owner report, site inspection
| checkpoint | 3 - Steel Anchor Rod Material Compliance
2881fe03-ff04-588d-9435-ce44066664ac | note | ACTION (Hold, Monitor, Witness) - W
6d76b4a3-dbc8-5766-b5ff-afcf187b245a | note | Detail - Design Life of 30 years
acc7b316-5fa7-516d-9fed-fca864a8ef63 | note | ○ Design Working Load (DWL) per Anchor: 168kN
23681ecc-fe9d-5dba-b2ba-74508c294e99 | note | ○ Anchor rod diameter: minimum 25mm threaded bar, with a minimum yield strength of 500 Mpa
82a9e9d0-82d6-5fe2-9381-30bd5e9b37e6 | note | ○ Minimum anchor rod length: 12m
1f372ea4-83aa-522c-9fbd-5e5497865a8b | note | Frequency - At least 1 week prior to Testing
c39c36f8-e2b7-5f61-b6e1-78543e7bf077 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
58201b60-6e76-56a1-bbdf-c77f2865c385 | note | Conformance Criteria - Design Working Load (DWL) per Anchor: 168kN
6b7fd233-0ade-5d47-8cd3-527adcd10fcb | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
8910bcb9-1e97-5a50-ac97-dd4c02057537 | note | Records - Materials receipt
| checkpoint | 4 - Steel waler Material Compliance
db375b06-22a4-5513-9776-895cd6a20522 | note | ACTION (Hold, Monitor, Witness) - M
717dfcaf-951a-5971-b136-41806e787193 | note | Detail - The steel structural sections for the Waler assemblies shall be primed with ethyl silicate or alkali silicate zinc rich primer in accordance with AS/NZS 4680, ASNZS 2312 Part 1 Paint Coatings and NZTA S9 respectively.
c4de7caa-0566-5d72-a93d-7f2b5d2b31cf | note | Frequency - Prior to Install
3c303fff-921f-56e3-9031-cebc944037d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
6a774218-2f10-5bbd-ba92-f71cb65556be | note | Conformance Criteria - AS/NZS 3679.1, AS/NZS 4680, ASNZS 2312 Part 1
ebbfd09f-2a4d-5d4e-b28c-1da06122b770 | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
e07317d9-7667-50db-9a88-124bae974ead | note | Records - Materials receipt
| checkpoint | 5 -
171c6894-c006-5007-a03a-490b45d55e7f | note | ACTION (Hold, Monitor, Witness) - M
49d9d488-f686-5f29-9489-988a867e147f | note | Detail - The Contractor shall provide the engineer with test certificates giving the tensile and yield strengths of the steel used to manufacture the structural steels and steel plates at least seven days prior to the fabrication of waler.
7f41fa5b-25d8-50fc-8570-e9554bd0bbdc | note | Frequency - Prior to Install
6217d645-fc4d-5427-9a0f-fb9d95634bff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
5485e335-4634-5c64-ab3c-eded6bdca952 | note | Conformance Criteria - Test certificates of tensile and yield strengths, 7 days prior to installation, 150 mm x 75 mm PFC WALER BEAM
a6c8bb3f-eebc-5985-bda2-684c1ba67b28 | note | Records - Materials receipt, test results
| checkpoint | 6 -
2a9e6d54-ca73-555c-bfaf-41065b82c40e | note | ACTION (Hold, Monitor, Witness) - M
5a29f75d-d691-5fe4-9a51-418144d00bea | note | Detail - Confirmation of waler dimensions
2d354958-401d-5bae-a402-509b8567812a | note | Frequency - Prior to Install
fb4c8a52-3ddb-575b-84c3-641e911edd2d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
a657737b-338f-5b17-9fbb-43aa1385ddc0 | note | Conformance Criteria - 150 mm x 75 mm PFC WALER BEAM
ce3ec849-bf72-5797-b1b5-bf12b6e003a2 | note | Records - Materials receipt
| checkpoint | 7 - Bearing Plate Material Compliance
29e83b48-0501-5327-9df9-27baa121f9b5 | note | ACTION (Hold, Monitor, Witness) - M
67b7f40f-8ff6-5219-be20-6107b0964950 | note | Detail - Bearing plates shall be steel with a minimum yield strength of 350MPa and the final size and thickness shall be confirmed by the Contractor in conjunction with the anchor supplier.
9b9967c2-58fd-5094-a958-44f762736f3e | note | Frequency - Prior to Install
f49231ce-cf64-5382-9fc1-adecce0e49a8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
0b2ac64b-76aa-525b-b41d-870aad53947b | note | Conformance Criteria - minimum yield strength of 350MPa
99b29078-56fa-5f1f-a2b0-1e01a28e3ffd | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
95dfd25b-fe7f-530f-b458-19b71c660238 | note | Records - Materials receipt
| checkpoint | 8 -
db386b6d-5287-5fa1-bb7d-09490c6784e4 | note | ACTION (Hold, Monitor, Witness) - M
9ae4cf23-39d9-571d-8e82-3049258e5374 | note | Detail - Confirmation of plate dimensions
1ecf9133-a2bb-5f9d-819d-d8eb69f3c2b1 | note | Frequency - Prior to Install
5208c752-e5ed-5e34-ac91-c1fa02225ec4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
2dc2ce37-68dc-583e-b49e-dfa2c9ebbb61 | note | Conformance Criteria - 16mm stiffener plates
c169f88d-57db-5b3f-9cc0-25c264a5c5fb | note | ○ 150x150x20 plates
a339a983-f2bf-5075-8250-ff7e45e39b18 | note | ○ 200x80x6 plates
ed6c4ff4-2910-5b6d-b60a-1117ad5b06e5 | note | ○ 250x300x16 plates
13637350-c496-5523-b29a-fe86e6b99b6f | note | ○ 250x250x16 plates
a73ca856-0b0c-56bc-aba7-85a9e9a22584 | note | ○ 100x100x6 washers
088193a0-2316-5164-9a24-d0b6abd9ad55 | note | ○ 200x80x6 plates
785d8dfa-4145-540f-bf14-f0f6b4033b06 | note | Records - Materials receipt, test results
| checkpoint | 9 - Hex nut/ Washer Plate Material Compliance
15c05c19-ce66-5cfa-b747-8a2e381609d8 | note | ACTION (Hold, Monitor, Witness) - M
0aa129a5-9f8c-55e5-a45a-657b50a42f91 | note | Detail - Shall be standard, heavy-duty, high strength, structural quality only, flat base, machined from steel, designed for use with the all-threaded anchor rod.
55d0ff13-7e17-5440-983c-4873223e1f62 | note | Frequency - Prior to Install
3b7cc288-1394-5cd0-821c-6f3005300556 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
45c996e5-e927-54b4-b58f-59934ab91b45 | note | Conformance Criteria - conforming to Grade AS/NZS 1252
ca17e480-cbe7-5e72-ae38-c1e0c1ea8e7b | note | ○ Develop more than 125% of the yield strength of the anchor rod & ultimate strength of not less than 100% of the guaranteed ultimate tensile strength
c55f67e1-4424-5315-8bb2-236e171ca682 | note | ○ Hex nut/washer shall be hot dipped galvanised.
ee28f67f-ee15-5771-98db-71532599ed9e | note | ○ Certified mill test results
927f074f-53fa-57da-8021-1a0aaabd2bea | note | Records - Materials receipt, test results
| checkpoint | 10 - Mechanical Couplings Material Compliance
0c654219-c5a6-58ef-a97e-250527def15f | note | ACTION (Hold, Monitor, Witness) - M
24ae8b56-7f1d-5641-ba84-52e7a63c4cf9 | note | Detail - Mechanical couplings, when required, may be used to splice the anchors.
c713d6fe-ef6e-5c11-a6f4-b1077647f6e3 | note | ○ The couplings shall be stainless steel and wrapped in Denso Tape to satisfy double corrosion protection requirements.
42ef2dca-af78-5b55-a117-a033b82b2976 | note | ○ Grub screws or locknuts shall be installed and mechanically tightened either side of the mechanical couple
5994f9a2-9407-5741-973c-541a760633c0 | note | Frequency - Prior to Install
d974c640-507f-5640-b91b-d976794aa6cd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Inspection
e31f50ea-4468-5cda-a5b1-63ca2b4d2496 | note | Conformance Criteria - 100% of the guaranteed ultimate tensile strength of the anchor rod
c9f33b96-bf38-5f46-a81b-54c645b65324 | note | ○ Steel conforming to AS/NZS1252.
03486d38-f075-5473-b3ca-c308e07aa5cb | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
6e6b9d39-03da-5f63-818b-0acf04660b4f | note | Records - Materials receipt, test results
| checkpoint | 11 - Anchor Construction Submittals
08caede1-931b-581e-8a9c-73129681492d | note | ACTION (Hold, Monitor, Witness) - H
c16cace3-8921-569d-880d-24f68a3531c4 | note | Detail - The Contractor shall submit a construction plan and detailed construction sequence to the Engineer at least 1 week to commencing pull-out testing
969f9b56-ba14-5bbc-acf9-6b438cf64ed9 | note | Frequency - One week prior to install
aaa32728-769a-55ba-b134-215d948d3576 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
1261313e-fa4e-5cc8-aee2-7d941f5c19ab | note | Conformance Criteria - Document outlining Start date, working drawings, methods, manufacturer certificates, detailed construction sequence
8cf53d19-e777-5e5c-ba57-1af8e4634060 | note | Records - Submitted documents
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Anchor Construction Submittals - Working drawings
674ca231-a2b8-51ed-a92c-a34c028be208 | note | ACTION (Hold, Monitor, Witness) - H
1b8c4d0f-09a6-5d9d-b25f-1f0b4c5f627d | note | Detail - The contractor needs to supply working drawings which outline the details and location of the pull out tests
e3f95039-07af-55b4-92a2-ad9a142ffc11 | note | Frequency - One week prior to install
ecf78379-0e0c-5278-9144-f195648aa957 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
6937a615-93d9-5be3-8597-787c9a454857 | note | Conformance Criteria - Installation method
5cd4dec9-2d21-5d0d-9d25-0aa25221c8c3 | note | ○ Location of the tests (approved by CPS)
c2554208-24e0-52d5-90e3-34658909ae3e | note | ○ Testing methods and equipment
44d9dec0-4195-57ba-a4c9-20259650d678 | note | ○ Ground anchor Schedule
5708a8c2-6666-541e-8361-549073c681d5 | note | Records - Document
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Anchor Construction Submittals - Ground Anchor Schedule
644e173e-fd26-5095-a320-45c2f61047fc | note | ACTION (Hold, Monitor, Witness) - H
171d590e-e83f-592b-97da-1c2adedeeb0b | note | Detail - The contractor needs to supply a ground anchor schedule which outlines the strength and detailing requirements:
eeaa3124-5340-5017-8f0b-5cb93297fb80 | note | ○ Ground anchor number
e8e52a15-8a9f-5a3b-8801-9d39079938f9 | note | ○ Ground anchor DWL
67472420-7116-542b-9fb9-2141a7447a68 | note | ○ Ground anchor DUC
5758c266-b610-555c-9504-e3c66c0bae1c | note | ○ Ground anchor capacity reduction factors for rod & pull-out
04312f16-2fc8-5693-a95b-c8509791d28e | note | ○ Type and size of anchor rod;
e5ec270e-f8c2-54fd-83d8-1a23abf5b0bf | note | ○ Anchor inclination;
c48a2a8b-204a-53ce-8dd4-f8900098e978 | note | ○ Minimum total anchor rod length;
398ec44a-7727-5426-965a-689b0ccdc971 | note | ○ Corrosion protection system.
9035a750-cf27-5bfe-ad16-b84bafab5b62 | note | Frequency - One week prior to install
5371abeb-dc5b-5c86-ab46-ee1b829a54bd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
c6429465-b09a-5462-b9f1-a4088ba003d4 | note | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
eead5b9f-e09f-5d97-a77a-c8546ecb0f73 | note | Records - Document
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Anchor Construction Submittals - Testing Methods
2e0b110b-879a-5de7-a49e-589481fbb9af | note | ACTION (Hold, Monitor, Witness) - H
b4350c98-cce4-51b6-95a5-fd609cac7e41 | note | Detail - Details of the jacking frame and appurtenant bracing.
b99d5479-fac2-5291-a921-2730cab0c574 | note | ○ Identification number and certified calibration records for each test jack and pressure gauge and
e233ec5e-23ec-5559-96f9-6c79c9107b48 | note | ○ load cell to be used. Calibration records to include the date tested, device identification number, and the calibration test results and shall be
d2f6c338-f338-5b2a-ac17-72849a704570 | note | ○ conducted by a qualified independent testing laboratory within forty-five (45) working days prior to submittal
1873e010-7e79-5ec6-af90-3d3dede1deb2 | note | Frequency - One week prior to install
c3792b9c-72bd-5f41-937d-faacbf992882 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
0f7596c6-6772-5a3e-9746-73d5f1e497d7 | note | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
b73b697e-65fc-5893-a548-de525dc5c509 | note | ○ Certified for an accuracy of at least 2 percent of the applied certification loads
9ff8786b-72eb-57e1-8a84-7b6f4f47ab18 | note | Records - Document
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Anchor Construction Submittals - Testing equipment
c141fa6b-7d39-52be-8f5c-31c0bb60a500 | note | ACTION (Hold, Monitor, Witness) - H
90c0f665-fccc-5806-99cb-aebd306be804 | note | Detail - Testing equipment shall include dial gauges, dial gauge support, jack and pressure gauge, electronic load cell, and a reaction frame. Contractor shall provide the description to the Engineer prior to testing.
16e1d5cf-adf0-5e1b-a2e7-4a3cf48f52b8 | note | Frequency - One week prior to install
77ee96dd-9c54-5b5b-859f-9bde894d5340 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
ccedf6b6-15e8-592f-a78d-983c74944b95 | note | Conformance Criteria - description of test setup and jack, pressure gauge and load cell calibration curves
5976ee00-bb9e-5fa2-b213-475b905b1f1f | note | Records - Document
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 -
34fb898a-59b6-5847-9e73-40f889f019f9 | note | ACTION (Hold, Monitor, Witness) - M
00bb3889-454c-56fa-9612-fc9bdca93702 | note | Detail - The testing reaction frame shall be sufficiently rigid and of adequate dimensions such that excessive deformation of the testing equipment does not occur.
f400be07-be73-5757-affc-5f4319371219 | note | Frequency - One week prior to install
8c257f5e-1041-5c0d-a993-13ea51bc4d7f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
1123c46f-d8c0-5d16-a4ef-15206b89eb1c | note | Conformance Criteria - Reaction frame sufficiently rigid
fd021c52-adb9-56cb-90fc-01f4aac3afbc | note | ○ Support and centre jackover anchor rod
0f389d6c-0391-5f7f-ba32-fc352ecfb3f2 | note | ○ Jack, bearing plates and stressing anchorage aligned with rod to as not require repositioning during test
5e99158c-1995-5771-8439-31275149f66c | note | Records - Anchor Test log, photos, submittal doc
| checkpoint | 17 -
a2f098f1-aa76-5a78-9a04-5e601f61b8a1 | note | ACTION (Hold, Monitor, Witness) - M
1c21ebb8-984f-5dca-b845-16ee522fed01 | note | Detail - Test load shall use hydraulic jack and pressure gauge. The pressure gauge shall be graduated in 500 kPa increments or less. The jack and pressure gauge shall have a pressure range not exceeding twice the anticipated maximum test pressure.
1432fb0a-5b29-50bb-938b-ac04c15a6f2c | note | ○ Monitor the anchor load during the pull-out test with both the pressure gauge and the load cell. Use the load cell to maintain constant load during the creep test portion of the pull-out test.
885a62a2-3027-5da6-925d-df8dd248954b | note | Frequency - Prior/ during testing
e5f62759-28c4-50da-84a3-ba57f1bfb5bc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspections
13fd0bdb-9e3e-5693-bbb7-1aec83f73f01 | note | Conformance Criteria - Jack and pressure gauge shall have a pressure range within requirements
30091e8b-0e19-5a81-877d-214ee8e31aff | note | ○ Gauge graduated in specified increments
4c900274-e152-5412-b576-8ba2a1a60b9b | note | Records - Anchor testing submittal, Anchor testing log
| checkpoint | 18 -
f6168c51-f37e-5dd2-ac01-cc7261aec8d1 | note | ACTION (Hold, Monitor, Witness) - M
9048c0cb-4bcc-54cc-bd07-79139b50e552 | note | Detail - Measure the anchor head movement with a dial gauge capable of measuring to 0.025 mm. Use two dial gauges when the test setup requires reaction against a soil cut face.
87aecb4a-2152-5052-b502-7da47346ad71 | note | Frequency - Prior/ during testing
1b45dade-62e3-5318-96c8-d6704c89519a | note | Conformance Criteria - Gauge capable of 0.025mm used
3eb18229-a642-5924-a8f0-414764b09674 | note | ○ Sufficient travel to conduct test
ee7efd73-96c2-5c76-9a9d-c137a67fbb41 | note | ○ Visually aligned gauge parallel with axis of anchor
863a400a-02f7-5dac-bd54-c5c67a93b17e | note | ○ Two gauges used during reaction against a soil cut face
993d4cb4-24cb-589f-ba76-0d01d611eb61 | note | Records - Visual inspection, photos, Anchor testing log
| checkpoint | 19 - Anchor Construction Submittals - Ground anchor report
a8f80b50-6fbd-57f7-ae9d-43f761a1df49 | note | ACTION (Hold, Monitor, Witness) - H
0cc17bf4-f2bb-59aa-8d5f-fd48249d6c23 | note | Detail - As-built drawings showing the location and orientation of each ground anchor, anchor capacity, total anchor length as installed. Ground anchor test results, graphs and supporting interpretation
8fcec186-1e61-512e-99fc-f9ba97b01dd7 | note | Frequency - within twenty (20) calendar days after completing installation
26bb232e-3c33-525b-9370-a31de5b3f6e6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
5b596424-9236-5139-afdc-98873f5c478b | note | Conformance Criteria - Ground anchor report sent to engineer within twenty (20) calendar days containing:
c1dd6ba8-9b1c-5631-9a77-08c5339b4275 | note | ○ Ground anchor test results
8edac8f1-1aa3-57fc-9496-715088d50f1f | note | ○ As-built drawings
6b36af88-20ea-5011-a99a-0b1c3ed592e1 | note | Records - Report, document
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 20 - Ground Anchors
812e1059-496d-549b-9c23-63af2ffb1070 | note | ACTION (Hold, Monitor, Witness) - M
870c146a-3538-564d-9f62-bd5a57766188 | note | Detail - store steel and accessories without damage or contamination. All materials shall be stored on timber pallets on hard ground in a secure area, clear of any construction operations.
a0197b22-5c12-5c85-9ad3-1a2ca9af644b | note | Frequency - Throughout works
caf48723-0ae9-5a65-9aa8-40fc93a03fee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
9a1519c9-8717-5773-8261-939ad1691d50 | note | Conformance Criteria - Stored on timber pallets
0c0317d0-1690-5436-8486-3f2c9c89913c | note | ○ Hard Ground
08fffe2a-3be6-579f-9b5a-9da0c250f8f6 | note | ○ Secure Area
8ca9df54-f519-5a32-af66-ce7c8f82593a | note | Records - site inspection, Photos
| checkpoint | 21 -
17084e57-53f7-5de2-aa89-88db92b5edd4 | note | ACTION (Hold, Monitor, Witness) - M
08099199-2b0f-5da8-a900-36bd7a3173fe | note | Detail - Anchor components incorporated in the wall shall be free of corrosion and physical damage at the time of placement
e57c2564-eceb-53e7-8794-be28ae09cb66 | note | Frequency - Throughout works
23d929c5-378c-5c86-ab54-5c0a80285646 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
3bca332b-4e7e-5ec1-9a51-11c10c4cb6fc | note | Conformance Criteria - Free of corrosion and physical damage, Placed so will not damage ground
9100991a-d393-5b1c-a146-fdae07f25234 | note | Records - site inspection, Photos
| checkpoint | 22 -
67627495-25c7-5dab-8290-c3f0d5383b7f | note | ACTION (Hold, Monitor, Witness) - M
079a7785-163b-58eb-8b33-8197ec624d59 | note | Detail - Works shall be carried out in accordance with NZGS (2023) Ground Anchors: Design and Construction Guideline. Should any discrepancies between the relevant codes and standards contained in the above Guideline and this Specification arise, they shall be brought to the attention of the Engineer
4c93151c-4767-5371-998e-b273a0dcac9a | note | Frequency - During Installation
6ed1c0fa-7cff-552b-b7f6-b68f1f078b28 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
5ac424d5-c8b4-5b28-9442-aa90bfcdb54b | note | Conformance Criteria - NZGS (2023) Ground Anchors: Design and Construction Guideline
5fb2f3f0-938d-5708-85e8-e96e6b4a7b37 | note | Records - site inspection, Photos
| checkpoint | 23 - Ground Anchors - Tolerances
7cd3c381-9cee-5d01-92ce-af4bd92c8de9 | note | ACTION (Hold, Monitor, Witness) - M
2bdf4b5f-5091-5797-b5b8-cf02253ef743 | note | Detail - Anchors shall be installed at an angle within ±2 degrees of the angle of the theoretical centreline and shall be located horizontally on the face of the wall accurately
ff78d446-9746-5295-8f12-da50b42bafa6 | note | Frequency - During Installation
da596ff6-dad6-5fa7-8ebe-74230605f81a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ff8fe1eb-1ea1-5d5b-bfc9-400a20f84db1 | note | Conformance Criteria - Angle within ±2 degrees of the angle of the theoretical centreline plus or minus 25 mm from the position shown on the drawings.
64ab86d9-4ba2-5152-a4be-17b23d7c55ac | note | Records - site inspection, Photos
| checkpoint | 24 - Ground Anchors - Anchor Testing
cc11aeed-e605-5701-881d-64fff80a4adb | note | ACTION (Hold, Monitor, Witness) - M
5b54be5c-6b22-5c35-a459-915d54964f53 | note | Detail - No-load greater than 10% of the design load can be applied to the ground anchor prior to testing. The maximum test load shall not exceed 80% of the specified minimum ultimate tensile strength of the anchor rod.
6172d9ea-ff60-5409-81e3-71d1b87cf311 | note | Frequency - During Installation
f475ab1a-696f-5c51-9694-ad993d3a766e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection,
8df0d540-2d12-5926-9764-513f6d86abdf | note | Conformance Criteria - Pull-Out Test Schedule <80% min ULT load
9052ffb9-42c5-5bfe-a01c-ad4b83521739 | note | Records - Pull out test log
| checkpoint | 25 - Ground Anchors - Pull out Testing
c0848f19-1c47-53e7-ad59-32e2a7a140fe | note | ACTION (Hold, Monitor, Witness) - H
fc4b9612-9c78-592a-9177-d7758092dee1 | note | Detail - Pull-out testing shall be carried out on one sacrificial ground anchor, The pull-out test shall be done at a location and elevation agreed and approved by the Engineer.
0ccc369a-e70f-502b-90b7-dab263676976 | note | Frequency - Prior to installation of anchors
23165f9b-d872-563f-ac15-7c1d39a6f02a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
51df7fbf-9c25-5ee7-8e3d-0c1f0eb4c433 | note | Conformance Criteria - Conducted prior to installation, Location approved by CPS Engineer
8f9da01f-59a0-54b0-9285-b3f3f439dc29 | note | Records - Pull out test log, Submittal
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 26 -
1b4cd79b-d010-5c72-ac02-fbb12db6e73b | note | ACTION (Hold, Monitor, Witness) - M
a4b9f5d4-5e26-5dc5-96ae-d9c561ad62fb | note | Detail - The pull-out test shall be carried out to 150% of the Design Working Load (DWL) and the contractor shall supply a larger anchor rod (if required) to safely accommodate the maximum test load. Anchor movements during the Creep Test shall be measured and recorded.
542c89c1-b9e4-5dcf-959d-71a265c19e44 | note | Frequency - During Pull out testing
2c5fd92d-0527-586a-8b0d-bbebe831b383 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
de4e9419-72a2-580f-aff3-aeebf5858960 | note | Conformance Criteria - Refer to the Pull out test schedule
3c0c90d1-80ba-571f-8ab9-6a58625b8386 | note | – – – – – – – – – –
7b3e90b5-8f1a-57d4-8dc1-5d422810f2f0 | note | Pull-Out Test Schedule
f9892107-25ef-5ca5-a7ae-ceea6e51dd8c | note | – – – – – – – – – –
7470e92b-8d1f-5640-b9a0-0f6f599116cf | note | Load ¦¦ Hold Time
d8b17642-48dc-5c4b-903a-900a3ec5154e | note | – – – – – – – – – –
2f6e071a-8fc2-5117-9d0d-1bdd134f8dd8 | note | 0.05 (DWL) ¦¦ 1 minute
8829115e-7466-5f6b-a2af-ba6c7e439892 | note | 0.25 (DWL) ¦¦ 10 minutes
831c2d3f-01f0-5aaf-9076-953572340431 | note | 0.5 (DWL) ¦¦ 10 minutes
fbf79713-e465-5a23-a91c-14548ebf65ac | note | 0.75 (DWL) ¦¦ 10 minutes
5c490679-4bdf-511b-b15e-5f1b92ebb615 | note | 1.00 (DWL) ¦¦ 10 minutes
0ac3d99a-3a8a-57d8-a573-df0d7389105d | note | 1.25 (DWL) ¦¦ 10 minutes
7a37a96a-f911-5060-acca-926afca8d64b | note | 1.50 (DWL) ¦¦ (creep test) 60 minutes
18bd9e0e-07cb-5b71-a553-b8b617cbf99f | note | – – – – – – – – – –
1a9e7757-097c-538d-88ed-abb69aa7b7b1 | note | ○ Recorded at 1, 2, 3, 5, 6, 10, 20, 30, 40, 50 and 60 minutes
f9c3414b-f49b-52ab-9216-77e1aef85beb | note | ○ Maintained within 2% of the intended load
1862245d-736c-560d-a421-6d15ddfc86d0 | note | Records - Pull out test log
| checkpoint | 27 -
ddb258e7-bcb2-5cbe-9fbd-fbe79e6a2f10 | note | ACTION (Hold, Monitor, Witness) - M
121764b5-38a9-5b61-a6b5-86c0bd7b0f15 | note | Detail - The alignment load (AL) should not exceed 5% of the DWL. Dial gauges should be set to zero after the alignment load has been applied.
12e384e0-a4ce-5ce3-9f79-d8aa2bd4a43e | note | Frequency - During Pull out testing
1d54a500-1ed7-56d1-b9ef-5581f5dacc4f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
689b321a-59ae-5654-aa0e-d50470ef67f8 | note | Conformance Criteria - AL not exceed 5% of the DWL
16e597a6-f366-51e3-912f-e2577f6a242b | note | Records - Pull out test log
| checkpoint | 29 -
6264c0bc-19ff-5244-b4d8-ef3d180442db | note | ACTION (Hold, Monitor, Witness) - H
2c1b77bc-8df5-5ced-afb3-80c54f103604 | note | Detail - The results of the pull-out test, along with calculations and their interpretation shall be forwarded to the Engineer
f20d9c7f-e9ba-5f3a-a95a-24301428d3c7 | note | Frequency - During Pull out testing
73d046cf-3f09-5a0d-93e6-08ab74afca09 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
48660374-2d8b-5db0-ba74-fa7f79370313 | note | Conformance Criteria - Engineer to send through approval within 48 hours of receiving results
f8e1f522-2fea-5dc3-8eed-b03062cdbad3 | note | Records - Pull out test log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 30 - Ground Anchors - Proof Testing of Anchors
16635a30-06b1-54ce-92d7-0d4c117b3d10 | note | ACTION (Hold, Monitor, Witness) - W
6fbec8f5-31df-5715-9af2-da94df6a6fe7 | note | Detail - The proof tests shall incrementally load each ground anchor in accordance with the Proof Test Loading Schedule and in conjunction with the specifications 5.7.3.3
0b4520d1-c3e3-57ea-b3c5-0ea02d570d36 | note | Frequency - During Proof testing
eabf1fd8-93be-5153-b05d-3e566676e974 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
80d9320b-83ff-5b38-9c1e-82d52ba140e0 | note | Conformance Criteria - Proof testing completed on two anchors as selected by the Engineer
d1a8ad24-6401-5a1e-9a09-91f4f8f96650 | note | Records - Anchor Proof test log
| checkpoint | 31 -
44418fca-a711-5994-92dc-8fc3e1eecc7c | note | ACTION (Hold, Monitor, Witness) - W
464ad6a3-4af4-5aec-ad3d-567b106cee7d | note | Detail - The maximum test load in a proof test shall maintain a constant load. The load-hold period shall start as soon as the maximum test load is applied and the ground anchor movement with respect to a fixed reference shall be measured
fc9f46c9-605d-548c-bb38-03a1e2b8cd59 | note | Frequency - During Proof testing
76ee0662-0767-5519-bafb-42245bd4e6c4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
ed3cc313-4ce9-5ce3-bd08-91a89bc93899 | note | Conformance Criteria - recorded at 1, 2, 3, 4, 5, 6 and 10 minutes. If creep test up to 10 minutes exceeds 1 mm, the maximum test load shall be held for an additional 50 minutes
eee934ef-9c31-5b2a-98b2-700f9f11bcc3 | note | Records - Anchor Proof test log
| checkpoint | 32 -
11a818b3-cb13-53fd-a3f2-ed3ee19e35f1 | note | ACTION (Hold, Monitor, Witness) - W
39266888-6081-5583-b508-7616133a308c | note | Detail - The remaining anchors should also be tested to the same methodology up to 1.00 of the DWL unless approved otherwise by the Engineer.
c1033b36-6f86-5ce5-8939-463d123f08eb | note | Frequency - During Proof out testing
368ce410-e02a-5a3f-a867-426df28cfc2e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
884d8ec3-4d52-5049-afff-2f5c03036420 | note | Conformance Criteria - Total movement within the 10 minute hold is less than 1 mm between 1 and 10 minutes.
e30f5b3c-bdbc-532b-9c5b-bc7e49b3918a | note | Records - Anchor Proof test log
| checkpoint | 33 - Survey As Built
e048e06a-612a-50fd-bd7d-d5f01d1b9a15 | note | ACTION (Hold, Monitor, Witness) - M
8ead4107-8a60-52db-ac2d-05806a6a219e | note | Detail - Survey final position and R.L. of each anchor, produce As-Built drawings
ff5c8b89-b6cf-5e6e-a0e8-9ea18f27d811 | note | Frequency - Each anchor
17bb6571-bdb1-54ed-9c8a-f8bb81c500eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
254ec04e-6f45-5e54-88c1-a8d0a09a1df0 | note | Conformance Criteria - As-Built Drawing
151042a5-92e3-57c1-8f90-effe2db75a6b | note | Records - Survey receipt
| checkpoint | 34 - Lot Number QA File
6b639507-409f-5a70-8258-46d9dc5ade30 | note | ACTION (Hold, Monitor, Witness) - M
6caca58d-f01f-5f81-8431-dc1cb59eb796 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
50367b3c-6403-5f06-aff3-bd713d19f811 | note | Frequency - At completion of Lot
462cc030-b92b-5de3-8d3f-b618f543ed24 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4cdaca21-67b6-5f12-a594-c76f0ba91de0 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
f41a7b0b-add1-52b1-849b-cf063436b679 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 35 -
b25338ad-0609-5c85-8e42-1b868b72aa02 | note | ACTION (Hold, Monitor, Witness) - M
67656e4e-dcd0-5368-897f-3a65ac79baf8 | note | Detail - Check all anchor records are completed and signed by the relevant signatory.
3e56608d-10a8-530d-ad23-c5096ef8d8f8 | note | Frequency - At completion of Lot
b3d5e95f-60e1-5441-bbd7-9866314ad191 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
67759f6e-b607-5ab8-b293-c55b43d994e8 | note | Records - Document Review
| checkpoint | 36 - As-builts
a41a1fac-b9ee-52c4-958d-fdb2c096e4d6 | note | ACTION (Hold, Monitor, Witness) - M
701d61cd-9257-5d57-be02-51e40e66f052 | note | Detail - Red pen mark up drawings to be included in QA file
8ecbb795-857e-5fa9-a3f8-3ce3978a18df | note | Frequency - At the completion of the Lot of work
9a0b2271-28bb-5de4-95ab-a01b4ef12178 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
b6b6abae-4cdb-5872-849a-97f2f780c9de | note | Records - As-built Drawing
| checklist | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | itp | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill |  | e4173bd3-2a17-4f67-a764-abb84968d108
| checkpoint | Project Site reps.
b05bfea2-e0b7-5f61-8c49-5d042c7c60e3 | textbox | CPS Eng.
2a96be31-b54e-5467-ab2a-acc26ff09fb8 | textbox | Site Engineer
9523ca51-cedf-51f6-b92b-a3000d53ae21 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
4329d3f1-4b6a-5892-9547-9a0f90d2a381 | note | ACTION (Hold, Monitor, Witness) - H
c21a4a29-a1b4-5e39-b963-a7b3c84f0af2 | note | Detail - Contractor to set out grid lines as per contract drawings and specification.
d58a3b52-34a9-58d7-a9f4-ee2ede24f51c | note | Frequency - Prior to commencement
94bdf949-1ed0-56cd-9cfb-75b2850f63f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
96aa777d-2a26-5a0b-806f-642e623a6159 | note | Conformance Criteria - Consistency with Construction Drawing
347d4a71-ea6a-5ffb-be0a-6c783b67fce9 | note | Records - CPS Engineer Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Timber Lagging Material Compliance
99f774ff-b79b-537e-a6f6-d519ac5d6b22 | note | ACTION (Hold, Monitor, Witness) - W
3c299ef5-2e78-57c3-b5d9-2613ceac7dd2 | note | Detail - The lagging must be radiata pine planks of normal density, All.
1b3fa55d-b042-5189-b930-719eef1b0f6a | note | Frequency - Prior to commencement
2f99d6e6-8e19-5156-851d-d86a7b3e25e2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
f5ce0e92-067c-5d91-b5f9-99e8f30e5bd0 | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance:
8b0a0c81-56c8-56de-9b64-abebe3525eb0 | note | ○ H4 treated in accordance with NZS 3640, H4
46770623-7dd9-55cb-ba55-0ecb428a2f6d | note | ○ Cut ends or notches shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative
2e35b755-49ca-5060-9a13-eb9326c0c6a1 | note | Records - Material receipt
| checkpoint | 3 -
0ddf14af-6f5a-5b5c-a939-ef4b99798bc7 | note | ACTION (Hold, Monitor, Witness) - M
74a967be-0a93-54a3-86ed-9fd2fdb6bc1f | note | Detail - Each section of lagging shall span a minimum of three poles.
f66c9a7c-658b-503f-ac4d-dd64eaf6791c | note | Frequency - Prior to commencement
b9ccd96f-5734-5aa3-819b-004e58e205f7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
32b940f8-8ad0-53db-b891-43af5148d2e5 | note | Conformance Criteria - Inspect and document span of lagging
9c06dd49-6bac-549d-870d-8f66691c8224 | note | Records - Photos, site inspection
| checkpoint | 4 - Backfill Material Compliance
23053c83-4c80-5e82-9862-a0a3cdbe72b8 | note | ACTION (Hold, Monitor, Witness) - W
d6ed38bc-b61c-55e0-8123-0a756136f2c9 | note | Detail - The granular aggregates for use behind the wall shall be open course graded clean washed durable aggregate
e4fd072f-9332-577a-b541-c9746f17b857 | note | Frequency - Prior to commencement
ad5eb9f2-1ab1-5817-b844-016668c91027 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
5aef291a-5655-58aa-ae3e-583ded8fea9f | note | Conformance Criteria - Crushing resistance of not less than 100kN when tested in accordance with NZS 4407:1991
24d1d6d6-b0bb-5b50-bc61-d73d28fe48d4 | note | ○ Be crushed aggregate with a min. 50% broken faces (NZS 4407 Test 3.14);
1b01c5b9-3738-5b8e-b3e8-a2f7e7837b9c | note | ○ Free of organic and other deleterious material; and
3ec77809-f86a-5308-a70a-d80525bf011d | note | ○ Meet the particle size grading envelope outlined in the specifications table in drawing C200
a3443625-de32-5127-8b35-ed1a8923fedb | note | Records - Materials receipt, test results
| checkpoint | 5 -
9cf87e2b-8ed0-5292-a5c8-3f13d65c9c26 | note | ACTION (Hold, Monitor, Witness) - W
155ece68-d31e-51ca-9a64-c33726bbb039 | note | Detail - The Contractor shall test a representative sample of the proposed granular aggregate to be used to determine the maximum dry density and optimum moisture content, standard compaction and the particle size distribution
386e1c5d-cd6b-5949-a229-cea7f27bf273 | note | Frequency - Prior to commencement
f63686f6-5b95-5ab3-92f0-7a103a092397 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
945b033a-1387-503b-81ef-c41cfb22d131 | note | Conformance Criteria - NZS 4402: 1986 Test 4.1.1, NZS 4402: 1986 Test 2.8 .2
31790dc4-39c0-5b67-bb7e-ac2113c36520 | note | Records - Materials receipt, test results
| checkpoint | 6 -
0c1e874b-9c14-5a5e-8fa4-12783569fd50 | note | ACTION (Hold, Monitor, Witness) - W
d572b8a7-1c8a-503a-b9f9-c3d9f7408fe0 | note | Detail - The test results shall be no older than 3 months so that they represent the actual proposed materials.
edfe4dcc-4982-5dd6-bb56-bdb5ecfc913c | note | Frequency - Prior to commencement
5d9982a6-9322-5856-b40b-2acb1ddebdfe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
fb1d7ff8-9267-548e-8772-c5e1aceeb341 | note | Conformance Criteria - Check testing results are less than 3 months old
2427b484-4b7f-5e72-869b-52a2ce9215fa | note | Records - Materials receipt, test results
| checkpoint | 7 -
936002f7-7ec5-56cc-9c99-20d9ced3c6a0 | note | ACTION (Hold, Monitor, Witness) - M
e5407c15-61c0-5592-ab4a-56f30e6b0dda | note | Detail - All material sampling and testing shall be completed by a suitably qualified laboratory and laboratory personnel
0b5648c0-8252-57cc-b36f-1d06255b68a7 | note | Frequency - Prior to commencement
ca460067-51d7-5f21-980b-60b8e36b4169 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
152845bf-694f-5823-9ad5-f7539bcb8193 | note | Conformance Criteria - IANZ registered laboratory, laboratory certified to ISO 9001 or 9002
773c0a4d-190b-56b9-ab56-7f4350ced8b7 | note | Records - Certification
| checkpoint | 8 - Geotextile Material Compliance
c1985ada-a9d8-510a-bedd-fbacc49414c4 | note | ACTION (Hold, Monitor, Witness) - W
c3a6cacb-3758-5b4b-9c5e-c09354bf0653 | note | Detail - The geotextile filter fabric lining the excavation and wall, Examples of acceptable materials are 'Duraforce AS410' and 'Bidim A29' or similar approved equivalent.
27ac0d5d-6938-56d8-a42d-a43252f70acb | note | Frequency - Prior to commencement
bc3d112c-d1b9-5a26-9f39-5f79d87c9878 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
8debf3f3-59a2-5ad3-971f-0c4e757f0868 | note | Conformance Criteria - non-woven geotextile and meet the requirements of TNZ F/7:2003 for strength Class C and filtration Class 1
53858759-a35b-5dd2-80f3-f107a68827e1 | note | Records - Material receipt
| checkpoint | 9 -
87be8b32-3956-517b-b7dd-2bb94b2512ca | note | ACTION (Hold, Monitor, Witness) - M
1ce60f18-6c5f-5b19-b242-69d28a1ff722 | note | Detail - The geotextile's properties, testing, storage and installation shall comply with the requirements of Transit NZ
ec4bfe89-a947-5b2d-85cf-0f4536dd2ad9 | note | Frequency - Prior to commencement
d69eec38-ab1a-51a5-a474-55dd678455a4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
5ab17b54-faff-570a-b4e0-5edd8aba0999 | note | Conformance Criteria - TNZ F/7:2000
89586a6d-81f7-5d79-a461-d170221d1446 | note | Records - Material receipt
| checkpoint | 10 - Subsoil drainage Material Compliance
98f825df-5442-56e6-adc9-6a3881ef930d | note | ACTION (Hold, Monitor, Witness) - W
6310b2ec-61d2-52d8-9398-7d5977d25be9 | note | Detail - The subsoil drainage pipe shall be smooth bored, perforated 110mm dia. HDPE or PE complying with NZS 7604:1981 and TNZ F/2:2000. The perforations shall be circular 6.5 mm (+1.5 mm) in diameter, arranged as shown in the Appendix 1 of TNZ F/2:2000, “Pipe Subsoil Drain Construction”.
6e532b45-080c-52f0-b1a6-7284b2082b9e | note | Frequency - Prior to commencement
a422761f-1118-5020-9c35-ad288e4b383b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
71408f06-e6bb-5e40-8ab5-3a81f518859b | note | Conformance Criteria - complying with:
07c6ae30-b833-582c-98a1-fb3bfae112b1 | note | ○ NZS 7604:1981
7941c2af-c3f3-532a-b427-fbfc4cc571e1 | note | ○ TNZ F/2:2000
04ef69ca-f686-54a1-aa34-5bd7e6e45f24 | note | Records - Material receipt
| checkpoint | 11 -
425308fa-d004-50c0-bdee-289e1de85a8d | note | ACTION (Hold, Monitor, Witness) - M
d020f1bf-e6e1-5dd7-b0c5-11ee4656a1c5 | note | Detail - Outlet and connecting pipes shall be unperforated.
89301b0d-2b01-53d1-9788-7e3d3a143023 | note | Frequency - Prior to commencement
782b02b3-647d-5fcb-9891-c103bce845a0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
cdd21bdf-985c-5c7d-871c-eb957f6a100b | note | Conformance Criteria - complying with:
428e18d5-93dd-5a24-b98d-fce5facd5339 | note | ○ NZS 7604:1981
4ee6774d-7c2a-51ab-a54c-8a9615a8c36f | note | ○ TNZ F/2:2000
74152d46-a8e8-53dc-ae8f-54075201fc1c | note | Records - Material receipt, site inspection
| checkpoint | 12 -
9e1999fb-fb8e-56bd-a1f9-a66c8723e89c | note | ACTION (Hold, Monitor, Witness) - W
0d5f8085-0a2d-5c8c-9167-561aaf565239 | note | Detail - The drainage pipe shall be wrapped in a drainage blanket geo-composite, such as 'Filter sleeve' or equivalent approved.
4e990a0c-a7a7-5055-bffc-b15493b846d6 | note | Frequency - Prior to commencement
cd165d5c-bb17-572a-be96-dd09181ea6b4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
fad49e43-0c8d-56dd-ba5a-80f5359d9100 | note | Conformance Criteria - Confirm drainage blanket before install
0f2d605f-e2e9-5586-9168-b1835238ffd5 | note | Records - Material receipt, site inspection
| checkpoint | 13 - Timber Lagging Installation
a635a422-c016-5076-8694-6a6b74affb26 | note | ACTION (Hold, Monitor, Witness) - M
0a59807b-740e-5e8e-be58-747cf855959f | note | Detail - The timber lagging shall be placed against the back of the poles so that they fit closely to the poles and to the lagging board below. Only lightweight compaction to be used within 0.5 m of lagging with care to avoid lagging deformation.
db68d73b-1622-5dca-afd6-9da1b201491a | note | ○ All lagging joints shall be located against a pole. Lagging joints shall be staggered so that there is a continuous lagging board above and below each joint.
f76fa834-f0e8-56aa-bdfe-e0bbdee97b0f | note | Frequency - Pre/ During install
0b5e4d3d-2e71-579c-ab4c-94f86c9805f9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
eeee478b-e909-59b0-87ae-2b1806f95a21 | note | Conformance Criteria - Confirm lagging is placed correctly, and no heavy compaction conducted within 0.5m
ad15b6b9-7d06-522d-a31c-a864b081a615 | note | Records - site inspection, Photos, log
| checkpoint | 14 -
cc9695be-0b06-5c3a-a311-1d712921f8d6 | note | ACTION (Hold, Monitor, Witness) - M
ca6dda3d-1aea-5efe-b704-6ea460ea8a4e | note | Detail - The lagging shall be held in place using screws. No boards with obvious defects shall be used e.g. severe warping, knots etc.
694dba47-dbfc-5132-8698-a9b9a46ce969 | note | Frequency - Pre/ During install
654701fb-66b7-57d7-966e-672cd9aac491 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
53820310-ee37-5364-a092-33b461ef6f2b | note | Conformance Criteria - Confirm and document screw installation is correct and lagging timber is appropriate
73ca901b-1876-5f27-bdf0-2f2761b4645f | note | Records - site inspection, Photos, log
| checkpoint | 15 - Geotextile Filter fabric installation
5075f4ec-0ae6-5f15-bd80-b3882c580a66 | note | ACTION (Hold, Monitor, Witness) - M
9d061467-9ed1-5a5e-aae1-2a3a3e984933 | note | Detail - Geotextile filter fabric shall be placed in the locations shown on the drawings. At joins the fabric shall be overlapped by a minimum of 200mm.
9b9a7aa7-ab0b-5ac3-9a5b-171648cb1a10 | note | Frequency - Pre/ During install
bc28438b-1578-5726-97b3-2ce0a2d3dffc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
90c45369-f62a-5965-8f50-1ab5cf5065d7 | note | Conformance Criteria - At joins overlapped by a minimum of 200mm
690d8337-9de8-5ed3-871a-63093074b164 | note | Records - site inspection, Photos
| checkpoint | 16 -
3c55b368-725c-5aaf-86b2-c360c1f8ec5f | note | ACTION (Hold, Monitor, Witness) - M
9dcc0ac7-1354-5e84-8341-a3fed103d55d | note | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area, with a 200mm overlap on all sides
0c57c9d2-f624-5807-b96c-1d5217f2b0d1 | note | Frequency - Pre/ During install
5c628d35-a8cd-568a-9839-41f69bdf3c48 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
fb9229c8-a2f3-576c-b5da-05a7de54588a | note | Conformance Criteria - tears shall be repaired by contractor, overlapped by a minimum of 200mm
b615a9c4-7287-5011-80dd-96d748a8ea43 | note | Records - site inspection, Photos
| checkpoint | 17 - Subsoil Drainage
2b436e13-f6d4-5b56-b741-e05eb0562cc8 | note | ACTION (Hold, Monitor, Witness) - W
b89d01d8-1eb6-5b4c-8785-7abd4d06570e | note | Detail - The subsoil shall be placed as shown on the drawings. Outlets from the subsoil shall be constructed to discharge water clear of the site, onto stable ground, with sufficient fall across the length of the subsoil pipe to prevent silting.
a1b40941-d41d-5ee0-b984-a8f56341f93d | note | Frequency - Pre/ During install
7c3af5ce-9b67-5bf7-bc5d-2a14cf3d8687 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7f7616a2-f76b-56fa-98de-09d59730aa51 | note | Conformance Criteria - Outlets from the subsoil shall be constructed to discharge water clear of the site
16e67474-8c45-55ad-8d25-b9082066aa37 | note | Records - site inspection, Photos
| checkpoint | 18 -
a589d508-f4c5-518e-b9b3-b9df08cf53fe | note | ACTION (Hold, Monitor, Witness) - H
0f274aa9-746f-55d3-a628-a7e571a2d542 | note | Detail - The location of the outlets shall be determined in conjunction with the Engineer on site
1d6369d8-d627-5516-9af5-9fa2a1d8e27c | note | Frequency - Pre install
eb87262a-f602-56f3-887b-2c06187a55b7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document review
9f9a94a1-4ce6-558a-a9e2-e3a42557e624 | note | Conformance Criteria - HOLD POINT: CPS engineer to review and approve location of outlets
65b9d6a3-258d-5998-bc26-d48fc7dbe62e | note | Records - CPS Engineer Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 19 - Retaining Wall Backfill
86509298-765d-55c7-b502-036dad0e36d7 | note | ACTION (Hold, Monitor, Witness) - W
3ba880b4-369f-51e7-acba-a89d3f81eac5 | note | Detail - The Contractor shall ensure that the method of placement and compaction permits safe labour about the excavation.
52675688-027e-56b7-8f50-3752a92af42d | note | Frequency - Prior to commencement
97dc0b60-6f2e-5703-9aee-4f3963c71de8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
f2c26d0f-55c3-5691-993e-70c581e5c25b | note | Conformance Criteria - Temp works confirmation for excavation area, for placement and compaction
731e0261-8ba3-570b-b337-178aac7176c6 | note | Records - site inspection, Photos
| checkpoint | 20 -
cb343e8f-29c7-54a5-bba9-779308cf3652 | note | ACTION (Hold, Monitor, Witness) - M
314e56dc-c805-572a-8b75-5f73fd6fd58a | note | Detail - Lightweight compaction shall be undertaken within 1 m of the wall face, to prevent damaging wall components.
5647a9f0-6bc9-5307-8eca-29ec342a2831 | note | Frequency - Pre/ During install
aa9a3dae-1bdc-5c10-976c-e493f8e4fcfc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c1078d49-f3d1-5fee-8589-549b69d85c0f | note | Conformance Criteria - Not heavy compaction works within 1m
58b9ae4f-3fa9-5679-9c98-85ce6f06415c | note | Records - site inspection, Photos
| checkpoint | 21 -
e71d75f6-db7e-59f6-a42a-d9957620ca2c | note | ACTION (Hold, Monitor, Witness) - M
c746a2e7-2b49-5596-96b9-a6b941b42a24 | note | Detail - The backfill material shall be placed and compacted in layers of no more than 200mm loose depth. Each layer shall be compacted by hand operated mechanical plate compactors, heavy compaction may be used from 1 m behind the wall to aid compaction.
8731b274-466a-5971-b504-7e2a7086163c | note | ○ Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
4c7f24db-06ce-5e16-9ea5-959d69d3c414 | note | Frequency - Pre/ During install
4d1fd0f3-2dc9-51bb-82a7-a7cf6f87e2e8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
afb098b9-f4f7-5016-ba03-9e1388df5b3a | note | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
50f90d85-cc5d-5656-bbef-c02f4dddcc7c | note | Records - site inspection, Photos
| checkpoint | 22 -
f49bf372-aa4f-5413-a427-bf06584b18ef | note | ACTION (Hold, Monitor, Witness) - M
793b562b-0201-5fe3-b38a-7c6d922a3c5b | note | Detail - 1m behind the wall compaction requirements vary from within 1m. But Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
d0d3250b-271e-5f1c-bbc7-ede58b4d3dec | note | Frequency - Pre/ During install
ee1deeb6-a60b-533f-9943-3f4ee4866c13 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
417a8204-4ad4-51ca-9cea-963ab023e9d3 | note | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
446d5e87-c759-559e-b25f-8d09d07c8a35 | note | Records - site inspection, Photos
| checkpoint | 23 -
fedba573-c4bb-51f6-b10d-53cf12018278 | note | ACTION (Hold, Monitor, Witness) - W
73eab55f-f099-504e-93a7-7c7f78cc0536 | note | Detail - At least 3 sets of at least 5 NDM tests shall be carried out, Back-fill shall be compacted in layers no greater than 200 mm loose 'lifts'. Clegg Hammer tests shall be conducted every second lift along the length of the wall.
4dc9278f-96d2-54a2-b233-61d458646b1b | note | Frequency - During install
2f328b11-170b-54b5-a9cc-b65892b94857 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
51467152-ba2a-5325-ae6f-e36a90a37708 | note | Conformance Criteria - l 3 sets of at least 5 NDM tests
658f2408-24cd-5cf2-9c66-1beaf70a83c8 | note | ○ Carried out at approx. 1/3, 2/3 and finish level.
37f43e8e-1ccf-56d6-bf42-f979fc9ad229 | note | ○ Results shall be forwarded to the Engineer within 24 hours of the tests being carried out
dfe1bc85-05f7-5745-99f1-320d69ef597e | note | Records - site inspection, Photos, test results
| checkpoint | 24 - Subsurface drainage
05e2d470-b159-58e5-b65e-70beb3e3c710 | note | ACTION (Hold, Monitor, Witness) - M
fb709d71-9b06-5f60-9cfb-4ecda70b4f75 | note | Detail - All the surface water should be diverted away from the proposed retaining wall.
7a60a9ba-9256-5359-8b68-61b00eb8661c | note | Frequency - Pre/ During install
91b520ee-e5c8-5f1d-be6f-6891b4ca48af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a7127de8-4e21-5dca-a89b-d6bc613d713f | note | Conformance Criteria - Subsurface designed on site in a way to ensure surface water is diverted away from the retaining wall.
da2106af-2c82-54a7-8534-6041685bf2b1 | note | Records - site inspection, Photos
| checkpoint | 25 - Survey As Built
2055fb05-7dd8-50d8-a9b2-9f8e8a83325a | note | ACTION (Hold, Monitor, Witness) - M
66f2b5e1-95cd-5f03-a256-72a7558bfe06 | note | Detail - Ensure all works comply with design prior to carrying on with next construction process
9007b607-ea8f-514f-98e7-6a1122dffb8a | note | Frequency - At completion of sub soil drainage line
59bd4bcd-4a76-5d9b-8677-359550ddbb79 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
a8a86f5d-9ec2-524e-b115-fac809a4154e | note | Records - Survey receipt
| checkpoint | 26 - Lot Number QA File
6a8f9592-6196-5512-800a-bf2b76954b7f | note | ACTION (Hold, Monitor, Witness) - M
75c03242-6f66-5f36-82b3-88029f4bf65f | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
1873fe6c-886a-5247-a522-3575abd4c444 | note | Frequency - At completion of Lot
b743ee8e-48e0-58ae-a41b-241c1c5b36a0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1266a891-6783-5a8e-80dd-1720b3479860 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
3b403cf2-21a8-5800-ac79-c1fdd684725a | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 27 - As-builts
0efbfb4f-4a08-520a-a507-bb4f060cf59b | note | Detail - Red pen mark up drawings to be included in QA file
09730124-cc66-5576-b4cc-600d0ac85f98 | note | Frequency - At the completion of the Lot of work
74271c37-7ade-54a3-90b0-e0ac0b2580f1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
b996e380-26be-5920-a949-63d25944c0b4 | note | Records - As-built Drawing
| checklist | Ω (Deprecated) ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt - Surfacing (AC 14) (old version) | itp | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt - Surfacing (AC 14) |  | bc91395c-3574-4df1-817b-1c6ed833c600
| checkpoint | Project Site reps.
dd97d2f3-04f3-5375-946e-99945aa9c3ad | textbox | CPS Eng.
88de46ff-3f8c-5f16-8eaa-9a46471fcdca | textbox | Site Engineer
88ec92cf-f25e-5055-8cfe-ac9595f40975 | textbox | Quality Eng.
| checkpoint | 1 - Installation of Erosion and Sediment Controls
ec3706ea-3787-505a-81c9-56f74b80688c | note | ACTION (Hold, Monitor, Witness) - M
5cf6ba6b-7d9d-5988-9c81-a36b50cf1180 | note | Detail - Monitor effectiveness of the ESCP Controls throughout the construction process
f885ce89-7ae8-5944-a5ab-028cb75328ae | note | Frequency - Prior to commencement
07ba551a-83cc-5d80-867a-b877fbc391cd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e2c303ef-e489-5dcd-95af-2df7c1385e5b | note | Conformance Criteria - Visual Inspection
| checkpoint | 2 - Survey Setout
45c22153-d3c7-5732-a6e1-76d70a5c46d2 | note | ACTION (Hold, Monitor, Witness) - H
3fb8d337-2268-59c2-9fbd-401a98e1e80c | note | Detail - Set out pegs installed every 20m if required
e1a024cd-8830-56d8-b74c-463694515b6b | note | Frequency - Prior to commencement
7d63004f-9404-5478-9d68-cc5ac765a900 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
b38ec1c0-1250-5999-9e8e-60d80bc20c32 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 -
cf030fc0-539e-57c2-9058-a4570f913722 | note | ACTION (Hold, Monitor, Witness) - W
97bc7611-ea62-550f-9910-07db8268f789 | note | Detail - Determine paving run start/stop locations
6eb93131-fcfd-53e0-a9fe-f546539dae20 | note | Frequency - Prior to commencement
03adaaeb-584a-5700-afa7-17b64425ef18 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
39fc1a1a-7f18-56ef-8958-74cbcd7faa67 | note | Conformance Criteria - Mark out on site
6556e340-1572-5382-bf54-e46c350660b2 | note | Records - Subcontractor QA Records
| checkpoint | 4 - Material Compliance
8a69f5d4-32ee-53c0-8e78-4ea493b4c891 | note | ACTION (Hold, Monitor, Witness) - H
12bdfbf8-34b8-51bb-9abc-7c44d85698cd | note | Detail - Mix Design approved including peer review
46f0a0d3-62c5-503a-8b53-70af4cc9ca11 | note | Frequency - Prior to commencement
268e3e13-7ec3-52bd-b3ff-ed87bc31e4a5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
98db704d-158f-5d88-a4b0-fe2bfd2bc007 | note | Conformance Criteria - Material is approved by a Notice to Supplier being issued
d5911bc1-7335-5137-86ef-be96f604713c | note | Records - Mix Design
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 -
0969cc3b-1bf0-5226-861f-2f27f0242e1b | note | ACTION (Hold, Monitor, Witness) - H
9f37d8cc-a167-5175-94a8-953bfe64c55a | note | Detail - Asphalt Material Quality Testing
81779b37-9045-55ae-b0e6-2580d0ea7112 | note | Frequency - Prior to commencement
17a7528b-d063-527f-8d77-de93257c6266 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
23b1ddf3-4a4c-5022-8214-978679553f46 | note | Conformance Criteria - Fine and Coarse aggregate Weathering, Crushing, Sand Equivalent, Broken faces, PSD, PSV. Bitumen testing, Penetration @ 25 degrees Celsius, Dynamic Viscosity at 60 degrees Celsius
fbad5d01-45cb-5b9f-abf6-e651f76b0a9e | note | Records - Asphalt Plant Results
| checkpoint | 6 - Asphalt Production Testing
7439643c-f313-57e1-abb0-eabedd485eda | note | ACTION (Hold, Monitor, Witness) - H
1d60bc71-57d9-5755-b668-684eb227b852 | note | Detail - Full volumetric and air voids test 1 test - 1 test per day. Binder content and grading 1 test per 100t.
42eb7b11-0a11-5f30-8ee1-a70b6fde0df5 | note | Frequency - Prior to commencement
e64519ed-9ae0-54b3-98ac-53c883d2f9bf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing and measurements
b86df6e9-cbf9-51a2-b451-80a83d184840 | note | Conformance Criteria - Binder content, PSD, Mix Volumetric, Mix performance related properties resilient Modulus and wheel tracking, mix production temperature and load out temperature
87c7804c-471f-5cdc-8556-59cbaa5ac865 | note | Records - Asphalt Plant Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Tack Coat
0406553e-4558-5ac6-a7a1-fe8a1d2c95f6 | note | ACTION (Hold, Monitor, Witness) - M
483546b9-cd63-5e7d-ba7c-f86e99720e22 | note | Detail - A Spray sheet for every day
b03d475d-157a-5596-9cc2-f21875c343ba | note | Frequency - Prior to placing Surfacing AC
6ec5941f-2cda-5dc2-9a81-05f720674371 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
64940ddb-098c-54bf-ad0b-2f26483b99ec | note | Conformance Criteria - Showing the required spray rate 0.2 L/m2 with a tolerance of +or- 0.1 L/m2
5d255db8-42c2-571e-a7c4-111fcafe9bb9 | note | Records - Subcontractor QA Records
| checkpoint | 8 - Construction of Surfacing Asphaltic Concrete
3f1925e3-2eeb-5781-8bc4-172c00e78e03 | note | ACTION (Hold, Monitor, Witness) - H
d5f70935-e6d0-584c-ae3c-c3f37ca07cec | note | Detail - Site team QA Checks
18d69fc3-8056-5324-845c-67ad586bc498 | note | Frequency - During Construction
e0c1bcb4-8b69-58ea-bbf3-2385d29bdd50 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
96974d6a-4194-58d4-afa4-b8c18e66a1db | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
790f8d4f-2590-5e15-a034-ab893f39fbb6 | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Surface finish visual inspection
794fd98a-5589-584f-b141-224664c0a537 | note | ACTION (Hold, Monitor, Witness) - H
2de6cb83-df27-54ff-b0ce-b302fd806f3b | note | Detail - Site walk over
29dd2d38-0484-5df3-9ea7-cc01065af781 | note | Frequency - Post Construction
ea4c6dd0-0300-5b82-9e2e-03165aabb15d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
58e6a9a3-72b9-5fcc-88c6-8c7658de501b | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
ecd82465-a0cb-5caf-b9bf-2359bb888bf2 | note | Records - Subcontractor QA Records
| checkpoint | 10 - As-builts
bc71e17d-d0ff-5080-8dfd-4e9b6a642d39 | note | ACTION (Hold, Monitor, Witness) - H
2721306e-1a0b-5f12-bcd4-792ebf10d6fd | note | Detail - Red pen mark up drawings to be included in QA file
47d8243c-57cd-536d-8916-188e9691113c | note | Frequency - At the completion of the Lot of work
d522578f-81cb-5827-9186-24e1f012acbf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
19f28616-a1d2-5580-b442-07f90c313ccf | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Quality Assurance deliverables
f56a7804-4f46-5c48-84c0-4c1bc5f8db33 | note | ACTION (Hold, Monitor, Witness) - W
36678925-3bc1-57d0-8d5d-3a37bb9ce273 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
499a7f78-8f05-5973-834c-20b2820f4305 | note | Frequency - At completion of Lot
d725802e-8896-5317-9388-2d253a24f7f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4dfe398e-0173-5eed-ad61-2a45d3fa1712 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
cdc7d351-8d14-5ace-958a-d14244cc37b4 | note | Records - Asbuilts, NCR's and RFI's
| checkpoint | 12 - Completion Sign Off From Fields Below
502affd4-8d82-5843-871d-ec7f9d9f4fbb | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel (old version) | itp | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel |  | 61fb0043-01fa-4c72-802b-95b80aa741a9
| checkpoint | Project Site reps.
2068c3a5-d340-578f-9ed5-8d470d533164 | textbox | CPS Eng.
ebd1b16b-14c2-53ef-af80-496e7c371c0b | textbox | Site Engineer
c6882f25-ecf7-5955-b49f-560ae08a5412 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
c811ce24-3dad-56a1-9f4a-3aece818902a | note | ACTION (Hold, Monitor, Witness) - H
d932d3b5-e629-5fca-bb07-6e365e432cd1 | note | Detail - Set out kerb line and level at 1m offset to EOS
0ea94e7b-68e0-5441-ba55-a88140bf18cc | note | Frequency - Prior to commencement
ce38bafe-ecdf-5cf1-87e9-14aa3ce5e0c9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
6b618bca-ae7e-51a4-b359-e6b65bf054ea | note | Conformance Criteria - Consistency with Construction Drawing
b26f78a5-951d-5bab-a5a2-a9766cc1f814 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Material Compliance
ea6b5fc4-e799-541c-a0f3-1d68d296043e | note | ACTION (Hold, Monitor, Witness) - H
d82ade8d-4f6d-5a57-b60b-7b9a1d1bd996 | note | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
91ff5a31-51f0-5804-99b6-b9addb8300e3 | note | Frequency - 1/600m3, minimum of 1 per source
a34469e8-1418-569b-81c0-9997027ba93f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
a0cc8f9b-b5c9-5b7f-9505-89ef120709f9 | note | Conformance Criteria - 20MPa at 28 days
6b7caa11-8d17-5744-a015-414a10de6491 | note | Records - Concrete Delivery Dockets and lab test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 -
02479aac-3ec5-5a40-b2e5-da3b71fcde3c | note | ACTION (Hold, Monitor, Witness) - H
21505e53-e4c5-5eaf-ad4d-4aaa74421776 | note | Detail - Ensure the slip form moulds match the dimensions of the design kerb
5b30ceac-6f8b-55e4-a493-063bdc6966ab | note | Frequency - Prior to commencement
1acd2ba3-6971-5b01-9873-be06c9861ed3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
c883785b-c7af-5527-b359-90eb9c585284 | note | Conformance Criteria - Measurements match the design kerb dimensions
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Kerb Foundation
94091e79-3d19-5b02-ab15-af8aa4ce7499 | note | ACTION (Hold, Monitor, Witness) - H
2b5b3535-b26a-597d-939b-724c26ba06ef | note | Detail - Ensure Sub base construction is completed
29aebc11-61ee-5685-ab01-47350539ab15 | note | Frequency - Prior to commencement
285ab1fc-b214-5f5e-939f-962fcf922b3f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
779d61c0-42b2-5305-bcc5-fe57ab272084 | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
6ed7938e-f167-5c29-92fc-fe076c2292f1 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Stringing
ef6aeaa9-533f-5198-8c5e-60c26368db4a | note | ACTION (Hold, Monitor, Witness) - H
90a0a50b-248b-5ede-9de5-149818062a0c | note | Detail - Check weather forecast and avoid adverse conditions
15ff8af8-7c56-5ab0-8c77-18a828be5ac2 | note | Frequency - Prior to commencement
8e739954-e216-5b1a-abb9-dd8ba2a39b4e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
18d243e8-7237-5c17-a9ae-b55a648a6608 | note | Conformance Criteria - No concrete to be placed in adverse weather conditions
76d956bd-0ae5-5c5a-bebc-edf500c16334 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 -
c1b09587-634b-5ef9-9543-c8bfa13e8ffa | note | ACTION (Hold, Monitor, Witness) - W
67c82388-b619-5b2e-b2e2-2caf9524b276 | note | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
f203367b-f8b8-5d55-a626-f6b0b7fb1d7b | note | Frequency - Prior to commencement
f12ace9e-07a6-5f1e-8a6f-1209bcfb4743 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
d1f89205-0ea0-5fda-b827-ea9dbfdea9c0 | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
3bc572a5-e9b4-5d0f-916a-0a896a028565 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 7 -
82796926-c960-5ed5-be47-cfe624593f25 | note | ACTION (Hold, Monitor, Witness) - H
f4a03c9b-f2c2-57d4-b1b3-e4b7bfc216dc | note | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
43c35cad-df23-55eb-9b4f-3cf8f65c7916 | note | Frequency - Prior to commencement
1e6a0494-6207-5ae5-ac16-9497064f47d4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
e3c3d5a5-4115-57f3-80c7-e8809700c09e | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
cf20fddd-a4cb-5e6a-bd0e-5ec10d0fc07c | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Slip forming
68126dbb-f9cc-5fe5-878e-91cd074893dd | note | ACTION (Hold, Monitor, Witness) - H
d28efda9-f1b9-554f-9106-0c008e1f3b9e | note | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
5c7f7a7c-c7db-515e-b2da-edc50e301ed8 | note | Frequency - Prior to slip forming
d0050eb6-121f-5f49-9553-9537f0efc9b3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
10f62909-cf2a-5176-8405-0f9b87937e41 | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
fa39b0b0-bd8b-5764-bde8-6c98172074af | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 -
d04f3a92-a6ac-5a94-93e2-8d6f956f9931 | note | ACTION (Hold, Monitor, Witness) - W
271dda04-c147-5b73-8063-c04d143233dc | note | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
6d8e2dc0-c10a-5d43-b31d-627bd005f50f | note | Frequency - During Slip forming
480c22fd-30d4-5e7a-af44-4c3f27fc629e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
5218d382-78b3-5d86-a972-68edaf0f62e1 | note | Conformance Criteria - To ensure the correct concrete mix is delivered
6ce66b10-8223-5e74-980f-d29c1a60b3d9 | note | Records - Concrete Delivery Dockets and lab test results
| checkpoint | 10 -
df408c63-170e-517d-8832-ce7572900434 | note | ACTION (Hold, Monitor, Witness) - W
4b7d689c-f5c8-5f7b-b542-3adb7e269f8e | note | Detail - Expansion joints to be formed at 5m centres
561c56e4-a48a-5d9b-8def-fdcb47a790dc | note | Frequency - During Slip forming
ca9aa79b-d557-50e2-9613-c53b4ce98c86 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
4563ef5f-700b-5792-a378-50a22f806706 | note | Conformance Criteria - Kerbing Specification
ba4b8b07-cc5b-5b1d-abfb-c5129c1752c2 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| checkpoint | 11 - Tie-in with pre-cast components
8f98a052-decb-549f-a18c-702f2bfb08db | note | ACTION (Hold, Monitor, Witness) - H
c34dfcc9-0f67-565f-8423-dc35a72a0856 | note | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
0d0b7377-715a-536e-94d6-87f0ee8d8060 | note | Frequency - During Slip forming
c9ec5894-a6f6-59ac-b142-437d4c6c403e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
65f7dc66-2fc0-54c1-afec-aaf8f419f320 | note | Conformance Criteria - Consistency with Work Instruction
b1cb43b5-531a-5326-a58b-fc599f2421c8 | note | Records - CS-4045 Kerb Construction Record Check Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Protection
c884ad58-3d7e-5d2b-af00-bb718932d275 | note | ACTION (Hold, Monitor, Witness) - H
c318eecc-fec5-58f0-bcd7-caaf0d46be7b | note | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
a79321b8-685f-59a9-8826-1fa5a3a821a2 | note | Frequency - Prior to backfilling
82e7d284-4875-50a3-bad6-e465a6f6e1de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
024fb1f5-0fbb-5309-9030-0aa4d252d3b7 | note | Conformance Criteria - Backfilling to commence only after 72 hours
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - As-builts
940c45ba-beb8-54c9-a630-d1810802fe54 | note | ACTION (Hold, Monitor, Witness) - H
3fd34caf-c625-523b-89a7-0f20cb0a836a | note | Detail - Red pen mark up drawings to be included in QA file
29ff40f2-53c2-5d90-8e80-3ad862353796 | note | Frequency - At the completion of the Lot of work
fa6564b4-f659-584b-ac9b-d67749252084 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
9f4822a5-7d91-5171-b499-df7cefac04db | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Completion Sign Off From Fields Below
a806c201-1e08-5bcf-8ac2-e604f5e63f3e | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP (old version) | itp | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP |  | 4bdfc2f9-d444-4927-8bc0-f8f80ec25e59
| checkpoint | Project Site reps.
1ada93f4-c708-5341-9c25-0e79dd74edf5 | textbox | CPS Eng.
260594a3-bd8b-53a0-b7cc-e383ec9e1b41 | textbox | Site Engineer
cda3c0b8-07fb-5265-b8ba-76a6c1ab8483 | textbox | Quality Eng.
| checkpoint | 1 - Environmental Controls
308f647f-f405-57cb-90ea-29ead3c21977 | note | ACTION (Hold, Monitor, Witness) - W
4c741b73-aa6c-5f22-ab02-80a5b69f6c88 | note | Detail - Contractor to ensure all the environmental Controls are in place as per EMP
a047754d-53d7-528c-b7c2-f826873f8286 | note | Frequency - Prior to commencement
f47ed79a-1177-54b0-acfc-a87f70bcc773 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f8968fe7-2d30-5825-9144-0bd2cf02b8d7 | note | Conformance Criteria - EMP
39b6be00-c4c1-50e3-84b9-456b8f618cd4 | note | Records - Photos, Site log
| checkpoint | 2 - River diversion (Temp) and Control Drop Installation
2b2ed4d8-f9f1-5bd3-b2c1-619a874482f0 | note | ACTION (Hold, Monitor, Witness) - H
31c3a7e4-53cf-58c5-80b2-32a595e43f29 | note | Detail - Engineer to accept the methodology for construction of the Control Drop point
3f49cada-d25a-5112-ad81-d3aebe3cd138 | note | Frequency - Prior to commencement
2d921a6c-6bdc-57b2-a5f1-80f1a990f8df | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
51191c40-c53c-52ff-9153-dfb19ea3d8c3 | note | Conformance Criteria - Confirmation from the Engineer
daacf54e-daa9-5690-bca7-bc1c48f2586d | note | Records - Emails and site visits
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 -
846a4bc9-7c53-5ef4-a3a0-d45500ce2111 | note | ACTION (Hold, Monitor, Witness) - H
43e3c801-fb84-5640-ace5-a43ce493177a | note | Detail - Location to be confirmed with the Engineer
fc73a85f-2fb0-5559-a8aa-58cdb8df7c40 | note | Frequency - Prior to commencement
dea508fd-0810-549e-a9fa-a06d54ff2f71 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
a428450f-61fd-5980-bc0b-49899a0f09fc | note | Conformance Criteria - Confirmation from the Engineer
7028b2ba-3934-534d-9233-b687978212e2 | note | Records - Photos, Site log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
01f17779-e3b7-55e1-9221-3a45fc3dcffb | note | ACTION (Hold, Monitor, Witness) - W
d0954251-9914-5a97-9f95-09444af97241 | note | Detail - Locate existing services by hand digging
f31f9438-2b7a-5cff-9bda-ed98e63c2a9c | note | Frequency - Prior to commencement
f1887144-0642-57cc-9828-bed4f8172da8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
34d6c3a0-e1e3-5fd1-99f7-cbb12a8f5f48 | note | Conformance Criteria - All conflicts have been located
ddebdf34-85f9-50db-8d94-ea82b2bd4c72 | note | Records - Permit To Dig
| checkpoint | -
b96ce061-f877-5a6c-884a-d28f98bb78cf | note | ACTION (Hold, Monitor, Witness) - H
bb683435-62bb-50d2-9131-e47c9a76a60f | note | Detail - After regrading, Engineer to determine location and number of controlled drops
0213c11f-9607-5ffd-93b1-3ecb559cc666 | note | Frequency - During Construction
eaecadab-ea73-5024-ab87-72cf82720bb6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
8e6ef822-d060-5919-b37d-e75fd250a6b7 | note | Conformance Criteria - Engineer acceptance
eda0c4ab-ea25-53a1-8226-2b10d10a8797 | note | Records - CONQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 -
d6517e2f-6b2c-5086-8a58-dced3e927d57 | note | ACTION (Hold, Monitor, Witness) - H
13e50283-d676-5dee-8874-2ab24a9b18a0 | note | Detail - The engineer shall be notified and afforded the opportunity to be onsite and to direct as necessary as the construction of the control drops
40938287-9705-536e-bb9d-a6d8dc39241d | note | Frequency - During Construction
326489d6-deba-509e-a5ef-c5467fe79b07 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
344ee9b2-2ccb-543b-8117-113152249fc6 | note | Conformance Criteria - Engineer acceptance
cebb7328-ccc1-5668-a6d2-f9cf8b13af92 | note | Records - CONQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Debris Clearance
ff08be04-aba9-5ea8-a5a1-06025ad1b55c | note | ACTION (Hold, Monitor, Witness) - H
29689732-0e68-5c32-9a07-dd8564b55eec | note | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
04c80320-82e2-5ab8-bc60-3916d6aad96c | note | Frequency - After clearing debris
53712a70-0902-50ed-8636-23b5ace73a36 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f53f08d1-d610-59bb-8705-ffd0e0af580f | note | Conformance Criteria - Confirmation from the Engineer
87dc847a-671c-542a-b160-5eb07a71d883 | note | Records - Site visits,emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Stream and Bank Regrade
46e5f81e-71be-577b-8738-3bf3e1d485cf | note | ACTION (Hold, Monitor, Witness) - H
b7cb7664-0db0-570e-a505-9254a1516ed6 | note | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
f258f56f-b7d3-5da3-9668-071c27126f49 | note | Frequency - After clearing debris
2db244fd-c4e2-51de-9689-ee8e401a13ed | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
75d4b918-f353-5782-8aed-4bdf88969199 | note | Conformance Criteria - Confirmation from the Engineer
014d6792-575a-5cae-af56-a2522ebdd277 | note | Records - Site visits,Photos emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 -
f9962e4d-16ac-50db-b97e-a3fe42aeb6fb | note | ACTION (Hold, Monitor, Witness) - H
5df2bdf2-5251-5ca2-8fee-f801e91ebe5f | note | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
a5aff2ee-2d19-5939-92a9-ba0a42be8165 | note | Frequency - After clearing debris
f885acac-319d-5177-b9d0-2a6a5b333075 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
4b1b9fd7-8f46-518c-bf85-dc292d95278f | note | Conformance Criteria - Confirmation from the Engineer
0d50eaaf-58e3-5f70-a5bc-62d2204bd918 | note | Records - Site visits,emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Gabion Basket Installation
68ebc367-49ad-5274-b2d3-7de69440d4ce | note | Detail - separate ITP provided
| checkpoint | 10 - Subsoil Drain
2584ebfe-eb8e-5b8c-991c-1561262573cf | note | Detail - separate ITP provided
| checkpoint | 11 - Parking Bay Construction
efc15218-475a-5937-a47e-bb830aa5f826 | note | Detail - separate ITP provided
| checkpoint | 12 - Kerb and Channel
055bd6ab-b59b-5f30-8539-3654ab898d3e | note | Detail - separate ITP provided
| checkpoint | 13 - Guardrail
893e3bd2-fc05-5a84-a2a2-ee9b5c2db686 | note | Detail - separate ITP provided
| checkpoint | 14 - Swale
445184a9-2783-54bc-9099-372bfd8e18db | note | ACTION (Hold, Monitor, Witness) - H
e57d80dc-e54c-5054-b3b3-12bd8a1ffb47 | note | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
ffe37c95-8f4b-567b-a5ca-210a252938da | note | Frequency - Once the swale is set out.
bb9bee5f-9409-581c-900f-b030e8d9eaf7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
90e6506c-1afa-5a8a-9ccc-adc9c740879c | note | Conformance Criteria - Engineer acceptance
5d95c1f0-892c-5355-83e1-f7bf8133fa52 | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Berm Demolising
36e65d45-034b-5d75-b80c-bea20c0ae497 | note | ACTION (Hold, Monitor, Witness) - H
c6d65483-6eb5-5015-ae4c-9ba163d5ea25 | note | Detail - Final inspection to be done before berm demolision
6354fed4-6e40-594c-871f-08c2157769b4 | note | Frequency - Before Diverting back the River
ccfba7c3-5594-554b-8e1d-9245228ddbee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
51627757-8054-58ab-8b2c-ec39f769f3c7 | note | Conformance Criteria - Engineer acceptance
6749d0a9-fbd9-5361-970d-234b1fac1da2 | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - General Planting
18fe958f-e078-5938-a059-cf8577a6b452 | note | ACTION (Hold, Monitor, Witness) - H
2d43b1a5-fd5b-577b-81f0-4b7beb7eda62 | note | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
0134c1d2-2741-5af8-8d01-1ebb0c123d9b | note | Frequency - During planting
1048f3b2-aa90-55c4-892a-9bc6cfbfbb49 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
14951d1e-de69-5fdd-b6d1-28f767de6b0e | note | Conformance Criteria - Engineer acceptance
f1ef8259-05ee-58ad-9027-5226bb2f28e7 | note | Records - Site visits, emails
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - Site Clean Up
e23ad1d2-3525-54de-81a2-2be3316f8c74 | note | ACTION (Hold, Monitor, Witness) - W
e5a03010-2248-56d1-8f18-e20e2083cd59 | note | Detail - Confirm site clean up is done regularly and all rubbish and trays are taken away.
26fb1c8d-70c4-58c8-9953-1823bccfb9d5 | note | Frequency - As required
0c47ddc9-3dc3-528d-bb04-51e4b7f0a29d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
45ac34cd-eae9-5fb2-9684-c5f60c86eca2 | note | Records - Photos, Site log
| checkpoint | 18 - Lot Number QA File
44a06009-386e-5993-a45e-d083f9ebad82 | note | ACTION (Hold, Monitor, Witness) - W
71424502-3897-5a57-86a9-78a6a85ced40 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
ab2bb467-e49f-553d-8c54-f51f399a8365 | note | Frequency - At completion of Lot
66d9fdca-c437-5072-a17b-1ea8f7af6497 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
75509e4e-5b21-5b05-9fe5-915278c192f5 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
811605d6-e438-5d99-a9fe-5a88a4d4e4f2 | note | Records - Delivery Dockets, Test Reports, Lab Testing Registe
| checkpoint | 19 - As-builts
a94ae467-f6bc-5303-bde4-a599b8479286 | note | ACTION (Hold, Monitor, Witness) - H
925b95ec-9efc-5166-89da-8f5a82865682 | note | Detail - Red pen mark up drawings to be included in QA file
ff1c8bb8-81f0-543d-9295-ca131fdd87ee | note | Frequency - At the completion of the Lot of work
03ef5f47-f8eb-56f8-8f56-3d1c69de8ef5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
dc887fb3-0744-52da-bcfe-bbfb11789200 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Ω (Deprecated) ITP - E3001 - SH05 SIP Generic - Pavement Construction (old version) | itp | ITP - E3001 - SH05 SIP Generic - Pavement Construction |  | 3a1d22fe-c551-4a3f-ae0f-be3fdd2243c4
| section | 1. Setout & Saw Cutting
| checkpoint | Project Site reps.
6ea2e9b0-3e99-515b-8af7-0ff1cc351d4d | textbox | CPS Eng.
a1ccf71d-377d-59ec-a75e-937d152a07fc | textbox | Site Engineer
24b53b5e-8359-54ba-90f2-0bf1919c2e02 | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout
0ee1be7d-466b-5bb0-bda2-fb13d54353a7 | note | ACTION (Hold, Monitor, Witness) - M
30a17514-b305-5d91-95b4-1c6d1d56b912 | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
252d7dc2-2808-547a-84ab-e2a8fde743bd | note | Frequency - Prior to commencement
ca1c2cd4-99d7-5431-a2a4-bec2573cf7f1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
8e8dc048-fefc-5e77-a938-15b5f5fea317 | note | Conformance Criteria -
72a7b585-b5ca-5d22-aa57-24497eee6a17 | note | Records - Survey receipt
| checkpoint | 1.2 - Saw cutting
895c7822-c09b-5446-bf04-565f7b21b767 | note | ACTION (Hold, Monitor, Witness) - H
18983e90-1ada-5aa0-b14d-d3e6023a6578 | note | Detail - Proposed Sawcut line to be inspected by the engineer
8e05daa0-c3c9-5855-a441-ededb80ba7ea | note | Frequency - During construction
c923999d-0696-5e2f-b60e-cdea5b012567 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
215687a8-f104-504d-84df-0947cfe76e7a | note | Conformance Criteria - Project Specification 6.6
9d626d29-a8b2-5f2d-8174-015bf2fc6ed5 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| section | 2. Material Compliance
| checkpoint | 2.1 - Sub Base Material Compliance
b6018eea-16a5-574e-8472-911419491cd2 | note | ACTION (Hold, Monitor, Witness) - H
682ce5b7-8519-5217-a57d-aee6c4127020 | note | Detail - Aggregate material compliance for Sub Base stockpiles
9b14de80-269d-5959-9d8c-2195501696d4 | note | Frequency - Prior to commencement
1c688bb0-7482-59e9-8369-16d1f71cb5e2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
3dd00bb4-298f-5653-96ca-d468c67cadd3 | note | Conformance Criteria - Comply with TNZ M/3 Specification.
93887794-75b2-58c6-bc4b-e3596c7d5ac8 | note | ○ NZTA B/2 Specification Lab test for MDD at OWC
81b800f1-6a6c-5813-ba2e-4b8de6e9fd41 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Base Course Material Compliance
b51447ed-eb37-51b4-a6af-2f8c5e8484dd | note | ACTION (Hold, Monitor, Witness) - H
063e5cf1-bddb-583e-99f4-4b2617b4a1ee | note | Detail - Aggregate material compliance for Base Course stockpiles
94526e72-d168-5bfb-ac84-77a4686b82b9 | note | Frequency - Prior to commencement
b36ecc74-8ff8-5f1c-91fc-e494307d2ad5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
2b71edbc-3376-55b3-9e5d-c2911961c706 | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
0e9e8491-caf6-51e4-a636-af6f3e4d9bf6 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Base Course Mat Sample Testing
99f9ff7b-4ed2-553b-b6d2-fcd8ebc1537a | note | ACTION (Hold, Monitor, Witness) - H
ff0679ab-f699-54e1-8909-833171f8d034 | note | Detail - Mat sampling of Basecourse Material
72b25cb6-8795-5ab8-9ed7-900f72514fc1 | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
7cde541c-7ea7-576f-808a-9d0f142c3668 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
6fd03ea9-009d-5679-847a-3fa7e4fdbd74 | note | Conformance Criteria - Grading to comply with specification
b6021767-392d-53aa-ad87-25ef4de60c2e | note | Records - Mat sample lab test result
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Chip Seal design
6cb76005-ed6a-5b71-9b4e-a401467f532c | note | ACTION (Hold, Monitor, Witness) - H
18a64b26-47b9-5b09-831d-ab9204f52645 | note | Detail - Seal design to be reviewed prior to sealing.
37eeb198-4f90-5ef3-b157-014f36c8bf17 | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
78eaa47c-f9e0-58da-8115-9f85a223f672 | note | Frequency - Prior to Sealing
96fcfd5e-5c5b-5d59-b37e-662741d7538a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
f7dafc8d-a89e-5413-b156-695121c19b3d | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
51776416-837c-5e3c-92c0-81751a00c3f6 | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| section | 3. Sub Grade Construction
| checkpoint | 3.1 - Sub Grade Strength
ae64bb17-e97d-5506-9b11-2f58eaee14a1 | note | ACTION (Hold, Monitor, Witness) - H
cc7399ba-26fe-56b8-a4ef-994e4ca4abf6 | note | Detail - Determine Bearing strength of Sub Grade
a351a4a3-1fda-52b5-a489-f4a0fd20e655 | note | Frequency - After Dig out, every 5m
da115f0f-fa99-52b2-910c-408e78f5c754 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
7898c6e9-a567-5a75-baff-fba901c57fc5 | note | Conformance Criteria - Min. 2 blows /100mm
68b7e438-a634-5b5c-abd6-638ded287e59 | note | ○ 2 blows = 4 CBR
27a2b633-bcae-5404-bb27-86ff5c7600ce | note | Records - QA measurement Sheet, CS-4000 1m Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Proof Roll of subgrade
b8946c21-8e0f-57ff-8b66-049307f9ef4f | note | ACTION (Hold, Monitor, Witness) - H
e5a44703-1ef6-5e00-bb0a-6ac84c81f4a4 | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
ca054a18-e63b-54ca-b637-4de0b2b8765c | note | Frequency - Prior to Sub Base Construction
ad86e5c6-fab0-59ab-a466-93da00a6aeac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d88e0662-448a-57b7-a3c3-d25958f5a551 | note | Conformance Criteria - Engineers Acceptance
d5783548-4fd3-5b62-9958-3ec294c8cd87 | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| section | 4. Sub Base Construction
| checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
90a61496-bb5d-5408-8fff-882fc7731f67 | note | ACTION (Hold, Monitor, Witness) - M
02a946bb-66a3-546d-b95a-4746ffa5ce7e | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
d83812b1-5250-5635-b968-b73a5b22b190 | note | Frequency - During construction
7aeb445e-3f00-5999-8968-399aec327010 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
5e7eb728-afdb-539e-b59e-b76394498146 | note | Conformance Criteria - Comply with TNZ M/3 Specification.
26ab1f2d-ffa7-5968-9b3c-a8a9c3995f83 | note | ○ NZTA B/2 Specification
54836ac7-06f3-5157-9abb-3f7627977f71 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 4.2 - Sub Base Material Contamination Checks
bb08d263-81f2-5548-9161-fa2e6c82e9ed | note | ACTION (Hold, Monitor, Witness) - M
fad86ded-c37e-5764-9c17-877f72d7c361 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
d9f8382a-af29-5f95-b49b-ed792fd77995 | note | Frequency - During construction
165c3b73-5b09-5250-83c2-752bc08110e6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
f1652b3e-e7f0-5098-b957-98417ef27f82 | note | Conformance Criteria -
50eec905-5274-50f9-8c16-6e1014ac2412 | note | Records - Photos
| checkpoint | 4.3 - Sub Base Trimmed Level Checks
05a03da3-4468-50ea-9058-85092c9b892b | note | ACTION (Hold, Monitor, Witness) - M
64acba90-39ec-5ec7-89c7-96cea54bf112 | note | Detail - Carry out a Level Check on the trimmed Sub base
72aac000-e52a-5329-97e4-96f71d84bff7 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
86f9dd8a-9f23-5cae-ad8d-70c5e22b7973 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
0725ca40-7792-52fc-af1b-c11a6e146afe | note | Conformance Criteria - TNZ B/2
fe9c2327-8ad1-5fc0-9ce1-fd447a3f8c3a | note | ○ Tolerance = -25mm/+5mm
6914bc45-8ab6-5b59-b08e-861cf1540a89 | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
| checkpoint | 4.4 - Sub Base Compaction Lower
9f376486-aacf-584d-a65b-025ee3d382a6 | note | ACTION (Hold, Monitor, Witness) - H
6dbb00e2-e26f-5d32-9e48-8138b0855984 | note | Detail - Degree of Compaction.
e19580b3-71d5-5b1a-9640-ab3b0ee2864f | note | ○ The subbase shall be constructed in two layers.
067055a3-8a5d-54bd-8d1b-daaf2c051bbd | note | ○ Lower subbase results must be approved before construction of upper layer.
6cbc8cf1-67d0-5a57-93b9-0e85774b836c | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
b9911019-0976-5c3e-884c-7eb3bd659ae4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
dcd1e9cd-e4e4-5714-b7cc-68e879489eac | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
910139be-b2b4-5b17-ac06-956749fe91dd | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Sub Base Compaction Upper
698c8699-81a1-55f5-82d8-95567c907031 | note | ACTION (Hold, Monitor, Witness) - H
50a54336-831f-5867-9752-2faade92565c | note | Detail - Degree of Compaction.
0eee789c-4be8-55e6-8b06-537c1367a6f5 | note | ○ The subbase shall be constructed in two layers.
a27921f1-caeb-563c-a303-343ca7c24b87 | note | ○ Upper subbase results must be approved before construction of basecourse.
a4358bd3-a241-56ad-a2f6-7ccc7641e744 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
432e36fe-def3-5e02-b8d3-17e838591c57 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
8e67e332-e320-5880-9346-876b04a9f5b3 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
5fbb47ca-306c-529d-8ea0-b936ed89fcdf | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| section | 5. Base Course Construction
| checkpoint | 5.1 - Base Course Aggregate Delivery Checks
0e655c31-5121-59a4-9ad8-ab8d33bad0b5 | note | ACTION (Hold, Monitor, Witness) - M
0efe8526-ca6d-5232-9388-2769f1d8a0c3 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
92a11ca4-adc6-597e-8684-47a9b485c8e4 | note | Frequency - During construction
0611c7f9-c68a-52b3-8091-98b5c7edf8d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
4063ac84-5e5a-5ecd-8ef9-8e8791b13f62 | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
14350f2a-c720-5f6c-9d5a-d784641fe57e | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 5.2 - Base Course Material Contamination Checks
646c831a-ebaa-5764-8452-0531550227ef | note | ACTION (Hold, Monitor, Witness) - M
03057e0c-35a6-5eb6-a374-1ef8fd237751 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
9575eb34-3e23-535b-9cc1-06f7acbb58ad | note | Frequency - During construction
cb588cbc-5c2c-5c62-84f6-1e609b0ef0e3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
fb2c983b-cdaa-5713-8d9e-a9783647cef8 | note | Conformance Criteria -
0849127a-5d25-5273-abda-b01fa3e1b165 | note | Records - Photos
| checkpoint | 5.3 - Base Course Trimmed Level Checks
0ea7d093-7aa3-5ee6-a394-085f362883b2 | note | ACTION (Hold, Monitor, Witness) - M
dd53081e-7111-5338-829a-04f1fbbf9b34 | note | Detail - Carry out a Level Check on the trimmed Basecourse
69b5cc46-cdde-5c5b-b1e9-5d885d5d2f59 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
dee576d0-61fb-542a-9287-4f8ffec5c634 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
27107afd-68d8-5606-97b6-d27b3c127408 | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
2c4c703b-7aac-5183-97d9-03aa4acaeeee | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| checkpoint | 5.4 - Base Course Compaction
9cc77dd4-2d79-543f-a0f7-cb53f9158c4d | note | ACTION (Hold, Monitor, Witness) - H
1bf4d2b7-d308-5fa2-8659-a6d3182da809 | note | Detail - Degree of Compaction
d1ddf990-4365-5740-9066-a50160d0a047 | note | Frequency - 5 per Lot
14a2bcaf-022f-53da-b97a-b3f1532626a3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
32fea6b3-8a4d-54f2-ae30-1da69957f536 | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
59aba317-3e2f-545d-8239-f2e8e36dc133 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Base Course Surface shape check
4fa7dd78-583b-5e96-8b47-78377ef45724 | note | ACTION (Hold, Monitor, Witness) - H
0a95c74d-92ab-5fea-afd1-82f3c91f003b | note | Detail - Surface shape check
a1d5ab5d-0506-5bb3-af25-d5abc6548db5 | note | Frequency - Prior to sealing
0ea633e9-0b81-555d-aa0a-b53ea929e7cc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
9ff8d790-2783-5d38-812a-657cd28c169e | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
163d5a1a-3908-55d2-afd3-86cf85a52d4f | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Base Course Surface finish check
ff9cd5ee-eff3-564a-aeb6-7500757b6981 | note | ACTION (Hold, Monitor, Witness) - H
d6bc956d-c1ee-50d7-8e03-f286b32fc7b8 | note | Detail - Surface finish check
e8924a93-4ae0-51eb-98fd-86a5b683f095 | note | Frequency - Prior to sealing
f9baefac-7955-56ed-a83d-9d8f27fe2040 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
8a2c9c49-661e-50de-a385-6c97fdbd6be5 | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
b095856c-23e0-57ab-9870-0d89374998b7 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | 6. Sealing
| checkpoint | 6.1 - Location/Size Confirmation
c399061b-2739-525a-9154-ed0adb2802fc | note | ACTION (Hold, Monitor, Witness) - W
18f05878-56aa-5ff3-8bf6-af9d43a29a41 | note | Detail - Mark up extent of Chipseal
7f4ee690-8323-5e62-80b7-d014e9c7d21e | note | Frequency - Prior to Sealing
13abd30c-5421-5926-935c-f9369708816a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
3f1fe611-0081-536d-9d1a-ab13935d173c | note | Records - Photos
| checkpoint | 6.2 - Surface Cleanliness
c7e6eb72-009a-5b1a-9441-e5b50e0841a6 | note | ACTION (Hold, Monitor, Witness) - W
32487b15-225f-5de7-8e8f-ca1bbe87f9e9 | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
20e1c398-29a1-5b67-87a0-52a437fa1207 | note | Frequency - Prior to application of binder
ad033c84-bd93-532d-bd1f-85462f63dff8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
4c3aa560-6110-59a2-9f26-d05dc954c43c | note | Records - Photos
| checkpoint | 6.3 - Binder Application
ba5de36b-c8b0-527a-ab9e-77f5fbe848a3 | note | ACTION (Hold, Monitor, Witness) - W
d4a15de7-53d4-5f9d-8c9a-bfda00411c3b | note | Detail - Ensure the Binder application is according to the seal design
92867935-84aa-5dec-8092-7af1c0231117 | note | Frequency - During sealing
ddb8af94-5f39-53ca-a413-c29d73a77963 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
af9398ae-369d-5d37-82f9-aa685db9b5cd | note | Conformance Criteria - According to seal design
74498145-30e2-5af1-9d47-d94ba22e7ce6 | note | Records - Sealing sheet
| checkpoint | 6.4 - Chip Application
e389d6bb-6f45-5ab1-b10f-9b74eb95b389 | note | ACTION (Hold, Monitor, Witness) - W
df676853-d375-5069-adc0-9aab01f082b0 | note | Detail - Ensure the Chip application is according to the seal design
2db41e56-7a32-5923-8c49-3aaaa776beb7 | note | Frequency - During sealing
ab130ae3-bf29-5f20-9f70-bb2b99a6fd76 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
a7a06eb8-8d26-5f77-b001-5c5e7d2e5d9b | note | Conformance Criteria - According to seal design
d538e32e-104d-542a-a853-230a96f89d5f | note | Records - Sealing sheet
| checkpoint | 6.5 - Compaction
a73973bc-15af-5c94-ac57-baa4806f9a40 | note | ACTION (Hold, Monitor, Witness) - W
16f961dd-135e-5d2a-bbc6-900d6fc52ddc | note | Detail - At completion of rolling
9d8dcae7-0637-5dbd-aa49-767aa03bcaec | note | Frequency - During sealing
d12c285e-8a28-53cd-a1be-23211a9a8c65 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
2ea7a3bb-bdd2-5d62-8baa-764574daa9e4 | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
202ab1f6-88ef-58ed-9f12-1405b5d316f3 | note | Records - Photos, QA measurement Sheet
| checkpoint | 6.6 - Removal of excess chip
4baef4f6-2e6e-5846-9e5c-22e9572c410c | note | ACTION (Hold, Monitor, Witness) - M
8923bc8a-a675-57e9-b94d-0a78da9be64f | note | Detail - Removal of excess chip
09e9dcba-cab0-55cd-80d3-f9ab06d72fba | note | Frequency - Within 48 Hours of Sealing
1e3803da-43b7-5763-8e70-313c74d5f3e6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
ecacffd0-9af1-5265-aa01-a859daac1df4 | note | Conformance Criteria - Ensure all excess chip removed from site.
9e25d188-06dc-5bcc-9f7a-f6b841c8399b | note | ○ No chip windrows left on site in Shoulders.
fbdef7e5-ba58-536d-8af9-01c239eb3d7a | note | Records - Photos, Site logs
| checkpoint | 6.7 - Surface finish check
b0496b9c-76d6-5210-8d12-915ee13d3f10 | note | ACTION (Hold, Monitor, Witness) - H
35208f78-017b-52f6-959f-832f45df06dc | note | Detail - Surface finish check
4a0cc324-9233-57bf-a277-3fdf34638cda | note | Frequency - After sealing
3bea6c29-258e-566e-82c1-9cbc1900c868 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
94127224-b7d4-52cd-8081-af9e0a751039 | note | Conformance Criteria - Engineers Acceptance
80d571f0-ecd3-5460-aacb-ac07c61dfcc7 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 7. Road Marking
| checkpoint | 7.1 - Road Marking
14835991-4d51-5cd5-983f-5ce9a0abe4d7 | note | ACTION (Hold, Monitor, Witness) - H
2ce389ee-838f-5d0e-81bd-3dd906952987 | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
62c6603e-32bd-51a4-a1f6-78d8d0859f0b | note | Frequency - Prior to the final line marking
06b45db0-725d-5912-bbc5-4b00e54980e7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
aa0b4278-0aeb-56b6-83ce-13f52ea9496e | note | Conformance Criteria - Engineers Acceptance
151ac3d7-05ee-5089-af42-baac5fcabc40 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 8. Hydroseeding
| checkpoint | 8.1 - Hydroseeding
5bd91a3e-afc5-55ed-a12b-0e6685153b02 | note | ACTION (Hold, Monitor, Witness) - H
05661e4e-e6a3-5c9b-a97d-6225b8578a34 | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
d6ba0565-ef35-5377-818d-265bd88824bb | note | Frequency - At the completion of the Lot of work
885746cf-5489-5756-86ba-bbffc9a52886 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
78a1ca4d-1450-5092-9304-2d5c8c9c2586 | note | Conformance Criteria - Engineers Acceptance
fac8b7a1-91a5-5b08-8d96-124fdc400221 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 9. Post-Construction Closeout
| checkpoint | 9.1 - Final Walkover (Snags)
19f6be86-a5df-55d5-8d44-45379cb22fa2 | note | ACTION (Hold, Monitor, Witness) - H
4459d765-aa11-5154-9b2a-ce8c8b37e36e | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
f80a2e4c-2146-51c4-90c7-069bccabf285 | note | Frequency - At the completion of the Lot of work
55081097-a8e2-5643-9257-66ae49121a0d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
e16298eb-558d-58ac-99c5-5aa33e9987e8 | note | Conformance Criteria - Completed report
2d47c780-4fd5-592d-ad75-b29f07898122 | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9.2 - Survey As-builts
0479ea7c-c60d-5ca1-aa71-b98bcb83f6ff | note | ACTION (Hold, Monitor, Witness) - H
7a5e63e2-34e9-5f2d-b779-6dbec2cff15f | note | Detail - Red pen mark-up drawings are to be included in the QA file.
bed34a48-c741-5dea-be95-5caa7ba7c19a | note | ○ A survey as-built of completed work must be provided
b008360a-1c88-51ad-b6aa-75493199ebce | note | Frequency - At the completion of the CWP of work
025066a4-a42a-5dbb-a615-bd560df255d1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
154040db-ee46-580d-8578-7e417c84c30b | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded.
0e0b2de3-628b-50d6-8a65-6de45aa86556 | note | ○ Signed and dated
d3ea43a5-2412-5ddf-aa49-f2bf843227f1 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9.3 - Quality Assurance Deliverables
5c053464-d4e4-5d01-ae42-eb8067d66dfe | note | ACTION (Hold, Monitor, Witness) - W
f8c5ce4e-42a2-524b-963d-a21ff1ad31d9 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
f570f929-5577-5146-b86d-3d0735c05d26 | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
9ada14f6-7ee5-5a89-95c9-6bc5ffc8accb | note | Frequency - At the completion of the CWP
24ab9273-ec73-594f-a256-90210192c868 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0a719fa8-fc36-5ee7-9c7b-d4fb8fc96860 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
5ca0768e-978a-5e2c-9eae-c81080a75bad | note | Records - As-builts, NCR's and RFI's
| checklist | Ω (Deprecated) ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn (old version) | itp | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn |  | e9b02e05-4a8b-4ec3-8f68-9fc7efbfc9ce
| section | 1. Setout & Saw Cutting
| checkpoint | Project Site reps.
9ce1f35e-76a7-5b3c-aa9a-fc1df0c0f5d6 | textbox | CPS Eng.
2c8a9808-6c01-57c1-86e2-47990d510f5f | textbox | Site Engineer
bf9f9142-454e-5d51-b1e7-820f48a4f833 | textbox | Quality Eng.
| checkpoint | 1.1 - Survey Setout
7ae96138-2bde-5db0-98e9-86903f764f7e | note | ACTION (Hold, Monitor, Witness) - M
3149dec2-142e-5574-9558-ebd0d2054dfc | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
0929aa0b-4ffa-501d-876f-ebfa101dbce9 | note | Frequency - Prior to commencement
54b47c6f-6bdb-5122-8b07-1cbafe785304 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
273d53ec-98b5-5fcd-bac1-58b80ab1ba08 | note | Records - Survey receipt
| checkpoint | 1.2 - Saw cutting
1a3e5c4a-15c8-53cb-9e41-8933c41c25a1 | note | ACTION (Hold, Monitor, Witness) - H
018fdcee-a87f-5b3f-9834-2c40339f1918 | note | Detail - Proposed Sawcut line to be inspected by the engineer
dbc2cf99-fecd-5a12-8958-503e3394de6f | note | Frequency - During construction
463bdaa6-f8e7-5263-894b-c40166c6d949 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
558e0bbf-7f12-510a-a6cb-d95cabb7127f | note | Conformance Criteria - Project Specification 6.6
c97ac814-ee34-55c2-8d0a-04ec024669f8 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| section | 2. Material Compliance
| checkpoint | 2.1 - Sub Base Material Compliance
7ac2b99f-54f4-5d43-8f20-118c413297b0 | note | ACTION (Hold, Monitor, Witness) - H
5a0ce795-39d5-588e-b14b-66cb3284d482 | note | Detail - Aggregate material compliance for Sub Base stockpiles
00a8935a-729a-5bab-9d82-a2e4439c4457 | note | Frequency - Prior to commencement
e65cac31-644a-51fb-94b3-f9d2b39a24bf | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
7c08b8da-d6be-57a0-b52a-0aae34ee3178 | note | Conformance Criteria - Comply with TNZ M/3 Specification.
2ade152a-4211-5591-bdc4-e2203e08a656 | note | ○ NZTA B/2 Specification Lab test for MDD at OWC.
1443824a-5374-5d59-b9ab-cb8178316a5d | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Base Course Material Compliance
6c5c5a07-4d3f-5547-bfd9-6ce0fbaa7897 | note | ACTION (Hold, Monitor, Witness) - H
5ddf5f74-7c1f-5e71-a926-80b877f370b2 | note | Detail - Aggregate material compliance for Base Course stockpiles
3b560496-63bc-5fbe-bdf9-040cba51c859 | note | Frequency - Prior to commencement
47dd98e9-3514-5dc5-8995-47f58f792b24 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
a0671090-cede-55d6-89b1-816d9dcbe83a | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
0acd8990-8b54-5a75-9b93-f1a2ec1c84db | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Base Course Mat Sample Testing
2fbc43ab-1bb9-5883-a701-83325110de10 | note | ACTION (Hold, Monitor, Witness) - H
bef1127a-c8a4-5ddc-a0d5-f1d0d327e68a | note | Detail - Mat sampling of Basecourse Material
4c731d45-cb3a-52d2-b51f-6b07e8723cd4 | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
d6de8b2c-bea9-5edb-9d2c-cecb7ff2e5b7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
daea67b6-d86c-5aab-ab18-923513e05a5e | note | Conformance Criteria - Grading to comply with specification
f7439385-b22b-578f-a741-4fc74921e776 | note | Records - Mat sample lab test result
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Concrete Pipes
87314527-dbd1-509d-915e-9b569e7cb185 | note | ACTION (Hold, Monitor, Witness) - W
e7a27303-17ca-53d1-81e9-6290b952a968 | note | Detail - Specification Compliance
20687415-62aa-5be4-aa46-665cb1131b4b | note | Frequency - Each delivery to site
e6e586fb-d9a3-5822-a73c-ff33cf38f5b4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
fd3bcc6d-0db6-5678-9970-dd5943bc7e61 | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
76c1a483-b959-5144-b95b-5af03d72e2bc | note | Records - Delivery Dockets
| checkpoint | 2.5 - Pipe Bedding Material Compliance
4d8f8f37-8fab-59f1-8b9f-f618ec0f9f2b | note | ACTION (Hold, Monitor, Witness) - H
440b398b-5de6-5a4d-bce8-de50a5cf67ed | note | Detail - Material to meet specifications dependant on material type selected
ba3e5641-445e-5ea5-adca-92b125824f7b | note | Frequency - Each material used
8a2bbef4-da7a-563d-8aa2-f1180cbbcd5a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
48af8dff-b831-5610-a47d-d2a363082cfd | note | Conformance Criteria - Compliance with requirements from Specifications
f0c2eaff-b884-5e78-8844-c56c7b27731d | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Pipe Backfill Compliance
762d2c41-f39b-5c7e-8496-2071e341d1c9 | note | ACTION (Hold, Monitor, Witness) - H
4961cd62-56ef-5a6f-8fa1-93d94c1c7276 | note | Detail - Material to meet specifications dependant on material type selected
659e0b65-f1b8-56b1-95a7-18d7f885022a | note | Frequency - Each material used
4722293d-6139-5345-8313-6eb4f3090d9e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a932c686-c766-5ab7-a363-80889c364842 | note | Conformance Criteria - Comply with grading specification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Chip Seal design
cfe837e3-5f4d-5555-bc8b-ce44ac847e57 | note | ACTION (Hold, Monitor, Witness) - H
abc3a8d4-b7b2-54db-a8c0-6af326661e9f | note | Detail - Seal design to be reviewed prior to sealing.
63ffc584-6c48-5010-813b-47091e3e5932 | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
ea27dac5-e63e-5da0-9853-58263ea709d7 | note | Frequency - Prior to Sealing
703382c7-24f9-5f6e-84eb-89ffd5486cd3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
8df544c3-a3e8-556e-aef6-7053cd09631f | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
d24acce0-8bf9-5b66-a9ff-e5a0d15b6ee4 | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| section | 3. Sub Grade Construction
| checkpoint | 3.1 - Sub Grade Strength
a863b3d0-161b-5434-a9fc-31038b113ab1 | note | ACTION (Hold, Monitor, Witness) - H
b4cd07f6-b8d8-5a27-9503-27af5853c622 | note | Detail - Determine Bearing strength of Sub Grade
816cbf19-00c0-50f1-98e4-8f9577685ee9 | note | Frequency - After Dig out, every 5m
a252a2d1-a13c-5e97-869e-592547972c9c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
fbbb8b09-b4bd-56f3-8f34-727633cc0695 | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
fea47037-19a5-56da-aef8-049ca4f77f34 | note | Records - QA measurement Sheet, CS-4000 1m Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Proof Roll of subgrade
cebf5dc1-3f52-51a3-9cb9-c691bd285146 | note | ACTION (Hold, Monitor, Witness) - H
fdf3506f-1119-5453-9b12-41d3444b941f | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
e0724539-3029-564b-82dc-183caf047a3c | note | Frequency - Prior to Sub Base Construction
255594cf-14be-55d6-8f31-d6eed92106a2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
efa8800f-47ac-5e7a-bc55-6476280e937f | note | Conformance Criteria - Engineers Acceptance
7f785f2a-9e27-5740-a8ae-bf3a40d457d8 | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| section | 4. Sub Base Construction
| checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
b4364af1-0076-5bb9-8477-e6cdf8367d53 | note | ACTION (Hold, Monitor, Witness) - M
d2b2edcf-94cb-50c8-8c67-a7a4ae0d5f3e | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
2e29359d-1e74-5b60-8e22-4409361d4ed0 | note | Frequency - During construction
b57e3707-d9bb-5004-aa66-6acb13586e20 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
f9a0b613-4da9-5a93-a402-ed6b8c89465a | note | Conformance Criteria - Comply with TNZ M/3 Specification.
34ce98f0-d165-53a4-8445-034f5ba6b130 | note | ○ NZTA B/2 Specification.
ec3e09a5-3df4-5d67-98e4-00565e19cb38 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 4.2 - Sub Base Material Contamination Checks
2b3ef890-d249-5a26-b5b9-41020ebb90cf | note | ACTION (Hold, Monitor, Witness) - M
20b90db6-b628-5075-827c-a533b08b7771 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
810beec6-525f-5cc2-bce2-e7c2cd34ab43 | note | Frequency - During construction
c7ebec40-40c6-5f43-baa1-13dfcd43eab0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
9f99e5d3-06ea-501a-a300-c60229241bfb | note | Records - Photos
| checkpoint | 4.3 - Sub Base Trimmed Level Checks
55298ce3-3d8a-5ea8-8f30-c70907cbccf2 | note | ACTION (Hold, Monitor, Witness) - M
fb1f9f6d-5f7e-5b7b-a14e-158ffa13d2b2 | note | Detail - Carry out a Level Check on the trimmed Sub base
a8b3b83e-422f-5111-855d-1fd9ad5d693e | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
1b9de626-57ab-52df-818f-6ea43bd55f4a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
61f12aaa-4659-5ce0-b3ff-15876d44a660 | note | Conformance Criteria - TNZ B/2
765304c5-b343-5c54-aff0-b61374f1a180 | note | ○ Tolerance = -25mm/+5mm
043cbbe0-a382-5be3-8e0a-709c40708100 | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
| checkpoint | 4.4 - Sub Base Compaction Lower
9240d5e8-058d-58df-8e41-56d5753b414f | note | ACTION (Hold, Monitor, Witness) - H
51a429e5-812a-5dc9-a09d-d20a069a127d | note | Detail - Degree of Compaction.
7cfd3ac8-b279-5735-a571-ea3573829e8a | note | ○ The subbase shall be constructed in two layers.
863ff24f-da28-50f4-9e42-0b59864fe73a | note | ○ Lower subbase results must be approved before construction of upper layer.
1b38f1d9-01b0-559e-ae65-04ae3937b5f6 | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
a61430f9-7862-5868-a6b4-6b89bc0a6562 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
5dac9e67-70dc-51a4-b36c-53e8241c6bf9 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
869295c9-93d4-5b81-bf01-7ad2ab2d73fd | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Sub Base Compaction Upper
dfb65156-7da8-580a-a0fb-3212d845895c | note | ACTION (Hold, Monitor, Witness) - H
e4f42a23-2779-5483-9492-bfbcbb01fa7a | note | Detail - Degree of Compaction.
d826c4b7-02b7-55c0-94ba-d8512d70ab9b | note | ○ The subbase shall be constructed in two layers.
00d72ab9-d80a-547a-b9dc-512d21118e60 | note | ○ Upper subbase results must be approved before construction of basecourse.
c67894f7-3671-575e-a5ce-98b94fbb1fda | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
c4895cfe-eb9c-5810-93da-003197349279 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
a02d2c91-e8c3-5de5-951c-49ebd7c43a22 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
77891d4c-2c21-5992-b3ea-ae84aa78446b | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| section | 5. Base Course Construction
| checkpoint | 5.1 - Base Course Aggregate Delivery Checks
d4c78109-34a3-5b73-a7b2-0f93f34fa78c | note | ACTION (Hold, Monitor, Witness) - M
0a112c96-a607-571a-9497-06d4fca3dc5d | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
29efe8de-6493-5c47-af74-3a8ff5baa834 | note | Frequency - During construction
8cb6be14-829f-5f4a-8865-e64a7dd1abae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
61afba88-1b1a-5769-bc3d-cf099b62c59c | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
477f6cb3-84a6-511f-87c8-5cae4ba2bd5f | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 5.2 - Base Course Material Contamination Checks
b03b4fd4-693e-5d31-98d1-5c4a5e0d65ba | note | ACTION (Hold, Monitor, Witness) - M
61da3a9b-7e56-5b37-ab77-38256c0a1518 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
625932cd-2942-541e-988c-d4a36709f87e | note | Frequency - During construction
c787a0d5-993a-5165-8d18-5096bf99c2ff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3dc89d11-e3ee-5097-9c73-037e4e9d7e9d | note | Records - Photos
| checkpoint | 5.3 - Base Course Trimmed Level Checks
cd2584b1-504c-582a-8b34-5352fc333c63 | note | ACTION (Hold, Monitor, Witness) - M
41abc580-20c0-5c1a-adec-e7b5b3c7b51b | note | Detail - Carry out a Level Check on the trimmed Basecourse
d71a8625-551b-5ec6-821c-d8b909c7b0d7 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
d8668638-7d69-5437-b232-9369941442a0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
99149bf0-b529-5ce4-bfad-46626380f421 | note | Conformance Criteria - Tolerance = -5mm/+15mm
4c685373-b6ac-585d-88cf-b4d01b51633c | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
504ccab6-21c5-520b-99c6-313e4450b5db | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| checkpoint | 5.4 - Base Course Compaction
8c4b8e61-9c58-5142-833d-2a383d998e77 | note | ACTION (Hold, Monitor, Witness) - H
f46a1184-0d38-5fb4-8a93-0efc79b6be71 | note | Detail - Degree of Compaction
e4c6919f-5621-5e43-94bf-ae5cc8a8292e | note | Frequency - 5 per Lot
1aae71af-5d32-5633-a6fb-f240cad7e9e7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
831df6a8-3210-59d0-b483-ac0eeb3edb6a | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
e01e0f79-7dee-5736-b2c4-436777b91786 | note | Records - Pavement Lab Testing Spreadsheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Base Course Surface shape check
91c53700-df46-5077-9683-57750b487068 | note | ACTION (Hold, Monitor, Witness) - H
a99319c9-723a-5920-a501-2cb5365f7f69 | note | Detail - Surface shape check
62716a5f-12f8-5a62-ba65-331ae54d086a | note | Frequency - Prior to sealing
60097ab6-6f2f-5d79-b89b-e1cc8ca71e01 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
9ca60351-2997-5d5c-adbb-7b0783edb75b | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
1564206e-39f9-59ae-b3c5-8d1625f84755 | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Base Course Surface finish check
ab0793cf-9c5a-59ef-8a69-69e91a182787 | note | ACTION (Hold, Monitor, Witness) - H
f43da890-92bd-5018-b4b2-9725a7a281c5 | note | Detail - Surface finish check
1422edc3-96af-56ea-9512-0d5c8fc9a48e | note | Frequency - Prior to sealing
60d94cde-8839-510c-8b4d-0bc40f734006 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
f28573d7-41bb-5f80-8f8d-3e09c026b1bd | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
263f1acb-a5ba-5056-b144-1c0c9e690eb4 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | 6. Extension of Culvert
| checkpoint | 6.1 - Foundation Compliance
1b3f5216-3428-5662-a510-32239bb67f92 | note | ACTION (Hold, Monitor, Witness) - H
7c0714ff-1227-52e7-909f-a859b10653fa | note | Detail - Test formation level on completion of excavation to check if undercut required
ab13df29-0a3f-5316-8897-29d3be2ce1c2 | note | Frequency - One test per 5 linear metres
02d56bea-8350-5799-85e4-a21032538c78 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
372212f1-c350-5835-8a32-9f70fe99bf27 | note | Conformance Criteria - Min. 2 blows /100mm
9d285fca-d44b-5568-b6f7-3871de00b547 | note | ○ 2 blows = 4 CBR
0108a17d-ea92-573b-a725-d676d4f5fc03 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Levels Compliance
45c3e8f7-d899-557e-bf10-23ca4f5b2a88 | note | ACTION (Hold, Monitor, Witness) - H
27778dfe-fef7-54a1-bf7d-9b4b060e32e7 | note | Detail - Test formation level on completion of excavation to check if undercut required
642edcad-c648-516a-8f3d-1fd6f39a0774 | note | Frequency - As stated
54890746-774a-55bd-a528-fc578379fb9e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
a8cd8454-22c4-5813-8137-461ee98cbe11 | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
33e9021e-8b77-53d0-a689-720143bf11c9 | note | Records - Photos, Visual
| signoff | AUTHORITY HOLDPOINT
| section | 7. Sealing
| checkpoint | 7.1 - Location/Size Confirmation
0b3abbbe-61c2-5deb-9410-3239b458ce3d | note | ACTION (Hold, Monitor, Witness) - W
889a6e99-7292-5a03-baf8-c4e8205232f6 | note | Detail - Mark up extent of Chipseal
5a1b5bf3-736e-5c18-9ad5-3605efb07b40 | note | Frequency - Prior to Sealing
1d228bfa-7520-50ee-84b3-ad5b6920b822 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
dd2b1ee3-9645-5503-ba98-4ecd17714dec | note | Conformance Criteria -
250138ae-4472-576e-a097-d1b669b7d464 | note | Records - Photos
| checkpoint | 7.2 - Surface Cleanliness
6fd44084-ca2a-50ea-9ae8-c9cde660bdbe | note | ACTION (Hold, Monitor, Witness) - W
69367b26-3272-5c25-bf9e-769822ac1959 | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
8f7916b6-4a2b-5b48-9f1d-4eb492dddae5 | note | Frequency - Prior to application of binder
3e339253-537e-5a8e-9141-9e157f02cbf6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
24a023a8-5f74-51e4-b2ae-88574f27b0b3 | note | Records - Photos
| checkpoint | 7.3 - Binder Application
890ca594-f9ea-5616-9a25-deb604ea5e43 | note | ACTION (Hold, Monitor, Witness) - W
b2687fbf-ad33-582a-a613-fe32e21798a8 | note | Detail - Ensure the Binder application is according to the seal design
4c0a9797-43bc-5994-9bd0-8d6681f094ea | note | Frequency - During sealing
e17d31ef-dd19-5c75-b7ab-e012ce07694a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
1b2d9547-3a45-55e4-a46a-efab039af768 | note | Conformance Criteria - According to seal design
af43d413-bd2a-5f0b-8aed-36c37b5ecb63 | note | Records - Sealing sheet
| checkpoint | 7.4 - Chip Application
5a2ebc7e-1fed-54bd-bad5-b81208e4dcd0 | note | ACTION (Hold, Monitor, Witness) - W
a2bf96b2-7f02-502b-b82a-3ae3e5d71c40 | note | Detail - Ensure the Chip application is according to the seal design
f6dc59dd-348d-5862-a9c6-c62ab75d65fc | note | Frequency - During sealing
c5252c26-5cec-5141-989f-ba419b8595b8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
d45e4c50-cdf1-5b89-96a3-b6b7248ae5d3 | note | Conformance Criteria - According to seal design
a6f825e1-6cf7-5663-99aa-83477e0391b5 | note | Records - Sealing sheet
| checkpoint | 7.5 - Compaction
9dd05e4f-ad2a-5794-8771-32f5c9470d84 | note | ACTION (Hold, Monitor, Witness) - W
18832216-c261-5271-acae-a4227d7532bf | note | Detail - At completion of rolling
efc81bde-e9c9-5c64-91ef-42638232d46f | note | Frequency - During sealing
d799f111-d74a-5f7c-afa4-766ddc20dbe3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
ea6650da-5d6d-5b40-9076-ca20c98f12a8 | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
d7b24350-f433-57bd-b97d-3d0a6b613567 | note | Records - Photos, QA measurement Sheet
| checkpoint | 7.6 - Removal of excess chip
13005bc4-804c-53ed-a1ed-6d289fcb2224 | note | ACTION (Hold, Monitor, Witness) - M
dbeb6b00-35dd-57de-9141-992ec1033593 | note | Detail - Removal of excess chip
e78207ec-60be-503a-9d27-a995f5670a67 | note | Frequency - Within 48 Hours of Sealing
007dcf16-629b-5d68-a13c-8115d1b7f4a9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
fcbd0f76-3a5b-59a3-81ba-9f0c2eddc9d2 | note | Conformance Criteria - Ensure all excess chip removed from site.
79473162-10d4-5de4-8bf8-092d903115ac | note | ○ No chip windrows left on site in Shoulders.
a10b2fc2-4cd8-5028-bfa9-9f92062505a8 | note | Records - Photos, Site logs
| checkpoint | 7.7 - Surface finish check
0d8add72-8214-51b9-8944-3dec0f2c3b7c | note | ACTION (Hold, Monitor, Witness) - H
1c0d802e-8633-5fa7-9eae-53fa77d937bc | note | Detail - Surface finish check
a1ea5924-f7e8-5499-b586-d65f631962ca | note | Frequency - After sealing
d186cc22-6f94-5ebc-a7af-596c3449e0b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
8e8b4d46-3cbd-5014-8cef-ed7d31b1e23a | note | Conformance Criteria - Engineers Acceptance
9c77c6a8-de48-509f-912b-6a9cd891bab1 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 8. Road Marking
| checkpoint | 8.1 - Road Marking
85189b8a-220c-5649-bb53-5fd852cd7067 | note | ACTION (Hold, Monitor, Witness) - H
8c1238ba-7c3c-5601-bd79-8b96449fbae3 | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
81f6d7b7-548b-54d8-9d63-97beeafd7084 | note | Frequency - Prior to the final line marking
bec53a2c-92e1-527d-bcea-a1b089fd9c35 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
97d210df-4dfd-599f-b7f1-1dc4a2956715 | note | Conformance Criteria - Engineers Acceptance
b5a23775-828d-563f-9151-c9bcf26792ee | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 9. Hydroseeding
| checkpoint | 9.1 - Hydroseeding
24d16e96-c7a1-5341-8799-5cbfccd931a3 | note | ACTION (Hold, Monitor, Witness) - H
283e78f0-a8ee-52d5-85ae-18912a42a915 | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
caed83b7-df0b-53a6-a057-4feca423fe0c | note | Frequency - At the completion of the Lot of work
6c07c63a-a10a-5004-abdd-5fbed3538814 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
e602bb73-fb78-5635-a4ad-70fe46f3b7c8 | note | Conformance Criteria - Engineers Acceptance
5490f4f7-7e5d-5c41-914f-f16aa20e9f89 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | 10. Post-Construction Closeout
| checkpoint | 10.1 - Final Walkover (Snags)
263515ad-4454-5eb1-96fe-65456f96d0d2 | note | ACTION (Hold, Monitor, Witness) - H
8cd81723-329e-5d40-a9e9-96d91a72abdf | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
bf751700-4f4e-57ad-bb13-9f4e7a7afb1f | note | Frequency - At the completion of the Lot of work
de116035-741d-5f0e-a69c-6bb35db60a51 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
b972551d-4d0b-56a6-968f-4c3533cb629f | note | Conformance Criteria - Completed report
d10daeaf-8ec9-53d0-905f-ba857372075c | note | Records - Snag List signed by attendees
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 - Survey As-builts
afb36436-7fa4-5891-add7-be4534a7a400 | note | ACTION (Hold, Monitor, Witness) - H
f2601dbc-319e-517f-9d8e-507835da97d5 | note | Detail - Red pen mark-up drawings are to be included in the QA file.
ce2daadf-4d83-5492-bd71-0a7f0d636ca0 | note | ○ A survey as-built of completed work must be provided
ccda0400-3db7-5547-8971-f44ac254256c | note | Frequency - At the completion of the CWP of work
641eebb3-a697-5ebd-a38d-335e35d45cc8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
4ad4db0d-b4cf-56e6-bbe1-9471fac6e8c3 | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
6ba3039d-7126-571c-9b67-e9786f11aef8 | note | Records - As-built Drawings. Redline Markups
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.3 - Quality Assurance Deliverables
0de96a70-f838-58e1-b37f-1ac078da2344 | note | ACTION (Hold, Monitor, Witness) - W
fb6d43f0-a347-5ed6-b420-1582b68833d0 | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
cd2a1882-6eaf-58bc-8e3c-27e4554ea43e | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
ec63282f-fe5c-5a90-8b1f-e55d9d935535 | note | Frequency - At the completion of the CWP
7d37fd43-f24f-5546-9467-102be1b8d659 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
14632523-b5d6-5b8a-826b-06ad5c17f0e3 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
b08e92bd-15f0-5f78-89f3-911152dbe7d8 | note | Records - As-builts, NCR's and RFI's
| checklist | Ω (Deprecated) ITP - E3001A - SH05 SIP Site 1 - Pavement Construction (old version) | itp | ITP - E3001A - SH05 SIP Site 1 - Pavement Construction |  | f3cbf27c-bd31-431e-a580-9c262f9e9028
| section | Survey Setout
| checkpoint | Project Site reps.
95e36960-0f44-59e7-b8b6-14e42d889e8d | textbox | CPS Eng.
2824c54f-ef10-5f71-bd34-8cca164080cf | textbox | Site Engineer
ea45a22f-879f-515e-a84c-e2297a7c4fdc | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
ea0b8d2d-950a-5ce6-a9de-656123ba6805 | note | ACTION (Hold, Monitor, Witness) - M
db1b826a-a5b2-559d-af10-2d91da596d9b | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
d80add25-2fea-52f3-a6a7-854c24d281c6 | note | Frequency - Prior to commencement
10872cfd-fbca-527a-947b-c84a86423b95 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9beaa8d1-fd8b-5c4c-9c3d-20627d72fb01 | note | Records - Survey receipt
| section | Sub Grade
| checkpoint | 2 - Sub Grade Strength
df2f0c61-cf0d-5c10-9441-5b7eb838642f | note | ACTION (Hold, Monitor, Witness) - H
2ae50419-40ac-582e-8690-c2e3ae233ce8 | note | Detail - Determine Bearing strength of Sub Grade
82664e5e-0d40-594e-b65e-d26e78a9f386 | note | Frequency - After Dig out Every 5m
a7f704b6-588a-5686-86fb-72b8183e58ae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
d8def8d6-5773-5dc9-ae8f-87a8acb30f91 | note | Conformance Criteria - Min. 4 blows /100mm
74190072-5015-5b2e-af23-58526321a84b | note | Records - QA measurement Sheet (CS-4000) 1m Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Proof Roll of subgrade
030d113b-fab0-5776-978e-5589049a6628 | note | ACTION (Hold, Monitor, Witness) - H
0f81fdb9-598f-5cd5-9bd6-5f9405be87c6 | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
0f6657d7-4fef-5465-8e72-bd1c68283376 | note | Frequency - Prior to Sub Base Construction
a70220d8-7cf8-5fff-b790-120a4fc0386c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4a673cc2-41af-580c-9424-eec918d1c17e | note | Conformance Criteria - Engineers Acceptance
e5ae4f58-2c05-50b7-8a7e-1e7f1f9aaceb | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| section | Sub base
| checkpoint | 4 - Material Compliance
4241f76b-cc22-5af8-8075-9d4cc8bd7984 | note | ACTION (Hold, Monitor, Witness) - H
0bcb0e91-e79f-5972-9aed-aa533e1708f5 | note | Detail - Aggregate material compliance for Subbase stockpiles
d205c2ca-9026-5e24-969b-9756df572af0 | note | Frequency - Prior to commencement
c83795fd-d266-51ce-9ca5-a3bb364ddae5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
92139b96-71eb-517a-a76c-36f71b3dc676 | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
79405a2c-50a2-5925-bde1-0fe5dec906df | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| checkpoint | 5 - Material Compliance
d37f8c02-ad22-5fc5-9c72-4b232f293dd8 | note | ACTION (Hold, Monitor, Witness) - M
d7419b9a-1d45-5ef6-a79a-4c3188c4eb71 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
4f10568a-01cf-56a0-8a63-4e94acefda90 | note | Frequency - During construction
3db631f4-8dbd-52ab-ac09-73cd7e9cfaf6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
49f3534a-47dc-569d-82f9-a1171e356d20 | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
5ac2b9b1-ef5e-564d-9c72-5babcc96c413 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 6 - Saw cutting
2883083b-fa90-5b46-b6bd-764206182518 | note | ACTION (Hold, Monitor, Witness) - H
cf9695a7-a20c-5f54-960c-3f6ff5be3264 | note | Detail - proposed Sawcut line to be inspected by the engineer
3573352e-8d7e-58d3-b4dc-054d5464bae3 | note | Frequency - During construction
a7a21952-55c5-583f-a379-08533d422eb9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
205ccacb-90b8-55d2-bf39-5a7f58366ff9 | note | Conformance Criteria - project spec 6.6
3ee2ff66-5770-5906-8720-ffa47beb112d | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Sub Base Construction
b3f9f7fe-4a4f-5c2d-a4ac-a50e128bd31b | note | ACTION (Hold, Monitor, Witness) - M
6469eb0b-5db6-5301-9fe9-cf0143dc0474 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
6fc9a07b-42e1-5fd3-b706-384098d570ed | note | Frequency - During construction
86b40359-2eb6-5836-93f1-85ee80aded7a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
368712ef-5c26-5dbd-aa4f-4538e7051ba9 | note | Records - Photos
| checkpoint | 8 - Sub Base Construction
99b323e2-e6b7-5a57-ad2a-3a067fa3117a | note | ACTION (Hold, Monitor, Witness) - M
903785f2-fd6e-5d24-becd-a6f24a2a1fe4 | note | Detail - Carry out a Level Check on the trimmed Sub base
65480e54-d199-59a1-969c-0c15a0d16b23 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
45ceb81f-ce6b-5f24-b941-e19ce7111a6f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
e48472b8-433b-5d76-a432-cceea9190a18 | note | Conformance Criteria - Tolerance = -5mm/+15mm
64f1daed-2319-558c-9f93-a05f7fa26a72 | note | Records - QA measurement Sheet
| checkpoint | 9 - Sub Base Construction
1b167e96-26d5-58bf-bee2-4cbc35551ec4 | note | ACTION (Hold, Monitor, Witness) - M
0272f934-bc18-51f1-9cbb-d7b4869a2ec1 | note | Detail - Degree of Compaction
6aef43a9-fdc3-5ed5-bf23-a27bb4dbe060 | note | Frequency - 5 per Lot
762ac5d3-da1f-5bd6-b369-44ee1d5b090b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
31dbc2c2-134c-5d9d-a147-516c08860087 | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
bf76b00a-1463-5512-bb85-7dece0b390da | note | Records - Pavement Lab Testing Spreadsheet
| checkpoint | 10 - Sub Base Construction
faa702b1-48ba-512d-a4be-27c4a68f1b41 | note | ACTION (Hold, Monitor, Witness) - H
552567c8-eb97-5bec-8567-7fd43448bff8 | note | Detail - Surface shape check
f7e571f6-b097-5d4c-b297-08b7657f23b9 | note | Frequency - Prior to base course Construction
249efe03-36d6-5056-852f-b101df813e6c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
e8e663c4-b23e-550e-a9eb-42cd4b77519e | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
3645976b-26af-5925-acd3-9dc78ed0bde6 | note | Records - QA measurement Sheet
| signoff | AUTHORITY HOLDPOINT
| section | Base Course Construction
| checkpoint | 11 - Material Compliance
51ed6460-b614-5fc4-ae72-fd1c91c45786 | note | ACTION (Hold, Monitor, Witness) - H
ccc22f5f-eefe-56c7-a53e-b617fa659639 | note | Detail - Aggregate material compliance for base Course stockpiles
a0baa6be-ddbc-5d2e-a2d2-c25d0ac0112d | note | Frequency - Prior to commencement
8d22f10a-89c1-5e48-b9f4-2783ade0be7e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
c905c117-690f-5e1e-b8a5-ec3a64908e6a | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
c49c28a4-e816-5137-9089-b9c441337212 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Material Compliance
2901494d-8bf7-5164-9833-315f8ddc0597 | note | ACTION (Hold, Monitor, Witness) - M
95d18a78-06fc-58e6-bc89-7b6887e6fa09 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
e5385767-f309-55ca-a5b2-9035b7651529 | note | Frequency - During construction
d9230cb4-5fe6-541e-aaf9-bdc38ae7d619 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
b33c412f-006e-59ab-9228-aa9fda5329be | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
3e017c69-e9d7-5dba-aecf-5d59918696f5 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 13 - Base Course Construction
0e41d4a9-61db-54be-b3ca-e5130b2d42e5 | note | ACTION (Hold, Monitor, Witness) - W
8e623039-036a-5446-b4f0-c38a550e0af1 | note | Detail - Mat sampling of Basecourse Material
7a5cad43-1c37-5dfe-a0f3-50b973d29598 | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
4c9727b4-0a4d-5919-ba7d-8d726e4ceb20 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
795d6b3c-af21-5b88-8a94-c8be1df6a5e2 | note | Conformance Criteria - Grading to comply with specification
e75e93b0-025e-587a-9ade-5345270f67cd | note | Records - Mat sample lab test result
| checkpoint | 14 - Base Course Construction
419fa2f5-d4c1-5f03-8f23-6a4d38eb896d | note | ACTION (Hold, Monitor, Witness) - M
e862d8bc-7bf3-5ea6-9d71-da09fbc221d4 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
efb1530d-4749-5ed7-b518-ae6b308d8bd4 | note | Frequency - During construction
dcc40f09-31dc-54e4-a501-27a9c97fbf0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
58d67b24-abca-5d39-8ee2-2db7dbc1a74d | note | Records - Photos
| checkpoint | 15 - Base Course Construction
4e2ba83f-881d-5015-ab5e-0826ebe7e2c9 | note | ACTION (Hold, Monitor, Witness) - M
a0339c51-d203-5aee-a3e8-235a86764e4a | note | Detail - Carry out a Level Check on the trimmed Basecourse
033c1216-895c-5216-9fe6-dbbd42dbf275 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
77c0ee77-2e7f-5079-933b-38502cf5af6f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
b36434d8-2d26-5cce-af28-9365c5f972b8 | note | Conformance Criteria - Tolerance = -5mm/+15mm
a8105d8d-d214-5a6f-bce2-a0e2c9bd53f9 | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
72490a64-41b1-5fe2-a80d-b23e4ea7c0ab | note | Records - QA measurement Sheet
| checkpoint | 16 - Base Course Construction
133f1ced-0b73-56e0-acaa-95bd68a148b7 | note | ACTION (Hold, Monitor, Witness) - M
a0324919-c357-541f-8b4b-0dcde1d6b6c8 | note | Detail - Degree of Compaction
47761358-9fda-5dfb-80c0-38247a58fd86 | note | Frequency - 5 per Lot
f7e47071-2b75-5024-b5a8-f0e9589297c1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
7bd08962-e0c2-5c4f-b76c-2abb067ce9c4 | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
204f4119-d10a-53e0-9466-88ad08ed08b0 | note | Records - Pavement Lab Testing Spreadsheet
| checkpoint | 17 - Base Course Construction
720a2457-3a05-5ed9-acbf-365b71db73fe | note | ACTION (Hold, Monitor, Witness) - H
ad78bc89-c0e5-5011-82f1-16cb5fb8a690 | note | Detail - Surface shape check
771d3a75-7c08-5599-8861-57f22e747a19 | note | Frequency - Prior to sealing
8031421c-6869-54e0-a745-c248669cc022 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
20332fec-6ec9-5e44-ba6f-2a2a617c1e99 | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
e3a8827b-c72f-5ce0-add0-423c5fce2aef | note | Records - QA measurement Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - Base Course Construction
d7cd3ae6-bc88-5ec7-8bd6-c306dac228ef | note | ACTION (Hold, Monitor, Witness) - H
c3417ff0-dd5f-502a-b194-b7b4820de217 | note | Detail - Surface finish check
60430a24-ced8-5414-b17d-e5da6b5fe783 | note | Frequency - Prior to sealing
21a3a31f-f29b-5864-8b27-57aa5981f2a3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
132e1ac2-0150-5a38-8774-3fe32c683476 | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
f42b6529-cd2d-5598-97df-e4e30b0aa722 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | Sealing
| checkpoint | 19 - Seal design
f8e2f490-3d34-583a-996f-2a009d08cedf | note | ACTION (Hold, Monitor, Witness) - H
23fc39c0-8cc6-5288-8d1c-f0badbb53e83 | note | Detail - Seal design to be reviewed prior to sealing
cf611b15-186c-5f3d-a9b9-532595616ec3 | note | Frequency - Prior to Sealing
eb9910c1-c4e2-553c-955a-b005a8023f8b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
a92faff2-0915-5538-ba64-56dcca7971e1 | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 20 - Location/Size Confirmation
2f8c3013-d04c-559c-8617-b9164e583aea | note | ACTION (Hold, Monitor, Witness) - W
7ed6814d-f28a-5408-a486-1efa62981f19 | note | Detail - Mark up extent of Chipseal
6e9de0a7-884f-5dc1-ab9e-0cfabb6c856e | note | Frequency - Prior to Sealing
b91a9d06-73d4-5897-a799-d28a03ea3289 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
c7600a81-b918-5a55-9cf4-2b86ea7ee319 | note | Records - Photos
| checkpoint | 21 - Surface Cleanliness
0d8b8d4e-c8c6-590d-890a-e2c7d8bc62f6 | note | ACTION (Hold, Monitor, Witness) - W
a298b0d0-cafa-531b-b10e-247bb7a62c6f | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
2ba37e51-1d9f-5c9a-8610-8e98d593b1aa | note | Frequency - Prior to application of binder
ef11102a-4906-5963-9d58-73a9e85b5ded | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
5d53cbe8-75eb-5ca7-ab01-02b2ea304af6 | note | Records - Photos
| checkpoint | 22 - Binder Application
5da651b3-4cbf-5aeb-9f5b-884423520abe | note | ACTION (Hold, Monitor, Witness) - W
fdccd612-1d83-53ee-a3c0-e6ddd61718b1 | note | Detail - Ensure the Binder application is according to the seal design
b565f0cb-9059-5ed8-a21a-35a9108ba5ba | note | Frequency - During sealing
25c77802-79be-50cc-8d58-8defc8aa9c73 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
1d0d9cbb-ce30-5eac-ae62-28feaa7de358 | note | Conformance Criteria - According to seal design
6623bccc-1ced-5bd0-9f3c-481627e1ea6c | note | Records - Sealing sheet
| checkpoint | 23 - Chip Application
9e031834-5be7-5f52-8172-d8126b8198b8 | note | ACTION (Hold, Monitor, Witness) - W
00fcd43e-335b-5866-90a2-78a82d61169a | note | Detail - Ensure the Chip application is according to the seal design
cab4487d-ae8e-5123-a7d0-ba2361e9a6d2 | note | Frequency - During sealing
457f2b2c-5e74-5c8d-a805-5adc657fecd4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
54f94261-669b-5948-b655-dc5ff332cba6 | note | Conformance Criteria - According to seal design
398ab96a-471c-51b8-b2b9-27aaecc1e26a | note | Records - Sealing sheet
| checkpoint | 24 - Compaction
162eb295-3e9a-53d0-926c-40932b143efc | note | ACTION (Hold, Monitor, Witness) - W
aa044b9c-95b5-59fc-b1fe-90c65a7ee67d | note | Detail - At completion of rolling
310e7cdf-75e3-5f66-a3c8-4da912498209 | note | Frequency - During sealing
1c72d500-716e-5aa5-95e0-8a4fd45e3134 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
f898307a-01bb-50a3-a9fb-3006f9eefb6e | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
446095f0-848e-5451-abeb-58ce5a408b11 | note | Records - Photos, QA measurement Sheet
| checkpoint | 25 - Photos, QA measurement Sheet
b3a077b7-48e3-5115-82df-9703fec2bab8 | note | ACTION (Hold, Monitor, Witness) - M
e567a069-cef7-5ed3-a7b3-eda3f2a76f92 | note | Detail - Removal of excess chip
a3f5b202-b5d1-57ee-94f2-28bf3a7d2ade | note | Frequency - Within 48 Hours of Sealing
7c6f22c3-cd4e-58c7-851c-f9daa255b3b1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
0c5c5010-3afe-5b68-86c8-091ca53f5e6a | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
b6422c6c-30c3-5b7e-a1aa-540876378fbc | note | Records - Photos, Site logs
| checkpoint | 26 - Compaction
6bfd5eda-4a6b-52de-9626-3d3797c56b88 | note | ACTION (Hold, Monitor, Witness) - H
8848c619-713d-560f-8d94-bf1a4b52b87e | note | Detail - Surface finish check
109a8e7b-d582-561a-ba1d-f6bdbecf3368 | note | Frequency - After sealing
060e7d25-a06e-54d2-a4f4-1e4b0f7f513e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
f5dbcf16-5396-5770-a4bb-f6efae58f91b | note | Conformance Criteria - Engineers Acceptance
e1cc6816-e88a-5d11-b201-ee32c273bda7 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | Road Marking
| checkpoint | 27 - Road Marking
d7c97dd9-f0e3-5af7-8a64-371269240feb | note | ACTION (Hold, Monitor, Witness) - H
00e3103f-18ac-5122-b2c1-0e782f743505 | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
ed0a2251-2c5e-5cb7-b607-5147bbd3a259 | note | Frequency - Prior to the final line marking
389d49a6-506b-597f-baa2-9fab0b3f2784 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
e188f3a3-aacb-5eb0-8834-218d6f5ea504 | note | Conformance Criteria - Engineers Acceptance
d48c5991-3d2f-509f-83b6-1ae74ac7c4e7 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | Hydroseeding
| checkpoint | 28 - Hydroseeding
43bc1796-5fc7-56e8-bd47-ef8c32d39928 | note | ACTION (Hold, Monitor, Witness) - H
b6d28b08-99be-5b11-bf58-d9b0947b2bd8 | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
792b4fe0-913a-520a-9b1d-51f5e497fbac | note | Frequency - At the completion of the Lot of work
b463cf11-502f-57d2-b12c-6c1d2011f2be | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
ce5c40fd-afab-56e2-8efa-6723653fcff9 | note | Conformance Criteria - Engineers Acceptance
f418fb20-020d-5e61-bf95-90bff0e5858c | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | Final Inspection and Handover
| checkpoint | 29 - Quality Assurance deliverables
e59ee23f-4bd8-5b2d-9c29-ea8ba812f172 | note | ACTION (Hold, Monitor, Witness) - W
de6b2fd8-50a6-530d-b101-40e09e917cd4 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
657121df-3073-5345-992f-1ce2512ad087 | note | Frequency - At completion of Lot
4f893e6d-c756-56bd-bd9d-8c9ab3a2bef3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
58b36bca-d887-5e43-ae4f-90d038f0f7a2 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
c5415ccc-44c6-52ff-97d9-7ac558546783 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 30 - Completion Sign Off From Fields Below
948e2af4-3520-5317-a58a-e152c71a2a29 | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - E3001B - SH05 SIP Site 2 - Pavement Construction (old version) | itp | ITP - E3001B - SH05 SIP Site 2 - Pavement Construction |  | 7039ce80-9c90-4e12-b242-61337fbc3f7a
| section | Survey Setout
| checkpoint | Project Site reps.
6ae201c9-1d66-52f0-8380-ea730b29c656 | textbox | CPS Eng.
47ac752c-9e55-5bc3-9376-2b5870f18b38 | textbox | Site Engineer
9b3f78c7-290a-50d7-acdf-d1ecd7933f66 | textbox | Quality Eng.
| checkpoint | 1 - Survey Setout
87f0cd87-3e2c-5845-9a8e-e3031f5aa52c | note | ACTION (Hold, Monitor, Witness) - M
9a3b6972-bf41-56ca-986f-619aa0fe6332 | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
7c3b3a16-c7e2-5c38-b1ba-8b4ee3234e49 | note | Frequency - Prior to commencement
331b95d1-90fe-59e6-b9a9-f02a39d1b558 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
90edc683-0d9d-5d63-ab04-4bf84e3d9aa7 | note | Records - Survey receipt
| section | Sub Grade
| checkpoint | 2 - Sub Grade Strength
24ceeb11-4bf7-5036-b147-e528347d93f1 | note | ACTION (Hold, Monitor, Witness) - H
12348a14-8e3c-5acb-9229-ccc994c55b38 | note | Detail - Determine Bearing strength of Sub Grade
f93e51b8-0e6b-59a5-990e-75379795e8ee | note | Frequency - After Dig out Every 5m
de506733-17e4-53ac-b7e8-519037432548 | note | Conformance Criteria - Testing
da9d56a4-a1f7-51e1-81d6-1072dbd9142d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Min. 4 blows /100mm
27c067d5-80df-5537-867b-19cf605280e9 | note | Records - QA measurement Sheet, CS-4000 1m Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Proof Roll of subgrade
ee46b25c-570c-5438-94f3-28c2d1c52853 | note | ACTION (Hold, Monitor, Witness) - H
5f32d64e-f09a-5ba0-9e72-f5e60cf6fd0b | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
5a2928b0-d3bf-52f5-951f-6a6d1a7df40e | note | Frequency - Prior to Sub Base Construction
de5f0b61-9c7f-5dc9-911c-8820c61a9df1 | note | Conformance Criteria - Visual Inspection
de5700ae-423b-5cc4-94e4-c549e644586f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
4da94ced-0087-5e33-acb9-327737f9e3ed | note | Records - Emails
| signoff | AUTHORITY HOLDPOINT
| section | Sub base
| checkpoint | 4 - Material Compliance
1ab6e2d9-bc3f-532f-bc07-43b60b2418a7 | note | ACTION (Hold, Monitor, Witness) - H
1df9b4cd-120f-5087-91c7-77da29f3944c | note | Detail - Aggregate material compliance for Subbase stockpiles
3155d271-f99f-5dc6-bf21-228ea3fbfb2a | note | Frequency - Prior to commencement
93e83d88-2158-5148-8540-b2478892c2a9 | note | Conformance Criteria - Lab Testing
5e7b1001-2103-5b1a-810c-499ef1714917 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC
d5765071-1356-5b6b-ae9a-b13e05af4bb5 | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance
e8b60e6d-d5e8-5e77-804a-4769062e9622 | note | ACTION (Hold, Monitor, Witness) - M
1b73c271-5b4d-5e08-97ce-dc798efe7500 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
760dc99d-00ea-5e5e-83ae-eeea77dfa057 | note | Frequency - During construction
07e52da3-20b3-585f-bc16-221a28850e8a | note | Conformance Criteria - Measurement and recording
c215a95e-0150-5e08-a27d-b48c4742327b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Comply with TNZ M/3 Specification. NZTA B/2 Specification
8aebe967-cd42-5394-adfb-7395a58716ab | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 6 - Saw cutting
dc3b1ab1-75df-5e7b-9c1e-fc08e220e834 | note | ACTION (Hold, Monitor, Witness) - H
ccde8524-63d9-5980-9277-300cd359ec86 | note | Detail - proposed Sawcut line to be inspected by the engineer
902b456e-fa77-537a-a423-4b3f5accd5a7 | note | Frequency - During construction
fbf425a4-f4c6-5c86-8549-c6a69d54267c | note | Conformance Criteria - Visual Inspection
360c3b25-a41a-5079-8a07-12a0ff8e88f8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - project spec 6.6
01e959d3-d21f-586f-9a20-0e83bb397f41 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Sub Base Construction
85043001-0600-55dc-a939-9094d7e5a624 | note | ACTION (Hold, Monitor, Witness) - M
aafe8f14-3d32-5e3c-8454-9d4f4d08cd54 | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
3388b6f0-c46c-59ca-9ae7-52a266526db0 | note | Frequency - During construction
0ec0a2f1-5527-50f8-9770-0bedd43d100f | note | Conformance Criteria - Visual Inspection
0aafab0f-d764-5fbb-ac11-cbe13a23bc09 | note | Records - Photos
| checkpoint | 8 - Sub Base Construction
2e595bd2-bd61-5616-a111-8e87e8914ff7 | note | ACTION (Hold, Monitor, Witness) - M
1662689f-0096-57b6-8993-13d90e13a6f5 | note | Detail - Carry out a Level Check on the trimmed Sub base
d81a6657-7a57-52eb-8888-36671e0cb544 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
0c691550-060b-53f3-b46a-e4dedf47df01 | note | Conformance Criteria - Measurement
e39fa841-925a-50c6-8775-d61bddb88ce1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Tolerance = -5mm/+15mm
cec3812f-8302-56f8-b0f5-a34efc4feba1 | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
| checkpoint | 9 - Sub Base Construction
ffd904af-fc4e-5c73-ba76-165908ccbf14 | note | ACTION (Hold, Monitor, Witness) - M
8538a8d9-1f14-50de-9aa5-5dca3206c665 | note | Detail - Degree of Compaction
e24bd6d1-57e5-58fd-8fcc-638680f6e969 | note | Frequency - 5 per Lot
02f25af1-8ad4-5be3-a0ef-c0f4599061e8 | note | Conformance Criteria - NDM Lab Testing
4bc839b2-7037-5341-8cb2-174c4a4503ff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Avg. >= 95% MDD and Min. >= 92% MDD
9319f825-46de-53e7-ad47-b5a057bb90cd | note | Records - Pavement Lab Testing Spreadsheet
| checkpoint | 10 - Sub Base Construction
977d4364-9c1e-505b-9759-b1bb289763ba | note | ACTION (Hold, Monitor, Witness) - H
bab8518f-cf6a-5d3a-825b-03abc15c0a68 | note | Detail - Surface shape check
5c5e330a-e81b-500b-b571-b4d4bfb189cc | note | Frequency - Prior to base course Construction
7806fe89-1c89-5dac-86ff-58d5e3227dff | note | Conformance Criteria - Measurement
f492ee12-8aeb-5655-adc3-c3b46371e574 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - No point of the surface shall vary more than 10mm over a 3m long straight edge
4b61bf37-996d-5308-b0b5-4ec47be28f59 | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
| signoff | AUTHORITY HOLDPOINT
| section | Base Course Construction
| checkpoint | 11 - Material Compliance
f38e6867-129a-5ec8-8d6b-daff5bc88f58 | note | ACTION (Hold, Monitor, Witness) - H
27990f74-cbdd-551e-9a44-c46fb1ad28ca | note | Detail - Aggregate material compliance for base Course stockpiles
8970fcec-4686-5a9b-9733-75f3219b3862 | note | Frequency - Prior to commencement
65472436-d274-56e3-a22c-495bb45bdfc3 | note | Conformance Criteria - Lab Testing
df63ddd2-ffd6-57ba-b2ef-8bcfc7d09e9e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Aggregate shall comply with TNZ M/4
6904d9cd-0a40-582f-8e51-7500af27a47e | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Material Compliance
005bb68a-c030-5f09-90e6-b6dab9572ef2 | note | ACTION (Hold, Monitor, Witness) - M
7172b102-5b4c-5bde-b45a-ff21a244c659 | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
4ff19556-6c3c-5057-a580-8e54e8fe9838 | note | Frequency - During construction
0b48133e-2f3d-58ba-ab38-b79bb312555d | note | Conformance Criteria - Measurement and recording
7a206615-fe1d-5f84-8d19-02ff3a535f4a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
4dfc8f90-9bca-5932-8b01-7ed21af85013 | note | Records - Delivery Dockets, Aggregate Deliveries Register
| checkpoint | 13 - Base Course Construction
0800a305-6caa-559d-b3e5-49e36d193fbc | note | ACTION (Hold, Monitor, Witness) - W
c21f83a0-3405-5f51-9159-278cb8aced65 | note | Detail - Mat sampling of Basecourse Material
521b9f63-15d6-5767-83cd-d81cb4c230bf | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
313531ed-87ab-5a4b-88af-78ebb40f6b44 | note | Conformance Criteria - Lab testing
2d74a5e4-9225-59ae-8011-568e633510a8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Grading to comply with specification
f8698cc3-774b-51de-aa08-6e6117ff128c | note | Records - Mat sample lab test result
| checkpoint | 14 - Base Course Construction
c2dfe403-6bd6-5a61-933b-f1cdc2bd8771 | note | ACTION (Hold, Monitor, Witness) - M
969bceb1-4882-512a-aab4-11f95f2a576f | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
0a0df35d-74ec-56f1-9832-7bf7b372a96b | note | Frequency - During construction
b5573015-6324-5701-8a71-e9e80e3ecfd0 | note | Conformance Criteria - Visual Inspection
5575a6d1-958a-5e7e-aeca-af3b669df7b1 | note | Records - Photos
| checkpoint | 15 - Base Course Construction
e748c4b5-7246-5e59-bfda-537a218678fa | note | ACTION (Hold, Monitor, Witness) - M
be158a83-ce59-5617-ab41-e47311b84e02 | note | Detail - Carry out a Level Check on the trimmed Basecourse
01234e45-a9a8-5f7b-88ee-e10d95405be4 | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
1987d9f5-0027-5652-a46f-d59c421a2027 | note | Conformance Criteria - Measurement
76a92f01-1265-5366-91c7-00a1a8ba8e3e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Tolerance = -5mm/+15mm if constrained (kerb)
03075162-4647-5889-9d50-fede9ca6781f | note | ○ Tolerance = -5mm/+5mm
1c21a97b-a004-5469-84ce-633e1ad4821b | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| checkpoint | 16 - Base Course Construction
cec63c20-4549-5d4f-8bbc-1b63c4dda40b | note | ACTION (Hold, Monitor, Witness) - M
040b5cdd-58bf-5dbd-959d-313cbea001fe | note | Detail - Degree of Compaction
7b5759f2-7af8-5067-a1b0-e0c03322ef17 | note | Frequency - 5 per Lot
e7884e8a-9f00-5674-a572-d7cd3dbb85f8 | note | Conformance Criteria - NDM Lab Testing
a76c6f17-8964-564e-8c86-6cb6c5616b9b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Avg. >= 98% MDD and Min. >= 95% MDD
982a4a5b-439a-5c9e-9c51-d54ac1845b0b | note | Records - Pavement Lab Testing Spreadsheet
| checkpoint | 17 - Base Course Construction
1ea92510-317d-5f63-886d-ff0c9c643d14 | note | ACTION (Hold, Monitor, Witness) - H
f60704b9-0eaa-52b2-aa3a-257a57458d53 | note | Detail - Surface shape check
a0fe91a2-f6ae-59c4-89e4-90e25e30d59e | note | Frequency - Prior to sealing
538d79e2-65ff-565a-b04b-eafa84d07880 | note | Conformance Criteria - Measurement
84c8fba6-4d3b-5f76-a463-f2bd99cec00a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - No point of the surface shall vary more than 10mm over a 3m long straight edge
a1183c27-c0aa-5ebc-a348-59fdb1e4be65 | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - Base Course Construction
6da2f5bb-54f1-55a5-b356-40af0714de0c | note | ACTION (Hold, Monitor, Witness) - H
b57dedba-4de5-5f8f-9187-e522ad943702 | note | Detail - Surface finish check
22cec296-ffe6-5d1b-bca0-05030a3b11fb | note | Frequency - Prior to sealing
c9a5a12b-d350-5684-afd9-a3abe3bef8d6 | note | Conformance Criteria - Visual inspection by CPS Engineer after site sweeping
c25869d4-deab-512e-ab93-ee96550fa02d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
c19dd802-c492-5f18-b092-af259785eeb2 | note | Records - Site photos, Emails
| signoff | AUTHORITY HOLDPOINT
| section | Extension of Culvert
| checkpoint | 19 - Foundation Compliance
c453b766-4d03-50c1-8ec9-6a643f61a9a6 | note | ACTION (Hold, Monitor, Witness) - H
e7f73845-0715-5f34-812b-9c73bf74a9cb | note | Detail - Test formation level on completion of excavation to check if undercut required
0b181c21-e1f6-53d7-8bee-5c796a6e5f4f | note | Frequency - One test per 5 linear metres
65c00509-64a0-55f3-bd01-f33ae0cb4e6e | note | Conformance Criteria - Scala Penetrometer
20e4eb8c-866d-5974-8d25-5fc24a68821c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Min 4 Blows/100
6a45421e-c422-55a1-9e05-8617b7bca607 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 20 - Foundation Compliance
e9c3dc9c-3e23-5eb9-8115-70390ab4103c | note | ACTION (Hold, Monitor, Witness) - H
09d9d0e3-14ec-5d16-bae0-8a10b2b7a35a | note | Detail - Test formation level on completion of excavation to check if undercut required
3c008aaa-15aa-52a4-8e10-088ddd21894f | note | Frequency - As stated
1517d179-decd-5e11-97b2-e271111dad47 | note | Conformance Criteria - Visual
eedb5ddb-d64c-5327-9290-5bc77c19374e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Designer to inspect formation level at outfalls / inlets.
1f8674fd-b5e3-576a-8504-246b97ef8ee3 | note | Records - Photos, Visual
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 21 - Materials (Pipes and drainage aggregate)
ec11128d-cd5d-53fe-82b6-e3b89da81d68 | note | ACTION (Hold, Monitor, Witness) - W
3b3a6c12-e43d-54e8-a36f-c1bc9fb69639 | note | Detail - Specification Compliance
d8704604-0a31-547d-8362-2c5fe78b17b5 | note | Frequency - Each delivery to site
2c0e35e2-afc4-59b1-b68c-f61382c510d7 | note | Conformance Criteria - Certification
125d29f6-6965-5eca-8218-9575e4fc4377 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Compliance with requirements from Specifications
860b80de-2d70-5e62-b7a0-3a5d054836ba | note | Records - Delivery Dockets
| section | Sealing
| checkpoint | 22 - Seal design
3dcc2ae1-d5ff-5887-b184-46e226460865 | note | ACTION (Hold, Monitor, Witness) - H
0badc0ac-c767-55da-b9ae-3cd37ff526bd | note | Detail - Seal design to be reviewed prior to sealing
636bf2ad-e81b-5cd6-9378-10e6f59dbb87 | note | Frequency - Prior to Sealing
ac774314-0817-5265-855f-e6c8bcd7eff4 | note | Conformance Criteria - Review
dac1f1ff-b078-56bc-aa87-208856ccc219 | note | Records - Emails/NTE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 23 - Location/Size Confirmation
700e3c0b-2d8d-52d4-8f71-ed664a8e9864 | note | ACTION (Hold, Monitor, Witness) - W
92feb180-32ef-534d-b827-cd871865a288 | note | Detail - Mark up extent of Chipseal
0da31666-49f6-58d6-b3f1-9b104ed01cf9 | note | Frequency - Prior to Sealing
5c8e7de7-14b6-56aa-b2d0-ff290eae92b2 | note | Conformance Criteria - Mark out
ecc6574d-7880-5bc4-a7ad-247ee11b55cd | note | Records - Photos
| checkpoint | 24 - Surface Cleanliness
25dec5dc-fc39-53bf-8721-c2550e7c48b5 | note | ACTION (Hold, Monitor, Witness) - W
6263d642-6f64-5e46-923c-bf712cf61c8f | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
289056ea-2ff4-508b-b4ce-29c72253d563 | note | Frequency - Prior to application of binder
5bf7fe40-5966-5c54-aeef-bdf990beb14a | note | Conformance Criteria - Visual inspection
7029de6c-7d0c-52fa-88f8-ddd5376e9b99 | note | Records - Photos
| checkpoint | 25 - Binder Application
64144a37-8bca-5751-8413-f598d2716e43 | note | ACTION (Hold, Monitor, Witness) - W
fa2f3664-a20b-5af9-b047-ca668def3389 | note | Detail - Ensure the Binder application is according to the seal design
e8454c5e-f8ff-5c6c-be90-7b3b7cf28991 | note | Frequency - During sealing
41d90711-102d-5bb6-b208-4d953f616a2d | note | Conformance Criteria - Measure
6902806c-20ef-5c6b-8216-5d0132563677 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - According to seal design
47b753cf-8684-5c31-97b8-7328a50024b3 | note | Records - Sealing sheet
| checkpoint | 26 - Chip Application
70dbb959-50eb-5416-aaf4-6298e2124cda | note | ACTION (Hold, Monitor, Witness) - W
3b2d0811-30cd-56fc-ac19-bc2770450790 | note | Detail - Ensure the Chip application is according to the seal design
07fc4e6b-89ba-5def-bbc6-f033ab1d610a | note | Frequency - During sealing
6248b35d-08f2-566a-a403-3e6e1876049a | note | Conformance Criteria - Measure
c077ff1f-d750-57e4-b299-fa39eea14155 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - According to seal design
f172cfad-ff5a-5d41-8e5c-95525052c887 | note | Records - Sealing sheet
| checkpoint | 27 - Compaction
5ab19bd9-5cae-5bb8-84ee-3cc36c7e4eb3 | note | ACTION (Hold, Monitor, Witness) - W
6bdd99f8-7c3b-5a8d-a67a-3aae8a959cf7 | note | Detail - At completion of rolling
b1e0e1e8-5e40-5393-b161-6af7df2c7e19 | note | Frequency - During sealing
fee21524-c683-513a-9ccc-cd2f65260d4f | note | Conformance Criteria - Visual
66d4bfd4-54f3-5819-9806-4a4ceff75029 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
fa486582-4a26-5209-8e86-879105da9ffc | note | Records - Photos, QA measurement Sheet
| checkpoint | 28 - Compaction
6d423816-c634-51f1-91ed-472d6ac69c55 | note | ACTION (Hold, Monitor, Witness) - M
868d443f-718d-5b68-9293-f7a922c3ecff | note | Detail - Removal of excess chip
0f33d570-007e-55ad-86b3-d291fe5a624a | note | Frequency - Within 48 Hours of Sealing
c4f9bfbb-cca3-5ecd-880d-994e33faf201 | note | Conformance Criteria - Visual
e0d324c0-169e-5e98-a0c4-16b9fc8a6596 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
b4a459cf-60c2-50be-83bb-9b1c70f9044d | note | Records - Photos, Site logs
| checkpoint | 29 - Compaction
f5bfb9b5-8a58-52ba-a735-50604325ea94 | note | ACTION (Hold, Monitor, Witness) - H
a6d7dc60-b72d-5574-9227-ae12ea80c606 | note | Detail - Surface finish check
9c6d3ad4-3781-572f-a723-e3e14d5cf8d1 | note | Frequency - After sealing
b3ebfc1b-95e4-5cf3-bc7f-7a1074ff4e15 | note | Conformance Criteria - Visual
f71cd3d5-a81a-5d84-8fe7-7ddf90c49de7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
212e1879-0b7e-55b5-8302-f95e4d12db35 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | Road Marking
| checkpoint | 30 - Road Marking
752281e9-c63d-5d7b-b4c7-8af9826f0f6e | note | ACTION (Hold, Monitor, Witness) - H
aa86f78e-52ee-581e-b28b-c52ca6b77228 | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
1c0b1211-74b7-5c10-bef4-faddb1a05c19 | note | Frequency - Prior to the final line marking
c34e20a3-a35f-55c9-a783-5c91c58bd079 | note | Conformance Criteria - Visual
29cd481a-c3e4-5a61-9e74-7dc9a2919afe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
112e36cf-1415-5d6a-93b9-8992ce4be647 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | Hydroseeding
| checkpoint | 31 - Hydroseeding
bae93316-f80d-5438-aa05-068c11034ed8 | note | ACTION (Hold, Monitor, Witness) - H
d286a686-7f08-5cbc-b937-f9671be4603a | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
e5c26cde-ce21-563e-a495-2f96ede4d434 | note | Frequency - At the completion of the Lot of work
dc1db1c4-3951-55d8-9173-8abba74afeda | note | Conformance Criteria - Visual
1b587f00-15d0-5448-adba-9dd64593da91 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
b66cf478-8cab-538e-9ac6-9e894ad5ec98 | note | Records - Photos Email
| signoff | AUTHORITY HOLDPOINT
| section | Final Inspection and Handover
| checkpoint | 32 - Quality Assurance deliverables
06aa1799-29d6-5d40-9422-2ddb9361def2 | note | ACTION (Hold, Monitor, Witness) - W
0fd28ea0-2aa1-5ffd-8345-0133ef57db17 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
f0685855-43b8-5d1f-9b64-260e8e5a3190 | note | Frequency - At completion of Lot
bb541ec9-d059-568c-b8f8-51687c772891 | note | Conformance Criteria - Document Review
34269409-2607-5ce1-ab46-5d899b39fb02 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all QA is uploaded into ConQA / Procore
a29efc20-f41e-54d0-8bac-6adb03e4ec88 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 33 - Completion Sign Off From Fields Below
44e830c4-6caa-533d-8fd9-754aed7e4156 | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - F3002D - Mangahuini Long Drop Site - ITP for works (old version) | itp | ITP - F3002D - Mangahuini Long Drop Site - ITP for works |  | c26c115f-33e7-4ae6-9c0c-177c7ec0243e
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
a9ef3422-cf18-5e07-95f5-b983861f6c25 | textbox | CPS Eng.
1c7f6ca3-0c79-50a4-90a0-39e9bf8e661b | textbox | Site Engineer
c670454a-08e0-5e75-b4dd-7317d3e654d7 | textbox | Quality Eng.
| checkpoint | 1.1 - Buttress Rock Armour (D50=800mm)
c03a65c0-ea92-5fbf-889d-e3593fc3ba9d | note | ACTION (Hold, Monitor, Witness) - W
82ede738-003a-51d3-a1c8-7928fa284a46 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
7a862530-a12a-56b7-9f9b-93281c2f1b85 | note | Frequency - Prior to commencement
fa82e688-0b3f-5323-92ad-99411b5d52f5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
3754b16b-d255-5fca-acd7-6a94747d8ef3 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 800mm with a minimum specific Gravity SG of 2350kg/m3.
3cc65163-0bd9-5a91-b119-ad8c8ae64f57 | note | Records - Material source test results, Delivery dockets, Photo's
| checkpoint | 1.2 - Culvert Rip rap rock (D50 = 500mm)
6f11bac8-5ff4-5f1e-b357-b3b3470c1cb8 | note | ACTION (Hold, Monitor, Witness) - W
ff483354-72a4-5a50-9667-b0680b7be3d2 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
293475d9-e6d5-5c52-b990-87078c3e00f0 | note | Frequency - Prior to commencement
7ce9b540-2c6f-5f09-9c7c-64dac7573ba9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
2d07d77a-881c-5883-a0aa-d56214b0bc65 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 500mm with a minimum specific Gravity SG of 2350kg/m
cbbafe0e-7d89-5fde-937e-569318fea65d | note | Records - Material source test results, Delivery dockets, Photo's
| checkpoint | 1.3 - Drainage material
d2d7b4c5-c4ae-5da7-a934-c6ffacd87e78 | note | ACTION (Hold, Monitor, Witness) - W
1c6684d0-6e9a-5c6e-a94b-f54acadc2eb7 | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
514e4d67-e043-5a9e-accb-ad613dd2fe56 | note | Frequency - Prior to commencement
9f40bc43-58e0-5455-845e-ccf6d8e9c810 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
8b8c52a4-0b0a-5819-a8f5-9c3e63debe66 | note | Conformance Criteria - Comply with TNZ F/2 or approved equivalent.
0795f3c0-a764-5049-b1fd-4c40d19ea30a | note | Records - Material source test results, Delivery dockets
| checkpoint | 1.4 - AP65 Granular fill
0d08838e-b18f-5cb8-9522-9b75fc949598 | note | ACTION (Hold, Monitor, Witness) - W
edcbf013-294e-563c-974a-73fcf9feb66e | note | Specification/Drawings Reference - F3002D 2-U3436.BM
7b675523-017f-5cb0-9e96-d4618489228b | note | Frequency - Prior to commencement
a4d0f02a-796c-53cd-9925-9019d2db8d97 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Particle size distribution test
0ae45cfb-9d2a-5aca-8610-be2559169ab1 | note | Conformance Criteria - Test results from a representative general fill sample tested in an independent accredited laboratory
09fb2d97-a197-5c2f-b0cb-7cb7a54df5a6 | note | Records - Material compliance cert, delivery dockets
| checkpoint | 1.5 - Class D A49 Geotextile
3618705d-f5e7-539c-99e0-c70f42443444 | note | ACTION (Hold, Monitor, Witness) - W
ce140532-f616-5fb1-8cb8-befc888e41be | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA F/7
dc3276e0-eca2-5304-b0e9-51d37c17e0bb | note | Frequency - Prior to commencement
313a8183-b64e-5525-80dc-905b0f76f8a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
5e9076cb-28dc-5769-8383-aba37c52b016 | note | Conformance Criteria - Non-woven & NZTA F/7 compliant, On dry bed below fill
ff33550d-4c2c-5803-a479-480db728b5da | note | Records - Material compliance cert, photo's, delivery dockets
| checkpoint | 1.6 - Perforated lateral drains
5f247443-504f-5e3c-8a29-98975bf6f1bb | note | ACTION (Hold, Monitor, Witness) - W
d7f57fd1-78fc-5363-a524-155d2bcfcff6 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
7d6aff42-ebfe-52b3-8927-104d962bd4ad | note | Frequency - Prior to commencement
b2dbce8b-b3b6-58c0-b9eb-1b1400c3bc47 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
826c43ab-a1d4-5703-81cb-4cf318bbc629 | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved.
e8bba67d-4edf-5b7d-96a7-b179e9154209 | note | Records - Material compliance cert, photo's, delivery dockets
| checkpoint | 1.7 - Precast concrete box culverts
92c9288e-f734-578b-b2dd-4768e8ca156d | note | ACTION (Hold, Monitor, Witness) - W
a29391f5-ab9a-5f22-98c7-27c1b7cd3281 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
4fa3117c-9a1f-5709-a93f-a86aca799f4a | note | Frequency - Prior to commencement
afc84df0-d27e-5e19-ae0e-713c9ff28a0a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
cce606a5-a5c3-506f-9dea-3f6d723a99b6 | note | Conformance Criteria - Delivery Dockets are collected and signed before precast wing walls are removed from the truck.
46ec0856-0784-5260-a2ee-66db83489272 | note | Records - Material compliance cert, photo's, delivery dockets
| checkpoint | 1.8 - Precast concrete wing walls
bb243049-2fad-5f77-83a7-78a57720b393 | note | ACTION (Hold, Monitor, Witness) - W
d03c9aec-6f89-511a-9f5f-310157e6a26b | note | Specification/Drawings Reference - F3002D 2-U3436.BM
6256cdea-fb71-5c66-8697-9e1c4d5ce587 | note | Frequency - Prior to commencement
17cf72d9-0182-5f1c-ba3e-f4c19face22c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
3c6c3f17-f531-560d-9697-1cc334f13486 | note | Conformance Criteria - Delivery Dockets are collected and signed before precast wing walls are removed from the truck.
52027a57-bcae-5416-a287-27dfc8cdc637 | note | Records - Material compliance cert, photo's, delivery dockets
| checkpoint | 1.9 - Precast materials
317be5b5-ef9f-543c-af0c-57895778e6b1 | note | ACTION (Hold, Monitor, Witness) - H
2b64fc08-8a27-5674-a95e-1b063c1879dd | note | Frequency - Prior to unloading
cff43614-6a9b-51c6-8ff4-5701fd607107 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
3274bec8-283c-5334-9735-1d8e01b85ca6 | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
ab513b4c-8e89-57c0-adcf-203636eac19b | note | Records - Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.10 - AP40 (Basecourse)
c344cab7-8b40-5201-a1cf-c43d9eba008b | note | ACTION (Hold, Monitor, Witness) - W
b3c54fac-938d-57c4-919f-b08d29da6853 | note | Specification/Drawings Reference - TNZ M/4
1bce9c57-1b10-5399-99a0-48b28755599f | note | Frequency - Prior to commencement
a5d88b4f-6f5f-55f0-afa5-92061b268e0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
633c0d81-624e-5243-8c83-a9bd21081390 | note | Conformance Criteria - Source property testing, Traceability of all materials delivered to site
f40fa169-dc4b-57c0-8f7c-1163c10ae89e | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.11 - AP65 (Sub-base)
123f072b-f90e-5c76-ad02-ebeb9ec55b2d | note | ACTION (Hold, Monitor, Witness) - W
44811f22-3ce9-5cd3-85cf-a4bb97df66cc | note | Frequency - Prior to commencement
05ec2c5a-1ef3-54ae-8944-fae2fe010709 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
0aae071a-0fad-5e4b-8243-baffcb6e6630 | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
829278be-5376-505e-a49e-b6828b7e7cd5 | note | Records - Lab test report, Delivery dockets
| checkpoint | 1.12 - Grade 2/4 Chip
66111881-6678-56bf-8ceb-861332e5faf5 | note | ACTION (Hold, Monitor, Witness) - W
6cd91063-75db-5649-9c35-69d26df3efff | note | Specification/Drawings Reference - NZTA M/6
3d1203ea-7e0d-5b61-93b9-4db4ed0715ac | note | Frequency - Prior to commencement
d6c9cb2c-3a50-5193-943e-2ed56b6e7ae4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
cb59b10a-e502-5c77-963b-c5d1b4ad64f1 | note | Conformance Criteria - Source property testing, Traceability of all materials delivered to site
31cb2573-9eba-50c9-b1da-f2307a755fe8 | note | Records - Lab test reports, Delivery dockets
| checkpoint | 1.13 - Cement Material cert
7030eb22-2303-5aac-9ac0-5885baa93f48 | note | ACTION (Hold, Monitor, Witness) - W
44b930b8-62b4-5543-90db-5333cae2eb1b | note | Frequency - Prior to commencement
60e0de73-92a6-56b7-8144-7ca5cbeabebd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
fcaeaeb7-f6dd-5ecd-a260-258edf2e6327 | note | Records - Material certificate(s)
| checkpoint | 1.14 - Bitumen
a97225ed-df3e-53a9-a91a-0b8d8c969c94 | note | ACTION (Hold, Monitor, Witness) - W
5b25d497-83c6-54b1-9279-2259cc8ddf3c | note | Specification/Drawings Reference - TNZ M/1
0b27f2f0-b54f-5e04-a1c9-37365c978cc5 | note | Frequency - Prior to commencement
6163deec-f423-57e0-9240-00d7c6898204 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
d3e4a8db-35f8-5a99-acf2-4597177739a1 | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
36664ebf-055a-5156-961f-bdd4f337ae7f | note | Records - E2 Certificate
| section | Section 2: REVETMENT & BACKFILL INSPECTIONS
| checkpoint | 2.1 - Survey Setout
7da3f0b9-5d65-5fcb-854e-674e50295a1d | note | ACTION (Hold, Monitor, Witness) - H
406c77ee-3c05-5b14-a8ab-d200feaef8b7 | note | Specification/Drawings Reference - Consistency with Construction Drawing
851a5c60-4afd-5d45-8fb6-707895e5a909 | note | Frequency - Prior to commencement
a12cb09e-5272-5f84-b14a-a0e37373f1b5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
2b4794da-6bec-5a4a-ba64-0db681f2da3b | note | Conformance Criteria - Set out extents of fill and check against design drawings
ea7acb07-35c5-5452-bd55-cf94b6f9c961 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Unsuitable loose material and vegetation
be6c13ae-5810-5260-8a29-f60420352b9a | note | ACTION (Hold, Monitor, Witness) - W
eab67c33-1009-506c-8d0b-e6bb762e281d | note | Specification/Drawings Reference - F3002D 2-U3436.BM
b50f8387-5ba5-545c-ac75-e57b3e65d0cf | note | Frequency - During Construction
25227ef3-73c8-541c-809d-04b36e5d29b1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7341260e-cd6a-5d68-acf2-94cc7b2adbe4 | note | Conformance Criteria - Remove and clear any vegetation, trees and unsuitable material
6dcc4955-9a38-5c2d-b216-ec81d7d2a607 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Inspection
5d788543-4e87-5231-acb3-18c83e897db2 | note | ACTION (Hold, Monitor, Witness) - H
f67ba027-9fd0-5a4c-9fb6-019253125e60 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
dd222ce0-241a-5ee5-848a-2b0c50c07a1c | note | Frequency - Per area as required
65e0541a-8439-52c2-9ab7-07480fc681eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d1adaa3d-cb22-58a1-843d-e94af84e89b3 | note | Conformance Criteria - Inspect fill foundation, Fill foundation must be approved, in writing, before filling commences
056a8437-8ede-539d-b0ae-79c1e9659724 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Class D (A49) Geotextile placement
11f108fa-d610-5559-aec7-4be3a3cc1589 | note | ACTION (Hold, Monitor, Witness) - M
21b4c435-67e4-5104-97ab-f33a314aebc5 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
7cad53fc-f208-5a75-9431-e95f0e804b94 | note | Frequency - During Construction
2722b31b-d429-5f11-8830-24ceceff4b8c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8d266f1c-6eb6-5242-8e8c-7ca9a57e849e | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A49 or similar approved before placing granular fill. Bidim layer required between granular fill and rock armour.
84424e6b-8dc8-520d-96ce-3b1230dfb76b | note | Records - Photo's
| checkpoint | 2.5 - Sub soil drainage
85f372ac-6535-50da-91c9-0db286c825bd | note | ACTION (Hold, Monitor, Witness) - H
1b37ae33-80de-5348-9c06-b59a32c7f152 | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
d174de45-6679-512a-9e06-c271dc0d3414 | note | Frequency - At lower bench level and mid bench prior to placing granular fill.
11167a2b-9335-5ed5-965f-9675cc1a91f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
89a1ced0-5b37-5bd6-ae70-a75cfdc8727a | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. To be inspected and approved by CPS Engineer prior to install.
3dfec212-b757-5523-884b-87555d8cbdc9 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Imported Granular Fill Placement
71aa9db8-621d-5246-a7d1-eb5ed2aba815 | note | ACTION (Hold, Monitor, Witness) - H
0049cd55-5b9d-5e5c-9321-980bd817500c | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS4431:2022
2f95ce24-7300-549e-a30f-f88fd59da3a0 | note | Frequency - During Construction
d81ae3b5-a6f2-5caa-8d2e-3cabbf05431b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
eb34cb0c-7e1e-5424-adc5-acca7f8cefcd | note | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade.
8bb8503f-e988-57a6-b700-6f2073f55cbb | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Imported Granular Fill Compaction
32884c5b-0bb7-5a32-9733-cf01894f9c47 | note | ACTION (Hold, Monitor, Witness) - H
8c49d56b-8070-5aa9-b735-f2e32dac9ebd | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS 4402:1986, Test 4.1.3
4cfc5b80-de1a-586e-9390-f6dfd11736a9 | note | Frequency - During Construction
2a7f51a2-a2b1-5bab-ab41-2c9437313081 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM & Clegg hammer testing
4134df0c-dede-584f-b5ce-4b646900a06d | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Testing done as per Site Instruction by CPS Engineer.
cce5123c-e95b-58e9-a247-a71783506d54 | note | Records - Test results, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Form and cut fill batter as per design 1.5H:1V
91f09654-8b72-510b-a91d-a0fe01f86273 | note | ACTION (Hold, Monitor, Witness) - H
563f42f3-d666-50f4-9de2-198a45767fd2 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
b37562c8-6604-598a-8d55-2be008c5bd4e | note | Frequency - During Construction
bd14e94b-1017-5c59-aaca-8f4bd6bc3b23 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
151eae9e-3134-53fb-be16-01ce47d20ed9 | note | Conformance Criteria - Benches to be cut and profiled to suit slope profile
a8bd0aa3-8d3f-5eee-b780-82a277808c05 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.9 - Rock Armour (50-800dia) to form revetment
8085f2d1-c815-53b1-b13b-9947d1af01b9 | note | ACTION (Hold, Monitor, Witness) - M
16c087b0-93ed-5d8e-9bb4-092601834c06 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
53e57817-b2bf-55a9-82eb-0a50b8ecae1e | note | Frequency - During Construction
225a6808-e2ad-50de-945c-9a2b689364ea | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c4d5107e-d130-508d-8854-2fb70db0ce8f | note | Conformance Criteria - The buttress is to be keyed in to ground directly behind existing displaced reno mattresses and existing railway line timber panel retaining wall
b0b5120f-ddec-525d-8288-f2b932b2ee27 | note | Records - Photo's
| section | Section 3: CULVERT EXTENSION INSPECTIONS
| checkpoint | 3.1 - Clear, reshape & apply rip rap to culvert inlet
d076819e-d147-5f8b-b13b-b82052361596 | note | ACTION (Hold, Monitor, Witness) - H
b3824a2f-dab4-5bd8-902d-952bfb54ca3f | note | Specification/Drawings Reference - F3002D 2-U3436.BM
8a36cd12-f137-56b6-a9b0-e4e3fa5d240d | note | Frequency - During Construction
d30b5756-8050-520d-9ece-540a3ec6bc41 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
ee12a33c-e0f1-56ab-b763-05470255b842 | note | Conformance Criteria - As agreed on site with CPS Engineer
6fa166ed-35e7-5786-a4d9-990d0923908f | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Form foundation for culvert extension
55109c44-b41a-5a69-8287-2c866e852561 | note | ACTION (Hold, Monitor, Witness) - H
897afe54-2359-5396-bb69-4b8c8e76486c | note | Specification/Drawings Reference - F3002D 2-U3436.BM
16103866-10a5-5e72-938f-e457e7f94b1a | note | Frequency - During Construction
8c55a817-780c-529e-a249-ed4e91344501 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
7e6894a3-a38c-526e-8633-7ed13a8f3f1e | note | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
a6ff5ec6-f6a0-5a96-b4ce-cc5216af97dd | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Expose the end of the existing concrete culvert
248cb304-17bd-5670-9872-d793128b59c2 | note | ACTION (Hold, Monitor, Witness) - H
490a5c4c-900d-52c8-8cf9-ba7dd4bca2d3 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
cd86a046-e785-5e59-805f-66728e2ce44f | note | Frequency - During Construction
0e3ddb8a-7d17-5470-8acc-97b72b538c36 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b57f29b6-e007-5268-b3c0-f4b0a89ae262 | note | Conformance Criteria - Once exposed, CPS Engineer is required to carry out a Structural Integrity inspection on the culvert
a7c424ff-844c-54c0-8e63-549e364a19bd | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Install precast concrete culvert units & headwalls
8dd15534-cfab-585c-a2b6-106512eddfbc | note | ACTION (Hold, Monitor, Witness) - H
28b3079e-410a-577c-aa7c-1629aded0c02 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
24986c80-7e50-598b-987b-fdbc9f09f0e0 | note | Frequency - During Construction
4f502ccc-f9ab-5d27-bac6-6554601d23e8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
8f111287-daf3-5886-aa82-6774da78c23b | note | Conformance Criteria - Precast materials will be placed in accordance with the manufacturers recommendations & as per design
a71cec3a-7632-58c2-9ce3-405672b542e2 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Rock Rip rap (50-500dia) placed at culvert outlet
b9a2c042-179d-546d-a640-2840d0014d93 | note | ACTION (Hold, Monitor, Witness) - H
3664566f-14fe-57ed-8ebb-a8d0df65db48 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
72ea57fc-fb40-5867-a5aa-6501c3bba42d | note | Frequency - During Construction
4372c090-d4cf-5666-b644-40b83304bfa6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
25815389-a9bf-526e-bb10-e78c920d5600 | note | Conformance Criteria - Riprap rock to be placed around culvert outlets. Bidim A49 to be placed at base
a1744f78-5477-58e0-aa2a-8d3eaee9aea1 | note | Records - CPS COR Report, Photo's
| signoff | AUTHORITY HOLDPOINT
| section | Section 4: PAVEMENT INSPECTIONS
| checkpoint | 4.1 - Saw cut existing pavement
710edcfa-fd40-592d-98fe-90ec40eb5306 | note | ACTION (Hold, Monitor, Witness) - W
00ff4a36-0d4c-59db-ab3e-65615492515f | note | Frequency - Prior to pavement construction
cdaeb63b-7066-5b3c-9669-ab2202e7ac13 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ba4dd4da-cae6-5350-a07d-e0b019e440ce | note | Conformance Criteria - Smooth and straight saw cut
e5a7754f-d963-55eb-a3a6-a1c0e2cbacd8 | note | Records - Photo's
| checkpoint | 4.2 - Subgrade construction
4cc7e69b-2f46-52ad-a050-e84e2d951b16 | note | ACTION (Hold, Monitor, Witness) - W
57d20c28-4e32-583c-83b6-f846c7843962 | note | Specification/Drawings Reference - TNZ B2
51c6cc3f-1e65-5948-b65e-1ecce0798e45 | note | Frequency - Every 20m and/or at random
d58338ad-5ff5-599c-a151-8e74aff58532 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
c222b690-0528-52e2-8a3b-51ba28253c36 | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
229c3c51-c399-5442-9bfa-1fb74d6c8db3 | note | Records - Subgrade Approval Check sheet, Test (CS-4100) reports
| checkpoint | 4.3 - Subgrade Cement Application rate
dd661f3e-2a5d-5b8b-9525-cddb305f475f | note | ACTION (Hold, Monitor, Witness) - W
bfccb06c-34ae-54ad-bfb3-55a551c3d73b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
629eb42e-55b8-53b1-b9c4-8220c5e7d642 | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
0374ff82-d082-5930-9bb1-bd78dd092537 | note | Records - Bag test records
| checkpoint | 4.4 - Pavement construction: Sub base and base course
cb80c122-1cf9-5e63-b603-e0b2ba9e671c | note | ACTION (Hold, Monitor, Witness) - M
55745685-ca12-56cf-ad55-0558d6bcfb76 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
dcd43ec6-7d4a-5a90-9ce0-6af7b1f556f7 | note | Frequency - During Construction
fb172aef-b24c-536e-aa97-2b168ed22b4f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
54af69e1-77c0-5605-923e-3ea746ea0a89 | note | Conformance Criteria - Sub base and base course to be placed in accordance with TNZ B2. Compaction required in accordance with NZS 4407:2015. Cement supplied to NZS3122 and stabilised in accordance with TNZ B/5.
6f540409-c418-5191-8a59-2b71a2166ca8 | note | Records - Photo's
| checkpoint | 4.5 - Sub-base construction
817110a1-3da4-5632-855b-edcd072f715a | note | ACTION (Hold, Monitor, Witness) - W
6742271d-37bb-56a6-a23b-2dd19fd866f6 | note | Specification/Drawings Reference - TNZ B2
792c1fb2-28af-5b8a-8646-9f5fb3210a4a | note | Frequency - Every 20m and/or at random
5ac77008-8fa0-527f-bd4c-c385e891ce21 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
5181a94f-9752-5b57-acba-acfdde25ceb4 | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%, Average 95% of MDD with nothing less than 92%
8cbb7d97-87c6-579d-9ff6-523dff586dc8 | note | Records - Test reports
| checkpoint | 4.6 - Sub-base construction
52b24b3a-83d9-5540-99d7-5a43b44b0b83 | note | ACTION (Hold, Monitor, Witness) - W
51be4e72-aef6-5fc8-965a-c9a400a6164e | note | Specification/Drawings Reference - TNZ B2
3a8c312e-f53e-5748-bd0d-9771f2eebf7a | note | Frequency - Every 20m and/or at random
dab84777-e98d-5bbd-a022-31e2376b24ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
2a256567-5f53-531c-9de2-c8a52fe79673 | note | Conformance Criteria - CIV>=25
fb660500-8100-5640-aa05-4a733de3888a | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
| checkpoint | 4.7 - Sub-base construction
4671bc3d-22bd-5d06-8d41-14a1c51b0d1d | note | ACTION (Hold, Monitor, Witness) - W
6af96b19-be96-5160-a9ae-8b21c57f93b6 | note | Specification/Drawings Reference - TNZ B2
fe22fd06-761f-5e39-9d78-adb55e46dcd3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
cd87e44e-9a52-51a0-812d-f4d83fdb6597 | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
b00ac2c4-2afe-5d99-bce0-8c5893d0fba9 | note | Records - Survey as-builts
| checkpoint | 4.8 - Basecourse construction
59565f1f-e742-587f-aac4-4ed220f0be55 | note | ACTION (Hold, Monitor, Witness) - W
ecf1921e-9394-50c1-8bcd-0516b9bb7744 | note | Specification/Drawings Reference - TNZ B2
09f7e13c-fdd1-593c-aba4-248e82160d04 | note | Frequency - Every 20m and/or at random
ce8387cc-0b25-5f08-ba97-0902000bbf77 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
bb425576-355f-5cac-9073-242eca1b7cef | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%, Average 98% of MDD with nothing less than 95%
4915793c-a33d-528f-ba01-adf98b6378f3 | note | Records - Test reports, Photo's
| checkpoint | 4.9 - Basecourse Cement application rate
eefc9803-168f-5b45-b6ff-f8cf0543bd31 | note | ACTION (Hold, Monitor, Witness) - W
2cc6bf52-a046-5f24-b0e1-86d2c94a2680 | note | Specification/Drawings Reference - TNZ B/5
1979dccd-90da-5c76-ad40-b82cb21ee0b2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
24a7dcc8-074a-5f28-8655-5e77d5dc0ecd | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
948a1fbf-b2bc-5270-937b-326f839cdde8 | note | Records - Photo's
| checkpoint | 4.10 - Basecourse construction
b2809508-80ad-5f07-803f-5c5009989323 | note | ACTION (Hold, Monitor, Witness) - W
65b3eeef-96ba-51b3-ae1d-b7cfcd00353a | note | Specification/Drawings Reference - TNZ B2
431ebb1e-3f9c-533a-b80a-b87c1a9455b6 | note | Frequency - Every 20m
1b4a8ecf-d0aa-5f22-b896-1f59b8f1d9b6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
67d56403-499e-5046-941d-2935d4b911b7 | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
a5848cb4-00fe-59d9-b4a5-58bb16510bcb | note | Records - Survey as-builts
| checkpoint | 4.11 - Basecourse construction
d694245c-8b3a-50fd-9f7c-90b7344bb526 | note | ACTION (Hold, Monitor, Witness) - W
b8e04bdd-330b-5cff-8933-206d29e964b1 | note | Specification/Drawings Reference - TNZ B2
e78397cc-e89c-5d25-ab92-f49ed69c045a | note | Frequency - Every 20m and/or at random
d448cb1c-a25d-5a9b-bb2b-1f2534f5786a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
8590ea8e-dfa4-54b2-8b86-f03f18beb37a | note | Conformance Criteria - CIV>=25
f6e63303-1408-58b6-8c71-e3a010d125e4 | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
| checkpoint | 4.12 - Basecourse construction
c7a01409-f9c0-50b9-be07-5d40f127846f | note | ACTION (Hold, Monitor, Witness) - W
246d0095-ca47-5939-9378-bbd594aee71c | note | Specification/Drawings Reference - TNZ B2
85edb96b-d490-5a7f-b948-3103778f4377 | note | Frequency - Before sealing
c5b76d4a-5044-5f2f-a71b-6916972fa106 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
aa7e6455-c163-57ec-8a21-86b5001cb67d | note | Conformance Criteria - Mosaic surface
cf8eae15-4e4a-536d-ad6c-8bff749f270d | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| checkpoint | 4.13 - Applying Bitumen
1b208aa0-3550-58cd-a74b-9f82bb50a2f0 | note | ACTION (Hold, Monitor, Witness) - W
d88ad228-04bf-5377-9322-c4c716c88ec0 | note | Specification/Drawings Reference - NZTA M/6
dd3f81f5-b3d7-56b2-aaff-2af00861916c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ff31b8e1-27ac-5ddb-a5e0-218003e2c4d9 | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
28154d3b-b2ff-555c-88d6-4a05f80248dc | note | Records - Photo's, Pre-seal checksheet (CS-4060)
| checkpoint | 4.14 - Degree of saturation
e7a00282-380c-52d9-b50c-7f371f511469 | note | ACTION (Hold, Monitor, Witness) - W
5cf1640b-1cea-5c2d-afba-d6dc9ac59dc6 | note | Frequency - Before sealing
7b1906a8-d1ea-59b4-b0ca-6550aa70b6de | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
bbeb4d1a-304d-5c9d-b66c-193eff011470 | note | Conformance Criteria - Degree of saturation should not exceed 80%
b7f0bfe3-311b-57e5-aa5d-61db4ab3c915 | note | Records - Pre-seal checksheet (CS-4060)
| checkpoint | 4.15 - Chip seal laying
b67a40c5-eed7-50eb-b190-543e0df9f894 | note | ACTION (Hold, Monitor, Witness) - M
ac79861d-73be-56ca-8ea8-d2b8fc85bb86 | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA M/6
c9d705cc-90c0-5b14-92c2-afd808f4fb88 | note | Frequency - During Construction
96d4120c-94a7-55f6-b12a-bdecddc9cc96 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
30260e0b-7633-5153-8ff0-202640bbb00e | note | Conformance Criteria - Chip seal will match existing seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
772f1aa1-d52b-583f-89ab-3557e71798a6 | note | Records - Photo's
| checkpoint | 4.16 - Verge
032f2c41-230e-5533-83d9-fbe4563ebd12 | note | ACTION (Hold, Monitor, Witness) - M
15ef146a-6d2e-5481-b9f6-163295a9eaf3 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
d45e62e2-874f-5489-85a5-eabc13a62400 | note | Frequency - During Construction
62ab50de-2177-5691-bd40-f1f919e2bb44 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bc40de31-e6dc-54bc-ad09-c839a6dd9593 | note | Conformance Criteria - Verge reinstatement to match existing
6a56a8a7-a3f3-51e0-8526-1f3b4869c1c2 | note | Records - Photo's
| checkpoint | 4.17 - Sweep & Line mark new chip seal road
cc54946e-c3e2-540e-b988-60e6da65b593 | note | ACTION (Hold, Monitor, Witness) - W
0d9b2772-1076-53de-9747-eddce6d37773 | note | Specification/Drawings Reference - TNZ P/12:2000
ea8d196c-f304-5ab8-aa7b-2ff59eab259e | note | Frequency - During Construction
fa11f26d-acbd-5368-a8f9-daa98c750616 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
059c4f85-aa1d-5ee2-96f9-d1982e581a5d | note | Conformance Criteria - As per TNZ P/12:2000
0d95f362-ecdd-5221-9f40-0ce430396284 | note | Records - Photo's
| checkpoint | 4.18 - Install Traffic services
b8ed0110-4dd5-5a5d-a815-40bfa102045e | note | ACTION (Hold, Monitor, Witness) - W
6c5fe011-6c15-5e40-852a-e9095b61ed90 | note | Specification/Drawings Reference - F3002D 2-U3436.BM
59f1eb50-79c1-5bf0-b580-1b24068b3835 | note | Frequency - During Construction
3212adb4-eb93-51dc-b749-21f98e3922b0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
406d6ee5-69f2-583d-aa65-35a26916f1ae | note | Conformance Criteria - Traffic services including signs and edge marker posts to be supplied and placed in accordance with TNZ C/20
1984da92-b7cb-5e21-81bf-895e69a54f12 | note | Records - Photo's
| checkpoint | 4.19 - As-built Survey
dac24ce2-cad6-56b1-9afc-62341879af1e | note | ACTION (Hold, Monitor, Witness) - H
2dd4c9ed-1dda-54a2-a74f-4951f9366c46 | note | Frequency - At completion of Lot
28fccd8f-48eb-5cf7-b934-6f020c98d0c6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
2739aa90-9602-56a4-8975-389b397aa1e8 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
635f52ae-34bc-522e-86f2-37964043babf | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 5: Final Inspection and Handover
| checkpoint | 5.1 - Quality Assurance deliverables
3a188a2e-7b4e-5ae2-a2a6-e7988254e9d2 | note | ACTION (Hold, Monitor, Witness) - W
fcfb7b96-8418-5abb-a4ba-ea2846757d0d | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
e4acff03-2b8d-58cf-8d27-2cd1d84fa02e | note | Frequency - At completion of Lot
bd6c3791-b80a-5328-a88f-b8f7f13a20e4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
b5ff29d7-cca9-553a-8275-b58a66a25fba | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
380f38a8-c5f3-5acc-bfce-711b99f09e9a | note | Records - As-builts, NCR's and RFI's
| checkpoint | 5.2 - Completion Sign Off From Fields Below
14de49a7-97cf-593c-b022-6bc3a00e4c5e | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation (old version) | itp | ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation |  | c13fcb74-c6bb-4ccf-af26-adfa7f821e68
| checkpoint | Project Site reps.
29030db5-c00a-5b76-8e85-eb4404a9a888 | textbox | CPS Eng.
b1819594-5ef7-580d-b4ab-2d32a8e7bbeb | textbox | Site Engineer
01af451b-070b-54a3-af99-fd72751c6a1f | textbox | Quality Eng.
| checkpoint | 1 -
6dea88ec-f58b-501d-93d7-ebe9321acfad | note | ACTION (Hold, Monitor, Witness) - H
e2b7f8d1-f743-5c3d-b96d-ddeec4662f68 | note | Detail - Earthworks and pavement construction shall be completed prior to barrier installation.
3d1b7539-b5a4-5fb0-96a4-7a711a9a67d5 | note | Frequency - Prior to commencement
f7f07292-9d4a-5fe9-bd99-544ff0e59e66 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 -
b4d1b46c-d3cf-5dce-8af9-9b2118e5b1c1 | note | ACTION (Hold, Monitor, Witness) - H
fd791560-24a0-5cba-89b2-5614beb3ff29 | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
45bb7fb4-fa52-5425-9cee-20e73b2cdc4e | note | Frequency - Prior to commencement
da9da46b-3e10-5b2c-a0c4-46c90b193eca | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
8cf02767-536a-5b90-93ba-0fb1a6a07af8 | note | Conformance Criteria - National Standard for Traffic Signal
e1a6c097-4c60-5fd5-992e-458a89670ed9 | note | Records - OFI or NTD/NTC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout
cc7b4c94-fcc6-5d9b-b31e-c4c3b73a0444 | note | ACTION (Hold, Monitor, Witness) - H
74046930-de13-54a9-97bd-75341a09cc5f | note | Detail - Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred.
eecd08ac-cfc5-558e-8fc2-29e426462a0e | note | Frequency - Prior to commencement
9179c29a-c84e-5494-b4d1-e5af0211fbf0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
ed185c4e-f0e5-5d57-a2de-4d45da1890d4 | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
58cc6129-b50b-54bb-99f3-272f57897a2e | note | Records - Approved Construction Drawing.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Material Compliance
233b4d6d-2bb1-5890-a1a7-9d78ae99e9a0 | note | ACTION (Hold, Monitor, Witness) - H
ab460161-921d-51a5-88d5-129389fdcdc7 | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
5432a543-85de-50a3-ac6e-93a1495fe1f3 | note | Frequency - Prior to commencement
129c1afb-386f-5c1c-bea0-4f202db11fe0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
3c1bcf6a-5c66-58af-b5cf-d955a2b528ad | note | Conformance Criteria - TNZ M/23:2009
5a71919f-4867-5c44-b0d4-c8fb1222b41e | note | Records - Manufacturing certificates and delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Guardrail Installation
635c447b-241f-562a-a41a-e64794178222 | note | ACTION (Hold, Monitor, Witness) - W
535dd2ef-9199-5ec6-ae4a-eaeba9eee84a | note | Detail - Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
fa3ee647-49fd-5f03-b55a-d00991d50621 | note | Frequency - During installation and on completion
48aa63b9-dccb-50c0-af1e-1f9548ba3a66 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
ddd40a3e-864f-5ed9-bed5-1b156d454036 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
f20f2faf-8ae1-5e13-b2f3-05d312ee7ed4 | note | Records - CS-4117
| checkpoint | 6 -
bd31f059-a6ae-58f5-a3d1-0f696684cea5 | note | ACTION (Hold, Monitor, Witness) - W
fc916c8a-8f72-59ff-b542-a84c12b3b363 | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
3b14b24f-290a-5901-8e36-881d6e834327 | note | Frequency - During installation and on completion
2e01dd05-689a-5aae-aa45-8fa7d0d6c2a1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
b473369e-cec7-57a9-9841-1fee3b11c242 | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
383552a4-6603-5ef4-a69c-09d1a17fe519 | note | Records - CS-4117
| checkpoint | 7 -
c4779109-59af-5f99-b511-8b2d4b38941e | note | ACTION (Hold, Monitor, Witness) - W
b42d7b6c-a6da-5bc4-a39b-0b853b6e25b6 | note | Detail - Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
730916ea-5aaa-5269-8362-6450c76557d9 | note | Frequency - During installation and on completion
f2793c75-5064-51b2-b568-c5ed5f5c9e44 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
8fc72101-7539-5344-9387-ee862663bddf | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
fdb25ff3-fa19-5687-b44e-9fdd6bfd0b10 | note | Records - CS-4117
| checkpoint | 8 - Lot Number QA File
6a94fcf7-bf73-5fb0-85cd-bc85e8b1aea6 | note | ACTION (Hold, Monitor, Witness) - W
9faec207-dc75-5bc7-beb0-899cf0eb72d0 | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
cf38c6b2-2650-5b7e-a488-41a027fdfd23 | note | Frequency - At completion of Lot
8404a664-fc35-5666-89c0-37f8b6713dd5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
e114dbe6-7bbd-5767-9f8a-ae0cb7cfacad | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
8f12b964-f263-5df6-94fb-6ad076e6ff68 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 9 - As-builts
f873b643-3c92-5754-a495-8f8e9fcfc7ba | note | ACTION (Hold, Monitor, Witness) - H
baaa1cf1-66b9-5b21-97d8-5ea87ed9f116 | note | Detail - Red pen mark up drawings to be included in QA file
677c987d-f423-5afe-8ae3-e23dee0e244b | note | Frequency - At the completion of the Lot of work
46f55ef4-025d-5ae3-98d1-7284c2f83ef8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
b4a953d2-9324-5f84-b162-c5d61b856abf | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Quality Assurance deliverables
488bfea8-12ee-5683-a6bb-e585b6e494e5 | note | ACTION (Hold, Monitor, Witness) - W
7bd1409e-5c51-574a-94ea-5d1a577d0ab7 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
afdb8cde-14df-593c-9b6d-cf1b34638285 | note | Frequency - At completion of Lot
7d7ce66b-c1e6-5c98-b8ad-041593cf4433 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
ff76fa94-d064-5be4-bdbf-4cf71d915da8 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
77b45e4c-4079-5210-b526-133a44e1be5f | note | Records - Asbuilts, NCR's and RFI's
| checkpoint | 11 - Completion Sign Off From Fields Below
466662aa-c337-5563-97ac-633f107d1786 | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) (old version) | itp | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) |  | 94259252-c925-4900-855f-1a4e517fa531
| checkpoint | Project Site reps.
2e08fbd2-a3b6-5d62-b0f9-a0ada44c7a37 | textbox | CPS Eng.
54611865-1909-590a-9a58-5307fac3e2ee | textbox | Site Engineer
f52a4f33-a0b2-56a6-8161-21ff78fd0212 | textbox | Quality Eng.
| checkpoint | 1 - Erosion and Sediment Control Plan
9c4923b9-26fb-5282-aa40-54bb2ea3f2db | note | ACTION (Hold, Monitor, Witness) - H
6f087281-1ae9-5781-b797-6fc0160e9bb4 | note | Detail - Need ESCP before construction begins
87d943c6-33f2-5779-984f-eba7f4616c40 | note | Frequency - Prior to commencement
8668f1f6-76e5-5e50-bdea-669bdda4c3c9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
41c753fe-56e2-5a23-831d-ad7e9f187873 | note | Conformance Criteria - Erosion and Sediment Control Plan must be submitted to the design team
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 -
b37b7eab-1daa-5df1-a8b9-5c3586ddf343 | note | ACTION (Hold, Monitor, Witness) - H
b30b8259-014d-54d2-bd15-5e378228fb82 | note | Detail - Implement ESCP approved by environmental team
40c09d8e-65c6-5de3-9778-02ddbe572cdb | note | Frequency - Prior to commencement
fdc5d510-f84b-553f-9689-b459ef3b2fad | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Road Safety Barriers (1)
f94407f6-4848-5fd5-87b1-196ecaa64f75 | note | ACTION (Hold, Monitor, Witness) - H
37660f0f-ccd0-558f-86cb-ad824d686127 | note | Detail - Proprietary barrier system type and installation methodology
78a5d5bd-46c4-5c85-9647-bbaa5209dc18 | note | Frequency - Prior to commencement
193f83c4-110f-5354-bddb-a66aade4f46a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
c9091017-556c-5a3a-b5e1-2b57e0e43d00 | note | Conformance Criteria - Approval from Design Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Road Safety Barriers (2)
77d2929a-19db-531a-a3ef-2319769c19bb | note | ACTION (Hold, Monitor, Witness) - W
cc7728de-2884-5ea3-996c-648d6282b8b5 | note | Detail - Propritary barrier system compliance records
4764b12e-959d-5f2f-8a57-246dfb9164b9 | note | Frequency - Daily
cc3a4fa8-ceda-5872-982f-f2396fd713dd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
6606412f-8816-5874-950d-f845e8aec77e | note | Conformance Criteria - Daily checks to ensure the safety barriers are instyalled correctly and that no damage has been sustained
| checkpoint | 3 - Clearing & Earthworks
4281375b-b432-5196-bcdf-7f9fbae85b1c | note | ACTION (Hold, Monitor, Witness) - H
12aaeaec-450c-5e32-8507-7f7a4aa4c70d | note | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
463321d3-8425-5738-92e6-65c2465fe3b1 | note | Frequency - Prior to commencement
758402c3-e96b-577c-99c8-e13f4c48b912 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
11f96e6a-98f7-5190-991f-49809136af49 | note | Conformance Criteria - In accordance with TNZ F/1
472762a8-38ff-50b6-be65-9bbb37062f1d | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 -
cd9254a7-36ea-561b-9860-907a9fefcb42 | note | ACTION (Hold, Monitor, Witness) - H
2bd05ba1-e814-53f2-bf2f-23b6078ec335 | note | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
3c8404ec-0f36-5f9c-bb40-912fc9b64f12 | note | Frequency - Prior to commencement
5019dac6-4bff-5295-bc90-b1efb136095a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
14bdf43a-5958-59ea-b09e-913e8f4396a1 | note | Conformance Criteria - In accordance with TNZ F/1.
af911c5e-396b-5e8a-ad8c-ff5fed141144 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
ae1cf51d-518a-597d-9a19-72e9150cee06 | note | ACTION (Hold, Monitor, Witness) - H
e01d78e4-a035-5fc1-bf6e-974afaedbde6 | note | Detail - Arrange for a set out survey to be carried out & check against design drawings
8dedc862-2ab3-5aa7-8178-c7c4cc4269cd | note | Frequency - Prior to commencement
600f1aa2-be0d-5eba-8cc3-2e39cce9a3d5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
9fa88142-0560-5af0-a89a-6e02237f0238 | note | Conformance Criteria - Consistency with Construction Drawing
ef7fd4bb-c2d3-5306-880e-267b88f14730 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance and Methodology Approval (1)
7924f54c-55be-5e73-9d8f-ea3aa0a2128f | note | ACTION (Hold, Monitor, Witness) - H
c785dfa6-809d-505e-8c2a-e5b3e726765d | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
a72c1159-69b0-5ec6-aac0-19bc89bdf12d | note | Frequency - Prior to commencement
12bf91e7-781e-5da9-9ee1-1385398660e9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
f334f386-37e0-5705-a522-53c520e80491 | note | Conformance Criteria - Grade 500E soil nail
9e96c3fc-3a02-59f5-8642-d0b5e436a32d | note | ○ Class II corrosion protection
a5a5d80f-85f8-5a0d-9cbd-35df09c12f79 | note | ○ Lengths and diameters shown on drawings are the minimum required
6180addc-c69e-509f-845e-e78fafa02b63 | note | Records - Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance and Methodology Approval (2)
0bebe6dd-6a7b-5648-90b1-3e097b3a7e5f | note | ACTION (Hold, Monitor, Witness) - H
32b22426-2b02-54d7-86a0-1b30a8f2df9a | note | Detail - Concrete quality plan
7e56dce0-4256-5d90-9c08-2d7a804bc232 | note | Frequency - Prior to commencement
518ccda1-e334-56ca-a104-9afb67c1f711 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
a3b303d2-4aab-51f4-8afc-2b4f3e45bb72 | note | Conformance Criteria - Including:
ee761071-342a-5d06-bdec-e6a460537b29 | note | – Name, qualification and expoerience of concrete works inspector
642e355e-af4a-5e90-b55f-2383b894e9ed | note | – Form and content of concrete placement card
af257b23-aa95-517e-ae96-5dfc5de47b73 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance and Methodology Approval (3)
f7e03c44-5a87-5789-ac43-86d0fa49d817 | note | ACTION (Hold, Monitor, Witness) - W
9ddf62f1-fd3b-51ed-bc56-21d9e725754a | note | Detail - Details of concrete supply plant, copy od certificate of audit for plant
779d825b-217d-5348-b473-1376eeb0471a | note | Frequency - Three weeks prior to pouring concrete
da91a3cc-9dce-5f24-a434-6794cc29d3d4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4afbce4f-9d99-5c00-b7c6-3fcde734c63f | note | Conformance Criteria - Including:
77a84885-2a90-5cc4-aa82-201a93fbddfb | note | – Plant test Results
4b90e87b-da89-5e0d-b3f6-6b0de9cc6cd6 | note | – ASR Compliance Records
cf6513a1-9eae-5cc3-b6c4-2c8a3bcef0e6 | note | Records - Email
| checkpoint | 6 - Material Compliance and Methodology Approval (4)
28af4e27-67a4-5019-8172-7cfaacce26be | note | Detail - Concrete work plan
b7d611e9-d81d-509f-89cf-531dc8e42344 | note | Frequency - At least 10 days before commencing works oinsite
340cffae-6883-5d87-9979-85ae0b335355 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
5aea05ce-7dee-5d52-8fc0-07b938fd1bd3 | note | Records - Email
| checkpoint | 6 - Material Compliance and Methodology Approval (5)
238bd1ca-ab0f-58b5-86cc-48dd079e82cd | note | ACTION (Hold, Monitor, Witness) - W
def2d018-bed9-5f35-afc4-97b182e18e09 | note | Detail - Reinforcing steel manufactureers test reports and certificates
14cf4d8e-222d-58ca-a22b-d3b24de161c2 | note | Frequency - Prior to undertaking works
d14ccb4f-73c5-5813-a8ff-8dd98b259e3c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
fc3cedda-658b-5f89-8763-59bd316fe249 | note | Conformance Criteria - Including despatch records
8d121cde-6829-5eaf-acf6-b7d269fe0390 | note | Records - Email
| checkpoint | 8 -
cc948d8e-fc09-5038-bd7f-1a0b303891de | note | ACTION (Hold, Monitor, Witness) - W
86f39136-e6b9-569c-9016-f465278644bd | note | Detail - Submit all concrete mix designs, trial mixes and compliance records
38f82903-3ee1-5b04-afb3-fa2d08158490 | note | Frequency - Three weeks prior to pouring concrete
fcd32786-381e-5d97-9b0b-bd5b85874215 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
ce6061f1-1982-5cab-b0de-4cd30052f480 | note | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
015f5c0c-b3bd-5d27-bf6c-40acc0cdafa3 | note | Records - Email
| checkpoint | 9 -
8a8134f1-284b-5dde-b04d-6c3252e9ede5 | note | ACTION (Hold, Monitor, Witness) - H
65c08e5e-6ceb-5e5a-a8d6-4f89b3f20d63 | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
3b7a6d00-ff27-5879-9ca5-a4c34e6a16f4 | note | Frequency - Prior to commencement
09a23709-f1f6-5baf-aed8-3b9ac57b84b6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
f1fcc6be-9b0f-5ea9-8e98-3deaac4bb841 | note | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
b2af9b3d-f2e3-5745-8700-0d1fb4f63a83 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 -
5853eb55-dfb2-5145-8ff2-05106696c74d | note | ACTION (Hold, Monitor, Witness) - W
b65c8cfb-ef28-571d-9079-79bbda5ea456 | note | Detail - Grout checked if its free from lumps & segregation
a674fe0e-6954-5319-b3fc-8eecd07eb6df | note | Frequency - Prior to commencement
a3f9beb4-9e72-57a1-98d6-58957d645c67 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| checkpoint | 11 -
35b6c3a3-c568-5e9b-b4e3-46f9de823b12 | note | ACTION (Hold, Monitor, Witness) - H
c0cf27d6-11ce-5691-87c8-4b58c71c1604 | note | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
4892e9e4-4b78-53fc-ade4-8092c1b42858 | note | Frequency - Prior to Commencement
375bd94f-8a51-5ece-8d40-2a067026b31b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4b1be4db-032b-546b-a978-cdd90d2cb3bb | note | Conformance Criteria - If required
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 -
7b40de65-84c3-5055-bcde-1e7bd6e30ebd | note | ACTION (Hold, Monitor, Witness) - H
69c5bf4f-bf11-501f-b0e4-aa2f90ccbc18 | note | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
abcad524-d823-58c5-bd19-5d2d3e19f0b2 | note | Frequency - Prior to commencement
d430108a-28ee-57e2-ba20-5e73efb87277 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
c0ec667e-7c91-5101-bf63-c1275ec0e623 | note | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
| checkpoint | 13 - Working Bench
d05ec5a1-da9b-5eec-850d-0782ab8ed225 | note | ACTION (Hold, Monitor, Witness) - H
7d8ccc5e-1e91-532f-a264-4f1a8b021570 | note | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less.
3be47c70-9eae-5cfb-b45b-ddd0bb6e3e3d | note | ○ The construction team shall protect the face of the excavation from damage at all times.
958e9c02-6712-5d9c-b605-d8c4692cc380 | note | Frequency - Prior to commencement
0991d622-6e2d-53cd-8c5b-7ae9e4a17c35 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
1accea89-427a-5dc8-a526-59782d1ec236 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 21 -
7a29f3f3-c580-5d36-a879-a74d84f092ad | note | ACTION (Hold, Monitor, Witness) - H
d69779ea-2fe7-5333-b3b9-f50a10987b74 | note | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
2147da13-2ac3-5e29-9253-7f2eafd28b62 | note | Frequency - Prior to Trial
f48bece2-d2f1-5368-a5bd-2324a04f94f7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
3b23ec92-7fb4-5aba-ad50-86c6eac6a81b | note | Records - Photos, Site Diary
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - (1)
9f8d3823-513e-5209-9e9c-137af1450fa8 | note | ACTION (Hold, Monitor, Witness) - H
6ffed7d6-3e21-507a-9b96-a685cc43db85 | note | Detail - Insert micropile bar (ReidBar RB32) to full required length
e314c402-28f2-5fe0-ad8c-257f3a6bddb8 | note | Frequency - During Construction
2d508046-64c2-5eb6-8dff-59250abe8d87 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
04d3d86b-138c-54b3-8c0d-7dfb909737c8 | note | Conformance Criteria - Embedded length of micropile 3.0m into ground
494e90db-6153-5756-a72b-20a672c4a7ab | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - (2)
8ed618f7-2498-54b3-ac5a-2dd8b865cd6c | note | Detail - Drill hole
d570e94e-2bfe-5ab3-904c-c91e35bf70a6 | note | Frequency - During construction
25184bba-5b1e-5ed5-9735-662b1ca00e62 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
e2d0f7bd-dfda-5a66-b9e8-b5c5de3bfb4d | note | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
0dfc5cef-17d9-5758-9886-447dd648970d | note | ○ Submit all installation records for each soil nail and pile.
| checkpoint | 29 -
061b1afb-356a-5705-949f-dfa51a91e4e4 | note | ACTION (Hold, Monitor, Witness) - H
ae61c3ab-1250-53cf-aa41-4f0f5c280d5e | note | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
aecc33ec-43ac-5554-ae54-8f73399d7790 | note | Frequency - During Construction
dc5eae4f-88fc-50d6-b701-fc726b772534 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 31 -
865d3ff4-20d4-5c38-a014-c52ab95580b3 | note | ACTION (Hold, Monitor, Witness) - H
83da2bf5-586b-52c3-a619-6e89ee0f383b | note | Detail - Insert soil nails as specified
f76f8fdd-80cb-5fea-a4b4-355937c68967 | note | Frequency - During Construction
60335836-dce2-5aaa-befe-087f0b5a49bc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
de0fcc36-c47e-5dc6-8bf4-0f03c982377f | note | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
5c735cdd-f329-5cba-bfbd-e24c31503136 | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 32 -
e18c8d52-22c2-5d1e-8224-0631d890cc04 | note | ACTION (Hold, Monitor, Witness) - W
3f306aa4-7a59-50bd-a505-7be978d6e2e7 | note | Detail - A record is to be maintained showing the type and installation date for each soil nail
1d3aae72-3fb2-5c57-b9ed-3de32e2041bd | note | Frequency - During Construction
e5d82ec9-6570-55c3-bbe0-f9636760354a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
9be4e0b3-23a9-5ca2-a1c4-dde0b4ea335a | note | Conformance Criteria - Installation records shall include:
b5d45de4-f3a3-5fe5-8eb2-b37ff25b0bc2 | note | – Length of bar
ed148775-d2fb-52df-b8a1-93f70710edb9 | note | – Depth of drill hole
cc043f9a-ca59-589f-b764-b9961466e3ff | note | – Inclination/Verticality achieved
5c4c2083-9cab-5b7d-9a1e-9c42fca9e4b2 | note | – Level of grout placed
eb50d99d-3fbd-512d-8129-1638ffca87b3 | note | – Batch numbers associated with grout placed in each hole
1ec141b4-6f4e-5f0e-93b0-ef83c3b77347 | note | Records - Subcontractor QA Records
| checkpoint | 18 -
1337721c-5957-560b-bb27-3b4ad8d85d02 | note | ACTION (Hold, Monitor, Witness) - H
47d3a89e-acea-59ed-9bd4-3f770e847f44 | note | Detail - Install Grout
db81b36b-dc4f-53a3-a7e1-b86413ee5f87 | note | Frequency - During Construction
d476496b-4277-5f13-9c41-c7d38a9b490d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
530473d2-4a5c-51ad-9dd5-7d35de72a55e | note | Conformance Criteria - Including :
ea775a6a-c04f-5ff2-90bc-46e5a0182f79 | note | – Concrete despatch records
6feee161-2388-504e-b824-e8d7adb2ba0f | note | – Compression test results
89e6ee14-ed27-5906-971a-5e99504a2e2a | note | ○ Must notify CPS for any failed result and cease works until resolved
9360a16c-235b-5769-ae62-e1d697aea97e | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 33 -
f5638925-bda7-5a8f-9852-325f74b991d2 | note | ACTION (Hold, Monitor, Witness) - H
7d8495b8-05cd-57b9-8085-52611c43edb6 | note | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
f1dc0494-8138-5e7a-ba2d-37f124137dc5 | note | Frequency - During Construction
f30750c9-76ee-52c2-b49d-bec1ba0adbb3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3db3e17d-24b9-5bb1-9502-1d51e0570be0 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 34 -
7d85c194-ea63-58e7-9fa9-92b5fc54b828 | note | ACTION (Hold, Monitor, Witness) - H
48eae4eb-52f0-5799-9b9c-0e5b4d3d3ec8 | note | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
7ad16412-46d1-59eb-afee-ea2640fa4490 | note | Frequency - During Construction
79680c5e-cb37-5ca0-be8e-9a7ff2ee34be | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
48d09ecf-3e2c-526a-ae8f-7da459e30060 | note | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
c65839f7-28da-563b-aecc-78c3e2c07baf | note | Records - CONQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 35 -
d4491a30-eb7a-5d20-b58c-924012ec43b8 | note | ACTION (Hold, Monitor, Witness) - W
da03c785-6efd-55d5-9d73-9c42268c55e4 | note | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
a8c10b7a-341f-5942-80bd-3f2953ef617e | note | Frequency - During Construction
5f20c536-106a-51b3-bb27-62a51085ddf9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
4bf97c30-aeef-5759-97ac-92c59d35da0a | note | Records - Subcontractor QA Records
| checkpoint | 36 -
4a32e18c-99d4-5c43-b757-d786aeba77fd | note | ACTION (Hold, Monitor, Witness) - H
b463f295-f826-5e3a-b7a9-95ce8e67ebc5 | note | Detail - Install Bolts/Nails washers & nuts
64bed8dd-c015-533b-be02-65c3b4230307 | note | Frequency - During Construction
1b701791-6a15-5882-839f-0eaea1c9c275 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
bcb861f1-6ce6-5bdf-b463-7c7a68915431 | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
64b7fb8d-9a30-5fb7-8471-6d939c2270ff | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 37 - Testing of Soil Nails
f6e444cd-90ca-58ba-90b3-e5dc76a0f3af | note | ACTION (Hold, Monitor, Witness) - H
a0b94712-f11b-5e61-88be-88a6ce0f2f56 | note | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
c325c938-e2e7-5976-92cb-c7a39a3a24ac | note | Frequency - After Construction
72afb0a6-3920-5eb7-bf2c-096e1f09f411 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
b26985e6-87e0-54c3-ae3b-5914e39c98df | note | Conformance Criteria - Certifications of all testing equipment within the last 3 months
3fb64ab3-2a3b-5518-9fc3-c46c3082fec2 | note | Records - Certifications
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 38 -
f1d9f2b7-9029-56ff-98a5-a270527a556d | note | ACTION (Hold, Monitor, Witness) - H
9171556b-f9e0-563b-a79f-4546327082b4 | note | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
1618ae3f-cc1d-5a48-a848-8fc68e6e5de7 | note | Frequency - After Construction
54fd5915-6c04-5eca-8d55-4c0799f84f36 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 39 -
69f7a75b-04f1-5702-b4c4-ef0d1a495a59 | note | ACTION (Hold, Monitor, Witness) - H
6589b5ab-faf7-5687-a780-8ce513ad7368 | note | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
b395ad4f-9edb-5ffb-828b-cf4d2dd1e578 | note | Frequency - After Construction
b2637abb-4ae7-57f3-9796-c2d9aa4d45a5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
b45b3c9d-ccf0-5998-a118-0b1b3768b56c | note | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
2955c343-7592-5443-a32b-764ce5dcd8de | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 40 -
0b537d9f-77cd-552a-8c33-4a93114073d3 | note | ACTION (Hold, Monitor, Witness) - H
6389a486-de36-5b57-99e6-a6e8bc53ac43 | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
5212ceee-d31e-54c7-ba7e-1bf340bc61c5 | note | Frequency - After Construction
4f3df9d2-ead0-5600-881d-4efbbdf5ae7b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7fa025be-86cd-5f34-a268-3ada64c26c03 | note | Conformance Criteria - CPS Engineer to give approval via a NTC
3b34cf71-463b-5343-9e73-b9f989facbda | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 41 - Shotcreting
e4154589-58ac-54f7-888a-26170a7f80ed | note | ACTION (Hold, Monitor, Witness) - H
a40a4dcc-44bf-5774-813e-ee77ecb5a310 | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
1cab9b94-f783-5973-b861-8b05614643f7 | note | Frequency - During Construction
dda277ac-2127-539f-be53-86c350dc2ded | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3b6a9d14-ff99-561f-9993-039b4831bf10 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 42 -
1f4c1218-eb10-5f98-9e96-dbe776e51cb5 | note | ACTION (Hold, Monitor, Witness) - W
e4315cbd-239c-5b34-823f-a732a5db353e | note | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
5d16ec90-b722-54d6-9d7e-dd39f69a83dd | note | Frequency - During construction
50f9d0e7-86e4-5cc6-b750-20e77a7da38b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3175f56a-8397-5641-b6ac-3b2d8ff5ed62 | note | Records - Photos
| checkpoint | 43 -
61454bf7-5f0b-5274-a651-57bf64d75d2f | note | ACTION (Hold, Monitor, Witness) - W
c22eddac-60f5-52c6-a37f-7f2d6f623d34 | note | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
f420409a-d8e3-5139-a098-a37088b7291c | note | Frequency - During Construction
7174d3a5-f81a-50b7-8062-aeed5f6bd220 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3ab633b8-0e62-5fab-9cab-ade69fe271ae | note | Records - Photos
| checkpoint | 44 -
08b30fa7-f611-5af2-bcc3-aaae13d215e9 | note | ACTION (Hold, Monitor, Witness) - H
1190faf1-c170-55b5-9f0c-fd7d7612fb96 | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
252c24fb-5b11-5b4c-acbd-828217ec25b1 | note | Frequency - After Construction
c256687d-e467-5628-90a3-b92090932c17 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
20cbdd3b-74bc-5926-8dce-e0ee29b08c15 | note | Records - Test results to CONQA Procore
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 45 -
2d127220-0560-58e6-a733-eec5aeb5accc | note | ACTION (Hold, Monitor, Witness) - H
724598e5-e2d1-5075-ab3b-ba85522208ef | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
014e80a0-f162-5403-99a6-33237bfed7eb | note | Frequency - After Construction
cd26d7bd-886d-50ae-a17b-b025db24b4e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4167d080-eec7-5ba3-bca5-bd8329d503a0 | note | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
26e4607f-34f7-5f21-ba5b-a5452fd44e66 | note | Records - Email
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 46 - Post Construction Survey
6bee2354-423b-53f4-b6e6-923291f08ac2 | note | ACTION (Hold, Monitor, Witness) - H
1154b71e-8116-5446-b9cc-93893ccc4a9e | note | Detail - Survey final position of bolts for as-built purposes
8032a508-14e8-5a98-9eb4-da7d1188d7f4 | note | Frequency - At completion of Lot
b6912d89-32ba-5e24-9fd6-98be3ad02134 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b6d790b6-9c95-5b22-ab79-08bd512ea0c9 | note | Conformance Criteria - Survey report complete and conforms to specification
d405e6f8-9e45-5f53-bd2f-2d80a93286db | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 47 - Lot Number QA File
bf90cd8f-eef5-56b7-87f5-7cc60cceea87 | note | ACTION (Hold, Monitor, Witness) - W
ba5fca82-2437-5527-8bfc-43bc48b0adab | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
dfb01f9f-07e2-5a94-a005-1e149578c4a6 | note | Frequency - At completion of Lot
38c61592-223a-5e17-a4f6-8d5491773085 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
0e361d37-2b15-52cc-8ec4-dd9858d845d3 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
9561ca11-5d2a-5faf-82bc-12623a7674c1 | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
| checkpoint | 48 -
c06cce51-93c8-5346-bde4-ff6d7533d838 | note | ACTION (Hold, Monitor, Witness) - W
5acdee03-8adf-5209-9099-94e0d8dd466d | note | Detail - All subcontractor documentation to be included in QA file
63ff7980-238e-5b46-a7c5-09cce94944fc | note | Frequency - At completion of Lot
09b3a1b5-f4ee-5818-89c3-cab8321722af | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7ab619be-78c1-5bf0-b3cf-cfaa79208795 | note | Records - Subcontractor QA Records
| checkpoint | 49 - As-built
1c6f8078-c481-55dc-ac87-07240043c399 | note | ACTION (Hold, Monitor, Witness) - H
ddde80ac-7209-503c-a476-dd9d0bc77d8f | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
77e1d642-efd3-506d-a962-6f8ecf9796fc | note | Frequency - During and at completion of work.
91e43805-8cca-595b-bcdb-826e7fbc0f8f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
c7e62184-7943-596a-aabe-bf399c11b37b | note | Records - Survey receipts, As-built plans
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 50 - Quality Assurance deliverables
44c48998-6a4b-53b8-8b3f-f65af6ee4723 | note | ACTION (Hold, Monitor, Witness) - W
127de175-ba10-5b4b-80be-61a993be103f | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
bdf86c6d-5c63-579b-972a-f8a9374f0011 | note | Frequency - At completion of Lot
f66e3a1e-e9d5-570b-80b7-1a50d7ecf890 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7f5fa922-e07d-5f13-9271-e0fe9c9d47c1 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
bf5a3195-1d2e-5a15-ac51-41d382687398 | note | Records - Asbuilts, NCR's and RFI's
| checkpoint | 51 - Completion Sign Off From Fields Below
2ca9959d-2d15-502c-afab-a25fa184aeb7 | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage (old version) | itp | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage |  | 770b6e32-6ce5-42cc-a44f-b57055e2d09d
| section | Pre-Construction
| checkpoint | Project Site reps.
79f83b13-569f-52e5-a9ca-b6fbfd50d7dc | textbox | CPS Eng.
c3a5e179-0f54-5b1c-ac95-2e9b1c1f0b09 | textbox | Site Engineer
04036cc1-181b-5512-acf0-f2381303924d | textbox | Quality Eng.
| checkpoint | 1 - Drawings and Specification
0e69d760-b4f5-58ca-b4c9-d97966bba459 | note | ACTION (Hold, Monitor, Witness) - M
5306936c-ea3f-55ff-9b7b-8334be494e42 | note | Detail - Check drawings and spec are the latest version.
b1998854-4929-5cfb-b7a1-63b70933b173 | note | Frequency - Prior to commencement
bba20ce4-39d7-5e62-9920-697756d76b73 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
| checkpoint | 2 - Survey Setout
a00e56da-431e-55cf-8234-baf98115dbab | note | ACTION (Hold, Monitor, Witness) - W
cdd4758e-87f3-55d8-b324-87c1a57b8fa9 | note | Detail - Set out as per design
803829a9-4d40-50b0-9926-2d7c2c827f84 | note | Frequency - Prior to commencement
4ef6441d-1475-5a92-93e0-7388dce1a266 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
26f6795e-45bc-5426-ad6a-6042a1bd8879 | note | Conformance Criteria - Check against plans for any discrepancies
d9ac2ab7-fbcd-5405-9ea6-d684d4a0bd86 | note | Records - Survey receipt
| checkpoint | 3 - Material Approval
4b137c95-6607-532e-a71f-22aac00978e4 | note | ACTION (Hold, Monitor, Witness) - M
f9260d02-fc90-5f4c-987f-71e346fedf2f | note | Detail - Materials as per design
f643a428-6917-5a97-962b-51c3c5224371 | note | Frequency - Prior to commencement
c2fb43c8-569a-560d-b8ff-2fd690a38a7b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
77a16953-d49f-5899-a9d4-add8886b203c | note | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
| checkpoint | 4 - Location of underground services
0dda9022-e22c-5de0-bddf-c5f9d67a0559 | note | ACTION (Hold, Monitor, Witness) - H
117fa14d-8b9c-58cf-b57a-12d6ed900100 | note | Detail - Ensure undderground services are positively identified and asbuilt. If the service conflicts with the design confirm resiolution with CPS
c30225b8-2ffa-5b4a-89dc-cdad703539a1 | note | Frequency - Prior to commencement
b3bee91e-afd4-52e9-b74f-fc209ef157fa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Drainlayer Qualifications
11d0be2a-3d97-5298-899b-08804ebe22d0 | note | ACTION (Hold, Monitor, Witness) - W
ffbfdeae-0dc4-5623-9ec4-19b252b625f7 | note | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
941dd3ec-c119-50d9-b8c5-edfbe808442a | note | Frequency - Prior to commencement
ccfc206d-debd-5180-bfc2-d394a38057e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
36421d97-414a-58e0-8833-4dac62c66150 | note | Conformance Criteria - Drainlayer Certs
| section | Construction
| checkpoint | 6 - Trench and excavate for pipeline to design subgrade
6e361085-f9bf-5ea3-ae92-55301d35b78f | note | ACTION (Hold, Monitor, Witness) - W
f5b3a719-6db2-53fa-bf84-6f02c23cc3d3 | note | Detail - Check subgrade with visual inspection and
a750e081-3732-5374-81c1-e686a268934d | note | Frequency - During Construction
47968c6b-9496-558c-9f99-6a800cba598b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
982d65b1-510a-58c3-a3c2-720cb24629b4 | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
ea6acd3e-448e-5213-b1f8-448b72cb486d | note | Records - Subcontractor QA Records
| checkpoint | 7 - Surface finish visual inspection
1768b7ec-dda6-5d2b-af77-b1f23fa7bfc2 | note | ACTION (Hold, Monitor, Witness) - H
97b39c38-5d89-56bb-89e8-891ddb09c2b3 | note | Detail - Site walk over
a256a169-8fd0-55e1-9d8f-0131d3cdfff9 | note | Frequency - Post Construction
5365fcde-752b-5cd7-b5f0-515342428a2a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
4f21f253-1d9c-5bc1-8105-af295a9ef691 | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
6924bbae-8745-5b99-95c1-dd8fb562799b | note | Records - Subcontractor QA Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - As-builts
5e019847-5c2c-553f-8837-d785d920a7df | note | ACTION (Hold, Monitor, Witness) - H
04cb7e7b-5897-598e-84e6-df89d07c2448 | note | Detail - Red pen mark up drawings to be included in QA file
5a89915e-0277-5fe0-980f-c754772a6df8 | note | Frequency - At the completion of the Lot of work
ec83cdbb-a0c4-5b29-90f9-ca9aecafba5f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
4e494b31-4ea7-554e-86e0-1f5384c48844 | note | Records - As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Quality Assurance deliverables
5c20ad53-eab8-5286-b737-2272f0e4e28f | note | ACTION (Hold, Monitor, Witness) - W
00cc0a1c-bd4f-56a3-9b66-95247775e505 | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
a9c57284-0bc1-5b8a-b37b-72f8a8b4f491 | note | Frequency - At completion of Lot
a0804abe-4d7d-51ad-9f66-7f032534c814 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
8700cab0-338e-51d8-a4c7-977e5cfcf9cf | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
87b2b2c0-1327-54fb-a1aa-11838e25c84a | note | Records - Asbuilts, NCR's and RFI's
| checkpoint | 10 - Completion Sign Off From Fields Below
9762feb8-90cd-5ba6-883e-5b24b024236c | note | Records - Signatures
| checklist | Ω (Deprecated) ITP - Te Puia Subsidence Site - F3001B Fault ID609 (old version) | itp | ITP - Te Puia Subsidence Site - F3001B Fault ID609 |  | 20cd30fd-064c-4178-b260-ef0bfb10f11e
| section | Section 1: RECEIVING INSPECTIONS
| checkpoint | Project Site reps.
387737d1-6f89-5c2c-ade5-30221700306a | textbox | CPS Eng.
4cb7b80e-8d0f-5700-81df-0383f8955348 | textbox | Site Engineer
a25aaa56-b259-52b2-a47e-a3a08d656df6 | textbox | Quality Eng.
| checkpoint | 1.1 - Rock Armour (D50=450)
fd751104-a075-5b11-ae0e-74d85fb3bc11 | note | ACTION (Hold, Monitor, Witness) - W
a26ef81e-5121-5097-91b4-d3092380b40f | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
777e6bb8-6ff6-5505-942d-62f478595537 | note | Frequency - Prior to commencement
c9ff6e43-c882-5ad0-ac3a-f9e2449d6251 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
d48ce603-f661-57c0-bec2-d6998e675d46 | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
739d14cc-f89a-592e-9a67-718b29c0b88b | note | Records - Material source test results
| checkpoint | 1.2 - BulkFill (GAP65/GAP100) or similar
c4cc4156-0e67-50f1-b353-941b69a337d9 | note | ACTION (Hold, Monitor, Witness) - H
973e9a7e-ee40-5171-9022-30a476e0297a | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
56986806-463a-592f-b833-fff5f0da9fa5 | note | Frequency - Prior to commencement
d009aacc-c874-5c42-ad92-1c89d4b09699 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
b28c5971-11dd-528b-a007-cb543128b4bd | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
004c911e-7751-56b0-b244-f2edc66e72bc | note | ○ Material source testing
d2faf1f8-a6f5-5634-befe-126a8fb00ef4 | note | Records - Material source test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - TNZ F/2 drainage material
67c8d7e3-28f0-5ea2-a69b-aef6e548cd85 | note | ACTION (Hold, Monitor, Witness) - W
1e0d6420-6b3b-5ef1-86c1-b2d85811b3c4 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2
0e13bc9b-e6c8-5ca6-ac68-0c486ca098a2 | note | Frequency - Prior to commencement
20edff98-18c8-5d31-b2d2-8eedc3425889 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
408b133c-6207-5137-8987-21f0cd36bf2d | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
6af6c48b-e7bf-5247-ac6d-feae285b8d96 | note | Records - Material source test results
| checkpoint | 1.4 - Class D A39 Geotextile
522366e7-d6c8-5dae-9b92-c79777ad79ad | note | ACTION (Hold, Monitor, Witness) - W
d7497e4e-57d5-5b2c-a845-1bfb67b71c1f | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
ab2c2ac4-cdfe-53e3-ab18-a37b58fd2a10 | note | Frequency - Prior to commencement
8d3ed4fd-9d92-5d70-8100-b5b68aaf93d8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
5e8ed595-40c1-5cd1-bafd-d8f15546945a | note | Conformance Criteria - On dry bed below fill
737594c9-a0e1-5b1a-83d0-929a2e3a24fe | note | Records - Material certificate(s)
| checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
d9cd11ac-7df5-5157-a865-a45f7f48e156 | note | ACTION (Hold, Monitor, Witness) - W
abd81951-2642-5bff-84fe-24d1fec1d374 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
eadd19ab-40f1-52aa-8757-24e2f6a40f19 | note | Frequency - Prior to commencement
7b83b49a-9c17-5199-bd96-f96fed967e91 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
5609ae32-516e-5404-8c33-7e4f379a8871 | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
e3fb31ca-4569-5079-9533-bafd262bc529 | note | Records - Material certificate(s)
| checkpoint | 1.6 - Biocore erosion control matting
301307e0-922e-54eb-9e6f-2c1b40c3d1bb | note | ACTION (Hold, Monitor, Witness) - W
ede3573b-d139-5eb1-b78c-f4f80c8f2073 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
b0236efa-e03e-5bb4-a5ed-d72baf8978b2 | note | Frequency - Prior to commencement
444074dc-c97e-5566-add9-4f67e01340e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
bc2b6686-91cd-5113-a577-80e3ef408a7b | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
37a7b7be-8e56-5290-b1f6-463c5808c933 | note | Records - Material certificate(s)
| checkpoint | 1.7 - Enkamat 7018
92d8c535-1c63-5391-9840-249b9d925ef9 | note | ACTION (Hold, Monitor, Witness) - W
60875ead-888d-5991-a5ff-35cfd7885cf9 | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
a377e86d-47f3-5195-9e95-388102027e61 | note | Frequency - Prior to commencement
4d3f9f66-1392-551a-bc6b-62f2559d0773 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
a043d11a-80a8-5fab-868c-cab32d3b64f2 | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
291cde82-7661-5ab9-ae06-ca31120e5fa3 | note | Records - Material certificate(s)
| section | Section 2: IN PROGRESS INSPECTIONS
| checkpoint | 2.1 - Survey Setout
29456b74-512a-54dc-9440-13ff561d9489 | note | ACTION (Hold, Monitor, Witness) - H
8bd0c152-c8f6-5a93-8179-7b66f59f9477 | note | Specification/Drawings Reference - Consistency with Construction Drawing
2ce8bf52-7fc5-5dea-a89e-c84b4ff5dd9d | note | Frequency - Prior to commencement
86f1dbb8-61bd-5290-8156-b361697e49ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
bfd83c62-be95-5f08-9a09-84ff6595f9b1 | note | Conformance Criteria - Set out extents of fill and check against design drawings
9f4a052e-eea2-580b-9fb1-e55ab24cb5e1 | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
5e12d260-e3aa-5c75-8448-909cb0082acf | note | ACTION (Hold, Monitor, Witness) - W
3e86b697-c26b-5f82-a300-9dcfdfa2f563 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
dc02935b-8058-54a1-859a-9a740ccc977c | note | Frequency - During Construction
6cb5d342-b243-543f-97cf-97f741c45c6e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
3810f695-3009-5a2f-b215-4ad5625b19c6 | note | Conformance Criteria - Remove and clear the vegetation
a1db5fd6-08ed-584a-b45f-dd46cf985220 | note | Records - Photo's
| checkpoint | 2.3 - Subgrade Inspection
bdfd71a4-b3ad-5949-af1c-525eceba6660 | note | ACTION (Hold, Monitor, Witness) - H
c3f41507-6103-57ad-872b-270dbe5d0f83 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
5eff28e2-c0bc-5414-b1dd-44d4b62ca814 | note | Frequency - Per area as required
24d8c89e-6fb3-5eac-bef9-414973509634 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager or representative
0034614a-f248-5de7-a846-ab568e49bb44 | note | Conformance Criteria - Inspect fill foundation.
2ad396c6-3ffc-582e-84cb-6eae59ae070c | note | ○ Fill foundation must be approved, in writing, before filling commences
46fa74db-4b7b-53c5-8221-ad5c40c76b08 | note | Records - CPS COR report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Ground Improvements
a9fa913e-e7aa-53cb-b03b-0c69ab4e8418 | note | ACTION (Hold, Monitor, Witness) - H
229e2fa6-2625-5e70-a532-2282e6ec13de | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
1448d6c2-2048-5c99-8092-313af21a3e7f | note | Frequency - During Construction
bcb3fae2-41b8-5500-878d-41178d6fd599 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
9848809c-dfa8-5c86-b3ea-556310267dfc | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
44a30e8a-57cc-596e-9e30-9ecb61efe5ca | note | Records - Photo's, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Class D (A39) Geotextile installation on the excavated face
9ccfa142-6a09-52d6-b275-33fae0a6b8b4 | note | ACTION (Hold, Monitor, Witness) - W
2993367b-c6ad-5c6e-9384-8b868fe521d4 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
8c6faf6f-9bfa-5942-aab0-1fbf32b52e0f | note | Frequency - During Construction
54ed3fd1-fa4b-55c9-a091-a5f826975636 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
e2df4d15-252a-5449-976e-91076397cc5d | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation materail and engineered fill.
bd2b65fe-26cd-5e48-9777-22126bfd8c62 | note | Records - Photo's
| checkpoint | 2.6 - Sub soil drainage
93207115-da8c-5d01-9860-386a8172b371 | note | ACTION (Hold, Monitor, Witness) - H
9a9e1b8d-60ab-51e7-a744-06e392533a72 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent
0973a1e5-e3aa-5ef0-a017-70ad46aa6703 | note | Frequency - As works progress in agreement with the engineer
86f5ce2f-39fc-5570-a177-ddfeb7af7846 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b50ba4f1-75e3-557f-9197-774ade71e41b | note | Conformance Criteria - Engineer to assess suitable drainage location and confirm drainage positions on site.
418b0bf1-274e-5fad-b619-366347815adc | note | Records - Photo's, Drainage Line Record check sheet (CS-4025)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
847c6f88-f8d7-5426-aa36-0565bf156c28 | note | ACTION (Hold, Monitor, Witness) - W
4a7d2846-2d44-5f05-929b-c00f6130f311 | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
d4c28b34-850b-5400-b70d-fb408e620cfd | note | Frequency - During Construction
77cd5ccc-a9fd-5d07-9925-425264a26d35 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
53545623-1cf3-52c7-a162-30e2788d546d | note | Conformance Criteria - Installed in accordance with manufacturers recommendations
011f95e9-b158-5019-a996-788608f67d6c | note | Records - Photo's
| checkpoint | 2.8 - Bulk Fill Placement
608faabf-9206-54e6-94c3-1fd3dd01cc0a | note | ACTION (Hold, Monitor, Witness) - M
f9c64c66-e7a4-5834-a562-5849f9557918 | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
027eb05a-db06-50c1-b98c-fbb1936950ba | note | Frequency - During Construction
b1b90da0-d10a-5f43-9c07-09d494ad27d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
de00e51c-edb1-5312-80df-9f3e115d03fe | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade
392da913-e13a-5cac-a56e-904762747785 | note | Records - Photo's, Bulk Fill Earthworks Check Sheet (CS-4020)
| checkpoint | 2.9 - Bulk Fill Compaction
fc6badb0-1e26-5ed6-83c1-413512eb1e0f | note | ACTION (Hold, Monitor, Witness) - M
3d09ba4f-fe44-5a57-a79a-f476c9fd6f8f | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
cad8da2f-13ef-5ff5-855c-4fc7edd07f44 | note | Frequency - During Construction
b54af2fe-10b1-571a-974f-77fe4be250ac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing (Clegg 100kpa)
7153015c-eedc-55a8-89a3-51690f942e94 | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
0519493a-f937-5801-b3f1-96f42ccb03ed | note | Records - 1M Scala Check sheet (CS-4000), Lab test report
| checkpoint | 2.10 - Form and cut fill batter as per design 2H:1V
7c51cf76-5002-5afd-935f-83ed9853126a | note | ACTION (Hold, Monitor, Witness) - H
f0242da0-8c7b-546f-9767-ecf51b6bbb91 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
48a2d9ee-377a-56da-99d3-709a828cc2f9 | note | Frequency - During Construction
94041f71-59dd-5a16-94dc-942091de5c56 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
fb70153d-f58f-5431-8515-22ad1426f619 | note | Conformance Criteria - Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations
ea1a5c5d-d2e4-504c-bc7d-6d9e9226b099 | note | Records - Site inspection on completion, Survey as builts
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Rock Armour (50-450dia) placed on the toe of the slope
c582850a-fb75-5c34-95b9-dc7ed15dd466 | note | ACTION (Hold, Monitor, Witness) - W
76e3b22c-c37e-5152-a1ef-82b0e4035086 | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
e775bda3-206d-533a-a01b-5b9e63467d8e | note | Frequency - During Construction
aeffda59-5db2-545b-8134-b0b25220ce2d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
14115f65-ae3f-5554-86a7-a5a3b45cd74f | note | Conformance Criteria - The buttress to be keyed in to natural ground as required and agreed with the engineer. Rock armour to be added to the toe as required
67263a22-5014-502e-8f8b-33c35cf980d1 | note | Records - Photo's
| checkpoint | 2.12 - Verge Reinstatement
7a7ddabc-03ad-5c66-b719-bc657a791781 | note | ACTION (Hold, Monitor, Witness) - W
e8a617ba-5e31-578f-beaa-8305e46ee16c | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
96cbc927-d5be-5782-b8c9-8fffc1b9f96d | note | Frequency - During Construction
9bd12995-2b09-5ed2-8f7c-4db862789d0d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d97d8bef-5aa8-5ca8-b66a-be1f23b1ea89 | note | Conformance Criteria - Verge reinstatement as per site instruction by Engineer
bdefba70-24dc-5685-9088-e8cb0c951944 | note | Records - Photo's
| checkpoint | 2.13 - As-built Survey
f1bb4c30-4b7e-551a-b170-3e9419e9755a | note | ACTION (Hold, Monitor, Witness) - H
f4f5c5cf-6db2-5d24-9dbd-20ccc45a367f | note | Frequency - At completion of Lot
7f37d804-35d8-576d-b074-2efe2279fc82 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
7e0b8903-b48d-511e-9848-7e2875295576 | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
ec742a71-2c43-58ab-9442-96cbb774e916 | note | Records - As-builts, CPS COR Report
| signoff | AUTHORITY HOLDPOINT
| section | Section 3: Final Inspection and Handover
| checkpoint | 3.1 - Quality Assurance deliverables
791510b3-e069-5a7d-b62d-b27d9b952043 | note | ACTION (Hold, Monitor, Witness) - W
eaaa695e-7a52-51d1-9274-c93fffe8fea5 | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
08078da2-8a9d-5352-b4c5-f14a9bf181fd | note | Frequency - At completion of Lot
5e0e1d9c-9e5b-57dd-a5f1-633f8f8480d0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
490b8c3a-93f6-5611-9b90-4060c36628c7 | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
ce8d2010-6c81-53a2-ac9d-0c438ecc7dd0 | note | Records - As-builts, NCR's and RFI's
| checkpoint | 3.2 - Completion Sign Off From Fields Below
dc6d04ec-9559-512d-a102-d49c78919c9e | note | Records - Signatures