## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1001F - Devil's Elbow Culvert - Asphalt Surfacing | itp |  |  |  |  | ITP - B1001F - Devil's Elbow Culvert - Asphalt Surfacing
section | 1 - Pre-Construction
checkpoint | Project Site reps.
textbox | Project Manager
textbox | Project Engineer
textbox | Site Engineer
textbox | Quality Engineer
textbox | CPS Engineer
textbox | CPS Manager
checkpoint | 1.1 - Survey Setout - Milling
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | Frequency - Prior to commencement
label | Conformance Criteria - Mark out on site, confirmed by CPS Engineer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Survey
label | Records - Survey, Photos, COR
checkpoint | 1.2 - Milling Existing AC
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Milling undertaken to correct depth of nominal thickness
label | Frequency - During operation
label | Conformance Criteria - Design Report, depth of milling confirmed by CPS
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - COR
section | 2 - Material Compliance
checkpoint | 2.1 - Binder Penetration Grade
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M01: 2020 - Table 6.1 and TNZ P11: 2007 - Table 5.2 Lab Mix
label | Frequency - Prior to commencement
label | Conformance Criteria - NZTA M01: 2020 - Table 6.1, TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Records - Lab Report
checkpoint | 2.2 - Coarse Aggregate Source
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with TNZ P11: 2007
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Conformance Criteria - 230kN minimum Crushing Resistance AA or BA Weathering Quality Index
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Records - IANZ Report
checkpoint | 2.3 - Blended Coarse Aggregate Production
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with TNZ P11: 2007
label | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | Conformance Criteria - 2.25 Max Particle Shape 98% Broken Faces
label | ○ Report Value - 5 minimum Cleanness Value
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Records - IANZ Report
checkpoint | 2.4 - Asphalt Mix Design
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Mix Design approved including peer review
label | Frequency - 10 days minimum prior to paving
label | Conformance Criteria - All production test records complied with the approved Job Mix Formula (JMF)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Records - JMF compiled with test records
section | 4 - Asphalt - Surfacing
checkpoint | 3.1 - Survey Setout - Paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Determine paving run start/stop locations
label | Frequency - Prior to commencement
label | Conformance Criteria - Ensure accurate survey setting out is in place.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | Records - Subcontractor QA
checkpoint | 3.2 - Weather Check
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure weather conditions are acceptable for work to proceed
label | Frequency - Prior to commencement
label | Conformance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
label | Records - Subcontractor QA
checkpoint | 3.3 - Surface Preparation
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure previous layer is broomed clean.
label | Frequency - Prior to commencement
label | Conformance Criteria - Truck broom to have been used and surface approved by CPS Engineer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photos
checkpoint | 3.4 - Membrane seal
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Application as per Design Requirements (Chip size / binder application rate)
label | Frequency - Prior to asphalt, Spray sheet for everyday.
label | Conformance Criteria - Application as per Design Requirements (Chip size / binder application rate)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
label | Records - Spray sheet, QA records
checkpoint | 3.5 - Temperature Asphalt for paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Check temperature of Asphalt for every truck entering the paver.
label | Frequency - Any truck load
label | Conformance Criteria - NZTA M10: 2020 (9.5.2)Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, except that placing at lower temperatures can be permitted subject to agreement with the Engineer on procedures used to compensate for rapid cooling of asphalt materials.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
label | Records - Subcontractor QA
checkpoint | 3.6 - Thickness (Cores)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Layer thickness measured from core samples.
label | Frequency - Each core taken for density
label | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Core Test
label | Records - Lab test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Compaction and air voids
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - To comply with NZTA M10: 2023 OR project specification
label | Frequency - AS per specification
label | Conformance Criteria - NZTA M/10: 2020 - section 9.9.3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
label | Records - IANZ Report, QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Surface Finish and Roughness
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - No visible cracks, defects related to poorly constructed joints, water ponding,
label | Frequency - Post Construction Site walkover.
label | Conformance Criteria - No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection.
label | Records - COR
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Conformance Criteria - Completed report
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - B1001F - Devil's Elbow Culvert - Stabilised Pavement | itp |  |  |  |  | ITP - B1001F - Devil's Elbow Culvert - Stabilised Pavement
section | 1 - Pre-Construction
checkpoint | Project Site reps.
textbox | Project Manager
textbox | Project Engineer
textbox | Site Engineer
textbox | Quality Engineer
textbox | CPS Engineer
textbox | CPS Manager
checkpoint | 1.1 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - i) Has the underlying layer been tested and results acceptable?
label | ii) Has the material used in this layer been formally accepted for use?
label | Frequency - Prior to commencement
label | Conformance Criteria - Subbase material test Records
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 1.2 - Compaction NDM
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - NDM test
label | Frequency - Post Construction
label | Conformance Criteria - Design specification ; Mean ≥ 98 % Minimum ≥ 95%
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Lab report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Surface level, thickness shape and visual inspection
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | Frequency - Post Construction
label | Conformance Criteria - Visual inspection
label | Inspection / Test Method submission, visual inspection, testing, measure, review - String sheet / Survey
label | Records - COR
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Material Compliance
checkpoint | 2.1 - AP40 material
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Material review for works
label | Frequency - Prior to commencement
label | Conformance Criteria - Weathering Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Lab report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - AP40 material
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Material review for works
label | Frequency - Prior to commencement
label | Conformance Criteria - Crushing Resistance
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Lab report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - AP40 material
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Material review for works
label | Frequency - Prior to commencement
label | Conformance Criteria - PSD, broken face
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Lab report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - AP40 material
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Material review for works
label | Frequency - Prior to commencement
label | Conformance Criteria - MDD sand Equivalent
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Lab report
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Construction 1
checkpoint | 3.1 - Survey set out
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Install offset pegs and mark out the extent of stabilisation
label | Frequency - Prior to commencement
label | Conformance Criteria - CPS approval
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - COR / survey
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Weather conditions
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Ambient Temperature (C&L) Material to be stabilised (BE&FBS) Wind
label | Frequency - Prior to spreading
label | Conformance Criteria - Measurement Ambient Temperatures: Cement: > 5°C
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Site Diary / Subcontractor QA
checkpoint | 3.3 - Stabilising Agents
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Cement, GP
label | Frequency - Per batch
label | Conformance Criteria - Confirm specification
label | Inspection / Test Method submission, visual inspection, testing, measure, review - on site monitor
label | Records - Subcontractor QA
checkpoint | 3.3 - Cement application - Mat test
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Frequency - Every 400 m2 every 150m for a 2.4m width
label | Conformance Criteria - ±0.50kg/m² of specified rate
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Subcontractor QA
checkpoint | 3.4 - Cement application - Average Usage Test
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Within ±2.5% of specified rate
label | Frequency - On-going measurement by computer/load cells concrete
label | Conformance Criteria - Within ±2.5% of specified rate
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Subcontractor QA
checkpoint | 3.5 - Stabilisation depth
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Maximum variation is -5mm and +15mm
label | Frequency - In first 20m and then every 50m
label | Conformance Criteria - In first 20m and then every 50m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Subcontractor QA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Moisture Content Check
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Visual check
label | Frequency - Every 50m
label | Conformance Criteria - Every 50m walking behind the stabilising the plant
label | Inspection / Test Method submission, visual inspection, testing, measure, review - On site Monitor
label | Records - Subcontractor QA
checkpoint | 3.7 - Compaction NDM
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - NDM test
label | Frequency - 5 per 1000m2
label | Conformance Criteria - Mean ≥ 98 % ; Minimum ≥ 95% MDD greater from Plateau or MDD lab report
label | Inspection / Test Method submission, visual inspection, testing, measure, review - On site testing
label | Records - Lab Report
checkpoint | 3.8 - Finished Basecourse layer
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Surface shape , level and crossfall
label | Frequency - Post construction
label | Conformance Criteria - Submission
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - COR
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Conformance Criteria - Completed report
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided.
label | Frequency - At the completion of the CWP of work
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - B1001F - Devil's Elbow Culvert - Guardrail | itp |  |  |  |  | ITP - B1001F - Devil's Elbow Culvert - Guardrail
section | 1 - Pre-Construction
checkpoint | Project Site reps.
textbox | Project Manager
textbox | Project Engineer
textbox | Site Engineer
textbox | Quality Engineer
textbox | CPS Engineer
textbox | CPS Manager
checkpoint | 1.1 - Design Check
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Conformance Criteria - National Standard for Traffic Signal
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Records - COR, Photos
checkpoint | 1.2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Surveyor to mark Start and End Point of Barriers
label | Frequency - Prior to commencement
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Approved Construction Drawing.
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Material Compliance
checkpoint | 2.1 - Barrier Compliance
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - All roadside barriers shall comply with TNZ M/23 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Conformance Criteria - TNZ M/23
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Guardrail Installation
checkpoint | 3.1 - Guardrail Installation Locations
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Conformance Criteria - TNZ M/23
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Records - Installation Checksheet
checkpoint | 3.2 - W-Beam Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Conformance Criteria - TNZ M/23
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Records - Installation Checklist
checkpoint | 3.3 - Leading & Trailing End Terminal Installation
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Conformance Criteria - TNZ M/23
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Records - Installation Checklist
checkpoint | 3.4 - Fit for purpose Inspection
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Barrier to undergo fit for purpose inspection by competent person.
label | ○ System checklists to be completed and co signed by contractor and CPS.
label | ○ All faults to be rectified before acceptance into network maintenance and RAMM
label | Frequency - Post-construction, ideally before TTM removed
label | Conformance Criteria - Pass inspection, RSHDS 4
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection: Kurt Samson
label | Records - Confirmation from inspector
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Conformance Criteria - Completed report
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT