## ITP -1
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Witness Point | Quality Controller Sign Off | Date | Engineer Sign-off | Date | Compliance Manager Sign off | Date
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C, E or Sp |  |  |  | Y/N | Y/N | Name / Signature | Date All Records verified complete | Name / Signature | Date All Records verified complete | Name / Signature | Date All Records verified complete
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
1. Procurement
Pre-construction tasks. e.g. approval of materials | Design
| Geometric Design | Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual | Principal Approval | Contractor and Principal peer review | per design revision |  |  | C or S |  | C | E | Y
| Pavement Treatment Design | Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Principal Approval | Contractor and Principal peer review | per design |  | Approvals Register - SH30 Frosts - Pavement Rehabilitation Design Report | C or S |  | C | E | Y
Materials: GAP 65 Pre-treatment Material
| Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet | C or S |  |  | S
| Source Property Test | CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Soaked CBR ≥ 40 | Soaked CBR test (NZS:4407:2015:3.15) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y
| Production Property Test | Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Sand Equivalent Test (NZS:4407:2015, 3.6) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y
Materials: M/4 AP40 Basecourse Material
| Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet
| Source Property Test | Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | less than 10% fines passing 2.36mm sieve size under a load of 130kN | Curshing Resistance Test (NZS 4407:1991, Test 3.10) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
|  | Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | AA, AB, AC, BA, BB or CA | Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
|  | California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Soaked CBR ≥ 80% | California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
| Production Property Test | Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
|  | Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Broken Face Test (NZS:4407: 1991, Test 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
|  | Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
Materials: Cement
| Stabilising Agent Selection | Cement (4.1.2) - TNZ B/5: 2008 | GP | Visual inspection of supplier docket | per truck load | Quality Controller | Supplier Docket Supplier Cert | Sp or S |  | Sp or S | C | Y
Materials: Water
| Water draw for stabilising | Water (5.0.0) - TNZ B/5: 2008 | Free from impurities justified by use of municipal water supply | Visual inspection of hydrant use form | per truck load | Quality Controller | Hydrant use form | Sp or S |  | Sp or S | C | Y
Materials: Geotextile
| Geotextile (Strength Class C) A29 or greater | TNZ F7 Specification | Details on Docket | Visual inspection | Per Delivery | Quality Controller | MDS | Sp or S |  | Sp or S | C | Y
Materials: Geogrid
| Geogrid Triaxial Tx160 or similar equivalent | As per NZTA list of approved materials/suppliers | Details on Docket | Visual inspection | Per Delivery | Quality Controller | MDS | Sp or S |  | Sp or S | C | Y
2. Pre-Implementation
| Production Testing of stabilised material - OMC/MDD | TNZ B/5 section 7.5 & 7.7.1 | To obtain OMC & MDD | NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Once on commencement and then each stablilised layer at one test per 5000m2 | Quality Controller | Test report | C | C | C |  |  | Y
| Production Testing of stabilised material - Solid Density | TNZ B/5 section 7.7 | For info. and use in MDD calculation | NZS 4407; test 3.7.1 | Once on commencement and if any materials chage | Quality Controller | Test report | C | C | C |  |  | Y
| Project survey setting out | Reference from Project Drawings |  | Survey/Mobile Roads, Marks with Dazzle | Chainages for every different pavement sections | Subcontractor/ Engineer | Construction drawings | C |  | C |  | Y
| Records Management (i.e. it is known what documented records are to be kept) | ITP and QMP state what quality documentation is required | Filled in and Signed ITP | Visual inspection, recording and approval | As per hold points in collaboration with the programme | Quality Controller | ITP and all referenced documents | C |  | C | E | Y
3. Construction - Pre-treatment Digouts
Construction phase - Digouts | Pre-treatment Repair Method Selection | Site specifics to be confirmed | Confirm scala acceptance criteria based on treatment type | Scala Penetrometer on Excavation Floor | As required | Quality Controller | Agreed treatment plan | S | C | S | E | Y
| Excavation floor drainage | Higgins SOP 0128 - Digout Repair | 4-8% toward edge of seal | Digital level | As required | Quality Controller | Dig out QA form | S | C | S | C |  | Y
| Subgrade material hardness Check base of excavation | Higgins SOP 0128 - Digout Repair | Scala > 3 blows per 100mm | Scala Penetrometer test on base of digout | As required depending on size of digout | Quality Controller | Test report | S/C | C | S/C | E | Y
| Geotextile (Strength Class C = A29) Layer beneath treatment layer | TNZ F7 Specification | Meet TNZ F7 Spec. | Visual inspection | Per Delivery | Quality Controller | Certificate of conformance | Sp or S |  | C | C |  | Y
| Geogrid Triaxial Tx160 or similar equivalent | As per NZTA list of approved materials/suppliers | On the list of approved materials/suppliers | Visual inspection | Per Delivery | Quality Controller | Certificate of conformance | Sp or S |  | C | C |  | Y
| Place and compact GAP65 in digout area | Higgins SOP 0128 - Digout Repair | Clegg > 45 | Clegg Test | Min. 2 per digout | Quality Controller | Test report | S/C | C | S/C | E | Y
4. Construction - Granular make up and In-situ Modification
Construction phase - Rehab | Place M/4 AP40 Basecourse Material | TNZ B/5 (section 7) | Evenly spread, no segregation, placed near optimium moisture content | Visual Inspection | On completion of placement | Quality Controller | Photographs and Daily Site Record | S or C |  | S or C | C |  | Y
| Spreading of Cement | Spreading of Cement (7.3) - TNZ B/5: 2008 | Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate | Mat test (1m² canvas) and Average Usage Test | per 400m² and upon emptying the spreader | Quality Controller | Mat Test Form and truck dockets | S or Sp |  | S | E | Y
| Addition of Water | Addition of Water (7.5) - TNZ B/5: 2008 | 90-100% OWC | Nuclear Densometer Testing prior to Stabilisation | ≥1 per 1000m² lot | Quality Controller | NDM Record | S |  | S | C |  | Y
| Cut Depth | Control of cut depth (7.6.1) - TNZ B/5: 2008 | -5mm and +15mm of design stab depth | Physical Measure and Visual Record | ≥1 per 200m of cut length | Quality Controller | Photographs and Daily Site Record | S |  | S | C |  | Y
| Longitudinal Joints | Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008 | The greater of 100m or 50% of layer thickness | Visual Record | per sucessive cut | Quality Controller | Photographs, Daily Site Record and Stabilising Plan | S |  | S | C |  | Y
| Continuity of Layer | Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008 | Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents | Visual Record | per sucessive cut | Quality Controller | Photographs, Daily Site Record and Stabilising Plan | S |  | S | C |  | Y
| Stabilised Material Particle Size | Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008 | No excessive breakdown of stabilised material | Visual Record | within 20m of each section and then regularly based on material variability | Quality Controller | Photographs | S or C |  | S or C | C |  | Y
| Establish Compaction Methodology - type of plant, number and speed of passes | Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008 | To establish type of plant, number and speed of passes to achieve MDD | Plateau Density Testing | 1 time, or additional tests when material changes visually | Supervisor | Test record | C |  | C | C |  | Y
| Establish Compaction Target | Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | To provide MDD for NDM testing | Plateau Density Testing | Minimum once per Lot. A lot shall not exceed 1000 m2. | Quality Controller | Test Record | C |  | C | E |  | Y
| Degree of Compaction MDD to obtain target for NDM testing | Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | To provide MDD for NDM testing | Laboratory MDD at OMC NZS 4402 test 4.1.3. | Minimum once per Lot. A lot shall not exceed 5000 m2. | Quality Controller | Test Record | C |  | C | C |  | Y
|  |  | Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test | Plateau Density Testing Lab. MDD | At commencement of construction and whenever materials change | Quality Controller Engineer | Notice to Contractor/ Notice to Engineer | C |  | C | E | Y
| Compaction Acceptance | Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005 | Mean value ≥ 98% and Minimum Value ≥ 95% | Nuclear Densometer Testing | ≥ 5 tests per 1000m² lot | Quality Controller | NDM Record | S or C |  | S or C | C | Y
Final Testing, Inspection and Acceptance | Control Testing (if required) | Control testing during and after construction (7.7.2) - TNZ B/5: 2008 | Nil | Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | when agreed with the Engineer | Quality Controller | Test Report | S or C |  | S or C | E
| Surface Smoothness | Surface shape (7.8) - TNZ B/5: 2008 | ± 10mm deviation along a 3m straight edge No water ponding | 3m Straight Edge | during construction and prior to seal | Supervisor | Photographs | S |  | S | E | Y
| Surface Shape | Surface shape (7.8) - TNZ B/5: 2008 | Between -5mm and +15mm | String lines or Survey Asbuilt | during construction and prior to seal | Supervisor | String Sheet/Survey Asbuilts | S |  | S | E | Y
| Cross Fall | Crossfall (7.9) - TNZ B/5: 2008 | 0.5% ≤ X ≤ -0.5% | 3m straight edge or Survey Asbuilt | during construction and prior to seal | Supervisor | Cross Fall Records/Survey Asbuilts | S | C | S | E | Y
| Surface Finish | Surface finish (7.10) - TNZ B/5: 2008 | Tightly bound matrix post sweep | Visual inpsection | prior to seal | Supervisor | Pre-seal inspection sheet | C | C and E | C or S | E | Y
| Degree of Saturation, DOS | Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005 | ≤80%, however 65% is ideal | Nuclear Densometer Testing | ≥5 tests per 1000m² lot | Quality Controller | NDM Record | C | E | S | E | Y
| Roughness (NAASRA) | NZTA Maintainence specification section 6.1.2 | For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km | NZTA Maintainence specification section 6.1.2 | Average of three replica runs for each lane reported at 20m intervals. | Quality Controller | Test Records | C | E | S | E | Y
5. Chip Sealing
5.1. Procurement | Chipseal Resurfacing
Pre-construction tasks. e.g. approval of materials | Binder - Penetration Grade | TNZ M/1 | Table 1 | Property Test | Annual | Bitumen Supplier/ Surfacing Project Manager | IANZ Report's | C |  | C | N |  | Y
| Binder - Polymer Modified Emulsion | Higgins Internal Specification | % PMB Required, PH, Residue by Evaporation, Viscosity | Property Test | 1/100,000 litres supplied |  |  | C |  | C | N |  | Y
| Source Property -Coarse Aggregate - Crushing Resistance | TNZ M6, RNZ 9805:2009 | <10% fines under 230kN minimum | Sample Test - Crushing Resistance NZS 4407 Test 3.10 | 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Surfacing Project Manager |  | C |  | C | N | Y
| Source Property -Coarse Aggregate - Weathering Resistance |  | AA or BA | Weathering Quality Index NZS 4407 Test 3.10 |  |  |  | C |  | C | N | Y
| Source Property - Skid Resistance | NZTA T/10 | Meet Skid performance Requirement | Aggregate Perfomance Method TNZ T/10 section 12.3 | Each Site |  |  | C |  | C | N | Y
Initial production testing and design approval | Production Property - Cleaness Value | NZTA P/17, M/6 | G2 - 89 min, G3 - 87 min, G4 - 85 min | Sample Test - Cleaness Value NZS 4407 Test 3.9 | Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples |  |  | C |  | C | N | Y
| Production Property - Particle Size/Shape |  | As per Table 3 NZTA M/6 | Sample Test - Particle Size/Shape NZS 4407 Test 3.13 |  |  |  | C |  | C | N | Y
| Production Property - Broken Faces |  | Min. 98% | Sample Test - Broken Faces NZS 4407 Test 3.14 |  |  |  | C |  | C | N | Y
| Chipseal Designs | EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17 | Client Approval | Review | Annual |  | EBOP NOC Design Report Acceptance | C |  | C | N | Y
5.2. Construction | Chipseal Resurfacing
| Ensure limits of site are marked | EBOP NOC Design Report | Visual Inspection | Visual | Prior to start sealing each site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y
| Sweep surface clean of deleterious material | P/17 | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y
| Record ATP's on site | N/A | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y
| Confirm correct treatment(s) and chip | EBOP NOC Design Report | Details/chip correct | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | Y
| Cutback Bitumen Blend | RNZ 9803_0513 | +/- 2PPH Cutter, +ve for Adhesion agent presence | Sample and test | 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed | Surfacing Project Manager, Surfacing Supervisor | IANZ Report's | C |  | C | C |  | Y
| Bitumen Application Rate | E/2 Certificate, Seal Design / Spray Instruction | Current E/2 Certificate +/- 4% per Spray Run | Test, Review | Per Sprayer, Per Site | Surfacing Supervisor | E/2 Certificate. Spray Sheets | C |  | C | C |  | Y
| Chip Application Rates | Chipsealing in NewZealand | As per Chipping Guide | Visual | Each Site |  | Chip application check sheet. Chip Sealing Quality and Site Record | C |  | C | C |  | Y
| Rolling | Chipsealing in NewZealand | Mimimum as per CS in NZ - Bit volume / 3600 | Visual | Each Site |  | Chip Sealing Quality and Site Record | C |  | C | C |  | Y
| Cleanup | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site |  | Chip Sealing Quality and Site Record | C |  | C | C |  | Y
| Post Sweeping | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site |  | Site Record | C |  | C | C |  | Y
| Linemarking and RRPM Reinstated | MOTSAM | Matches previous linemarking - within 48hours of sealing | Visual | Each Site |  | Site Record | C |  | C | C |  | Y
5.3. Post Construction | Chipseal Resurfacing
Final Testing, Inspection and Acceptance | Post Construction Walkover |  | Formal Agreement | Visual Inspection | Post seal sweep | Quality Controller, Supervisor and Engineer | Meeting Minutes | C | C, S and E | C | E | Y
| Resurfacing Construction Completion report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Within 2 months of completing the annual resurfacing programme | Surfacing Manager | Construction Completion Report | C |  | C | C | Y
| Chipseal Post-Verification Testing and Report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Each Site | Surfacing Manager | Chipseal Post-Verification Testing and Report | C |  | C | C | Y
6. Close Out
Final Closeout and Handover | Pavement Rehabilitation Construction Completion Report | Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Engineer Approval | Visual Inspection | ≤2 months of 1st Coat Seal | Quality Controller/ Contract Manager | Signed Report | C | C, S and E | C | E | Y
S – Subcontractor |  | C – Contractor |  | E – Engineer/Principal Representative |  | Sp – Supplier
Quality Control Records Compiled by: |  | Name: |  |  |  | Reviewed / Approved by: |  | Name:
|  | Role: | [5 empty] | Role:
|  | Signature: | [5 empty] | Signature:
|  | Date: | [5 empty] | Date