## ITP Cover Page
Streetlighting Inspection and Test Plan
Project: SH29 Tauriko West Enabling Project
Number and Revision: DN1210 - SP2-011-006 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | SH29 Tauriko West Enabling Project |  |  |  |  | ITP Number: |  | SP2-011-006
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  | IFC
ITP Description: |  |  | ITP NAR & Car park Streetlight |  |  |  |  | Revision: |  | 1
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  | 23273502 - WSP-DR-LIG
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  | SH29 Tauriko West Enabling Works Contract No.NZTA8287 Section 23
Quality Specified: |  |  | ISO9001: 2015
Review / Update History | [8 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  | Activity Key |  |  | Responsibilities Key
0 | Submitted to WSP- IFC | 2025-12-03 |  | WSP |  | Came back with comments. NTC#516 |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[9 empty] | B | Report by Breach |  | CR | Customer Rep
1 | IFC | 2025-01-05 |  | Cordelia GIrdler-Brown & Nick Adams |  | Comments from NTC#516 added to ITP and CWP |  |  | C | Check |  | PD | Project Director
[9 empty] | D | Dimension Inspection |  | PM | Project Manager
[9 empty] | E | Examine |  | OP | Operations Manager
[9 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[9 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[9 empty] | I | Inspection |  | PE | Project Engineer
[9 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[9 empty] | O | Operation |  | QE | Quality Engineer
[9 empty] | R | Review |  | SUP | Superintendent / Supervisor
[9 empty] | S | Subcontractor |  | SV | Surveyor
[9 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[9 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 2025-02-05 | Downer PM | Nick Adams
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 2025-01-05 | Downer QM | Cordelia Girdler-Brown
Client (If Applicable) | [7 empty] | Client (If Applicable)

## STREETLIGHT
Streetlighting Inspection and Test Plan
SH29 Tauriko West Enabling Project
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
3.1 | Location of Lighting Poles and Cameras | Confirm with surveyor and mark out the exact locations of lighting poles, Cameras, Cable Pits and Montrose boxes before installation. | IFC Drawings | Survey data/Comms with Client | Prior to Installation | H | PE
3.2 | Material grading: Materials (GAP20/AP20) | Material grading:PSD | Sieve Size % Passing 19.0mm 100% passing 13.2mm 80-95% passing 9.5mm 64-76% passing 4.75mm 37-58% passing 2.36mm 30-40% passing 1.18mm 18-28% passing 0.600mm 12-22% passing 0.300mm 6-14% passing 0.150mm 2-7% passing 0.075mm 0-3% passing | PS-21.5.7 PS-21.7.2 Table 21.2 | Lab Test Report NZS 4407.2015 Test3.8.1 | HP | ENG
3.3 | Weathering index: Materials (AP20) | Weathering index: | AA to CA | PS-21.5.7 PS-21.7.2 Table 21.3 | Lab Test Report NZS 4407.3.11 | HP | ENG
3.4 | Crushing Resistance: Materials (AP20) | Crushing Resistance | >100kN | PS-21.5.7 PS-21.7.2 Table 21.4 | Lab Test Report NZS 4407:1991 Test.3.10 | HP | ENG
3.5 | Luminaires & Poles -WK & TCC NAR & Carpark | Luminaire and Pole types shall be supplied and installed as detailed on the drawings or as per instruction of Client Luminaire Controller - PDL- 56SS10. | PS 23.1.5 g) & Drawing 0411, 0412 | Material data sheet and engineers approval | Before each Installation | HP | ENG |  |  | Purchase of Luminaires/Poles already approved by Client. PE/SE need to check on site to guarantee right type of luminaries and poles are installed at specific location.
3.6 | CCTV Cameras and DIN rail-mounted switch board | TCC Approved IP67 IK10+ With Weatherproof Housing , Vandal Resistant and PoE Dome (HD1080p, 2MP), Sensitivity down to 0.01 lux Have intelligent auto exposure to offer front and back light compensation. TCC IT-approved DIN rail-mounted switch board min 8 ports and 2 SFP ports | PS23.1.5 n) | Material data sheet and engineers approval | Before each Installation | HP | ENG
SECTION 4 – CONSTRUCTION
4.1 | Lighting Equipment-Luminaires & Poles (WK & TCC) | Types of luminaires and poles shall be installed as per details on the drawings or as per instruction of Client Luminaire Controller - PDL- 56SS10. Luminaires shall be fitted with Shorting Caps. | PS 23.1.3 c-d); 23.1.5 f-g) & Drawing 23273502-WSP-DR-LIG- 0004; 0112; 0410 | Photo/Visual Inspection | Each Installation | I | PE/SE
4.2 | Lighting equipment- Circuit Cabling (WK & TCC) | Supply and Install final circuit cabling to Luminaires from via underground ducts and conduits as per Drawing | PS23.1.3 g); 23.1.5 e) & Drawing 23273502-WSP-DR-LIG- 0112 | Photo/Visual Inspection | Each installation | I | PE/SE
4.3 | CCTV- Camera and Cabinet Location | All CCTV cameras will be installed at a high level, either on lighting columns or other designated high-level mounting points, providing optimal coverage The CCTV lockable cabinet will be securely mounted at a high level on lighting column TC94, ensuring a stable and protected enclosure for network and power components. | 23273502-WSP-DR-LIG- 0410 | Photo/Visual Inspection | Prior to installation | H | PE
4.4 | CCTV- Circuit Cabling | All CCTV cameras will be installed at a high level, either on lighting columns or other designated high-level mounting points, providing optimal coverage | 23273502-WSP-DR-LIG- 0414 | Photo/Visual Inspection | Each installation | I | PE/SE
4.5 | CCTV- IP Addressing, Programming of PoE Network Switches | Liaison with TCC for IP addressing and Programming of PoE Network switches. | PS 23.1.4 m) | Comms Record | Prior Installation | H | PE
SECTION 5 – Commissioning and Testing
5.1 | Luminaires (TCC) | Carry out full commissioning of the Light Controls as detailed on the drawings. Also record "Benchmark" energy meter reading from the lighting switchboards of all levels to demonstrate power consumption when ALL luminaires are running at 100%. | PS 23.1.5 g) & h) | Photo/Visual Inspection and Commissioning Records | Each Commissioning | W | ENG
5.2 | CCTV- Cameras | Testing CAT6A U/UTP Cabling from CCTV Cabinet to each CCTV Camera. Liaison with TCC for Commissioning and Testing including camera adjustment to achieve the desired FOV. | PS 23.1.4 m) | Testing/Commissioning Record | Each Testing/ Commissioning | H | PE
SECTION 6 – POST CONSTRUCTION ACTIVITY
6.1 | Electrical Certificate of Compliance (CoC) & Record of inspection (ROI) Electrical Safety Certificate (ESC) | Obtain final certification of the installed systems by an independent electrical inspector approved by the Electricity Workers Registration Board. | PS 23.1.5 p) | CoC,ROI and ESC | Post commissioning | R | PE
6.2 | As-Built | As-built drawings with 1) ducting routes. 2)) control groups, 3) scene settings 4) override sequences, 5) luminaire and pole locations, 6) the individual addresses of each luminaire, and their corresponding groups (if DALI) shown clearly for maintenance purposes. 7) All changes to design to be noted, highlighted or markup clearly. | PS 23.1.5 h) & 23.8.5 a)-b) | As-built Drawing/Survey Data | Post construction | H | PE/ ENG