## ITP
Inspection and Test Plan Te Ara o Te Ata MMA-QA-ITP-Z06-BR1-SU002 Title: Ground Anchors & Micro Piles
| This ITP has been prepared by |  |  |  | Reviewed by Quality Manager |  |  | Reviewed by CPS |  |  |  |  | Approved by Construction Manager
Rev # | Name | Signature |  | Date | Name | Signature | Date | Name |  | Signature |  | Date | Name |  | Signature |  | Date
Rev 01 | Jordan Stoneman, Joshua Davis & Nick Myers-Kay | See Approvals Tab |  | 2025-04-04 | Whineray Arries and Manoj Jayasundara | See Approvals Tab | 2025-05-01 | Dave Averill |  | See Approvals Tab |  | 2025-05-02 | Hardus Pieters |  | See Approval Tab |  | 2025-05-02
Rev 02
Rev 03
Rev 04
Method Statement Ref:
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity / Specification: | [7 empty] | Area Location / Work Breakdown:
Item | Construction Step or Material |  |  | Specifications and Standards |  | Acceptance criteria and testing | [5 empty] | Responsible |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
[6 empty] | Method / Description | Test frequency |  | Conformance Criteria |  |  | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.01 | Approved CWP |  |  |  |  | Document Review | Prior to personnel starting |  | Ensure all crew members are briefed on the CWP |  |  | H | H |  |  | Signed off CWP
1.02 | IFC issued |  |  | Consent conditions |  | Document Review | Prior to starting |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB |  |  | H | H |  |  | IFC drawings or written approval from PAB
1.03 | Approved SCWMP |  |  | Consent conditions |  | Document Review | Once prior to works commencing |  | TRC review and approval |  |  | H |  |  |  | Approved SCWMP
1.04 | Method Statements At least 5 days before commencing works a method statements shall be submitted to the the Design Engineer for review. |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 4.1 |  | Document Review | Prior to starting |  | Review and Approval |  |  | H | H |  |  | CPSA
2.0 Material Compliance
2.01 | Material Compliance - Micro pile tendons, plates and nuts 57mm DYWIDAG E 150 ksi threadbar, DYWIDAG plates & nuts. Threadbar requires Class 1 corrosion protection. |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 6.1, Table 6.5 of NZTA Bridge Manual, BS 8081:2015 |  | Mill certificate documents for review | Prior to commencement |  | CPS Approval |  |  | H | H |  |  | Request for approval
2.02 | Material Compliance - Steel casings & Nelson Studs G350 LO 273mm diameter x 12.7 CHS, with 19mm diameter x 180mm long Nelson Studs |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 6.1.2, ISO 22477-5 |  | Mill certificate documents for review | Prior to commencement |  | CPS Approval |  |  | H | H |  |  | Request for approval
2.03 | Material Compliance - Rock anchors, trumpet plates, bearing plates, nuts & protective caps 57mm DYWIDAG E 150 ksi threadbar, DYWIDAG plates & nuts. Threadbar requires Class 1 corrosion protection. Trumpet, bearing plate and protective cap to be HDG thickness of 600gm/m² |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 6.2, Table 6.5 of NZTA Bridge Manual, BS 8081:2015 |  | Mill certificate documents for review | Prior to commencement |  | CPS Approval |  |  | H | H |  |  | Request for approval
2.04 | Material Compliance - Cement Cements used for grouting to comply with NZS 3122 |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 6.2.2 & NZS 3122 |  | Document review certificates provided | Prior to commencement |  | CPS Approval |  |  | H | H |  |  | Request for approval
3.0 During Construction
3.1.1 | Setting Out Rock Anchors & Micro pIles set out in accordance with IFC construction drawings |  |  | IFC Construction drawings |  | Survey team | Prior to comencement of works or as required |  | Survey report |  |  | H |  |  |  | Signed pre-pour inspection sheet
3.1.2 | Install 1No Suitability Test Anchor Test required to confirm the grout to bond strength. Drill & install 75mm diameter 150ksi anchor in 250mm diameter drilled hole. Test location to be confirmed by CPS. |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 8.2.4, Rock Anchor Notes MMA-DES-STR-E1-DRG-1010 & 1015 |  | Drill, grout and test | Prior to comencement of drilling |  | Drilling, grouting and stressing records for CPS approval |  |  | H | H |  |  | Data results
3.1.3 | Install Ground Anchors Four ground anchors at Abutment A and Eight ground anchors at Abutment B. |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 7.2, Rock Anchor Notes MMA-DES-STR-E1-DRG-1010 & 1015 |  | Drill, grout and test | During installation |  | Drilling, grouting and stressing records for CPS approval |  |  | H | H |  |  | Data results
3.1.4 | Install Micro Pile Twelve Micro piles at Abutment B. 48 total across four pier foundations. |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 7.1, Micro Pile Notes MMA-DES-STR-E1-DRG- 1015 & 1021 |  | Drill, grout and test | During installation |  | Drilling, grouting and stressing records for CPS approval |  |  | H | H |  |  | Data results
4.0 Post Construction
4.01 | Acceptance Test Ground Anchors All ground anchors require acceptance testing. |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 8.2.5 & 8.2.6, Rock Anchor Notes MMA-DES-STR-E1-DRG- 1010 & 1015 |  | Reaction frame, 200t hydraulic jack and dial gauges | At completion of installation |  | Testing records, CPS approval |  |  | H | H |  |  | Data results
4.02 | Acceptance Test Micro Piles Seven only micro piles require acceptance testing. |  |  | MMA-DES-GEO-E1-SPC-8999, Clause 8.3.4 & 8.3.5, Micro Pile Notes MMA-DES-STR-E1-DRG- 1015 & 1021 |  | Reaction frame, 200t hydraulic jack and dial gauges | At completion of installation |  | Testing records, CPS approval |  |  | H | H |  |  | Data results
4.03 | Welding Nelson Studs to Micro Pile Casings At completion of of micro pile testing, all Nelson studs to be site welded onto the micro pile casings |  |  | AS/NZS 1554.2:2003 |  | Approved weld proceedure for site welding | At completion of installation |  | Approved weld proceedure, NDT results |  |  | H | H |  |  | Inspection report
4.04 | As-built Final survey required to capture any deviation from IFC and to be used for Redline mark up drawings |  |  | MMA-DES-GEO-E1-SPC-9349, Clause 4.3, Table 1 |  | Survey | At the completion of works |  | Survey report, CPS approval |  |  | H | H |  |  | Survey report
4.05 | Final Handover Site inspection with bridge builder checking site is ready to handover |  |  |  |  | Visual inspection | At completion of works |  | Bridge builders acceptance |  |  | H |  |  |  | Site record
5.0 Close-Out & Approval/Acceptance
ITP Close-Out by
Site Engineer/ Project Engineer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Zone Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Construction Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Quality Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date: