## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Ground Anchors & Micro Piles | itp |  |  |  |  | ITP - Ground Anchors & Micro Piles Rev 1
section | 1.0 Pre-Construction
checkpoint | 1.01 - Approved CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personnel starting
label | Conformance Criteria - Ensure all crew members are briefed on the CWP
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - IFC issued
label | Specifications and Standards - Consent conditions
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Conformance Criteria - Ensure all drawings are approved and of the latest revision, or written approval from PAB
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Approved SCWMP
label | Specifications and Standards - Consent conditions
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - TRC review and approval
label | Constructor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
checkpoint | 1.04 - Method Statements - At least 5 days before commencing works a method statements shall be submitted to the the Design Engineer for review.
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 4.1
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Conformance Criteria - Review and Approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - CPSA
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Material Compliance
checkpoint | 2.01 - Material Compliance - Micro pile tendons, plates and nuts - 57mm DYWIDAG E 150 ksi threadbar, DYWIDAG plates & nuts. Threadbar requires Class 1 corrosion protection.
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 6.1, Table 6.5 of NZTA Bridge Manual, BS 8081:2015
label | Method/Description - Mill certificate documents for review
label | Test frequency - Prior to commencement
label | Conformance Criteria - CPS Approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Request for approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Material Compliance - Steel casings & Nelson Studs - G350 LO 273mm diameter x 12.7 CHS, with 19mm diameter x 180mm long Nelson Studs
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 6.1.2, ISO 22477-5
label | Method/Description - Mill certificate documents for review
label | Test frequency - Prior to commencement
label | Conformance Criteria - CPS Approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Request for approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Material Compliance - Rock anchors, trumpet plates, bearing plates, nuts & protective caps - 57mm DYWIDAG E 150 ksi threadbar, DYWIDAG plates & nuts. Threadbar requires Class 1 corrosion protection. Trumpet, bearing plate and protective cap to be HDG thickness of 600gm/m²
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 6.2, Table 6.5 of NZTA Bridge Manual, BS 8081:2015
label | Method/Description - Mill certificate documents for review
label | Test frequency - Prior to commencement
label | Conformance Criteria - CPS Approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Request for approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Material Compliance - Cement - Cements used for grouting to comply with NZS 3122
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 6.2.2 & NZS 3122
label | Method/Description - Document review, certificates provided
label | Test frequency - Prior to commencement
label | Conformance Criteria - CPS Approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Request for approval
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 During Construction
checkpoint | 3.1.1 - Setting Out - Rock Anchors & Micro pIles set out in accordance with IFC construction drawings
label | Specifications and Standards - IFC Construction drawings
label | Method/Description - Survey team
label | Test frequency - Prior to comencement of works or as required
label | Conformance Criteria - Survey report
label | Constructor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed pre-pour inspection sheet
checkpoint | 3.1.2 - Install 1No Suitability Test Anchor - Test required to confirm the grout to bond strength. Drill & install 75mm diameter 150ksi anchor in 250mm diameter drilled hole. Test location to be confirmed by CPS.
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 8.2.4, Rock Anchor Notes MMA-DES-STR-E1-DRG-1010 & 1015
label | Method/Description - Drill, grout and test
label | Test frequency - Prior to comencement of drilling
label | Conformance Criteria - Drilling, grouting and stressing records for CPS approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Data results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Install Ground Anchors - Four ground anchors at Abutment A and Eight ground anchors at Abutment B.
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 7.2, Rock Anchor Notes MMA-DES-STR-E1-DRG-1010 & 1015
label | Method/Description - Drill, grout and test
label | Test frequency - During installation
label | Conformance Criteria - Drilling, grouting and stressing records for CPS approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Data results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Install Micro Pile - Twelve Micro piles at Abutment B. 48 total across four pier foundations.
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 7.1, Micro Pile Notes MMA-DES-STR-E1-DRG- 1015 & 1021
label | Method/Description - Drill, grout and test
label | Test frequency - During installation
label | Conformance Criteria - Drilling, grouting and stressing records for CPS approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Data results
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Post Construction
checkpoint | 4.01 - Acceptance Test Ground Anchors - All ground anchors require acceptance testing
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 8.2.5 & 8.2.6, Rock Anchor Notes MMA-DES-STR-E1-DRG- 1010 & 1015
label | Method/Description - Reaction frame, 200t hydraulic jack and dial gauges
label | Test frequency - At completion of installation
label | Conformance Criteria - Testing records, CPS approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Data results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Acceptance Test Micro Piles - Seven only micro piles require acceptance testing
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-8999, Clause 8.3.4 & 8.3.5, Micro Pile Notes MMA-DES-STR-E1-DRG- 1015 & 1021
label | Method/Description - Reaction frame, 200t hydraulic jack and dial gauges
label | Test frequency - At completion of installation
label | Conformance Criteria - Testing records, CPS approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Data results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Welding Nelson Studs to Micro Pile Casings - At completion of of micro pile testing, all Nelson studs to be site welded onto the micro pile casings
label | Specifications and Standards - AS/NZS 1554.2:2003
label | Method/Description - Approved weld proceedure for site welding
label | Test frequency - At completion of installation
label | Conformance Criteria - Approved weld proceedure, NDT results
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Inspection report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - As-built - Final survey required to capture any deviation from IFC and to be used for Redline mark up drawings
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349, Clause 4.3, Table 1
label | Method/Description - Survey
label | Test frequency - At the completion of works
label | Conformance Criteria - Survey report, CPS approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Survey report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Final Handover - Site inspection with bridge builder checking site is ready to handover
label | Method/Description - Visual inspection
label | Test frequency - At completion of works
label | Conformance Criteria - Bridge builders acceptance
label | Constructor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Site record
section | 5.0 Close-Out & Approval/Acceptance
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE