## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
88cf6478-fe8d-49ca-b2e3-e2b32b24ba69 | checklist | NSW-G38-SED-ITP Erosion & Sediment Control - Public Roads Upgrade | itp | NSW-G38-SED-ITP Erosion & Sediment Control - Public Roads Upgrade
6c32ad6a-1302-4692-93b0-d1fcfc5708b7 | section | Details
a84747d8-b9b9-4ae8-a019-615639f5f4a5 | checkpoint | 1 - Prepare Erosion & sediment Control Plan (ESCP) for the Works Under the deed
ba385930-7f7d-5a13-8e59-d87601f5e935 | note | FREQUENCY: Once
55d9456f-817e-5382-9fca-f0e1ed7ab2c4 | note | ACCEPTANCE CRITERIA: The ESCP will form part of the EMP and will be incorporated in the ERA.
4f3f03e6-fc8a-5a0a-8c27-44c257828ae9 | note | REFERENCE DOCUMENTS: G38.2.2
14c32e29-40a5-5d14-8fea-624f345b9ffc | note | RECORD OF CONFORMITY: Verification Checklist
e66a4eb8-9ef1-5b61-bd18-08e5e0ada3e1 | note | IP
5f621b6d-e192-5d74-900d-72be898e16ed | note | RESPONSIBILITY: Environmental Rep.
beb2a646-7311-5d01-93c0-e7834fd533d6 | date | Date Completed:
da518059-6b37-4a8d-91cc-e93b5ec9cc8e | checkpoint | 2 - Install Erosion and Sediment Controls
b43a0759-e491-54b9-8735-5f8d40b3ac57 | note | FREQUENCY: Per Area
3ac4ccd3-571a-5701-ae7d-a5a2a4d3a8f4 | note | ACCEPTANCE CRITERIA: Installed in accordance to the approved progressive ESCP and guided by the BLUE BOOK.
c03aa4f2-84ef-50e2-8b59-ac8f19aa5d4e | note | REFERENCE DOCUMENTS: EMP
ca945e5b-7900-5aa2-b53b-33d36e0cfc9c | note | RECORD OF CONFORMITY: Verification Checklist
e40803bd-4f7b-57f9-acb2-87502710e66d | note | IP
696def53-a510-5aef-8a28-beee1391461f | note | RESPONSIBILITY: Environmental Rep.
a0e3c064-f689-53b5-8d24-169b8b2d89c1 | date | Date Completed:
24fab352-b7c1-4553-a699-8e22124a252b | checkpoint | Final Inspection
d0b5a8bd-17e6-55dd-9ba2-8dde5a50802c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
7c482e35-f62d-5a12-8f80-5f74d30c1e8f | textbox | Print Name:
7c47c40f-5d8d-5424-8ae2-fde886f9f936 | textbox | Position:
288db12f-5844-5651-8543-dfcc79c1549a | date | Date:
ab8af3bc-b5d4-4cf2-af5c-ebc011de6176 | signoff | Sign ITP
4a1cb36c-16b4-4808-876b-93509d783351 | checklist | NSW-R11-ODR-ITP-Open Drains - Public Roads Upgrade | itp | NSW-R11-ODR-ITP-Open Drains - Public Roads Upgrade
49edc76f-27c6-4cc7-ae6d-78036e3e885e | section | Details
e78883a4-dced-4466-8af6-0eb9dd39d1d0 | checkpoint | 1 - Drain
35ceb6c4-1f09-56c5-a3c3-b9ab07542ba8 | note | FREQUENCY: Per Area
7f30d315-a6a1-5c31-ab42-a9f6100f4708 | note | ACCEPTANCE CRITERIA: As indicated on design drawing
321c2112-e6d0-504c-9f54-6105889865c5 | note | REFERENCE DOCUMENTS: Design DWGS
e605ff19-c6fb-5547-b600-8835b6af1f40 | note | RECORD OF CONFORMITY: Verification Checklist
7c50a79c-6a9c-5ee2-b54a-aae9c72b00cc | note | IP
ee783f17-7e72-5580-a947-ace1150c4324 | note | RESPONSIBILITY: Site Engineer
51f2e835-7dff-5c65-84eb-4d35b725e822 | date | Date Completed:
54da8a86-68c1-4b50-b157-0efe31b95b86 | checkpoint | 2 - Set out the works
7fb5b512-a45b-514e-8fc2-7fff0dd86089 | note | FREQUENCY: Per Lot
38b9c43c-6110-5386-b015-7dcd2035a81e | note | ACCEPTANCE CRITERIA: Notification that set out of drainage system has been completed. The Nominated Authority will inspect the set out prior to authorising the release of the Hold Point.
7705e473-5e0d-59d2-810d-fc6919b96a18 | note | ○ Set out the location and level of open drains as shown on the Design Drawings.
8fad609f-f2c1-559b-9b07-7d998b7ff129 | note | REFERENCE DOCUMENTS: R11.4.1.1 Design DWGs
05d031d9-f139-5985-8c3e-78b53ff6beaf | note | RECORD OF CONFORMITY: Hold Point
13a5c34a-ae3a-502d-8bea-8a66429c413c | note | IP
43f24300-07d7-524f-bd6a-9b5110c62c9f | note | RESPONSIBILITY: Site Engineer
63c8f61c-e4a4-5f1f-ac7b-7c29c15c935e | date | Date Completed:
749a3d08-487d-4061-b39d-7f4c0727dda5 | checkpoint | 3 - Excavation for Drainage Structures
fdcd9344-1263-5812-9670-ad17f8e02748 | note | FREQUENCY: Per Lot
a39143af-6e25-5e89-9a69-2658a7da3e06 | note | ACCEPTANCE CRITERIA: Excavate to dimensions shown on drawings.
8be0fec2-9d88-5d51-9eb4-2b0c814ba574 | note | ○ Where dimensions are not shown, excavate to:
5a366ba8-5730-5098-99b3-68ab338e06b1 | note | — Min 300mm depth
1894f7b5-7c5b-5973-b24f-0c9cdeb2bbd0 | note | — Min waterway of 0.2 m²
f3dce400-99ec-5c91-a8d3-e4d4331fb8be | note | — Batter slope ≤ 2H:1V steep
2524cdc5-4af5-5b28-998a-48a0d6ef2d1b | note | — Have a grade slope of ≥1%
0b6cc90a-c694-561f-9f56-fff4939380be | note | — Extend open drains as necessary to natural drainage depressions or to a drainage system.
4f0f1559-6b14-58c0-bee6-c61f9cb057f3 | note | REFERENCE DOCUMENTS: R11.4.2.1
bcd9ab73-7689-5254-a6d2-e42f93c9fd1d | note | RECORD OF CONFORMITY: Verification Checklist
65574d95-e456-54b4-adc9-c904f1ce5c47 | note | IP
4066c142-81ee-5763-a1e1-9f14302d2b94 | note | RESPONSIBILITY: Site Engineer
7a54745a-3bdb-5d1d-9810-458aaa5fac46 | date | Date Completed:
ead48ad5-3889-4d21-8b17-abc2d8146d91 | checkpoint | 4 - Construction of open drains with grade less than 1%.
836283e0-1622-550f-be6a-4247c09f68f7 | note | FREQUENCY: Per Lot
40cbc4e1-b8ef-5321-9dff-af75d0a336ca | note | ACCEPTANCE CRITERIA: Notification that 1% minimum grade cannot be achieved.
0a1debeb-0105-5a1f-b0cf-b5f2b4f53061 | note | ○ The PV will consider the matter, and will direct you further, prior to authorising the release of the Hold Point.
29551f29-b142-5986-a93c-3e1e25eec4f1 | note | REFERENCE DOCUMENTS: R11.4.2.1
0b1b7990-ea3a-5f90-af15-1728e6ed865b | note | RECORD OF CONFORMITY: Hold Point
2f817544-0658-532f-8f4d-949ac6755621 | note | HP
9ec810d1-5853-593c-b000-39ea85fdc44b | note | RESPONSIBILITY: Site Engineer
e4ae2762-72ca-5f01-bd58-b31d17d51685 | date | Date Completed:
cd8415d0-8458-4bcb-b228-874475f81a39 | signoff | AUTHORITY HOLDPOINT
96bc80a8-0374-4f9c-86c7-4b24acb66a0f | checkpoint | 5 - Inadequate Foundation Material
bbb0fa64-15e4-57cc-82af-8c435d72af19 | note | FREQUENCY: Per lot
5b69dc89-401e-588e-a73c-8869d37cb20c | note | ACCEPTANCE CRITERIA: Notification to the PV that inadequate foundation material has been excavated to the extent required.
d24878fe-8b00-546c-b25f-ed662c9b38eb | note | ○ Replace inadequate foundation material with materials from cuttings, or with other conforming material, and compact to the requirements of Clause 4.9.2 of this Specification.
a84413ce-d62e-5c29-bd84-3aeb03dadbaf | note | REFERENCE DOCUMENTS: R11 4.3.3, R11 4.9.2
2ee5e633-4f7c-563a-bbb8-f5cbf2eb4ab8 | note | RECORD OF CONFORMITY: Witness Point
fc69d4e1-eb02-5df9-b66b-4a3a5e723d37 | note | WP
dc684b8c-32c2-50aa-a92e-e22963244cf0 | note | RESPONSIBILITY: Site Engineer
83ddc965-f16e-52ef-b11c-eb89384f95ad | date | Date Completed:
398c08c5-dc19-489f-877d-93ba8802baf3 | checkpoint | 6 - Trim and compact open drains
5deb5b13-1fa0-5676-8afa-16fa7357d904 | note | FREQUENCY: Per Lot Q6/L.3.1
d9f6f195-772e-5728-a399-1aaafff58bf3 | note | ACCEPTANCE CRITERIA: Trim open drains to produce a uniform surface free of irregularities.
bd57b96f-030b-5a24-a285-101a7f441bd6 | note | REFERENCE DOCUMENTS: R11.4.2.1, R11.4.9.2
4c3329bb-442d-533e-a865-404f034c1f33 | note | INSPECTION / TEST METHOD: T166
e7b64901-a032-528e-a848-73f4c8d82892 | note | RECORD OF CONFORMITY: Test Report
7605876b-adc1-597b-aa64-4b6bdca7539e | note | TP
ed6b6881-5823-59df-9bac-e8eb08da43fd | note | RESPONSIBILITY: Site Engineer
3959d593-20b3-5b9f-b6c3-1252b7e44b6c | date | Date Completed:
124bb7ea-e9f7-4715-9644-cf335f216f47 | checkpoint | Final Inspection
61f7aff1-6d05-5796-8914-a58ed1c67974 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
36e8a32c-1a70-5bb8-b7e3-25f993e028f7 | textbox | Print Name:
161a0c72-acf9-5741-bab5-e07e5a55da1f | textbox | Position:
86060c5d-7d17-5153-a685-abd59e1ccb38 | date | Date:
28077ce0-9b8b-4890-a70b-5f3f5e103228 | signoff | Sign ITP
cf2e3bcc-c563-4821-854c-ee81db3d64b9 | checklist | NSW-R44-FIL-ITP-Select Fill - Public Roads Upgrade | itp | NSW-R44-FIL-ITP-Select Fill - Public Roads Upgrade
41788057-728d-4b89-b5a2-07ec7ac9fa11 | section | 1 - Preliminary
486a40f2-35b2-40ef-8250-3c53838fbbd1 | checkpoint | 2 - Set out the works
1d119af2-9e7a-57b0-9974-46dd39c6c610 | note | FREQUENCY: Each Section
aa30ef36-0299-561f-9fef-636ae80aca90 | note | ACCEPTANCE CRITERIA: Establish Pegs (or equivalent) to identify the extend of filling
6673f932-7c40-5a67-b7ec-0e024d2315f5 | note | REFERENCE DOCUMENTS: Design DWGs, Survey Management Plan
3e7347a1-ff9b-5687-9763-791a3fa0feb6 | note | RECORD OF CONFORMITY: Verification Checklist
31c70c33-890b-50dd-bdee-b99b422d38e7 | note | IP
9c8a42ac-e5b0-51e6-8581-dfd892bc9308 | note | RESPONSIBILITY: Surveyor
6671c547-1648-5407-9563-f0bf6a96a83f | date | Date Completed:
fc620bee-cb4d-40d6-8160-8871c2f6248a | checkpoint | 3 - Verify conformance of select fill material
dc83f1f5-e9c4-5086-952d-9d39ff89aa71 | note | FREQUENCY: As required
13c10ba4-feeb-5db3-95fc-9b22e5eecc31 | note | ACCEPTANCE CRITERIA: Imported Select Fill Material: CBR15
f72f1493-9f5f-550f-8262-8e6d9adc4ee5 | note | REFERENCE DOCUMENTS: Design Plans
ec3c9355-d1f0-5848-840f-7a1b4c50de93 | note | INSPECTION / TEST METHOD: Verification
7ec7b294-4214-54f4-9416-0408c788f76f | note | RECORD OF CONFORMITY: ITP, Material spec report
05c50051-4471-5846-84a4-64f46246ef78 | note | IP
be5605dc-f9bd-5628-9e38-aac648b85be5 | note | RESPONSIBILITY: Site Engineer
676cec81-08ce-5871-8ffd-409de8b49160 | date | Date Completed:
5e898025-62a8-44c6-84eb-5ab53ab9d34c | section | 4 - Construction
c48e9111-9dd4-4a98-a2fb-9258d9c6a466 | checkpoint | 5 - Place, spread fill material (parallel to the grade), compact and test to specified densities
2974c17b-a147-508c-be13-95bdd8c5567b | note | FREQUENCY: Per Lot, Q6/L3.1
405aa4c9-a3a4-5b54-9cd8-13fa93460839 | note | ACCEPTANCE CRITERIA: 95% Std compaction
519efe6a-5c98-5e36-8019-997f55625015 | note | ○ Minimum layer thickness after compaction ≥ 100mm
81d00ebe-3d19-5046-886d-2b61f35aff55 | note | ○ Maximum layer thickness after compaction <= 150mm unless otherwise approved
67c4b4e9-51ee-5759-8d0e-21c2d9184758 | note | ○ Ensure insitu sampling and testing for compaction conformity is undertaken in accordance with TfNSW Q6 Annexure L
51cea6c2-d4c4-561f-aab4-bd3f942a7237 | note | REFERENCE DOCUMENTS: R44.5.1.3, R44.5.2.2, R44.7.2, R44.7.3, R44.7.4, R44/A5
2db995ae-04a0-50fc-b20b-5ec231d61c0f | note | INSPECTION / TEST METHOD: T166
58a4f983-5ed6-5503-b931-c02410c4c720 | note | RECORD OF CONFORMITY: Test Report
f2edbf26-b84f-5186-91db-fff46d84d09b | note | TP
8d8531e9-4286-5c05-8e4c-d365e73a4e1f | note | RESPONSIBILITY: Site Engineer
06a07b21-a927-5e30-9c7a-0e4b6ebbbbac | date | Date Completed:
e012340d-ac58-4431-8fad-f75023ea9b4a | checkpoint | 6 - For hill side embankment foundation, terrace 1m wide of the hill side of embankment and ensure its free draining
078753d3-0b17-52e8-a6fd-af0787928a6b | note | FREQUENCY: Per Lot
4ad7bb6b-aa16-5952-b1ea-693dcb025043 | note | ACCEPTANCE CRITERIA: Minimum Step Depth ¦¦ Slope
7955ba46-985d-5770-aa6b-fe5f09ca49d4 | note | 600mm ¦¦ > 4H:1V
0dcb5950-643f-5455-8cb8-5e27935a0f11 | note | 300mm ¦¦ < 4H:1V
e25c7f2b-fbbb-5f38-8255-f6c802f5e1db | note | ○ Terraces not required on slopes < 10H:1V
fe40350a-71a9-5ec7-bd73-ba93347b4837 | note | REFERENCE DOCUMENTS: R44.3.3 Fig R44.4
64c5916c-a23f-50fb-9c9b-d62de0e3daa7 | note | RECORD OF CONFORMITY: Verification Checklist
e64312d6-2844-5db4-ba9f-443b14994e47 | note | IP
6c418f0a-9d72-55a5-8fd7-1a44a336eb93 | note | RESPONSIBILITY: Site Engineer
ccd99cf1-f020-57f5-8682-bedd603c75f5 | date | Date Completed:
e8bbd68b-e8e8-482e-9c1c-ab26de65573a | checkpoint | 7 - Conduct Deflection Testing – Proof rolling Method within 1.5m underside of SMZ
99c06bcd-bb43-5df2-abe6-b2fd5fd6989a | note | FREQUENCY: Per Lot
daa24dcb-5ea5-5b8e-9334-031a24302381 | note | ACCEPTANCE CRITERIA: Must not exhibit deformation, yielding and/or show signs of distress or instability.
51bb8992-1beb-5e30-b92b-7d608d1cb2da | note | ○ All embankment layers and other surface within 1.5m of underside of SMZ
5b669f4e-df96-5fa6-93f7-768406bef7bf | note | ○ With refer to RFI 436: Clause 3, Note B on T198 states that other equipment may be used,
28742199-42bf-51a7-aa68-e9137d884446 | note | 1. Benkelman Beam truck (as per T160)
c9c5db50-aa8c-57c7-8385-798f07bc63d2 | note | 2. Loaded bogie truck
dfcef72a-ba75-5769-b423-11ada8f42c0c | note | 3. 12M Grader (or larger
bba9fb2d-8467-542d-b5c9-c7779aea8dcf | note | 4. 12t Roller (or larger)
1c03c5be-72f8-53fc-b739-9bea93ca3b18 | note | REFERENCE DOCUMENTS: R44.7.6.1
27e3b68b-c08e-5b5d-ad91-6bf3f85708b9 | note | INSPECTION / TEST METHOD: T198
c8655182-7f57-52d3-ade8-65e235f4185b | note | RECORD OF CONFORMITY: Witness Point
e779abcb-b29b-58ac-90e5-308e39e41041 | note | WP
bead7f4f-51ab-5da0-a0b3-3b833502e0eb | note | RESPONSIBILITY: Site Engineer
6faed000-7e02-5526-abb0-0f021ae21907 | date | Date Completed:
661a540f-6418-4b94-b091-4cf413802e09 | checkpoint | Final Inspection
0ed8a5d3-a974-518a-8e07-c7de58631295 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
a7b5a7f8-f215-54e3-9486-03f2a81b93cc | textbox | Print Name:
30d0a478-cd9e-5f44-b5b6-c8fc086efb3c | textbox | Position:
8cc3690f-44bf-5e6e-8341-9b9b3e160c46 | date | Date:
4da70fea-717c-42f9-b6a1-9fe3e917ad3d | signoff | Sign ITP
28325234-8c5b-4ced-8cf6-e49e81aa26d1 | checklist | NSW-R71-UCP-IPT-Unbound Pavement Course - Public Roads Upgrade | itp | NSW-R71-UCP-IPT-Unbound Pavement Course - Public Roads Upgrade
7d972222-2305-4966-a574-565c75e15c68 | section | 1 - Preliminary
93d0175c-2c3a-4e8a-bdac-cc762adfc502 | checkpoint | 2 - Set out the works
e1352da0-8979-5311-99ed-2855319c0009 | note | FREQUENCY: Per Lot
51db1a63-2dcd-5126-b0c7-916c38d13d84 | note | ACCEPTANCE CRITERIA: Establish Pegs (or equivalent) to identify the extent of pavement
7a8662e5-0951-5ea6-a84c-32bc03f27e52 | note | RECORD OF CONFORMITY: Verification Checklist
efaaeb58-4d51-5922-8906-2b2fc75b17d6 | note | IP
cf596d86-6380-5137-827a-ed3ff8310627 | note | RESPONSIBILITY: Surveyor
d3ce0973-fd16-52b5-86d9-fdbce6482dfd | date | Date Completed:
b414137f-0fd5-46d5-ac9f-9dc611e3a042 | checkpoint | 3 - Check underlying lots are conforming and closed
66cd3023-21fc-5da6-a145-b42de323ee72 | note | FREQUENCY: Per Lot
4e68a96d-e2d0-5922-98c4-003d30789509 | note | ACCEPTANCE CRITERIA: Check underlying drainage and earthwork lots are conforming and closed, Hold Points released
7ecd42f8-b3bd-5469-8a47-beead254e66c | note | REFERENCE DOCUMENTS: R44.6.1.2, R11.4
bf2f375f-634a-50d3-9a10-58e4d2d68bb6 | note | RECORD OF CONFORMITY: Verification Checklist
f00cffa0-3faa-56f9-b449-9a72a3903226 | note | IP
df5d273b-20b7-55c4-9120-82e98c49d61d | note | RESPONSIBILITY: Site Engineer
018d3c04-44ad-5c27-955d-7d932ba07e58 | date | Date Completed:
deecbb26-c06b-48cb-8c8b-bf0b8463d792 | section | 4 - Materials
d494e9b5-1ebd-448e-bc03-1c158bc17527 | checkpoint | 5 - Obtain material specification certificates
a2460008-afa0-5332-9eaa-8069efc26ae4 | note | FREQUENCY: Per Stockpile
58fa522b-ddb7-5023-915a-c881a972226e | note | ACCEPTANCE CRITERIA: Verify material meets the requirements of R71 and D&C 3051. Attach NATA endorsed test results to the statement, indicate the quantity of material represented by the test results.
85c1ebd8-d92b-5c12-bdc2-a421e21b292e | note | REFERENCE DOCUMENTS: R71.2.2
96e459b5-60eb-5ee5-aa08-2a69df43b367 | note | RECORD OF CONFORMITY: Hold Point
13ecb6d7-004a-5fe1-b181-0dd1985cf8e1 | note | HP
3e983622-c2ac-51f9-bc4b-bae41c801245 | note | RESPONSIBILITY: Site Engineer
0afe65d1-8756-5c8e-8854-dd557a061bdc | date | Date Completed:
5a47d6f6-52dd-4d5c-a41c-1ebfd5cb2bb0 | signoff | AUTHORITY HOLDPOINT
d904f992-fd99-4a6a-a971-69d2f0362194 | section | 6 - Construction
2baf8cae-ba2a-42aa-9d4e-4faadee878c4 | checkpoint | 7 - Check material upon delivery
e6972578-c0f0-57a8-a842-6541720aa9f9 | note | FREQUENCY: Per Lot
9bba883c-8f30-5a31-a910-65a51bc88e72 | note | ACCEPTANCE CRITERIA: The material must be slightly damp and at the time of delivery
e26837c2-86ba-5165-bbe7-322f524979e4 | note | ○ Check delivery docket to ensure correct materials supplied
da2a21cc-ab1b-55f3-965e-f2da05b9365a | note | REFERENCE DOCUMENTS: R71.2.4
8bfcb6a5-9473-5576-b824-0c2109b26c30 | note | RECORD OF CONFORMITY: Verification Checklist
ad3aa973-ae18-5f0c-b70b-be59e8ccf610 | note | IP
9cf0fd7d-2406-51ba-931f-bbf3de7e2acd | note | RESPONSIBILITY: Site Engineer
9eb3b3f5-0dc1-5155-9509-f93a25f83f91 | date | Date Completed:
91e01ddb-640a-406e-9557-1e2c5af734ae | checkpoint | 8 - Placing, spreading, compaction and trimming the material
60ef997a-726d-5a3e-a1ba-f141a00633e7 | note | FREQUENCY: Per Lot
9c26b882-f045-5df0-ab64-ab2d1d5a896f | note | ACCEPTANCE CRITERIA: Maintain field moisture content during placement and compaction within the target moisture content envelope
88d20a8c-e151-545c-bce7-aa03e8502c18 | note | ○ Compacted layer to be 100-150mm thick
d56f8baa-231c-58b4-9caa-66b59f48eac3 | note | ○ For modified (sub)base, complete the construction within the Allowable Working Time
187b9f03-c37a-52ac-8d3e-88d1ddbc928f | note | ○ No roller marks left after final trimming
ed93693e-fc89-5f8a-abad-5c53bdb0161e | note | ○ No delivery traffic allowed on the placed
1cccafda-44bf-5a8b-a344-90655cbfbf8c | note | ○ Trim the pavement course to design level
20caceca-5471-5ba6-ac42-13abf42972dc | note | REFERENCE DOCUMENTS: R71.6.5
31d2e3c0-3c66-5379-9dfe-9fe49ffef21d | note | RECORD OF CONFORMITY: Verification Checklist
55c55e63-6794-55a1-8554-a27d9c15fbc1 | note | IP
ee2cd44b-41d7-5b50-b68f-ce70e63fcde3 | note | RESPONSIBILITY: Site Engineer
bd40272f-c9ce-59ba-8792-9e11274ee5c1 | date | Date Completed:
c44df2d4-14b3-4b52-96c6-078b602a30fb | checkpoint | 9 - Verify finished pavement properties
ee3ba84d-9519-5b17-bec2-813430cd5e44 | note | FREQUENCY: Per Lot
ed82ff43-d326-5aac-a39a-dfe7e91ace6f | note | ACCEPTANCE CRITERIA: Compaction to 100% std
f1db41cd-12ab-55a5-911c-6deb1cd076bc | note | ○ Moisture content ≤70% of OMC prior to seal – as relative compaction frequency
c8979e02-2bad-5f4c-8cfc-ef15de59bc06 | note | ○ Level within -0/+10mm (base), or -10/+0mm (subbase) - 1 per 20 linear metres, offset as per table G71.7
2564e559-8869-5197-a2b8-630ac1e92890 | note | ○ Layer thickness within -0/+20mm (base), or -/+10mm (subbase) – at least one site per 75m, with a minimum of 2 per lot
5856dcfc-37a9-5c10-9742-60e7f5406870 | note | ○ 3m straight edge: max. 5mm – minimum 1 per 20m2
934b5be5-d892-5749-b0ec-4509bbed266d | note | ○ Pavement width ≥ design width – minimum 1 per 20 linear metres.
3967e108-aed0-5b08-868f-ece298dc39c9 | note | ○ Unconfined compressive strength is less than 1 MPa (accordance with T116)
d8f251ec-86dc-58f7-81a0-95fa2ec5ba55 | note | ○ Minimum frequency of testing (T116 one pair per 400 tonnes or part thereof)
47bb43f1-fe54-5e0d-94b0-c682260ed0af | note | REFERENCE DOCUMENTS: R71.8, R71.8.4.2, R44.7.4
435ff9a4-fbfd-559a-ae1b-b3d267f5865a | note | INSPECTION / TEST METHOD: T116, T173, T166
a8c268c2-cc40-5f05-b810-4db4cca399bb | note | RECORD OF CONFORMITY: Test Report
d7b18973-9135-5824-90aa-61f0dad50678 | note | TP
c3d32dda-6c62-5e6d-97d4-67b2f98752e3 | note | RESPONSIBILITY: Site Engineer
b8bfbfdd-423f-538a-9733-5b14bf1e32b7 | date | Date Completed:
f8ec3f57-0005-4d7a-b743-cb6f36c0c77c | checkpoint | 10 - Obtain approval for sealing of the pavement
98ef0158-7af7-568b-88c2-4c46d1b3deb5 | note | FREQUENCY: Per Lot
a0f19000-7a33-5b7b-b01f-ecec48f24cf4 | note | ACCEPTANCE CRITERIA: Submit to the Project Verifier with test results of above pavement properties
3a428c3c-316b-583b-a46e-b76aff7b812c | note | REFERENCE DOCUMENTS: R71.6.8
99472908-31a9-5b1e-8fdc-5db554831b1a | note | RECORD OF CONFORMITY: Hold Point
6c8f9ca6-f73f-5163-bcde-4b2c2ba13731 | note | HP
b4f2bb2a-98de-5f0a-b180-ff741c88676d | note | RESPONSIBILITY: Site Engineer
d301c36e-8166-5e1a-bc38-6d77b53be5c5 | date | Date Completed:
53037953-9ab6-4eb7-8ecc-6d0aab754efe | signoff | AUTHORITY HOLDPOINT
77120c63-1f4f-4407-9097-748e4c805617 | checkpoint | 11 - Carry out base course surface assessment
75e077c8-d8c0-526f-b96c-e5535857c304 | note | FREQUENCY: As directed
2d5e7c41-ec29-5c2b-8b6f-5d9317284ea8 | note | ACCEPTANCE CRITERIA: The average ball penetration value of a sample location (Pes) is ≤ 3.0 mm; and the characteristic ball penetration value is ≤ 2.5 mm.
cde00aa9-d5d4-5e93-8494-2ec6204bca12 | note | REFERENCE DOCUMENTS: R71.8.10, Q6/L3.2
31567ff5-c1c8-5a3e-9d64-a4077ce04fb8 | note | INSPECTION / TEST METHOD: T271
c1990b4b-05bb-51fb-93bf-a7d4f6cbde5e | note | RECORD OF CONFORMITY: Test Report
d662a809-6d5c-5c0c-bb1f-69257ea024a0 | note | TP
c9f76b13-62cd-5b64-9a4e-8438801565e6 | note | RESPONSIBILITY: Site Engineer
5cbf15ad-287c-536e-8323-fd60e346d1fd | date | Date Completed:
67c5f034-be4b-4d1a-99ad-1335d50382cb | checkpoint | 12 - Obtain approval of treatment of non-conforming lots
46b8d742-486e-5e6d-8529-15aac3ade279 | note | FREQUENCY: Per Area
5aded2c3-f0ab-5c17-82aa-0571454c8ffc | note | ACCEPTANCE CRITERIA: Submit to the Project Verifier a NCR and details of proposal to rectify or replace the Lot, prior to carry out the rectification works
b1b36afd-06cc-5256-b9ea-26f50f92b925 | note | REFERENCE DOCUMENTS: R71.8.12
61c7c027-888b-57b4-8bf6-3c07d8fc00f6 | note | INSPECTION / TEST METHOD:
697c4d7c-ee24-548b-9707-4bb5e51f290d | note | RECORD OF CONFORMITY: Hold Point
02c73500-9552-5fe9-9b81-324c4c4a4010 | note | HP
79503fde-d177-5538-9a69-f9b297666a10 | note | RESPONSIBILITY: Site Engineer
66e809a3-f59b-53be-987f-25c9fba02c56 | date | Date Completed:
2ffdce1f-94bb-42bc-89c5-fd3219066415 | signoff | AUTHORITY HOLDPOINT
0218aecd-6220-4d0d-8736-b9129e65673a | checkpoint | Final Inspection
d465a78c-9acd-57e7-a33d-d39fe02a6545 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
ff9a2764-0d83-5f87-9256-88fe005a91c3 | textbox | Print Name:
6b8b197a-74ec-5743-93f0-9598d063183c | textbox | Position:
bbc7ee7c-893c-53a2-ade1-eb6a9c25a023 | date | Date:
ff638fbc-f686-4211-84c8-6f2d7e58af2f | signoff | Sign ITP
560bcdff-eb81-4ffe-8e33-0c101ac316e6 | checklist | NSW-R116-ASH-ITP-Asphalt Pavement - Public Roads Upgrade Upgrade | itp | NSW-R116-ASH-ITP-Asphalt Pavement - Public Roads Upgrade Upgrade
34bb219e-bbf2-4849-aec9-0bed9a936c4f | section | 1 - Preliminary
bbd65495-7a77-453e-b162-e2e0ebf89c6d | checkpoint | 2 - Confirm the type of asphalt seal to be laid against the design drawings
d4d78fc9-a156-5ede-ab07-9e58c224f712 | tickbox | Correction
a98b9a78-f448-53c3-beb5-e69afac74308 | tickbox | Intermediate
3c41f966-ac72-564b-98b6-542a331b7372 | tickbox | Wearing
41b26090-1d26-5e63-b128-3ef051516fb4 | tickbox | AC20
1c8a0631-f922-5606-9387-4fa5ae3c3fbb | tickbox | AC14
ceef70a7-4f76-575b-8cee-901f2dcf03d4 | tickbox | AC10
a9fec8a3-b51f-54b7-84a4-be003c5461e6 | tickbox | AR450
4ff2e985-41fe-5850-8322-45a9cd5f5cec | tickbox | A15E
1ed57e3a-8052-5d58-9fa4-c3066e462bf2 | textbox | Other:
eacefaaf-2356-5b24-9264-432030e7c4d2 | textbox | Thickness:
04b1d2b2-2b19-5943-8993-2c3eaa23af00 | note | FREQUENCY: Per Lot
100d4c35-f475-5386-8ed1-aea1825af2d5 | note | ACCEPTANCE CRITERIA: The type and thickness of asphalt are proposed as per the details shown on pavement design drawings
391c0b0a-db73-5cf6-90c6-ca19cff44f66 | note | REFERENCE DOCUMENTS: Design DWGs
feb07a1b-588f-5604-99aa-dbcab9f5202b | note | RECORD OF CONFORMITY: Verification Checklist
c31fc233-96e7-55d5-886f-758685ee5249 | note | IP
53dcd996-eb74-56dd-adf7-02b3483f4599 | note | RESPONSIBILITY: Site Engineer
f216a74e-75ec-5edc-9459-e20734244cbf | date | Date Completed:
972f7684-b357-451c-88de-5ab72039f1b8 | checkpoint | 3 - Mix Temperature for Laying
b2dd2844-d22d-5c2b-a5db-07588aadc442 | note | FREQUENCY: Each Lot
53e2713a-709b-5103-9e0f-163ce914d1ee | note | ACCEPTANCE CRITERIA: Warm Mix:
fdf11ca0-2c49-551e-a58c-c35a5c1292f5 | note | — To be delivered into the paver between 120C-165C. Minimum temperature before compaction of 110C.
f0078291-5e39-5866-96ac-3c1e8b83882a | note | ○ Hot Mix:
c5622deb-6eda-5c34-9667-5e31fce8d7bf | note | — To be delivered into the paver between 140C-175C. Minimum temperature before compaction of 120C.
6dcba46f-3ea8-5c0b-b2d0-72577b763cec | note | ○ Temperature recorded by Infra-Red Temperature Gun & Probe.
8858c0e9-3dc9-5945-912f-763e9fe2f3e7 | note | REFERENCE DOCUMENTS: R116 and Asphalt Laying Procedure. Measure using an infrared thermometer.
164fc990-fab4-5663-9c45-6132899f8a50 | note | RECORD OF CONFORMITY: Hold Point
af8f104e-da1a-52c2-89a6-3ace6fd6aa50 | note | HP
b4e81b24-fc84-5a3d-8b5c-2f8f48ae4dbd | note | RESPONSIBILITY: Site Engineer/ Foreman
93262fcf-dc4c-58f4-b0e6-173c86b96b93 | date | Date Completed:
45740f29-3048-40ee-83a5-9ad34a24f802 | signoff | AUTHORITY HOLDPOINT
d4f8b4a9-b191-4541-aaec-733c4e87819d | section | 4 - Preparation of Pavement Surface
0c57f1f2-0fd9-4b9a-add6-1c6f486c31ff | checkpoint | 5 - Setup the working area
9192b12f-bd6e-50e8-9af8-59e88dd7d1b7 | note | FREQUENCY: Per Lot
fe138284-ea26-569d-b997-fa4b7f3d4a50 | note | ACCEPTANCE CRITERIA: Mark-out the placement boundary, chainage and required thickness on the surface of the areas
a92eb738-81ac-5e34-a92f-386613de2e0b | note | ○ Ensure the mark-outs matches drainage inlets including kerb and gutters
8ff43065-4b20-532f-931c-2de27acdd1a9 | note | REFERENCE DOCUMENTS: R116.4.3
e4e7d1d8-5c1a-539c-aa94-470f81d27fa8 | note | RECORD OF CONFORMITY: Verification Checklist
a52786d1-9b1e-54a7-a1c5-8611e67a5ee5 | note | IP
ce70eb07-026a-5e50-a6c5-c5ee097587c0 | note | RESPONSIBILITY: Site Engineer
ee9d5143-c262-5442-9387-744641520364 | date | Date Completed:
4b908c3f-5e98-46b8-a0d7-944e7e136e9f | checkpoint | 6 - Preparation of pavement surface
61e420e9-6240-585d-b678-2f5edd0411b1 | note | FREQUENCY: Each Lot
117f008b-29a9-5a21-a130-be30e644bafd | note | ACCEPTANCE CRITERIA: Prior to place asphalt, prepare the surface to a clean, no loose material, defect free and road markers removed, road services and fixtures in vicinity covered, and where required, prime sealed.
79056ad0-3cbb-51fe-9e23-3bfb822b4c17 | note | ○ Sweep to extend 300mm beyond each edge of area to be paved.
677d3307-1e88-5ab0-bccc-be27fe3ef5e3 | note | REFERENCE DOCUMENTS: R116.3.2, AS2150.10
d15aff98-00ac-5977-8acb-63c848145a1d | note | RECORD OF CONFORMITY: Verification Checklist
9d18f239-411f-5d06-a0c2-7f167fb5b1e3 | note | IP
e9619fe5-61e9-54b1-818d-b1ca2f9147f9 | note | RESPONSIBILITY: Site Engineer
3816f717-4af6-5f0c-9f7b-dfc98f0e85f4 | date | Date Completed:
3145d3ff-5082-49f1-af9d-fa9a7f795d7d | checkpoint | 7 - Check and record pavement temperature and weather conditions
392e8f5e-3f1e-58e9-87c9-9bd511476ec1 | note | FREQUENCY: Each lot / 1 check per 2 hours
b887a1db-bf36-5249-9836-a9bfba02bb49 | note | ACCEPTANCE CRITERIA: With zero wind speed pavement temperature must above:
d091c4fb-b454-5041-b308-01fd21dfa39a | note | Binder ¦¦ Aggregate ¦¦ Temperature
9a3f300a-9398-5c44-a64a-9ed7fa7b5435 | note | A15E ¦¦ AC20 ¦¦ 10°C
481c7312-0d94-51c5-816c-d6aa589f0251 | note | A15E ¦¦ AC14 or smaller ¦¦ 15°C
38c20ce9-042a-5ce8-af4b-0b1318b6f361 | note | AR450 ¦¦ AC20 ¦¦ 5°C
887a0d7a-dda4-5b67-a6e3-85de0ae52677 | note | AR450 ¦¦ AC14 or smaller ¦¦ 10°C
f6cc8099-40fd-5604-8181-e26decffe6ad | note | ○ Add 5oC to above limits for each 5 kph of wind speed above zero
bc9425d9-4531-5e93-9280-d5aed3c9a50a | note | ○ Do not place tackcoat and/or asphalt when the pavement surface is wet and/or rain is imminent.
ef8a4abe-ba9b-53cb-8bfb-6ea7289aee09 | note | REFERENCE DOCUMENTS: R116.3.7, 3252, 3253
ad91ad81-b397-5e58-a9f3-abb3a471a2bb | note | RECORD OF CONFORMITY: Asphalt Placement Record
e46f4402-27af-5be1-ab1e-36ee21bfd96d | note | IP
d8c18ce3-985c-5583-9d9a-ed7ce650b4e1 | note | RESPONSIBILITY: Site Engineer, Subcontractor
24081ccc-fdbb-57fc-b169-9167b76b9879 | date | Date Completed:
ce4397bf-f30c-4190-8af4-eb8d08ba6fbd | section | 8 - Construction
a259c14d-bee6-4829-a1c5-640fe5870e4e | checkpoint | 9 - Construction of temporary ramps / preparation of construction joints
1d492d03-ad2d-5351-8848-d52441010713 | note | FREQUENCY: Each Lot
4d1e284a-d8f4-58c9-92b0-3fc7fe3adf2a | note | ACCEPTANCE CRITERIA: Set up and prepare the temporary ramps and construction joints for safe access and protection of constructed works
53849491-7a6e-54a5-88a8-7c78f5d64c7e | note | REFERENCE DOCUMENTS: R116.3.12, AS2150.A
65e305be-e93f-5d2b-b78c-55595551c108 | note | RECORD OF CONFORMITY: Verification Checklist
cc0e1f72-5d62-514a-bcd3-0607b2df61d5 | note | IP
b1e713c1-b276-58a1-b3dc-6029d8b3a6ae | note | RESPONSIBILITY: Site Engineer
55c8c2b1-4aa4-5d09-87e5-aed1feb2690b | date | Date Completed:
ffd05bc4-b0ee-4fe6-95f2-190a2ed6a268 | checkpoint | 10 - Application of tack coat
db65d20b-bc08-5f05-9398-bcdd95c6d4da | note | FREQUENCY: Each Lot
01e35acb-abcb-56ff-9911-716cbff2963c | note | ACCEPTANCE CRITERIA: Apply Tack coat at the nominated rate, and record the rate in the Asphalt Placement Record Sheet
4394b239-0257-5185-8ded-0c3558705b63 | note | ○ The application rate is to be between 0.15-0.3 L/m2, if not otherwise specified
6f1f9e8a-af26-5986-ab41-b6ccee7f110b | note | ○ Nominate in writing to the RMS rep your proposed tackcoat application rate prior to applying the tackcoat.
aa221076-e2cd-53b3-92a8-e89c5d1348c3 | note | ○ Reduced application rate for tackcoat is acceptable due to the existing underlying pavement material. Comply with PV first.
c3464a0f-df49-586d-aa5e-2b0c50b165a1 | note | ○ Report the application rate in terms of residual bitumen and state the percentage dilution of the tackcoat used during spraying
c6b72f91-2e5c-59cd-98db-badff6919c7a | note | ○ Provide to RMS rep a daily record with your endorsement, of the average tackcoat application rate applied to each lot.
9a205961-e714-5d55-a5b0-8853b49f009a | note | REFERENCE DOCUMENTS: R116.3.9
d1481e79-6a24-5668-ac7c-35f1dd2d184f | note | RECORD OF CONFORMITY: Asphalt Placement Record
d637d0da-7f91-508b-b13d-6815ed0c6772 | note | IP
355aedb2-1c17-5345-b01c-45134285a023 | note | RESPONSIBILITY: Site Engineer
f5aebbad-23dd-5e62-a8d0-6a30c1d5efba | date | Date Completed:
f0d0ab14-9dbd-4d2a-a4c1-852dfa1a4a26 | checkpoint | 11 - Check Asphalt Temperature
d769a803-da14-563c-95d8-99edb82d7276 | note | FREQUENCY: Per Delivery Load
ad92aaec-a242-5dd4-a8c4-4886713a7696 | note | ACCEPTANCE CRITERIA: Measure and monitor paving and compaction temperatures and ensure they are not fall below which nominated in item 5.
f8e5a22a-f917-5f02-8e72-a3a39a0479ba | note | REFERENCE DOCUMENTS: R116.3.8
455bd2f6-da2b-5d96-82d3-5c3cffa1d972 | note | RECORD OF CONFORMITY: Asphalt Placement Record
9d4c45c6-f27e-5ce7-8476-1897640ff2ec | note | IP
152aab23-8513-5577-b520-da93867d2107 | note | RESPONSIBILITY: Site Engineer
4da0fa37-75f8-511a-9ee6-8bc2269b16bc | date | Date Completed:
ada999c5-2891-49b5-abd6-5e0ca21a884d | checkpoint | 12 - Construct joints to specified locations
73e1c080-b98e-531e-b4a7-5ba6ac478ea8 | note | FREQUENCY: Per Lot
fbbbcfad-de7e-5027-8952-4a0ce5c16773 | note | ACCEPTANCE CRITERIA: Longitudinal joints are to be:
f835afc0-a337-5017-8b32-af1c014af7fb | note | — Offset 150mm from the joint of underlying layer, within 150mm of the line of cross fall change
f048cc14-8365-5c28-a406-0f2bd5ef404e | note | — Located out of wheel paths & in surface layers, coincident with final traffic markings.
11defa88-9a7e-52ec-83ca-6383de736d29 | note | ○ Transverse joint are to be:
5f99e004-0ff8-591a-a9c6-9432abd95d0c | note | — Located a min 25m apart
7f79555f-89aa-5880-90b6-d7b97a403c0d | note | — Offset 1m from the joint in the underlying layer
3d301eb0-e435-59e6-8371-1f7523c8a303 | note | — Formed at the commencement of each paving run
a538f7bd-b734-5bbb-ac35-5cd0eb88087e | note | — Formed when a delay in paving causes asphalt temperature to fall below the initial compaction temperature nominated in Clause 3.8..
f11e9485-1ea8-558a-93e7-667bee0e2302 | note | REFERENCE DOCUMENTS: R116.3.10
0f3ca65f-0af4-5f00-9b9c-868c7f598a4c | note | RECORD OF CONFORMITY: Verification Checklist
ca3632e2-58ec-5892-8049-8396f55c9261 | note | IP
aa89465a-92b6-5ca5-8d35-2d36b70962cf | note | RESPONSIBILITY: Site Engineer
997a1377-f7a5-59ae-959c-db6a88549fbd | date | Date Completed:
0522e970-33c3-497a-9d61-2a2fc03f6e8e | checkpoint | 13 - Supervise the placement work
bb372c71-ae80-5409-88c5-9baeb1a7c265 | note | FREQUENCY: Per Lot
0b1ef242-c795-5093-bffd-cb95b5d94126 | note | ACCEPTANCE CRITERIA: All asphalt must be homogenous in appearance. Areas of asphalt that exhibit segregation, cracking, ravelling, bony or fatty material, or damages rectified or replaced.
34c31ab0-0fe0-5709-ad83-3948823882db | note | REFERENCE DOCUMENTS: R116 5.1
d4dd3299-0b12-5756-aa3d-2d8742e76885 | note | RECORD OF CONFORMITY: Verification Checklist
1454abb6-1e30-5550-88dd-e34925e5a6c3 | note | IP
3bc09bc2-c0b8-5bcd-bf97-5d2529ea9d70 | note | RESPONSIBILITY: Site Engineer
e484dc8a-fa9e-545b-b955-2a2573901f9e | date | Date Completed:
37d7088b-f250-4f6e-bb09-2152d681edcf | section | 14 - Post Placement
3152b29c-094b-48b2-ba02-958d3117ad2c | checkpoint | 15 - Protect services
cbeaeca6-17fd-5b86-82ae-7dc7e42a6004 | note | FREQUENCY: Per Lot
d8b95ff5-1869-5311-985b-d697ce1a4111 | note | ACCEPTANCE CRITERIA: Immediately after the asphalt has been placed, clean & remove off waste asphalt from affected services and road fixtures
90c6d40a-9625-5373-a30c-186ce94be8ea | note | REFERENCE DOCUMENTS: R116.4.3
0df008e5-c37f-5b28-b2b6-c3893c96d8ad | note | RECORD OF CONFORMITY: Verification Checklist
0e025406-fb18-5aa0-9203-c1a2fae02d0f | note | IP
b6e06b73-9cd2-5497-8ccd-cdddad6c01e4 | note | RESPONSIBILITY: Site Engineer
90eb2b42-dd33-5b4b-be46-680080984137 | date | Date Completed:
14a4ccdc-5d2f-439e-bd2e-2188663d4dd6 | checkpoint | 16 - Obtain and verify conformance records including relevant verification sheets
24116ad1-6d9c-5455-849b-3f2bd9cbd425 | note | FREQUENCY: Per Lot / R116.L
99f15681-fc47-5077-9614-88ffaaa0681c | note | ACCEPTANCE CRITERIA: Check conformance report against conformance criteria:
65fee221-77c5-515c-bc8e-09558c174168 | note | ○ Production test results
c71013d7-7d05-5024-8e9c-1bd4682171ee | note | ○ Asphalt placement record with all dockets
32fecdc6-7375-5d8d-af7b-e8e2686dcaf9 | note | ○ Field test results – insitu air void, course thickness
e58ae313-27ea-5a3e-b467-1458cf60514e | note | ○ Lot diagram with chainages
031f5780-c3ab-5ff5-b7cc-36e519370be8 | note | ○ 3m straight edge report
74739a20-5135-5a4a-8069-5357df310b24 | note | ○ NCRs if required
99038458-eef1-5410-9fe9-b9610429ae8b | note | REFERENCE DOCUMENTS: R116.L Q6
a6f640b7-57cf-5200-b44e-ffd876ed8a79 | note | RECORD OF CONFORMITY: Asphalt Placement Record
94092fb4-e2e4-58da-be71-be388787cd7a | note | IP
29e9e2b5-570e-5c87-b528-5be82970d638 | note | RESPONSIBILITY: Site Engineer
d517e3da-1172-5934-9653-533d042bf727 | date | Date Completed:
c71f6fb5-1f81-41d5-906a-ed96d294d43c | checkpoint | 17 - Conformance of Levels and Thickness of Pavement
941f3b96-f9f1-531a-9af6-e05ea3958f36 | note | FREQUENCY: Per Lot
3685e159-afcc-54c4-b54f-cfd73f7ee055 | note | ACCEPTANCE CRITERIA: Level of any course placed meets table R116.9 except where tying in to existing surface where the pavement is to drain surface water and match levels of existing surface.
3357ce17-e9b3-5147-9c88-0915f5a6576a | note | ○ Average thickness of calculated by survey consistent with average thickness calculated from cores except for wearing course which is to be within 10% of design thickness.
7b3908e9-73a3-5149-8249-601b74962c72 | note | REFERENCE DOCUMENTS: R116.4.3.1
431f4766-f3e4-5237-9eff-f9cd8c63d0e1 | note | RECORD OF CONFORMITY: Survey Report
fd161d54-a6fb-53a6-9092-8eda0511f193 | note | SCP
f3b9b37c-0bf9-593e-9639-b6e91f840f6b | note | RESPONSIBILITY: Surveyor
938d5ee0-a6e9-58d8-a623-05ea3ee57a0b | date | Date Completed:
cf873cce-1796-4501-8ccf-29c8bc580c72 | checkpoint | 18 - Submit Test results to RMS
a6435e21-54ca-51f8-bbcf-6ad96f184280 | note | FREQUENCY: Per Lot
f2032564-0263-535a-965c-f784fe9b19fa | note | ACCEPTANCE CRITERIA: To be submitted progressively
c230ea89-b88f-54b2-a0a3-45e2e45e4c06 | note | ○ Binder content, combined particle size distribution, air voids – within one day of mixing
0ab2fcec-03ba-5dc9-856f-62819d55c874 | note | ○ In-situ air voids, course thickness and course shape within 3 days of placing
9bc9fa46-766a-5310-af29-8e24bd55fe01 | note | REFERENCE DOCUMENTS: R116.5.3.3
ac308d5c-5d34-52aa-8989-9dd4577492c3 | note | RECORD OF CONFORMITY: Transmittal
47590ee3-cefd-543c-91d6-423afe724366 | note | IP
9aa34c19-4a24-5e0e-8357-03c47e50cb9b | note | RESPONSIBILITY: Site Engineer
d3c0b4c5-f64f-515d-9852-569eb09ae5e2 | date | Date Completed:
e9c527dc-240a-4aeb-98d6-306091bca315 | checkpoint | Final Inspection
e4561363-0af6-56d9-8fcb-798f0cc7cf99 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
d348d2a3-12df-5b49-86df-e510b592077f | textbox | Print Name:
48ad5213-c799-57b4-8d25-8c19f1a9fdde | textbox | Position:
cab77e17-6d89-5749-b81d-8a188a282d92 | date | Date:
5e415cc0-b892-4481-9c49-7c27bcb859fb | signoff | Sign ITP