## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
9630dacc-0e8f-4a76-b011-0f44d92b1f3e | checklist | ITP-005 - Rock Beaching/Structures Rev0 | itp | ITP-005 - Rock Beaching/Structures
23972fcd-7bf0-485a-ac31-5e448b46c69e | section | 1 - Preliminaries and Submissions
6479579f-6c2c-4b1e-a89e-77467c929dcc | checkpoint | 1.1 - Check for correct documentation
86972dc9-717c-56de-9723-2e365ed02dc4 | note | FREQUENCY: Before commencement of activity
109b2576-b80e-5fb3-bebf-2c1693479564 | note | ACCEPTANCE CRITERIA: Check correct documentation is being utilized
8ee83079-bc63-5a6a-b9e2-14515864c5f6 | note | REFERENCE DOCUMENTS: Drawings
43969167-b458-5a42-bc9f-5fa37505b8f7 | note | INSPECTION/TEST METHOD: Current revision of drawing
6b3cfc62-99e7-5838-bcc4-e55c7d32116c | note | CONFORMANCE RECORD: Current revision of drawing
e90ae509-7592-5d95-b1e7-fc4629e1913d | note | *HP
0afa7d27-b874-550b-858f-383c5cb4620f | note | RESPONSIBILITY: Fulton Hogan
739d4066-ea62-53c2-b927-84782f96cccc | date | Date Completed:
f7087bf2-a719-4215-8b9b-64a32731d43e | checkpoint | 1.2 - Ensure Safety, Traffic, Quality & Environmental management measures are in place
56b1dc22-a8a3-5bc0-9454-1655aef897dc | note | FREQUENCY: Prior to commencement of activity.
739479ae-0df5-5ce0-a052-c0e4269ffb15 | note | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
c88e006f-7ea6-52b6-b8d6-0d1d178b5f75 | note | REFERENCE DOCUMENTS: PSP, TMP, EMP
e43ac2c1-dd6d-5a76-8859-7c982d6e7324 | note | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
0dd9d6fe-9326-5539-b792-5e8ea3daaac1 | note | CONFORMANCE RECORD: Inspection
98eaedf5-c182-5b95-95b9-35edf8401c39 | note | HP
bf183dae-b682-564f-a294-db42f6653d2e | note | RESPONSIBILITY: Fulton Hogan/Client
9cf2ae88-731c-513f-93c0-0bd3dd2cc2c1 | date | Date Completed:
6153a31b-3628-4ea8-acbe-52b20e832026 | signoff | AUTHORITY HOLDPOINT
7bded62c-94a5-4f58-917e-16f4ad4de12f | checkpoint | 1.3 - Stockpiling
a888b771-997e-56da-95bf-013fade7b6d3 | note | FREQUENCY: Prior to removing material
72efd116-d161-513e-8480-67e7c6a6ba0b | note | ACCEPTANCE CRITERIA: Confirmation of stockpile location approved by superintendent.
e710054c-50ed-5222-8db3-b02b87b0f5fa | note | REFERENCE DOCUMENTS: FH Scope document, EMP
204db9ae-7c61-5ec7-8001-73ae20f97b81 | note | INSPECTION/TEST METHOD: Approval
996c17aa-fc6b-50df-815e-54f117387a92 | note | CONFORMANCE RECORD: ITP
50aa88b4-c34f-5f1d-b3cc-3aeae46d1f87 | note | WP
5a48a156-417d-50f0-8df3-172f4eb03ee1 | note | RESPONSIBILITY: Client/ Fulton Hogan
4ee9ca70-f562-5433-8da5-14827ed49665 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
881d22ca-c6c1-4e0c-9dc2-942a83ae2733 | checkpoint | 1.4 - Identification of services
cc576fe2-5137-5715-a721-5b448147a045 | note | FREQUENCY: Prior to commencement
1b7ba89b-4d3e-5134-9b89-cd339783b595 | note | ACCEPTANCE CRITERIA: Any existence of underground services to be located and proven
e17436f1-948b-5b9f-a0cb-03aac9ff2b5f | note | REFERENCE DOCUMENTS: BYDA Section 100.8
86f05acf-7ad4-5afd-8e91-343f6d5ad87d | note | INSPECTION/TEST METHOD: Inspection
ddffdcea-2296-5148-b7e7-756d7066ab94 | note | CONFORMANCE RECORD: ITP
e06f025f-8db0-5fa0-aa6e-4d825a040535 | note | HP
24ad337c-370f-5833-b559-e6e6f438e6ad | note | RESPONSIBILITY: Fulton Hogan
c174aa04-a398-516e-b345-a7069605e5c8 | date | Date Completed:
05fb7890-3d22-4f3a-9347-56b5ec45d875 | signoff | AUTHORITY HOLDPOINT
92b393f8-cbc4-41f2-ac65-aa245ca66e47 | checkpoint | 1.5 - Project management Plan Completed
3344529d-d7ed-50a5-82c4-2b4c2df23bdb | note | FREQUENCY: Prior to commencement
0a5381db-e7bc-5327-9348-7cf52155ec21 | note | ACCEPTANCE CRITERIA: PMP Completed
bc100208-2b50-5af7-aaa2-70f86951a440 | note | REFERENCE DOCUMENTS: PMP checklist completed
7b6ec8b1-845e-535a-8c16-fe5dfaf5aed4 | note | INSPECTION/TEST METHOD: Inspection
195219c8-2320-58f5-b3c3-68838a2f11c2 | note | CONFORMANCE RECORD: ITP
6e5688d3-469c-55c7-b7a8-2446e580af67 | note | HP
5ddbe819-f32b-51d8-81d9-e75e676ab531 | note | RESPONSIBILITY: Fulton Hogan/Client
aca27d08-9b73-56b6-8db7-7dfc6614f57b | date | Date Completed:
44866846-2432-4872-b1f0-e41abaac75e2 | signoff | AUTHORITY HOLDPOINT
c2706d86-fc79-4be2-93ba-c77fc2edf2b5 | checkpoint | 1.6 - Site set out
3e52002d-1d45-585b-8934-24927a16803e | note | FREQUENCY: Prior to commencement
9f0552e9-7658-5d47-ba6d-73f2ac5999af | note | ACCEPTANCE CRITERIA: Site inspection
e2abe5b0-bdad-5ca5-83fb-b57285a313e9 | note | REFERENCE DOCUMENTS: Scope document Drawing 796684
1eb9242d-26ec-589c-b4ad-043561037f71 | note | INSPECTION/TEST METHOD: Site inspection
7df0f874-d0e5-57ef-9734-863a94c63dc2 | note | CONFORMANCE RECORD: ITP
6cdb30fe-988e-5f58-9790-0f24195053ac | note | HP
6cedc16b-78a0-5915-b72a-eb814c75f066 | note | RESPONSIBILITY: Client/ Fulton Hogan
081b0637-0b09-5f08-96ef-2a4841f95b93 | date | Date Completed:
fe2e276b-390e-47cc-9965-9f5dd1a4019a | signoff | AUTHORITY HOLDPOINT
7d3ef194-a5a5-4f36-9047-c25c45ee5003 | checkpoint | 1.7 - Ground breaking
cceb0762-fe35-5cb0-ac15-ea0e86823c02 | note | FREQUENCY: Prior to excavation
d64201e4-131c-5044-82b5-dc9e6f9b9a37 | note | ACCEPTANCE CRITERIA: Works to be reviewed and agreed by Superintendent
01eeb70c-27f6-5cef-a70c-9a33f8a459b2 | note | REFERENCE DOCUMENTS: Hold Point release for Commencement of Works Letter
d995078b-381f-5de4-8d8a-bdf9f295f329 | note | INSPECTION/TEST METHOD: Inspection
ee1f0828-1fd7-5083-8c18-4641f2b83890 | note | CONFORMANCE RECORD: ITP
acdec092-a7d7-529b-a808-a8a35fad8f8e | note | HP
1bd41eb8-8037-5fae-a1aa-11e0e4499ae6 | note | RESPONSIBILITY: Client
f9a4aee8-2bb0-5de0-a564-f3ac4b7b4560 | date | Date Completed:
c1b59637-7ad9-4494-a9ac-6a1b3ed7c6ff | signoff | AUTHORITY HOLDPOINT
f5685ce4-5701-4a74-9325-ed18a04580cf | checkpoint | 1.8 - Landowner Agreement with property owner
76dc988a-17d6-58b5-b5d9-1f73ddce1cc2 | note | FREQUENCY: Prior to breaking ground
3c571266-c38a-54be-97e6-8d1986e3861d | note | ACCEPTANCE CRITERIA: Letter to be signed
3a8d3b66-c4d0-50ec-923f-46ee72d98b88 | note | REFERENCE DOCUMENTS: Signed landowner agreement
312ade4e-2e58-5685-a81e-963d3a9c6572 | note | INSPECTION/TEST METHOD: Hold point
1fe4069b-edf7-5310-ae1a-b37c40ea94e1 | note | CONFORMANCE RECORD: ITP
2312b8a9-c5fe-559b-a472-e19b664f12fc | note | HP*
fb3f5b9c-1a45-5c3f-a593-d1b3b179a5c8 | note | RESPONSIBILITY: Fulton Hogan
ae0d9a35-f358-55a3-9bd2-d04136181bc4 | date | Date Completed:
4b4fda3d-0361-41c6-9aff-bcb25296e5f6 | checkpoint | 1.9 - Environmental controls
3408cb5f-cd00-5357-a975-b9296691913a | note | FREQUENCY: Prior to commencement
bfe2f238-ece3-5ddf-a060-6296ee64c74f | note | ACCEPTANCE CRITERIA: Environmental controls installed and maintained as per EMP
b0738b62-991f-56ba-a4be-3c6e8208e727 | note | REFERENCE DOCUMENTS: EMP
23acd49c-2366-5b78-8e6e-fb200707dd22 | note | INSPECTION/TEST METHOD: Inspection
4fe9b664-a444-50cc-9f3a-45cdf803c30a | note | CONFORMANCE RECORD: ITP
ed1ad6ee-e713-5cf4-88e6-113c6b4bdbcc | note | HP*
57e1cbbe-d3ae-5978-9ae4-aa2a6a57889d | note | RESPONSIBILITY: Fulton Hogan
3e59d740-9279-5c2a-ab6a-d3b167723df3 | date | Date Completed:
dc8d5d43-31cd-439e-8dc8-adbc4e8dee81 | section | 2 - Site Access / Rock Fill / Wingwall Repairs
3fe307de-47f0-4cc0-85d1-f6f605300dc7 | checkpoint | 2.1 - Control of water through site
22a732b6-8004-5728-8850-829d6473d3de | note | FREQUENCY: Prior to excavation of toe
cc5ceccc-7d94-54bb-8c5b-18aafc1e84d5 | note | ACCEPTANCE CRITERIA: Dewatering and earth bund to be confirmed on site
371bc85b-511b-5536-8f7a-ed14559f9c3a | note | REFERENCE DOCUMENTS: Environmental Management plan
2f58e12c-16b6-5721-89d0-06d46c3ab29a | note | INSPECTION/TEST METHOD: Site inspection
d6939bff-57a3-5109-b683-a5bb23bcc60f | note | CONFORMANCE RECORD: ITP
8c7d01bd-34e2-5ec7-aced-e756583cf82e | note | IP
c2023ac1-3eee-5f9b-8470-429d4940025b | note | RESPONSIBILITY: Client and Fulton Hogan
187a8938-b4d9-58e5-952f-7f10e4994e53 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
dc8a564e-6985-4f0d-bc04-4b91f4e37746 | checkpoint | 2.2 - Tree removal
b220dd35-f225-578f-8539-e2a66c3a2bd7 | note | FREQUENCY: Prior to commencement
4f005b0d-86a3-55bc-b462-83ab2e09416d | note | ACCEPTANCE CRITERIA: Trees for removal marked out and approved for removal
10eeb016-697b-5e8d-b15f-350651ba3e7e | note | REFERENCE DOCUMENTS: Environmental Management plan, DEECA permit
fa2cceab-eb7d-5d18-bb96-7fc71a86978f | note | INSPECTION/TEST METHOD: Site Inspection Permit
4756e140-5109-5fb5-aaaa-a277a6b3e06f | note | CONFORMANCE RECORD: ITP Permit
0c93464c-2a60-583c-b12d-b194c826ba38 | note | HP
522088ec-4e0c-5770-a33c-f882b66a5574 | note | RESPONSIBILITY: Client and Fulton Hogan
cf426b20-4f34-5154-84dd-2bf6db161ace | date | Date Completed:
0f86e23d-12dd-4164-8056-597f0bfdc33e | signoff | AUTHORITY HOLDPOINT
66db1a0f-4300-49f2-a8a2-d225af9a15ee | checkpoint | 2.3 - Site Benching/ access track
ca4f56d4-6736-5303-a908-0c320991f490 | note | FREQUENCY: Prior to commencement
a8f17b97-5129-5439-baa3-34a3a11f579d | note | ACCEPTANCE CRITERIA: Adequate benching and site access track constructed
7497f064-fe61-5a47-81c7-a3622b6c8f3e | note | REFERENCE DOCUMENTS: Scope document
52b7d868-db04-52b2-8da9-c9c5f376cd70 | note | INSPECTION/TEST METHOD: Inspection
5d620460-201c-5bad-9c7d-22b4ca08ade5 | note | CONFORMANCE RECORD: ITP
e51f381e-898d-5db0-be7a-58d1ac3bb153 | note | IP
4e86d240-2d7b-5d4f-8c86-6b96bc4933bd | note | RESPONSIBILITY: Fulton Hogan
3c4be706-9eba-5c74-9280-00f6c095c7a4 | date | Date Completed:
1786c8c2-9b3e-4d00-8c2d-d775c2238457 | checkpoint | 2.4 - Fill Material
09e9f7b4-a01b-51b1-a44b-6bf905de7b5a | note | FREQUENCY: Prior to placement
4d709c2a-3454-5cee-846e-653c68c19c64 | note | ACCEPTANCE CRITERIA: Suitable Type A Fill material used for placement behind upstream wingwall
ddd07a7f-fda6-5d43-b857-cfd2f83df254 | note | REFERENCE DOCUMENTS: Scope document Drawing
72661d1a-ee5d-5d2a-8853-16760cb49504 | note | INSPECTION/TEST METHOD: Inspection
3fabbae5-825d-5f85-8f4a-9bfb14e5ab02 | note | CONFORMANCE RECORD: ITP
ea2bfde5-768b-5d88-a7cd-72756312743d | note | WP
59c90a93-627b-5857-8f0f-19b35c5fabc5 | note | RESPONSIBILITY: Fulton Hogan/Client
75397d65-b63a-5cc5-b93d-34571d3f4547 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
4c34d7a5-51e0-4a84-9a2b-3fad41a1957a | checkpoint | 2.5 - Geofabric
e5a9f997-cdc8-5c79-ace9-231bdfe41200 | note | FREQUENCY: Prior to wingwall form and rock placement
a31e81d2-d192-5817-96b3-05463f78784f | note | ACCEPTANCE CRITERIA: Geotextile layer placed under rock beaching and behind wingwall
6a11e3e1-8628-5670-8828-debd2cc2b611 | note | REFERENCE DOCUMENTS: Drawing
6003b5dd-a924-53aa-bc61-568eaa7d3171 | note | INSPECTION/TEST METHOD: Inspection
536571fb-d06c-5b63-b12d-1934fcb1f77f | note | CONFORMANCE RECORD: ITP
139bfdcd-11f2-5a19-af3f-54b6efd84ecf | note | IP
79d8a9b3-7356-5c4b-8326-b86d285e4ff9 | note | RESPONSIBILITY: Fulton Hogan
3b87ded8-d0ca-550c-9c07-21e3124f65dd | date | Date Completed:
123c5750-9021-4ef9-aeb2-3217bc3378c9 | checkpoint | 2.6 - Toe Rock Placement (downstream)
ef80ed61-5dad-5756-a57c-1234db8d9a53 | note | FREQUENCY: During the placement of the toe rock
65e31746-f0d1-520a-bfd1-263ea26b2f7d | note | ACCEPTANCE CRITERIA: Solid base, Maximum particle sizes 750-1000mm
34f7119e-b208-57e7-8a07-f313472dff12 | note | REFERENCE DOCUMENTS: N/A
a7e7802d-c09d-5dbb-b8b7-21f05cd46aa6 | note | INSPECTION/TEST METHOD: Inspection
b738b76d-018d-5930-8674-2b04795fe788 | note | CONFORMANCE RECORD: ITP
9d0e1727-3427-5940-a396-61dc7f70bf92 | note | IP
98b9da54-ee7b-54a3-b218-f01a77f88317 | note | RESPONSIBILITY: Client/ Fulton Hogan
7b616f31-d2d5-52d4-9503-a010b370acbd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
9649a14b-f864-46ad-9716-496530e0c81e | checkpoint | 2.7 - Flowable grout
e1deaa71-a772-5b2c-8b4c-b1de6fb010a5 | note | FREQUENCY: During construction
ea2168d9-3149-5437-9cc9-31f4971178b7 | note | ACCEPTANCE CRITERIA: Flowable grout adequately placed to fill void under downstream wingwall
5815cd49-a60f-5495-9b20-e9c2cc9f4d22 | note | REFERENCE DOCUMENTS: Drawing
76ee8585-27a5-5153-936a-9e86855122e6 | note | INSPECTION/TEST METHOD: Inspection
c247c4c3-5fc3-5a17-9a8e-687efb767177 | note | CONFORMANCE RECORD: ITP
d7fbff92-6ef2-50a7-bdd8-207b79225325 | note | HP
261e77dd-4725-55a0-a5d9-dad16b6b0a63 | note | RESPONSIBILITY: Client
b0300632-24d8-50c4-ae1b-07d80f7b65a7 | date | Date Completed:
e204b073-f4c9-4474-a594-fa66fce1fc59 | signoff | AUTHORITY HOLDPOINT
3e8186c8-e503-4e50-9c34-9b5bd1b5ca22 | checkpoint | 2.8 - Demobilisation
31ca16d2-abe1-58ff-93e7-963ab53d53e5 | note | FREQUENCY: At the completion of works
ccdf9231-4030-5f45-a2e8-8ec6f791b257 | note | ACCEPTANCE CRITERIA: Stockpiles and temporary works are removed.
f263b8f8-0189-5650-95ef-ea4e870c8284 | note | ○ Minor defects are agreed with client
09c9d659-7312-5346-a3d8-0f9ef27613b3 | note | REFERENCE DOCUMENTS: NA
6c2a902a-955f-5f7e-ba48-794f04bc129d | note | INSPECTION/TEST METHOD: Inspection
ce2cee31-45a0-5fe5-860b-a92bcdfa4963 | note | CONFORMANCE RECORD: ITP
1ba09c54-53fc-515d-8ea1-75abcef6b8d9 | note | HP
16500acf-6bf4-591d-9619-3de49b6b959d | note | RESPONSIBILITY: Client
1274209d-8441-57bf-b51d-f27d3de4d89c | date | Date Completed:
fa2ddeac-5a4e-4963-b46d-f5971794cde9 | signoff | AUTHORITY HOLDPOINT
2e38cba5-3b11-4e26-b65f-71267becce09 | checkpoint | Final Inspection
7cb09cc9-5b1c-5482-88b7-39c5eaaa1b58 | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
4311ad4e-2c61-5654-bc8c-59f942490957 | textbox | Print Name:
4e1f2671-43dc-5586-9796-9d3069c606e4 | textbox | Position:
c66ee8ff-cbc2-57dc-b9cd-75dd1bf30e0d | date | Date: