## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
0b5d38d5-d9bf-4ad6-ba97-f036b79846f5 | checklist | Add As Built drawing (ITC - 31) |  | AS BUILT DRAWING
8414708d-1ff4-4227-82fb-d4337a99722e | section | Testing and Commissioning
c05b2b25-7d97-481e-9b73-7d95b63541f7 | checkpoint-no-value | AS BUILT DRAWING:
b0ecea6e-95e5-5fa8-887c-f77e2b2f820f | textbox | AS BUILT DRAWINGS NO:
70c55206-6c52-5023-be95-3ceab23230cd | textbox | DRAWING TITLE
349697d5-02d6-576f-9346-0502ea09b6d2 | textbox | FINAL REVISION AND DATE
569fb4ea-e334-542b-9e55-95be1c529ddc | textbox | NAME
1db2b88c-6018-5dd4-bbd2-4ccaafe45d03 | textbox | COMPANY/DEPARTMENT
61db3303-6c97-4754-b643-8faf710ff762 | checkpoint | MANUALS (DRAFT) ACCEPTANCE
c4f92946-e7e8-4bf2-a792-fa6cbbf80062 | checkpoint | MANUALS AND DRAWINGS SUBMITTED
77705003-ec91-464a-a689-ad7fc871c66d | checklist | Add Testing and Commissioning item (ITC - 30) |  | ITEM
911cfe6d-1455-4452-9776-ad7502a91677 | section | Testing and Commissioning
f30bc3be-e931-47ce-9f65-b0f1c25c9b15 | checkpoint-no-value | ITEM:
837ef965-a7f6-5cbc-b489-117e46fd3d36 | textbox | DESCRIPTION
0ccaad96-b206-5535-895a-2672c7fa8856 | date | DATE OF TESTS
a001f101-7ad0-55fc-a483-6ec7d4c4ac3b | note | INSPECTION/WITNESS BY:
13d8ff29-5539-5120-9a15-3de664d65d1b | textbox | NAME
d8d58a7a-9e1e-522e-9f16-0e8cce6ac006 | textbox | COMPANY/DEPARTMENT
46294ef3-93b4-4a68-a462-08386ffddb50 | checkpoint | ACCEPTANCE
abadc903-b96c-43c2-bd05-7bd68968dc2a | signoff | CONFIRMATION
c69f940f-4d13-4e07-9d24-5da7e8b7d301 | checklist | ITC - (001) Drawing Register (For Construction) |  | DRAWING # / TITLE
4ef31683-1f89-45b8-bc97-25a74d5e5e33 | section | Drawing Register (For Construction)
c428085d-fb91-4c7a-9cb4-5e61bd391f35 | checkpoint-no-value | DRAWING:
62ef8beb-d8b6-5764-ab8a-db875661c5f0 | note | ALL PRODUCTIVE DRAWINGS MUST BE REGISTERED AND STAMPED IN RED TO INDICATE PHYSICAL CHECK AND PROCESS TO QA REQUIREMENTS.
1e11cf3a-0e91-53ac-adc5-b1ca1900a63b | date | Date:
fff54d53-c759-58ae-b97f-d01f7c7ee811 | textbox | DRAWING No.
542be0ec-5049-52de-95c7-5e78714e39f0 | textbox | DRAWING TITLE
1e1f7cef-9166-559e-861b-313757a843bb | textbox | REVISION / ISSUE
a4be0185-ce7f-4f10-b790-119c1b5c1490 | checkpoint-no-value | DISTRIBUTION:
03ad3df9-66d8-5070-94af-5166422a79a6 | textbox | SITE OFFICE
fe24a2bc-23ec-5130-88ad-7911615d267c | textbox | SITE
c69f9891-b978-44bf-b1f5-a01550da2b1f | checklist | ITC - (002) Main and Distribution Panels |  | BOARD TYPE / NUMBER / AREA
c9a7f111-28cc-4700-a1d2-fc1ed96cd5a2 | section | Main and Distribution Panels
d7cde8e3-613c-401a-9da8-1d3dd74cdf7e | checkpoint | ACCEPTANCE CRITERIA
ca6f5d7c-7f15-4b05-9ffc-c6c745a2237b | checkpoint | MFG QA
5c6a0e6e-82c7-4cf8-b2e1-4c4ebe295436 | checkpoint | DAMAGE
968fa547-dac9-42d7-a120-9395cdfee391 | checkpoint | LOCATION TO DRAWING
8c43c550-aa3c-4db0-a1f8-2a99d7385a93 | checkpoint | EQUIPMENT TO DRAWING
6ba534e1-584f-4b0c-90a7-96d829799226 | checkpoint | CONNECTIONS INCOMING & OUTGOING BY HEYDAY.
fb34b65a-0d93-4cf7-a697-86067b72fc79 | checkpoint | NEUTRAL CONNECTIONS CORRESPOND
f3a6e84a-254c-44bd-a623-ae5d040c11db | checkpoint | CORRECT EARTHING AND SOLIDLY FIXED
dffa06ac-e11c-44b2-89eb-a99a5b9c0e4a | checkpoint | POLE FILLERS INSTALLED
839c5de1-bf7a-4de0-80c9-13c832787b86 | checkpoint | ALL CABLE ENTRIES WITH ESCUTCHEON PLATES AND SEALS FITTED
609ded83-f7b6-41a0-b6ec-0d3039e5630f | checkpoint | BOARD SEALED AND LOCKED FOR SAFETY INC: FRONT AND REAR PANELS
5c2f6d38-09ef-40e6-a0a4-6213677f01cc | checkpoint | LABELS AND SCHEDULE LIST CORRECT AND INSTALLED
0b12790d-2aab-45df-91e4-d5237920578e | checklist | ITC - (003) Main and Submain |  | LEVEL / AREA / FED FROM / TO DB #
5e5504fa-7edc-4fa0-9c17-6945d4b49a5c | section | Main and Submain
44a7d532-a81a-4b32-84ca-96e75f5be18d | checkpoint | COMPLIES TO SPEC AND LATEST DRG
72a29986-ff15-40ff-a609-443c53448a6e | checkpoint | SIZE CORRECT
cdb2d0f1-9320-41c7-a422-04959de4b7a4 | checkpoint | INSTALLED CORRECT
aa12c03d-ea52-4d9e-a4b0-93a81736595e | checkpoint | TERMINATED
9c43245a-8f5d-4f8a-8bc5-680ecc2526ef | checkpoint | TESTED AS PER NOEW FORM
fd756bcd-b228-4303-96ba-4c574ecbd34c | checkpoint | NOEW SUBMITTED TO COUNCIL
edb625bb-9a63-4015-9e97-56d21eeb9dbe | checkpoint-no-value | REMARKS
44dbe8d5-d494-5ccf-9914-af11dcf523d2 | textbox | Remarks:
79a25df3-8f85-4896-9042-41db952aecf8 | checklist | ITC - (004) Cable Tray-Ladder |  | LEVEL / AREA
8444a188-fe8a-4ad5-a6bf-9b2f0e531df2 | section | Cable Tray-Ladder
6adaf83b-0f18-4d00-a6bb-ac8298381e45 | checkpoint | AREA/LOCATION TO DRAWING
40068001-b539-4d7f-a4b4-15205830c01f | checkpoint | CORRECT SIZE, TYPE & SPARE CAPACITY
00d50479-9236-4abd-983c-8a37687f7039 | checkpoint | GALVANISED / PAINTED
4edc9d56-71dd-491c-8cd6-bd6ac3e69500 | checkpoint | CORRECT SPACING
8d4fb606-3fc2-4d0d-9a81-2be31ba07bd9 | checkpoint | CORRECT ALIGNMENT
6e53fbfe-d566-4888-881e-1e6e8e63fb25 | checkpoint | CORRECT BRACKETS AND SAFE FIXING
9b2e4113-2d4a-4836-85af-dcb38dbca211 | checkpoint | CLEAR TO OTHER SERVICES
ccc25a66-482f-4d52-8573-cf22a4afebce | checkpoint-no-value | REMARKS
4d75bf73-6f66-5aa9-b4a6-1cb0f99f1dec | textbox | Remarks:
73d8f2e1-5e24-469f-a500-9c738f392843 | checklist | ITC - (005) - In-ground Conduit Installation (UPDATED) |  | Pour #
ae5b7970-7d5c-4c36-8106-9e7e376510de | section | Inground Conduit Installation
33779d1b-92dd-4b1f-bc59-a355571acbce | checkpoint | Correct location to drawing
1c5fb067-0030-5721-981b-c60c70cd79db | textbox | Drawing Number:
9dac69c0-a5f8-50c1-acd1-d61f7c85f7e8 | textbox | Revision:
02d87056-df72-4496-a9d9-df76a4722c57 | checkpoint | Correct size and type
86e26973-27fa-5060-8625-2e77c7492e25 | textbox | Conduit size & type required:
ff97890b-892e-5765-b5d8-3fbe9e04cc70 | textbox | Conduit size & type installed:
843a6385-61c4-47b2-bd0b-6ddad25999eb | checkpoint | Correct spacing in slabs
a58a39ac-a9bd-508a-ae06-a7f12a6cccc6 | textbox | Spacing required:
4ebabab6-ac8e-5b2f-ab9a-4414ceb760f6 | textbox | Spacing measured:
825588ce-5e35-4e42-adb3-9f36340075f9 | checkpoint | Correct alignment
91a50086-3977-4ff0-8ebc-d429e805c502 | checkpoint | Clear to other services
7f8a6d6f-c349-4255-9778-f139def2a2ad | checkpoint | Correct depth underground
59e0b636-9323-583e-a3f3-31d65f7e25c5 | textbox | Depth required:
04712e61-6ba7-5f89-bd4a-00aebb7f7213 | textbox | Depth measured:
b00bb701-41fd-43e0-aafb-35943f5266c0 | checkpoint | Correctly marked (tape or other)
934ce5fb-ba80-5f79-bd85-e76b8170b428 | textbox | Tape/cover used:
78f7e172-0850-51ac-8295-062eaccc324d | tickbox | Photo of marking tape/cover used
b720b61d-fa92-4525-b9a2-da7aff36347f | checkpoint | Correct fixing and safe
5941bc1e-5ce6-544b-889f-eae33f714167 | textbox | Fixing used:
ba5840fb-2c82-5a6d-b838-4719f440ad8f | tickbox | Photo of fixing used
461b1231-5d54-4e12-a677-0036b0248632 | signoff | HOLD POINT - SIGN OFF BY WATPAC & HEYDAY
9816de6c-887b-46bc-b0ee-aaee0c7b7496 | section | Trench Backfill
bd48bea3-dce7-429c-8261-2e870d4dffdf | checkpoint | Correct backfill and surfaces
64d614a1-3951-528a-a8c3-2d5a9090d66f | textbox | Backfill used:
70ba6766-b3c7-58f2-9eab-5e9e8b467b00 | tickbox | Photo of backfill
ca7ef0a8-37c0-4c9a-a31d-41975816ca96 | checkpoint | Sufficient photo evidence uploaded
51893cce-12e6-5adf-abb2-33bee503c1c3 | note | Attach Photos:
ae329d77-ba6b-5afc-8e59-e8d2cad78eab | tickbox | Before install
9aa440ff-5e8c-59b4-b7bc-e7066548fd8b | tickbox | During install
5e822094-f3dd-5b9b-86f1-c189ac128069 | tickbox | Pre backfill
3c5c7821-4d7e-5ea0-94cb-c9aa47638b8f | tickbox | Finish
5a174fae-ea93-45ef-b3d2-19fa6233a452 | signoff | Heyday sign off
616316bf-b729-4897-8f15-3f5e0280346e | checklist | ITC - (005) - Slab Core |  | LEVEL / AREA
78131dd3-6d6f-415b-8ceb-0fd76c80ce8e | section | Inground Conduit Installation
6ac688e7-27d1-49f9-bfc7-46a45f8d528a | checkpoint | CORRECT LOCATION TO DRAWING
da0e19c2-9f2b-430f-9dcc-f09b2eaa1701 | checkpoint | CORRECT SIZE AND TYPE
4ee65c5a-91d8-423a-93cf-75f282b4fd75 | checkpoint | CORRECT SPACING IN SLAB
4c0df84b-f747-48ca-9f9b-7752dea09126 | checkpoint | CORRECT ALIGNMENT
bc4ee864-eb8a-4634-8800-4b2d5e4b0be6 | checkpoint | CLEAR TO OTHER SERVICES
b50898d6-17f3-4544-b0cd-4a83e98359b2 | checkpoint | CORRECT FIXING AND SAFE
34d3f90d-f076-4146-a0f4-53d68bd6b372 | checkpoint-no-value | REMARKS
db757bda-a8d9-5a8e-81ae-75eec79f8477 | textbox | Remarks:
f569e034-e1ae-4f10-a0ee-8ac846af88cd | checklist | ITC - (006) Lighting Circuits |  | LEVEL / AREA / D.B. # / CCT # / CB #
2caaaea3-4a2b-4674-bc5b-842d3a902d35 | section | Lighting Circuits
b3073d49-9b79-4970-af5f-321acbfcb1ba | checkpoint | CONDUIT
f9a7dd60-47ff-45e2-82f8-98c23a4999ef | checkpoint | ROUGH IN
0377184c-68f3-4464-a06a-c4aa03e7df11 | checkpoint | FIT OFF
88694c90-1592-4c7a-bfbf-7bce72723102 | checkpoint | TESTED
53cf20e5-85d9-4167-b7d9-7fa35158057d | checkpoint | NOEW SUBMITTED TO COUNCIL
120005c4-075b-4999-8458-733773718e4d | checkpoint-no-value | REMARKS
fbb44502-0ca4-5467-970b-b86d2002f2c5 | textbox | Remarks:
8cf309be-70e8-4e81-b1bd-f6bbcdb1fe79 | checklist | ITC - (007) Power Circuits |  | LEVEL / AREA / D.B. # / CCT # / CB #
27a2166e-e121-4277-b519-26e357fd17df | section | Power Circuits
4da845f7-2a46-4ba1-9d8d-a1cb8f30ea49 | checkpoint | CONDUIT
3a4fcf74-4aae-4546-ac2b-629a7949fb12 | checkpoint | ROUGH IN
afbba306-a33d-4eb4-83f6-035ada8ce07c | checkpoint | FIT OFF
9c82ce8c-bd1b-48d4-b066-7f9a7a770124 | checkpoint | TESTED
43730b1d-c628-433b-9474-cbf88cf0abd8 | checkpoint | NOEW SUBMITTED TO COUNCIL
c94be465-1b1e-4fb4-a38f-8adfbbe2d4ed | checkpoint-no-value | REMARKS
db12eb80-8acd-5c49-99fc-629fad935177 | textbox | Remarks:
1d90baaf-0535-4bd7-83b7-b2af3727b2e8 | checklist | ITC - (008) Electrical Equipment-Accessories |  | ITEM #
07082710-3c29-4a24-848b-f3291aa7ad50 | section | Electrical Equipment-Accessories
07c8e970-8edc-4883-8e2d-de741fec6835 | checkpoint | CORRECT TYPE / COLOUR
057327af-6ceb-427d-b507-b94c159d5fd6 | checkpoint | CORRECT ALIGNMENT LOCATION
5d944f4a-e1d5-40c1-bb58-edd4526f8166 | checkpoint | CORRECT FIXING AND MADE SAFE
f6f0647b-c0a0-4313-a2dc-51c2212fb4b0 | checkpoint | CORRECT LABELLING
e35618dc-16be-4ad1-8aec-cc6020d67baf | checkpoint | CORRECT TERMINATION
6917cdd5-7f1b-4ff0-bb35-9db27ece20c7 | checkpoint | CORRECT EARTHING
e6799c7f-6de0-465f-9ce1-39357b950585 | checkpoint | CORRECT IP RATING
54ad5916-3224-43b4-900e-0bdf0b1811e0 | checkpoint | CORRECT CLASSIFICATION
e8267a60-40f2-4d92-b8a4-57cc3d9c5843 | checkpoint | FINAL CHECK AND NO DAMAGE
ca316143-f2e1-41db-a463-1c2412654ef8 | checklist | ITC - (009) Main Earthing System |  | CABLE ID / FROM / TO
b062f8e4-a840-4020-9729-36c5ecf1fe03 | section | Main Earthing System
efb5bdc1-4e14-490b-aad8-1b21fae264d8 | checkpoint | PRE-REQUISITE WORKS
1b622548-4852-4c6b-a20b-487919135e8e | checkpoint | VISUAL CHECK
dab8fb20-0358-4584-ad35-c44c610ec31a | checkpoint | CONTINUITY TEST
865cfc4d-7973-4c81-8cef-996546d8c200 | checkpoint | ELECTRICAL RESISTANCE TEST
2a37a125-7cc6-55ca-be58-c858057147a9 | textbox | RESISTANCE (OHM)
f28a0826-d17c-5431-a644-c6b5d2b964b3 | textbox | TARGET RESISTANCE (OHM)
85d039e9-074b-44eb-bf25-ce46ef0431a4 | checklist | ITC - (010) Cardiac Earthing |  | DESCRIPTION
28b56133-bda1-41fb-919c-93b8e5a392d7 | section | Cardiac Earthing
2ce9633d-49e8-43bd-b77d-f4d400c8b50a | checkpoint-no-value | CABLE DETAILS
2f20f237-7211-54fc-baa2-fc0300aec57a | textbox | FROM:
c89ecc2d-287d-5906-bd12-62e4dd770bc8 | textbox | TO:
7733ffd9-08bf-4e50-872d-0589aad8d066 | checkpoint | CABLE SIZE INSTALLED AS PER AS/NZS 3003:2018 TABLE D1
bdaeb716-13bf-4786-9d37-3ac9bd1be397 | checkpoint | ROUGH IN – HIGH / LOW LEVEL
a0e4f4ec-d26f-44dc-9d8b-cf2e5af6217c | checkpoint | FIT OFF
deb636ca-dfa6-4dfb-a6d0-c3fa1dcb012d | checkpoint | POINT TO POINT TEST
08638ecf-ed82-4a1f-bfe3-98763fe9c3b2 | checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
baddf121-d2d1-4b33-bedb-34400376f4ba | checkpoint-no-value | REMARKS
18e939ae-6adc-5405-9a4e-7051a41b1431 | textbox | Remarks:
f203414b-4097-4209-92b6-ad7bb063904a | checklist | ITC - (030) Testing and Commissioning |  | Testing and Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8ea30fc4-b21e-4fe8-9e95-d1fad8a49f58 | checkpoint-no-value | REMARKS
d0c52289-9db8-5568-834c-b3455f8d8a9b | textbox | Remarks:
389e407e-72ef-45db-8f79-29cd27fe2606 | section-nested-checklists | EQUIPMENT / SYSTEM TO BE COMMISSIONED
295d57d1-6592-4c07-a93f-f2fab69bc1ed | checklist | ITC - (031) As Built Drawings-Maintenance Manuals |  | As Built Drawings-Maintenance Manuals
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
5670ea89-9c98-45ae-9219-2d088f77f2d2 | checkpoint-no-value | REMARKS
141d3c7f-e9c0-57d3-b975-cd4969468da8 | textbox | Remarks:
3516617a-08ed-4532-9206-92efd82cfa55 | section-nested-checklists | AS BUILT DRAWINGS
4ea97326-2aa4-4079-b46a-3c7c4dd5a1c7 | checklist | ITC - (XXX) - Suspended Slab Pours |  | Pour #
d1272611-67e2-4578-8aa1-903b3a5e3d28 | section | Inground Conduit Installation
6ed4e9f3-4ceb-4aa5-8fdd-e4ea58ffba10 | checkpoint | Correct location to drawing
482fdbfa-f624-5128-b876-7f3d03441349 | textbox | Drawing Number:
9e28ed98-895b-58a3-bffb-05d2bafed888 | textbox | Revision:
4b53b8e7-229d-4f73-9c70-8c9a6f92591f | checkpoint | Correct size and type
a0ab9b20-7c52-5bf0-9092-9976f6612a86 | textbox | Conduit size & type required:
7db618dc-2725-5434-91d2-744cbaa1e02b | textbox | Conduit size & type installed:
740268fa-7e79-4c21-a9c9-38617b889e4d | checkpoint | Correct spacing in slabs
b83a6d98-b635-5c63-94b6-6fdff35a2ec0 | textbox | Spacing required:
07a77b33-f8c4-5362-99b8-b73f8493c0fb | textbox | Spacing measured:
ac13dfa1-eeac-462c-9c44-327431cbd8f8 | checkpoint | Correct alignment
bb4a209c-bf79-4577-866e-28c7518f9612 | checkpoint | Clear to other services
f8d4b03d-8cb8-4a5b-bf7b-3801ec401eaf | checkpoint | Correct depth underground
d594c71f-fb8b-5f58-bd8b-953ea424d644 | textbox | Depth required:
720b3107-151d-5d95-afac-1ef82d5107e5 | textbox | Depth measured:
b37d3c57-bd23-4792-9bb3-43b2793394b1 | checkpoint | Correctly marked (tape or other)
f3dd2d5a-0c97-5cb9-9a6e-5eba01799eaf | textbox | Tape/cover used:
91339be2-87e3-50e7-a588-de2f47cba63f | tickbox | Photo of marking tape/cover used
9fa5d947-4845-46d6-92f3-975f9a825cea | checkpoint | Correct fixing and safe
15ed3e0f-2042-5638-98d0-05aad88536f9 | textbox | Fixing used:
4a2137a5-8869-5545-9707-a1959fbc0ef9 | tickbox | Photo of fixing used
e92731c5-c8dc-40ec-9691-7208f0a7c9b5 | signoff | HOLD POINT - SIGN OFF BY WATPAC & HEYDAY
fd46c82a-dfa4-4118-9ccc-a9e50034fe01 | section | Trench Backfill
4a34287b-3ecb-4014-aa70-601886bd60c2 | checkpoint | Correct backfill and surfaces
26f06942-58d1-5f48-bd53-d06754701846 | textbox | Backfill used:
136acc3e-c974-5b6b-a570-7447f96ddddd | tickbox | Photo of backfill
f1e7778d-bec9-439c-ba87-4444f350ae12 | checkpoint | Sufficient photo evidence uploaded
b8bad109-e624-5105-9d3c-4f5672ed285c | note | Attach Photos:
2c506170-8af3-55f2-a197-56dfea6a518f | tickbox | Before install
5ecaaf4d-6805-5ffb-840b-128f82bea0f9 | tickbox | During install
4c71c439-a668-5a1e-b593-b6c2ce96de76 | tickbox | Pre backfill
91281ed9-1804-5748-aa15-92358f7a62be | tickbox | Finish
136d84dc-17bc-41cc-8ec2-539a4e3e732b | signoff | Heyday sign off