## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 - Establishment and Initial Set Out | itp
section | Establishment and Initial Set Out
checkpoint | 1 - Award of contract
label | ACTIVITY TASK - Award of contract
label | ACCEPTANCE CRITERIA - Letter of Award
label | FREQUENCY - Prior to Project Commencement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Letter of Award
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Management Plan
label | ACTIVITY TASK - Project Commencement
label | ACCEPTANCE CRITERIA - Submission to engineer to the contract
label | FREQUENCY - Pre-Construction Phase
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - SSSP, EMP, QCP, TMP, JSA
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 3 - Insurance
label | ACTIVITY TASK - Project Commencement
label | ACCEPTANCE CRITERIA - Current Certification
label | FREQUENCY - Pre-Construction Phase
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Current Certification
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4 - Bond
label | ACTIVITY TASK - Project Commencement
label | ACCEPTANCE CRITERIA - Current Certification
label | FREQUENCY - Prior to First Progress Claim
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Current Certification
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 5 - Programme of Works
label | ACTIVITY TASK - Project Commencement
label | ACCEPTANCE CRITERIA - Detailing weekly scheduled tasks, milestones and hold points
label | FREQUENCY - Pre-Construction Phase and Updated Prior to the Regular Progress Meetings
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Preferably in Gantt Chart Format
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 6 - Dilapidation Survey
label | ACTIVITY TASK - Project Commencement
label | ACCEPTANCE CRITERIA - Photos and description of scope of work prior to commencement of physical works.
label | FREQUENCY - Pre-Construction Phase
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Existing Condition Photos Report
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 7 - Notification to Residents
label | ACTIVITY TASK - Project Commencement, Notification
label | ACCEPTANCE CRITERIA - Letter to be distributed to affected residents
label | FREQUENCY - Prior to Commencement of Work.
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Letter to residents
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 8 - Information Sign Boards
label | ACTIVITY TASK - Project Commencement, Notification – Sign Boards to be supplied and installed
label | ACCEPTANCE CRITERIA - As per WDCEES
label | FREQUENCY - Pre-construction Phase
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 9 - Temporary Works Design
label | ACTIVITY TASK - Design and construction of any Temporary Works required,
label | ACCEPTANCE CRITERIA - As per WDC Condition of Contract Clause 5.1.3 pg. no. 71 (69)
label | FREQUENCY - Prior to any required Temporary Work
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Design calculation, Drawings, Specifications
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Initial Survey Setting out
label | ACTIVITY TASK - Setting out of all Contract Works including offset pegs (if required).
label | ACCEPTANCE CRITERIA - As per approved drawings and design model - WDC Condition of Contract section 15 pg. no. 114(111)
label | FREQUENCY - Prior to any contract works construction
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Registered Surveyor to undertake, as per engineer’s approval
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Notification of Hazard
label | ACTIVITY TASK - Notifying WorkSafe of all notifiable construction work
label | ACCEPTANCE CRITERIA - Notification to Work safe
label | FREQUENCY - Prior to commencement of work or hazardous work – 24 hours in advance
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Copy of Notification to work safe
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 11.1 - Notification of Hazard
label | ACTIVITY TASK - Working around overhead lines
label | ACCEPTANCE CRITERIA - Notify NorthPower Prior to works starting
label | FREQUENCY - Update close approach every month
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Close approach permits and Standover
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 11.2 - Notification of Hazard
label | ACTIVITY TASK - Working around GAS line
label | ACCEPTANCE CRITERIA - Notify First GAS
label | FREQUENCY - Update close approach as required
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Close approach permits and standover
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 12 - B4UDig
label | ACTIVITY TASK - Submit B4UDig Notification
label | ACCEPTANCE CRITERIA - B4UDig Submission confirmation – Mark out – Close Approach Permits
label | FREQUENCY - Prior to commencement of works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - B4UDig Plans and sequence numbers – Mark out – Close Approach Permits
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 13 - Environmental Controls
label | ACTIVITY TASK - Environmental Controls in Place
label | ACCEPTANCE CRITERIA - Environmental Controls in place as per EMP/CEMP
label | FREQUENCY - Prior to commencement of works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - CEMP, Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 14 - Temporary Works
label | ACTIVITY TASK - Set up of temporary work provisions such as: - Shoring Protection - Temporary Access provisions - Dewatering
label | ACCEPTANCE CRITERIA - Temporary work provisions in place as per relevant approved SWMS or JSA prior to commencement of works
label | FREQUENCY - As Required
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Relevant WMS, SWMS or JSEA
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 15 - Stockpile Location
label | ACTIVITY TASK - Agree Stockpile Locations with Engineer
label | ACCEPTANCE CRITERIA - Suitable stockpile locations reviewed and agreed with Engineer
label | FREQUENCY - Prior to Earthwork
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per Engineer’s acceptance
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Dewatering
label | ACTIVITY TASK - Controlling water in trenches or Pumping water from trench
label | ACCEPTANCE CRITERIA - Submit Method Statement, install temp pond, manage clean discharge, as per T- WES 00011 – Earthworks, Reinstatement and Dewatering
label | FREQUENCY - Prior to Earthworks
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Method Statement Acceptance
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - P
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP-002 - Stormwater | itp
section | Stormwater
checkpoint | 1 - Site Preparation
label | ACTIVITY TASK - Site Clearance
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Prior to trench excavation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per Engineer’s acceptance
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - W
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 1.1 - Concrete Pipes and Pre-cast Structures
label | ACTIVITY TASK - Delivery of Pipes and Pre-cast structures
label | ACCEPTANCE CRITERIA - Visual Inspection – as per WSP T-WES00012 Section 2.3 pg. no. 262
label | FREQUENCY - Upon delivery on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Delivery Dockets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 1.2 - Trench Fill Material
label | ACTIVITY TASK - Trench fill material
label | ACCEPTANCE CRITERIA - MDD using NZS 4402 Test 4.1.3
label | FREQUENCY - One Week prior importing trench fill material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Copy of lab test report
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Initial Set Out
label | ACTIVITY TASK - Setting out M/H locations and Trench Alignment
label | ACCEPTANCE CRITERIA - As per approved drawings and design model provided
label | FREQUENCY - Prior to trench excavations
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per Engineer’s acceptance
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Trench Excavation
label | ACTIVITY TASK - Trench Excavation
label | ACCEPTANCE CRITERIA - Visual Inspection – As per T-WES 00011 section 3.2.4 pg. no. 251
label | FREQUENCY - During and after excavation works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3.1 - Pipe General Bedding
label | ACTIVITY TASK - Place and Compact GAP20 Bedding or Approved, WDC EES Sheet 31
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - Prior to pipe laying
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - W
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3.1.1 - Steep Pipe – Concrete Bedding
label | ACTIVITY TASK - Cement Stabilised AP20 bedding where required as per drawing (generally for trenches with >5% slope)
label | ACCEPTANCE CRITERIA - Visual Inspection – 40kg Cement to 1000kg aggregate, thoroughly mixed and compacted – T- WES 00012 section 3.1.5
label | FREQUENCY - Prior to pipe laying
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3.2 - Pipe Laying
label | ACTIVITY TASK - Laying and Jointing of the pipes
label | ACCEPTANCE CRITERIA - Visual Inspection - Lay and joint pipes in accordance with the manufacturer’s recommendations and AS/NZS 3725. – T-WES 00012 Section 3.1.1
label | FREQUENCY - During and upon completion of laying
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet, As-Built information – Invert level, Gradient ±0.1%
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3.3 - Pipe Embedment (1)
label | ACTIVITY TASK - GAP65 or approved selected material compacted in 200mm layers
label | ACCEPTANCE CRITERIA - Clegg Hammer Test: 0- 300mm DEPTH RANGE CLEGG READING NOT LESS THAN 45.
label | ○ 300-1500mm DEPTH RANGE CLEGG READING IS NOT LESS THAN 30.
label | ○ 1500mm TO TOP OF PIPE BEDDING MATERIAL CLEGG READING IS NOT LESS THAN 25.
label | ○ WDC EES Sheet 31
label | FREQUENCY - Upon completion of each compacted layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Clegg Hammer Test Record Sheet – Engineer to review at least weekly
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Pipe Embedment (2)
label | ACTIVITY TASK - GAP65 or approved selected material compacted in 200mm layers
label | ACCEPTANCE CRITERIA - Nuclear Densometer or agree an alternative method with the Engineer where a Nuclear Densometer is not appropriate for the material type.
label | ○ Minimum MDD not specified. T-WES 00012 section 4.5
label | FREQUENCY - Carry out one test every two layers per 50 m linear pipeline
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Records - Engineer to review at least weekly
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Trench Fill
label | ACTIVITY TASK - Lay and compact in 200mm layers
label | ACCEPTANCE CRITERIA - Maximum dry density -
label | ○ ≥95% Road, paths and pavements
label | ○ ≥90% in Berm.
label | ○ Carry out compaction testing using a Nuclear Densometer or agree an alternative method with the Engineer where a NDM is not appropriate for the material type.
label | FREQUENCY - At least two layers of trench fill for every 50m of trench.
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Records - Engineer to review at least weekly
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Manhole and Catch-Pit Construction
label | ACTIVITY TASK - Pre-cast Manhole base
label | ACCEPTANCE CRITERIA - Visual Inspection - 75mm min. of Bedding material.
label | FREQUENCY - Prior installation of Manhole Base
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4.1 - Manhole installation
label | ACTIVITY TASK - Manhole risers and components
label | ACCEPTANCE CRITERIA - As per drawing DRAINAGE TYPICAL DETAILS SHEET 1
label | FREQUENCY - During and after installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4.2 - Manhole installation
label | ACTIVITY TASK - Catch-Pit back entry and surrounding
label | ACCEPTANCE CRITERIA - As per drawing DRAINAGE TYPICAL DETAILS SHEET 1
label | FREQUENCY - For each Cath-Pit
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5 - Downstream Defender
label | ACTIVITY TASK - Install and connect downstream defender
label | ACCEPTANCE CRITERIA - Typical Detail K – As per drawing DRAINAGE TYPICAL DETAILS SHEET 1
label | FREQUENCY - For each Downstream Defender
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Wingwall
label | ACTIVITY TASK - Wingwall installation
label | ACCEPTANCE CRITERIA - As per drawing DRAINAGE TYPICAL DETAILS SHEET 2
label | FREQUENCY - For each Wingwall installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 7 - Trapezoidal Swale
label | ACTIVITY TASK - Swale construction
label | ACCEPTANCE CRITERIA - As per Drawings and design model
label | FREQUENCY - Upon completion of the construction
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built surface information
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 8 - Subsoil Drain
label | ACTIVITY TASK - Trench Excavation
label | ACCEPTANCE CRITERIA - As per drawing no. 1- 14547.01 sheet no. C040
label | FREQUENCY - Prior to installation of subsoil drain
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - QF 007 Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 8.1 - Subsoil Drain
label | ACTIVITY TASK - Placing filter fabric around drainage aggregate
label | ACCEPTANCE CRITERIA - Enginneer’s approved filter fabric
label | FREQUENCY - Prior to placing drainage material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 8.2 - Subsoil Drain
label | ACTIVITY TASK - Install Subsoil drain
label | ACCEPTANCE CRITERIA - 100m slotted subsoil drain with filter sock or approved
label | FREQUENCY - Prior to backfilling
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet, As-built plans
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 8.3 - Subsoil Drain
label | ACTIVITY TASK - Backfilling
label | ACCEPTANCE CRITERIA - 20/7 drainage metal, Minimum 70mm below the drain
label | ○ Minimum 300mm cover to subgrade improvement layer
label | FREQUENCY - Prior to pavement construction
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 9 - Testing
label | ACTIVITY TASK - Flush pipeline
label | ACCEPTANCE CRITERIA - Flush any debris
label | FREQUENCY - Prior testing
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - CCTV inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 9.1 - Concrete pipes
label | ACTIVITY TASK - Leak Testing
label | ACCEPTANCE CRITERIA - Low-pressure air test, if a length fails use a hydrostatic test
label | FREQUENCY - Prior to final surfacing
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.2 - CCTV
label | ACTIVITY TASK - CCTV Inspection of completed pipeline
label | ACCEPTANCE CRITERIA - Free from – Displaced joints, Ovality, Dips, Reverse grades, Debris in pipeline, particularly construction debris
label | FREQUENCY - Prior to final surfacing and after leak test
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - CCTV footage
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 9.3 - Manhole Testing
label | ACTIVITY TASK - Water drop test
label | ACCEPTANCE CRITERIA - As per T-WES 00012 section 4.7
label | FREQUENCY - Prior to final surfacing
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - As Built & Final Design Documentation
label | ACTIVITY TASK - Supply As-built Plans
label | ACCEPTANCE CRITERIA - Engineer to review and accept as-built Drawings
label | FREQUENCY - For all completed works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Engineer’s acceptance of as-built drawings
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP-003 - Watermain | itp
section | Watermain
checkpoint | 1 - Site Preparation
label | ACTIVITY TASK - Site Clearance
label | ACCEPTANCE CRITERIA - Site clear of debris and vegetation
label | FREQUENCY - Prior to commencing watermain construction works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 2 - Pipe Delivery and Storage
label | ACTIVITY TASK - Delivery of Pipes and Fittings
label | ACCEPTANCE CRITERIA - Pipes and fittings free from damage, correct type and size
label | FREQUENCY - Upon being delivered on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Delivery Dockets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Pipe Delivery and Storage
label | ACTIVITY TASK - Storage of pipes and fittings
label | ACCEPTANCE CRITERIA - Pipes and fittings stored as per manufacturer’s recommendation
label | FREQUENCY - Upon being delivered on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3 - Excavation and Bedding
label | ACTIVITY TASK - Initial set out
label | ACCEPTANCE CRITERIA - Setout as per drawings and provided design model
label | FREQUENCY - Prior to excavation works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Excavation and Bedding
label | ACTIVITY TASK - Excavation
label | ACCEPTANCE CRITERIA - Excavation to correct depth and width, no damage to ex. Services
label | FREQUENCY - Prior to place bedding material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3.2 - Excavation and Bedding
label | ACTIVITY TASK - Place Pipe Bedding and Surround Material
label | ACCEPTANCE CRITERIA - Granular material for all pipe bedding and surround shall consist of uniformly sized particles between 5mm and 10mm and be composed of crushed blue metal or an approved alternative. – WDC Specification for the installation of watermains – Section 4.4 pg. n. 12
label | FREQUENCY - Prior to installation of pipe
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - Pipe Installation
label | ACTIVITY TASK - Pipe laying
label | ACCEPTANCE CRITERIA - Pipes laid to line and grade; joints correctly made
label | FREQUENCY - Upon completion of jointing the pipes
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4.1 - Pipe Installation
label | ACTIVITY TASK - Pipe Jointing – Butt Weld
label | ACCEPTANCE CRITERIA - Joints made as per manufacturer’s instructions; data logged - WDC Specification for the installation of watermains – Section 5.1.6
label | FREQUENCY - Each Joint
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Data Logg, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4.2 - Pipe Installation
label | ACTIVITY TASK - Pipe Jointing – Electrofusion Welding
label | ACCEPTANCE CRITERIA - Joints made as per manufacturer’s instructions; data logged -WDC Specification for the installation of watermains – Section 5.1.6
label | FREQUENCY - Each EF Joint
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Data Logg, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4.3 - Pipe Installation
label | ACTIVITY TASK - Flanged Joints
label | ACCEPTANCE CRITERIA - For jointing ductile iron fittings to PE80 pipe stub or slim flanges with nylon coated backing plate shall be used. – Stainless steel 316- bolts and washers.
label | ○ Torqued as per manufacturers instruction. - WDC Specification for the installation of watermains – Section 5.1.7 Denso
label | FREQUENCY - Each Flanged connection
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Fittings Installation
label | ACTIVITY TASK - Installation of Valves
label | ACCEPTANCE CRITERIA - Valves installed as per drawings and specifications
label | FREQUENCY - Each valve connection
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5.1 - Fittings Installation
label | ACTIVITY TASK - Installation of Hydrants
label | ACCEPTANCE CRITERIA - Hydrants installed as per drawings and specifications
label | FREQUENCY - Each Hydrant connection
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5.2 - Fittings Installation
label | ACTIVITY TASK - Installation of Air Valve and Scour Valve
label | ACCEPTANCE CRITERIA - Valves installed as per drawings and specifications
label | FREQUENCY - Each valve connection
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Testing
label | ACTIVITY TASK - Pressure Test – Main larger than DN63mm PE80 – Decay Test Method as per approved WMS
label | ACCEPTANCE CRITERIA - No Leaks, pressure maintained as per specification
label | FREQUENCY - Each Sections
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Data Logg, Test Record Sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6.1 - Testing
label | ACTIVITY TASK - Weld Testing
label | ACCEPTANCE CRITERIA - Tests to verify if the butt weld is ductile and stronger than the pipe itself will be conducted in accordance with ISO 13953:2001. For EF welds, the required destructive test is the peel decohesion test, which must be performed in accordance with ISO 13954:1997.
label | FREQUENCY - Random Samples – typically between 1% and 2% of the total welds
label | ○ WDC Specification for the installation of watermains – Section 5.1.8
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - ISO-accredited lab test report
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 8 - Anchor Blocks
label | ACTIVITY TASK - Construction of Anchor Blocks
label | ACCEPTANCE CRITERIA - Visual Inspection – Completed as per approved drawing sheet no. C033C & C033D
label | FREQUENCY - Each Anchor block as per drawings
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Prepour Inspection Checksheet, Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Backfilling
label | ACTIVITY TASK - Backfilling of the trench
label | ACCEPTANCE CRITERIA - Visual Inspection – Material as per specification, compacted in layers
label | FREQUENCY - Each layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Compaction test record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 10 - Disinfection
label | ACTIVITY TASK - Disinfection of the watermain
label | ACCEPTANCE CRITERIA - Visual Inspection – in accordance with WDC Water Services – Hygiene Code of practice
label | FREQUENCY - Prior to connection with live main – Upon completion of backfilling and testing each section
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Record Sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 11 - Water Main Commissioning
label | ACTIVITY TASK - Connection to live mains
label | ACCEPTANCE CRITERIA - New water mains must be connected to live mains within 10days of completing the disinfection process.
label | FREQUENCY - For each new water mains installed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Record Sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 12 - As Built & Final Design Documentation
label | ACTIVITY TASK - As-built Plans
label | ACCEPTANCE CRITERIA - Engineer to review and accept as- built Drawings
label | FREQUENCY - For all completed works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-Built Plans, Operation and Maintenance Manual
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP-004 - Roading and Pavements | itp
section | Roading and Pavements
checkpoint | 1 - Site Preparation (1)
label | ACTIVITY TASK - Site Clearance
label | ACCEPTANCE CRITERIA - Site clear of debris and vegetation
label | FREQUENCY - Once
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 1 - Site Preparation (2)
label | ACTIVITY TASK - Survey Set-Out
label | ACCEPTANCE CRITERIA - As per drawings and design model provided.
label | FREQUENCY - As required
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material (1)
label | ACTIVITY TASK - Geotextile and Geogrid
label | ACCEPTANCE CRITERIA - Engineer approved geotextile and geogrid
label | FREQUENCY - Prior to order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material (2)
label | ACTIVITY TASK - Granular subbase metal
label | ACCEPTANCE CRITERIA - Granular Subbase metal shall be AP65 complies with either TNZ M/03 or ES 2022 Section 3.3.2 Pavement Materials.
label | FREQUENCY - Prior to commencing works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material (3)
label | ACTIVITY TASK - Modified Basecourse metal
label | ACCEPTANCE CRITERIA - M4AP40 WITH 1.5 - 2.0%
label | ○ CEMENT subject to the confirmation of mix design
label | FREQUENCY - Prior to commencing works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material (4)
label | ACTIVITY TASK - Two coat Chipseal
label | ACCEPTANCE CRITERIA - First coat - Grade 2 chip followed with Grade 4 chip
label | ○ Second coat – in accordance with WDC ES 2022 Clause 3.3.5.4
label | ○ Second Coat Chip Seal and Resealing.
label | ○ Binder shall comply with TNZ M/1
label | FREQUENCY - Prior to commencing works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material (5)
label | ACTIVITY TASK - Dense Graded Asphalt
label | ACCEPTANCE CRITERIA - AC14 Asphalt Concrete mix design is subjected to approval from Engineer at least 5 working days prior to asphalt paving.
label | FREQUENCY - Prior to asphalt paving
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation according to NZTA M10:2020 Clause 3.6.1 or M27:2020
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material (6)
label | ACTIVITY TASK - Raised Platform Concrete
label | ACCEPTANCE CRITERIA - 40MPa concrete compressive strength at 28 days
label | FREQUENCY - Prior to ordering concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (7)
label | ACTIVITY TASK - Traffic Signs
label | ACCEPTANCE CRITERIA - Fabricated in Aluminium grade 5251-H34 or similar and shall be a minimum thickness of 2.5mm stiffened.
label | ○ As per WSP site specification - PROFESSIONAL SERVICES PAVEMENT AND SURFACING
label | ○ SPECIFICATION section 2.2 pg 4-6
label | FREQUENCY - Prior to ordering material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 3 - Pavement Construction (1)
label | ACTIVITY TASK - Trim and Prepare Subgrade
label | ACCEPTANCE CRITERIA - Visual Inspection, CBR 3.0%, SCALA testing as required by the engineer
label | ○ Level = +0mm – 20mm
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test record sheet, String record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pavement Construction (2)
label | ACTIVITY TASK - 200mm AP65 Sub- grade improvement layer
label | ACCEPTANCE CRITERIA - A layer of Geogrid and Geotextile placed at the base of the excavation.
label | ○ A 200mm thick layer of AP65 will then be carted to site and spread in required locations.
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - String record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pavement Construction (3)
label | ACTIVITY TASK - 250mm AP65 Sub-base course
label | ACCEPTANCE CRITERIA - Level = +10mm – 0mm
label | ○ NDM = mean value ≥ 95% of MDD with no single value less than 92%
label | ○ Proof Roll
label | FREQUENCY - No less than 24 hrs prior to placement of the subsequent pavement layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Lab test report – NDM String record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pavement Construction (4)
label | ACTIVITY TASK - 180mm M4AP40
label | ○ Basecourse stab with max. 2% cement.
label | ACCEPTANCE CRITERIA - Level = ± 5mm
label | ○ NDM = mean value ≥ 98% of MDD with no single value less than 95%
label | ○ Benkelman Beam = 15 m staggered by wheel path for each lane – As per WDC EES 2022
label | ○ Degree of Saturation (DOS) = less than 80%
label | ○ Proof Roll
label | FREQUENCY - No less than 24 hrs prior to placement of the subsequent pavement layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Lab test report – NDM, Beam, DOS, String record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Pre-seal inspection
label | ACTIVITY TASK - Prepare Basecourse for sealing
label | ACCEPTANCE CRITERIA - Swept basecourse to produce a tight mosaic surface and sweepings removed.
label | FREQUENCY - Prior to surfacing
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-seal Inspection checksheet, String record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Surfacing (1)
label | ACTIVITY TASK - Chipseal Surfacing Grade 2/4
label | ACCEPTANCE CRITERIA - Tie-ins to match ex. Surface.
label | ○ First coat grade 2 chip followed with grade 4.
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Construction photos, checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Surfacing (2)
label | ACTIVITY TASK - 50mm AC14 Asphalt Concrete
label | ACCEPTANCE CRITERIA - As per NZTA M10:2020
label | ○ No Water Ponding on finished surface
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Raised Safety Platform (1)
label | ACTIVITY TASK - Prepare subgrade
label | ACCEPTANCE CRITERIA - Visual Inspections 50mm thick AP20 layer
label | ○ 0.25mm polythene placed on top of ap20
label | FREQUENCY - Prior to placing formwork and reinforcement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Raised Safety Platform (2)
label | ACTIVITY TASK - Pre-Pour Inspection
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet, Concrete Dockets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Raised Safety Platform (3)
label | ACTIVITY TASK - Tactile Paving
label | ACCEPTANCE CRITERIA - Installed as per drawings and manufactures guide
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation, Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 7 - Concrete Footpath (1)
label | ACTIVITY TASK - 50mm Compacted GAP20 Basecourse
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 7 - Concrete Footpath (2)
label | ACTIVITY TASK - Pre-Pour Inspection
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | ○ 100mm 20MPa concrete
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet, Concrete Dockets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Vehicle Crossing (1)
label | ACTIVITY TASK - Trim to subgrade
label | ACCEPTANCE CRITERIA - Scala CBR = 10
label | FREQUENCY - Prior to placing basecourse
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Scala test record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 8 - Vehicle Crossing (2)
label | ACTIVITY TASK - 100mm compacted GAP40 Basecourse
label | ACCEPTANCE CRITERIA - Clegg test
label | ○ WDC Engineering Standards for residential vehicle crossing.
label | FREQUENCY - Prior to placing formwork and reinforcement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Clegg record checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 8 - Vehicle Crossing (3)
label | ACTIVITY TASK - Pre-pour inspection
label | ACCEPTANCE CRITERIA - 125mm thick 30 MPa concrete with 668 mesh placed centrally on basecourse
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet, Concrete Dockets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Pavement Marking and Delineation (1)
label | ACTIVITY TASK - Raised Reflective Pavement Markes, Hazard Markers
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation, Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 9 - Pavement Marking and Delineation (2)
label | ACTIVITY TASK - Road marking
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation, Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 10 - Traffic Signage
label | ACTIVITY TASK - Installation of Traffic signage
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation, Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 11 - Roadside Safety Barriers (1)
label | ACTIVITY TASK - Survey Setout
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Design set-out model, Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Roadside Safety Barriers (2)
label | ACTIVITY TASK - Install W-Beam Guardrail
label | ACCEPTANCE CRITERIA - As per drawings, site specification and manufacturer guide
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Design set-out model Visual Inspections, Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 11 - Roadside Safety Barriers (3)
label | ACTIVITY TASK - Install Precast concrete TL4 Barrier & Steel Handrail
label | ACCEPTANCE CRITERIA - As per drawings, site specification and manufacturer guide
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Design set-out model, Visual Inspections, Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 11 - Roadside Safety Barriers (4)
label | ACTIVITY TASK - Install Cyclist / Pedestrian Handrail
label | ACCEPTANCE CRITERIA - As per drawings, site specification and manufacturer guide
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Design set-out model, Visual Inspections, Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 12 - As-Built plans
label | ACTIVITY TASK - Final As-built Drawings
label | ACCEPTANCE CRITERIA - As reviewed and approved by the Engineer
label | FREQUENCY - At the completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-Built plan
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP-005 - Kerb and Channel | itp
section | Kerb and Channel
checkpoint | 1 - General (1)
label | ACTIVITY TASK - Concrete Strength
label | ACCEPTANCE CRITERIA - 30 MPa minimum at 28 days
label | FREQUENCY - For Each sections poured
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Supplier documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 1 - General (2)
label | ACTIVITY TASK - Kerb Profile
label | ACCEPTANCE CRITERIA - Standard Kerb and Channel & flush edge beam as per WDC EES 2021 Sheet 13
label | FREQUENCY - Prior to preparation works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - QF011 Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Set out
label | ACCEPTANCE CRITERIA - Horizontal: +/- 10mm
label | ○ Vertical: +/- 10mm
label | ○ No variance on a flat surface greater than 3mm on a 3m straight edge.
label | FREQUENCY - Prior to preparation works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - QF011 Checksheet No ponding of water
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Bedding
label | ACTIVITY TASK - Subbase
label | ACCEPTANCE CRITERIA - Clegg CIV
label | ○ Extend 300mm B.O.K.
label | FREQUENCY - Prior to concrete pour
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - > 25 recorded on Clegg sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - Pre-pour inspection
label | ACCEPTANCE CRITERIA - Stringline Depth Check
label | FREQUENCY - Prior to each pour
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - String check sheet, Pre pour inspection checklist
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5 - Construction Joints
label | ACCEPTANCE CRITERIA - At maximum of 4m intervals
label | FREQUENCY - Post-pour
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 6 - As-built plans
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As reviewed and accepted by Engineer
label | FREQUENCY - At the completion of the work
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built plans
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP-006 - Riprap | itp
section | Riprap
checkpoint | 1 - Site Preparation
label | ACTIVITY TASK - Site Clearance
label | ACCEPTANCE CRITERIA - Site clear of debris and vegetation
label | FREQUENCY - Once
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 2 - Material (1)
label | ACTIVITY TASK - Filter Cloth
label | ACCEPTANCE CRITERIA - Approved filter cloth with class 1 filtration and class C strength class - Bidim A49 or equivalent
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (2)
label | ACTIVITY TASK - Rock Boulders criteria
label | ACCEPTANCE CRITERIA - According to WDC Physical work Section E.6. Rip Rap Specification Section 2 page 856
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (3)
label | ACTIVITY TASK - RIP-RAP grading
label | ACCEPTANCE CRITERIA - According to WDC Physical work Section E.6. Rip Rap Specification Section 3 page 856
label | FREQUENCY - Upon delivery of material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3 - Initial set out
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As per drawings and provided design model
label | FREQUENCY - Prior to subgrade preparation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Subgrade Prep (1)
label | ACTIVITY TASK - Trim subgrade to suit
label | ACCEPTANCE CRITERIA - As per drawing and provided design model
label | FREQUENCY - Prior to placing Geotextile
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey – As-built surface
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4 - Subgrade Prep (2)
label | ACTIVITY TASK - Place Geotextile
label | ACCEPTANCE CRITERIA - As per drawings and specification.
label | FREQUENCY - Prior to placing RIP- RAP material
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 5 - RIP-RAP Placement
label | ACTIVITY TASK - Install RIP-RAP stones
label | ACCEPTANCE CRITERIA - According to WDC Physical work Section E.6. Rip Rap Specification Section 4 page 856 with approved machinery.
label | FREQUENCY - During and Upon completion of work
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey As-built topography Photos, Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Maintenance
label | ACTIVITY TASK - Maintain RIP RAP protection until accepted by Engineer
label | ACCEPTANCE CRITERIA - As required
label | FREQUENCY - Upon completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 7 - As-Built Plans
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As accepted by the Engineer
label | FREQUENCY - Upon completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built plans
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checklist | ITP-007 - Geotechnical Structures | itp
section | Geotechnical Structures
checkpoint | 1 - Site Preparation
label | ACTIVITY TASK - Site Clearance
label | ACCEPTANCE CRITERIA - Site clear of debris and vegetation
label | FREQUENCY - Once
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 2 - Material (1)
label | ACTIVITY TASK - Class C Geotextile
label | ACCEPTANCE CRITERIA - As approved by the Engineer
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (2)
label | ACTIVITY TASK - Miragrid GX130 Geogrid
label | ACCEPTANCE CRITERIA - Free from damages
label | FREQUENCY - Upon delivery on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (3)
label | ACTIVITY TASK - Green Terramesh or similar approved
label | ACCEPTANCE CRITERIA - As approved by the Engineer
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (4)
label | ACTIVITY TASK - Keystone Units
label | ACCEPTANCE CRITERIA - As approved by the Engineer
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Material (5)
label | ACTIVITY TASK - Granular Fill
label | ACCEPTANCE CRITERIA - As per WSP technical specification section 5.3.2 Pg 11
label | FREQUENCY - Prior to placing order
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 3 - Initial set out
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As per drawings and provided design model
label | FREQUENCY - Prior to subgrade preparation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - MSE Wall (1)
label | ACTIVITY TASK - Subgrade Prep
label | ACCEPTANCE CRITERIA - Excavate to suit grade and slopes as per drawing and provided design model
label | FREQUENCY - Prior to placing Geotextile
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey – As-built surface
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4 - MSE Wall (2)
label | ACTIVITY TASK - Place Class C Geotextile
label | ACCEPTANCE CRITERIA - As per drawings and site specification.
label | FREQUENCY - Prior to placing drainage aggregate
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4 - MSE Wall (3)
label | ACTIVITY TASK - 150mm thick 20/7 drainage metal or approved metal
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - Prior to placing Geogrid
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4 - MSE Wall (4)
label | ACTIVITY TASK - Install subsoil drain
label | ACCEPTANCE CRITERIA - As per drawings and site specification
label | FREQUENCY - Prior to placing Subsequent lift works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - MSE Wall (5)
label | ACTIVITY TASK - Miragrid GX130 Geogrid
label | ACCEPTANCE CRITERIA - Placed in continuous strips, tensioned and anchored in place on level compacted fill as per IFC drawings
label | FREQUENCY - Prior to placing ea. Subsequent lift works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - MSE Wall (6)
label | ACTIVITY TASK - Green Terramesh Wall
label | ACCEPTANCE CRITERIA - As per IFC Drawings, site specification and manufacturers specification.
label | ○ Void in face to be filled with Granular fill
label | FREQUENCY - Prior to placing ea. Subsequent lift works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection Photos
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - MSE Wall (7)
label | ACTIVITY TASK - Ea. 500mm GAP65 fill lift
label | ACCEPTANCE CRITERIA - Placed and compacted in layer – not exceeding 300mm layers
label | FREQUENCY - Prior to placing ea. Subsequent lift works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test record sheet – as per requirement given below, Visual Inspection, As-built surface top of each finished lift
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Compaction Test
label | ACTIVITY TASK - NDM compaction test
label | ACCEPTANCE CRITERIA - MDD ≥ 95%
label | ○ Minimum of 5 NDM tests to be carried out at ½ height and again at the top of the granular backfill.
label | ○ As per WSP technical specification section 5.2.1 pg 11
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - NDM test records
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Retaining Wall (1)
label | ACTIVITY TASK - Foundation works
label | ACCEPTANCE CRITERIA - Thoroughly Compacted granular fill foundation as per IFC drawings and site specification.
label | FREQUENCY - Prior to starting Subsequent works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspections, Test as directed by the Engineer
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Retaining Wall (2)
label | ACTIVITY TASK - Install keystone units
label | ACCEPTANCE CRITERIA - As per IFC drawing, site specification and manufacturers specification
label | FREQUENCY - During and Upon installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection. Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Retaining Wall (3)
label | ACTIVITY TASK - Install 110mm subsoil drain
label | ACCEPTANCE CRITERIA - As per IFC drawings and specification
label | FREQUENCY - Prior to backfill drainage metal
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey as built
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 6 - Retaining Wall (4)
label | ACTIVITY TASK - 300mm wide approved free draining granular metal
label | ACCEPTANCE CRITERIA - Backfilled back of the retaining to the bottom of finished surface
label | FREQUENCY - Prior to prep for the concrete footpath
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 7 - As-Built Plans
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As accepted by the Engineer
label | FREQUENCY - Upon completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built plans
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checklist | ITP-008 - Temporary Bypass | itp
section | Temporary Bypass
checkpoint | 1 - Site Preparation
label | ACTIVITY TASK - Site Clearance and Excavation
label | ACCEPTANCE CRITERIA - Free from organic material, ground prepared for the accurate placement of piles and temporary access Road
label | FREQUENCY - Once
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Initial set out
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As per approved drawings, offset pegs for the pile location as required
label | FREQUENCY - Prior to start predrilling or installation of piles
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 3 - Temporary Access Road – 4m Wide (1)
label | ACTIVITY TASK - Prepare Subgrade
label | ACCEPTANCE CRITERIA - Clear or relocate vegetation as required, trim subgrade to suite
label | FREQUENCY - Prior to building temporary access way
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3 - Temporary Access Road – 4m Wide (2)
label | ACTIVITY TASK - Geotextile
label | ACCEPTANCE CRITERIA - Visual inspection
label | FREQUENCY - Prior to placing Basecourse
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3 - Temporary Access Road – 4m Wide (3)
label | ACTIVITY TASK - 300mm Basecourse
label | ACCEPTANCE CRITERIA - Placed and compacted in layers
label | FREQUENCY - Prior to installation of temporary bridge
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 4 - Pile Installation (1)
label | ACTIVITY TASK - Supply Timber poles and Steel Casing Sleeve on site
label | ACCEPTANCE CRITERIA - As per approved design
label | FREQUENCY - Upon being delivered on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - Pile Installation (2)
label | ACTIVITY TASK - Drive piles
label | ACCEPTANCE CRITERIA - As per approved design, The piling Rig to drive the piles into the ground to a depth of approx. 12m
label | FREQUENCY - Prior to installation of timber poles
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection Photos, Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - Pile Installation (3)
label | ACTIVITY TASK - Place Timber Pole
label | ACCEPTANCE CRITERIA - Timber post to be placed on top of the driven piles
label | FREQUENCY - Prior to installing steel casing
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - Pile Installation (4)
label | ACTIVITY TASK - Install Steel Casing
label | ACCEPTANCE CRITERIA - Steel casing driven to refusal
label | FREQUENCY - Prior installation of steel headstocks and girders
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5 - Supply and Install Steel Headstocks and Girders (1)
label | ACTIVITY TASK - Supply Steel Headstocks, Girders and fixings
label | ACCEPTANCE CRITERIA - Correct type and sizes as per approved design
label | FREQUENCY - Upong being delivered on site
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5 - Supply and Install Steel Headstocks and Girders (2)
label | ACTIVITY TASK - Install Double Headstocks
label | ACCEPTANCE CRITERIA - Stitch welded together as per approved design and specification
label | FREQUENCY - Prior to installing Girders
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5 - Supply and Install Steel Headstocks and Girders (3)
label | ACTIVITY TASK - Install UB Girders with transverse braces
label | ACCEPTANCE CRITERIA - As per approved design alignment and fixing detail
label | FREQUENCY - Prior to installation of Precast Concrete Panels
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Supply and Install 7.5m wide concrete reinforced Pre- Cast deck panels (1)
label | ACTIVITY TASK - Supply 7.5m wide concrete reinforced precast deck panels
label | ACCEPTANCE CRITERIA - As per approved design, Free from damages and cracks
label | FREQUENCY - Prior to Installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 6 - Supply and Install 7.5m wide concrete reinforced Pre- Cast deck panels (2)
label | ACTIVITY TASK - Install Pre-Cast deck panels
label | ACCEPTANCE CRITERIA - Correct fixing as per approved design
label | FREQUENCY - Prior to install Barrier
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractors’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 7 - Temporary Vehicle Barriers
label | ACTIVITY TASK - Install Water filled barrier or similar
label | ACCEPTANCE CRITERIA - Install Water filled barrier or similar
label | FREQUENCY - Install Water filled barrier or similar
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 8 - Final Inspection
label | ACTIVITY TASK - Thorough Inspection
label | ACCEPTANCE CRITERIA - Constructed in accordance with the approved design and specifications.
label | FREQUENCY - Prior to handing over for use
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Written approval from Inspector
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Regular Maintenance Checks
label | ACTIVITY TASK - Conduct regular maintenance checks
label | ACCEPTANCE CRITERIA - Monitor the condition of the bridge, ensuring it remains safe and functional
label | FREQUENCY - During Operational Period – as directed by the engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Inspection report
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Decommission of Temporary Bypass (1)
label | ACTIVITY TASK - Remove bridge deck, headstock, girders, piles and access road.
label | ACCEPTANCE CRITERIA - No debris to be left, reinstate ground to original condition
label | FREQUENCY - After decommissioning of temporary bypass
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 10 - Decommission of Temporary Bypass (2)
label | ACTIVITY TASK - Landscaping
label | ACCEPTANCE CRITERIA - As required or to original state
label | FREQUENCY - After decommissioning of temporary bypass
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 11 - As-Built Plans
label | ACTIVITY TASK - Survey – Final surfaces
label | ACCEPTANCE CRITERIA - As directed by the Engineer
label | FREQUENCY - Upon completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built plans
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP-009 - Bridge Replacement | itp
section | Bridge Replacement
checkpoint | 1 - Site Preparation (1)
label | ACTIVITY TASK - Site Clearance and Excavation
label | ACCEPTANCE CRITERIA - General site clearance, removal of the trees
label | FREQUENCY - Once
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 1 - Site Preparation (2)
label | ACTIVITY TASK - Demolition and removal of existing bridge
label | ACCEPTANCE CRITERIA - Removal of existing bridge including the bridge piles from the previous bridge.
label | ○ Structures to be salvaged and transported to WDC Yard
label | FREQUENCY - Once
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - R
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - R
checkpoint | 2 - Initial set out
label | ACTIVITY TASK - Survey
label | ACCEPTANCE CRITERIA - As per IFC drawings, and design model provided
label | FREQUENCY - Prior to start Bridge Construction
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (1)
label | ACTIVITY TASK - Predrilling
label | ACCEPTANCE CRITERIA - As required – to ensure proper foundation conditions for the pile installation
label | FREQUENCY - Prior to Installation of Pile
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (2)
label | ACTIVITY TASK - Dry Mix Concrete Driving Plug
label | ACCEPTANCE CRITERIA - Placed directly from the concrete truck into pile casing, ensuring accurate quantity and proper distribution.
label | FREQUENCY - Prior to placing casing into the ground
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Suppliers’ documentation, Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (3)
label | ACTIVITY TASK - Mobilising the pile
label | ACCEPTANCE CRITERIA - Gently tapped to mobilise the pile by tapping the dry mix charge.
label | FREQUENCY - Prior to diving pile
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 3 - Pile Installation (4)
label | ACTIVITY TASK - Driving the pile casing
label | ACCEPTANCE CRITERIA - Drive the pile casing down to designed depths.
label | ○ Welded additional lengths of casing as per IFC Drawings and specification.
label | ○ Final splice completed to ensure piles are constructed to the specified depths and length.
label | FREQUENCY - Prior to install reinforcement pile cage
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation Subcontractors Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (5)
label | ACTIVITY TASK - Ultimate Geotechnical Strength Check
label | ACCEPTANCE CRITERIA - Hiely Formulae to estimate ultimate geotechnical strength to ensure specified value in IFC drawings.
label | FREQUENCY - Prior to installing reinforcement pile cage
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test record sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (6)
label | ACTIVITY TASK - Install pile reinforcement cage
label | ACCEPTANCE CRITERIA - Pile reinforcement cage prefabricated to as per IFC drawings and specification
label | FREQUENCY - Prior to installing in casing
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (7)
label | ACTIVITY TASK - Pre-pour inspection
label | ACCEPTANCE CRITERIA - Pile casing and cage installed as per IFC drawings and specification
label | FREQUENCY - Prior to concrete pour
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection check list
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (8)
label | ACTIVITY TASK - Concrete Placement
label | ACCEPTANCE CRITERIA - Concrete poured at cut-off levels using concrete pump hose, lowered to the base of the pile.
label | ○ Concrete poured in stages to reach required depths
label | FREQUENCY - During concrete placement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection, Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (9)
label | ACTIVITY TASK - Final Inspection
label | ACCEPTANCE CRITERIA - Pile cage securely placed, and the concrete placement is complete
label | FREQUENCY - Upon completion of the concrete placement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Inspection check sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Pile Installation (10)
label | ACTIVITY TASK - PDA Testing
label | ACCEPTANCE CRITERIA - At minimum 20% of driven pile, with minimum of 1 pile at each abutment shall be tested. As per site technical specification section 8.3.2
label | FREQUENCY - At minimum of 72 hours after initial driving or as directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Record sheet PDA test – obtain written approval from Engineer
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Abutment Construction (1)
label | ACTIVITY TASK - Abutment footprint preparation
label | ACCEPTANCE CRITERIA - As per IFC drawings and design model provided to enable blinding concrete works.
label | FREQUENCY - Prior to placing blinding concrete – Pre-pour Inspection
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Abutment Construction (2)
label | ACTIVITY TASK - Place blinding concrete
label | ACCEPTANCE CRITERIA - 50mm thick 10MPa blinding concrete as per IFC Drawings and Specification
label | FREQUENCY - Prior to installing subsequent works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 4 - Abutment Construction (3)
label | ACTIVITY TASK - Survey Setout
label | ACCEPTANCE CRITERIA - Setout completed on blinding concrete, including offset dimensions to the abutment beams and RLs as per IFC drawings and design model provided
label | FREQUENCY - Prior to installing reinforcement works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Provided design survey model, Visual inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Abutment Construction (4)
label | ACTIVITY TASK - Main abutment beam and pile caping – reinforcement install
label | ACCEPTANCE CRITERIA - Prefabricated reinforcement as per IFC Drawings and specification provided
label | FREQUENCY - Prior to installing subsequent work – as directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Abutment Construction (5)
label | ACTIVITY TASK - Pile starter bars
label | ACCEPTANCE CRITERIA - Flange and nuts epoxied to the pile starter bars as per IFC Drawings and specification
label | FREQUENCY - Prior to Prior to installing subsequent work
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Abutment Construction (6)
label | ACTIVITY TASK - Abutment Upstand starter bars
label | ACCEPTANCE CRITERIA - Positioned correctly and bars as per IFC drawings and specification
label | FREQUENCY - Prior to installing subsequent works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Abutment Construction (7)
label | ACTIVITY TASK - Pre-Pour inspection
label | ACCEPTANCE CRITERIA - Formworks within tolerance and reinforcement and other fixings according to IFC drawings and specification
label | FREQUENCY - Prior placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Abutment Construction (8)
label | ACTIVITY TASK - Place concrete
label | ACCEPTANCE CRITERIA - 40MPa concrete as per IFC Drawings, Concrete compaction with vibrators and application of surface retarder to the construction joint at the base of the abutment upstand.
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 5 - Pre-cast Beams (1)
label | ACTIVITY TASK - Installation of the Elastomeric bearings
label | ACCEPTANCE CRITERIA - Bearings and joint preparing as per IFC Drawings and specification
label | FREQUENCY - Prior to installing SHC beams, and as directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet, Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pre-cast Beams (2)
label | ACTIVITY TASK - Pre-cast Single Hollow Core Beam
label | ACCEPTANCE CRITERIA - Pre-cast completed and cured to archive designed strength at 28 days, free from damages and cracks.
label | ○ Northen beams dressed with steel pipe brackets, pipe hangers.
label | ○ As per drawings and specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pre-cast Beams (3)
label | ACTIVITY TASK - Install 400mm&300mm sections of pipe
label | ACCEPTANCE CRITERIA - Prefabricated and braced on hangers as per IFC Drawings and specification
label | FREQUENCY - Prior to installing beam on the position
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet, Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pre-cast Beams (4)
label | ACTIVITY TASK - Install SHC beams
label | ACCEPTANCE CRITERIA - Placed on beam locations setout on abutment beams including level check of the beam sills within tolerance level as per IFC drawings and specification
label | FREQUENCY - Prior installing subsequent works, and as directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built data, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pre-cast Beams (5)
label | ACTIVITY TASK - Transverse Stressing Duct
label | ACCEPTANCE CRITERIA - Ducts fed through SHC beams, ducts taped together as per IFC drawings and specification
label | FREQUENCY - Prior to start grout works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check sheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Grout infill between SHC (1)
label | ACTIVITY TASK - Pre-grout
label | ACCEPTANCE CRITERIA - The sides of the beams sealed to contain grout
label | FREQUENCY - Prior to place onsite mixed Sika 212 grout
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Grout infill between SHC (2)
label | ACTIVITY TASK - Grout works
label | ACCEPTANCE CRITERIA - Sika 212 grout mixed on site and poured as per IFC drawings and specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation, Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - SHC Beam Post Tensioning (1)
label | ACTIVITY TASK - Super Strand Anchor Heads
label | ACCEPTANCE CRITERIA - Installed at each end of Transverse Stressing Duct
label | FREQUENCY - Prior installing super strands
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation, Visual Inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 7 - SHC Beam Post Tensioning (2)
label | ACTIVITY TASK - Super Strand Installation
label | ACCEPTANCE CRITERIA - The 7 super strands fed through all SHC beams at each PT locations as per IFC Drawings and specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers Documentation,
checkpoint | 7 - SHC Beam Post Tensioning (3)
label | ACTIVITY TASK - Post Tensioning
label | ACCEPTANCE CRITERIA - Strands tensioned up to the design loads and locked in position with a wedge plate at the anchor heads, grouting ports are epoxied in position as per IFC Drawings and specifications
label | FREQUENCY - During and upon completion of post- tensioning
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractor documentation, Record sheets
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - SHC Beam Post Tensioning (4)
label | ACTIVITY TASK - Pre-Grout inspection
label | ACCEPTANCE CRITERIA - All tendon locations stressed and the epoxy at the grout ports has reached strength
label | FREQUENCY - Prior to grout filling
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - SHC Beam Post Tensioning (5)
label | ACTIVITY TASK - Pumping grout into strand ducts
label | ACCEPTANCE CRITERIA - Grout pumped into the ducts under pressure until its bleed out of the breather ports at the far end which are then crimped until grout bleeds out of the pumping end ensuring all air voids are removed from the duct
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - SHC Beam Post Tensioning (6)
label | ACTIVITY TASK - Post-Grout
label | ACCEPTANCE CRITERIA - Ends of strands are trimmed and the rebates for the anchor heads are mortar filled and finished flush with the edge of the beams at all locations
label | FREQUENCY - Upon completion of the grout works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspections
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 8 - Abutment Headwall (1)
label | ACTIVITY TASK - Surface preparation
label | ACCEPTANCE CRITERIA - The day after the abutment beam pour, Pressure blasts the construction joints to a type B roughness
label | FREQUENCY - Prior to installing reinforcement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual inspection
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 8 - Abutment Headwall (2)
label | ACTIVITY TASK - Reinforcement
label | ACCEPTANCE CRITERIA - Installed as per IFC Drawings including linkage bars and ducting for services accurately
label | FREQUENCY - Prior to placing formworks
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Abutment Headwall (3)
label | ACTIVITY TASK - Pre-pour Inspection
label | ACCEPTANCE CRITERIA - Formwork placed with in tolerance and as per IFC Drawings and specification
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Abutment Headwall (4)
label | ACTIVITY TASK - Concrete pour
label | ACCEPTANCE CRITERIA - 40MPa as per site specification and IFC drawings, Finished surface as per specification – B1
label | FREQUENCY - During and upon concrete placement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 9 - Walkway and service hanger (1)
label | ACTIVITY TASK - Pre-cast walkway panels
label | ACCEPTANCE CRITERIA - As per IFC Drawings and Specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Walkway and service hanger (2)
label | ACTIVITY TASK - Installing Pre-cast panel
label | ACCEPTANCE CRITERIA - Positioned between the service brackets, the end in contact with the abutment headwalls are jointed with sealant, pipes are connected as per IFC Drawings and specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 9 - Walkway and service hanger (3)
label | ACTIVITY TASK - Reinforcement and formworks
label | ACCEPTANCE CRITERIA - As per IFC drawings and specifications
label | FREQUENCY - Pre-pour inspection
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Walkway and service hanger (4)
label | ACTIVITY TASK - Concrete placement
label | ACCEPTANCE CRITERIA - As per IFC drawings and specification – Broom finished
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 10 - Wingwall Construction (1)
label | ACTIVITY TASK - Reinforcement and Formwork
label | ACCEPTANCE CRITERIA - As per IFC Drawings and Specification
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Wingwall Construction (2)
label | ACTIVITY TASK - Pre-pour inspection
label | ACCEPTANCE CRITERIA - Inspected and accepted by the Engineer
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Wingwall Construction (3)
label | ACTIVITY TASK - Concrete pour
label | ACCEPTANCE CRITERIA - As per IFC drawings and specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 11 - Settlement Slab (1)
label | ACTIVITY TASK - Subgrade prep
label | ACCEPTANCE CRITERIA - Trim subgrade to suit, Bedding metal placed and compacted as required
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - W
checkpoint | 11 - Settlement Slab (2)
label | ACTIVITY TASK - Reinforcement and formworks
label | ACCEPTANCE CRITERIA - Installed with in tolerance as per IFC drawings and specifications
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Settlement Slab (3)
label | ACTIVITY TASK - Pre-pour inspection
label | ACCEPTANCE CRITERIA - As per IFC drawings and specification
label | FREQUENCY - Prior to placing concrete
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Pre-pour inspection checksheet
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Settlement Slab (4)
label | ACTIVITY TASK - Placement of concrete
label | ACCEPTANCE CRITERIA - Concrete and grade and finish surface as per IFC drawing and specification
label | FREQUENCY - As directed by the Engineer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Suppliers’ documentation
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - As-Built Plans
label | ACTIVITY TASK - Survey – Final surfaces
label | ACCEPTANCE CRITERIA - As directed by the Engineer
label | FREQUENCY - Upon completion of the works
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As-built plans
label | VERIFICATION SIGN OFFS: INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY - H
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - H
holdpoint | AUTHORITY HOLDPOINT