## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
ca6c2686-4381-4c5d-9d9c-d254452e5f91 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-02 | ITC - ASB-DBN-01-02 - Distribution Board Installation - ITC3
31cf2e91-22a0-4466-872e-25f391263d96 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-02 | ITC - ASB-DBS-01-02 - Distribution Board Installation - ITC3
f0c48501-2fea-44d6-9b3b-b0ec4f78d663 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-03 | ITC - ASB-DBN-01-03 - Distribution Board Installation - ITC3
4fb01dbb-62ac-476e-8729-3af7358aeb8b |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-04 | ITC - ASB-DBN-01-04 - Distribution Board Installation - ITC3
dd4646bd-f3cc-4380-8a7f-4e43e66eda18 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-04 | ITC - ASB-DBS-01-04 - Distribution Board Installation - ITC3
0ad50702-b7b1-4e3a-8489-9393c294083e |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-05 | ITC - ASB-DBN-01-05 - Distribution Board Installation - ITC3
0587dc1a-5da6-4430-9094-3ffe4c921247 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-05 | ITC - ASB-DBN-00-05 - Distribution Board Installation - ITC3
70392547-da2c-421a-bac3-fb97624f0134 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-06 | ITC - ASB-DBN-01-06 - Distribution Board Installation - ITC3
f576e162-1708-4135-87c6-cdc155557e5a |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-06 | ITC - ASB-DBS-01-06 - Distribution Board Installation - ITC3
0db8a1f1-fce1-4a4e-9b54-42983756ac7d |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-07 | ITC - ASB-DBS-01-07 - Distribution Board Installation - ITC3
5d265226-afcb-45b7-8d29-5bc1a6439eaf |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-01 | ITC - ASB-DBU-01-01 - Distribution Board Installation - ITC3
ad3e1906-cb4b-49cb-a895-ce68f9ee7c93 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-02 | ITC - ASB-DBU-01-02 - Distribution Board Installation - ITC3
53ba7998-ecaa-4b4c-b8f9-786df8a62751 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-03 | ITC - ASB-DBU-01-03 - Distribution Board Installation - ITC3
fae1b8d6-b9ca-452f-8767-8cdebed67b52 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-04 | ITC - ASB-DBU-01-04 - Distribution Board Installation - ITC3
28f663be-742c-4496-939d-ffaf487cf31e |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-01 | ITC - ASB-DBN-02-01 - Distribution Board Installation - ITC3
67babc9b-6814-4882-83aa-04a906b8910f |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-01 | ITC - ASB-DBS-02-01 - Distribution Board Installation - ITC3
44a57545-787a-449c-a405-44e314706a49 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-01 | ITC - ASB-DBU-02-01 - Distribution Board Installation - ITC3
afbd70f3-c2d7-4df2-a88d-3c2bb57c8ae8 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-02 | ITC - ASB-DBN-02-02 - Distribution Board Installation - ITC3
5558f6e5-6f09-4923-a6d5-d5a283b1855d |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-02 | ITC - ASB-DBS-02-02 - Distribution Board Installation - ITC3
336d2d51-0dff-4425-9441-4cf25bbc714f |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-02 | ITC - ASB-DBU-02-02 - Distribution Board Installation - ITC3
6c640259-cd9f-4438-b8f8-7263841931f6 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-03 | ITC - ASB-DBN-02-03 - Distribution Board Installation - ITC3
a336de49-c73e-4421-8fbe-24638e2ca57a |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-03 | ITC - ASB-DBS-02-03 - Distribution Board Installation - ITC3
6faf58d3-8aad-4175-9b01-92f388daa5a5 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-03 | ITC - ASB-DBU-02-03 - Distribution Board Installation - ITC3
8fa97a11-4bed-4180-b41c-b2d0ca113ce1 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-04 | ITC - ASB-DBN-02-04 - Distribution Board Installation - ITC3
3b07f6cd-df4a-4fa9-9578-d7c10a34022a |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-04 | ITC - ASB-DBS-02-04 - Distribution Board Installation - ITC3
956461b8-74e8-4309-8629-7e9007594b02 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-04 | ITC - ASB-DBU-02-04 - Distribution Board Installation - ITC3
46b72e92-6785-4f14-b155-1d37704bb40e |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-05 | ITC - ASB-DBN-02-05 - Distribution Board Installation - ITC3
2e9b5b53-f281-4f40-9c79-1c81c106771c |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-05 | ITC - ASB-DBS-02-05 - Distribution Board Installation - ITC3
d0cef659-a6aa-4ec7-9e0b-908498979651 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-05 | ITC - ASB-DBU-02-05 - Distribution Board Installation - ITC3
51fd6387-4c74-495e-8b46-72d895425ab8 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-06 | ITC - ASB-DBN-02-06 - Distribution Board Installation - ITC3
3ce1b6d3-124a-4c5c-b1ed-f7bbe72d031e |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-06 | ITC - ASB-DBS-02-06 - Distribution Board Installation - ITC3
364fbfdd-753c-4b3e-9b97-859103f98c5e |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-07 | ITC - ASB-DBS-02-07 - Distribution Board Installation - ITC3
61405e11-1ed0-4426-96da-ecdabc7063bf |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-08 | ITC - ASB-DBN-02-08 - Distribution Board Installation - ITC3
c55e4a25-fd0c-4146-bcc9-e247c7df015f |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-08 | ITC - ASB-DBS-02-08 - Distribution Board Installation - ITC3
5e699557-2977-4231-a122-c83e6710c765 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-09 | ITC - ASB-DBS-02-09 - Distribution Board Installation - ITC3
c1b4b4e9-3597-4eec-baed-230c684f4608 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DAS-03-01 | ITC - ASB-DAS-03-01
77d6750e-8804-4ac4-888a-9666638726de |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DPV-03-01 | ITC - ASB-DPV-03-01
5f4868dc-1f43-4e3f-be53-50b50401d66d |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-01 | ITC - ASB-DBN-03-01 - Distribution Board Installation - ITC3
723022f4-cce4-4fe2-b9ff-cda4db58bbec |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-01 | ITC - ASB-DBS-03-01 - Distribution Board Installation - ITC3
e5937927-3b28-4fd9-9409-539507d59aba |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-01 | ITC - ASB-DBU-03-01 - Distribution Board Installation - ITC3
00dd53bf-f894-4419-8785-e50f459106f3 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-02 | ITC - ASB-DBN-03-02 - Distribution Board Installation - ITC3
924df1b0-9ced-43f5-94ea-ac0d6db1a5ac |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-02 | ITC - ASB-DBS-03-02 - Distribution Board Installation - ITC3
692de196-3985-4169-9188-5ab80448040a |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-02 | ITC - ASB-DBU-03-02 - Distribution Board Installation - ITC3
ed3f8b1c-23bf-4456-bceb-3ffd1418dd66 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-03 | ITC - ASB-DBN-03-03 - Distribution Board Installation - ITC3
d2640a3e-aca1-42f2-b52b-6c5f35be5a68 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-03 | ITC - ASB-DBS-03-03 - Distribution Board Installation - ITC3
d3458b35-3dc7-4e38-a5a2-b2cee84898f1 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-03 | ITC - ASB-DBU-03-03 - Distribution Board Installation - ITC3
03f57ad2-1951-47c8-83b7-6c02536c33c7 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-04 | ITC - ASB-DBN-03-04 - Distribution Board Installation - ITC3
ce20de77-1a14-47cd-8546-cfe748b094d5 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-04 | ITC - ASB-DBS-03-04 - Distribution Board Installation - ITC3
e514072e-b21c-4424-904a-59530cae16a7 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-04 | ITC - ASB-DBU-03-04 - Distribution Board Installation - ITC3
7bc70e20-d873-46e9-9048-72afa42745db |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-05 | ITC - ASB-DBN-03-05 - Distribution Board Installation - ITC3
87db8a44-fa9d-41e5-8ced-d5132b23d193 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-05 | ITC - ASB-DBS-03-05 - Distribution Board Installation - ITC3
9f8c7f6d-85ff-4280-9a67-169af969866d |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-05 | ITC - ASB-DBU-03-05 - Distribution Board Installation - ITC3
27588234-74b4-4dca-8e4f-0c0835adb82f |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-06 | ITC - ASB-DBU-03-06 - Distribution Board Installation - ITC3
3362ca09-5962-491d-bd7d-280e3112dedd |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-01 | ITC - ASB-DBN-04-01 - Distribution Board Installation - ITC3
8598c475-34f2-47f8-9c8b-79619935a8ce |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-01 | ITC - ASB-DBS-04-01 - Distribution Board Installation - ITC3
76e3eeba-acd4-43fe-b51f-aac79fea04f2 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-01 | ITC - ASB-DBU-04-01 - Distribution Board Installation - ITC3
de9b93e7-d2d4-4a46-9b97-465dddd6d315 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-02 | ITC - ASB-DBN-04-02 - Distribution Board Installation - ITC3
7e3df9c0-ba4d-4667-947b-9016799404ea |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-02 | ITC - ASB-DBS-04-02 - Distribution Board Installation - ITC3
bee25aa9-3cc2-4891-af2a-76b0888c7f67 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-02 | ITC - ASB-DBU-04-02 - Distribution Board Installation - ITC3
cba63e6b-771c-454b-9e9e-afbd0cac6888 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-03 | ITC - ASB-DBN-04-03 - Distribution Board Installation - ITC3
2cde775f-61fe-4f6f-8052-e4d9358730c8 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-03 | ITC - ASB-DBS-04-03 - Distribution Board Installation - ITC3
058f495d-0292-4bca-8871-e02bb7b77517 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-03 | ITC - ASB-DBU-04-03 - Distribution Board Installation - ITC3
fe1183a3-b604-4257-9d8c-b1c5f14b82d2 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-04 | ITC - ASB-DBN-04-04 - Distribution Board Installation - ITC3
92c9df79-7acb-4484-beda-022f9348d279 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-04 | ITC - ASB-DBS-04-04 - Distribution Board Installation - ITC3
d305fa9d-c110-4537-b8ec-d556843847b3 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-04 | ITC - ASB-DBU-04-04 - Distribution Board Installation - ITC3
072e168d-01bc-4158-9c48-90bf4523b12f |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBN-05-01 | ITC - ASB-DBN-05-01 - Distribution Board Installation - ITC3
022ba93c-dbcd-4bdb-9e85-4a0970f1d402 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBS-05-01 | ITC - ASB-DBS-05-01 - Distribution Board Installation - ITC3
67417f66-38dd-4757-af3d-2203d9eb8d19 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBU-05-01 | ITC - ASB-DBU-05-01 - Distribution Board Installation - ITC3
a0fe3f4e-1d13-4e75-881a-0a16c59404e3 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBN-05-02 | ITC - ASB-DBN-05-02 - Distribution Board Installation - ITC3
8dcba30b-8879-4b59-8d55-be6831a67f7b |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBS-05-02 | ITC - ASB-DBS-05-02 - Distribution Board Installation - ITC3
bf7787dc-dc22-46a7-9ff3-268021111442 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBU-05-02 | ITC - ASB-DBU-05-02 - Distribution Board Installation - ITC3
6e28951a-00b0-4398-9dc8-f8b44491d4d5 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBN-05-03 | ITC - ASB-DBN-05-03 - Distribution Board Installation - ITC3
3bd24aa4-1c72-4c89-b952-a0d85c815215 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBS-05-03 | ITC - ASB-DBS-05-03 - Distribution Board Installation - ITC3
527babcb-e6da-4e1d-9147-b06ab053ca87 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBN-06-01 | ITC - ASB-DBN-06-01 - Distribution Board Installation - ITC3
fd452caf-669f-45a8-9848-4e09d7fc740f |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBS-06-01 | ITC - ASB-DBS-06-01 - Distribution Board Installation - ITC3
3e5704d0-17d9-446c-8c21-b33d5155c635 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBU-06-01 | ITC - ASB-DBU-06-01 - Distribution Board Installation - ITC3
46af5d6d-65e3-4e26-92f6-11753a14ed65 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBN-06-02 | ITC - ASB-DBN-06-02 - Distribution Board Installation - ITC3
fd0ea2d2-17a6-4bc9-8b4d-853f682536ab |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBS-06-02 | ITC - ASB-DBS-06-02 - Distribution Board Installation - ITC3
4eaeccb7-f1dc-4580-ab62-f9bd0f7ed708 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBU-06-02 | ITC - ASB-DBU-06-02 - Distribution Board Installation - ITC3
c35d3f87-aa1d-4cd8-b4dd-d6ccf479d549 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBN-06-03 | ITC - ASB-DBN-06-03 - Distribution Board Installation - ITC3
f8171abd-4c98-452c-a572-a67aa398d5aa |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBS-06-03 | ITC - ASB-DBS-06-03 - Distribution Board Installation - ITC3
0b417561-4730-46cf-9160-b59d45514ca4 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBN-07-02 | ITC - ASB-DBN-07-02 - Distribution Board Installation - ITC3
e902391c-987e-4902-947a-5729dd5d1be7 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBN-07-03 | ITC - ASB-DBN-07-03 - Distribution Board Installation - ITC3
4edd4cc2-05e6-4370-92f8-7afdd2dda4e3 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBN-07-03H | ITC - ASB-DBN-07-03H - Distribution Board Installation - ITC3
04403250-cbd9-4cd0-8937-d66e4f723dd8 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBS-07-02 | ITC - ASB-DBS-07-02 - Distribution Board Installation - ITC3
d20695d4-9950-40c6-8cf5-3ec7a5ff2647 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBS-07-03 | ITC - ASB-DBS-07-03 - Distribution Board Installation - ITC3
ea550958-52b4-40f6-9367-48d6a782c538 |  | not-started | ITC - (3A) MSB and DB's TEST Sheet V3 | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBU-07-01 | ITC - ASB-DBU-07-01 - Distribution Board Installation - ITC3