## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
f98bcf8c-85f9-4bf2-9045-b50f540d190f |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBN-00-01 | QA - ASB-DBN-00-01 (Board Itself)
5dee3971-b40c-4b36-ae73-2fc4a8dc3f05 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBS-00-01 | QA - ASB-DBS-00-01 - Distribution Board Installation (Board Itself)
ea95cab0-4e07-4140-a5c2-44b680651393 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBU-00-01 | QA - ASB-DBU-00-01
fe9d1d69-6a86-4aeb-b9d3-35bf779b087f |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBN-00-02 | QA - ASB-DBN-00-02 (Board Itself)
8867cbd4-6550-4408-98ab-be0cc50f8f4e |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBS-00-02 | QA - ASB-DBS-00-02 (Board Itself)
b4ad4af7-fe2d-4382-a4e1-580e95f6771d |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBU-00-02 | QA - ASB-DBU-00-02 - Distribution Board Installation - ITC3
88b74859-0c60-475b-a0aa-512ce7e4c37d |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBN-00-03 | QA - ASB-DBN-00-03 - Distribution Board Installation - ITC3
2a214fcf-33ab-4b38-8e67-fdd11c764e22 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBN-00-04 | QA - ASB-DBN-00-04 (Board Itself)
e2b12ff6-88a5-4281-b37b-f28c28d97d9c |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBS-00-04 | QA - ASB-DBS-00-04 (Board Itself)
136b54cb-a511-4881-9a46-4ec4c186d3d3 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBN-00-05 | QA - ASB-DBN-00-05 (Board Itself) - Distribution Board Installation - ITC3
268d2221-3bb2-4ddc-b9ab-c4048fa18e91 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Ground 00 | ASB-DBN-00-06 | QA - ASB-DBN-00-06 (Board Itself) - Distribution Board Installation - ITC3
3ff6eed3-0acf-4d56-8f38-4ccb795be668 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-01 | QA - ASB-DBN-01-01 (Board Itself)
19d3bab7-e945-497e-bdf1-499f2034368c |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-01 | QA - ASB-DBS-01-01 - Distribution Board Installation - ITC3
c42cbca2-5d57-4243-a2ef-0cf68a5bd51f |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-02 | QA - ASB-DBN-01-02 - Distribution Board Installation - ITC3
d8050b09-9135-49e1-a91a-691145d72a11 |  | work-in-progress | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-02 | QA - ASB-DBS-01-02 - Distribution Board Installation - ITC3
3d568962-5e34-4dc2-8d78-d3b9b168d0dd |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-03 | QA - ASB-DBN-01-03 - Distribution Board Installation - ITC3
bfa97862-a29f-40c6-898b-5df9699842a9 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-04 | QA - ASB-DBN-01-04 - Distribution Board Installation - ITC3
c060b02a-7c92-4df1-95bd-baf05637956a |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-04 | QA - ASB-DBS-01-04 - Distribution Board Installation - ITC3
08a25b16-6ac3-4139-acdf-e950531d9897 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-05 | QA - ASB-DBN-01-05 - Distribution Board Installation - ITC3
7a3ebe32-6a4f-40b2-8af9-34980f6bb6f1 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBN-01-06 | QA - ASB-DBN-01-06 - Distribution Board Installation - ITC3
506568c3-c0ae-403e-856e-711247093f48 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-06 | QA - ASB-DBS-01-06 - Distribution Board Installation - ITC3
76a57615-8c7f-404c-8d14-316c87d202b6 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBS-01-07 | QA - ASB-DBS-01-07 - Distribution Board Installation - ITC3
7f3a896b-e6d8-4160-9428-875983bb092f |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-01 | QA - ASB-DBU-01-01 - Distribution Board Installation - ITC3
a19e1358-572f-43ce-ac25-5983b1227ded |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-02 | QA - ASB-DBU-01-02 - Distribution Board Installation - ITC3
7ad6bd02-84a3-4c4a-b093-2594c52da639 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-03 | QA - ASB-DBU-01-03 - Distribution Board Installation - ITC3
18390c4a-3b33-4a03-ad9a-8297023a9939 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 01 | ASB-DBU-01-04 | QA - ASB-DBU-01-04 - Distribution Board Installation - ITC3
ab81f034-1871-4109-b674-04127ec3efc0 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-01 | QA - ASB-DBN-02-01 - Distribution Board Installation - ITC3
34926492-d6f9-4b79-9c09-9a7337a249be |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-01 | QA - ASB-DBS-02-01 - Distribution Board Installation - ITC3
ca972487-3c9c-45da-8113-31e3281da00f |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-01 | QA - ASB-DBU-02-01 - Distribution Board Installation - ITC3
e08c1ead-bf32-4009-bed9-ad71cab9a7c7 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-02 | QA - ASB-DBN-02-02 - Distribution Board Installation - ITC3
c72b9996-00b8-47c1-8823-2fdd7ce58e5b |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-02 | QA - ASB-DBS-02-02 - Distribution Board Installation - ITC3
61cad0cc-b35b-4398-b8ab-b3c3c188f0a5 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-02 | QA - ASB-DBU-02-02 - Distribution Board Installation - ITC3
91973974-55f7-4af2-8dbf-2dfb94786f6d |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-03 | QA - ASB-DBN-02-03 - Distribution Board Installation - ITC3
c14e6da9-1eb6-43f8-9d63-f8adf05cb26f |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-03 | QA - ASB-DBS-02-03 - Distribution Board Installation - ITC3
c2c45fc1-a063-41b2-99ec-d492024d8f71 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-03 | QA - ASB-DBU-02-03 - Distribution Board Installation - ITC3
ebc4b00d-c6dc-42c3-94c9-ccd85b61f7e1 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-04 | QA - ASB-DBN-02-04 - Distribution Board Installation - ITC3
789e544c-d40d-438a-9ef9-e7ad268f913d |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-04 | QA - ASB-DBS-02-04 - Distribution Board Installation - ITC3
d535d835-811b-4658-9691-2e00d84e4851 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-04 | QA - ASB-DBU-02-04 - Distribution Board Installation - ITC3
09f58bf2-292c-45b1-8795-bbbc92f7d335 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-05 | QA - ASB-DBN-02-05 - Distribution Board Installation - ITC3
108d2991-448d-4344-bb15-4041c4d97da7 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-05 | QA - ASB-DBS-02-05 - Distribution Board Installation - ITC3
36cfdf42-7a29-4d47-b564-0a61c1a3faa7 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBU-02-05 | QA - ASB-DBU-02-05 - Distribution Board Installation - ITC3
8be683d8-9535-41f7-beb6-7d76b14be3b4 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-06 | QA - ASB-DBN-02-06 - Distribution Board Installation - ITC3
14e7f4d2-1728-4d34-a1e7-a3f8fe549ec0 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-06 | QA - ASB-DBS-02-06 - Distribution Board Installation - ITC3
6e3a472b-e5f6-425a-aff5-6402b883d7f4 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-07 | QA - ASB-DBS-02-07 - Distribution Board Installation - ITC3
5d7b95e4-9975-42aa-b8cd-e7d37407baeb |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBN-02-08 | QA - ASB-DBN-02-08 - Distribution Board Installation - ITC3
7a5fb69a-b5aa-4805-9634-f3fc81da022c |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-08 | QA - ASB-DBS-02-08 - Distribution Board Installation - ITC3
c13fb172-c70b-4dd5-8c2b-b8c9287fd105 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 02 | ASB-DBS-02-09 | QA - ASB-DBS-02-09 - Distribution Board Installation - ITC3
13ac6425-80fd-48e9-b5ff-8428e9d276e6 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DAS-03-01 | QA - ASB-DAS-03-01
8aafd081-f260-4038-b778-161ca86502c3 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DPV-03-01 | QA - ASB-DPV-03-01
0e4eec5f-63fc-4f6c-a9d4-e723fd2c0dd7 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-01 | QA - ASB-DBN-03-01 - Distribution Board Installation - ITC3
2495c4f0-6aaa-43ef-8bee-9779d3d3f432 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-01 | QA - ASB-DBS-03-01 - Distribution Board Installation - ITC3
b89807f8-615f-4239-8dac-49428daba805 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-01 | QA - ASB-DBU-03-01 - Distribution Board Installation - ITC3
06b94d45-6bf4-42ae-8c9c-d117b0212107 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-02 | QA - ASB-DBN-03-02 - Distribution Board Installation - ITC3
b4b10b2c-d4e7-4865-8704-8719a466b554 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-02 | QA - ASB-DBS-03-02 - Distribution Board Installation - ITC3
ce9e2981-7e6c-4f87-8454-c77088cccbc2 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-02 | QA - ASB-DBU-03-02 - Distribution Board Installation - ITC3
a808b298-4191-488f-aa97-6341c0fe2503 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-03 | QA - ASB-DBN-03-03 - Distribution Board Installation - ITC3
f8de2e88-f950-4479-be6b-66cdb74d0932 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-03 | QA - ASB-DBS-03-03 - Distribution Board Installation - ITC3
3d6c7603-fb80-4016-a7d4-d3388e7a98ac |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-03 | QA - ASB-DBU-03-03 - Distribution Board Installation - ITC3
049ee5f6-0714-4966-842d-3800e3c2032d |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-04 | QA - ASB-DBN-03-04 - Distribution Board Installation - ITC3
c0c8aee3-d5a7-4f12-9120-6b7ae4c2656b |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-04 | QA - ASB-DBS-03-04 - Distribution Board Installation - ITC3
e7c9612e-29fb-4768-92d0-9c0125b70360 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-04 | QA - ASB-DBU-03-04 - Distribution Board Installation - ITC3
b79fc09f-2209-404a-b8a7-0f37831135a1 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBN-03-05 | QA - ASB-DBN-03-05 - Distribution Board Installation - ITC3
43e54208-bc90-41c7-9d51-7fda8f4d6578 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBS-03-05 | QA - ASB-DBS-03-05 - Distribution Board Installation - ITC3
b7b100a0-838a-441c-9273-18b6c0124b46 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-05 | QA - ASB-DBU-03-05 - Distribution Board Installation - ITC3
d222dde9-9cb5-4e97-81b7-e641ecb48b0b |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 03 | ASB-DBU-03-06 | QA - ASB-DBU-03-06 - Distribution Board Installation - ITC3
3bdc6013-2dc2-455b-8203-01583faa91b6 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-01 | QA - ASB-DBN-04-01 - Distribution Board Installation - ITC3
10d224ab-5b80-4b15-a43e-012352ba7706 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-01 | QA - ASB-DBS-04-01 - Distribution Board Installation - ITC3
3dc513f1-6f46-4119-a545-e78ba72c606b |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-01 | QA - ASB-DBU-04-01 - Distribution Board Installation - ITC3
a17e70de-8ba8-4eea-87c6-83d548f455f8 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-02 | QA - ASB-DBN-04-02 - Distribution Board Installation - ITC3
85a4540c-7b0b-486a-994b-3b9ff876ac51 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-02 | QA - ASB-DBS-04-02 - Distribution Board Installation - ITC3
4b4fe30a-88a4-4af8-a644-252ef3b5e8a3 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-02 | QA - ASB-DBU-04-02 - Distribution Board Installation - ITC3
861d35a7-a73a-44ac-9611-2f735718417e |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-03 | QA - ASB-DBN-04-03 - Distribution Board Installation - ITC3
143534ab-f61c-4416-9180-a59fa0b1c891 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-03 | QA - ASB-DBS-04-03 - Distribution Board Installation - ITC3
22c9c61a-ebae-4432-a75a-f9132e9dd00a |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-03 | QA - ASB-DBU-04-03 - Distribution Board Installation - ITC3
dbadfd43-296b-4fb2-8f80-c4346291f709 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBN-04-04 | QA - ASB-DBN-04-04 - Distribution Board Installation - ITC3
fe3604f6-d36b-4689-8073-939a51e4247c |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBS-04-04 | QA - ASB-DBS-04-04 - Distribution Board Installation - ITC3
63c9e930-e38d-4b91-9c4c-4d19d1678526 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 04 | ASB-DBU-04-04 | QA - ASB-DBU-04-04 - Distribution Board Installation - ITC3
06c85418-e46a-4de2-9c9c-505f032564ac |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBN-05-01 | QA - ASB-DBN-05-01 - Distribution Board Installation - ITC3
27737b67-ffe2-434f-a720-0fd738c4298a |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBS-05-01 | QA - ASB-DBS-05-01 - Distribution Board Installation - ITC3
332c5d6a-e8cf-4a9c-b699-66bc1aad5497 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBU-05-01 | QA - ASB-DBU-05-01 - Distribution Board Installation - ITC3
c0ad43d0-37b4-4d2d-a343-4463b81e0dd5 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBN-05-02 | QA - ASB-DBN-05-02 - Distribution Board Installation - ITC3
decb8a5e-611e-4506-a045-049104c3416b |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBS-05-02 | QA - ASB-DBS-05-02 - Distribution Board Installation - ITC3
eadb8f5e-713b-4412-bc7c-cbf55a96e3d6 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBU-05-02 | QA - ASB-DBU-05-02 - Distribution Board Installation - ITC3
fd61486d-0a35-4af4-9c6f-5765357bdedd |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBN-05-03 | QA - ASB-DBN-05-03 - Distribution Board Installation - ITC3
de9da6ca-d569-4d61-9506-49aeefcbd9c7 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 05 | ASB-DBS-05-03 | QA - ASB-DBS-05-03 - Distribution Board Installation - ITC3
ac682f72-1df7-44b8-91b8-ae766988b30e |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBN-06-01 | QA - ASB-DBN-06-01 - Distribution Board Installation - ITC3
644f3e1c-b132-4f5c-b0b5-d33c736b2b9c |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBS-06-01 | QA - ASB-DBS-06-01 - Distribution Board Installation - ITC3
4a4deefe-046d-4fec-b7ab-a12335f8296c |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBU-06-01 | QA - ASB-DBU-06-01 - Distribution Board Installation - ITC3
f92596fc-024d-46e3-bed6-7f5ef11b3356 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBN-06-02 | QA - ASB-DBN-06-02 - Distribution Board Installation - ITC3
0d50b188-76ad-4bd9-8e16-a3ee772bfaad |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBS-06-02 | QA - ASB-DBS-06-02 - Distribution Board Installation - ITC3
5d4d130c-ee8b-48d0-b31e-40c1530ec3c9 |  | pass | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBU-06-02 | QA - ASB-DBU-06-02 - Distribution Board Installation - ITC3
bd26e296-577b-441f-b3fb-0ddda73cea8a |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBN-06-03 | QA - ASB-DBN-06-03 - Distribution Board Installation - ITC3
e3dfbbc2-c6e6-496d-8847-f5f3dc1c0834 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 06 | ASB-DBS-06-03 | QA - ASB-DBS-06-03 - Distribution Board Installation - ITC3
e63433e6-eb6f-4833-9f3c-6de90d45e694 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBN-07-02 | QA - ASB-DBN-07-02 - Distribution Board Installation - ITC3
02500032-aef6-437e-8553-7cbbc194f467 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBN-07-03 | QA - ASB-DBN-07-03 - Distribution Board Installation - ITC3
d096e7fa-a4f5-4dea-80c3-648563e62e12 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBN-07-03H | QA - ASB-DBN-07-03H - Distribution Board Installation - ITC3
91d61252-d02d-4a78-9602-b3a8ea9dbe32 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBS-07-02 | QA - ASB-DBS-07-02 - Distribution Board Installation - ITC3
b2e72a4c-c728-47bd-8349-26d3516ddf29 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBS-07-03 | QA - ASB-DBS-07-03 - Distribution Board Installation - ITC3
a95270bc-f00a-405a-ba38-717c63925500 |  | not-started | ITC - (3) Main and Distribution Panels | checklist | FALSE | FALSE | Acute Services Building | Distribution Board | Level 07 | ASB-DBU-07-01 | QA - ASB-DBU-07-01 - Distribution Board Installation - ITC3