## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Exterior QA |  |  |  |  | Yes | Exterior QA | 016bc997-de79-4b28-bb5c-4d9415cb144b
checkpoint-status |  |  | checkpoint | Weatherline
checkpoint-status |  |  | checkpoint | Abodo/ timber cavity battens
boolean | 287664a0-8090-5215-b8b4-d122fa5caa5b |  | tickbox | Fixings at correct centres
boolean | 80ed95f2-efc6-510f-a49d-00b10d81ad2e |  | tickbox | Taping installed adaquately
boolean | 14350d16-71ba-5980-bce5-cbad389a42fd |  | tickbox | Vermin strip installed
checkpoint-status |  |  | checkpoint | Metal Cladding Aluminium cavity battens
boolean | bd75cb66-2779-5173-ad11-6a1be8289e3f |  | tickbox | Screws at correct centres
boolean | 41b9a89f-14c2-563c-ae8a-5a8c32909cc1 |  | tickbox | Appropriate sealants where necessary
checkpoint-status |  |  | checkpoint | James Hardie Exotec Jmoulds
boolean | 564783f8-bcbc-5423-8835-4050199bdc19 |  | tickbox | Installed to specification
checkpoint-status |  |  | checkpoint | Exotec fibre cement board install
boolean | 738ece5d-d547-5ada-abc8-68daff0bb0ca |  | tickbox | Substrate ready for install
boolean | fd11f6e6-236a-517a-8538-9e17e3839981 |  | tickbox | Correct fixing centres
checkpoint-status |  |  | checkpoint | Eterpan fibre cement soffit framing/ linings
boolean | 2cb6bc27-7793-585d-a4f5-2d55ad48def3 |  | tickbox | Substrate ready for install
boolean | 93622c8c-27cb-50c0-8b9a-53284212b8a9 |  | tickbox | Correct fixing centres
checkpoint-status |  |  | checkpoint | Internal doors
checkpoint-status |  |  | checkpoint | Skirtings
checkpoint-status |  |  | checkpoint | Architraves / Jamb liners
checklist-flat |  |  | checklist | Exterior QA Building B |  |  |  |  | Yes | Exterior QA Building B | a8a2b636-8bec-4afb-bb63-790783b10afc
checkpoint-status |  |  | checkpoint | Weatherline
checkpoint-status |  |  | checkpoint | Abodo/ timber cavity battens
boolean | 5f11bf95-988f-54bf-8b0e-02ff368de534 |  | tickbox | Fixings at correct centres
boolean | 4e471ec4-b3ea-5108-ae6b-da53f337dc56 |  | tickbox | Taping installed adequately
boolean | bba3f8e2-9953-5686-9ffe-11df85bb3d99 |  | tickbox | Vermin strip installed
checkpoint-status |  |  | checkpoint | Metal Cladding Aluminium cavity battens
boolean | 46ce7da3-5fbc-57ab-9ca8-cebea0501108 |  | tickbox | Screws at correct centres
boolean | 395f7c2d-1861-5cf7-b30e-9f4c442f22f8 |  | tickbox | Appropriate sealants where necessary
checkpoint-status |  |  | checkpoint | James Hardie Exotec Jmoulds
boolean | 9c985baf-2a1f-57e2-83e8-90e4f616e1ce |  | tickbox | Installed to specification
checkpoint-status |  |  | checkpoint | Exotec fibre cement board install
boolean | 424cfa1f-8025-5ca1-bf78-855d79959712 |  | tickbox | Substrate ready for install
boolean | 9eae7bae-41e1-5b12-82d1-63b8ed38c694 |  | tickbox | Correct fixing centres
checkpoint-status |  |  | checkpoint | Eterpan fibre cement soffit framing/ linings
boolean | 897eb88c-07c3-5ce2-9883-cb7b735ba4d0 |  | tickbox | Substrate ready for install
boolean | 21e87d8c-7a52-5bf6-90d5-82bdee3e9abe |  | tickbox | Correct fixing centres
checkpoint-status |  |  | checkpoint | Abodo cladding
checkpoint-status |  |  | checkpoint | Internal doors
checkpoint-status |  |  | checkpoint | Skirtings
checkpoint-status |  |  | checkpoint | Architraves / Jamb liners
checklist-flat |  |  | checklist | QA - Alberton |  |  |  |  | Yes | QA - Alberton | cdf975b4-548f-4952-be50-fa819d6fd93a
checkpoint-status |  |  | checkpoint | Substrate ready to start work
checkpoint-status |  |  | checkpoint | Mid floor framing
checkpoint-status |  |  | checkpoint | Mid floor stringer bolt fixing
checkpoint-status |  |  | checkpoint | Mid floor joist hangers
checkpoint-status |  |  | checkpoint | Mid floor double joist nail plates (Top & Bottom)
checkpoint-status |  |  | checkpoint | Strap brace around PFC beam (Front & back)
checkpoint-status |  |  | checkpoint | Plywood mid floor
checkpoint-status |  |  | checkpoint | Plywood fixing
checkpoint-status |  |  | checkpoint | Front and back framing
checkpoint-status |  |  | checkpoint | Roof framing
checkpoint-status |  |  | checkpoint | Roof framing stringer bolt fixing
checkpoint-status |  |  | checkpoint | Roof framing joist hanger
checkpoint-status |  |  | checkpoint | Pfc beam packing front and back (ground)
checkpoint-status |  |  | checkpoint | Wall framing front and back (ground)
checkpoint-status |  |  | checkpoint | Straping ground floor and level 1
checkpoint-status |  |  | checkpoint | Internal walls ground floor and level 1
checkpoint-status |  |  | checkpoint | Weatherline
checkpoint-status |  |  | checkpoint | Internal doors
checkpoint-status |  |  | checkpoint | Skirtings
checkpoint-status |  |  | checkpoint | Architraves / Jamb liners
checklist-flat |  |  | checklist | QA - Alberton |  |  |  |  | Yes | SYS - QA - Alberton V0 | e9cf81e7-8875-41b8-b041-3b6087d9052b
checkpoint-status |  |  | checkpoint | Mid floor framing
checkpoint-status |  |  | checkpoint | Mid floor stringer bolt fixing
checkpoint-status |  |  | checkpoint | Mid floor joist hangers
checkpoint-status |  |  | checkpoint | Mid floor double joist nail plates (Top & Bottom)
checkpoint-status |  |  | checkpoint | Strap brace around PFC beam (Front & back)
checkpoint-status |  |  | checkpoint | Plywood mid floor
checkpoint-status |  |  | checkpoint | Plywood fixing
checkpoint-status |  |  | checkpoint | Front and back framing
checkpoint-status |  |  | checkpoint | Roof framing
checkpoint-status |  |  | checkpoint | Roof framing stringer bolt fixing
checkpoint-status |  |  | checkpoint | Roof framing joist hanger
checkpoint-status |  |  | checkpoint | Pfc beam packing front and back (ground)
checkpoint-status |  |  | checkpoint | Wall framing front and back (ground)
checkpoint-status |  |  | checkpoint | Straping ground floor and level 1
checkpoint-status |  |  | checkpoint | Internal walls ground floor and level 1
checkpoint-status |  |  | checkpoint | Weatherline
checkpoint-status |  |  | checkpoint | Internal doors
checkpoint-status |  |  | checkpoint | Skirtings
checkpoint-status |  |  | checkpoint | Architraves / Jamb liners
checklist-flat |  |  | checklist | Level 2 Checklist |  |  |  |  | Yes | Level 2 Checklist | e9f3679e-a600-4832-8c90-2ac9aa242020
checkpoint-status |  |  | checkpoint | Level 2 Mid floor Framing
checkpoint-status |  |  | checkpoint | Level 2 Joist Hangers
checkpoint-status |  |  | checkpoint | Level 2 Mid floor Stringer Bolt Fixings
checkpoint-status |  |  | checkpoint | Level 2 Nailon Plates
checkpoint-status |  |  | checkpoint | Level 2 Mid floor Plywood
checkpoint-status |  |  | checkpoint | Level 2 Ply wood Fixing
checkpoint-status |  |  | checkpoint | Level 2 Internal Framing
checkpoint-status |  |  | checkpoint | Stair Fixings
checkpoint-status |  |  | checkpoint | Internal doors
checkpoint-status |  |  | checkpoint | Skirtings
checkpoint-status |  |  | checkpoint | Architraves / Jamb liners