## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A174 - Manildra - ITC 001 (ITP001) - B341 Demolition Works and Rock Platform Preparation | [5 empty] | A174 - Manildra - ITC 001 (ITP001) - B341 Demolition Works and Rock Platform Preparation
checkpoint | A - Safety Review
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted
label | • Required Safe Work method statement completed and signed
label | • Subcontractors’ safety plan/procedure approved
label | Inspection by who – SIGN: ACPL / S
text | INSPECTION:
checkpoint | B - Environment
label | REQUIREMENTS / REFERENCE:
label | • Project Enviro Plan
label | • R44 CL1.7
label | ACCEPTANCE CRITERIA:
label | • Sediment controls installed as per EMP and Sediment Control Plan
label | • Ensure surface runoff is mitigated
label | Inspection by who – SIGN: ACPL / S
text | INSPECTION:
checkpoint | 1 - Designers’ safety report
label | REQUIREMENTS / REFERENCE: B341 CL3.1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • Prior to commencement of demolition, submit a report of results of preliminary investigation and demolition designer’s safety report if any conditions of Clause 3.1.4 are applicable
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Demolition Plan
label | REQUIREMENTS / REFERENCE: B341 CL3.5.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • 5 working days prior commencement of demolition, submit the demolition plans including items listed in annexure B341/D.
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Service location
label | REQUIREMENTS / REFERENCE: G1.21.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • Prior to commencing any temporary works at Manildra bridge, locate and document all existing public utilities and physically mark locations on the ground
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Scour protection
label | REQUIREMENTS / REFERENCE: G1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • Details regarding the properties and source of the rip rap rock to be submitted.
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Final survey report
label | REQUIREMENTS / REFERENCE: B341.8.1
label | ACCEPTANCE CRITERIA:
label | • Submit to RMS survey report after removal of working platform to verify that all substructure members have been removed to the specified depths.
label | Inspection by who – SIGN: ACPL / S
text | INSPECTION:
label | COMMENTS / ATTACHMENTS / RECORDS:
label | • Survey report
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature