## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A174 - Manildra - ITC 004 (ITP004) - Erection of Pre-Tensioned Precast Bridge Members (B150) | [5 empty] | A174 - Manildra - ITC 004 (ITP004) - Erection of Pre-Tensioned Precast Bridge Members (B150)
checkpoint | 1 - Safety Review
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environment and cultural)
label | • Subcontractor’s safety plan/procedure approved
label | FREQUENCY: Prior to work commencing
text | INSPECTION:
checkpoint | 2 - Environment
label | REQUIREMENTS / REFERENCE:
label | • Project Environment Plan
label | • G36 CL 3.1
label | ACCEPTANCE CRITERIA:
label | • Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP
label | • Identify and install appropriate warning signage at Environmental No-go zones.
label | FREQUENCY: Prior to work commencing
text | INSPECTION:
checkpoint | 3 - Pre-Erection Requirements (1)
label | REQUIREMENTS / REFERENCE: B150.4.1
label | ACCEPTANCE CRITERIA:
label | • Prior to bringing any lifting equipment or plant to the Site provide drawings and calculations certified by a Chartered Professional Engineer with membership of Engineers Australia practicing in the field of geotechnical engineering (or equivalent) of any working platforms or supports required to keep the crane stable and safe during lifting operations at the site.
label | • HOLD POINT:
label | • Submit to the Principal for acceptance details of the of the proposed lifting equipment and method together with certification, including calculations, by a Chartered Professional Engineer with membership of Engineers Australia practicing in the field of geotechnical engineering (or equivalent) that under the proposed set up and site conditions, the equipment nominated will be used within its safe working capacities.
label | FREQUENCY: Prior to work commencing
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
label | COMMENTS / ATTACHMENTS / RECORDS:
label | • Relevant drawings and calculations
holdpoint | HOLD POINT
checkpoint | 3 - Pre-Erection Requirements (2)
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • Submit a certificate from an Engineer, certifying the structural adequacy and compliance of the proposed method of erection (including all supporting and bracing measures) and the falsework with any applicable regulations, Australian Standards, this Specification and relevant design requirements. The certificate shall be accompanied by any drawings necessary to clearly describe the proposed method of erection including detailed drawings of any supporting and bracing measures.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Conformity of Structural Members
label | REQUIREMENTS / REFERENCE: B150.4.2
label | ACCEPTANCE CRITERIA:
label | • Do not erect any member until:
label | (a) Full conformity records for that member have been made available to the Principal;
label | (b) The concrete in the supporting members has attained at least 80% of the specified strength, and
label | (c) The supporting framework for these members has been removed, unless specified otherwise on the Drawings.
text | INSPECTION:
label | COMMENTS / ATTACHMENTS / RECORDS:
label | • Conformity records
checkpoint | 5 - Pre-Alignment
label | REQUIREMENTS / REFERENCE: B150.4.3
label | ACCEPTANCE CRITERIA:
label | • At least one working day prior to erection, submit a certificate verifying that the location and levels of all permanent and temporary supports are in accordance with the profile shown on the Drawings.
text | INSPECTION:
label | COMMENTS / ATTACHMENTS / RECORDS:
label | • Pre-alignment survey
checkpoint | 6 - Joint Survey (1)
label | REQUIREMENTS / REFERENCE:
label | • B150.4.3
label | • G71
label | ACCEPTANCE CRITERIA:
label | • Apply the requirements in RMS G71 for Joint survey to the verification of locations and levels of all permanent and temporary supports and the certification must conform to the requirements of RMS G71 for Product Conformity Survey
label | • HOLD POINT:
label | • G71 Notification of Joint Survey of permanent and temporary supports for girder bridges
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Joint Survey (1)
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • G71 Submission of survey report for permanent and temporary supports for girder bridges
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Erection
label | REQUIREMENTS / REFERENCE:
label | • B150.6.1
label | • B150.6.2
label | ACCEPTANCE CRITERIA:
label | • The erection operation must be supervised by an Engineer
label | • Ensure that:
label | (a) Each member is placed in position safely, without damage to the member or the structure; and
label | (b) The intended permanent structural action of the member is not:
label | ○ (i) Restrained; or otherwise
label | ○ (ii) Adversely affected by the process of erection or by movements which occur due to environmental or construction-related forces, Before the member is finally integrated with the adjacent parts of the structure.
label | • Lift members only by the devices specified on the Drawings, unless approved otherwise by the Principal. The angle of the lifting sling must be specified at all times.
label | • The mass of super T’s must be within the safe capacity of the equipment, as certified by an Engineer.
text | INSPECTION:
checkpoint | 8 - Profile Diagram
label | REQUIREMENTS / REFERENCE: B150.8
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • G71 Submission of Profile Diagram for girder bridges.
label | • Before placing of the cast-in-place concrete, submit a diagram that sets out the profile of the completed member(s) in relation to the profile specified on the Drawings. For girder bridges this diagram must conform to the requirements of Specification RMS G71 for Product Conformity Survey and apply the associated Hold Point.
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Removal of Temporary Works
label | REQUIREMENTS / REFERENCE: B150.9
label | ACCEPTANCE CRITERIA:
label | • Unless agreed otherwise by the Principal, remove all inserts and fixtures used solely for lifting or installation, temporary supports, packers, falsework and temporary bracing and carry out any repairs due to the use of such temporary works using suitable cementitious patching material to the specified finish as the Works proceed.
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature