## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A174 - Manildra - ITC 005 (ITP005) - Manufacture and Installation of Bridge Bearings (B284) | [5 empty] | A174 - Manildra - ITC 005 (ITP005) - Manufacture and Installation of Bridge Bearings (B284)
checkpoint | A - Safety Review
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environmental and cultural)
label | • Required Safe Work method statement completed and signed
label | • Subcontractors safety plan/procedure approved
text | INSPECTION:
checkpoint | B - Environment
label | REQUIREMENTS / REFERENCE:
label | • Project Environ Plan
label | • R44 CL1.7
label | ACCEPTANCE CRITERIA:
label | • Ensure controls in place around the grout mixer prior to commencing mixing works
text | INSPECTION:
checkpoint | 1 - Material
label | REQUIREMENTS / REFERENCE: B284 cl 2
label | ACCEPTANCE CRITERIA:
label | • 2 sets of 3 cubes per abutment and 4 sets of 3 cubes for headstocks for testing of grout used to construct the pads.
text | INSPECTION:
checkpoint | 2 - Construction of pad
label | REQUIREMENTS / REFERENCE: B284 cl 4.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • Submit to principal details of materials and procedures for construction of mortar pads and (if applicable) manufacturer’s recommendations for surface preparation, bonding, placement and curing of the mortar pad material.
label | • Certificate must also verify that the location and level of all permanent and temporary supports comply with the Drawings
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Setout of bearing pads and fixing of bearings
label | REQUIREMENTS / REFERENCE: B284 Cl 5.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • Submit a certificate from an engineer confirming the that the proposed method of installation complies with the specification and drawings.
label | • Certificate to include a survey report verifying that the position and level of all temporary supports are in accordance.
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Test for drumminess
label | REQUIREMENTS / REFERENCE: B284 Cl 4.4
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT:
label | • For each constructed pad do not transfer loads onto bearings until the pads have been successfully tested for drumminess.
label | • Notify RMS of the time and date for drumminess test of each completed grout pad after the grout has developed its specified design strength and formwork has been removed at least on working day prior to conducting test.
label | Inspection by who – SIGN: ACPL / W
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 6 - Tolerances
label | REQUIREMENTS / REFERENCE:
label | • B284 cl 6.1.1 and Cl 6.1.2
label | ACCEPTANCE CRITERIA:
label | • For plain elastomeric strips and pads or laminated elastomeric bearings, the tolerances in Table B284.1 apply.
text | INSPECTION:
checkpoint | 7 - Testing and Compliance
label | REQUIREMENTS / REFERENCE: B281 cl 2.2
label | ACCEPTANCE CRITERIA:
label | • Provide evidence to principal to verify the elastomer used in manufacture of strips has been tested in a laboratory with appropriate NATA registration, and that it complies with AS5100.4
label | • Test the bearing in accordance with AS5100.4 using equipment and personnel with NATA registration
label | • Testing equipment to be capable of measuring to an accuracy of +/-3% or better for compressive and shear loads, and +/-1% or better for deflection. Test temperature must be between 15 and 30 degrees.
label | • Reject bearings represented by sample tested which have compressive stiffness exceeding +-15% of the mean compressive stiffness of the samples.
label | • Test each strip sample in shear in accordance with AS5100.4, reject strips represented by sample tested which have shear stiffness exceeding a tolerance of +-20% of the shear stiffness given in Appendix A of AS5100.4
label | Inspection by who – SIGN: ACPL / S
text | INSPECTION:
label | COMMENTS / ATTACHMENTS / RECORDS:
label | • Material compliance, testing and certification documents
checkpoint | 8 - Bearing test report
label | REQUIREMENTS / REFERENCE: B281 cl2.2
label | ACCEPTANCE CRITERIA:
label | • Provide a report to the Principal verifying that all bearings conform to the requirements of the specification B281. The report must include a summary of all test results with clear identification of the bearings tested. Reject all non-conforming bearings
label | • A bearing is considered conforming, if it does not exhibit any sign of damage. During and after the tests described in clauses 4.4 and 4.5 of B281, all bearings to be observed and reported for any visible fault or damage including
label | a. Tearing of elastomer or splitting between elastomer and steel plates
label | b. Permanent deformations
label | c. Significant irregular or unsymmetrical surface bulging.
label | Inspection by who – SIGN:
text | INSPECTION:
label | COMMENTS / ATTACHMENTS / RECORDS:
label | • Bearing test report
checkpoint | 9 - Delivery of bearings to site
label | REQUIREMENTS / REFERENCE: B281 CL5.2
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT:
label | • Protect bearings from dust, moisture and damage until their installation.
label | • Submit to principal elastomer conformity evidence (Clause 2.2.2) bearings report (clause 4.7) and traceability documentation (clause 5.1) at least five working days before the proposed date of delivery of bearings to the site.
label | Inspection by who – SIGN: ACPL / H
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Certification
label | REQUIREMENTS / REFERENCE: B284 cl 6.3
label | ACCEPTANCE CRITERIA:
label | • After installation of the bearings and removal of temporary supports submit a certificate from an engineer stating that the bearing installation , including their final positions and levels, complies with the specification B284 and the drawings.
text | INSPECTION:
label | COMMENTS / ATTACHMENTS / RECORDS:
label | • Certificate of compliance for bearing installation
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature