## Resources
type | name
checklist | 1. Standard
section | Precast Element Details
checkpoint | Concrete Details Complete
textbox | Concrete Volume
textbox | Concrete Strength
textbox | Enter Drawing Revision Number
textbox | Cast Date
section | Reinforcing Yard Checks (Reo QA)
checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint | Cut and bent bars checked off against detail sheet
checkpoint | Perimeter bars and spacing marks confirmed
checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
section | Formwork Set Up Checks (Tables QA)
checkpoint | Sides Straight & Magnets Fastened
checkpoint | Mould Face Clean
checkpoint | Length/Width/Thickness/Cutouts
checkpoint | Edge Details & Rebates
checkpoint | MF Weld plates in correct location and siliconed to table
section | Prepour Checks (Tables QA)
checkpoint | Main Reinforcing
checkpoint | Starters
checkpoint | Stirrups
checkpoint | Lifters
checkpoint | Mould Cleaned & Oiled
checkpoint | Tie wire Trimmed
checkpoint | General Photos Attached
checkpoint | Concrete Docket Attached
checkpoint | Shop Drawing Checked Off (attach photo)
section | Post Pour (Table Supervisor)
checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint | Face lifters placed in correct location
checkpoint | Roughening Lines Correct
checkpoint | Curing compound sprayed
section | Demould Inspection (Yard QA)
checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint | Stitch joints have been jet washed
checkpoint | MF roughening's jet washed
checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint | Grade 500 starters are straight
checkpoint | NF Quality acceptable (attach photo)
checkpoint | MF Quality acceptable (attach photo)
checkpoint | Structural repairs required (if yes photograph before)
checkpoint | Shop drawing checked off
section | Overall Panel Quality (Yard QA)
checkpoint | Overall Panel Quality Ratings Recorded Below
note | The higher the number the better the quality
note | e.g. "1" is unacceptable
button | Vibrating Quality
button | Trowelling Quality
button | Silicone Quality
button | Chamfer Quality
button | MF Quality
section | Loading Out (Yard QA)
checkpoint | Load Docket Given to Driver
checkpoint | Photo take of Panel on Truck
checkpoint | No remedial work required on site
section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint | Upload reinforcing detail sheets
checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint | Upload Concrete test results