## Breakdown
Keith Park - Watertight | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5
| QA | Stage 7
B07
Saranfil
Ground Level
Apartments
[7 empty] | G40 | Prepopulate | ST - S - Sarnafil
[7 empty] | G41 | Prepopulate | ST - S - Sarnafil
[7 empty] | G42 | Prepopulate | ST - S - Sarnafil
[7 empty] | G42 | Prepopulate | ST - S - Sarnafil
[7 empty] | G44 | Prepopulate | ST - S - Sarnafil
[7 empty] | G45 | Prepopulate | ST - S - Sarnafil
[7 empty] | G46 | Prepopulate | ST - S - Sarnafil
[7 empty] | G47 | Prepopulate | ST - S - Sarnafil
Common areas
[7 empty] | Grid A 3-4 | Prepopulate | ST - S - Sarnafil
[7 empty] | Grid C - E | Prepopulate | ST - S - Sarnafil
[7 empty] | Grid D - E | Prepopulate | ST - S - Sarnafil
[7 empty] | Grid G 3-4 | Prepopulate | ST - S - Sarnafil
[7 empty] | Slab Area B | Prepopulate | ST - S - Sarnafil
Panel Sealant (Joints)
[5 empty] | Basement | pre-populate | F - S - Precast Fire Joint Sealant
[5 empty] | Ground Level | pre-populate | F - S - Precast Fire Joint Sealant
[5 empty] | Level 1 | pre-populate | F - S - Precast Fire Joint Sealant
[5 empty] | Level 2 | pre-populate | F - S - Precast Fire Joint Sealant
[5 empty] | Level 3 | pre-populate | F - S - Precast Fire Joint Sealant
[5 empty] | Level 4 | pre-populate | F - S - Precast Fire Joint Sealant
|  |  | Completion Docs |  |  |  |  | Pre-populate | CST - S - Completion Documents

## Checklist
Checklist | ST - S - Sarnafil
section | Sarnafil perimeter
checkpoint | Area clean and accessible
checkpoint | Concrete Ground
checkpoint | Edges Bevelled
checkpoint | Concrete in acceptable condition
input | last 6 digits of batch number
checkpoint | RAB boards installed
checkpoint | Sikalastic 152 applied
checkpoint | Area left tidy and accessible, and signed off
section | Sarnafil Decks
checkpoint | Area clean and accessible
checkpoint | Concrete Screeded
checkpoint | Correct Falls
checkpoint | Sarnafils drops installed
checkpoint | Ring clamps on site
checkpoint | All openings electronically checked
checkpoint | Deck protected
checkpoint | Area left tidy and accessible, and signed off
section | Electronic Testing
checkpoint | Area on site testing
checkpoint | Electronic tested
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | F - S - Precast Fire Joint Sealant
checkpoint | Details
text | Date:
text | Area:
text | Installer:
text | Weather Conditions:
text | Sika Specification (if any)
text | Joint dimensions width x depth
checkpoint | Substrate
checkpoint | Sika products used last 6 digits of Batch number
checkpoint | Method of substrate preparation (e.g.. grinding, abrading, drying etc
checkpoint | Sika cleaner / primer used
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
` | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS