## ITP Cover Page
Rain Garden Inspection and Test Plan
Project: Peacocke Whatukooruru Drive Stage 2A
Number and Revision: DN1205 - 119 - Rev B
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive Stage 2A |  |  |  |  | ITP Number: |  |  | 119
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Rain Garden |  |  |  |  | Revision: | 1000 |  | B
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A-2195 REV7, 2151-2152 REV7, 3155 REV 4
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification, Appendices and GWS
Quality Specified: |  |  | TNZ F/5
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
B | Draft for Approval | 2024-03-19 | [7 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)
Note on A8: Callun Purchase:

## ITP Master Body
|  |  |  | Stormwater Treatment Device | Inspection and test plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Methodology and ITP to be submitted to the Engineer and approved prior to works beginning | Downer | Construction Pack | Submit 10 days prior to commencement of works | HP | ENG
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | TopoGraphic Surveys for measurement | The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities. | PS 2.2.12 | As-built | Prior to works and Post works | H | PE
3.01.07 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Earthworks Materials
4.01.01 | Re-Use Suitability Approval | The Contractor shall test representative samples of the site-won material to be used as Bulk Fill, the results are to be sent to the Engineer for approval. | GWS 2.4.2.1 | MDD, OMC, Shear Vane, PSD | At least 2 days prior to placement and compaction. | HP | ENG
4.02 | Subsoil Drainage
4.02.01 | Subsoil Pipes | Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer. | GWS 3.2.1 | Datasheet | Prior to installation | C | SE
4.02.02 | Subsoil Drainage Aggregate | When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max) | GWS 3.2.2 & 3.4 | PSD, CR | Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required. | C | SE
4.02.03 | Filter Cloth | Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. | GWS 3.2.3 | Datasheet | Every Delivery to site | C | SE
4.03 | Rain Garden Materials
4.01.01 | GCL Liner | GCL to be meet or exceed the test values of Bentosure NW4000. | Project Sechedule | Technical Datasheet | Atleast 2 days prior to placement | HP | ENG
4.01.02 | Geotextile | NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used to wrap 20/40 drainage aggregate. Confirm before placement | GWS 3.2.3 | Technical Datasheet Delivery Dockets or photos | Before placement | C | SE
4.01.03 | Drainage Aggregate | Drainage aggregate should be taken to the underside of the next layer. Drainage Aggregate should be deep washed and in accordance with TNZ F/6 including gradings (40/20 aggregate). Open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max) | GWS 3.2.2 & 3.4 | PSD, CR | Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required. | C | SE
4.01.04 | Pipes and fittings | Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 110 mm diameter Class 200 complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer. | GWS 3.2.1 | Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class | Before placement | C | SE
4.01.05 | Filter Media | Filter/ Planting Media must follow the specification as per RITS 4.2.19. Seen below. ∙ Minimum depth of 500mm ∙ Saturated Hydraulic Conductivity: 50 to 300mm hr-^1 ∙ Plant Available water: 100mm ∙ Organic matter: 10% - 30% by volume ∙ pH range 6.5 – 7.5 + ∙ Electrical Conductivity: < 2.5 dS m-^1 ∙Total Nitrogen: < 1,000 mg kg-1 ∙Total Phosphorus: Leachate testing required if > 100 mg kg-^1 ∙Total Copper: ≤ 80 mg kg-^1 ∙Total Zinc: ≤ 200 mg kg-^1 ∙Media sources: From a clean source (no waste Products) | RITS 4.2.19 | Verifying documents Dockets | Every Delivery to Site | C | SE
4.01.06 | Scour Protection/RipRap |  | BBO | Verifying document to be copy of delivery dockets, photos of mix | Every Rain Garden | C | SE | D50 = Gap 65 Riprap 200Mm Surrounding Manhole And 150Mm Deep
4.01.07 | Coconut (Coir) Matting | Biodegradable Erosion Mat (Coir Mat). Biodegradable mulching fabric 450 gsm | DWG 2195 REV1. Schedule SP2 4.3.7 | Verifying document to be copy of delivery dockets, photos of mat onsite | Every Delievery to Site | C | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Ponds General
5.01.01 | Clearing | All surface objects including fences, gates, debris, wood, dumped rubbish, concrete and other protruding obstructions shall be cleared and disposed of | PS 3.1 | Site Records | Prior to earthworks | C | SE
5.01.02 | Plant Clearance | Vegetation, Tree stumps, shrubs, plants, logs, including any roots greater than 25mm in diameter shall be cleared and disposed of | GWS 2.5 | Site Records | Prior to earthworks | C | SE
5.02 | Earthworks General
5.02.01 | Groundwater Management | The Contractor shall provide all pumping plant and drainage systems required to ensure excavations are always free from water. | PS 3.4 | Correspondence | Prior to excavation | W | SE
5.02.02 | Cut to Waste Approval | The Contractor shall obtain written approval from the Engineer prior to cutting any material to waste. To include evidence and extents of cut to waste. Topography survey data of all material to leave site, photographs of material and any material test reports. | GWS 2.4.3 | Correspondence/Photos/Survey | Prior to cut to waste | HP | ENG
5.02.03 | Foundation Suitability | The foundation on which filling is to be placed must be observed by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient. | GWS 2.7 | Site Record | Prior to the placement of any filling | HP | ENG
5.02.04 | Unsuitable ground | Unsuitable ground shall be defined as any pre-existing uncertified filling or natural silts/clays having an undrained shear strength of less than 70kPa or natural sands having less than 3 blows per 100mm penetration when tested with a Scala penetrometer. The contractor shall obtain instruction from Engineer around extent and depth of undercut. | GWS 2.7 | Shear Vane / Scala penetrometer | Prior to the placement of any filling | I | SE
5.02.05 | Preparation for Filling | Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal). | GWS 2.9.2 | Site Record | Prior to placement and compaction of fill | I | SE
5.03 | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
5.03.01 | Compaction Testing | Bulk fill shall be tested by DT at 300mm probe depth 95% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. | GWS 2.9.4 | Test Results | 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x DT within a 3m radius) | R | SE/ENG
5.03.02 | Scala Penetrometer Testing | Bulk fill shall be tested by Scala Penetrometer every 500m3 to: 4 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. | GWS 2.9.4 | Test Results | 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius) | R | SE/ENG
5.04 | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
5.04.01 | Vane Shear Strength Testing | Bulk fill shall be tested for Vane Shear Strength to: Minimum average 120kPa over 10 tests, minimum single value 110kPa. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm. | GWS 2.9.4 | Test Results | 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius) | R | SE
5.04.02 | Air Voids Testing | Bulk fill shall be tested for Air Voids to: Maximum average 10% over 10 tests, maximum single value 12%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm. | GWS 2.9.4 | Test Results | 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius) | R | SE
5.05 | Finish level
5.01.01 | Pre Topsoil Levels | Shaped surface (pre topsoil) in forebays meets design RLs. Sloped areas must conform to the desiged grades. |  | AsBuilt Data / PDF | Every Pond | HP | ENG
5.01.03 | Topsoil thickness | Topsoil thickness must meet minimum requirements. Planted areas must have a minimum topsoil thickness of 300mm. Non planted areas must have a minimum thickness of 100mm. |  | Photos | Every Pond | HP | ENG
5.01.03 | Topsoil Finished Levels | Top soil meets finished level RL's in forebays. Sloped Areas must conform to the desiged grade. |  | AsBuilt Data / PDF | Every Pond | HP | ENG
5.06 | Rain gardens
5.06.01 | Set-out | Check set-out prior to excavation of Rain Garden. | PS - 2.2.12 | Hold Point Release | Min 48h Notice | H | SUP
5.06.02 | Excavation | Excavations shall be completed in such manner that it is true to the drawings will allow novacoil to be laid true to the depths, grades and lines. | Downer | Survey Data, Photos | Prior to laying filter cloth | H | SV
5.06.03 | GCL liner | GCL liner overlaps must welded. Installation, anchoring and pipe penetrations according to manufacterers spec. Extent of GCL liner must conform with the design. | Manufacturers Guidelines 18.2 | Site Photos | Prior to backfill | I | SE
5.06.04 | GCL Repair | GCL to be repaired as per manufacture's guidelnes (Bentofix PVB5100c). GCL becomes damaged, torn or punctured during installation, the affected area should be repaired. For damaged areas, a separate piece of GCL shall be used and extend past the comprimised section by 500mm in every direction. Bentonite shall be used to connect the seperate GCL to the main liner. | Manufacturers Guidelines 21 | Site Photos | Prior to backfill | I | SE
5.06.05 | GCL Inspection | GCL to be installed as per manufacturers guide and true to the drawings.The inspection should include overlaps, alignments, penetrations, connections, detections of any defects, including installation damage. Detected falsely installed areas shall be marked, repaired and the repairs shall be inspected and approved engineer. | Manufacturers Guidelines 22.2 | Site Photos | Prior to backfill | HP | ENG
5.06.06 | Geotextile Installation | All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. | GWS 3.2.3 | Site Photos | Prior to aggregate placement | I | SE
5.06.07 | Geotextile Inspection | Before placement of any geotextile should form an Engineers inspection hold point | PS 2.2.16 | Site Records | Min 48h Notice | HP | ENG
5.06.08 | Bedding | TNZ F/5 - Bedding thickness shall be no less than 100mm | TNZ F/5 | Photos, Sruvey Data | Prior to laying Novacoil | I | SE
5.06.09 | Joining Pipes | TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations | TNZ F/5 | Copy of delivery dockets, photos of joins onsite with tag showing class | Every join | I | SE
5.06.10 | Pipe Grade | Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (Minimum grade of 0.5%) unless stated otherwise. | TNZ F/5 | AsBuilt | Every 10m | H | SV
5.06.11 | Pipe Cover | Pipe to have 100mm of drainage aggregate as top cover for pipe. | N/A | Site Photos | Every 10m | H | SV
5.06.12 | Filter Media | Filter media to be placed at a constant average thickness of 500mm, refer to drawing for detail. Filter media should be free of peaks and troughs. | N/A | Site Photos | Every Rain Garden | I | SE
5.06.13 | Coconut Matting | Mat shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. | GWS 3.2.3 | Site Photos | Every Rain Garden | I | SE
5.06.14 | Scour Protection GAP 65 Rip Rap | Scour protection shall be installed as per drawings around let downs, scruffy dome and the flush point end. | GWS 3.6 & BBO | Site Photos/ Survey Data | Every Rain Garden | I | SE
5.07 | Subsoils
5.07.01 | Filter Cloth Wrap Inspection | Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line. | GWS 3.2.2 | Every line | Photos of trench prior to backfill | HP | ENG
5.07.02 | Trench Backfill | Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied. | GWS 3.3 | Site Record | Each trench | I | SE
5.07.03 | Subsoil Flushing | On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer. | GWS 3.6 | Site Records | On completion of earthworks | HP | ENG
5.07.04 | Survey | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
5.07.05 | Excavation | Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings | Downer | Records | Prior to laying filter cloth | I | SE
5.07.06 | Bedding | TNZ F/5 - Bedding thickness shall be no less than 100mm | TNZ F/5 | Records | Prior to laying Novacoil | I | SE
5.07.07 | Joining Pipes | TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations | TNZ F/5 | Copy of delivery dockets, photos of pipes onsite with tag showing class | Every join | I | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
6.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level | Downer | Records | As-builts taken every 10m prior to backfill | H | SV
6.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations | Downer | Redlines | Post construction | H | PE
6.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE
6.01.05 | Photos | Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill. | Downer | Photo Records | Post construction | H | SE