## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 119 - Stormwater Treatment Device | itp |  |  |  |  | ITP - 119 - Stormwater Treatment Device Rev B
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - TopoGraphic Surveys for measurement
label | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
label | Standard / Specification - PS 2.2.12
label | Verifying Document - As-built
label | Frequency - Prior to works and Post works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.07 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Re-Use Suitability Approval
label | Acceptance / Conformance Criteria - The Contractor shall test representative samples of the site-won material to be used as Bulk Fill, the results are to be sent to the Engineer for approval.
label | Standard / Specification - GWS 2.4.2.1
label | Verifying Document - MDD, OMC, Shear Vane, PSD
label | Frequency - At least 2 days prior to placement and compaction.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02.01 - Subsoil Pipes
label | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | Standard / Specification - GWS 3.2.1
label | Verifying Document - Datasheet
label | Frequency - Prior to installation
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.02.02 - Subsoil Drainage Aggregate
label | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
label | ○ App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
label | – – – – – – – – – – – – – – –
label | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
label | Test Sieve Aperture (mm) ¦¦ Percentage Passing (%)
label | 53 ¦¦ 100
label | 13.2 ¦¦ 10 (max)
label | – – – – – – – – – – – – – – –
label | Standard / Specification - GWS 3.2.2 & 3.4
label | Verifying Document - PSD, CR
label | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.02.03 - Filter Cloth
label | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings.
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Datasheet
label | Frequency - Every Delivery to site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.01 - GCL Liner
label | Acceptance / Conformance Criteria - GCL to be meet or exceed the test values of Bentosure NW4000.
label | Standard / Specification - Project Sechedule
label | Verifying Document - Technical Datasheet
label | Frequency - Atleast 2 days prior to placement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.02 - Geotextile
label | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used to wrap 20/40 drainage aggregate. Confirm before placement
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Technical Datasheet Delivery Dockets or photos
label | Frequency - Before placement
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Drainage Aggregate
label | Acceptance / Conformance Criteria - Drainage aggregate should be taken to the underside of the next layer. Drainage Aggregate should be deep washed and in accordance with TNZ F/6 including gradings (40/20 aggregate). Open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
label | ○ App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
label | – – – – – – – – – – – – – – –
label | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
label | Test Sieve Aperture (mm) ¦¦ Percentage Passing (%)
label | 53 ¦¦ 100
label | 13.2 ¦¦ 10 (max)
label | – – – – – – – – – – – – – – –
label | Standard / Specification - GWS 3.2.2 & 3.4
label | Verifying Document - PSD, CR
label | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.04 - Pipes and fittings
label | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 110 mm diameter Class 200 complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | Standard / Specification - GWS 3.2.1
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | Frequency - Before placement
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.05 - Filter Media
label | Acceptance / Conformance Criteria - Filter/ Planting Media must follow the specification as per RITS 4.2.19. Seen below.
label | ○ Minimum depth of 500mm
label | ○ Saturated Hydraulic Conductivity: 50 to 300mm hr-^1
label | ○ Plant Available water: 100mm
label | ○ Organic matter: 10% - 30% by volume
label | ○ pH range 6.5 – 7.5 +
label | ○ Electrical Conductivity: < 2.5 dS m-^1
label | ○ Total Nitrogen: < 1,000 mg kg-1
label | ○ Total Phosphorus: Leachate testing required if > 100 mg kg-^1
label | ○ Total Copper: ≤ 80 mg kg-^1
label | ○ Total Zinc: ≤ 200 mg kg-^1
label | ○ Media sources: From a clean source (no waste Products)
label | Standard / Specification - RITS 4.2.19
label | Verifying Document - Verifying documents Dockets
label | Frequency - Every Delivery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.06 - Scour Protection/RipRap
label | Acceptance / Conformance Criteria -
label | Standard / Specification - BBO
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of mix
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.07 - Coconut (Coir) Matting
label | Acceptance / Conformance Criteria - Biodegradable Erosion
label | ○ Mat (Coir Mat). Biodegradable mulching fabric 450 gsm
label | Standard / Specification - DWG 2195 REV1. Schedule SP2 4.3.7
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of mat onsite
label | Frequency - Every Delievery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Clearing
label | Acceptance / Conformance Criteria - All surface objects including fences, gates, debris, wood, dumped rubbish, concrete and other protruding obstructions shall be cleared and disposed of
label | Standard / Specification - PS 3.1
label | Verifying Document - Site Records
label | Frequency - Prior to earthworks
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.01.02 - Plant Clearance
label | Acceptance / Conformance Criteria - Vegetation, Tree stumps, shrubs, plants, logs, including any roots greater than 25mm in diameter shall be cleared and disposed of
label | Standard / Specification - GWS 2.5
label | Verifying Document - Site Records
label | Frequency - Prior to earthworks
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 5.02.01 - Groundwater Management
label | Acceptance / Conformance Criteria - The Contractor shall provide all pumping plant and drainage systems required to ensure excavations are always free from water.
label | Standard / Specification - PS 3.4
label | Verifying Document - Correspondence
label | Frequency - Prior to excavation
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 5.02.02 - Cut to Waste Approval
label | Acceptance / Conformance Criteria - The Contractor shall obtain written approval from the Engineer prior to cutting any material to waste. To include evidence and extents of cut to waste. Topography survey data of all material to leave site, photographs of material and any material test reports.
label | Standard / Specification - GWS 2.4.3
label | Verifying Document - Correspondence/Photos/Survey
label | Frequency - Prior to cut to waste
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.03 - Foundation Suitability
label | Acceptance / Conformance Criteria - The foundation on which filling is to be placed must be observed by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient.
label | Standard / Specification - GWS 2.7
label | Verifying Document - Site Record
label | Frequency - Prior to the placement of any filling
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.04 - Unsuitable ground
label | Acceptance / Conformance Criteria - Unsuitable ground shall be defined as any pre-existing uncertified filling or natural silts/clays having an undrained shear strength of less than 70kPa or natural sands having less than 3 blows per 100mm penetration when tested with a Scala penetrometer. The contractor shall obtain instruction from Engineer around extent and depth of undercut.
label | Standard / Specification - GWS 2.7
label | Verifying Document - Shear Vane / Scala penetrometer
label | Frequency - Prior to the placement of any filling
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.02.05 - Preparation for Filling
label | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal).
label | Standard / Specification - GWS 2.9.2
label | Verifying Document - Site Record
label | Frequency - Prior to placement and compaction of fill
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.03.01 - Compaction Testing
label | Acceptance / Conformance Criteria - Bulk fill shall be tested by DT at 300mm probe depth
label | ○ 95% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
label | Standard / Specification - GWS 2.9.4
label | Verifying Document - Test Results
label | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x DT within a 3m radius)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE/ENG
checkpoint | 5.03.02 - Scala Penetrometer Testing
label | Acceptance / Conformance Criteria - Bulk fill shall be tested by Scala Penetrometer every 500m3 to:
label | ○ 4 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
label | Standard / Specification - GWS 2.9.4
label | Verifying Document - Test Results
label | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE/ENG
checkpoint | 5.04.01 - Vane Shear Strength Testing
label | Acceptance / Conformance Criteria - Bulk fill shall be tested for Vane Shear Strength to:
label | ○ Minimum average 120kPa over 10 tests, minimum single value 110kPa. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
label | Standard / Specification - GWS 2.9.4
label | Verifying Document - Test Results
label | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.04.02 - Air Voids Testing
label | Acceptance / Conformance Criteria - Bulk fill shall be tested for Air Voids to:
label | ○ Maximum average 10% over 10 tests, maximum single value 12%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
label | Standard / Specification - GWS 2.9.4
label | Verifying Document - Test Results
label | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.01.01 - Pre Topsoil Levels
label | Acceptance / Conformance Criteria - Shaped surface (pre topsoil) in forebays meets design RLs. Sloped areas must conform to the desiged grades.
label | Standard / Specification -
label | Verifying Document - AsBuilt Data / PDF
label | Frequency - Every Pond
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.03 - Topsoil thickness
label | Acceptance / Conformance Criteria - Topsoil thickness must meet minimum requirements. Planted areas must have a minimum topsoil thickness of 300mm. Non planted areas must have a minimum thickness of 100mm.
label | Standard / Specification -
label | Verifying Document - Photos
label | Frequency - Every Pond
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.03 - Topsoil Finished Levels
label | Acceptance / Conformance Criteria - Top soil meets finished level RL's in forebays. Sloped Areas must conform to the desiged grade.
label | Standard / Specification -
label | Verifying Document - AsBuilt Data / PDF
label | Frequency - Every Pond
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.06.01 - Set-out
label | Acceptance / Conformance Criteria - Check set-out prior to excavation of Rain Garden.
label | Standard / Specification - PS - 2.2.12
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - H
label | Verification Activity: By - SUP
checkpoint | 5.06.02 - Excavation
label | Acceptance / Conformance Criteria - Excavations shall be completed in such manner that it is true to the drawings will allow novacoil to be laid true to the depths, grades and lines.
label | Standard / Specification - Downer
label | Verifying Document - Survey Data, Photos
label | Frequency - Prior to laying filter cloth
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.06.03 - GCL liner
label | Acceptance / Conformance Criteria - GCL liner overlaps must welded. Installation, anchoring and pipe penetrations according to manufacterers spec. Extent of GCL liner must conform with the design.
label | Standard / Specification - Manufacturers Guidelines 18.2
label | Verifying Document - Site Photos
label | Frequency - Prior to backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.06.04 - GCL Repair
label | Acceptance / Conformance Criteria - GCL to be repaired as per manufacture's guidelnes (Bentofix PVB5100c). GCL becomes damaged, torn or punctured during installation, the affected area should be repaired. For damaged areas, a separate piece of GCL shall be used and extend past the comprimised section by 500mm in every direction. Bentonite shall be used to connect the seperate GCL to the main liner.
label | Standard / Specification - Manufacturers Guidelines 21
label | Verifying Document - Site Photos
label | Frequency - Prior to backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.06.05 - GCL Inspection
label | Acceptance / Conformance Criteria - GCL to be installed as per manufacturers guide and true to the drawings.The inspection should include overlaps, alignments, penetrations, connections, detections of any defects, including installation damage. Detected falsely installed areas shall be marked, repaired and the repairs shall be inspected and approved engineer.
label | Standard / Specification - Manufacturers Guidelines 22.2
label | Verifying Document - Site Photos
label | Frequency - Prior to backfill
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.06.06 - Geotextile Installation
label | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Site Photos
label | Frequency - Prior to aggregate placement
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.06.07 - Geotextile Inspection
label | Acceptance / Conformance Criteria - Before placement of any geotextile should form an Engineers inspection hold point
label | Standard / Specification - PS 2.2.16
label | Verifying Document - Site Records
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.06.08 - Bedding
label | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
label | Standard / Specification - TNZ F/5
label | Verifying Document - Photos, Sruvey Data
label | Frequency - Prior to laying Novacoil
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.06.09 - Joining Pipes
label | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
label | Standard / Specification - TNZ F/5
label | Verifying Document - Copy of delivery dockets, photos of joins onsite with tag showing class
label | Frequency - Every join
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.06.10 - Pipe Grade
label | Acceptance / Conformance Criteria - Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (Minimum grade of 0.5%) unless stated otherwise.
label | Standard / Specification - TNZ F/5
label | Verifying Document - AsBuilt
label | Frequency - Every 10m
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.06.11 - Pipe Cover
label | Acceptance / Conformance Criteria - Pipe to have 100mm of drainage aggregate as top cover for pipe.
label | Standard / Specification - N/A
label | Verifying Document - Site Photos
label | Frequency - Every 10m
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.06.12 - Filter Media
label | Acceptance / Conformance Criteria - Filter media to be placed at a constant average thickness of 500mm, refer to drawing for detail. Filter media should be free of peaks and troughs.
label | Standard / Specification - N/A
label | Verifying Document - Site Photos
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.06.13 - Coconut Matting
label | Acceptance / Conformance Criteria - Mat shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Site Photos
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.06.14 - Scour Protection GAP 65 Rip Rap
label | Acceptance / Conformance Criteria - Scour protection shall be installed as per drawings around let downs, scruffy dome and the flush point end.
label | Standard / Specification - GWS 3.6 & BBO
label | Verifying Document - Site Photos/ Survey Data
label | Frequency - Every Rain Garden
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.07.01 - Filter Cloth Wrap Inspection
label | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
label | Standard / Specification - GWS 3.2.2
label | Verifying Document - Every line
label | Frequency - Photos of trench prior to backfill
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.07.02 - Trench Backfill
label | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
label | Standard / Specification - GWS 3.3
label | Verifying Document - Site Record
label | Frequency - Each trench
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.07.03 - Subsoil Flushing
label | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
label | Standard / Specification - GWS 3.6
label | Verifying Document - Site Records
label | Frequency - On completion of earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.07.04 - Survey
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.07.05 - Excavation
label | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Prior to laying filter cloth
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.07.06 - Bedding
label | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
label | Standard / Specification - TNZ F/5
label | Verifying Document - Records
label | Frequency - Prior to laying Novacoil
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.07.07 - Joining Pipes
label | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
label | Standard / Specification - TNZ F/5
label | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
label | Frequency - Every join
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - As-builts taken every 10m prior to backfill
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.05 - Photos
label | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | Standard / Specification - Downer
label | Verifying Document - Photo Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature