## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP002 - Concrete - Suspended Slab | itp |  |  |  |  | ITP002 - Concrete - Suspended Slab
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - ELEMENT IDENTIFICATION
checkpoint | 3.2 - Survey / Set out
label | Inspection Point: Quality Control Activity - Levels confirmed on site
label | Acceptance Criteria - Set out in accordance with design drawings or site conditions
label | Verifying Document - Visual Inspection / On Site Verification
label | Key - I
label | By - IP
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Slab Type
label | Inspection Point: Quality Control Activity - Bondeck or Conventional Suspended Slab
label | Acceptance Criteria - Slab type is identified Bondeck / Conventional
label | Verifying Document - Note Only
label | Key - W
label | By - IP
checkpoint | 4.2 - Formwork Installation - Strength
label | Inspection Point: Quality Control Activity - Confirmation of Formwork Strength Requirements
label | Acceptance Criteria - Formwork is suitable for placement of wet concrete
label | ○ Bondeck – Steel / Block Walls installed and Props as per design
label | ○ Conventional – Formwork support system installed as per engineering design
label | Verifying Document - Engineering Design (if required), Bondeck installed in accordance with span tables
label | Key - I
label | By - IP
checkpoint | 4.3 - Formwork Installation – Level and alignment
label | Inspection Point: Quality Control Activity - Concrete slab formwork is set up to architectural levels
label | Acceptance Criteria - Slab Thickness maintained
label | ○ Set downs maintained
label | ○ Level and alignment of beams is as per architectural design
label | Verifying Document - Visual Inspection, Client Inspection Survey (If req)
label | Key - WP
label | By - IP
checkpoint | 4.4 - Reinforcement Installation
label | Inspection Point: Quality Control Activity - Structural Reinforcement as per Structural Design documentation / additional SDA
label | Acceptance Criteria - Installation of dowels satisfies embedment
label | ○ Top / Bottom reinforcement installed
label | ○ Beam reinforcement installed
label | ○ Re-entrant Bars installed
label | Verifying Document - Client Engineering Inspection
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Pre-Pour Concrete Check
label | Inspection Point: Quality Control Activity - Inspection of reo and Services conduit check
label | Acceptance Criteria - Steel reinforcement in accordance with design documentation. All services installed.
label | Verifying Document - Client Inspection
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Joints (If applicable)
label | Inspection Point: Quality Control Activity - Inspection of jointing detail
label | Acceptance Criteria - Joints installed in accordance with Design requirements
textbox | Expansion Joint Spacing:
textbox | Saw Cut Joint Spacing:
label | Verifying Document - Visual inspection only
label | Key - I
label | By - IP
checkpoint | 4.7 - Concrete Pour
label | Inspection Point: Quality Control Activity - Concrete is poured to required levels and strength
label | Acceptance Criteria - Strength and finish requirement met. Finished level within tolerances.
label | Verifying Document - Visual inspection Strength Test
textbox | Supplier:
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT