## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 11.00 - Sealing Works | itp |  |  |  |  | 11.00 - Sealing Works
section | Details
checkpoint | 1 - Permission to use construction procedures
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Hold Point 1
label | Reference - MRTS11 CL5.2
holdpoint | HOLD POINT
checkpoint | 2 - Construction procedures and ITP submitted to the Administrator seven days prior to use
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Milestone
label | Reference - MRTS11 CL5.2
checkpoint | 2 - The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Milestone
label | Reference - MRTS11 CL6.1.2
checkpoint | 3 - Contractor notified of Principal's seal design
label | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Principal
label | Check Item - Hold Point 2
label | Reference - MRTS11 CL6.2
holdpoint | HOLD POINT
checkpoint | 4 - Contractor provides Principal with seal design test results along with Ball Penetration test results
label | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Principal
label | Check Item - Milestone
label | Reference - MRTS11 CL6.2
checkpoint | 5 - The Contractor shall submit the seal design report to the Administrator at least seven days prior to commencement of spraying operations.
label | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
label | Check Item - Milestone
label | Reference - MRTS11 Cl. 6.3.2
checkpoint | 6 - Spraying operations shall not commence until the Administrator has approved the seal design report
label | Acceptance Criteria & Frequency (Project Specific) - Seal Design by Contractor
label | Check Item - Hold Point 3
label | Reference - MRTS11 Cl. 6.3.2
holdpoint | HOLD POINT
checkpoint | 7 - Cover aggregate is covered by a light plastic until it's implementation in the works
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 1
label | Reference - MRTS11 CL8.2
checkpoint | 8 - Binder storage temperature measured and recordered at delivery to site
label | Acceptance Criteria & Frequency (Project Specific) - Between 160 and 190 degrees celcius
label | Check Item - Witness Point 2
label | Reference - MRTS11 CL8.3.1
checkpoint | 9 - If binder temperature low, raise to within 160 and 190 degrees celcius. Heating shall be strictly observed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 3
label | Reference - MRTS11 CL8.3.2
checkpoint | 10 - Three days prior to sealing operation, the Contractor shall submit details of all plant to be used.
label | Acceptance Criteria & Frequency (Project Specific) - As per MRTS11.1 Annexure
label | Check Item - Hold Point 4
label | Reference - MRTS11 CL9.0
holdpoint | HOLD POINT
checkpoint | 11 - Ball penetration test results < 4mm unless approved by the administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5
label | Reference - MRTS11 CL10.1.2
holdpoint | HOLD POINT
checkpoint | 12 - Ensure enough cover aggregate available on site to complete works
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 6
label | Reference - MRTS11 CL11.1
holdpoint | HOLD POINT
checkpoint | 13 - Pavement Temperature above minimum specified
label | Acceptance Criteria & Frequency (Project Specific) - Primes: >/=10 degrees
label | ○ Cutback Bitument: >/=15
label | ○ Polymer binder: >/=20
label | Check Item - Witness Point 4
label | Reference - MRTS11 CL11.2
checkpoint | 14 - Unless otherwise approved, sprayed bituminous treatments that will be trafficked shall not be sprayed if the air temperature is likely to fall below 10C at any time during the first two weeks.
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Hold Point 7
label | Reference - MRTS11 CL11.3
holdpoint | HOLD POINT
checkpoint | 14 - Current QLD sprayer certificate to be sighted
label | Acceptance Criteria & Frequency (Project Specific) - Current Certificate
label | Check Item - Witness Point 5
label | Reference - MRTS11 CL12.4
checkpoint | 15 - Nomination and recording of cutting requirements where required
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 6
label | Reference - MRTS11 CL12.7
checkpoint | 16 - Wet cover aggregate containing free surface water shall not be loaded in the aggregate spreader
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 7
label | Reference - MRTS11 CL14.1
checkpoint | 17 - Loose aggregate signage requirements prior to opening to traffic
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS11 CL14.8
holdpoint | HOLD POINT
checkpoint | 17 - Following rain, or other events causing moisture ingress, sealing shall be postponed in accordance with the table in MRTS11.1 Cl. 10
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 9
label | Reference - MRTS11.1 Cl 10
holdpoint | HOLD POINT
checkpoint | 18 - Quality Verification Requirements
label | Acceptance Criteria & Frequency (Project Specific) - Testing Frequency
label | Check Item - MRTS11
label | Reference - Table 6.2
checkpoint | 19 - Particle Size Distribution, Flakiness Index, Avg. Least Dimension
label | Acceptance Criteria & Frequency (Project Specific) - One test per aggregate type, nominal size & source
label | ○ Repeat tests every 1000t
label | Check Item - Check Item
label | Reference - MRTS11 Table 6.2
checkpoint | 20 - Texture Depth: In and between the wheelpaths - that is, 3 tests at each test chainage per direction
label | Acceptance Criteria & Frequency (Project Specific) - Lesser of:
label | ○ Every 400m
label | ○ 3 test chainages per homogenous section
label | Check Item - Check Item
label | Reference - MRTS11 Table 6.2
checkpoint | 21 - Ball Penetration: Inner and outer wheelpaths - 2 tests at each test chainage per direction
label | Acceptance Criteria & Frequency (Project Specific) - 5 test chainages per homogenous section
label | Check Item - Check Item
label | Reference - MRTS11 Table 6.2
checkpoint | 22 - Spreading: Each spreader shall be tested in accordance with the Field Spread Rate Cover Aggregate Test (Q711A)
label | Acceptance Criteria & Frequency (Project Specific) - One test per spreader per day, Tolerance: ±10%
label | Check Item - Check Item
label | Reference - MRTS11 Cl. 14.4
checkpoint | 23 - Sampling of Bitumen (two x 1L samples) shall be undertaken before or during transfer of bitument to sprayers.
label | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size
label | ○ Asphalt = Each new tank
label | ○ Sealing = 150 tonnes
label | Check Item - Witness Point
label | Reference - MRTS17 Cl. 9.3.3
checkpoint | 24 - The minimum frequencies for sampling and testings in regards to the cutter oil and flux oil shall be in accordance with Table 9.2 of MRTS19
label | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.2
label | Check Item - Check Item
label | Reference - MRTS19 Cl. 9.2
checkpoint | 25 - The minimum frequencies for sampling and testings in regards to cutback bitumen shall be in accordance with Table 9.3 of MRTS20
label | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 9.3
label | Check Item - Check Item
label | Reference - MRTS20 Cl. 9.3
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP