## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 14.08 - Demolition, Removal, Salvage & Re-erection of Road Furniture | itp |  |  |  |  | 14.08 - Demolition, Removal, Salvage & Re-erection of Road Furniture
section | Details
checkpoint | 1 - The items of road furniture to be demolished and disposed of are listed in Clause 3 of MRTS14.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 7.2
checkpoint | 2 - Seven days prior to commencement, the Contractor shall submit a schedule of items to be salvaged in accordance with the design documentation.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS14 Cl 8.2
checkpoint | 3 - Dismantling and removal shall not commence until expiration of the seven day period.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS14 Cl 8.2
holdpoint | HOLD POINT
checkpoint | 4 - Salvaged materials shall be transported and stored in accordance with Cluase 1.2 of MRTS14.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 8.4
checkpoint | 5 - Seven days prior to commencement, the Contractor shall submit a schedule of items to be dismantled for re-erection in accordance with the design documentation.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS14 Cl 9.2
checkpoint | 6 - Dismantling and removal shall not commence until expiration of the seven day period.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS14 Cl 9.2
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP