## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments | itp |  |  |  |  | 14.20 - Installation of Steel beam Guardrail and End Treatments
section | Details
checkpoint | 1 - Manufacture of steel beam guardrail post, panel components and end treats are maufactured by an approved manufacturer
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.2.1
checkpoint | 2 - Manufacture of steel beam guardrail post, panel components and end treats are supplied by an approved supplier
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.3.1
checkpoint | 3 - All the steel manufacturer test certificates shall be supplied to te Administrator. The Administrator shall review and approve the certificates.
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Hold Point 7
label | Reference - MRTS14 Cl. 20.4.5
holdpoint | HOLD POINT
checkpoint | 4 - If test certificates are not available, the Contractor shall submit to the Administrator for approval a proposal for selecting samples for testing.
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Witness Point 2
label | Reference - MRTS14 Cl. 20.4.5
checkpoint | 5 - All projects are to be supplied with a min. two extra posts and panels from each batch. The Administrator shall randomy select from each batch two post and two panels for Audit testing.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 3
label | Reference - MRTS14 Cl. 20.4.6.1
checkpoint | 6 - Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS14 Cl. 20.4.6.3
holdpoint | HOLD POINT
checkpoint | 7 - All welders must comply with the requirements of Clause 20.5.2 otherwise a TMR representative shall be present when macro samples are prepared to show conformorance
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 9
label | Reference - MRTS14 Cl. 20.5.2
holdpoint | HOLD POINT
checkpoint | 8 - Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.1
checkpoint | 9 - Steel Posts driven into ground except where posts are to be driven into asphalt, concrete or rock.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.2
checkpoint | 10 - Where ground is asphalt, concrete or rock, a hole shall be excavated in accordane with Cl 20.6.2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.2
checkpoint | 11 - Terminals installed as per the design documentation
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.3
checkpoint | 12 - Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.5
checkpoint | 13 - Installed within Geometric Tolerances
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.6
checkpoint | 14 - Adminstrator accepts guardrail installation as per the design documentation
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS14 Cl 20.6.7
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP