## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 16.01 - Landscape and Revegetation | itp |  |  |  |  | 16.01 - Landscape and Revegetation
section | Soil Management Plan
checkpoint | 2 - Soil Management Plan - Construction and regular Updates submitted to the Administrator for approval
label | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
label | Check Item - Hold Point 1&2
label | Reference - MRTS16 Cl 5.2.2
holdpoint | HOLD POINT
section | Materials
checkpoint | 6 - Material transported from a Red Imported Fire Ant Zone has complied with all relevant laws and regulations
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | 7 - Materials are stored to ensure no deterioration or contamination occurs
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | 8 - Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | 9 - Containerised plants and ex-ground stock inspections conducted with Administrator, with 5 days notice, prior to delivery, within two months of acceptance of Plant Supply Proposal and every two months thereafter (where growing period is greater than 2 months)
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS16 Cl 7.8.1.1
checkpoint | 10 - The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8
section | Subsoil and Topsoil Amelioration
checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.1 TMR SD 1644, TMR SD 1646
checkpoint | 12 - Site is weed free prior to ground preparation operations
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS16 Cl 8.1.1.2
checkpoint | 13 - Administrator notified at least 3 days before each of the following:
label | ○ Application and incorporation of amelioration agents
label | ○ Ripping
label | ○ Cultivation
label | ○ Roughening
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS16 Cl 8.1.1.3 Cl 8.1.1.4 Cl 8.1.1.5 Cl 8.1.1.6 Cl 8.1.2.4
checkpoint | 14 - Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 6
label | Reference - MRTS16 Cl 8.1.2.3
holdpoint | HOLD POINT
checkpoint | 15 - Topsoil installed evenly over the surface, within 5 days of subsoil preparation and at the required minimum depth
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.1.2.4
section | Grass seeding, Hydromulching and Turfing
checkpoint | 19 - Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.2.2
checkpoint | 20 - Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.2.2 with initial watering on the day of installation and at least 10L/m2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.2.2
section | Establishment, Monitoring and Finalisation
checkpoint | 31 - Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.1
checkpoint | 32 - All Establishment operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.1.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.1.1
checkpoint | 33 - If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS16 Cl 9.1.1.5 Cl 9.2.1.5
holdpoint | HOLD POINT
checkpoint | 34 - Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2
checkpoint | 35 - All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.2.1
checkpoint | 36 - Certificate of finalisation of landscape and revegetation works monitoring period issued
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP