## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 02.01 - Traffic Management | itp |  |  |  |  | 02.01 - Traffic Management
section | Details
checkpoint | 1 - The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Check Item
label | Reference - MRTS02.1 Cl5.2
checkpoint | 2 - No traffic rearrangements shall be carried out until after the Administrator has advised the contractor that the Traffic Management Plan has been submitted and approved
label | Acceptance Criteria & Frequency (Project Specific) - Written Approval
label | Check Item - Hold Point 1
label | Reference - MRTS02 Cl 5.3
holdpoint | HOLD POINT
checkpoint | 3 - All TGS's prepared by a suitably qualified person and submitted and approved by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Written Submission
label | Check Item - Hold Point 2
label | Reference - MRTS02 Cl 6.2
holdpoint | HOLD POINT
checkpoint | 4 - Submission of Traffic Management Inspection Report
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Milestone
label | Reference - MRTS02 Cl 7.5
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP