## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 22.01 - Supply of Cover Aggregate | itp |  |  |  |  | 22.01 - Supply of Cover Aggregate
section | Details
checkpoint | 1 - Cover aggregate supplied by a quarry registered and operated in accordance with DTMR's Quarry Registration System requirements. Submitted to Administrator 7 days prior to supply
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS22 Cl. 6
checkpoint | 2 - Material from a quarry shall not be supplid or used without written permission from the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Hold Point 1
label | Reference - MRTS22 Cl. 6
holdpoint | HOLD POINT
checkpoint | 3 - Construction procedure shall be submited to the administrator atleast 7 days prior to the commencement of aggregate production for the works
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS22 Cl. 6
checkpoint | 4 - The cover aggregate particles shall comply with the requirements of Table 7.1.3 of MRTS22
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS22 Cl. 7.1.3
checkpoint | 5 - Where precoated cover aggregate is specified the Contractor shall submit to the Administrator 7 days prior, the procedure to be used for application of the precoating agent
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS22 Cl. 7.1.4
checkpoint | 6 - If stated in Clause 3 of MRTS22.1, a sample of 40kg of each type of aggregate to be used shall be supplied to the Administrator 14 days prior to use.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS22 Cl 8.1
checkpoint | 7 - Prior to commencement of delivery of aggregate to any stockpile, the Contractor shall obtain the Administrators authorisation
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS22 Cl. 10
holdpoint | HOLD POINT
checkpoint | 8 - Except for prime cover materials, all cover aggregate stockpiles shall be protected with a light plastic material
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS22 Cl. 10
checkpoint | 9 - Quality Verification Requirements
label | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
label | Check Item - MRTS22
label | Reference - Clause 8.3
checkpoint | 10 - Material compliance testing shall be conducted in accordance with the requirements of MRTS22 Cl. 8.3
label | Acceptance Criteria & Frequency (Project Specific) - Refer to Table 8.3.2(a) and 8.3.2(b)
label | Check Item - Check Item
label | Reference - Clause 8.3
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP