## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 27.01 - Geotextile | itp |  |  |  |  | 27.01 - Geotextile
section | Details
checkpoint | 1 - Geotextile strength and filtration classes as specified on drawings or within MRTS27
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS27 Cl6
checkpoint | 2 - Geotextile stored on site under protective covers, off the ground and in a manner unaffected by heat. Rolls clearly marked with manufacturer, type and batch.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS27 Cl7
checkpoint | 3 - Proposed Geotextile submitted to and accepted by Adminstrator for acceptability to Cl6.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS27 Cl8.1
holdpoint | HOLD POINT
checkpoint | 4 - Geotextiles installed as specified in the contract
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS27 Cl9.1
checkpoint | 5 - Area cleared and graded with all sharp objects and large stones removed and covered within 48hours of being placed
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS27 Cl9.1
checkpoint | 6 - Where batch size is >5000m2, sampling and testing undertaken according to Cl10.2. An area not less than 15m2 shall be sampled.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS27 Cl10.2
checkpoint | 7 - Where directed, an additional testing sample is provided to the administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS27 Cl10.2
checkpoint | 8 - Geotextile not placed until administrator accepts test results
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS27 Cl10.4
holdpoint | HOLD POINT
checkpoint | 9 - Quality Verification Requirements Test Method
label | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
label | Check Item - MRTS27
label | Reference - Clause 11
checkpoint | 10 - Testing of in situ/imported soil/fill material carried out in accordance with test methods: Q101, Q103A and/or Q103C
label | Acceptance Criteria & Frequency (Project Specific) - Two tests per 5000m3
label | Check Item - Check Item
label | Reference - MRTS27 Cl. 11
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP