## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 04.01 - Clear and Grub Stripping of Topsoil | itp |  |  |  |  | 04.01 - Clear and Grub Stripping of Topsoil
section | Details
checkpoint | 1 - Clearing limit plan prepared and approved by Prinicpal with boundary limits clearly marked
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04.1 Cl2.4
checkpoint | 2 - Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the area concerned.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS04 Cl7.2.2
holdpoint | HOLD POINT
checkpoint | 3 - Marketable timber shall be clearly marked by contractor Prior to clearing. Marked trees felled and handled avoiding damage to the trunks. The trunks trimmed and stacked in neat manageable stockpiles approved by the Administrator at spacings of not more than 500 metres.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS04 Cl7.2.3
holdpoint | HOLD POINT
checkpoint | 4 - Material suitable for organic mulch shall be in accordance with MRTS16B Vegetation Ground Works
label | Acceptance Criteria & Frequency (Project Specific) - Visual, MRTS16B
label | Check Item - Check Item
label | Reference - MRTS04 Cl7.2.4
checkpoint | 5 - Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl7.2.5
checkpoint | 6 - Topsoil stripped as required in Cl 3.1 of Annexure MRTS.04.01. Depth of excavation shall be specified in the Cl 3.1 of Annexure MRTS04.01 or as directed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl8.2
checkpoint | 7 - Surplus material and material considered not suitable for use as planting media in accordance with Cl 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed of in accordance with Cl 11
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl8.4.2
checkpoint | 8 - Material not removed from within drip lines of trees except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retainined are preserved where practical.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl8.4.3
checkpoint | 9 - Stripped material shall be stockpiled in the locations shown on the drawings, as stated in Clause 3.2 of Annexure MRTS04.1
label | Topsoil Stockpiles are;
label | ○ Less than 3m High
label | ○ Less than 10m wide
label | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
label | ○ Stockpiled for the minimum duration
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl8.4.4
checkpoint | Quality Verification Requirements, Test Method
label | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
label | Check Item - MRTS04
label | Reference - Table A1
checkpoint | 8 - Geometrics, Clearance Limits, Vertical (Stripping of Topsoil only)
label | Acceptance Criteria & Frequency (Project Specific) - 1000m, 1 test per 100m per side, 1 per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.1
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP