## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 04.09 - Subgrade | itp |  |  |  |  | 04.09 - Subgrade
section | Details
checkpoint | 1 - CUTTINGS: Tests conducted in accordance with MRTS04 Cl 18.3.3.2
label | Acceptance Criteria & Frequency (Project Specific) - RDD
label | Check Item - Check Item
label | Reference - MRTS04 Cl 18.3.3.2
checkpoint | 2 - Work stopped when excavation has reached sugrade level. Contractor shall carry out the requirements of the relevant provisions of Clause 13.3.2.1
textbox | Specified Subgrade Treatement (A-K):
label | Acceptance Criteria & Frequency (Project Specific) - MRTS04 Table 15.3-A, Table 15.3-B
label | Check Item - Hold Point 5
label | Reference - MRTS04 Cl13.3.2.1 Cl18.3.3
holdpoint | HOLD POINT
checkpoint | 3 - General fill material used for construction of subgrade where embankment or cutting treatment using general fill, if used in road embankments must comply with Cl 14.2.4
label | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Embankment ITP or Related Lot)
label | Check Item - Check Item
label | Reference - MRTS04 Cl 18.2.1
checkpoint | 4 - Unbound pavement material shall conform with the requirements of MRTS05 Unbound Pavements and shall be at least of the subtype specified in Clause 13.1 of Annexure MRTS04.1, or where no such subtype is specified, at least subtype 2.4.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl 18.2.2
checkpoint | 6 - Quarry Registration Certificate submitted to Administrator 7 days prior to sourcing high permeability drainage materials.
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Milestone
label | Reference - MRTS04 Cl18.2.4.1
checkpoint | 7 - A mix design shall be submitted atleast 14 days prior to commencement of subgrade stabilisation
label | Acceptance Criteria & Frequency (Project Specific) - Written
label | Check Item - Hold Point 7
label | Reference - Cl18.2.5.4
holdpoint | HOLD POINT
checkpoint | 8 - Subgrade and underlying work tested and conforming prior to placement of pavement.
label | Acceptance Criteria & Frequency (Project Specific) - ITP
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl18.3.1
holdpoint | HOLD POINT
checkpoint | 9 - Subgrade material provides a stable dense surface displaying no vertical movement under proof roll
label | Acceptance Criteria & Frequency (Project Specific) - Visual, No Delfection, Continuous
label | Check Item - Witness Point 3
label | Reference - Cl18.3.2
checkpoint | 10 - Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
label | Acceptance Criteria & Frequency (Project Specific) - Visual, Tolerances: Table 6.3.1, Subgrade = +25mm
label | Check Item - Check Item
label | Reference - Cl 18.3.3.1
checkpoint | 11 - Quality Verification Requirements Test Method
label | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | 15 - Compaction: Q140A, To a depth 150mm below subgrade = 97%
label | Acceptance Criteria & Frequency (Project Specific) - Single layer/day, 1 per 500m2, 1 per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.1
checkpoint | 16 - Geometrics, Horizontal Position
label | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
label | Check Item - Check Item
label | Reference - MRTS04 Table A.1
checkpoint | 17 - Geometrics, Vertical Level
label | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
label | Check Item - Check Item
label | Reference - MRTS04 Table A.1
checkpoint | 18 - Geometrics, Deviation from a straight edge
label | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
label | Check Item - Check Item
label | Reference - MRTS04 Table A.1
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP