## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 05.01 - Placement of Unbound Pavement | itp |  |  |  |  | 05.01 - Placement of Unbound Pavement
section | Details
checkpoint | 10 - Materials not incorporated unless it conforms with MRTS05
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS05 Cl9.1
holdpoint | HOLD POINT
checkpoint | 12 - Primary Geometric Tolerances, Layer Thickness between 75mm and 250mm
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS05 Cl8.2.3
checkpoint | 13 - Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by construction equipment nominated
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 2
label | Reference - MRTS05 Cl9.4.6
checkpoint | 14 - Additional Geometrics (final layer or where specified in MRTS05.1 Cl. 6.2)
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS05 Cl9.2.5.2
checkpoint | 15 - No Layer of Pavement shall be covered by a subsequent layer of pavement or by surfacing until all testing has been completed and the layer has been presented to the administrator for permission to proceed
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS05 C9.5.1
holdpoint | HOLD POINT
checkpoint | 16 - Construction Testing Requirements: Test Method
label | Acceptance Criteria & Frequency (Project Specific) - Min. Testing Frequency, Min. No. of Tests
label | Check Item - MRTS05
label | Reference - Table A3
checkpoint | 17 - Degree of Saturation: Q146, Type 2: 65%
label | Acceptance Criteria & Frequency (Project Specific) - 1 per 500m2, 4 per lot
label | Check Item - Hold Point 6
label | Reference - MRTS05 Cl. 8.2.4.1
holdpoint | HOLD POINT
checkpoint | 18 - Compaction: Q140A, C.V. of RDD >= 102% for all Type 1 Materials, C.V of RDD >= 100% for Type 2/3/4 Materials
label | Acceptance Criteria & Frequency (Project Specific) - 1 per 500m2, 4 per lot
label | Check Item - Check Item
label | Reference - MRTS05 Cl. 8.3.3
checkpoint | 19 - Vertical Position: Survey +/- 15mm
label | Acceptance Criteria & Frequency (Project Specific) - 1 per 20 linear meter
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.3.4.3
checkpoint | 20 - Deviation from a Straight Edge: Q712, Types 2, 3 & 4 materials: 5mm
label | Acceptance Criteria & Frequency (Project Specific) - 1 per 20 linear meter
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.3.5
checkpoint | 21 - Road Roughness: Q708B, Q708C & Q708D, Rs max. value: 2.31 (m/km)
label | Acceptance Criteria & Frequency (Project Specific) - As per Clause 9.4.9, Greater than 100m less than 500mm
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.3.6
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP