## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 05.02 - Supply of Unbound Material | itp |  |  |  |  | 05.02 - Supply of Unbound Material
section | Details
checkpoint | 1 - No unbound pavement works shall commence until all relevant construction procedures have been accepted by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS05 Cl. 5.2
holdpoint | HOLD POINT
checkpoint | 2 - The aggregate production procedures shall be submitted to the Administrator at least 7 days prior to commencement of material production
label | Check Item - Milestone
label | Reference - MRTS05 Cl. 5.2.1
checkpoint | 3 - The unbound pavement construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement works
label | Check Item - Milestone
label | Reference - MRTS05 Cl. 5.2.2
checkpoint | 4 - Copies of current paving material certificates (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS05 Cl6
checkpoint | 5 - Material from a quarry shall not be used until the quarry has been approved by the administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS05 Cl6
holdpoint | HOLD POINT
checkpoint | 6 - If more than one grading envelope is specified in Clause 2.1 of MRTS05.1 for a single location, the Contractor shall notifiy in writing, which of the grading envelopes will be used, at least two days prior to commencement
label | Check Item - Hold Point 3/4
label | Reference - MRTS05 Cl. 7.2.4
holdpoint | HOLD POINT
checkpoint | 7 - Use of alternative grading envelope not used unless submitted and approved at least 2 days prior to delivery.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3/4
label | Reference - MRTS05 Cl7.2.4 Cl7.3.4
holdpoint | HOLD POINT
checkpoint | 8 - Stockpiles located as specified in MRTS05.01 Cl. 6 or if not specified, on clear, even, firm, well drained ground where it can be clearly identified with individual stockpiles separated by at least 2m.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS05 Cl7.6
checkpoint | 9 - Separate stockpiles for each production lot, or stockpiles incrementally created from a single material subtype with each added lot tested and approved prior to subsequent lots being added.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS05 Cl7.6
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP