## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 52.01 - Erosion and Sediment Control | itp |  |  |  |  | 52.01 - Erosion and Sediment Control
section | Details
checkpoint | 1 - Submit an Erosion and Sediment Control Plan (ESCP) for that section
label | Acceptance Criteria & Frequency (Project Specific) - 14 days prior to tree removal as per Annexure 52.1
label | Check Item - Check Item
label | Reference - MRTS52 Cl 6.1
checkpoint | 2 - Administrator assessed suitability of Erosion and Sediment Control Plan for each stage and/or section of the works where required
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS52 Cl 6.1
holdpoint | HOLD POINT
checkpoint | 3 - Installation of appropriate erosion and sediment controls in each section of the works
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl 7.1
holdpoint | HOLD POINT
checkpoint | 4 - Any clearing required to be able to install sediment control must be discussed and approved by Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52 Cl 7.1
checkpoint | 5 - Erosion and sediment controls maintained and reconfigured throughout the stages of the project
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52 Cl 7.2
checkpoint | 6 - Remove temporary controls when permanent measures in place and/or site stabilisation occurred
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52 Cl 7.3
checkpoint | 7 - Install a proprietary rain gauge and monitor/record rainfall in spreadsheet (mm)
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52 Cl 8.2.1
checkpoint | 8 - Waters released from sediment basins or trap must be sampled prior to release.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52 Cl 8.2.2
checkpoint | 9 - Conduct water quality monitoring as per any licence, permit or approval conditions as per MRTS52 Cl 8.2.3 or varied by Clause 4.2 of Annexure MRTS52
label | Acceptance Criteria & Frequency (Project Specific) - Visual and Criteria table in Annexure 52.1
label | Check Item - Check Item
label | Reference - MRTS52 Cl 8.2.3, MRTS52.1 Cl 4.1
checkpoint | 10 - Water quality monitoring shall be undertaken 100 m upstream and 100 m downstream of the site during any rainfall event greater than 25 mm in a 24-hour period, or during times when construction activities have the potential to contaminate the waterway. In addition, any water discharged from the site into a waterway or a stormwater drainage network is to be tested prior to discharge to ensure compliance with water quality thresholds.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52.1 Cl 4.1
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP