## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 70.01 - Placement of Concrete | itp |  |  |  |  | 70.01 - Placement of Concrete
section | Details
checkpoint | 1 - Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Temp <35 Continuous
label | Check Item - Check Item
label | Reference - MRTS70 Cl 10.4
checkpoint | 2 - Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS70 Cl 15.3
holdpoint | HOLD POINT
checkpoint | 3 - No concrete placed until falsework, formwork, reinforcement and stressing materials inspected, foreign material removed from forms and equipment and placement procedures approved.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3/5
label | Reference - MRTS70 Cl 15.4.1 Cl 15.6.1
holdpoint | HOLD POINT
checkpoint | 4 - Concrete operations shall not commence until all relevant procedures have been approved by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS70 Cl 15.6
holdpoint | HOLD POINT
checkpoint | 5 - Administrator to be present for placement of concrete, with 24 hours notice.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS70 Cl 15.6.1
checkpoint | 6 - The placement of concrete underwater shall be carried out in the presence of the Administrator and shall comply with the requirements of Clause 19.2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS70 Cl 15.6.3
checkpoint | 7 - Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
label | Acceptance Criteria & Frequency (Project Specific) - Slump Test:
label | ○ <60 - ±10
label | ○ 60<80 - ±15
label | ○ 80<110 - ±20
label | ○ 110<150 - ±30
label | ○ 150< - ±40
label | ○ Every Load
label | Check Item - Check Item
label | Reference - MRTS70 Cl 11 AS1379
checkpoint | 8 - Samples for testing taken as required - min 2 cylinders/sample
label | Acceptance Criteria & Frequency (Project Specific) - 1-3 Loads - Every Load
label | ○ 4-10 Loads - 4 Samples
label | ○ 11-23 Loads - 5 Samples
label | ○ >24 Loads - 1 per 4 loads
label | Check Item - Check Item
label | Reference - MRTS70 Cl 15.2
checkpoint | 9 - Compressive Strength Testing
label | Acceptance Criteria & Frequency (Project Specific) - f'c
label | ○ <2Mpa Difference/2 Cylinders
label | ○ <3Mpa Difference/2 Cylinders
label | Check Item - Check Item
label | Reference - MRTS70 Cl 12.3
checkpoint | 10 - Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - minimum of two vibrators used with at least one per 4m3 of concrete placed per hour.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 15.6
checkpoint | 11 - Additional construction joints approved by Superintendent.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS70 Cl 15.13
holdpoint | HOLD POINT
checkpoint | 12 - Forms and Falsework not removed early unless approved by the Superintendent
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 6
label | Reference - MRTS70 Cl 15.8
holdpoint | HOLD POINT
checkpoint | 13 - Forms not removed until
label | ○ Non-structural - min(50% of 28 day strength or 3 days)
label | ○ Soffits of slabs, headstock and diaphragms - 7 days
label | ○ Side forms of structural concrete - 2 days (Exposure class A), 3 days (B1, B2) or 5 days (Exposure class C)
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 15.8
checkpoint | 14 - Forms removed with care and curing commence upon completion of finishing operations to approved procedures. If forms removed in under 7 days, curing commences within 1 hour
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS70 Cl 15.8
checkpoint | 15 - Following removal of forms
label | ○ Fins and unwanted projections are ground off
label | ○ Pockets and honeycombed areas repaired using approved methods
label | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 15.12
checkpoint | 16 - Concrete installed to within positional, dimensional and relative tolerances. Should a specified tolerance be exceeded, the work shall be liable to rejection.
label | Acceptance Criteria & Frequency (Project Specific) - Visual <Specified MRTS70 Cl22 QR-CTS-Part 7
label | Check Item - Check Item
label | Reference - MRTS70 Cl 15.7.2
checkpoint | 17 - Acceptance or Rejection of Hardened Concrete
label | a) < 0.9 Fc (Any sample)
label | b) < Fc (Ave 3 consecutive samples from Lot)
label | c) > 1.4 Fc (Ave 3 consecutive samples from Lot)
label | In addition
label | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consecutive weeks)
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 12.5
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP