## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 70.03 - Supply of Concrete | itp |  |  |  |  | 70.03 - Supply of Concrete
section | Details
checkpoint | 1 - Mix designs for each class of concrete forwarded to Administrator at least 4 weeks prior to first delivery
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 9.2
checkpoint | 2 - Where travel or placement times are, by neccessity, longer than those listed in Table 10.4 a procedure shall be submitted to the Adminstrator for approval.
label | Acceptance Criteria & Frequency (Project Specific) - Written, 6 weeks notice
label | Check Item - Milestone
label | Reference - MRTS70 Cl 10.4.1
checkpoint | 3 - All mixes >20MPa have a trial mix complete and Administrator given 3 days notice.
label | Acceptance Criteria & Frequency (Project Specific) - f'c, Each Mix
label | Check Item - Witness Point 1
label | Reference - MRTS70 Cl 15.1.1
checkpoint | 4 - Concrete not incorporated into works until trial mix completed or ready mixed concrete supplier is approved.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS70 Cl 15.1
holdpoint | HOLD POINT
checkpoint | 5 - All aggregate shall be sampled in accordance with AS 2758.1 during concrete production and tested for conformance to the aggregate requirements in MRTS70 clause 7.8 or Quarry assessment and certification approved
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 7.5
checkpoint | 6 - Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria & Frequency (Project Specific) - Visual, Ambient temp. > 35 degrees
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.5
checkpoint | 7 - Falsework details provided to Administrator at least 4 weeks prior to erection.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.3
checkpoint | 8 - Procedure for underwater concreting submitted to Administrator 2 weeks prior to first pour
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.6.3
checkpoint | 9 - Procedure for curing submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.11.1
checkpoint | Final Verification
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP