## Temporary Works R1
Temporary Works Inspection and Test Plan
Project: Misc.
Number and Revision: Temporary Works ITP Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 1 – DESIGN
1.01 | Temporary Works Drawing(s) | Detailed Temporary Works Drawing(s) to be issued by the Temporary Works Designer, and agreed with the Project Management Team, for the relevant portion of Temporary Works. | Downer | IFC Drawings | Prior to works start | H | Temporary Works Coordinator or PE
1.02 | Temporary Works Design Certificate | Temporary Works Design Certificate to be issued by the Temporary Works Designer, in conjunction with the Temporary Works Drawings, setting out all the considerations and requirements of the relevant Temporary Works portion. | Downer | Design Certificate | Prior to works start | H | Temporary Works Coordinator or PE
1.03 | Lift Certificate (for crane lifts only) | Where required, a Lift Certificate will be issued by the Temporary Works Designer, setting out all the considerations and requirements for lifting. | Downer | Lift Certificate | Prior to works start | H | Temporary Works Coordinator or PE
SECTION 2 – PERMIT TO LOAD
2.01 | Permit to Load Inspection | Complete a comprehensive inspection based on the temporary works drawings and the required methodology. | Downer | Site Records and sufficient photos to verify design requirements | As per Temporary Works Register | I | Temporary Works Coordinator or Temporary Works Representative
2.02 | Further Evidence | Any further evidence required, as set out in the Temporary Works Drawings, Design Certificate, or Lift Certificate, to be produced as per the relevant standard and attached here to support the Permit to Load sign-off - NDM test, Scala test, or other as specified. | Relevant industry, IANZ, AS/NZS Standards | Site Record Sheet or Lab Report | As per Temporary Works Design | I | Temporary Works Coordinator or SE
2.03 | Request for Authority Signoff | Being the appointed inspection reviewer of the above temporary works, I hereby certify that the works as described on the Temporary Works Certificate numbered above, and the associated documentation has been satisfactorily constructed. Approval is given to LOAD the temporary works as intended. | Downer | Hold Point Release | Prior to Loading | HP | Suitably Competent Engineer (Temporary works designer or Temporary Works Coordinator)
2.04 | Temporary Works Permit to Load Certificate | Permit to Load Certificate issued by Suitably Competent Engineer. | Downer | PTL Certificate | Prior to Loading | R | Temporary Works Coordinator or PE
SECTION 3 – PERMIT TO UNLOAD (IF REQUIRED)
2.01 | Permit to Unload Inspection | Complete a comprehensive inspection based on the temporary works drawings and requirements for unloading, as set out in the Design Certificate. | Downer | Site Records and sufficient photos to verify design requirements | As per Temporary Works Register | I | Temporary Works Coordinator or Temporary Works Representative
2.02 | Further Evidence | Any further evidence required, as set out in the Temporary Works Drawings or Design Certificate, to be produced as per the relevant standard and attached here to support the Permit to Unload sign-off - Compression test, NDM test, or other as specified. | Relevant industry, IANZ, AS/NZS Standards | Site Record Sheet or Lab Report | As per Temporary Works Design | I | Temporary Works Coordinator or SE
2.03 | Request for Authority Signoff | Being the appointed inspection reviewer of the above temporary works, I hereby certify that the permanent works as described on the Temporary Works Certificate numbered above, and the associated requirements for unloading has been satisfactorily completed. Approval is given to UNLOAD the temporary works as intended. | Downer | Hold Point Release | Prior to Unloading | HP | Suitably Competent Engineer (Temporary works designer or Temporary Works Coordinator)
2.04 | Temporary Works Permit to Unload Certificate | Permit to Unload Certificate issued by Suitably Competent Engineer. | Downer | PTU Certificate | Prior to Unloading | R | Temporary Works Coordinator or PE