## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Temporary Works ITP | itp |  |  |  |  | Temporary Works ITP Rev 1
section | SECTION 1 – DESIGN
checkpoint | 1.01 - Temporary Works Drawing(s)
label | Acceptance / Conformance Criteria - Detailed Temporary Works Drawing(s) to be issued by the Temporary Works Designer, and agreed with the Project Management Team, for the relevant portion of Temporary Works.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Activity - H
label | By - Temporary Works Coordinator or PE
checkpoint | 1.02 - Temporary Works Design Certificate
label | Acceptance / Conformance Criteria - Temporary Works Design Certificate to be issued by the Temporary Works Designer, in conjunction with the Temporary Works Drawings, setting out all the considerations and requirements of the relevant Temporary Works portion.
label | Standard / Specification - Downer
label | Verifying Document - Design Certificate
label | Frequency - Prior to works start
label | Activity - H
label | By - Temporary Works Coordinator or PE
checkpoint | 1.03 - Lift Certificate (for crane lifts only)
label | Acceptance / Conformance Criteria - Where required, a Lift Certificate will be issued by the Temporary Works Designer, setting out all the considerations and requirements for lifting.
label | Standard / Specification - Downer
label | Verifying Document - Lift Certificate
label | Frequency - Prior to works start
label | Activity - H
label | By - Temporary Works Coordinator or PE
section | SECTION 2 – PERMIT TO LOAD
checkpoint | 2.01 - Permit to Load Inspection
label | Acceptance / Conformance Criteria - Complete a comprehensive inspection based on the temporary works drawings and the required methodology.
label | Standard / Specification - Downer
label | Verifying Document - Site Records and sufficient photos to verify design requirements
label | Frequency - As per Temporary Works Register
label | Activity - I
label | By - Temporary Works Coordinator or Temporary Works Representative
checkpoint | 2.02 - Further Evidence
label | Acceptance / Conformance Criteria - Any further evidence required, as set out in the Temporary Works Drawings, Design Certificate, or Lift Certificate, to be produced as per the relevant standard and attached here to support the Permit to Load sign-off - NDM test, Scala test, or other as specified.
label | Standard / Specification - Relevant industry, IANZ, AS/NZS Standards
label | Verifying Document - Site Record Sheet or Lab Report
label | Frequency - As per Temporary Works Design
label | Activity - I
label | By - Temporary Works Coordinator or SE
checkpoint | 2.03 - Request for Authority Signoff
label | Acceptance / Conformance Criteria - Being the appointed inspection reviewer of the above temporary works, I hereby certify that the works as described on the Temporary Works Certificate numbered above, and the associated documentation has been satisfactorily constructed.
label | ○ Approval is given to LOAD the temporary works as intended.
label | Standard / Specification - Downer
label | Verifying Document - Hold Point Release
label | Frequency - Prior to Loading
label | Activity - HP
label | By - Suitably Competent Engineer (Temporary works designer or Temporary Works Coordinator)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Temporary Works Permit to Load Certificate
label | Acceptance / Conformance Criteria - Permit to Load Certificate issued by Suitably Competent Engineer.
label | Standard / Specification - Downer
label | Verifying Document - PTL Certificate
label | Frequency - Prior to Loading
label | Activity - R
label | By - Temporary Works Coordinator or PE
section | SECTION 3 – PERMIT TO UNLOAD (IF REQUIRED)
checkpoint | 2.01 - Permit to Unload Inspection
label | Acceptance / Conformance Criteria - Complete a comprehensive inspection based on the temporary works drawings and requirements for unloading, as set out in the Design Certificate.
label | Standard / Specification - Downer
label | Verifying Document - Site Records and sufficient photos to verify design requirements
label | Frequency - As per Temporary Works Register
label | Activity - I
label | By - Temporary Works Coordinator or Temporary Works Representative
checkpoint | 2.02 - Further Evidence
label | Acceptance / Conformance Criteria - Any further evidence required, as set out in the Temporary Works Drawings or Design Certificate, to be produced as per the relevant standard and attached here to support the Permit to Unload sign-off - Compression test, NDM test, or other as specified.
label | Standard / Specification - Relevant industry, IANZ, AS/NZS Standards
label | Verifying Document - Site Record Sheet or Lab Report
label | Frequency - As per Temporary Works Design
label | Activity - I
label | By - Temporary Works Coordinator or SE
checkpoint | 2.03 - Request for Authority Signoff
label | Acceptance / Conformance Criteria - Being the appointed inspection reviewer of the above temporary works, I hereby certify that the permanent works as described on the Temporary Works Certificate numbered above, and the associated requirements for unloading has been satisfactorily completed.
label | ○ Approval is given to UNLOAD the temporary works as intended.
label | Standard / Specification - Downer
label | Verifying Document - Hold Point Release
label | Frequency - Prior to Unloading
label | Activity - HP
label | By - Suitably Competent Engineer (Temporary works designer or Temporary Works Coordinator)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Temporary Works Permit to Unload Certificate
label | Acceptance / Conformance Criteria - Permit to Unload Certificate issued by Suitably Competent Engineer.
label | Standard / Specification - Downer
label | Verifying Document - PTU Certificate
label | Frequency - Prior to Unloading
label | Activity - R
label | By - Temporary Works Coordinator or PE