## QA Folder Structure
QA Folder Structure |  |  | Checklists
Site QA
| Project Photos |  | Project Photos Checklist
Site Wide
Sewer
QA8.1A – Below Ground Sewer Checklist
Grease Waste
QA8.1 - Below Ground Drainage Checklist
Stormwater
QA8.1B – Stormwater Drainage Checklist
Water and Fire Services
• QA8.1C - Below Ground Fire Service Pipework Checklist
• QA8.1D – Below Ground Water Pipework Checklist
• QA6 - Quality Control Pressure Test Report
Building Works
Sewer
QA8.1A – Below Ground Sewer Checklist
Trade Waste
Grease Waste
QA8.1 - Below Ground Drainage Checklist
Water and Fire Service
QA8.1C - Below Ground Fire Service Pipework Checklist
QA8.1D – Below Ground Water Pipework Checklist
QA6 - Quality Control Pressure Test Report

## Checklists ITPs
type | name | values | prefix | "Add+" Template Name | Q's for CONQA
checklist-flat | QA 8.1 - Below Ground Drainage Checklist |  |  | 8.1 - Below Ground Drainage Checklist
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out pits, trench depths and runs.
text | Drawing & Revision #
text | Survey setout completed by:
text | Starting IL established - enter IL
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Materials used:
button | Approved by Principal | Yes,No
checkpoint | Bedding material, placement and compaction meets specification.
label | Spec#: AS3500 and Hydraulic Specification
Text: | Material used:
checkpoint | Laying and jointing of pipes - RL and fall
Text: | Jointing Type:
Text: | Fall:
Text" | AS3500
checkpoint | Service run was inspected prior being covered
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Principal Contractor Representative Sign-Off added below | Yes,No
checkpoint | Hydrostatic tests are carried out as required.
button | Air or Water? | Water,Air
text | Geschke - Initial/Date
text | Principal- Initial/Date
checkpoint | Placement and compaction of backfill and material meets spec
Text | Material used:
checkpoint | Temporary cover provided to open drain.
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
button | Drain installed as per nominated drawing | Yes,No
Text: | Comments
checkpoint | Invert levels checked by a surveyor
label | As Built drawings and 3D Model to be updated as required
checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
label | Company: Geschke Group
label | Phone: 03 9798 1619
label | Address: 45 Pacific Drive, Keysborough
label | Project: Resilience Australia
label | Principal: MULTIPLEX
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Representative Sign-Off added below | Yes,No
checklist-flat | QA 8.1A - Below Ground Sewer Checklist |  |  | 8.1A - Below Ground Sewer Checklist
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out pits, trench depths and runs.
text | Drawing & Revision #
text | Survey setout completed by:
text | Starting IL established - enter IL
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Materials used:
button | Approved by Principal | Yes,No
checkpoint | Bedding material, placement and compaction meets specification.
label | Spec#: AS3500 and Hydraulic Specification
Text: | Material used:
checkpoint | Laying and jointing of pipes - RL and fall
Text: | Jointing Type:
Text: | Fall:
Text" | AS3500
checkpoint | Connections to pits and existing services as per Hydraulic Specification and Australian Standards
checkpoint | Hydrostatic tests are carried out as required.
button | Air or Water? | Water,Air
button | Inspected and recorded by Independent Certifier or PIC | Yes,N/A, No
text | Geschke - Initial/Date
text | Principal- Initial/Date
checkpoint | Placement and compaction of backfill and material meets spec
Text | Material used:
checkpoint | Temporary cover provided to open drain.
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
button | Drain installed as per nominated drawing | Yes,No
Text: | Comments
label | As Built drawings and 3D Model to be updated as required
checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
label | Company: Geschke Group
label | Phone: 03 9798 1619
label | Address: 45 Pacific Drive, Keysborough
label | Project: Resilience Australia
label | Principal: MULTIPLEX
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | MULTIPLEX Representative Sign-Off added below | Yes,No
checklist | QA 16.1 - Electrofusion Welding - Field Operational Sheet |  |  | QA 16.1 - Electrofusion Welding -
checkpoint | Operator Details
text | Name
text | ID No.
text | Company
text | Address
text: | Training ticket / certificate No.
checkpoint | Welding Machine Details
text | Manufacturer
text | Type/Model
text | Serial Number
text | Year Built
label: | Attach calibration certificate
checkpoint | Actual Pipe Size
text | Type
text | Brand
text | En
text | OD
text | Ovality %
checkpoint | Fitting Data
text | Brand
text | Type (Coupling, Tee, Reducer etc.)
checkpoint | Unit Setting
text | Manual
text | Automatic
checkpoint | Preparation
text | Cleaned and Peeled
text | Pipe/Fitting Clamped
checkpoint | Welding Times
text | Joining Seconds
text | Cooling Minutes
checkpoint | Conditions
text | Ambient Temp
text | Weather
text | Preventive Measures
checkpoint | Power
text | Mains
text | Gen Set
checkpoint | Operator Sign Off
checkpoint | Foreman Sign-Offs
checklist | QA 8.1B - Stormwater Drainage Checklist |  |  | 8.1B - Stormwater Drainage Checklist
checkpoint | Stormwater Drainage Inspection Report Details:
text | Spec No.:
text | Drawing & Revision no.:
text: | Shop Drawings no:
text: | Starting IL established:
checkpoint | Pipes and fittings comply with relevant Authority and Specification
label | Spec#: AS3500 and Hydraulic Specification
text | Materials used, Size and Class:
button | Approved by Principal | Yes,No
checkpoint | Pipe Lines
text | Date started:
text | Drainage Line Number:
button | Pipe Damaged? | Yes,No
text | Jointing Required
button | Bedding and Haunching | Yes,No
checkpoint | Bedding material, placement and compaction meets specification.
label | Spec#: AS3500 and Hydraulic Specification
Text: | Material used:
text | GPL - Initial/Date
text | Builder - Initial/Date
checkpoint | Laying and jointing of pipes - RL and fall
Text: | Jointing Type:
Text: | Fall:
Text" | AS3500
Text: | RL's as installed
text | GPL - Initial/Date
text | Builder - Initial/Date
checkpoint | Backfill
label | Spec#: AS3500 and Hydraulic Specification
Text: | Material used:
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Principal Contractor Representative Sign-Off added below | Yes,No
checkpoint | Drainage Pits
text | Date Installed:
text | Pit Number:
text | Pit Base:
text | Step Irons - GPL Initial/Date
text | Bedding - GPL Initial/Date
label | Benching, Grouting and Patching
label | Placement of cover
button | Concreting of cover | Yes,No
text | Comments
label | Final Sign Off (Initial & Date)
text | GPL
text | Builder - Initial/Date
checkpoint | Pit Sign off: Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Principal Contractor Representative Sign-Off added below | Yes,No
checklist | QA 8.1C - Below Ground Fire Service Pipework Checklist |  |  | 8.1C - Below Ground Pipework Checklist - Fire
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out trench depths and runs.
label | Project drawing #
label | Shop drawing #
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500
text | Material used
button | Approved by Principal | Yes,No
checkpoint | Bedding placement and compaction and material meets specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Geschke - Initial/Date
text | Principal- Initial/Date
text | Comments
checkpoint | Jointing of pipes
Text | Jointing type
Text | Attach welding checklist if applicable
text | Geschke - Initial/Date
text | Comments
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
label | Fire system tested to 1700 kpa regularly prior to finished surfaces installed. Independent fire test at completion.
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes, no
label | Detectable marker tape
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings and 3D Model
label | To be provided
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Principal Contractor Representative Sign-Off added below | Yes,No
checklist | QA 8.1D - Below Ground Water Pipework Checklist |  |  | 8.1D - Below Ground Water Pipework Checklist
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out trench depths and runs.
text | Project drawing #
text | Shop drawing #
text | Depth of the installed run
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500
text | Material used
button | Approved by Principal | Yes,No
checkpoint | Bedding placement and compaction and material meets specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Geschke - Initial/Date
text | Principal- Initial/Date
text | Comments
checkpoint | Jointing of pipes
Text | Jointing type
Text | Attach welding checklist if applicable
text | Geschke - Initial/Date
text | Comments
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
text | Water system tested to (kPa)
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes, no
label | Detectable marker tape
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings and 3D Model
label | To be provided
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Principal Contractor Representative Sign-Off added below | Yes,No
checklist | QA 6.1 - Quality Control Pressure Test Report |  |  | QA 6.1 - Quality Control Pressure Test Report
checkpoint | Quality Control Pressure Test Report:
text | Drawing No.:
text | Rev.:
button | Test: | Air,Water
text | Section
text | From
text | To
text | Applicable Standard No.
label | Specified System Working
text | Pressure (KPA)
text | Duration (HRS)
label | Specified System Test
text | Pressure (KPA)
text | Duration (HRS)
checkpoint | 1st Reading
text | Time
text | KPA
text | Ambient Temp
checkpoint | 2nd Reading
text | Time
text | KPA
text | Ambient Temp
checkpoint | Test Result - Passed?
text | Repeat
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Principal Contractor Representative Sign-Off added below | Yes,No
checklist | Water Services Flushing |  |  | QA 32 - Water Main Flushing
checkpoint | Water Services Flushing Details:
text | Zone/Pod No's:
Bool | Mains
Bool | Cold Water
Bool | Fire Hydrant
Bool | RW
checkpoint | As built information updated onto drawings
label | Ongoing
label | To be provided
checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
label | Company: Geschke Group
label | Phone: 03 9798 1619
label | Address: 45 Pacific Drive, Keysborough
label | Project: Resilience Australia
checkpoint | Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Supervisor Sign-Off added below | Yes, No
button | Principal Contractor Representative Sign-Off added below | Yes, No