## Checklists
type | name | values
checklist | Steel & Shotcrete ITP
section | Prior to Start
checkpoint | Submit site specific SWMS |  | Remove
checkpoint | Approval of shotcrete mix design
Tick box | Mix design sent and approved |  | Add under "Approval of shotcrete mix design"
checkpoint | Locate washout area
checkpoint | Provision of Certificates and test results |  | Add "Provision of Certificates and test results"
Tick box | Documents provided and attached |  | Add under "Provision of Certificates and test results"
section | Shotcrete Preparation
checkpoint | Surface check
Tick box | Surface checks of formwork and column dimensions - as per design drawings |  | Add under "Surface check"
checkpoint | Place reinforcement as per design drawings on Column Encasement
Tick Box | Required mesh secured with pins as per structural drawings |  | Add under "Place reinforcement as per design drawings on Column Encasement"
checkpoint | Inspection of shotcrete wall and/or Column
Tick box | Visual inspection to verify Mesh/Steel is as per structural drawings |  | Add under "Inspection of shotcrete wall and/or Column"
checkpoint | Testing of shotcrete
Tick Box | Onsite slump and visual testing by qualified concrete tester (4 Cylinders required for testing) |  | Add under "Testing of shotcrete"
checkpoint | Placement of shotcrete
Tick Box | Place shotcrete no less than the minimum thickness and cover as per structural drawings Design Strength of Concrete as noted on the structural drawing |  | Add under "Placement of shotcrete"
checkpoint | Finish of shotcrete
Tick box | Sponge Finish c/w expansion and construction joints as per structural drawings |  | Add under "Finish of shotcrete"

## Project Structure
Folder Structure | Checklists
Site QA