## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Steel & Shotcrete ITP |  |  |  |  | Yes | Steel & Shotcrete ITP | 759afd48-3b62-4c85-88e0-156751e4a9a6
checkpoint-group |  |  | section | Prior to Start
checkpoint-status |  |  | checkpoint | Submit site specific SWMS
checkpoint-status |  |  | checkpoint | Approval of shotcrete mix design
checkpoint-status |  |  | checkpoint | Locate washout area
checkpoint-group |  |  | section | Shotcrete Preparation
checkpoint-status |  |  | checkpoint | Surface check
checkpoint-status |  |  | checkpoint | Place reinforcement as per design drawings on Column Encasement
checkpoint-status |  |  | checkpoint | Inspection of shotcrete wall and/or Column
checkpoint-status |  |  | checkpoint | Testing of shotcrete
checkpoint-status |  |  | checkpoint | Placement of shotcrete
checkpoint-status |  |  | checkpoint | Finish of shotcrete