## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | GT4-ITP-017 - Concrete Rigid Pavement Construction | itp |  |  |  | Yes | GT4-ITP-017 - Concrete Rigid Pavement Construction
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents: PSP, EMP, TMP, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Concrete Mix Design
label | Frequency: Prior to first concrete pour
label | Acceptance Criteria: Concrete shall comply with the requirements outlned with defined pavement options specified within the Early works, Civil design drawings. Unless specified, then concrete used in this construction shall conform to AS 3600 and be provided by an approved pre-mixed concrete supplier, conforming with AS 1379.
label | Reference Documents: C.10.1 Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed, Mix design approval
label | HP*
label | Responsibility: Site Engineer/ Superintendent
date | Date Completed:
section | 2 - Initial Works
checkpoint | 2.1 - Setting Out
label | Frequency: Prior to start
label | Acceptance Criteria: Set out work in accordance with drawings. The Engineer and Supervisor will review and confirm set out with the surveyor.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP*
label | Responsibility: Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.2 - Pre-Seal Inspection
label | Frequency: Each Lot
label | Acceptance Criteria: Pre-Seal Inspection will be completed to ensure surface adequate for spray sealing
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | HP
label | Responsibility: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - De-Bonding Treatment
label | Frequency: Each Lot
label | Acceptance Criteria: Bitumen sprayed seal with 5-7mm aggregate or bitumen emulsion to be placed between Cement Treated Crushed Rock (CTCR) layer and Concrete.
label | Reference Documents: EW-CE-DRW-406-001
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
section | 3 - Construction Works
checkpoint | 3.1 - Formwork
label | Frequency: Each Lot
label | Acceptance Criteria: All formwork, shall be accurately constructed to the required lines and strong enough to remain in position without displacement during placement, compaction and support of concrete, and shall extend to the full depth of the concrete.
label | Reference Documents: C.10.5 AS 3610
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Reinforcement
label | Frequency: Each Lot
label | Acceptance Criteria: SL82 Mesh to be installed with a minimum 60mm cover to the surface. Reinforcement must comply with the requirements of AS/NZS 4671. Reinforcement mesh is not to continue through joint.
label | Reference Documents: DWG EW-CE-DRW-416-001 (Rev C) C.10.10
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Dowels
label | Frequency: Each Lot
label | Acceptance Criteria: Dowel bar size, length and spacing along the joints (Section 9.4.6 of Austroads 2017): 24mm diameter, 450mm long Grade 250N round bars at 300mm center to center spacing.
label | Reference Documents: C.10.28 DWG EW-CE-DRW-416-001 (Rev C)
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Tie Bars
label | Frequency: Each Lot
label | Acceptance Criteria: Tie bars should not be installed within a distance of 500mm from a contraction joint. The tie bars are recommended to be at least 1m long, 12mm diameter deformed steel bars. The spacing of tie bars can be determined from the ‘drag’ formula identified in Austroads, 2017.
label | Reference Documents: C.10.29 DWG EW-CE-DRW-416-001 (Rev C)
label | Inspection / Test Method: Verify
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Authority to Place Concrete
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete shall not be placed until:
label | (i) the evidence that the set-out and any formwork or reinforcement is conforming to the requirements of the specification and the drawings and has been reviewed by the Superintendent
label | (ii) Prior to placing concrete, all formwork, equipment to handle concrete, excavated areas, reinforcement and existing adjacent concrete are to be clean of all foreign matter and water.
label | ○ Superintendent requires 48 HR notice for inspection.
label | Reference Documents: C.10.6
label | Inspection / Test Method: Inspection / Test Method
label | Record of conformity: Inspection Checklist Doc No: 65473-CI-01A
label | HP
label | Responsibility: Site Engineer / Superintendant
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Concrete Placement
label | Frequency: Each Lot
label | Acceptance Criteria: The concrete pavement shall be a 160mm jointed reinforced concrete pavement with a characteristic 28-day flexural strength not less than 4.5mpa
label | Reference Documents: DWG EW-CE-DRW-406-001 (Rev E) C.10.6, C.10.26
label | Inspection / Test Method: Inspection / Test Method
label | Record of conformity: Visual Inspection, doc. No. 64573-CI 01D
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 3.7 - Compaction
label | Frequency: Each Lot
label | Acceptance Criteria: The entire volume of the pavement shall be thoroughly compacted using vibrators to ensure each load of concrete is vibrated into the face of the previously placed concrete and into edges, joints and around dowel bars and the like.
label | Reference Documents: C.10.7
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 3.8 - Surface Finish
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete pavements shall be finished with a steel trowel to a smooth surface at the correct levels, grades and shapes. After trowelling, the surfaces of pavements subject to traffic shall be broomed to form a non-skid surface with the pattern of the lines running in one direction only.
label | Reference Documents: C.10.12
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: ITP Signed
label | IP
label | Responsibility: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 3.9 - Joints
label | Frequency: Each Joint
label | Acceptance Criteria: Dowelled Expansion Joint
label | ○ Dowelled expansions joints shall be installed for transverse joints at 6m spacing.
label | ○ Dowells to be 24mm Ø grade 250N, 450mm long dowel bars @ 300 CTS debonded at one end.
label | ○ Cover from dowels to surface to be D/2 +/-25mm
label | ○ Cover from mesh reinfoircement to expansion joint to be 75mm each side.
label | ○ Joint to be sealed in accordance with Detail F of NSW transport RMS Standard Drawing DS2014/005559 ED2 Rev 0 (See below)
label | Tied Construction Joint
label | ○ Reinforcement to be N12 deformed bars @ 500 cts. 1000 mm long extending 500mm +/-35mm into each side.
label | ○ Joint to be sealed in accordance with Detail F of NSW transport RMS Standard Drawing DS2014/005559 ED2 Rev 0 (See below)
label | Reference Documents: EW-CE-DRW-416-001, NSW transport RMS Standard Drawing DS2014/005559 ED2 Rev 0, See Drawings Below
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 3.10 - Protection of concrete
label | Frequency: Each Lot
label | Acceptance Criteria: The finished product shall be protected from damage by passers-by and construction traffic through the use of bollards. Pavement to be protected for a period of 28-days following the last concrete pour. During this period the area shall remain untrafficked.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed
label | IP
label | Responsibility: Site Foreman
date | Date Completed:
checkpoint | 3.11 - Curing
label | Frequency: Each Lot
label | Acceptance Criteria: Approved covering shall be provided to protect the concrete surfaces against rain, hail, dust or any other cause that may damage the concrete during the carrying out of the work. The formwork may be stripped after 24 hours, but sufficient timbering must be provided to protect all exposed edges for at least four (4) days or longer, where in the opinion of the Builder, damage is likely to occur. The contractor will apply curing compound as per C.10.13 of the project specification.
label | Reference Documents: C.10.13
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP Signed checklist doc no: 65473-CI 01E
label | IP
label | Responsibility: Site Engineer/ Site Foreman
date | Date Completed:
section | 4 - Completion
checkpoint | 4.1 - Carry out sampling of concrete - strength and consistency
label | Frequency: Each 50m3
label | Acceptance Criteria: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Checklist
label | Record of conformity: ITP Signed/Test Records
label | TP
label | Responsibility: Site Engineer
date | Date Completed:
checkpoint | 4.2 - As-constructed survey and conformance documentation
label | Frequency: Each Lot (1 per day)
label | Acceptance Criteria: As-Built Survey Lot Maps shall be completed to show the extent of works for each lot.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: Visual match existing / This ITP signed off
label | SCP
label | Responsibility: FH Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
signoff | Sign ITP