## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-007-STR-Bridge Beams-Material Inspection-Precast Beams | itp |  |  |  | Yes | CHK-007-STR-Bridge Beams-Material Inspection-Precast Beams
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-007-STR-Bridge Beams-Material Inspection-Precast Beams
label | ITP list Description: Precast Beams Material Inspection
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 13/11/2023
label | ITP created by: Jon De Castro
label | ITP approved for use by: Jon De Castro
checkpoint | 1 - Delivery Details
label | Reference - Delivery Dockets/Packing List
label | Acceptance Criteria -
textbox | Enter: Delivery Docket Number:
textbox | Enter: Delivery Date:
textbox | Enter: Element ID / Birth Certificate:
textbox | Attach: Delivery Docket and packaging Slip
label | Method - Document Review Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 2 - Packaging Inspection-Quantity
label | Reference - Delivery Dockets/Packing List
label | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | Method - Document Review Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 3 - Packaging Inspection-Delivery Contents
label | Reference - Delivery Dockets/Packing List
label | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
label | Method - Document Review Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 4 - Packaging Inspection-Birth Certificate
label | Reference - Delivery Dockets/Packing List / Panel IDs
label | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
label | ○ Precast components are to be marked on the birth certificate.
label | ○ Cast date and lot are to be marked on the birth certificate.
label | Method - Document Review Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 5 - Packaging Inspection-Transport
label | Reference - Delivery Dockets/Packing List
label | Acceptance Criteria - Is the condition of packaging acceptable. Precast items are protected from damage during the transport
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 6 - Fault IDs:
label | Reference - Delivery Dockets/Packing List/IFC Drawings
label | Acceptance Criteria - For each precast element delivered, check for the following:
label | 1-Identification markings match the panel type
label | 2-Panels fabricated as per drawings
label | 3-Cracks
label | 4-Spalling/Damage to concrete surface
label | 5-Exposed Reinforcement
label | 6-Damage to Anti-Graffiti coating (where applicable)
label | 7-Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
label | 8- Others
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 7 - Check for Faults - 1
label | Reference - Item 1 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 8 - Check for Faults - 2
label | Reference - Item 2 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 9 - Check for Faults - 3
label | Reference - Item 3 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 10 - Check for Faults - 4
label | Reference - Item 4 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 11 - Check for Faults - 5
label | Reference - Item 5 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 12 - Check for Faults - 6
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 13 - Check for Faults - 7
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | 14 - Check for Faults - 8
label | Reference - Item 8 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Document Review Visual Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed Off
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP