## Table 1
Bus Shelter Foundation Inspection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - 006 - Rev 00
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By | MSQA signature (Blank as Req.) | Engineer Rep Signature (Blank as req.) | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
2001-01-03 | Construction Pack | Submit a Construction Pack including a Methodology and JSEA to the Engineer before works | Downer | Construction Pack | Submit 5 days prior to commencement of works | H | PE |  | R
2002-02-03 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre- construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
2003-01-03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
2004-02-03 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
2005-01-03 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE |  | R
2006-02-03 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Level and shape of Subgrade | pavement subgrade tolerance ; +/-10mm from design subgrade level. Excavation deppth must be at least the design pavement depth for LMC locations. Subgrade shape as per survey set out, to be verified on site | Aurecon Civil Spec; Section 5.6.9 | As-Built | Once per footing | I | SE | R
4.02 | Aggregate basecourse (If used) AP65 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. Grading to be compliant with AT 0800 grading specification | Aurecon Civil Spec 6.5.2 TNZ M/4 | Material Certificate / QA Sheets | Prior to Use | H | SE | R
4.03 | Mix design (Concrtee and Blinding) | Blinding to be 10Mpa mix Typical structures - confirm supply of "high strength concrete"; 20MPa concrete; 19mm max aggregate size. As specified on drawing use marine grade concrete 30MPa, | Aurecon Civil Spec Section 14.6 | Approval Mix Design | As required | H | PE | R
SECTION 5 – CONSTRUCTION ACTIVITY – BUS SHELTER FOUNDATIONS
5.01 | Setting Out | Before construction,Contractor to mark out extents of structure | Downer | Pre pour checksheet | Once per struture | I | SE | I
5.02 | Subgrade Testing | Conctractor to confirm subgrade strength and report to Engineer via QA inspection | Aurecon Civil Spec; Section 5.6.11 | Pre pour checksheet | Once per struture | H | SE | I
5.03 | Blinding Layer | 50mm 10Mpa blinding layer to be placed within footpring of structure | DRG-SS-2270 | Pre pour checksheet | Once per struture | I | SE
5.04 | Concrete | All concrete shall be batched by weight and mixed in an approved plant requirments of NZS 3104 High grade and Special Grade Concrete for sturtcures to be 30Mpa concrete with slump target as per mix design 3 Cylinders taken per pour | Aurecon Civil Spec Section 13.6.3 Clause 2.15.5.3.2 of NZS 3104 | Supplier Records Concrete Dockets | Once per Pour | H | PE | R | R
5.05 | Reinforcement | Reinforcement and embedded items cut, bent (cold) and accurately placed as shown on design drawings. At least 30mm cover to all reinforcing +5mm-0mm Bar spacing as per drawings +/- 10 mm Bend locations as per drawings +/-5mm | Aurecon Civil Spec;14.6.7 AS/NZS 4671 | Prior to Each pour QA Checksheet | In progress check | I | SE | I
5.06 | Pre-Pour Inspection | Notify Engineer for inspection of formwork 24 hours prior to pour I nspection | _ | Prior to Each pour QA Checksheet | Once per Pour | H | SE | H
5.1.2 | Post Pour | concrete curing for at least 5 days. Form removal after atleast 12 hours. Post pour inspection to be submmitted for Engineer's acknowlegement showing finished concrete is within tolerances (surface level +/-5 mm) | Aurecon Civil Spec Section 10.1.11 NZS 2566.2; Section 6.3.4.1 & 6.3.4.2 | Test Report | Each foundation | H | SE | R
5.1.3 | Testing | Slump test during pout to check workability of concrete or as directed by Engineer 3 cylinder test taken for each pour. Slump target as per mix design | Aurecon Civil Spec 14.7.12 NZS 3112 | Prior to Each pour QA Checksheet | In progress check | H | SE | R
5.1.4 | Independent testing (If Requested) | The Engineer's Rep may request site samples/ cores for independent testing of fresh or cured concrete to review the grading, mix design, strength and thickness | _ | Upon Request | IANZ lab resport | W | SE | R | R
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
2001-01-06 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE | R | H
2002-01-06 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting. Installation of works under contract compliant and in accordance with all rlevenat regulations, COP and standards unless specified by the engineer | Downer | Records | Post construction | H | SV | R | H
2003-01-06 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | H | PE | R | H
2004-01-06 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE | R | H