## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1211-004-ITP Light Pole Foundation | itp |  |  |  |  | DN1211-004-ITP Light Pole Foundation
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.1 - Construction Pack
label | Acceptance/Conformance criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
label | Standard/Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 5 days prior to commencement of works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Survey Setout
label | Acceptance/Conformance criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard/Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
label | MSQA signature - C
checkpoint | 3.3 - Service Location
label | Acceptance/Conformance criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard/Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.4 - Internal Permits
label | Acceptance/Conformance criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard/Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.5 - External Permits
label | Acceptance/Conformance criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard/Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Engineer Rep Signature - R
checkpoint | 3.6 - Approved Construction Drawings
label | Acceptance/Conformance criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard/Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.1 - Mix Design
label | Acceptance/Conformance criteria - Concrete to be 30Mpa as per DRG-SS-2231 19mm max aggregate . Contractor to provide mix design and strength testing records on request
label | Standard/Specification - Downer
label | Verifying Document - Approved MAR
label | Frequency - Once Prior
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - R
checkpoint | 4.2 - Mortar
label | Acceptance/Conformance criteria - Consisting of two parts fine, sharp, well graded sand to one part dry cement.
label | ○ Mix by hand or mixer in small quantities use within 30 minutes
label | Standard/Specification - Downer
label | Verifying Document - Approved MAR
label | Frequency - Once Prior
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - R
checkpoint | 4.3 - Reinforcing
label | Acceptance/Conformance criteria - Reinforcing as per Aurecon Specification
label | Standard/Specification - Downer
label | Verifying Document - Approved MAR
label | Frequency - Once Prior
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - R
checkpoint | 4.4 - Hold Down bolts
label | Acceptance/Conformance criteria - Hold Down bolts as per pole manufacturers requirements
label | Standard/Specification - Downer
label | Verifying Document - Approved MAR
label | Frequency - Once Prior
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - R
section | SECTION 5 – CONSTRUCTION ACTIVITY – LIGHT POLE INSTALLATION
checkpoint | 5.1 - Set
label | Acceptance/Conformance criteria - Centre of Pile set out as per Model coordinates provided.
label | ○ Hold down bolts to be surveyed to essure they align with the location of Light pole bolts.
label | Standard/Specification - Downer
label | Verifying Document - QA Checksheet
label | Frequency - Prior to concrete pour
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 5.2 - Reinforcing
label | Acceptance/Conformance criteria - Reinforcing and embedded items cut, bent (cold) and accurately placed as shown on design drawings. At least 30mm cover to all reinforcing +5mm/-0mm
label | ○ Bar spacing as per Drawings +/-10mm Bend locations as per drawings +/-5mm
label | Standard/Specification - Downer
label | Verifying Document - QA Checksheet
label | Frequency - Prior to concrete pour
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 5.3 - Conduit Install
label | Acceptance/Conformance criteria - Conduits installed as per NUO requirements and DRG-SS-2231
label | Standard/Specification - Downer
label | Verifying Document - QA Checksheet
label | Frequency - Prior to concrete pour
label | Verification Activity: Activity - I
checkpoint | 5.4 - Pre Pour inspection
label | Acceptance/Conformance criteria - Notify Engineer for inspection atleast 24 hours prior to pour
label | Standard/Specification - Downer
label | Verifying Document - Pre pour checksheet
label | Frequency - Prior to concrete pour
label | Verification Activity: Activity - H
label | Verification Activity: By - DES
label | MSQA signature - C
checkpoint | 5.5 - Light pole bases / Pile
label | Acceptance/Conformance criteria - Concrete shall be high grade with a minimum compressive strength at 28 days of 30 MPa
label | ○ Concrete slump shall be 175mm +/-25 mm.
label | ○ Concrete to be tremied. Vibrating pokers to be used during entire pile length pour.
label | ○ Delivery dockets dated and showing the concrete supplier and design strength shall be collected and held for every pour. Record location and date of each pour.
label | ○ 3 cylinders taken for each pour slump targets as per mix design (1 sample per 75m^3 or each pour)
label | Standard/Specification - Aurecon Spec 15.5
label | Verifying Document - QA Checksheet
label | Frequency - each structure During pour
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
label | MSQA signature - W
checkpoint | 5.6 - Post Pour
label | Acceptance/Conformance criteria - Concrete cylinders to achieve minimum target satrenght after 28 days. At the Engineers request site samples/cores for indepentdant testing of fresh or cured concrete to review grading, mix design, strength and thickness.
label | Standard/Specification - Aurecon spec 13.
label | Verifying Document - Test Report
label | Frequency - As requested
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | MSQA signature - R
label | Engineer Rep Signature - R
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.1 - Construction Record Compilation
label | Acceptance/Conformance criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Survey Records
label | Acceptance/Conformance criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Redline Drawings
label | Acceptance/Conformance criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard/Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Defect, Snag and Punch List
label | Acceptance/Conformance criteria - Update the project Defect, Snag and Punch List Register
label | Standard/Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1211-006-ITP Bus Shelter Foundation | itp |  |  |  |  | DN1211-006-ITP Bus Shelter Foundation
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.2001 - Construction Pack
label | Acceptance/Conformance criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
label | Standard/Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 5 days prior to commencement of works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Engineer Rep Signature - R
checkpoint | 3.02.2002 - Survey Setout
label | Acceptance/Conformance criteria - Survey Set out as per contract drawings and specification, capturing pre- construction levels where needed.
label | Standard/Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.2003 - Service Location
label | Acceptance/Conformance criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard/Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.02.2004 - Internal Permits
label | Acceptance/Conformance criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard/Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.2005 - External Permits
label | Acceptance/Conformance criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard/Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Engineer Rep Signature - R
checkpoint | 3.02.2006 - Approved Construction Drawings
label | Acceptance/Conformance criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard/Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01 - Level and shape of Subgrade
label | Acceptance/Conformance criteria - pavement subgrade tolerance ; +/-10mm from design subgrade level. Excavation deppth must be at least the design pavement depth for LMC locations. Subgrade shape as per survey set out, to be verified on site
label | Standard/Specification - Aurecon Civil Spec; Section 5.6.9
label | Verifying Document - As-Built
label | Frequency - Once per footing
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | MSQA signature - R
checkpoint | 4.02 - Aggregate basecourse (If used) AP65
label | Acceptance/Conformance criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | ○ Grading to be compliant with AT 0800 grading specification
label | Standard/Specification - Aurecon Civil Spec 6.5.2 TNZ M/4
label | Verifying Document - Material Certificate / QA Sheets
label | Frequency - Prior to Use
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | MSQA signature - R
checkpoint | 4.03 - Mix design (Concrtee and Blinding)
label | Acceptance/Conformance criteria - Blinding to be 10Mpa mix
label | ○ Typical structures - confirm supply of "high strength concrete"; 20MPa concrete; 19mm max aggregate size.
label | ○ As specified on drawing use marine grade concrete 30MPa,
label | Standard/Specification - Aurecon Civil Spec Section 14.6
label | Verifying Document - Approval Mix Design
label | Frequency - As required
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
section | SECTION 5 – CONSTRUCTION ACTIVITY – BUS SHELTER FOUNDATIONS
checkpoint | 5.01 - Setting Out
label | Acceptance/Conformance criteria - Before construction,Contractor to mark out extents of structure
label | Standard/Specification - Downer
label | Verifying Document - Pre pour checksheet
label | Frequency - Once per struture
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | MSQA signature - I
checkpoint | 5.02 - Subgrade Testing
label | Acceptance/Conformance criteria - Conctractor to confirm subgrade strength and report to Engineer via QA inspection
label | Standard/Specification - Aurecon Civil Spec; Section 5.6.11
label | Verifying Document - Pre pour checksheet
label | Frequency - Once per struture
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | MSQA signature - I
checkpoint | 5.03 - Blinding Layer
label | Acceptance/Conformance criteria - 50mm 10Mpa blinding layer to be placed within footpring of structure
label | Standard/Specification - DRG-SS-2270
label | Verifying Document - Pre pour checksheet
label | Frequency - Once per struture
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.04 - Concrete
label | Acceptance/Conformance criteria - All concrete shall be batched by weight and mixed in an approved plant requirments of NZS 3104 High grade and Special Grade
label | ○ Concrete for sturtcures to be 30Mpa concrete with slump target as per mix design
label | ○ 3 Cylinders taken per pour
label | Standard/Specification - Aurecon Civil Spec Section 13.6.3, Clause 2.15.5.3.2 of NZS 3104
label | Verifying Document - Supplier Records Concrete Dockets
label | Frequency - Once per Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - R
checkpoint | 5.05 - Reinforcement
label | Acceptance/Conformance criteria - Reinforcement and embedded items cut, bent (cold) and accurately placed as shown on design drawings. At least 30mm cover to all reinforcing +5mm-0mm
label | ○ Bar spacing as per drawings +/- 10 mm Bend locations as per drawings +/-5mm
label | Standard/Specification - Aurecon Civil Spec;14.6.7 AS/NZS 4671
label | Verifying Document - Prior to Each pour, QA Checksheet
label | Frequency - In progress check
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | MSQA signature - I
checkpoint | 5.06 - Pre-Pour Inspection
label | Acceptance/Conformance criteria - Notify Engineer for inspection of formwork 24 hours prior to pour I nspection
label | Verifying Document - Prior to Each pour, QA Checksheet
label | Frequency - Once per Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | MSQA signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1.2 - Post Pour
label | Acceptance/Conformance criteria - concrete curing for at least 5 days. Form removal after atleast 12 hours. Post pour inspection to be submmitted for Engineer's acknowlegement showing finished concrete is within tolerances (surface level +/-5 mm)
label | Standard/Specification - Aurecon Civil Spec Section 10.1.11, NZS 2566.2; Section 6.3.4.1 & 6.3.4.2
label | Verifying Document - Test Report
label | Frequency - Each foundation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | MSQA signature - R
checkpoint | 5.1.3 - Testing
label | Acceptance/Conformance criteria - Slump test during pout to check workability of concrete or as directed by Engineer 3 cylinder test taken for each pour. Slump target as per mix design
label | Standard/Specification - Aurecon Civil Spec 14.7.12 NZS 3112
label | Verifying Document - Prior to Each pour, QA Checksheet
label | Frequency - In progress check
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | MSQA signature - R
checkpoint | 5.1.4 - Independent testing (If Requested)
label | Acceptance/Conformance criteria - The Engineer's Rep may request site samples/ cores for independent testing of fresh or cured concrete to review the grading, mix design, strength and thickness
label | Verifying Document - Upon Request
label | Frequency - IANZ lab resport
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | MSQA signature - R
label | Engineer Rep Signature - R
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.2001 - Construction Record Compilation
label | Acceptance/Conformance criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.2002 - Survey Records
label | Acceptance/Conformance criteria - Ensure all items have been surveyed and records are assembled for asbuilting. Installation of works under contract compliant and in accordance with all rlevenat regulations, COP and standards unless specified by the engineer
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.2003 - Redline Drawings
label | Acceptance/Conformance criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard/Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.2004 - Defect, Snag and Punch List
label | Acceptance/Conformance criteria - Update the project Defect, Snag and Punch List Register
label | Standard/Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature