## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
254a0f5e-e733-4234-a934-4bfc0f40debc | checklist | ITP-015 - Drilling & Setting of Bonded Anchors | itp | ITP-015 - Drilling & Setting of Bonded Anchors |  | 45d432c1-024a-4f81-a48c-fade88501fcc
67df3fad-a7ac-49a2-9cae-d3a7945f272e | section | 1 - Preliminary Works
c333cc8e-7e35-4e1b-abfc-69c8fa407923 | checkpoint | 1.1 - Check for Correct Documentation
019aecf1-5b4d-5fa5-943e-f1d85dd37401 | note | FREQUENCY: Prior to commencing works.
fcd24139-6ab2-520c-b313-eaaccc269ca6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the complete set of the correct and most current drawings.
f5592bcf-fc8d-5321-b88a-dfe782d03fac | note | REFERENCE DOCUMENTS: Project IFC Drawings and Drawings Register
8c349264-45d2-58b8-a940-f4de5821031b | note | INSPECTION/TEST METHOD: Visual Inspection
7e2a4f0d-5303-5f76-96d0-48bdbc5b5723 | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
1eaab834-d02b-5e9f-a2cc-0c73cd97f99b | note | HP*
dbd27384-4c97-52d2-a73e-6d4a8ff53d8e | note | RESPONSIBILITY: Project Engineer/Site Supervisor
09259a37-b0c3-52a1-9746-386c3850e6f6 | date | Date Completed:
86d94163-b64d-4c63-ae63-29b9e722bb27 | checkpoint | 1.2 - Implementation of all measures and controls
7d95ee95-a205-57c8-8a88-15456ff629ea | note | FREQUENCY: Prior to commencing any works on site.
6a36ad06-48d8-5c9f-9438-8e0dd207bb30 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, ECP, TMP, SWMS
ad59e1d0-7dfe-503a-8153-2aaca337a627 | note | REFERENCE DOCUMENTS: PMP, EMP, ECP, TMP, SWMS
cd8b6ee7-888f-5f80-bbf7-5933a87d786d | note | INSPECTION/TEST METHOD: Visual Inspection
531bd80b-8c6c-5f74-a28d-a7e1ea601e2c | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
95dda548-ab58-5417-8b88-7e7c34890032 | note | HP*
e7d95320-8052-5890-a512-790fdcc894b5 | note | RESPONSIBILITY: Project Engineer
e6e379b1-0782-5689-8a93-7c20e1cd9202 | date | Date Completed:
cf7dfc09-1d61-4f2a-99e5-8f8c60e84d3f | checkpoint | 1.3 - Service Identification & Excavation Permit
a8423d1b-5714-513a-bf42-35332e8d3d4a | note | FREQUENCY: Prior to commencing any works on site.
22ed77cd-001c-508d-b08e-91cfbe656325 | note | ACCEPTANCE CRITERIA: All services are located, and the relevant service authorities have been consulted and permits obtained.
9cd843b2-da3d-55fd-af08-669125f57dfa | note | ○ Ensure an excavation permit is issued and all involved personnel are briefed about the services in the area before signing onto the permit.
b36c81ba-23a2-529d-b79b-c627f52ab25e | note | REFERENCE DOCUMENTS: DBYD
258cfa5e-e98d-5a8c-b64b-d2575e643c34 | note | INSPECTION/TEST METHOD: Verify
e675b4ca-f7a8-5a6b-8e48-d4ede1057686 | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
cf7dab97-dce0-5bef-b214-f3d8e9308504 | note | HP*
fcd2457f-ea5f-55d5-997e-2c5b51e73e2f | note | RESPONSIBILITY: Project Engineer
4cacebb6-3937-5ab5-ab96-4cb3baacd12a | date | Date Completed:
4ea1be53-feab-4f47-8143-8a83318bc55e | checkpoint | 1.4 - Training and Competency
4a202bc0-c021-5821-8f93-4edbe9ebb1a9 | note | FREQUENCY: Prior to commencing any works on site.
ab0f8738-1a50-58a9-a5f0-0153a9f865b5 | note | ACCEPTANCE CRITERIA: The bonded anchor installers, and all of its site personnel, shall be certified by the AEFAC, and shall provide evidence of this certification and of its competency acceptable to the Superintendent.
211c1c63-407a-50d6-88c8-9cca9e980b43 | note | ○ All personnel, including supervisory personnel, who are required to install bonded anchors shall also be trained on-site by the supplier of the bonded anchor system in the specific installation requirements of the project before bonded anchor installation works commence.
86e406f6-d78d-56cb-992d-56f0cc161f56 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.06
56b2007e-8045-5198-98c3-416113e65dc6 | note | INSPECTION/TEST METHOD: Verify
de809749-5b5f-59c8-a7b5-ee49fa8188c0 | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
6b07a12e-3b33-5086-8a04-86fd1e7195ca | note | HP*
e9fb3f50-8617-572e-bdbb-5e479adf8975 | note | RESPONSIBILITY: Project Engineer/ Site Supervisor/ Superintendent
52f38742-88ad-5b3b-855b-0f692595c413 | date | Date Completed:
b41b93c6-1909-4a5d-817d-1f088fac928c | section | 2 - Construction Works
812daa85-830e-439e-8116-00d0adf821eb | checkpoint | 2.1 - Survey & Set Out
62313bc0-08c5-553a-8efa-9e4b6e3b6dfe | note | FREQUENCY: Each Lot
97942abc-711c-579f-bb32-d4c7eaad6c32 | note | ACCEPTANCE CRITERIA: Ensure line and level of all bonded anchor holes is in accordance with design levels, survey files and drawings.
680f9bda-7bc3-52dd-9cd1-63a1b284c86c | note | REFERENCE DOCUMENTS: Project IFC Drawings and Survey Data
dd2bba38-f09b-513c-b0e7-37120d812f27 | note | INSPECTION/TEST METHOD: Visual Inspection
7c1e15a2-c670-5629-8ddb-a81984d33571 | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
4297b412-0092-5c36-b93a-95dfa1e746dc | note | HP*
7a88ade9-a9b5-505b-98f4-6042909d4e2a | note | RESPONSIBILITY: Project Engineer/Site Supervisor
1db356ca-6111-597e-867f-4431735d6c51 | date | Date Completed:
3466b47a-430b-4905-ace5-010939f5285a | checkpoint | 2.2 - Trial Installation
59902ead-3ee4-55df-b675-26642252023d | note | FREQUENCY: Each Lot
0a77fa22-f3f0-5a49-a59f-fef0939e70cc | note | ACCEPTANCE CRITERIA: The Contractor shall not proceed with the permanent bonded anchor installation works until the trial system installation have been carried out and the outcomes reviewed and approved by the Superintendent.
419dec4e-df0f-5466-b2ff-c1b54bf2c8a1 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.11
7cff8b83-bffd-5927-9d06-4d04d2696e90 | note | INSPECTION/TEST METHOD: Visual Inspection
c263b1b2-43f0-54ec-8522-827c216919e9 | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
8ccb5799-2893-5b7c-a9dd-0cdcb08a98f2 | note | HP
e37cd109-5410-5fd9-bbe8-6a67c62bad61 | note | RESPONSIBILITY: Project Engineer/ Site Supervisor/ Superintendent
eb60f8ba-e64a-5847-80ed-5c23546224e7 | date | Date Completed:
39cc1c37-d01c-43ed-ad7f-ab14cf9239e1 | signoff | AUTHORITY HOLDPOINT
a6587fa7-d0d6-4e07-84f4-37bfd2dacb44 | checkpoint | 2.3 - Drilling & Roughening of Anchor Holes
240510eb-bf86-58b8-95ac-4fea6d1925f7 | note | FREQUENCY: Each Lot
0a9de5f5-42cd-54fd-9560-a8ecd76f91c5 | note | ACCEPTANCE CRITERIA: The Contractor shall not proceed with drilling or cutting holes into the concrete, installation or removal of bonded anchor works until the WMS and ITPs have been reviewed and approved by the Superintendent.
b24481fa-5aeb-552b-b06a-96776bb8f9e6 | note | ○ Ensure hole depths and widths are drilled in accordance with Project IFC Drawings.
d762f09c-46a6-5a2b-a5a8-c965120b4b47 | note | REFERENCE DOCUMENTS: Drawing No.578259 – 578276, VicRoads Standard Section 680, Clause 680.11
dbe2761d-e4a9-5574-8b24-2a5e7d3d9474 | note | INSPECTION/TEST METHOD: Visual Inspection
aa4529ed-7682-5cbd-b0f6-5c0f2d3bf312 | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
259808c0-9b26-575e-a7ae-b4fbb8d6af2b | note | HP
35adf00a-e73b-520d-ae49-fbc2acafec08 | note | RESPONSIBILITY: Project Engineer/ Site Supervisor/ Superintendent
dda5a6c7-b497-503f-b5f6-b7a2119b186f | date | Date Completed:
4b2fe557-8468-4f5f-afb3-eed528503c8b | signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Cleaning of Holes
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Ensure all holes are cleaned in accordance with the manufacturer’s installation instructions. This must include the following as a minimum:
| note | ○ Air flush twice as the specified pressure.
| note | ○ Brush clean twice.
| note | ○ Air flush twice at the specified pressure.
| note | ○ Fingertip test the hole surface for dust, and if dust is still present, brush clean and air-flush until all dust is removed. Ensure hole is clean and free of debris, dust particles, oils and other contaminants over its full depth.
| note | REFERENCE DOCUMENTS: Section 680 Clause 680.08
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
| note | HP*
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
be1e2659-78da-408f-88c3-b11a37edd14f | checkpoint | 2.5 - Placement of Bonded Anchors
097df518-588c-5465-9280-4f34a2faec62 | note | FREQUENCY: Each Lot
9fe5bfb5-3b7b-599a-af85-ba81a314d58e | note | ACCEPTANCE CRITERIA: Ensure materials being used are in accordance with standard specifications and design drawings.
f927bd9c-6977-508f-965e-65a5a0559ace | note | ○ Chemical adhesives shall be allowed to gain strength for the minimum time specified by the manufacturer’s installation instructions before torque is applied to bolts and load is applied to the bonded anchor system.
e8691a12-a5bf-54c1-bfb4-e2929230fa86 | note | ○ Ensure bonded anchor casting register is populated including relevant details such as cast date, cast time, ambient temperature and time of casting, material batch no., and material batch expiry date.
2b42d000-8713-55d0-be26-de6a9cc94593 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 680
d64a7cb6-9679-5ab3-95ad-bb6bcfd160de | note | INSPECTION/TEST METHOD: Visual Inspection
516e7800-c99f-5869-884b-2ef7f3e2ebbc | note | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
19750beb-23f7-5267-b768-b0198cfeefc8 | note | HP*
d94b4a42-809c-5972-ad31-c7abd76913a9 | note | RESPONSIBILITY: Project Engineer/Site Supervisor/Supe rintendent
8492d592-8ffa-591c-b072-a6c201e558f5 | date | Date Completed:
76ec1fea-fd1f-4c7d-a825-bd8d1b38a617 | section | 3 - Testing
00c69c51-3c56-49a1-9e5a-b867251b52f1 | checkpoint | 3.1 - Calibration of Testing Equipment
6466f2d8-fab8-5faf-ad99-620603e19211 | note | FREQUENCY: Each Lot
0f5aa931-b218-57a1-9d54-bc1a506b3f16 | note | ACCEPTANCE CRITERIA: One week prior to testing the Contractor shall submit to the Superintendent calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devise to be used.
e8f0e76b-b98b-5f6d-ad3a-f7215b1a6a99 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.09
a3bb9560-cd03-5e39-8357-f8c503faa29a | note | INSPECTION/TEST METHOD: Test Point
1619a482-b40a-5e68-baf5-37345866bdef | note | RECORD OF CONFORMITY: Test Report
094fe86f-d047-59cd-9df4-eed741586727 | note | HP
030a4b9d-486b-5377-8e13-731feb754438 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c3f0b584-1f39-5b0b-b7bb-f33ae75b12af | date | Date Completed:
6f9475be-915e-4fc9-9ab8-e2182fd7cf5d | signoff | AUTHORITY HOLDPOINT
d3be852e-255e-438d-add5-c4fd861951e7 | checkpoint | 3.2 - Test Method
25c1399c-3f86-563b-a32b-ac16be68989a | note | FREQUENCY: Each Lot
b332d41a-16b1-5dd1-9de7-88c693765932 | note | ACCEPTANCE CRITERIA: Details of the test method including load increments and duration of sustained loading shall be submitted to the Superintendent for review not later than one week prior to the testing.
5fa6fa47-ee19-57ea-b49b-74ebd4d6d869 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.09
675b2022-b67c-5438-98b4-d9d8c59d950a | note | INSPECTION/TEST METHOD:
091aacb4-1e2e-5224-a3c7-210afccbc8a7 | note | RECORD OF CONFORMITY:
5c9bf736-5dc3-5daf-96ab-6a0f4f188319 | note | HP
a1d1649f-336a-5ea7-b3b2-2ec5b01f7789 | note | RESPONSIBILITY: Project Engineer/Site Supervisor/Supe rintendent
4f814817-b962-558b-90fe-d74b8cc01d6b | date | Date Completed:
44c5ed97-a8ab-4b56-a007-2189aeb3f392 | signoff | AUTHORITY HOLDPOINT
bf0f8b74-c1bf-4c5d-80d8-a921adbf5409 | checkpoint | 3.3 - Testing of Bonded Anchors
e2126fd1-8e82-509f-8748-168e6fa0ad57 | note | FREQUENCY: Each Lot
eb8f05b7-4d6b-54f9-b4df-895b40bc5f50 | note | ACCEPTANCE CRITERIA: Ensure a minimum of 20% of all bonded anchors subject to tensile loads, a combination of tensile and shear loads, or fatigue loads are tested and deemed to meet the minimum strength requirements.
f400d59a-8791-5b6d-86d3-6f9a4c649e44 | note | ○ 50 kN
2a39fd06-661f-5ec2-9b5b-d669a334ae74 | note | — The Contractor shall provide a test report to the Superintendent for review.
4b0f8968-9a0e-5e53-8e98-e2755bd27b7e | note | — If a bonded anchor fails either the ultimate load testing for suitability or the bonded anchor proof load test, the Contractor shall submit rectification proposals for review by the Superintendent prior to any further bonded anchor installation.
478dc7af-d94c-5ca5-a263-c3b09d62c071 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.09
9b798d6c-4b3b-57b5-ad51-653605b6e0f2 | note | INSPECTION/TEST METHOD:
ed593747-58c9-5eb3-8e01-25f1b8e7daec | note | RECORD OF CONFORMITY:
6dca7ea3-3290-5a43-bbac-2dc958b289f2 | note | HP
a00ff635-180d-5282-8789-fc83525025ce | note | RESPONSIBILITY: Project Engineer/Site Supervisor/Supe rintendent
df6ff5ea-570c-5fce-981e-53e9c18ac6ca | date | Date Completed:
614b63e3-53c9-44ea-8b25-e3570d6dc1f4 | signoff | AUTHORITY HOLDPOINT
a5703108-2a2b-4451-9a8c-e40f12268675 | checkpoint | Final Inspection
86a21c93-a87c-5e01-99f6-71eb043bbc14 | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
22c2ad99-4b76-5a6c-81f2-3a4f66f0b243 | textbox | Print Name:
bf223cdf-e7a7-514c-b497-d35504344646 | textbox | Position:
fef0a95a-44ba-5fac-8d37-93f379b4ae30 | date | Date:
33a12d86-45b5-4ce3-9091-dad00c7fe80e | signoff | Sign ITP