## Project Structure
Folder Structure |  |  | Checklists
Site QA
Job Name: | 11 Prosser Street - Stage 1
Job Number: | 3901
| Elevation | Window | Suite Type
| NORTH | NW-01 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-02 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-03 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-04 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-05 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-06 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-07 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-08 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-09 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-10 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-11 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-12 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-13 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-14 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-15 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-16 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-17 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-18 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-19 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-20 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-21 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-22 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-23 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-24 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-25 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-26 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-27 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-28 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-29 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-30 | Seismic Suite (Structurally Glazed Curtain Wall)
|  | NW-Auto door | Commercial/Domestic
| SOUTH | SW-01 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-02 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-03 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-04 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-05 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-06 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-07 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-08 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-09 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-10 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-11 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-12 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-13 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-14 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-15 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-16 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-17 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-18 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-19 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-20 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | SW-21 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
| EAST | E-01 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-02 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-03 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-04 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-05 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-06 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-07 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-08 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-09 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-10 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-11 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-12 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-13 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
|  | E-14 | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)

## Resources
type | QA description | Mandatory photo req Y/N
checklist-flat | Seismic Suite (non curtain wall)
checkpoint | Opening Prepared, Wrapped & Datums
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | Splicers, Soakers, Gussets & Fixings Sealed (provide photo reference)
checkpoint | Panel Fitted & Locked Off
checkpoint | Airseal and Internal Flashings (Photo)
checkpoint | External Flashings / Weather Seals / Drainage
checkpoint | Glass - Frame Glazed
checkpoint | Glass - Glazing Rubbered and Complete
checkpoint | Trade Clean
checkpoint | Wights - Sign Off
checklist-flat | Seismic Suite (Curtain Wall)
checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers, Soakers, Gussets & Fixings Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings (photo)
checkpoint | Smoke Seal Complete (photo)
checkpoint | External Flashings / Weather Seals/Drainage
checkpoint | Glass - Frame Glazed
checkpoint | Glass - Glazing Rubbered and Complete
checkpoint | Trade Clean & Sign Off
checkpoint | Wights - Sign Off
checklist-flat | Seismic Suite (Structurally Glazed Curtain Wall)
checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Installed correct location
checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers, Soakers, Gussets & Fixings Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings (photo)
checkpoint | Smoke Seal Complete (photo)
checkpoint | External Flashings / Weather Seals/Drainage
checkpoint | Blindboxes (photo)
checkpoint | Trade Clean & Sign Off
checkpoint | Wights - Sign Off
checklist-flat | Seismic Suite (Structurally Glazed Curtain Wall - No Brackets)
checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers, Soakers, Gussets & Fixings Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings (photo)
checkpoint | Smoke Seal Complete (photo)
checkpoint | External Flashings / Weather Seals/Drainage
checkpoint | Blindboxes (photo)
checkpoint | Trade Clean & Sign Off
checkpoint | Wights - Sign Off
checklist-flat | Commercial/Domestic
checkpoint | Opening Wraped & Prepared Correctly
checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed (photo)
checkpoint | Site Glazing Completed
checkpoint | Trade Clean & Sign off
checklist-flat | Skylights
checkpoint | Opening Wraped & Prepared Correctly By Main Contractor
checkpoint | Roof frame Installed / Fixed As Per Shop Drawings
checkpoint | Airseal and Internal Flashings (photo)
checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Glass - Frame Glazed
checkpoint | Glass - Glazing Rubbered and Complete
checkpoint | Wights - Sign Off