## struct
resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
|  | step |  |  | Site QA
|  | step |  |  |  | WP3
|  | step |  |  |  |  | WESTERN CAPRARK
|  | step | [5 empty] | UNDERGROUNDS
ITP No. 29 Installion of Electrical & Communication Pits |  | checklist | [6 empty] | PIT INSTALLATION
ITR No. 33 Installing Underground Services (Electrical) |  | checklist | [6 empty] | ELECTRICAL CONDUIT INSTALL
ITR No. 33C Installing Underground Services (Comms) |  | checklist | [6 empty] | COMMUNICATION CONDUIT INSTALL
ITR No. 34 Installing Light Pole Cages |  | checklist | [6 empty] | LIGHT POLE FOOTINGS
|  | step | [5 empty] | ROUGH IN
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | FIT OFF
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | COMMISSIONING
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step |  |  |  |  | INTEGRITY BUILDING
|  | step | [5 empty] | UNDERGROUNDS
ITP No. 29 Installion of Electrical & Communication Pits |  | checklist | [6 empty] | PIT INSTALLATION
ITR No. 33 Installing Underground Services (Electrical) |  | checklist | [6 empty] | ELECTRICAL CONDUIT INSTALL
ITR No. 33C Installing Underground Services (Comms) |  | checklist | [6 empty] | COMMUNICATION CONDUIT INSTALL
ITR No. 34 Installing Light Pole Cages |  | checklist | [6 empty] | LIGHT POLE FOOTINGS
|  | step | [5 empty] | ROUGH IN
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | FIT OFF
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | COMMISSIONING
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step |  |  |  |  | HORSE AREA 1
|  | step | [5 empty] | TEMP BOARDS
ITP No. 19 Installation of Temporary Power Board | ITP No. 20 Decommission Temporary Power Board | folder-with-checklists | [6 empty] | INSTALLATION OF TEMP BOARDS
|  | step | [5 empty] | TEMP LIGHTING
ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal |  | checklist | [6 empty] | INSTALLATION OF TEMP LIGHTS
|  | step | [5 empty] | IN SLAB CONDUITS
ITR No. 09 In Slab Conduits |  | checklist | [6 empty] | IN-SLAB CONDUITS INSTALLATION
|  | step | [5 empty] | CABLE TRAY
ITR No. 10 Cable Tray Installation |  | checklist | [6 empty] | INSTALLATION OF CABLE TRAY
|  | step | [5 empty] | ROUGH IN
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | FIT OFF
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | COMMISSIONING
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step |  |  |  |  | HORSE AREA 2
|  | step | [5 empty] | TEMP BOARDS
ITP No. 19 Installation of Temporary Power Board | ITP No. 20 Decommission Temporary Power Board | folder-with-checklists | [6 empty] | INSTALLATION OF TEMP BOARDS
|  | step | [5 empty] | TEMP LIGHTING
ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal |  | checklist | [6 empty] | INSTALLATION OF TEMP LIGHTS
|  | step | [5 empty] | IN SLAB CONDUITS
ITR No. 09 In Slab Conduits |  | checklist | [6 empty] | IN-SLAB CONDUITS INSTALLATION
|  | step | [5 empty] | CABLE TRAY
ITR No. 10 Cable Tray Installation |  | checklist | [6 empty] | INSTALLATION OF CABLE TRAY
|  | step | [5 empty] | ROUGH IN
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | FIT OFF
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | COMMISSIONING
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step |  |  |  |  | JOCKEY AREA/MOUNTING YARD
|  | step | [5 empty] | TEMP BOARDS
ITP No. 19 Installation of Temporary Power Board | ITP No. 20 Decommission Temporary Power Board | folder-with-checklists | [6 empty] | INSTALLATION OF TEMP BOARDS
|  | step | [5 empty] | TEMP LIGHTING
ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal |  | checklist | [6 empty] | INSTALLATION OF TEMP LIGHTS
|  | step | [5 empty] | IN SLAB CONDUITS
ITR No. 09 In Slab Conduits |  | checklist | [6 empty] | IN-SLAB CONDUITS INSTALLATION
|  | step | [5 empty] | CABLE TRAY
ITR No. 10 Cable Tray Installation |  | checklist | [6 empty] | INSTALLATION OF CABLE TRAY
|  | step | [5 empty] | ROUGH IN
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | FIT OFF
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | COMMISSIONING
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step |  |  |  |  | WESTERN EVENT DECK
|  | step | [5 empty] | UNDERGROUNDS
ITP No. 29 Installion of Electrical & Communication Pits |  | checklist | [6 empty] | PIT INSTALLATION
ITR No. 33 Installing Underground Services (Electrical) |  | checklist | [6 empty] | ELECTRICAL CONDUIT INSTALL
ITR No. 33C Installing Underground Services (Comms) |  | checklist | [6 empty] | COMMUNICATION CONDUIT INSTALL
ITR No. 34 Installing Light Pole Cages |  | checklist | [6 empty] | LIGHT POLE FOOTINGS
|  | step | [5 empty] | ROUGH IN
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | FIT OFF
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | COMMISSIONING
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step |  |  |  | WP4
|  | step |  |  |  |  | TEMP BOARDS/TEMP LIGHTING
|  | step | [5 empty] | GROUND
ITP No. 19 Installation of Temporary Power Board | ITP No. 20 Decommission Temporary Power Board | folder-with-checklists | [6 empty] | INSTALLATION OF TEMP BOARDS
ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal |  | checklist | [6 empty] | INSTALLATION OF TEMP LIGHTING
|  | step | [5 empty] | LEVEL 1
ITP No. 19 Installation of Temporary Power Board | ITP No. 20 Decommission Temporary Power Board | folder-with-checklists | [6 empty] | INSTALLATION OF TEMP BOARDS
ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal |  | checklist | [6 empty] | INSTALLATION OF TEMP LIGHTING
|  | step | [5 empty] | LEVEL 2
ITP No. 19 Installation of Temporary Power Board | ITP No. 20 Decommission Temporary Power Board | folder-with-checklists | [6 empty] | INSTALLATION OF TEMP BOARDS
ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal |  | checklist | [6 empty] | INSTALLATION OF TEMP LIGHTING
|  | step |  |  |  |  | IN SLAB CONDUITS
|  | step | [5 empty] | GROUND
ITR No. 09 In Slab Conduits |  | checklist | [6 empty] | IN-SLAB CONDUITS INSTALLATION
|  | step | [5 empty] | LEVEL 1
ITR No. 09 In Slab Conduits |  | checklist | [6 empty] | IN-SLAB CONDUITS INSTALLATION
|  | step | [5 empty] | LEVEL 2
ITR No. 09 In Slab Conduits |  | checklist | [6 empty] | IN-SLAB CONDUITS INSTALLATION
|  | step |  |  |  |  | CABLE TRAY
|  | step | [5 empty] | GROUND
ITR No. 10 Cable Tray Installation |  | checklist | [6 empty] | INSTALLATION OF CABLE TRAY
|  | step | [5 empty] | LEVEL 1
ITR No. 10 Cable Tray Installation |  | checklist | [6 empty] | INSTALLATION OF CABLE TRAY
|  | step | [5 empty] | LEVEL 2
ITR No. 10 Cable Tray Installation |  | checklist | [6 empty] | INSTALLATION OF CABLE TRAY
|  | step |  |  |  |  | ROUGH IN
|  | step | [5 empty] | GROUND
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | LEVEL 1
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step | [5 empty] | LEVEL 2
ITR No. 14 Mains and Sub Mains |  | checklist | [6 empty] | MAINS/SUBMAINS
ITR No. 05 Rough in |  | checklist | [6 empty] | LIGHT & POWER ROUGH IN
ITP No. 07 Structured Cabling Rough In |  | checklist | [6 empty] | STRUCTURED CABLING ROUGH IN
|  | step |  |  |  |  | FIT OFF
|  | step | [5 empty] | GROUND
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | LEVEL 1
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step | [5 empty] | LEVEL 2
ITR No. 16 Switchboard Installation and Terminate Submains |  | checklist | [6 empty] | SWITCHBOARD FIT-OFF
ITR No. 18 Light and Power Fit Off |  | checklist | [6 empty] | LIGHT & POWER FIT-OFF
ITP No. 08 STRUCTURED CABLING FIT OFF |  | checklist | [6 empty] | STRUCTURED CABLING FIT-OFF
|  | step |  |  |  |  | COMMISSIONING
|  | step | [5 empty] | GROUND
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step | [5 empty] | LEVEL 1
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step | [5 empty] | LEVEL 2
ITR No. 12 Switchboard Commissioning |  | checklist | [6 empty] | SWITCHBOARD COMMISSIONING
ITR No. 41 Field Commissioning |  | checklist | [6 empty] | LIGHT & POWER COMMISSIONING
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | checklist | [6 empty] | STRUCTURED CABLING COMMISSIONING
|  | step |  |  | Pre Start
|  | step |  |  |  | April 23
|  | step |  |  |  | May 23
|  | step |  |  |  | June 23
|  | step |  |  |  | July 23
|  | step |  |  |  | August 23
|  | step |  |  |  | September 23
|  | step |  |  |  | October 23
|  | step |  |  |  | November 23
|  | step |  |  |  | December 23
|  | step |  |  |  | January 24
|  | step |  |  |  | February 24
|  | step |  |  |  | March 24
|  | step |  |  |  | April 24
|  | step |  |  | Toolbox Meeting
|  | step |  |  |  | April 23
|  | step |  |  |  | May 23
|  | step |  |  |  | June 23
|  | step |  |  |  | July 23
|  | step |  |  |  | August 23
|  | step |  |  |  | September 23
|  | step |  |  |  | October 23
|  | step |  |  |  | November 23
|  | step |  |  |  | December 23
|  | step |  |  |  | January 24
|  | step |  |  |  | February 24
|  | step |  |  |  | March 24
|  | step |  |  |  | April 24
|  | step |  |  | Site Induction