## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
9f010e80-df25-5b5b-a903-6e9b4f217664 | checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
22f46605-abf2-5042-8ed0-8e0e9243e450 | checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
2eac1ff7-51f5-52ef-a9a2-2d81b08bda9a | note | Acceptance Criteria & Frequency (Project Specific) - Accreditation Supplied to Administrator
b3409669-0534-5917-a9b4-edacd63c32c6 | note | Check Item - Check Item
88090e52-6a21-535b-868d-9367d7a36901 | note | Reference - MRTS02 Cl. 5.2
42f59f71-5d9f-58ba-a29c-be7dae002798 | textbox | Submitted with TMP |  |  | SE/PE/WS/SS (Submitted with TMP __/__/____)
2c294e3e-9ea2-5d25-8e60-05bcfa2a4984 | checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
cd880b4f-1647-53ea-afee-461485db37eb | note | Acceptance Criteria & Frequency (Project Specific) - Approval via Contract Notice - Per NTO
6dbea37b-afc9-51d8-9293-081afe933f84 | note | Check Item - Hold Point 1
e13548c3-5f35-5dd0-9301-c7206d91a76d | note | Reference - MRTS02 Cl. 5.3
69359347-b7be-5097-8311-ec732c6d5972 | signoff | HOLD POINT
1c0d051d-0ce9-5321-a506-90b114803e9a | checkpoint | All traffic control devices inspected and records kept in accordance with the specification
ab4d03bd-96d3-58ac-a254-1b76c65160b0 | note | Acceptance Criteria & Frequency (Project Specific) - Site Records - Daily
f65a86a1-f9a1-5e32-af7e-c2997ef50556 | note | Check Item - Check Item
53f13cbb-d64b-51dd-94ce-2648d69fa94e | note | Reference - MRTS02 Cl. 5.6.4
5dfc3f53-239a-5486-b41a-446adb8be5df | checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
fa04007c-1c19-59ab-b1a4-8c3c8622ba71 | note | Acceptance Criteria & Frequency (Project Specific) - Incident Report - Per incident
fd66957a-dfad-5e1e-9805-6143f10bd36b | note | Check Item - Check Item
33656b03-0976-5115-8377-18ab1ad2cbac | note | Reference - MRTS02 Cl. 5.6.5
4b906790-087c-51f6-97ba-b99822d764cc | checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment, as required. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
602d2510-3aa8-5f54-b622-8524f0001f35 | note | Acceptance Criteria & Frequency (Project Specific) - TMD sign off of TGS and, RPEQ Risk Assessment as required
2e432909-7d38-5224-ae76-bf3a23dc3946 | note | Check Item - Hold Point 2
3d5cd4e3-68df-5120-ba26-406ad241de69 | note | Reference - MRTS02 Cl. 6.2
c84452fd-ccfd-5b74-b1af-a571343a2968 | signoff | HOLD POINT
e93307b9-9ce8-5551-b0ca-3f07b06564b9 | checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
2381e6c7-7169-5fc2-99de-5bf7b71256a0 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of report to Administrator - Per inspection
81bf71da-ad85-5972-bc37-bdd0517e7647 | note | Check Item - Milestone
680c3b6b-c8e1-5c21-907d-519881103a31 | note | Reference - MRTS02 Cl. 7.5
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
c8cf2668-d2cd-5646-9257-3eb171edd1e8 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
06a3e351-a9cd-56af-9b27-3077eeb58c7c | textbox | Print Name:
3940e32d-aa16-57d2-982f-5e30baa2ea86 | date | Date:
ac5d1a1c-7c27-54ba-a1db-0c39d65a49b8 | note | Project Manager Verify that the Above has been Constructed according to Specification
15f27d51-8d30-508c-9090-6cb0ef2bf8cc | textbox | Print Name:
a8992091-4638-5532-8343-5cdb76070052 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
0d753080-d7de-539e-9292-c34e17985621 | checklist | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs | itp | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
a75bf658-fe33-5b96-9410-aab4fc98ea76 | checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
c2eb0018-945a-5066-a706-5aada8e24d03 | note | Acceptance Criteria & Frequency (Project Specific) - Culvert Removal - Per Culvert
997f4869-2645-546e-8448-55b50238a7ba | note | Check Item - Check Item
f1a9835a-b4f0-586b-9cd9-9dd69fcfb56f | note | Reference - MRTS03 Cl 9.2
67e24e1d-ab5a-5a8e-b8ef-a9baf87bb975 | checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
c89e2b95-3d02-569d-8cb1-e9f527a1beca | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
40be8430-d9a1-5113-97f5-7e31954a4f17 | note | Check Item - Check Item
a41951b9-d85d-51ed-9c15-44bbe7264dce | note | Reference - MRTS03 Cl 9.2
eb5c8676-5f54-5aa6-a4ac-6d7f19909c96 | checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
42f30fbf-cabb-5588-adf4-1299707ace83 | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
d9164099-3395-5acf-9c76-8a705e31ed92 | note | Check Item - Check Item
11deed2a-28f6-570b-ac81-dd7111f27f44 | note | Reference - MRTS03 Cl 9.2
b2db4624-6dd4-59cf-a22f-9f81770cef72 | checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
cf5498cd-468c-539d-a397-0d534af597a7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
0c38b20e-05c0-54d4-b41b-276ae7b73443 | note | Check Item - Check Item
b284b42a-bfac-5f96-bd4e-c584fc3c015e | note | Reference - MRTS03 Cl 9.2
fffbf8e0-b888-5cc4-a36a-cd6c608c609e | checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
c24188cc-f258-5359-9a1f-e51ba493ab1f | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Kerb
64bfb9af-dfef-5dc1-b66c-b52abeb56d90 | note | Check Item - Check Item
d74ec44e-5d29-505b-8db0-dc27da42c462 | note | Reference - MRTS03 Cl 9.4
ee98be29-4973-555d-b05c-f367497653c2 | checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
fcc719aa-3d5b-565d-8daf-2c1cde30ef42 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0299771b-c40a-5514-96e8-39c416a61cee | note | Check Item - Check Item
44d347b4-aed2-59e9-90a0-24de1464c217 | note | Reference - MRTS03 Cl. 9.4
060b1b5c-9cf4-5462-a1f8-260e889c8fd8 | checkpoint | Kerb excavations shall be backfilled to flush with the surrounding area.
6b00e410-8367-5b2d-8508-31de6f2c5948 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
afd3b17d-9db0-5fff-94f4-72aaaa0212bc | note | Check Item - Check Item
01aa2a0e-a648-5644-8956-06294ea8dd17 | note | Reference - MRTS03 Cl. 9.4
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
b54e3f37-8053-5aff-b920-b04378f11a49 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
f170384d-e9aa-5d1f-871a-92d573d85808 | textbox | Print Name:
b8418a68-4925-5e1a-9b47-69ffef64aae0 | date | Date:
15e198ae-cfd9-525c-9f2b-3bca2fea3720 | note | Administrator's Representative Verify that the Above has been Constructed according to Specification
db0a80dd-a3ff-541a-8129-e2181d71dcfb | textbox | Print Name:
a9e090e7-3e01-5d3b-9cae-372fc32715df | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
318e5232-8d11-5d51-a2e4-ba5cb4bf095e | checklist | 03.10 - Supply and Installation of Precast Concrete Culverts | itp | 03.10 - Supply and Installation of Precast Concrete Culverts
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
e8e8b228-722c-548d-9ca6-905da58882bd | checkpoint | Maximum Lot Size - 1 Culvert
f0f88bb8-a574-5d41-a1e9-91ba77a6bd89 | note | Acceptance Criteria & Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
ab25d491-a421-5be5-b4cc-83fab634bdbb | note | Check Item - Check Item
a4da4aa3-793b-54ee-89c5-e845f0f17e2d | note | Reference - MRTS04 Table A.2
4c08aba5-0537-58f3-8ef1-c3b0ac7b2b24 | checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
15be0475-695e-5f10-a133-56e83e8f192e | note | Acceptance Criteria & Frequency (Project Specific) - Manufacture and Test Certificates
2f2aa830-b89c-5254-954b-e488aa567c97 | note | Check Item - Check Item
3c054959-bc12-5e28-a420-d5c7f42f6841 | note | Reference - MRTS03 Cl10.2
f29d5888-2591-5102-a45b-46e0982e0b3e | checkpoint | All pipes of diameter 800 mm or less shall have spigot and socket joints with rubber sealing rings. Joints for other sizes shall be as specified on the drawings.
c32bb72e-b40a-5c29-93d7-a893fc96643c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e65da96b-4795-52e7-a15c-3d23687b25fe | note | Check Item - Check Item
4a3065f3-f6ea-5a98-9a87-23ff47e13333 | note | Reference - MRTS03 Cl10.2
32702bc1-0c1b-5b8c-af4e-70e9568a060d | checkpoint | Component size, wall thickness and class is as specified in the drawings
727cefb7-fe32-57a1-ad9f-6f97737155c4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b2937dda-7ca2-571c-8fba-d0a3a77d9c54 | note | Check Item - Check Item
2c5a679b-7193-554e-b1fb-0581840ac64d | note | Reference - MRTS03 Cl10.2
4ff7d98b-4f30-57d4-8e05-bd0739243517 | checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
06006f9b-bdb3-550a-b0db-633d149b0187 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e4c2ae5a-a6ce-55c3-8430-7282419bf269 | note | Check Item - Hold Point 1
5c87b15c-b81e-5c4f-8d23-2cbf3bc373f2 | note | Reference - MRTS03 Cl11.2
50f7ae12-7cab-5d37-b257-02873d488b02 | signoff | HOLD POINT
e9cc1dca-70fd-50b8-993c-92df86263708 | checkpoint | Culvert Construction Procedures to be accepted prior to commencement of Installation
08c6ccef-cb24-5777-970e-68397ac4157b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2346e1b5-445c-54c8-96b1-0d4ad40fd8b8 | note | Check Item - Hold Point 2
eb83707a-4f5a-53a1-b4fb-454a90d6add8 | note | Reference - MRTS03 Cl11.3.1
f82b76a7-5ae4-521d-b0ab-579013eadcda | signoff | HOLD POINT
c98661bf-8aee-5ee0-8ab7-ea8c73d3d346 | section | Excavation
04f7fc75-9c25-5088-9613-9a1e3f0cef7a | checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earth works
a9a57f2a-153d-55b5-ad61-94c70a320d0c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fe95e149-4c84-5bbb-bb16-31d779e484f8 | note | Check Item - Check Item
3a7f7aae-ec69-55bc-8900-f5bc4a5f956a | note | Reference - MRTS03 Cl.11.3.1
8ad92036-4619-5673-8210-2c168449b22c | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL.11.3
138ec2fa-6b04-5594-910d-41f4769efbb9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a5eebcec-1e9b-5f4a-91e8-02c35f068e9f | note | Check Item - Hold Point 4
ff4a6eae-ec82-5f09-91e2-297c78ceae5f | note | Reference - MRTS04 Cl. 9.4
f30ad2be-93b1-560e-adf4-91f339a83d44 | signoff | HOLD POINT
3ec50264-4e63-5807-8d4d-908f50beab80 | checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation -RDD Q140A
b88d1b1f-9f1d-5709-850d-e2cf0431baa0 | note | Acceptance Criteria & Frequency (Project Specific) - Cl 15, Table 15.3(b) CV 95% minimum (1 tests / 50m2 - min 2 / lot)
fb63f21c-b830-51b0-bcdb-3dca6e85bfe3 | note | Check Item - Test results
09411c45-9667-5cb9-978a-c759c680478d | note | Reference - MRTS04 Table A.2
d37d7841-a4ac-5e9a-bf83-9837f648b525 | section | Culvert Installation
cced934e-e612-5ba6-8fec-1eb1dc17e59d | checkpoint | Components are assembled as per manufaturers specifications, and if possible, contruction commenced at outlet
1381bfcf-160a-5e64-9a33-4a2a3741295e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2e5d069f-58fb-5a52-a7f5-7c2448ef3ea7 | note | Check Item - Check Item
4c68f892-d8f1-5aba-82e1-df3dbee8774a | note | Reference - MRTS03 Cl11.3.3, Cl11.3.4
924ff8ec-2e08-5278-9baa-d2890d9bd1ef | checkpoint | Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet
1b6f8687-1bad-5f58-905a-50052de8ca84 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
29949f25-2da2-5a8f-a7d5-e56163d92792 | note | Check Item - Check Item
1f775793-a539-5cad-9f57-c8a1b1c817fe | note | Reference - MRTS03 Cl11.3.5
6e5431bf-ed4c-5195-9f5f-e89d3fe8da33 | checkpoint | The pipes shall be laid with the lifting hole or "TOP" marking uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
f5797ee5-7160-553c-952f-7f06af53e287 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e045efee-421d-5887-b531-9a63a30e582c | note | Check Item - Check Item
ee4884ae-5cd2-5a19-b73a-86bf2665eff6 | note | Reference - MRTS03 Cl11.3.5
f13886a9-d90a-50a2-b0b9-df23d9982ebc | checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
68646546-516b-5c88-ab1a-4689dca31bab | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7786e5e7-53ef-5a32-9fb3-04aa26d34efb | note | Check Item - Check Item
ed547427-2f46-523e-af2b-15879d6240f2 | note | Reference - MRTS03 Cl11.3.5
9bb078b1-0f5c-5b44-bceb-558b8a5e2e23 | checkpoint | The horizontal alignment of culverts shall not vary from the location specified in the Drawings by more than ± 100 mm
7fd91a1f-a283-5934-b1f3-434dc3c9c3f7 | note | Acceptance Criteria & Frequency (Project Specific) - ± 100mm (All points shown on drawings - min 1 per 20m or 3 points)
ce8b1357-df4c-5e29-a3d0-526abcb1fb46 | note | Check Item - Survey Results
f959d1a9-0d32-5017-8438-00102e1dac93 | note | Reference - MRTS03 Cl.8.2
4923a377-31e8-57b4-8eac-75cb6bbd3041 | checkpoint | The invert heights of culverts shall not vary from those specified by more than ± 10 mm and nowhere shall the grades of culverts depart from those specified by more than 1%
58d40b46-315f-5457-9e95-fcfd3dfe4eb7 | note | Acceptance Criteria & Frequency (Project Specific) - ± 10mm, ± 1% grade (All points shown on drawings - min 1 per 20m or 3 points)
4487efcc-a20d-5f0a-8ab5-619f1c8a81f8 | note | Check Item - Survey Results
e47375dd-8f2d-56bc-93ec-13be00a34648 | note | Reference - MRTS03 Cl.8.3
6ec1d577-3a5d-55a1-b557-23279c1a7b56 | section | Backfill
93518480-ca62-54eb-8e98-a013d53e94d3 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
d3981b85-540e-5397-9f29-83c95f2d4a41 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
829d46e8-3477-58f2-a625-c0f57c92f34c | note | Check Item - Hold Point 4
5a54b0aa-6c23-50de-b61c-abc0163847bd | note | Reference - MRTS03 11.3.10
42bc24eb-9065-587b-aa1f-b895b94149ae | signoff | HOLD POINT
17f346bd-1f53-5e14-9b8c-fe379786ce81 | checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, etc have been completed and inspected, and any specified curing periods have elapsed.
a6d641be-8b2e-56b1-a1ff-a56506a29afb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e37b9c66-916d-5254-a903-98cad220caf0 | note | Check Item - Hold Point 14
3916cc23-944e-5eaa-a4ce-de38a646a1d1 | note | Reference - MRTS04 Cl.19.3.3
7dc93689-7e89-5c13-8a6d-732580eff138 | signoff | HOLD POINT
062be017-49d7-548d-9de8-0cfb3dc90ba1 | checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 excep 100% material shall pass 25.0mm test sieve.
b16adf11-922d-5e6d-932b-89fe003b3715 | note | Acceptance Criteria & Frequency (Project Specific) - Class A1:
d0e8cbce-9817-5b90-929b-72a603b19ab5 | note | ○ Class A2:
69219317-3418-59d5-8e6c-387b41e59c0a | note | ○ Class B:
46f5d5a8-50d5-5f78-b38e-74343839ca78 | note | ○ Except: 100% passing 25mm
2cb41501-8452-5000-992c-ebbdb052a61f | note | Check Item - Witness Point
ec65dc6d-a9f4-5a61-96be-fe70d842a338 | note | Reference - MRTS04 19.3.1, 19.2.2 Table 14.2.2
e5e04338-5913-566b-8d33-0333f547f613 | checkpoint | Compaction - Q142A, Q141B
1b37dc4b-c4f9-531f-a11d-3207d8f4a6cd | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%, Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
4fb9cda4-499a-5115-b20f-bea1aabd8f72 | note | Check Item - Test results
17b1e9c1-bd00-5d0f-b0a1-0cb08defb699 | note | Reference - MRTS04 Table 15.3(b)
9768bc25-a56a-5bb7-8eef-c82def95a5a2 | checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
a3f2068f-1535-52f4-9b0b-93513ecac49d | note | Acceptance Criteria & Frequency (Project Specific) - Class A1/A2: 70-100%, Class B: 80-110%
72352dd4-30d6-5eea-8f99-8d5396577e5a | note | Check Item - Test results
4d2c28ec-4d75-591b-9156-d7f54fb74af1 | note | Reference - MRTS04 Table 15.3(c)
d80d130d-72f8-5fc9-872b-1fc379f43b15 | section | Completion
567ec777-38fd-5c41-a3cf-c5bcd1c05386 | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator. Visual inspection may be approved by the Administrator in lieu of CCTV inspection.
219f2176-c587-5c37-8e2d-acbbc9c9d962 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
10d5808b-9aa8-5a02-a429-4ab60e407757 | note | Check Item - Hold Point 3
632c7212-fcac-537e-ab10-6dbc087e12f3 | note | Reference - MRTS03 Cl11.3.5
cb97bb29-148c-52c6-af4f-47121565e3f4 | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
808ded52-cb3c-5d15-9dcc-d41a3e1eccb8 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
7b19176d-48e8-5f2a-bf1a-8c6f2466c359 | textbox | Print Name:
b6b0ca58-254a-51c8-80dd-095456fdf25d | date | Date:
fe35b67c-446a-5de5-8ee5-518211b76294 | note | Project Manager Verify that the Above has been Constructed according to Specification
0b7ffff2-8aac-5f05-a8fe-543a115d2bb4 | textbox | Print Name:
981c158a-a221-5072-a806-accdb6aeb849 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
14085c4b-a77f-5c90-ba00-4a516ee75be8 | checklist | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ | itp | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
e8e8b228-722c-548d-9ca6-905da58882bd | checkpoint | Maximum Lot Size - 1 Culvert
4c259fb9-4306-54e3-b278-7e377e0a2617 | note | Acceptance Criteria & Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
0786f319-b9f5-5011-b353-d230f19fde16 | note | Check Item - Check Item
16f1ca96-a631-5125-9a56-2801d3e52768 | note | Reference - MRTS04 Table A.2
83b1aa26-b214-570b-859f-1b8849fa0617 | checkpoint | Culvert Construction Procedures accept prior to commencement of Installation
06f14098-7069-5e75-94ab-b1dc8e831ede | note | Acceptance Criteria & Frequency (Project Specific) - Administrator Approval - Per Project
6916d95e-6983-52a1-af5a-f224f6f565a2 | note | Check Item - Hold Point 2
f369dbd2-84a2-5b12-b35a-bd3a1e2d6b91 | note | Reference - MRTS03 Cl 11.3.1
8ffd1ad4-76b5-5619-abf8-28a7670926c7 | signoff | HOLD POINT
c98661bf-8aee-5ee0-8ab7-ea8c73d3d346 | section | Excavation
d915db6a-a914-53e6-bf58-64e62fcb3fa3 | checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
1f1ab448-a19d-50b0-8b93-d4bd7281746b | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per lot
34f1ac86-4e1b-5017-953a-44889ff926de | note | Check Item - Check Item
74c98a0b-0e4d-59fc-aafd-cb688ebfb81e | note | Reference - MRTS03 Cl 12.3.1
6de18a97-b794-5f69-b18e-2ec491feb556 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.2 and CL.11
411e4805-0cce-5c57-a9a6-14a00f3d1d20 | textbox | Reference Unsuitable Lot No. :
167b22e8-0d46-597a-9c2e-d69c1dac3a20 | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per lot
09d43304-d703-55d5-b153-039a2acd6839 | note | Check Item - Hold Point 4
68c49069-ab75-5248-9ad9-e4a74060a073 | note | Reference - MRTS04 Cl 9.4
c1d45b2e-c720-5f9d-b6b7-87d44f86bd8b | signoff | HOLD POINT
36052031-552b-516e-9b0b-1ad34bf9faed | checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation - AS 1289.5.4.1 or AS1289.5.7.1
9cb6813b-d448-5713-91ea-7214385d2eca | note | Acceptance Criteria & Frequency (Project Specific) - Cl 15, Table 15.3(b) CV 95% minimum (1 tests / 50m2 - min 2 / lot)
b87f15d8-b0c7-510b-a096-a833b4343e80 | note | Check Item - Test results
6cad40b8-da8a-580f-8cd1-ebc04e7a2f37 | note | Reference - MRTS04 Table A.2
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
aadbf7a4-d74c-5e9d-96d9-5919496574dd | checkpoint | Cast In Situ material: In accordance with MRTS03 Cl.6.1, MRTS 70 and MRTS71
5e03c633-02a5-5b02-9dce-f0f2bc029ba5 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS03
d56e551a-56ab-5b0e-9ad9-f649cc630fd7 | note | ○ Cl.15: End Structures
beb87af1-3447-50b7-9b5c-59564f86533d | note | ○ Cl.21: Gullies
851e6bca-009c-595e-adaa-68cb3bfbf92a | note | ○ Cl.21: Access Chambers
0267a5ef-7f3e-5f30-8b6b-176479f45e22 | note | Check Item - Check Item
63acb582-35fa-5095-8145-6cbeeef06ab9 | note | Reference - MRTS03 Cl.6.1
74f2accc-995b-525c-88c2-0b678aaafc81 | checkpoint | Precast: Installed in accordance with MRTS03-Components shall be laid on a foundation bedding which provides continuous even support to the structures.
3ec4d64f-adca-59fb-a2e7-8bab94bac380 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
73b49687-0ea5-55df-8b54-33199009b186 | note | ○ Cl.19: Precast End Structures
175f89fc-3b0c-5f90-b5a5-713bab112bf3 | note | ○ Cl.21: Precast Gullies
d4f5ffd8-369f-574b-9a99-a86b42f4c7d8 | note | ○ Cl.21.5.1 Precast Access Chamber
5e28ed9a-694b-55ef-83b1-9cb8f6eee10c | note | Check Item - Check Item
910af781-3e45-56ff-9ba0-c571ce6ee993 | note | Reference - MRTS03 Cl. 16, Cl. 21, Cl. 21.5.1
ed4e3e78-1562-503f-a610-3dcdb4446513 | checkpoint | Precast: Culverts shall be joined to shafts/pits to form watertight joints using cement mortar. Cement mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to given smooth surfaces which are uniform with the surfaces of the shafts.
e3f890c7-5303-5b2b-802a-97941bff4b6c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
911fc8f1-9db4-5419-b5e8-cf55e36a99a1 | note | Check Item - Check Item
bd26c297-181c-5e11-8124-6e0d9f2bf489 | note | Reference - MRTS03 Cl. 21.3
e547b3c5-097c-5ba8-bee2-13a474ae3a04 | section | Tolerances
a0958d0b-ddd0-593d-9458-9063f9036be6 | checkpoint | Gullies/Chambers: Vertical Tolerances: Invert heights shall not vary from those specified by the Drawings by more than ± 50 mm
7ee1e0d7-4b61-5945-9cbc-b866bfe88eee | note | Acceptance Criteria & Frequency (Project Specific) - ±50mm (All points specified on drawings)
190dc973-a5b1-5f12-aee0-ca8f2c1a1b15 | note | Check Item - Survey Results
fa256116-86ab-5689-a8a6-7eb408c54dd1 | note | Reference - MRTS03 Cl.21.4.2
2c4e62bc-09e1-5eda-ac9c-6153e6b932f8 | checkpoint | Gullies/Chambers: Vertical Tolerances: The heights of the tops of back-units, grates and frames shall not vary from those described in the Drawings by more than ± 10 mm
e39bb6ef-95e3-5355-a51c-b99e49eaa4d5 | note | Acceptance Criteria & Frequency (Project Specific) - ±10mm (All points specified on drawings)
283f8c5b-d9d1-5972-98f6-abaf0661118e | note | Check Item - Survey Results
10c2c33b-7d65-5c4c-919f-dd1255cd62b4 | note | Reference - MRTS03 Cl.21.4.2
f2269644-0a09-5a86-ad30-427abc159893 | checkpoint | Horizontal tolerances: Gullies: shall not vary from those specified in the Drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line. Access Chambers: shall not vary from those specified in the Drawings by more than ±100mm
1bdf5e35-a5a9-5644-b046-2e7b0c56ea98 | note | Acceptance Criteria & Frequency (Project Specific) - Gullies:
d5c165a9-366e-5fca-aa6c-bd90e96b666a | note | ○ ±100mm in road direction
51443800-5856-506f-bbdf-a88111b12dbd | note | ○ ±50mm perpendicular to road
18de085f-43e5-54b9-b595-962ea08df850 | note | Access Chambers:
283217f8-ff6e-5ee2-9a8b-82b2f9a1839d | note | ○ ±100mm (All points specified on drawings)
11190c5b-1c56-5cc4-bc26-a31a79aaba3f | note | Check Item - Survey Results
9cc9b308-2bb0-56e8-8b9b-e33ca87a2e06 | note | Reference - MRTS03 Cl.21.4.1
87639e7d-f9c5-574c-89ee-03c9030c9926 | checkpoint | Gullies/Chambers: join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures.
08f9d342-faa2-5fc6-9cc2-4b8ead968acd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d34baa97-ebf4-5371-a0b0-ea9dbc0f6200 | note | Check Item - Check Item
775b187b-6edf-5694-b68a-2b17a3054d8b | note | Reference - MRTS03 Cl.21.4.2
884654ab-f3a5-5048-acd9-408d51d6eeed | checkpoint | Gullies/Chambers: Grates on gullies or Concrete top slabs on precast concrete access chambers shall not be installed until all the surveying requirements have been met and notice of such works provided to the Administrator
3e7e1e72-60d4-5439-bdf6-b9d08a08cfc2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
40e0fa22-56f1-5e76-a208-fcdabea37474 | note | Check Item - Hold Point 5, Hold Point 6
26c45252-edd6-5682-b844-6c717524147a | note | Reference - MRTS03 Cl.21.3
7d7c19b5-bb86-5622-a72a-ef91d9ee806b | signoff | HOLD POINT
6ec1d577-3a5d-55a1-b557-23279c1a7b56 | section | Backfill
93518480-ca62-54eb-8e98-a013d53e94d3 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
376de9f0-eb44-5f31-b7eb-7e206e1cfe33 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2a530356-b8c0-5f23-bf51-0c9805ee2438 | note | Check Item - Hold Point 4
0301639d-a5dd-5825-a5dc-24c0ffebd3bb | note | Reference - MRTS03 11.3.10
42bc24eb-9065-587b-aa1f-b895b94149ae | signoff | HOLD POINT
2c92b9e7-a03f-5c87-ad0f-da961733e6c7 | checkpoint | Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
6d396b1a-ea48-5dc8-b506-357d44b34913 | note | Acceptance Criteria & Frequency (Project Specific) - Quarry Material Test Results
32eee7b1-0c63-5a67-a565-3736e73b9a8b | note | Check Item - Hold Point 8
d741f7bf-1325-51ca-a537-f026e849d727 | note | Reference - MRTS04 Cl. 14.2.1
1d6ef02a-fbba-5e95-a4ff-3d7c56810e74 | signoff | HOLD POINT
5bab170f-183b-515c-ab5f-7783d51063a7 | checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the ContractEarth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
d3002297-c941-52a1-99aa-456cd51496d1 | note | Acceptance Criteria & Frequency (Project Specific) - Test Results
c97e207d-4fe5-53ad-984c-101bf2e6e927 | note | Check Item - Witness Point 5
7721af29-196a-5573-8cb5-a1418c118363 | note | Reference - MRTS04 Cl. 19.3.1
d6e534be-28d9-5a06-b16e-a8700afa0be0 | checkpoint | -
a39d010d-6489-559a-9a6f-cb6c00d21167 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c3dbe304-1723-5a53-839f-24daf886c152 | note | Check Item - Hold Point 12
a2f4a22b-e624-564f-9e26-46d8ab6c01c7 | note | Reference - MRTS04 Cl.19.3.3
dfcf56bb-b17d-5a38-8d79-2f197e5bf60e | signoff | HOLD POINT
fe4ef79f-cc72-5f33-b909-78f42ec8a851 | checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 except 100% material shall pass 25.0mm test sieve. Else where material may contain stone sized up to 150mm maximum dimension
8a20e9b3-8c12-5786-9b54-ff3cd3fbdb70 | note | Acceptance Criteria & Frequency (Project Specific) - Class A: WPI < 1200, PI > 7, % passing 0.075mm: 15 - 30
9c54e7e5-1fb4-5187-80b1-fdd36abd1e13 | note | ○ Class B: 1200 < WPI < 2200
8309627a-742d-5bc6-a7e3-ba7ee6874ddb | note | ○ Class A/B: 100% passing 25mm
8d0bb68c-99bc-569a-92d8-e71e9881e4c4 | note | Check Item - Witness Point
8319df49-9332-546d-acf8-f3d63e8018e1 | note | Reference - MRTS04 19.3.1, 19.2.2
e5e04338-5913-566b-8d33-0333f547f613 | checkpoint | Compaction - Q142A, Q141B
af1371ae-b10c-5c78-846a-01dcd1f53248 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
e4545eff-eeb9-5e4a-b6da-31b20520c4e6 | note | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
e31fea0b-6010-5dfb-9365-7f4dd7f26e21 | note | Check Item - Test results
02f01bd7-7616-591f-9ccb-73e1e38b102f | note | Reference - MRTS04 Table 15.3(b) MRTS03.1 Cl.1
9768bc25-a56a-5bb7-8eef-c82def95a5a2 | checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
dda82c75-63c8-5c4a-b0f2-e1c8fa705421 | note | Acceptance Criteria & Frequency (Project Specific) - Class A: 70-100%, Class B: 80-110%
651b987f-0ac3-57e9-80d3-2670b7feaf0e | note | Check Item - Test results
53e79cc9-46b8-5082-a288-d6676e29dc1c | note | Reference - MRTS04 Table 15.3(c)
d80d130d-72f8-5fc9-872b-1fc379f43b15 | section | Completion
a76b1a2c-078d-58f3-9751-aa677be58b6a | checkpoint | A water test on a side inlet gully shall be carried out where the longitudinal grade is less than 1%. Water shall be discharged into the side inlet gully to check uniformity of flow. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel.
8fd8ad99-2059-56b1-85da-339291749f59 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
df3b6081-1550-5384-ba28-a41ba86b1aab | note | Check Item - Witness Point
f68c7ed5-2b9e-5e56-b8f7-399fd90be879 | note | Reference - MRTS03 Cl. 21.6.2
c98f0758-5ff3-559c-a488-c0506b79d666 | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
06b8895a-cb2b-58df-8db0-dba3a14f9d9d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
67c819c1-12cf-5269-9642-3d231316db6c | note | Check Item - Hold Point 3
90f31ca7-0099-52e3-b6e0-c97b4193599f | note | Reference - MRTS03 Cl11.3.5
4e3f9bd4-5a71-5787-a65f-e0dc909c2c0c | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
ee5f8855-7f53-5d46-801c-319dc3581163 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
9969fee1-6fd5-5517-9129-5f06e5401446 | textbox | Print Name:
57e03ec6-db5d-5143-a223-1a9b721fecdb | date | Date:
6f37e305-3e7d-5f68-94fc-8834f58ecff1 | note | Project Manager Verify that the Above has been Constructed according to Specification
01fb806b-cebb-5069-946b-2353bec0e4d0 | textbox | Print Name:
f0a04642-821d-5387-9422-966878e0fec9 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
79a55a78-2b00-5358-bb0e-24f7327af108 | checklist | 03.22 - Subsoil Drainage | itp | 03.22 - Subsoil Drainage
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
ed934c9c-22c7-5d40-bb5b-015155b9335e | checkpoint | Subsoil Drains constructed to appropriate dimensions, inspect trench prior to backfill
2d89a09b-274b-56fe-aefc-bc8f249eb7a7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8c600897-97a6-59bd-9bfc-40bf8899f200 | note | Check Item - Check Item
7208b4bc-640d-51f3-abab-2a0f45c96d92 | note | Reference - BSD-2041
23b8ce4e-e814-5009-9f32-a1c1db1f9132 | checkpoint | Backfill material shall be damp when placed in trench. Material shall be carefully placed in layers not exceeding 200mm loose thickness. Shall be compacted to achieve effective mechanical interlock between particles.
2b62ace5-9a19-5029-bc68-e4212604ec96 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a2a46a9e-4e5b-5aca-a32c-056252be2daa | note | Check Item - Check Item
48b83de5-5df7-56bf-a40f-63eda3533287 | note | Reference - MRTS03 Cl 22.3
d9c5c5a6-8b49-5f54-a8ca-08623e730048 | checkpoint | Subsoil Drains shall be constructed in the locations and in accordance to the drawings. Subsoil Drains shall be installed to the grades specified in the drawings. Where the grades are not specified, the bottom of trenches shall be trimmed to provide not less that 0.5% longitudinal fall towards outlets for pipe type drains and not less that 1% longitudinal fall towards outlets for strip filter type drains.
4fd981e0-a1d8-5879-961b-b4007be62f54 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ba1f141c-81d3-57b6-a280-8760378bfd63 | note | Check Item - Check Item
f8c0363a-5f25-5fb4-b9b0-08c5160caf48 | note | Reference - MRTS03 Cl 22.3
81c3925e-2a40-53c4-9a80-0c98ca082710 | checkpoint | Cleanout and outlet pipes, Geotextiles, trench backfill, concrete for headwalls and surrounds, marker posts shall be as per specification
1b7e61ba-1c2a-5d5b-b9ab-8d39f462f300 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8ec05976-b02f-5fd4-b490-15fa22303ab4 | note | Check Item - Check Item
2a6eb36c-e7bb-5ca1-b2b8-e7fa53faeb97 | note | Reference - MRTS03 Cl22.2 BSD-2041
ec1b10eb-f84e-57f0-9329-e98333a89411 | checkpoint | Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60m for Type B subsoil drains and 50m for Type D subsoil drains. Cleanouts shall be constructed in accordance with the details shown on Standard Drawings 1116.
391555b2-3a33-50f1-8433-2c474ad931c0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5d355a61-4274-5165-8906-39d49e667fe6 | note | Check Item - Check Item
a5364585-bf3a-50d2-8a28-8241e70e14a6 | note | Reference - MRTS03 Cl22.3 TMR SD 1116
787a4ee9-0d76-51ea-95f6-4d140c5e5391 | checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
20346aa1-2d9f-54c2-909e-d671132e21d2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
81ffc51a-2fff-587f-87b2-f9bc23eae545 | note | Check Item - Check Item
61445518-caff-5489-ac1d-e9bdbd1a0fb9 | note | Reference - MRTS03 Cl22.2.7 TMR SD 1116
194ff421-0d5c-56d2-ad40-ea0749de93f3 | checkpoint | Where directed by Administrator, drains shall be flushed until outlet water is clean and flows consistently
3d307b3d-0523-5eab-b753-f58f59c686a7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1859b4e5-f30a-550c-9995-6f39d6f097a9 | note | Check Item - Witness Point
0fdd1167-f21b-55d9-9113-9007fc0f039f | note | Reference - MRTS03 Cl22.3
22d82654-f659-51f5-b19c-20d8e7b8bda6 | checkpoint | As Constructed drawings prepared
5cda2c25-33c3-502c-a5ce-b4e5c498b177 | note | Acceptance Criteria & Frequency (Project Specific) - As constructed drawings submitted to administrator
214cbde3-2073-5d7d-8a30-eb187a83af29 | note | Check Item - Witness Point
18fd4035-d865-530b-9d89-2730707f6f2d | checkpoint | All geometric tolerance requirements met
881dbee2-d054-5f90-91c9-17a166b86137 | note | Acceptance Criteria & Frequency (Project Specific) - Survey
2af3a2ba-aca1-5bcc-9126-6430e0c77b30 | note | Check Item - Check Item
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
e89e7589-681f-598a-94fd-15dc4093c56a | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
53f30444-70fc-53e3-a056-2f88c740492b | textbox | Print Name:
6a267689-8613-5b71-816c-c250046bfa4d | date | Date:
a64bd433-b510-527e-935b-1211b4f0c8c1 | note | Project Manager Verify that the Above has been Constructed according to Specification
d0cfaab0-bab8-5af3-bceb-b463eba14c41 | textbox | Print Name:
7437cd08-72f0-580e-8de8-8d108de4470d | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
e5d99075-fbd4-54bf-b1c0-2436345a82d7 | checklist | 03.35 - Rock Protection | itp | 03.35 - Rock Protection
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
a7ffbb81-d9cd-5f85-9828-ef936152d16a | checkpoint | Rock employed as per drawings. If not specified, between 150 - 500mm, with at least 50% larger than twice the minimum size
dd4352bf-1cad-59a0-b808-58320552909f | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
25288ba0-7fda-5ee0-9de7-084b42b025b8 | note | Check Item - Check Item
58ed7b1f-b2fc-5480-b419-866abe616327 | note | Reference - MRTS03 Cl 35.2
0ed21b02-aa94-5c0e-86b6-5cc21ba2c505 | checkpoint | Uniform appearance overall, and shall not have noticeable overall irregularities in horizontal and vertical alignments. The layers of placed rock shall be of even thickness and of even grading
92d8da8e-64d1-5b40-b85f-3cda72266e25 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
1f69ec87-821e-5c4a-a781-1642cf19aeb4 | note | Check Item - Check Item
3dbb9126-ce8b-5763-b4e3-10796a9c6a8c | note | Reference - MRTS03 Cl 35.3
a1ecf1ce-fd50-5186-8115-7d1d1aeb5492 | checkpoint | Ordering Geotextile Documentation which demonstrates that the design of the geotextile is in accordance with MRTS27 Cl. 6 submitted to the administrator and accepted prior to ordering.
806e1bdb-954a-5ba9-a3dc-4a5d61270124 | note | Acceptance Criteria & Frequency (Project Specific) - Written Approval
3c21d8e6-e793-5fee-a4c4-4ca051865bf7 | note | Check Item - Hold Point 1
be64163f-da5c-5c75-8c28-de0b34e66b9a | note | Reference - MRTS27 Cl 8.1
34cef178-64b1-54b2-ba64-94e0843f1cf7 | signoff | HOLD POINT
823f60aa-4e00-5e5c-a615-db22db57bf41 | checkpoint | Geotextile Inspection of product to be incorporated into works. Where Lot sites are greater than 5000m2, a representative sample covering approximately 15 m² of geotextile shall be cut from each sampled roll but not within two metres of the start or end of the roll. Where directed by the Administrator, samples shall also be cut and supplied to the Administrator.
5cddffcb-a7fa-5b37-98a7-2244b27f9317 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
671464ce-44bd-5de0-ba7c-bc963c7137b6 | note | Check Item - Witness Point 1
eedd918f-e6df-53f7-93cd-5be4b145271c | note | Reference - MRTS27 Cl 10.2
bc0f52ff-6291-5a38-9767-d08d42c6ac98 | checkpoint | Compliance of delivered Geotextile. Geotextile shall not be placed prior to acceptance of the test results by the Administrator.
9cb962e1-18ee-5bb5-9101-ec15614efdd1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
48e9ce59-7d7f-523a-af0d-c6242300f15a | note | Check Item - Hold Point 2
14217947-ec6f-5580-86d1-2f2e29d560b8 | note | Reference - MRTS27 Cl 10.4
c3a58e86-a794-51db-9493-78583263415f | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
a0f2d24e-3a34-5395-8cc2-3112bab63693 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
3b405a56-c7b9-5ab5-a46a-d860145f6b72 | textbox | Print Name:
c1778ccc-d0e7-5c34-ba36-ddc32a62e839 | date | Date:
ff321220-53e0-52de-b979-a48b007bf9ad | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
afbc2974-3f4b-536d-a5e7-d8bf827c4fc4 | textbox | Print Name:
4fb046cf-51a5-53b8-b36b-3df30c745890 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
d017e50c-2ad7-5cd8-a43b-a3ffefd73426 | checklist | 04.07 - Clear and Grub | itp | 04.07 - Clear and Grub
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
664369c7-5ba9-5dc1-b631-e509f6d35d5f | checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
d41e524f-c4fc-5082-9d84-101c6b5b9806 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ff5b5717-dd2c-58d7-8807-dbce300727b5 | note | Check Item - Hold Point 2
693af9be-5a14-52ee-bd67-874eb02726b8 | note | Reference - MRTS04 Cl. 7.2.2
2935e9af-c2e3-5ce3-a800-45e7ff6149c3 | signoff | HOLD POINT
e80473b9-0542-5dc2-bda9-edc8d3afd710 | checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 1.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
6ed6cd20-5ab7-5363-b68f-03d4ec8cbcb5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f800de32-4f30-5b88-bb2c-a3a7f55c576d | note | Check Item - Hold Point 3
651dfa43-485d-5e29-901a-f55fe8ef9077 | note | Reference - MRTS04 Cl. 7.2.3
c4660e9d-1842-5c69-a44a-3fc748b8db0a | signoff | HOLD POINT
9eec285c-853b-5559-bba1-c03294e94582 | checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area shall be installed.
26a3a376-9417-5379-be69-969eb00164e0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
28b90337-3927-59e2-95c5-59494efef722 | note | Check Item - Hold Point 2
778d7212-aac4-5f8a-bd69-bc8303dc8f51 | note | Reference - MRTS52 Cl. 7.1
1ddc0205-a5dc-59a4-9240-70491f33d7e2 | signoff | HOLD POINT
f0fb7fa6-aeec-59e8-a788-b18ea549b327 | checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
1c20b946-fe40-5109-a98e-0729a4ed1d75 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f7186aba-ac85-52f8-84ad-5c138c808e49 | note | Check Item - Check Item
bcd7a5a5-1ce3-5927-9353-fb24d23116da | note | Reference - MRTS04 Cl. 7.2.5
b66b05dd-8703-58f2-87da-0b7ff80fca86 | checkpoint | Surplus topsoil material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
359c16e2-d84e-542a-8f54-9774d655f0d9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
555b9dce-a6cb-525f-8a47-35dc6ac2e538 | note | Check Item - Check Item
69650099-11b9-543e-92c0-aa5c85b9f08f | note | Reference - MRTS04 Cl. 8.4.2
5f3ee9f4-96d3-53d5-88ba-5fab2de292d2 | checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 and Cl. 1.4
33638263-2bec-5ecf-b25f-3496e29b8228 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
58fe3e68-f026-5ae5-8fe9-c2e8c58c69f9 | note | Check Item - Check Item
8e694c7e-5f58-5e4a-bf78-b72fa9ec3fd5 | note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
410d155d-4d97-5f0c-9add-7da75d0360cd | checkpoint | The additional width for clearing (no grubbing) is 3.0m as per Annexure MRTS04.1
fafe0670-097b-51f7-8da6-3decf7c29e8b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
26de57f5-d3c3-5bda-a876-6260e81618c1 | note | Check Item - Check Item
71b07f46-b75a-57ea-94e4-f6362fef9e68 | note | Reference - Annexure MRTS04.1
5863e867-6144-5c02-b156-1f05bad37ff5 | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
a0081bec-8d1e-5def-aad6-09ffbac1ea39 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6c4411e1-90e5-516d-a1bc-d7a5f80a94a2 | note | Check Item - Check Item
f5175bce-205e-5d9e-bb4e-d5aa500d7c92 | note | Reference - MRTS04 Cl. 8.4.3
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
76bebcc9-a85d-502c-b800-d568da1f6dc6 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
3b6b831a-b41c-5ef7-b809-0060c6651d7d | textbox | Print Name:
60184d50-3c1c-56bb-9ea2-2790fc5b104e | date | Date:
efeb7446-78f1-54c9-969f-b3d0b19caf04 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
9fd5b1bc-dab0-50ca-ae19-dd1e5b524939 | textbox | Print Name:
186da9ca-55dc-5ba0-b857-70d46b8a4d4f | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
6f1c312d-55e1-5127-b872-9d13bc4cb335 | checklist | 04.08 - Stripping of Topsoil | itp | 04.08 - Stripping of Topsoil
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
77c046b0-302a-5335-bd03-41c56ed3370c | checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 75mm (+/-25mm) depth, or from areas and depths as specified in Clause 2.1 of Annexure MRTS04.1
b4cdc59a-8dad-56fb-ad3a-a4b91b288c67 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
68d282d0-5f78-5140-9ddc-ed99473c017c | note | ○ All areas within the earthworks footprint; beyond the back of existing kerb or where there is no kerb, beyond the existing road formation shall be stripped to an average depth of 75mm
66a0182a-c62a-53fb-9626-161fe6035b2d | note | Check Item - Check Item
81121c01-5ae9-5b31-acef-11178471b061 | note | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2.1
6ebca127-234c-5457-91a3-92a322a770c5 | checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
8fbd6039-66e3-5b51-b488-27331cbf735e | note | Acceptance Criteria & Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
d0f0d2a6-73a3-5766-a41e-cdbc1d115721 | note | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
a0add457-80b0-5c16-84fb-f6b9a5a2b689 | note | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
68527d20-1b56-5bc9-a0fe-be28e9d841fc | note | Check Item - Check Item
ae749139-433e-5705-aec8-3fb4164d8a97 | note | Reference - MRTS04 Cl. 8.3
a715d373-000f-58eb-836e-831527c24b91 | checkpoint | Surplus material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
7faf3d41-2a74-534f-b3c5-f68cc8048667 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ca1778c5-2293-5ecc-a688-60eaa27451b5 | note | Check Item - Check Item
4b312bcd-71e3-56cc-b270-8dd0cea559d9 | note | Reference - MRTS04 Cl. 8.4.2
5863e867-6144-5c02-b156-1f05bad37ff5 | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
749742f8-73c0-55c2-9b3f-e79060392b51 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8bb0fbf9-08fb-50a5-93b2-92c1bb2f99b3 | note | Check Item - Check Item
b94b804c-a745-5089-95cb-8e60dbab5cc8 | note | Reference - MRTS04 Cl. 8.4.3
7f2ebdf3-e80d-52ef-b1e0-bfc87a60a70d | checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor and approved by the Administrator, as stated in Cl. 2.2 of Annexure MRTS04.1 All costs associated with undertaking necessary earthworks required for the stockpile sites shall be deemed to be included in the Contractor’s scheduled unit rate for the corresponding earthwork items
7de73953-4f27-5874-bbe8-f5529d88e673 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
013e9be0-0883-5f43-8789-bcbb27177bf0 | note | Check Item - Check Item
121b9998-2d6b-55d5-8e88-dc19f0dbfa43 | note | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
7ca97287-9203-5a9c-946f-023dda0da5d3 | checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
a711dfb1-65ec-5092-8124-ff0aa3e49b3c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e38bf0c1-95e9-5289-90c5-e909c3cf2935 | note | Check Item - Check Item
6156611d-beab-575f-9f67-4fe427bd58cd | note | Reference - MRTS04 Cl 8.4.5
2a2a04dc-f419-5d70-b77c-80ecb329a66d | checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
4052bf09-528e-56ce-8d7b-261ba6d28faa | note | Acceptance Criteria & Frequency (Project Specific) - As Constructed Survey
07e56897-5610-5ec6-beb1-3ae4ad76b5ea | note | Check Item - Survey Report
c61e2444-5e7b-5b34-bf64-f5ef24bfd6c0 | note | Reference - MRTS04 Cl 8.4.5
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
58a6a64d-1f73-58b9-8ec1-afea957fa54c | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
dbbd4ecd-e4ad-57bb-9881-c120299d1eb1 | textbox | Print Name:
8e650b3a-2406-526b-abeb-3d21fcd2f7b0 | date | Date:
21fc0210-eff4-509d-804c-5fc95a80826c | note | Administrator's Representative Verify that the Above has been Constructed according to Specification
cb707e1d-24cb-5f9b-a26c-0c92ce1c7022 | textbox | Print Name:
3e134e83-f6be-5a38-bb5f-5c1ec6f39cc2 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
04215a61-aef6-537a-b01d-0e085f6923a0 | checklist | 04.09 - Unsuitable Material | itp | 04.09 - Unsuitable Material
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
7da1b574-4063-5c22-8967-d5a5a70d69fb | checkpoint | The identification of unsuitable material shall include items listed in MRTS04 Cl. 9.2
2145ff27-dece-5f6a-ad75-ccb4cdea0b06 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c7132e78-3cf9-5dce-bc38-2294ada9a2ff | note | Check Item - Check Item
16abf98b-87be-5cc4-9a86-c21095f9e19a | note | Reference - MRTS04 Cl. 9.2
d35d257c-6c54-59f7-a6f1-0c2285d21e7c | checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim.
053e05bf-4687-5d3c-a757-0da9f2ac0b96 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
766c3bd7-ef97-526e-8db7-81aa1e04e5d7 | note | Check Item - Hold Point 4
fa4f17e8-62ee-59e1-a80d-d4f334eef577 | note | Reference - MRTS04 Cl. 9.4
41a71747-8185-51c6-ab68-b3a7d3920565 | signoff | HOLD POINT
07389f6c-d602-5da6-a128-02adc748fc36 | checkpoint | Excavated as per MRTS04
369cd81a-2039-55b1-9009-fceeacd3c4cb | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (General Excavation ITP)
2538c9f9-b11d-57fb-9f72-6e5bb3763438 | note | Check Item - Check Item
ec9300ee-53c7-5183-964a-222bc049b6bf | note | Reference - MRTS04 Cl. 13
413da91c-fb37-5159-9cf7-387f022e3b1a | checkpoint | Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 and notice of such Works provided to the Administrator
aff2339b-730e-5ace-b673-cd956fd14d68 | note | Acceptance Criteria & Frequency (Project Specific) - Survey Report
ac82d58a-4466-5956-9fb7-b4932eae899a | note | Check Item - Check Item
0cf39f7d-a61f-5ace-bec4-a89c33e90808 | note | Reference - MRTS04 Cl. 13.3.2.2
aed454b7-d279-579b-9aaf-f8fb38a1953c | checkpoint | Backfill as per MRTS04 Replacement fill material shall be placed uniformly in layers and compacted using compacted layer method
07d96de4-4449-5853-b163-fde4a25e52c1 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Backfill ITP)
fd06afe3-800c-5398-aed9-0f21983388d0 | note | Check Item - Check Item
f52f2a8c-6400-5bad-9fb7-e369b7e3a39f | note | Reference - MRTS04 Cl. 13.3, MRTS04 Cl 15.3
92e2c8e8-4467-5dcd-a011-2bdff199cdd1 | checkpoint | After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken.
ec491be6-51d4-5bfc-aca3-fa5870cf4520 | note | Acceptance Criteria & Frequency (Project Specific) - Survey Report
49b78e84-02cc-5db0-b55e-39692f97d2bc | note | Check Item - Check Item
74c3408b-ee58-5f05-8dac-f39f75e0d33d | note | Reference - MRTS04 Cl. 13.3.2.2
bf831347-f2b8-54a0-bc1d-3887e361ddb1 | checkpoint | All surplus material and/or Unsuitable Material shall be disposed of off the Site
dfa7dc9a-4065-5187-8231-40d6b898da7a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
591ff2b8-9367-5579-bc2a-d0bd235c14c2 | note | Check Item - Check Item
1aea6f73-b23e-5519-8f25-0e3a64243e40 | note | Reference - MRTS04 Cl. 11.3
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
b3c36826-fc39-5098-a25e-208b664e25d2 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
67bb143c-2234-5613-8915-9221277885b6 | textbox | Print Name:
10a85c3d-4321-54b5-8f8a-3eb65c403172 | date | Date:
d4d0978c-576e-5743-a886-096b4e890f84 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
c983e31d-1075-59e5-a0f5-baf1fb8426c2 | textbox | Print Name:
a2a897fb-5e59-5118-87be-426d765d3ba8 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
f3040815-f88f-58c2-982a-09e5f7872883 | checklist | 04.12 - Ground Surface Treatment | itp | 04.12 - Ground Surface Treatment
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
fef421ff-1b2e-5740-80e4-75fc0b9a92ad | checkpoint | Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the Site which could reasonably be expected to have a possible acid sulfate potential.
32d45279-6d05-546c-a0ac-847226668f32 | note | Acceptance Criteria & Frequency (Project Specific) - Field pH testing As per National Acid Sulfate Soils Guidance
3cc9318f-bd7f-5df0-b6f0-b2dce1fc7e6f | note | Check Item - Hold Point 5
ffcce926-26cb-5537-af41-310b001fbb90 | note | Reference - MRTS04 Cl. 10.1.4 Table A2
0ddc893f-0f12-514c-ae3e-d0cb294f8492 | signoff | HOLD POINT
cf0a6d46-25e0-5d1b-9d7a-6a66d9b7db23 | checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
4caab747-244c-52af-b8f0-61733301355e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
47dc84b4-547a-5b45-9e92-09b0feffdeb2 | note | Check Item - Check Item
13df82e1-d237-5322-aa29-72fce1c06b09 | note | Reference - MRTS04 Cl. 12.2.1.1
cb89603d-bc62-5d87-b3b3-579a4280954e | checkpoint | Holes and localised depressions filled with similar material to the surrounding ground surface or material specified and compacted in accordance with Cl. 15
0ad7d230-16f6-5b62-9a00-219c8bd948b4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6676ff17-465d-5e77-a0f5-f9611c3819cb | note | Check Item - Check Item
79caac8c-a266-5b0a-880f-d8cf7a8b78fe | note | Reference - MRTS04 Cl. 12.2.1.2
730a2cf9-360c-52ad-9e60-b13cf7674bf7 | checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim
af671017-4e9a-5778-8a97-03f7d6fa4f79 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8e84ce28-553f-5e04-860e-90326effcae4 | note | Check Item - Hold Point 4
36cc2d85-c916-500c-802b-0f606b69bd7b | note | Reference - MRTS04 Cl. 9.4
33246af5-e23b-5f64-9317-7cd56254a2d0 | signoff | HOLD POINT
5925ff81-54ea-5c49-8c39-b7150fef1831 | checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl. 15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a maximum depth of 300mm using appropriate methods. Material below this depth shall be assesed under Clause 9.2.
fa0c7538-bb21-5bed-afa9-a1b599be0b96 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
525e6ac0-c7e2-5371-a1a8-efe7859eb200 | note | Check Item - Check Item
32038070-dc6b-5655-a4d7-f9db6201bb20 | note | Reference - MRTS04 Cl. 12.2.1.3
72668b6f-35c8-549d-87dc-bb5106709c99 | checkpoint | Relative Compaction - AS 1289.5.4.1 or AS 1289.5.7.1 After any clearing and grubbing, stripping of Topsoil and replacement of Unsuitable Material, the exposed ground surface on which an Embankment is to be placed shall, as a minimum, be scarified and re-compacted to a depth of at least 150 mm
9cfad661-5842-5c00-839c-140a1d25692c | note | Acceptance Criteria & Frequency (Project Specific) - CV 95% minimum - 1 tests per 500 m2 (min 1 per lot)
5873b74a-7cb5-59e5-bcd5-292f18a7139f | note | Check Item - Test
86312a87-1d83-59fc-ad35-dbf19ae37fec | note | Reference - MRTS04 Table 15.3(b) App. A
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
83c308d8-6254-5d54-90c2-3c6b0b0d925d | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
b2fa6d79-456a-51d5-b01a-9baaa7d85ae6 | textbox | Print Name:
4a7f172b-def5-5133-bfd0-94253d5129fe | date | Date:
638c6fa7-4215-509f-a0a2-7aff24f38737 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
7c45a26f-1578-5379-9030-21c63fda9bf2 | textbox | Print Name:
01afcf9c-f500-5b54-b7ea-dd85358e1636 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
337e45e4-700d-57fc-92a8-07f591015e44 | checklist | 04.13 - General Excavation | itp | 04.13 - General Excavation
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
b740724a-4267-5bf8-9697-33e9acf180d4 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
04abb5b1-384b-5ce1-8729-032d0b3f72c6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
33c5e7b4-5be3-5e86-8e9a-a781ce984c08 | note | Check Item - Hold Point 4
4751da71-d577-5816-abde-75f481792bf1 | note | Reference - MRTS04 Cl. 9.4
5598a9df-6cae-5cae-84d2-7583a3ab588f | signoff | HOLD POINT
e5f9b15c-a1a7-5468-893e-0930c1f8f446 | checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
d16a6292-3dfe-5cfb-8afd-a750de987546 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b5968691-c3f0-53ce-b6bd-9569ecedc2f9 | note | Check Item - Hold Point 8
8cef8bf4-348c-5f3a-91ed-c73355d8579c | note | Reference - MRTS04 Cl. 13.3.2.1
a67c1e62-90a9-5768-9a29-0b04f71086f9 | signoff | HOLD POINT
97e45626-d0e5-57b8-9ce2-c1ff0a371d61 | checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
3e31077a-5615-5327-9a6d-8ab8f63b2cb9 | note | Acceptance Criteria & Frequency (Project Specific) - Survey
dbaa7180-2eba-5ba4-888b-3feac7018284 | note | Check Item - Check Item
c472f582-bcc3-5376-86a1-7be92dfd5723 | note | Reference - MRTS04 Cl.13.3.1, Cl. 6
55165a54-81f6-5842-8ecc-b0096c9202d9 | checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
d46487e2-fe3a-5b1e-9f8e-640471fbbac3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c99bfa40-313a-5496-bd63-7b28d10d80db | note | Check Item - Check Item
10c6c75f-3026-5efa-b6da-87d083aea6ad | note | Reference - MRTS04 Cl. 13.3.3.3
36ec616c-3b62-5e75-97c0-8c06fa7a6e1a | checkpoint | Dewatering of excavations shall comply with requirements of EMP
038be423-dd90-590c-a1b6-ba7553c2de76 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
51952c2f-b94d-5738-a6d5-d19b6fea58bf | note | Check Item - Check Item
ec71f611-1b4c-59bb-a595-435c5083a4be | note | Reference - MRTS04 Cl. 13.3.8
990e647a-d819-5ec4-a96e-ff38f9171e9d | checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
96a2bb18-4413-591b-ab59-8aeaaccd87e2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f470a1b4-3712-5a1f-a2a8-63e13472179b | note | Check Item - Check Item
3af06b87-15e4-5b68-a83d-a99f608286c3 | note | Reference - MRTS04 Cl. 16.1
19ac1d81-2152-56da-8287-b5ee98a5051f | checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
bcf76677-d420-5b16-b587-910a35a5fdd2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0259410d-450a-53d4-a352-2e079a724560 | note | Check Item - Check Item
a94548cb-eb0c-5f28-b978-1a491f5d15ea | note | Reference - MRTS04 Cl. 13.3.2.4
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
a7eba785-1be8-5123-b0ac-5ab50ae6362a | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
081b9075-2384-53e2-a98a-3cb080f54dc5 | textbox | Print Name:
9976eb03-0a26-521e-a2e3-2e75940ff163 | date | Date:
774d07d3-d093-5dbd-bd28-e10b3bc9d8ae | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
9f44bb86-e5f3-5ec6-92f4-3def0a47e623 | textbox | Print Name:
d09be4e9-340b-5c24-8b21-ba08ca972f4b | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
db19c12a-1b17-5b2c-b809-432030246608 | checklist | 04.14 - Embankment | itp | 04.14 - Embankment
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
7d995657-4700-53b5-b63e-aa06af61c958 | checkpoint | Earthworks construction procedure shall be sumbitted to the Administrator at least seven days prior to commencing the Works.
16a4a1a2-13b8-5526-9e5e-2a70c96be68a | note | Acceptance Criteria & Frequency (Project Specific) - Construction Procedure Acceptance
d8335780-aa20-5f19-986b-a6ecd14398c6 | note | Check Item - Hold Point 1
d18a3e24-5a69-572b-bc78-25be80a0e73c | note | Reference - MRTS04 Cl. 5.2
2deaf61c-dac7-55bb-be9d-7da4a0484f23 | signoff | HOLD POINT
69103917-134e-535e-aa9a-52677f06c27b | checkpoint | Define lot size.
f6a0c921-cbd8-51c3-8917-2fd505f9a2f8 | note | Acceptance Criteria & Frequency (Project Specific) - Normal : Max 2000m2, Reduced Level : Max 4000m2
2ae4a55c-4bec-5826-90bd-01d7d7337ff4 | note | Check Item - Check Item
7b4d4f47-abb6-5cde-a94c-45c66e9d41d1 | note | Reference - MRTS04 App. A Table A.2
a55a4b07-2b27-5daa-a844-7eb74955dc6c | checkpoint | Earth Fill Material stockpile or source material results submitted to Administarator
af2dbc68-ff07-5fb5-837e-234ff1b92932 | textbox | Reference Stockpile Lot No. :
55f05e65-9bcd-5648-9885-f651ef966e45 | note | Acceptance Criteria & Frequency (Project Specific) - Stockpile Lot Acceptance
65d2659e-b82e-5cc5-ad77-0c2dbc7e2f81 | note | Check Item - Hold Point 10
69fb7bc7-3a9b-56bf-83ba-37eb8fd39285 | note | Reference - MRTS04 Cl. 14.2.1
62fdb3fa-1165-53b9-abb8-f12ba318add4 | signoff | HOLD POINT
8faae75a-730e-579d-8e9d-f1546ff320f4 | checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported, complies with General fill Class A1, A2 or B and is homogeneous.
f8923987-7f5d-5dbf-85f6-677efeeb47a8 | note | Acceptance Criteria & Frequency (Project Specific) - Stockpile Lot MRTS04 Table 14.2.2
c2e1ea52-79c4-561e-90b2-5d4ad9770555 | note | Check Item - Test reports
70fd26a1-6f55-536e-a192-a25fea976978 | note | Reference - MRTS04 Cl. 14.3.1
cba9bea8-418c-51c6-a8f7-089525db77fa | checkpoint | Compacted Layer Method: Fill material placed uniformly in layers. Uncompacted layer thicknesses;
bc56c227-67da-56d5-86f6-c405cbde2331 | note | – General Fill 150-300m
d27e6ed5-cb92-50e5-baa6-1045b4d2fcad | note | – Fill material in water-retaining embankments 150- 200mm
1220f118-bc3b-5c99-9713-da7ed8b4e2a1 | note | – Backfill except Sand 100-150mm
875e758c-8c60-51e1-b668-a19cd03c413f | note | – Sand 150-300mm
753d903b-65b7-5abd-9a57-135c79f9701f | note | ○ Fill compacted to required density (by Characteristic Value)
d9cc85a1-93f3-519d-b031-69d886b6b05d | note | Acceptance Criteria & Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
7e04500d-0eac-51c4-979c-5181c029b5a6 | note | ○ Top 300mm below Subgrade Level ≥97%
df071437-6a32-5fef-ad94-4ae03a5438b6 | note | ○ Greater than 300mm below Subgrade Level≥95%
264d2c55-178c-513d-9afb-3616b2db60fa | note | ○ Normal: 1 per 500m2 (per layer), 4 per lot
5df6f898-744f-5373-b17e-a8648183239b | note | ○ Reduced Level: 1 per 1000m2 (per layer) or 4 per lot
3004daf6-44c4-5eab-b8e3-f6d5e5b6fa4b | note | Check Item - Test reports
65f6e248-6673-5659-ae3f-3086cc2a8420 | note | Reference - MRTS04 Cl. 15.3 Table 15.3(b)
230874ec-0682-54d6-a537-c03a894f7f16 | checkpoint | Compacted Layer Method: Embankment moisture ratio within ranges specified Rainfall Zone: HIGH
4320ab68-032c-587f-adda-240735431cee | note | Acceptance Criteria & Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
3048cf83-8704-55c2-8863-0ef7217e214f | note | ○ Class A1/A2: 70 - 100
08c96c00-d1da-514b-ae51-316199a371f2 | note | ○ Class B: 80 - 110
2f95677f-e9bf-555a-b22c-68e39d6f347b | note | ○ Normal: 1 per 500m2/layer or 4 per lot
f29c134c-86af-5d56-9c29-4fd36f924d67 | note | ○ Reduced Level: 1 per 1000m2/layer or 4 per lot
58f9a9ea-d8ba-5b05-bacb-83c7eebd63a5 | note | Check Item - Test results
984b7a77-58c7-5783-8035-d673535f9f2b | note | Reference - MRTS04 Cl. 15.3 Table 15.3(c)
9626724b-fdcf-594f-a1ef-1b6ecd60ad1a | checkpoint | Testing of Each Layer: Each layer shall be tested to conform the requirements as per Clause 5.6 before placing the subsequent layers.
b23d0681-c9b0-579e-b66d-7b64a22d43d3 | note | Acceptance Criteria & Frequency (Project Specific) - Testing after compaction on site
cc3ce159-ec34-51fc-989f-d430096672a9 | note | ○ Gradings: AS1289.3.6.1
70024648-3039-551e-b133-ce2b0fa88973 | note | ○ PI: AS1289.3.3.1 or AS1289.3.3.2
0dff2ed4-bfc7-5630-858b-ee4908feed66 | note | ○ WPI: Test Method Q252
0e432f91-450e-5585-8e9c-486916d769c9 | note | ○ 1 per 1000m2(per Layer), 2 per Lot
c15575e7-7fca-561f-a3f8-868b17afb501 | note | Check Item - Witness Point 5
d1d0b002-d99e-5684-bff0-b6cd9c075867 | note | Reference - MRTS04 Cl. 15.3
aff05d78-2083-563b-988a-f55559c0178e | checkpoint | Mechanical Interlock Method: Each layer rolled until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
4b5ee2f5-c25f-51d8-9294-970a04efae3d | note | Acceptance Criteria & Frequency (Project Specific) - Table 15.4
36fcf632-57b2-564d-a18b-e6197bda2eb8 | note | Check Item - Witness Point 6
a40e0688-8913-58b6-b6d2-37add05d7630 | note | Reference - MRTS04 Cl15.4
21ab8c39-3d95-54a9-82e8-2e6c30369bcd | checkpoint | Geotextile placed at interchange between compaction methods
ef74f9b0-bdee-573d-a559-48684bd63582 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e372cca3-2f67-56f6-9337-15c4993b1ef7 | note | Check Item - Check Item
c9b1dee1-d2a4-5761-9899-dc5ede269ae7 | note | Reference - MRTS04 14.3.2
45559a51-3008-5b1b-a97e-f25e3c5c7318 | checkpoint | Within Vertical Geometric Tolerance
426e7397-b879-574b-9751-a7902b5bbf98 | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
1419edae-abfc-5d98-af9e-400efd37a0f9 | note | Check Item - Dip Sheet Records
47438ca1-9f23-5aba-adc6-e98e107e227a | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
6471b3b3-f00b-590d-ae14-42ff2a4ec1ec | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
b438b910-0dba-5814-8718-71920838a726 | textbox | Print Name:
2b80b62f-37ef-5af2-b653-3dbd94d4617b | date | Date:
23a13e4a-108c-5e84-87a4-a84e015c2afb | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
ae7d8768-9f0d-5e33-9c20-6b93f9fcbd74 | textbox | Print Name:
fee098f6-5131-5c58-ba13-aad6648cc60b | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
9337d250-4891-5881-b6b3-693f6dc96121 | checklist | 04.18 - Subgrade Testing | itp | 04.18 - Subgrade Testing
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
8fb0705f-255e-56ed-8cce-d7d8ec6c2af3 | checkpoint | All sampling shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
4b1e7a12-e133-5eb9-893c-c62c64a8c154 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9540c06d-d8d1-5780-af03-e0628b36abc2 | note | Check Item - Witness Point 6
fa80e8f4-5c1a-5da0-a471-f6f288ce9173 | note | Reference - MRTS04 Appendix B.4
ec00b901-05a9-5755-abeb-1136cc1292ef | checkpoint | Each different material encountered within this depth in Clause 18.1 shall be sampled and tested in accordance with this Technical Specification unless otherwise approved by the Administrator.
6bcc1937-4e2d-5cf0-91e8-2929b29c1606 | note | Acceptance Criteria & Frequency (Project Specific) - Testing
50b5e33c-7810-54bc-8169-35962acb411f | note | ○ 1.5m below subgrade in CUT
f3068df2-5ad3-5558-b510-9ab40c3452e7 | note | ○ 2.0m below subgrade in EMBANKMENT
fe94e147-d00b-554d-b7a7-e12fe23aadca | note | Check Item - Check Item
a6e5c275-0e37-5067-aee0-eba99d6e8a0d | note | Reference - MRTS04 Appendix B.3
7d646eb6-763d-563b-89c6-09c584bc1f05 | checkpoint | Untreated subgrade material shall be sampled from their natural location in accordance with AS1289.1.2.1. Untreated subgrade materials that break down under environmental and service conditions due to weathering shall be pre-conditioned by artificial weathering in accordance with Test Method Q101E
481eb28f-eb88-55c7-aeeb-1330793951f8 | note | Acceptance Criteria & Frequency (Project Specific) - Testing
7abe3768-10aa-5c23-b825-e6858faab624 | note | Check Item - Check Item
83ec5dc1-02ed-5bcc-a1e5-030e3b6d5f75 | note | Reference - MRTS04 Appendix B.4.1
2c1d2784-7725-5145-81ef-67db1ce1da79 | checkpoint | Fil Materials from Stockpile:Materials which breakdown, degrade or fracture during construction, such as highly and extremely weathered rocks, shall be pre-conditioned prior to compacting the specimens for testing. Preconditioning may include:
38b2794a-0c24-5b9d-ba81-6602929e45d3 | note | – Lab preconditioning
3a3c7d9c-d4f6-5563-84ea-b711fa3c20a2 | note | – Field compaction using construction methods propsed for the works
01abf471-5520-5a4b-88a5-6e978da57e5c | note | ○ The pre-conditioning method shall be recorded in the in the submission of the test results detailed in MRTS04 Clause B.5
53708d08-d8a6-56e1-b6b2-c49d3f5900bd | note | Acceptance Criteria & Frequency (Project Specific) - Pre-Conditioning
c9841292-e601-53e0-a098-ec74f5a0942e | note | Check Item - Check Item
88bd8100-c937-572b-8225-d5df27a8b6d3 | note | Reference - MRTS04 Appendix B.4
02a61ff0-8334-51b6-b6d7-9438c929b6bf | checkpoint | Fill Materials after Field Compaction: Obtain samples from the completed fill (after compaction and proof rolling) in accordance with AS 1289.1.2.1. Samples shall be taken over the full depth of the compacted layer.
7ec2bab1-4f89-5651-ab60-a9db344bb189 | note | Acceptance Criteria & Frequency (Project Specific) - Test Reports
26f2e916-550e-551a-b1b4-e612ff96d214 | note | Check Item - Check Item
c9bf6100-697a-5f71-8987-222c28a92fe8 | note | Reference - MRTS04 Cl. B3.2.2
50c56639-948e-5958-81c9-4cec6dd33e15 | checkpoint | All testing shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
357b42c4-223c-5a76-ad40-236873ccc42d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
65ecc99d-eddc-5019-9919-60f4a0b9b6ca | note | Check Item - Witness Point 6
d64935a3-4823-5d15-adc2-701e7b7c8388 | note | Reference - MRTS04 Appendix B.4
4f822a4c-3299-5d9e-a8f7-1ed073882dcd | checkpoint | Each untreated subgrade material sampe and each fill material sample shall be tested for: laboritory CBR, swell, PSD, maximum aggregate size of fill materials, liquid limit, plastic limit, plasticity index, weighted plasticity index, insitu moisutre content
a993f782-e647-51b2-9629-e89105ea759f | note | Acceptance Criteria & Frequency (Project Specific) - Testing per material type
514e2678-fca1-5d32-9ddb-b4e9236aaf71 | note | Check Item - Check Item
b630ebe8-7688-535b-b8ef-0d153f759436 | note | Reference - MRTS04 Cl. B.5.1
2541fe05-32b2-57e1-9dc6-8bc4905af93c | checkpoint | The contractor shall provide all the information to the Administrator as detailed in Clause B.6.2 or B.6.3 as relevant.
f93d280c-a134-571a-ba81-60d8ae52ed1c | note | Acceptance Criteria & Frequency (Project Specific) - Test Reports
a1ce8e37-a73f-5691-9be9-70462543e874 | note | Check Item - Hold Point 14
e7bdb7d0-55f6-5091-9aba-c6e97e3735c3 | note | Reference - MRTS04 Cl. B.6.1
8755a835-9cb6-5537-88b8-0df3509c8254 | signoff | HOLD POINT
f1418308-a26c-5988-925b-6ac60a790473 | checkpoint | For each untreated subgrade lot, the lot CBR, lot swell, and lot expansive nature classification shall be determined in accordance with Cl B.7 MRTS04. For each source and type of fill material, an assigned CBR and an assigned swell shall be determined in accordance with Cl. B.5.2 MRTS04.
48de4ddc-3f39-5819-8934-d1ef3c2751f0 | note | Acceptance Criteria & Frequency (Project Specific) - Testing per material type
965eed1e-3d51-5612-bf35-22381acd8b36 | note | Check Item - Check Item
fa062443-cf14-571e-b737-af0b382557b8 | note | Reference - MRTS04 Cl. B.6.1
aa481e61-b521-5047-9bc7-06dc6a9d5eab | checkpoint | Untreated subgrade material testing
711880de-f2d3-5a45-b685-915c3871ffef | note | Acceptance Criteria & Frequency (Project Specific) - Test Reports
a15047de-5fa4-5e0c-b090-fc1003d90c71 | note | ○ Soaked and Insitu CBR:lower value of the lower 10th percentile of laboratory CBR - per material
e34ab68a-1fcb-5cb5-8ef5-c0855bedb3f4 | note | ○ SWELL: the upper 10th percentile of the swell test results - per material
cea4d5af-6593-525c-8207-38ff357ae326 | note | ○ PSD, PI, WPI, LL, PL, Moisture - per material
29e2e045-535e-563d-8a65-52827f146160 | note | Check Item - Check Item
d0c98a27-03b8-5dce-933e-f8ead635b993 | note | Reference - MRTS04 Cl. B.4
cf85b8de-102b-55f4-917d-17552559511f | checkpoint | Fill material subgrade testing
80833f32-3896-5edc-973a-b549e671975f | note | Acceptance Criteria & Frequency (Project Specific) - Test Reports
1c93b5b5-650d-550f-ba5f-98e65249667e | note | ○ Soaked CBR:lower value of the lower 10th percentile of laboratory CBR
84a9638f-44e2-5cd4-a9cc-2fa9aa968590 | note | ○ SWELL: the upper 10th percentile of the swell test results
6578b9fe-18dd-552a-afca-dc30e2109686 | note | ○ Maximum aggregate size, PSD, PI, WPI, LL, PL, Moisture
74532acc-5632-51a7-8bba-9fa7d2b26cd4 | note | Check Item - Check Item
09e43801-2544-5822-b959-1e6cfcd71159 | note | Reference - MRTS04 Cl. B.4
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
82a8086d-6373-5220-9fdd-124b27c4eed7 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
1aa1a98c-e76f-526a-99a2-2bb02eb315c4 | textbox | Print Name:
444c708d-9588-5be0-875f-1d0c8367e1f7 | date | Date:
1dae8657-6a5a-5483-a105-1503311fc770 | note | Project Manager Verify that the Above has been Constructed according to Specification
fdcfc16b-005e-5f24-9967-0e7dbc9e3229 | textbox | Print Name:
af3bed0c-a66c-5ec1-89a9-da5670a8f4f0 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
99b7c633-3b1f-5628-bcf9-417a51adcc9b | checklist | 04.181 - Subgrade Level | itp | 04.181 - Subgrade Level
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
6aff2c5f-7614-59a2-9f3f-599a713936c0 | checkpoint | Define Lot
04cfe375-b967-5927-b8d1-2f807b99cdc8 | note | Acceptance Criteria & Frequency (Project Specific) - Normal: Max Lot Size : 4000m2, Reduced: Max Lot Size : 2000m2
422b5b4c-31c8-500b-bbac-95e2429cbe19 | note | Check Item - Lot Records
14d164bb-198e-5651-ae2a-ce3eb9db39a9 | note | Reference - MRTS04 App A
7d760127-2727-5729-a10d-9d94d804b705 | checkpoint | Reporting Pavment Design Requirements. For Contracts where the Principal has supplied the pavement design (that is, Construct Only or similar Contracts), the Contractor shall submit the following information to the Administrator for each existing Subgrade Lot:
d2360bb9-3678-5c9a-9464-03e9b7ea768a | note | a) test pit logs
e55cd5ad-b4d6-5123-a202-93c6c77a64e8 | note | b) all test results for each layer encountered within the test pit, including certified test certificates, and
f56f0e52-7966-59cc-84f3-a2a4248800f3 | note | c) marked-up drawings accurately showing all test locations within the Lot.
e69ecf01-b0cb-594f-981c-5aaa4b94b082 | note | ○ The Contractor shall allow a minimum period of 14 days for the Administrator to review the information prior to any Subgrade treatment and the placement of any overlying materials.
ebd53548-3c2b-5c63-b4db-c08c4e55f225 | note | Acceptance Criteria & Frequency (Project Specific) - Submission to Administrator
445bbf5b-1286-548d-8fe9-e09675d85e04 | note | Check Item - Hold Point 16
29801dbf-8211-5865-ac1f-baf33ef793f4 | note | Reference - MRTS04 App B.6.2
ce17b9f3-003f-5564-86eb-29f0b26351e1 | signoff | HOLD POINT
a678722e-ebaf-5674-9ab7-a7d518ffb72b | checkpoint | Bottom of Excavation for Cuttings: Where subgrade is reached in cutting works shall cease until subgrade treatment type has been directed by the Administrator in accordance with Clause 13.3.2.1
b118d746-f593-5e1f-9160-3745953b306c | textbox | Subgrade Treatment Type Directed:
4395bc51-4ea8-52e8-8b9a-cf26217f78a2 | note | Acceptance Criteria & Frequency (Project Specific) - As directed by Administrator
55f72396-0228-5bba-acae-22376be81086 | note | Check Item - Hold Point 8
ff06dadf-d4ec-5e3e-af70-346e79a558fc | note | Reference - MRTS04 Cl13.3.2.1, Cl 18.3.3
b0ed5269-baa2-5959-ba78-3083520a6507 | signoff | HOLD POINT
34dca0b7-3285-53ac-9de1-406075fe1c75 | checkpoint | Subgrade Treatment Type A: As ordered by the Administrator at subgrade level on all section. The material below Subgrade Level shall be to compacted a density of not less than that stated in Table 15.3(b) and to a depth of 150 mm.
e6448733-1325-507e-81b1-2672193df49b | note | Acceptance Criteria & Frequency (Project Specific) - Treatment Depth - 150mm
7461662d-e865-5358-a8b0-bdacab04bc8a | note | ○ Compaction Standard: min 97%
fd272ae4-3fa0-5f81-af60-30aed0afb22e | note | ○ Normal: 1 per 500m2, 4 per lot
685f50d9-df4b-5147-b307-53952116695c | note | ○ Reduced: 1 per 1000m2, 1 per lot
b1236ae1-10f5-56bd-8a90-23f623dc5130 | note | Check Item - Test Reports
1afb31f0-79ea-5036-acb1-71313df93b86 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
a4c1f4f0-6a34-5e09-bea9-6654b23f7508 | checkpoint | Subgrade Treatment Type B: As ordered by the Administrator at subgrade level on all section. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and to various depths, as directed by Administrator, typically between 150mm and 250mm.
566b8718-3161-59ac-9e8f-d3eec40eff92 | note | Acceptance Criteria & Frequency (Project Specific) - Treatment Depth - 150mm-250mm
1288e834-ccd6-5843-ba1a-4e9b79b487c4 | note | ○ Compaction Standard: min 97%
36271fc6-c104-5695-b9d9-2b0f1c84b88b | note | ○ Normal: 1 per 500m2, 4 per lot
2ca3390c-49b0-57b4-b445-3ec31c5d2104 | note | ○ Reduced: 1 per 1000m2, 1 per lot
0927695d-181c-56af-86b9-1fd56d0e4866 | note | Check Item - Test Reports
f868501a-ddb1-54ea-a1d9-3df2119bc697 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
e7522222-ba77-5b05-988e-c36386e01cb9 | checkpoint | Subgrade Embankment: Material to be compacted to requirements not less than that specified in Table 15.3(b) Subgrade relative density tested to Q140A
d8cdaf42-7248-5f19-932a-6254e650a16a | textbox | Material Source Stockpile Lot Ref:
bd0936c5-d2a6-548a-960a-d80a00b48dda | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level -
0f3d13b5-d72f-540b-a0ca-446b37ab35b5 | note | ○ Embankment Fill at subgrade: Class A1, B, Unbound Granular or stabilised material : min 97%
7a075b83-0d73-54f8-a135-adca5d9e98f9 | note | ○ Normal: 1 per 500m2, 4 per lot
ef0016a4-18a1-5ef8-9540-d5aee96f7d18 | note | ○ Reduced: 1 per 1000m2, 4 per lot
d65d3f08-a112-5d89-9d28-c78f3efab6d0 | note | Check Item - Test Reports
ca1c9050-3052-52f1-a621-fcd4827179f4 | note | Reference - MRTS04 Cl15.3(b) App A
00b385ed-e46e-55ff-ba39-a416c4622b5f | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
854cf68b-c022-5801-b689-bbe2e5273fc4 | note | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
78e3c937-47d1-5c89-a214-2003fe61df78 | note | – 10,000L water tanker with 600kPa tyre pressure.
728b6a58-e079-56c1-a71a-62c174ae30fe | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection, Continuous
032a6a45-b0db-5f32-af15-2a9e1335be67 | note | Check Item - Witness Point 8
9b690867-5cc3-5921-8c79-e9083424a158 | note | Reference - MRTS04 Cl18.3.2 Q723
887e0219-4f57-5f77-bbf1-061eb304e56e | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
7ea3dcea-218f-5815-80b8-14164c01a77e | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
c8771178-36fd-5f47-b1ed-a431f72172b1 | note | Check Item - Dip Sheet Records
df7a8c8d-7ca5-5bb2-97d0-4e2178a58845 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
261fbb24-c85e-5baf-81be-6bc38f2cd67b | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
0408f61b-2988-5de9-aed6-c9d1d7bcb21c | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
52eaad5a-e051-5097-918c-f5a6ce0165c7 | note | Check Item - Dip Sheet Records
c5c9be75-5fff-590f-a26d-c61e6088e2e3 | note | Reference - MRTS04 Cl. 6.3.2
02dc668f-dba0-5af8-a649-dae31f370fed | checkpoint | Subgrade shall not pond water and be free draining.
52492274-7305-58b6-ad37-eee6f7f0e83d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6b2490c5-91ec-50bd-b25b-30f87fab9792 | note | Check Item - Check Item
b4e58804-0b11-538d-93f1-e9fc12560b77 | note | Reference - MRTS04 Clause 6.3.2
d3ada7cc-0de6-5720-9dd2-104c39c6091e | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
4ad349aa-1478-5bea-94e7-580c3b40e1bd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
13ea3317-8881-52f4-bd4f-ed6f12ece93a | note | Check Item - Hold Point 12
3fbbe3f1-0fff-59af-989e-52982fdc5df6 | note | Reference - MRTS04 Cl. 18.3.1
43ba09e7-cac0-5469-8ec1-25a7d2ee4ddc | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
2c53bc98-9277-52c4-8ad0-b53589e23a42 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
13fa6715-b544-5f8e-8107-f1e493797965 | textbox | Print Name:
5cf93efc-1927-5e16-8ac6-15fd118d7f64 | date | Date:
e0a21632-1b51-5488-abff-5640367583b7 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
b3537807-4ede-5e1b-81dd-2c07cd2eb0ff | textbox | Print Name:
8c094eaa-0617-5b4f-bc3b-57a49aafb298 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
e84c32f1-bcc8-5de1-90bd-315e8ad140bd | checklist | 04.182 - Subgrade Treatment Type A | itp | 04.182 - Subgrade Treatment Type A
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
6aff2c5f-7614-59a2-9f3f-599a713936c0 | checkpoint | Define Lot
00f1eab3-5056-55e0-a625-eac45e35184d | note | Acceptance Criteria & Frequency (Project Specific) - single layer produced in a continuous operation in one day
8db0636d-9064-5cec-9525-6f59b809139d | note | Check Item - Lot Records
a434e9a0-64e7-5b3e-91b1-3cd3e1943ca1 | note | Reference - MRTS04 App A
2fb0c5f2-9e4e-57fd-b846-94975e1c4929 | checkpoint | Trim and compact existing: Subgrade Density requirements Q140A -Material to be compacted to a density of not less than that stated in Table 15.3(b)
09516035-863c-5f09-b2ea-1b001ded49b9 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level - Existing material in cuttings: min 97%
6f0401ac-f5e8-5a35-a0f2-cf9c36f2a828 | note | ○ Normal: 1 per 500m2, 1 per lot
bfc12fe7-7816-508e-a9fd-249c743786ba | note | ○ Reduced: 1 per 1000m2, 1 per lot
ccb7b081-417d-526f-8803-e98daff0c444 | note | Check Item - Test Reports
55f96158-9596-50bc-96da-893eb7e702b2 | note | Reference - MRTS04 Cl15.3(b) App A
00b385ed-e46e-55ff-ba39-a416c4622b5f | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
3147329d-bf46-56eb-8c74-8cd9862bfecb | note | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
a956c2aa-ccce-5b47-927a-beec6108866a | note | – 10,000L water tanker with 600kPa tyre pressure.
5a02fd24-d867-598b-8015-893cb02e8632 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Delfection, Continuous
110e4012-5c2d-54fd-845c-6aaeeb5149f2 | note | Check Item - Witness Point 5
7c762976-2fd9-59a8-96e0-530a67e7df63 | note | Reference - MRTS04 Cl18.3.2 RMS T198
887e0219-4f57-5f77-bbf1-061eb304e56e | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
da171bcf-c916-57ad-8c35-2ec25b7874c6 | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
48e4bb04-a588-52a7-b1fc-86516778081b | note | Check Item - Dip Sheet Records
690f6c5c-53d6-5f76-9d0a-5372ac9e2263 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
261fbb24-c85e-5baf-81be-6bc38f2cd67b | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
c9fe1f19-7095-5811-ba41-ea756ddd5f25 | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
73b3ff9a-acf3-528b-9b23-6c565fd24ff5 | note | Check Item - Dip Sheet Records
fa1a5082-a037-5b51-b2b7-027f731a4efb | note | Reference - MRTS04 Cl. 6.3.2
02dc668f-dba0-5af8-a649-dae31f370fed | checkpoint | Subgrade shall not pond water and be free draining.
0c6d3daf-4426-5b75-906f-e922063d2f86 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f8ae42c8-ea2b-5589-a6b7-8955bb3f557d | note | Check Item - Check Item
56b5e4b1-e63d-56ef-91dd-48980a55f229 | note | Reference - MRTS04 Clause 6.3.2
d3ada7cc-0de6-5720-9dd2-104c39c6091e | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
49649345-0448-58be-9b71-1aaab3689666 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4b83916d-4827-52ff-a703-b58da95fdd1c | note | Check Item - Hold Point 10
8fdef356-4366-525e-8e42-67a7234313ed | note | Reference - MRTS04 Cl. 18.3.1
43ba09e7-cac0-5469-8ec1-25a7d2ee4ddc | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
4ccb5947-37f6-5c67-ae56-45ec3d4592ae | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
da330a9a-b453-5faa-ad04-94063f1f2c86 | textbox | Print Name:
872c61b6-eb15-50d2-85a9-13fc84d193fd | date | Date:
919fede0-6a80-525a-a5a7-5c4870d17e97 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
916af632-6787-5a36-b8cf-925579c178b6 | textbox | Print Name:
07ef1817-81b8-516d-9d8c-6f02b6cd745a | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
6f89e164-d68d-5f61-a413-f4219103f85e | checklist | 04.183 - Subgrade Treatment Type C | itp | 04.183 - Subgrade Treatment Type C
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
6aff2c5f-7614-59a2-9f3f-599a713936c0 | checkpoint | Define Lot
832a5f77-8a8f-5028-a67d-11ee0b044893 | note | Acceptance Criteria & Frequency (Project Specific) - single layer produced in a continuous operation in one day
6f8b75cd-83fc-5d24-8913-31dc23281e3c | note | Check Item - Lot Records
77352f98-1768-5868-b5e7-02ec3000cee3 | note | Reference - MRTS04 App A
71be5531-b345-516f-8d37-d4a4ddb0a5bc | checkpoint | Unbound Granular Material incorporated into unbound treatment shall be as specified in MRTS04.1 Cl. 12.1 and meet the material requirements specified in MRTS05 Cl. 7.
78fb1403-54cc-5006-8eab-5dff7ee2c3f9 | textbox | Material Type:
11b6f756-bbe0-5688-8cd7-da9479f82993 | textbox | Material Source Stockpile Lot Ref:
9474c463-91da-512b-a63c-0d2a7a5ba8e0 | note | Acceptance Criteria & Frequency (Project Specific) - Unbound Granular Material Stockpile Lot
b4fd1b03-97ac-558f-a361-8c41da0762a0 | note | Check Item - Check Item
61107783-41a5-5cd6-be8e-02d7e3bb467b | note | Reference - MRTS04.1 Cl 12.1, MRTS05 Cl 7
14843373-7a6f-564a-aa39-7dc09b590064 | checkpoint | Subgrade Density requirements - Material to be compacted to a density of not less than that stated in Table 15.3(b)
82c86262-16f0-5f93-8f35-54116a3a22ef | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level - Existing material in cuttings: min 97%
f2ad5511-8c38-53a6-aec9-f9007afd81fb | note | ○ Normal: 1 per 500m2, 1 per lot
9d0582d7-c156-5076-a1a7-631e00bbc12b | note | ○ Reduced: 1 per 1000m2, 1 per lot
a17eef9a-3669-5926-921a-ef3c5706b292 | note | Check Item - Test Reports
e9e4157f-5288-5fad-a936-ba69130e3a66 | note | Reference - MRTS04 Cl15.3(b) App A
00b385ed-e46e-55ff-ba39-a416c4622b5f | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
02ff6e09-57c6-5060-8522-009482cc646e | note | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
6d37ba5a-c00d-557d-86ac-2286090fdc1c | note | –10,000L water tanker with 600kPa tyre pressure.
e54a3705-97b1-5f90-ae68-d3e0bd3d534f | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Delfection, Continuous
23c516e8-feeb-5efe-846a-b7dfb2e6f66b | note | Check Item - Witness Point 5
ca2f18d9-5661-5bf2-ace0-600475fb4ab5 | note | Reference - MRTS04 Cl18.3.2 RMS T198
887e0219-4f57-5f77-bbf1-061eb304e56e | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
255a9626-352e-5b3a-af45-b56989e52750 | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
96627556-1cc6-53dc-9d4e-034cdf494c53 | note | Check Item - Dip Sheet Records
d4476e18-71a6-5d02-935d-6bbab7848269 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
261fbb24-c85e-5baf-81be-6bc38f2cd67b | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
829f6007-cc8b-5824-9faa-0feef5e500cd | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
fe7ae3ca-22ca-5b0f-baae-b533c0802dd4 | note | Check Item - Dip Sheet Records
10aca999-5471-5e3e-88b8-56a9e32a99d9 | note | Reference - MRTS04 Cl. 6.3.2
02dc668f-dba0-5af8-a649-dae31f370fed | checkpoint | Subgrade shall not pond water and be free draining.
3db099b2-d328-583c-ae94-4e197f5a033b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e6eb7604-f7fd-5554-a954-d62511e37443 | note | Check Item - Check Item
40c5fe69-e201-59d8-b451-8f81eb16424d | note | Reference - MRTS04 Clause 6.3.2
d3ada7cc-0de6-5720-9dd2-104c39c6091e | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
b842565a-bb69-50ab-ba80-31da5312eff1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6d4e5efc-c791-586c-a261-5df4b9ce2dd5 | note | Check Item - Hold Point 10
f2f72459-31b8-56f1-b7a3-f31731929fa6 | note | Reference - MRTS04 Cl. 18.3.3.1
43ba09e7-cac0-5469-8ec1-25a7d2ee4ddc | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
0f9fb16c-2a30-5522-bcee-9fefd5ce98c7 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
6d791d38-25b9-5eda-941c-87b94b524d99 | textbox | Print Name:
74562d74-c03f-56ee-9ad2-0c1d0156743e | date | Date:
23408c6f-c250-5fe1-a305-876da88a0691 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
7a3391e6-9d84-56f4-8176-3f4a7711f94a | textbox | Print Name:
26b9a81e-ff99-5cb9-a307-b536784872f0 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
606332e2-ca1c-5a83-80a1-8cdcb874c683 | checklist | 05.01 - Unbound Pavement | itp | 05.01 - Unbound Pavement
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
f9e5a07e-5ed6-5330-b1ea-5f77eb95374d | checkpoint | Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
58844c8d-5b4a-54e8-8bc5-660914d07e57 | note | Acceptance Criteria & Frequency (Project Specific) - Supply of unbound pavement materials - 5000tn
18ef4913-9bd4-537c-9052-ef0b96ff348c | note | ○ Maximum lot size - A continuous single layer constructed in 1 day's production
c81fd578-e4d5-521e-b90e-f6254e41b13a | note | ○ Road rouhness testing: maximum lot size 100m
842e4cc9-60bc-5fc8-aff0-a2ddd712056d | note | Check Item - Check Item
0ff3c1ee-3b32-5e44-b17e-d26a62fdf1b9 | note | Reference - MRTS05 App. A Table A1
4d4c21ca-ff99-5aef-9d93-aa1b07f35d1a | checkpoint | Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
7510d645-84c7-5cbf-bffc-a58c9fc179fc | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Registration Certificate per quarry
aaeec6f2-387f-58b3-aaef-6506b0fb941f | note | Check Item - Milestone
fff9d5d9-e59e-5bc2-bbe0-c8811185cab8 | note | Reference - MRTS05 Cl.6.2
95fd4259-97aa-528c-bdc0-12d10411d7d3 | checkpoint | No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator.
6825e62a-c07a-58a0-8967-92f66ab0ac0b | note | Acceptance Criteria & Frequency (Project Specific) - Approval of procedure by from the Administrator
ea7ffb1c-753f-5ea6-b2a3-9fe226e66e40 | note | Check Item - Hold Point 1
09445996-9691-5355-b10c-0f522fe0ebdc | note | Reference - MRTS05 Cl 5.2.1
29a2626b-572a-523e-a5e5-d4c3354446e8 | signoff | HOLD POINT
8a91a2ab-bb29-5b61-b87f-2e7261936418 | checkpoint | The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the works.
1dc35860-b1bd-5f05-bfe4-efc86bbaf4b3 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of production procedure
b8080a50-8301-5921-a624-0db199923cfb | note | Check Item - Milestone
31d7773f-54f5-5ae2-b728-628d8bc8d497 | note | Reference - MRTS05 CL 5.2.2
ddf8ce49-c9ad-5696-8d01-bc4fab631aca | checkpoint | Submission of Construction Procedure for unbound pavement construction at least 14 days prior to commencement of works.
33fa169e-848c-5660-95c3-23d5eb261627 | note | Acceptance Criteria & Frequency (Project Specific) - Approval of procedure by from the Administrator
dc799e61-86f7-522a-8d39-554551a442ca | note | Check Item - Milestone
9e7fe602-6274-5eb0-a28a-d1184fd5dbc2 | note | Reference - MRTS05 Cl 5.2.3
ada6ef21-c116-534e-8c8a-d5de5b59ba99 | checkpoint | The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works.
5d013073-5793-5814-bfeb-70bb50e0c712 | note | Acceptance Criteria & Frequency (Project Specific) - Written Permission from Administrator
c8704bc3-fea3-5642-ad55-0e5a122120cb | note | Check Item - Hold Point 2
387299fc-c46e-5ccf-830c-eb44649c0161 | note | Reference - MRTS05 Cl.6.1
3cbf7e77-b8a4-5b3c-a2c5-2a9305a966d4 | signoff | HOLD POINT
afaf8c67-b8c8-511e-a75c-5249df7a605b | checkpoint | Layer Thickness between 75mm and 250mm for all subtypes excluding Type 1 (HSG).
a80dd513-28e2-50b8-a38a-5c87a5cc9d96 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Layer Thickness: 75mm - 250mm
2a68cee1-13c7-5795-a8c0-b98a83bcdb69 | note | Check Item - Check Item
674f0160-cd36-580c-9c65-7c393f59b9f6 | note | Reference - MRTS05 Table 8.3.3
52f3e944-8c7b-54fd-9081-36f46c534e1c | checkpoint | Minimum value of Relative Dry Density Requirements C.V of RDD = 100% MDD for Base course 2.1, 2.2, = 100% SDD for other than base course 2.1, 2.2 and 100% SSD for all layers of 2.3, 2.4 and 2.5.
ef81bed2-6163-5bab-815e-ac46e50bb8fd | note | Acceptance Criteria & Frequency (Project Specific) - C.V of RDD >= 100% MDD
a41ade15-261e-5c38-811f-a9142521c4ba | note | ○ Normal: 1 test / 500m2, 4 per lot,
5908d532-fe78-5aad-be1a-7fc292798ef2 | note | ○ Reduced: 1 test / 1000m2, 4 per lot
0db92b5e-58ba-5e10-a16f-1ac51f15321f | note | Check Item - Check Item
39984138-eedc-5a27-b7c1-ec3388d77467 | note | Reference - MRTS05 Table 8.4.3
cc9392de-f638-55b4-97e1-38a2a67cbdd4 | checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
527655be-0cee-5cd7-a0f0-7c4ccb071ace | note | Acceptance Criteria & Frequency (Project Specific) - All tests as described by this ITP and MRTS05
7893dc5e-5b37-52c5-b911-145de047d4db | note | Check Item - Hold Point 3
dce0f193-4b91-5c10-8acc-bbbb6fc80498 | note | Reference - MRTS05 Cl. 8.2
5bf60ad0-5bbb-54ee-944b-297e93ea6adb | signoff | HOLD POINT
8e73d789-d631-5e54-b16a-730ff3af6d52 | checkpoint | Moisture content such that the degree of saturation is less than 70%(modified).
f9cfedd3-3474-5c01-90fe-c8d08ca3ab5b | note | Acceptance Criteria & Frequency (Project Specific) - S < 70%
a25532f1-42f8-5d70-9f86-e1436af322c0 | note | ○ Normal: 1 test / 500m2, 4 per lot,
35d8581f-15d1-50d5-9e55-1f137c40c0eb | note | ○ Reduced: 1 test / 1000m2, 4 per lot
c6286b15-7c37-5339-a76b-1ba31ed631ca | note | Check Item - Hold Point 4
bdf9e4f4-ee80-5a8d-855a-7660951fb733 | note | Reference - MRTS05 Table 8.3.4.1
37b91539-a5ba-5638-98e8-489fed8ce77b | signoff | HOLD POINT
c9fec842-0400-5ca9-8447-3e881a725912 | checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
04c84779-626b-5812-a7a8-c5ababd87f63 | note | Acceptance Criteria & Frequency (Project Specific) - Min 1 per lot. Additional tests as directed by the Administrator.
8702de0d-f322-5df2-96c7-bcb4bfba1d38 | note | Check Item - Check Item
3f7cff0a-5300-568f-94cf-b05061b0df18 | note | Reference - MRTS05 Table A3
6af9b6b7-435f-5d39-afb8-ffeb4c22c40d | checkpoint | Geometric Tolerances in accordance with MRTS05 Cl.8.4.4.3
7e154357-fc33-50d2-a78a-8e433f99bde0 | note | Acceptance Criteria & Frequency (Project Specific) - ±10mm when covered by AC ±15 mm in all other cases (1 test / 20m)
15f2cf08-137d-50da-98fb-b9acf2cb2eff | note | Check Item - Check Item
f4b60e39-38dd-5b2a-9d1d-91510a23461a | note | Reference - MRTS05.1 Cl.8.4.4.3
046fe6c7-48dd-57ac-885f-31526bc9f63d | checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
7ef4b783-9f97-5e97-90b0-8f3a011c5e5f | note | Acceptance Criteria & Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
b1e67627-afc2-54dc-a424-c90044de7a90 | note | Check Item - Check Item
d02d27c8-479a-50af-b086-dd231c7e1803 | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
db5661fd-841f-5502-80ed-8c667462a234 | checkpoint | Deviation from a 3m straight edge shall be less than 5mm for material types 1,2,3 and 4
ba20ef6d-95fb-5dad-9017-af9371c9bd43 | note | Acceptance Criteria & Frequency (Project Specific) - Straight Edge Test, Less than 5mm, 1 test per 20m
5b2b159b-a994-5ce2-be30-345e2287ba1f | note | Check Item - Check Item
c3747545-25da-5960-816b-e6762aa4840a | note | Reference - MRTS05 Cl. 8.4.5
2a81372e-ef89-5476-8df2-01953b4a7baa | checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
8dd0f88f-0ed0-59eb-a588-99865149a3b6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Continuous testing
b04b4841-ac72-5cef-aacd-ecaa87a7762e | note | Check Item - Witness Point 2
288fc7a2-8341-5881-afba-cfe4003f0c2c | note | Reference - MRTS05 Cl.9.4.7
0bf18402-dceb-5624-b6b5-af2390df6fc9 | checkpoint | Additional Geometrics (final layer only). The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
a977ef75-6b60-5252-953a-2d0e201583fc | note | Acceptance Criteria & Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
c70ec1de-e556-586e-a5dd-dd53c51f565d | note | Check Item - Check Item
144a5e2d-27e1-5a63-8c70-c794028d2f00 | note | Reference - MRTS05 Cl.8.4.4.4
88e664d6-c734-5473-a2af-215621622509 | checkpoint | The contractor shall provide a methodology and calculations to determine the road roughness to the administrator for acceptance. Roughness shall be less than 2.31m/km.
b50b53a4-c238-575f-b8f1-3a8d55a731a7 | note | Acceptance Criteria & Frequency (Project Specific) - Less than 2.31m/km, 1 test per 500m
f197b6b3-c628-5db1-8793-2a9d6b0c997b | note | Check Item - Check Item
e874c86d-9d1e-5762-a1e2-f8083df768bf | note | Reference - MRTS05 Cl.8.4.6
4ee88c3d-f61c-5603-94b5-49c245e81093 | checkpoint | The finished surface of any unbound pavement layer shall:
0f9915bf-d735-5c44-b0be-a3f2147e5382 | note | – be hard and homogenous in appearance
2a768602-c876-504c-acd4-2030b7c38e5d | note | – not have any loose, segregated or contaminated areas
fc866333-f2f1-5a11-9bd7-c5a9aff437a1 | note | – have the coarse particles slightly exposed
5815516d-7dff-5e69-baaf-27ca6f44d00a | note | – not be affected by delamination
5da1ddf8-6a8a-5e05-abd0-cd6c4cbcde88 | note | – not show signs of water pumping, and
cc7df405-eb06-53d3-97d4-3c353c44724e | note | – not visibly deflect under load when proof rolled in accordance with Cl 9.4.7
61cf3596-6ab0-5b58-a307-7bc052d78d66 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
391861e9-f873-5ee0-92de-7656bbe44e03 | note | Check Item - Check Item
6a3337e1-7ea9-5af1-9e4d-76a06548c463 | note | Reference - MRTS05 Cl.8.3.5.1
511b7961-3e3d-5830-a085-4859b184b531 | checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
64fccaa2-e93d-58d2-b1f8-bb374fef4069 | note | Acceptance Criteria & Frequency (Project Specific) - Test Results per lot
d029b62a-22c5-599a-a42a-93ef4d614c1d | note | Check Item - Hold Point 5
b63c80be-3bda-58a3-a34c-575b029606cb | note | Reference - MRTS05 Cl.9.1
3fdc4145-60a4-5b07-b0fd-15c2459266d7 | signoff | HOLD POINT
e38bf971-aa6f-53c3-bd4f-00934837f082 | checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
b1525ef4-7e96-523a-a742-f54c6625a07d | note | a) all testing has been completed
fd73cd89-40b7-5b51-9986-3f7e54ab3940 | note | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
35fdb329-e223-5034-a991-2cac22fb2064 | note | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
0a4f8cd7-3b22-53b9-9e21-5a096f3659cb | note | d) the layer has been presented to the Administrator for inspection, and
61cf2f35-9a32-5240-a5ad-5c22514f7cf7 | note | e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
16005952-3482-5b44-8bf7-8cb0fd91f05b | note | Acceptance Criteria & Frequency (Project Specific) - Adminstrator Acceptance
c02c28b2-0305-5e09-8a73-e3afdc7a6385 | note | Check Item - Hold Point 6
7e980f9a-ab5f-54e1-874d-91b2c9548225 | note | Reference - MRTS05 Cl.9.5.1
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
631f1e64-5164-5cf6-b014-a6072cc74731 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
932db828-63fe-5265-8fb1-7f7f7f0a8329 | textbox | Print Name:
9c8a5078-12dc-5436-96a1-f232a20f714c | date | Date:
bf33deb8-3b12-5a8a-9968-446092de3eb4 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
b354cac1-e16b-585b-8f6d-197553af95aa | textbox | Print Name:
a9b14b32-3800-52e9-a6f9-21fa0ad307d0 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
67a5bddd-c246-5fde-9820-7b6aab55e180 | checklist | 10.01 - Plant Mixed Lightly Bound Pavements | itp | 10.01 - Plant Mixed Lightly Bound Pavements
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
243140dc-76f7-5961-9205-cdb0fce3a8fa | checkpoint | Construction Procedure
4b4ec2d3-c44f-57f3-a979-c9aacc74546d | note | ○ Documented procedure shall be prepared for all construction processes as defined in Clause 6 of MRTS50 and shall be submitted for approval at least 14 days prior to commencement of lightly bound pavement works (No work shall commence until accepted by the Administrator)
2f700929-d45d-5730-a114-535c32eb2f8c | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
6d88a7b2-0c4f-557b-8f30-dedf9aa7e2da | note | Check Item - Hold Point 1, Milestone
8d66f932-ce0c-51fb-b124-8fc1497d201c | note | Reference - Clause 5.2 MRTS10
6dac35f8-56fa-5881-a970-d3b9b186dcf7 | signoff | HOLD POINT
bc49bc48-2c20-50a8-89ce-4f9f4f8fafda | checkpoint | Material Requirements - Unbound Pavement Material
3a03f5ca-efda-598f-b43a-c1b2432a9b95 | note | ○ The Contractor shall not incorporate unbound pavement material into the works unless it has been demonstrated that the unbound pavement material lot conforms fully to the requirements of MRTS10. All conformance results shall be no more than six months old.
a2357c78-c4cd-5fa0-b567-c8a71e75ae4d | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
8602a0c9-19e4-5f78-9228-a3205053bf4b | note | Check Item - Hold Point 2
35de7388-4ddb-5f34-8476-2ae0942b1a30 | note | Reference - MRTS10 Clause 6.1.1
a3e7b37d-acd0-5bd9-9e26-64b49423c1a9 | signoff | HOLD POINT
25b7cfbd-b61f-5a9d-99de-6ff61d84939d | checkpoint | Mix Design Report
b12eb130-970a-5252-a956-4bc7e1d9cb4e | note | ○ A mix design must be submitted at least 14days before mixing operations commence. Construction of the lightly bound pavement layer shall not proceed until a conforming mix design (refer to Clause 7.2) has been deemed suitable and accepted by the Administrator.
c7a7cbe9-ece6-5984-a981-309965c5421d | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
c2c1d236-7e59-580b-9432-adf691ad29de | note | Check Item - Hold Point 3
d9757575-d960-540c-85c2-fdcca401667b | note | Reference - MRTS10 Clause 7.1
ed7486f1-e465-5f8a-93af-ee19363fbaec | signoff | HOLD POINT
d696ff76-9950-520d-a3bc-37efc8b22e56 | checkpoint | Moisture Content
25284aeb-e2a2-5415-8ffb-9703cba525a3 | note | ○ The Contractor shall nominate upper and lower moisture content limits as part of their Mix Design that will ensure:
c889df71-6ed8-56a4-9673-857e34cb7e55 | note | a) there is adequate moisture to achieve the specified compaction standard
6d0f01f7-1352-5bfb-bd6b-13c29396cc61 | note | b) the constructed lightly bound pavement layer is trafficked in accordance with requirements of Clause 8.2.11, and
2e9af4e3-ab5f-524e-bbc8-2012f068820c | note | c) the lightly bound pavement material does not exceed the optimum moisture content (OMC), determined in accordance with Test Method Q142A.
cdc860b7-c520-5c00-9d3d-46f3a57f3c34 | note | Acceptance Criteria & Frequency (Project Specific) - Testing - AS1289.2.1.1, 1 per 500m2, 4 per lot
c5e01a74-4809-5193-897f-1e0dd3a43df1 | note | Check Item - Test Report
3f887f4d-1503-58d3-94d8-b8c7899a3fef | note | Reference - MRTS10 Clause 8.2.5, Clause 9.4.8 Table A3
b11f1e9b-ede8-594a-8098-d0de12864985 | checkpoint | Construction - Trial Pavement
fdcdb6fe-fa4e-5c2f-b44f-9e17df1e4e5c | note | ○ Unless otherwise agreed by the Administator, a trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
06b6f855-f8a1-5327-841e-347c5b6b2483 | note | ○ The trial pavement shall be located within the site and be not less than 1000m2. It shall determine the characteristics highlighted in Clause 8.1 MRTS10. The trial may be incorporated into the permanent works at the Administrators discression.
62282f85-66a0-5a5b-aa28-954d8eb1d00a | note | ○ The Contractor is to undertake the material and construction compliance testing nominated in Clause 8.1 and the finished pavement complies with the technical specification of MRTS10. If deemed not conforming, further trialing shall be undertaken.
ac89084a-6b58-529b-9194-1f62e0a10318 | note | Acceptance Criteria & Frequency (Project Specific) - Visual & Check
8d301c89-718e-5c28-a735-cd74d31ad34d | note | Check Item - Witness Point 1 /Hold Point 4
d3befdd3-1134-5f78-91f9-f0eedacac6c3 | note | Reference - MRTS10 Clause 8.1
3b295591-2821-5562-b0cb-1b5aaeb4d9c0 | signoff | HOLD POINT
1cfc3111-1a9d-5d0d-b33f-99e2ac3bc23f | checkpoint | Material Compliance Testing
d2e7feba-deb1-5545-971f-d5a3554c5d57 | note | ○ Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
daf5895c-776a-53db-91f1-75845262fc9c | textbox | Material Type:
46fccaee-d1e6-5c8a-9aac-c2945d9513f1 | textbox | Material Stockpile Lot Ref:
c80bd8c5-4847-5bf6-87cf-cd7de9c3a595 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS05 Cl. 7, Table A1, MRTS10 Cl.6, Table A2
c9f41c07-4206-5dca-b3af-8905dcfcd038 | note | Check Item - Check Item
2ea8b70f-733f-5b9f-b9e8-d5b421ede4a7 | note | Reference - MRTS05 Clause 7
56377b54-fde7-5406-837c-3890686afe74 | checkpoint | Equipment
ca99a0de-52a8-517c-b6f5-eb8b5b743725 | note | ○ Equipment as specified in approved construction procedure
7788f511-ca01-5f2b-bfa2-bc55d8d0250c | note | Acceptance Criteria & Frequency (Project Specific) - Construction Procedure Approval
911d87b5-b1e5-584c-98bf-8ba17564d7de | note | Check Item - Contract Notice
e0139a31-d133-5e0b-82db-d216d79f4fb8 | note | Reference - MRTS10 Cl.8.2.1.4
1d851571-a928-5a25-b90f-6dc4951d0941 | checkpoint | Weather Conditions
8c3eb78c-cf9d-5b7a-84d3-9e06740ee011 | note | ○ CMB material shall not proceed when:
28f9e562-cd7a-560a-af88-bdc567b294d3 | note | a) air temperature is less than 10°C or greater than 40°C
4fe12a30-2e88-5f3a-9f5a-26782f7b3718 | note | b) during rain or when rain is likely to fall during placement
fc5ec0d3-1e87-5f5c-a44a-e8c23c7e49d1 | note | c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the CMB
2d533ba3-e131-5ffa-b28c-551f3855daef | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
61452252-3564-5349-8578-1084bbe26381 | note | Check Item - Check Item
eddb9e5c-6209-5b24-9ab6-23ad7b63d9ed | note | Reference - MRTS10 Clause 8.2.4
4e03ab1e-e68b-54c4-841d-13eb989c51d8 | checkpoint | Allowable Working Time
25443fc0-9420-5181-83c1-65a0bbe66983 | note | ○ Define as the maximum period between mixing the modifying binder into the unbound granular material and the completion of compaction.
abd907a8-1fd7-56f3-940f-a32de332ccd1 | note | ○ The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following
51dbbd4b-253e-588e-9e16-355a5a7a8c15 | note | a) Working time determined in accordance with Test Method Q136A
721e65be-38e3-5741-9138-f2d4fd2f81d9 | note | b) Four hours
3429c867-429b-54be-92c1-62b12cb11370 | note | Acceptance Criteria & Frequency (Project Specific) - Monitor
3c51e6ab-f007-5d89-8bcf-03afcb657b8b | note | Check Item - Check Item
8d57638f-a527-5fdc-87e3-8f9f321840bf | note | Reference - MRTS10 Clause 8.2.3
42fd55de-9d63-5d85-844a-49f359657c2f | checkpoint | Construction Joints
15aef852-d64e-53fa-a662-36f81f25d3a9 | note | ○ Deemed to be fresh when the material compacted on each side of the joint has been modified, placed and compacted within the allowable working time. In multi layer of lightly bound pavement, longitudinal joints of each layer shall be offset from the underlying layer by a minimum of 150mm.
d107e79c-c1b5-505f-b771-d58b993466e0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f59c5847-33ae-5c13-a9ea-00bbeb217b39 | note | Check Item - Check Item
c46f3098-ac31-57f3-b003-9ecdf9cc70f7 | note | Reference - MRTS10 Clause 8.2.10
09c077af-813c-5092-a8e3-c0018de0d0e2 | checkpoint | Fresh Joints
e67d1141-9cc6-5203-b7bb-87a10db44ecc | note | ○ Where fresh joint between adjoining or adjacent run is to be compacted, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
26c1fab6-c993-577c-8fdc-8c0f8d6b3298 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
166722e3-d852-5ce7-ab90-aef75dfef849 | note | Check Item - Check Item
1a44f8bb-16c5-5ea1-ac1d-e1510413caec | note | Reference - MRTS10 Cl. 8.2.10.1
fe775b8c-ae59-5b6c-9023-cee85f7e74d3 | checkpoint | Other (Cold) Joints
a55e0804-3cfc-5580-be16-0ea08c0a285f | note | ○ Joints that are not fresh shall be cut back to form a neat, clean vertical face.
408fb48f-6474-5d92-8e53-f97cf89b58d1 | note | ○ Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
37f79193-e8c4-5136-aa1d-de278704da39 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
12405f01-70b4-575e-bf1b-8532c7c41ae8 | note | Check Item - Check Item
07b0f1dd-7de2-5e98-8f3b-c4b68d51c3ce | note | Reference - MRTS10 Cl. 8.2.10.2 Cl.6.4
41055705-a004-5593-8172-bad48792c3a7 | checkpoint | Curing of CMB Layers
6fd77482-455f-552e-85a6-3b814827a04c | note | ○ The surface of an existing layer of lightly bound pavement shall be water cured until placement of the next layer and/or bituminous surfacing is applied. Unless approved, within 7 days of placement the lightly bound pavement shall be covered by a subsequent layer and/or bituminous treatment. Water curing shall be completed in accordance with Cl. 8.2.1.5
180b0d17-08ef-5ed7-b9f0-adbc81a3df67 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d44af67a-a3cc-5e36-a200-4fd148b95ced | note | Check Item - Check Item
94866467-792d-538c-b8f6-681b1d4a18db | note | Reference - MRTS10 Clause 8.2.9
1c825ecf-7382-5490-866d-b99a23800274 | checkpoint | Trafficking of CMB Layers during Construction
d81befe9-d628-53f2-8639-b66723356d77 | note | ○ Unless approved by the Administrator, lightly bound pavement layers shall not be opened to either construction traffic or general traffic until the lot has been tested for, and passes proof rolling (Cl 9.4.10)
21168a14-e415-56d3-a8f5-4804e07399ca | note | Acceptance Criteria & Frequency (Project Specific) - Check
c98b7623-b77b-56cf-9fca-fe83d208f373 | note | Check Item - Check Item
14a5dcd4-594b-5fb0-a982-07b7e7aa75cb | note | Reference - MRTS10 Clause 8.2.11
7fd44338-da44-5c5b-9f99-290fe3a4ff61 | checkpoint | Compaction Standard
8d60b723-1e22-50c4-8301-74ba0df4143c | note | ○ The characteristic value of relative compaction shall not be less than 100% standard, except for the upper most layer of lightly bound base which shall not be less than 102% standard
2d436cbe-1174-542a-a972-48cba44c6654 | note | Acceptance Criteria & Frequency (Project Specific) - 102% standard upper most layer
03d28018-81ba-5842-be6f-b97149fbef53 | note | ○ 100% standard lower layers
1660b746-1ca9-5449-9781-8b25d37d2332 | note | ○ (1/500m2, min 4/lot)
60ef7631-19ff-5c97-9168-aaeac0828f3f | note | ○ (1/1000m2, min 4/lot)
827ac221-bd7f-585e-af17-77f6647ed6a6 | note | Check Item - Test Report
7235a919-6f85-5455-8553-5a4e58d4e0a6 | note | Reference - MRTS10 Clause 8.3.4
ac9f11c6-86cb-54f1-bc10-08cb58380ce1 | checkpoint | UCS
ee36f699-ac57-5a6f-8059-12a4d7d021b2 | note | ○ Unconfined compressive strength between 1 - 2MPa
e4e91ca7-2975-56de-9e14-8c5944b9a3eb | note | Acceptance Criteria & Frequency (Project Specific) - UCS 1-2MPa (1 per lot)
444264d3-7193-5249-b7f3-6f643c242294 | note | Check Item - Check Item
add8098a-3cc0-5831-9dfa-d49152d5922e | note | Reference - MRTS10 Clause 9.4.9
ec616351-fefd-56b9-a41a-96f6f73ce7d7 | checkpoint | Stabilising Agent Content
14cc868f-bba2-52c6-b29b-a2db28d6b13f | note | ○ The actual content of stabilising agent for each lot shall be represented by both the:
ac682857-b8e0-5f67-ab1c-d45dc9602511 | note | a) minimum characteristic value of the actual content of stabilising agent, and
e69f96a4-8681-5a00-b6f7-b58a9aa7fc69 | note | b) maximum characteristic value of the actual content of stabilising agent.
c0cdfb5b-eb82-5656-bec1-52cd5d8f9dbc | note | ○ When UCS tests are being undertaken, the sample being used must also be tested for stabilising agent content.
6e7c14ce-88b4-53a0-934f-3cb6735f632c | note | Acceptance Criteria & Frequency (Project Specific) - Target content minus MPV, Min. test 1 per lot
4b84f01a-c741-5bec-bd6a-f482639fa883 | note | Check Item - Check Item
06110462-61a4-52a2-a00b-4a014bdc0fae | note | Reference - MRTS10 Clause 9.4.6
2f8e0836-4f19-5666-8540-e7e4a2288619 | checkpoint | Geometrics - Horizontal Tolerances
0187c15e-f8d7-58c7-98df-b0064edbcdc4 | note | ○ Shall not be more than ± 50mm except for the following:
6a9f9aa0-8298-5630-9063-6565e6774cc6 | note | a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm
ba68197f-7af6-54d2-9fd6-c1f07d25eee6 | note | b) Where alignment of the pavement with an existing structure is necessary, the new work shall be joined neatly to the existing in a smooth manner
36a2e849-0e69-52e0-842d-6506faf83f06 | note | Acceptance Criteria & Frequency (Project Specific) - -50mm/+250mm (1 per 20m)
b096310d-54ad-5cdd-90cd-0fa53e3a12d3 | note | Check Item - Survey Report
01da8e46-342d-57e8-b2fc-a633cbffc9d8 | note | Reference - MRTS10 Clause 8.3.5.2
ba73a75c-9cae-5363-b414-be622914880d | checkpoint | Geometrics - Primary Vertical Tolerances
da5e3b78-a239-549b-9419-eae776232f69 | note | ○ The vertical tolerances specified in Table 8.3.5.3 shall apply or:
06ca456e-0619-5f71-8058-cc22d588e63b | note | – the surface level measured at any point on the surface of any layer.
2a3403ab-2092-50f0-9bd0-a164bd023252 | note | – The average total thickness of the constructed course compared to the specified total thickness.
f1a8a279-8c6a-526a-8847-39558523e655 | note | Acceptance Criteria & Frequency (Project Specific) - ±15mm for layers that have been hard cut ±10mm for all other layers
4e22db10-147b-58b7-b9f3-49fea0bfd830 | note | ○ Layer thickness -20mm, +unspecified (1 per 20m at shoulders, lane lines & grade changes)
e8c95565-6133-57af-884a-03f40600ecd1 | note | Check Item - Survey Report
fd9c5302-4326-5448-98cc-ee397b3d3ca0 | note | Reference - MRTS10 Clause 8.3.5.3
8738e606-f651-5773-8edf-24a0dcc81fc9 | checkpoint | Geometrics - Deviation from a Straight - Edge
78f79cf4-ad21-532d-b22f-689ac4fecd2a | note | ○ Deviation of a straight edge place anywhere on the surface shall not exceed 5mm over 3m
6539ba4c-ea3c-5341-a10c-935fa9e89cf5 | note | Acceptance Criteria & Frequency (Project Specific) - 5mm over 3m (1 per 20m and at joints)
66e3b8da-b91f-50a9-aeba-c84ac7b0e589 | note | Check Item - Check Sheet
baa923d1-c787-55de-80d6-7accce0deb74 | note | Reference - MRTS10 Clause 8.3.6
f6dbef7e-9e7e-4f87-bc10-a7fdbc9ebd3c | checkpoint | Geometrics - Crossfall
aae18eda-e9da-5ebc-a006-43e2db8b032c | note | ○ Shall not differ from the designed crossfall by more than 0.5% absolute
9b31a421-40d3-51ef-b043-ed457b467cdc | note | Acceptance Criteria & Frequency (Project Specific) - Check
85b702ab-b5fd-5335-9cda-6da648857d45 | note | Check Item - Survey Report
7e54ccbc-cb58-5cd0-93cf-124cd6f56605 | note | Reference - MRTS10 Clause 8.3.5.4
58413aa0-fb89-4f8e-a1ed-26b3f2313a8d | checkpoint | Proof Rolling
5440b48d-cd23-5518-9c9e-1f65cfcbe23a | note | ○ The perceptible surface deformation test (Q723) shall be undertaken in the presence of the Administrator
7053fa6d-0d45-52f7-97cf-88cba2697907 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
67cc432f-89c0-59fa-a985-2d8d23c4ee7d | note | Check Item - Witness Point 2
04ce3180-97a7-56bd-a60c-af92b01d0a51 | note | Reference - MRTS10 Clause 9.4.10
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
c14ee595-1d14-532d-ad46-4ee7732db52a | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
66049e80-e655-5708-9b88-af9ec1851ac4 | textbox | Print Name:
72024633-bc93-5956-b3f5-2dd9f0685706 | date | Date:
ed94c1b7-8efb-5bfa-b05a-d0c710042e0a | note | Project Manager Verify that the Above has been Constructed according to Specification
7e7c2a49-b05f-51a5-a505-753c02b2659c | textbox | Print Name:
ee26d3ac-5770-5c3e-99fa-a77611531d50 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
691822fb-2360-4699-b395-4f015ffaefad | checklist | 11.01 - Sprayed Bituminous Treatments | itp | 11.01 - Sprayed Bituminous Treatments
2f1ed4af-bb5d-41db-ba19-cb44f547d1c1 | section | Details
ecd717eb-54d4-4802-b94d-255ce5e5094d | checkpoint | Document Submissions - As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
ead55b79-3589-55e4-a7e8-f826dae0d910 | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
02827e00-c62e-5c6b-8cfc-ee073c3f5773 | note | Check Item - Check Item
4cd95397-be77-4c6f-813a-9a5cd4ff70a1 | checkpoint | Traffic and Safety Controls - Traffic and safety controls are in place (eg. PPE, daily plant check)
6ff092e4-9053-58e2-9c4d-1c71964471f7 | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
e36db8f2-8d59-5f2e-9a46-d61fe23c23dd | note | Check Item - Check Item
191fa6af-abe8-48f3-b039-9013b9863a1e | checkpoint | Construction Procedures - The contractor shall documented procedures for all required processes in reference to Clause 5.2 MRTS11 to be submitted not less than 7days, these procedures and ITP shall not be implemented until permission has been granted
aa98d992-fe91-583a-bcb6-ef7566130342 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
b542df57-3e19-5173-8ae3-3d0986c632e1 | note | Check Item - MILESTONE/HOLD POINT
0780f4a8-2f24-5728-8f0f-2c48b3ae8a63 | note | Reference - Clause 5.2 MRTS11
d2b38e0f-14a9-4e6f-9310-5480d1cb11fc | signoff | HOLD POINT
90adccf0-2f3e-4a16-9219-69ede643fb0a | checkpoint | Seal Design - Binder Substitution - The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying.
daa977e3-c42a-55a6-8d51-3b22305eef9c | note | Acceptance Criteria & Frequency (Project Specific) - Approval
431c149e-a094-572f-9607-0086a49e8819 | note | Check Item - MILESTONE
f4cdf4aa-3916-568b-96c5-560f5cd9fa14 | note | Reference - Clause 6.1.2 MRTS11
965fe9c0-820c-4c6d-9233-1399b8063013 | checkpoint | Seal Design By Principal - Testing shall be completed by the Contractor at the test locations and minimum test frequencies detailed in Table 6.2. (Particle Size Distribution, Flakiness Index and Avegrade Least Dimension, Texture Depth and Ball Penetration.)
e7196785-56ba-5ef7-8d74-d1c2d7d60a81 | note | – Test results for the cover aggregate and texture depth has been submiteed at least 7 days
1eaae898-00aa-5b4c-8f67-6c2e81377337 | note | – Ball penetration testing has been undertaken in accordance with Table 6.2 and Clause 10.1.2 and passed on to the Administrator on the day of testing.
546aa3ff-1026-541c-86b1-bca9ec4d1970 | note | – Spraying shall not commenced until Designed Spray Rate and Designed Spread Rate has been confirmed.
b850825d-39b6-573b-9333-03edf5bc0a14 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
d5183ebc-743e-5cfe-8444-0c6da8b97679 | note | Check Item - MILESTONE/HOLD POINT
5f093790-9527-5028-8d83-2c408376504f | note | Reference - Clause 6.2 MRTS11
5244d2f2-2872-4f65-9ad2-438a3e2f7a19 | signoff | HOLD POINT
2c641a08-dc52-4c5b-994d-398e52924e5a | checkpoint | Seal Design By Contractor - Where the Contractor is nominated to undertake the Seal Design, the Contractor shall inspect each site and shall select inputs and associated design factors. The seal design reports shall include all inputs stipulated in the nominated clause.
eba6a502-4de3-5b28-9b89-4f525137156e | note | Acceptance Criteria & Frequency (Project Specific) - Check
e442c01f-5a3a-5680-87a1-2fd45959a583 | note | Check Item - Check Item
f7691e6f-56bd-5ef0-a8c0-1401dd5d37bb | note | Reference - Clause 6.3 MRTS11
c97d4ee0-da6a-4d5b-add7-c4f036e4f84d | checkpoint | Seal Design Report - A seal desin report shall be submited to the Administrator at least 7 days prior to commencing bituminous spraying operations. The Seal Design Report shall include the requirements of Clause 6.3.2 MRTS11. The Administrator shall have 3 days to consider the seal design report and spraying operations shall not commence until release of the hold point
2c50b08b-081b-51b8-a24b-cedd9b49b8a5 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
67fd3980-41b6-5a34-9caf-ee87f04653c2 | note | Check Item - MILESTONE/HOLD POINT
e66e39b8-a5c1-5e73-bc6f-c12c55220a41 | note | Reference - Clause 6.3.2 MRTS11
5ef13b5f-35e2-47ee-a541-e27f7fc6ce83 | signoff | HOLD POINT
8e4cb0d9-aeba-447e-9a3c-a27d0c51a1cb | checkpoint | Quarry Registration Certificate - Cover aggregate shall be supplied by a registered quarry comply with TMR Quarry Registration System. Certificate to be sent to the Administrator 7 days before material supply. Material from a quarry shall neither be supplied,nor used in the Works prior to written permission by the Administrator
4f4f2f7a-be0c-504f-8147-f5aaddb89557 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
de290188-242b-5513-b3e9-20d354608ac9 | note | Check Item - MILESTONE/HOLD POINT
6a768c43-f227-56bc-9b07-30026a66c9c0 | note | Reference - Clause 6 MRTS22
8bf406e1-ee0f-4bd8-addc-8ab9e5da154a | signoff | HOLD POINT
452c30a5-aaaf-4401-b115-1beadff73184 | checkpoint | Cover Aggregate - Cover aggregate shall not be exposed to contaminant agents and to be handle to avoid any contamination / deleterious effects. It shall be protected with a light plastic or similar material to prevent the ingress of moisture and other contaminants.
60266489-dd44-539d-a0ba-ab15dc41bc35 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
992bfcf9-6e69-57a5-b71c-c142b3565b43 | note | Check Item - WITNESS POINT
d51b5467-7edf-5de7-9159-5ec4641ba401 | note | Reference - Clause 8.2 MRTS11
c1299953-6927-4118-afd4-2fbd5f06459a | checkpoint | Bituminous Materials - Binder shall be delivered to the Works in accordance with Clause 8 MRTS17 Bitumen or Clause 8 of MRTS18 Polymer Modified Binder. Temperature at delivery to site shall be measured and recorded.
874c06c1-7f49-51c9-9eb9-e7d0839155d8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8a7f7379-ca7d-578a-b782-9a13a3cb7ba0 | note | Check Item - WITNESS POINT
f174495c-c5a8-5504-82f5-20fd5cb47311 | note | Reference - Clause 8.3.1 MRTS11
cb083f4f-4982-40ff-a24f-2a0547cbf186 | checkpoint | Bituminous Material Heating - Strict controls shall be applied to heating of bituminous material and in accordance to Austroads AP-G41Bitumen Sealing Safety Guide, the heating requirements shall strictly be observed.
4abe6a6a-5fda-5a57-bf36-555ab5f6d3d5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e3ad931a-cb18-5cec-b4e2-927ab6c375d4 | note | Check Item - WITNESS POINT
645bb8e6-ceb6-592a-9a4d-2aec4da8e68f | note | Reference - Clause 8.3.2 MRTS11
fdb148f2-fb93-4c87-848e-ba45148ed16e | checkpoint | Precoating Agents - Cover aggregate shall be precoated with one of the nominated approved products listed in Clause 2 of Annexure MRTS22.1. The Contractor shall submit to the Administrator details of the precoating agent procedures 7 days prior commencing.
0e92f4a0-2b8d-51b7-896e-95ceac9cea75 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e3896e96-ce4f-5c15-9452-3f5856e39fe1 | note | Check Item - MILESTONE
9cde00fd-52d9-51a0-ab49-004ca9656262 | note | Reference - Clause 7.1.4 MRTS22
9de48b4d-4239-4eec-a0aa-c0c73ce1c415 | checkpoint | Compliance Testing - The Administrator shall receive at least 15 working days a preliminary sample of 40kg of each type of cover aggregate to be used in the contract as per the requirments of Clause 3 MRTS22.1
1358d5f5-f708-5491-9c73-59c181e7c0ad | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
73bc301c-22e0-5439-a5cf-65b60f846245 | note | Check Item - MILESTONE
653e256e-f79e-5310-a84e-1d6fabab79e6 | note | Reference - Clause 8.1 MRTS22
bd521606-a30a-473f-94d1-1d7d7c574048 | checkpoint | Plant & Equipments - On site documentation of required plant will be provided no less than 3 days prior to sealing operations and shall satisfied as per Table 9. Additional plant requirements shall apply in accordance of Clause 5 MRTS11.1
a6dd217a-7369-5cb8-be27-b4e9e82a95aa | note | Acceptance Criteria & Frequency (Project Specific) - Check
2ee05da1-86fa-504d-a487-4ff6c246f53f | note | Check Item - HOLD POINT
94ada9b0-ddbf-5b65-8b80-d01a877761ac | note | Reference - Clause 9 MRTS11
8658bc61-e6d5-43fa-9837-44435b1c7300 | signoff | HOLD POINT
2cce0c81-1144-43a7-b196-d150e9fdcf9e | checkpoint | Initial Bituminous Treatments (No Existing Bitumen Treatment) - All foreigh and loose material, including lenses of pavement material shall be removed from the surface. The surface shall be swept with a road broom. Where a Ball Penetration test result exceeds 3.0 mm, the surface shall not be sprayed until approved by Administrator.
4b41a678-b2d7-5909-9d7f-6a50fceccce5 | note | Acceptance Criteria & Frequency (Project Specific) - Verify
16d0818b-54c8-5fd9-a9f5-5b42327688eb | note | Check Item - HOLD POINT
70d04455-d04c-5724-b8b6-41985bfb5c0e | note | Reference - Clause 10.1.2 MRTS11
fb23884e-4670-4047-90c2-c621a1cfa08c | signoff | HOLD POINT
f94faa39-dc66-4ca7-b55a-0b8b58b0c9f9 | checkpoint | Availability of Cover Aggregate - Prior to commencement of bitumen spraying operations, the contractor shall provide the Administrator with evidence there is sufficient cover aggregate for the extent of bitumen spraying work to be undertaken that day.
cd8524e1-4553-5388-aeef-31114298a4b5 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6ac23300-ce43-5db5-b942-f45a1418396a | note | Check Item - HOLD POINT
d3caa73a-43ea-5ed4-9aed-a10723345c4f | note | Reference - Clause 11.1 MRTS11
e3006ca0-00a3-4e05-9843-e6db5d014fbb | signoff | HOLD POINT
ecfae843-4a3a-4ec8-8ff2-2d197f30f397 | checkpoint | Pavement Surface Temperature - Spraying shall not commence until the temperature of the pavement surface is above the temperature given in Clause 6.2 of Annexure MRTS11.1.
98ce6c64-82dc-599a-b0b2-77e9b4679b6a | note | ○ 10℃ for primes
797dedbe-947e-5acf-b12f-1cde52379376 | note | ○ 15℃ for initial seals containing cutback bitumen (i.e AMC4 to AMC7)
c6a64a25-d87b-5f19-8fac-013c9a46b3a5 | note | ○ 20℃ for bitumen and polymer modified binders
87d887cd-65b5-5677-8aad-5e6514de5423 | note | These limits do not apply to WP-A and SAMI treatments
f2815643-91b7-5557-ba67-1132b2043022 | note | – placed over an existing seal or ashalt, and
051276a9-f945-5a0c-a6a5-6127bb51e13f | note | – overlaid with asphalt prior to trafficking.
10b7c704-9784-545e-b55d-e776b53580c6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
527d90d6-fa5b-5c89-8a95-fb1e0a704757 | note | Check Item - WITNESS POINT
66584fab-f073-5575-b453-665bf303e7a7 | note | Reference - Clause 11.2 MRTS11
75e703ba-8d29-4edd-8a3d-60fdb3083f9b | checkpoint | Spraying Requirements - Spraying shall not take place during rain of if rain is likely to fall prior to spreading cover aggregate and the completion of rolling. Further, spraying shall not take place during winds of greater than 30km/hr or during dust storms.
b7218441-a819-56fd-9ba5-026e118b9221 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f543b3b5-4157-57e6-9f5a-a196b00fb851 | note | Check Item - Check Item
a277872f-5f25-5e8c-a4a3-a39246576b82 | note | Reference - Clause 11.3 MRTS11
b51d1a64-b6a7-43b9-8eb5-809d7e95ecef | checkpoint | Time Period Between Bituminous Treatments - The minimum period of time between bituminous treatments shall be applicable as per the requirements of Clause 11.4 MRTS11
3456726e-dc94-53c1-9eb9-6dab66ae8f79 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
3c6285bd-47e5-56c0-8a21-f23c192f4f91 | note | Check Item - Check Item
3355bb09-0796-5903-bd14-3570e594fc32 | note | Reference - Clause 11.4 MRTS11
d5fb578d-b403-40a8-9bba-5cfe7438be56 | checkpoint | Spraying - The spraybar nozzles used shall be appropriate for each spray run and shall comply with QSC. A copy of the Queensland Sprayer Certificate shall be provided.
f28aa4db-02f5-58f9-9b23-90effdbf5348 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3a469f3e-702a-51be-b392-3282de5e9a86 | note | Check Item - WITNESS POINT
20afafa6-8c75-576f-a473-0f26dbd8e668 | note | Reference - Clause 12.4 MRTS11
75a98b09-98fc-47a6-8f3e-549f1499ed9c | checkpoint | Cutting Back Binder - Incorporation of cutter oil into the binder shall be caried out in accordance with Clause 8.3.3. Prior to each operation, Seal Designer Delegate shall nominate the cutter oil adjustments, which shall be recorded.
656be0f5-60ca-5b3d-94a2-7b20ec35d4e0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
06a5c644-fb38-5095-848f-20eab565b3a6 | note | Check Item - WITNESS POINT
d2831225-8691-5b59-a13a-4d9f806d9516 | note | Reference - Clause 12.7 MRTS11
52acc540-76a5-4c74-af2b-75b96703a16f | checkpoint | Spreading of Cover Aggregate - Wet cover aggregate containing free surface water shall not be loaded into the aggregate spreader.
ca3f2290-674c-5fde-89d6-00b531c21731 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0f7414b3-3bcf-5a34-a49c-e442a695a350 | note | Check Item - WITNESS POINT
68cd1042-0c49-551d-ad42-91972acd8f2d | note | Reference - Clause 14.1 MRTS11
5c328de1-4c65-42ef-a9db-3302c21e0ade | checkpoint | Time Limit for Cover Aggregate - Spreading of cover aggregate shall commence as soon as possible with the time limits specified below:
50caf652-f296-5cb5-b996-b78da1058a33 | note | – primerseals: 15 minutes
d6bcb743-2a03-5895-ae05-04c94e8cc41b | note | – Cutback Bitumen, Bitumen and Multigrade Bitumen: 10 minutes, or
6a201c07-5bcc-57cc-ac58-10ae9455f51d | note | – polymer modified binders including crumbed rubber binder: 5 minutes
1c6ec71e-6b9a-5804-b2d7-b9e7eb9c2bdd | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6e40ed74-2ca1-5cf3-9f24-3d68ae51285a | note | Check Item - Check Item
0affd5d8-ded5-5293-a979-518cdde4cdeb | note | Reference - Clause 14.3 MRTS11
0aaf1b8c-ed18-4ad7-8da6-c067d4b7639d | checkpoint | Early Trafficking Requirements - The requirements of Clause 14.8 shall be complied and the road shall not be opened to traffic until the release of this Hold Point by the Administrator
bedf804f-a1b1-5e61-b84a-473b8a05b3c2 | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
f284aa69-ec83-5a64-b4d3-36c07ebd915b | note | Check Item - HOLD POINT
e9078d1b-76f9-5432-8bff-1bdba4436ec6 | note | Reference - Clause 14.8 MRTS11
cdff4990-5e07-4e62-af29-2c8de75085a9 | signoff | HOLD POINT
3dca7278-efea-4077-876f-9ba7ec9fc970 | checkpoint | Delivery of Aggregate to Stockpile Site - Prior to commencement of delivery of aggregate to any stockpile site, the Contractor shall obtain the Administrator’s authorisation to place aggregates on the stockpile site.
f42f6670-861a-5bb3-8d28-63dc459f8695 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
fdad421d-6117-5a74-acb0-09fa09741e9e | note | Check Item - HOLD POINT/WITNESS POINT
370e2a17-936d-54d6-b953-2fcf1572ce2f | note | Reference - Clause 10 MRTS22
315e29ef-8b98-4c8c-93f1-201ad708c8ae | signoff | HOLD POINT
074dab34-53a3-4ed6-9526-ec5bed8c14dc | checkpoint | Final Verification
a32422de-2a06-5c13-bc63-127c10392b2b | note | Responsible Officer Verify that the Above has been Constructed according to Specification
083b717b-fb52-54c1-a62a-9d8aae5385e9 | textbox | Print Name:
c0282999-8e89-50d2-8be3-a9ef4b639727 | date | Date:
97207f24-7af4-5a28-899b-2fdb1f5968d1 | note | Verifying Authority Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
f7c66219-cd16-579a-b96d-86981c723468 | textbox | Print Name:
b2c58ed3-2478-54e4-8a36-23991255fdb3 | date | Date:
030dc38c-716c-489a-af25-807d66a40fe8 | signoff | Sign ITP
2c19226d-87ff-4921-b147-32be176506fa | section | Final Sign Offs (to be completed at closure of Lot)
04a55d5d-2d69-4b20-923e-9b238ec13046 | checkpoint | Agreed Quantities
a6746af6-7cb5-4137-bc66-9c294411dc0f | signoff | Agreed Quantities Sign Off
23b74b7e-70ce-40a2-ad5b-917bc66a0ab1 | checkpoint | Closure of Lot
6315a3d5-59d5-4209-9b62-5218520c396c | signoff | Closure of Lot Sign Off
96ee071a-e904-5075-824d-b409ed815cc8 | checklist | 14.07 - Demolition of Road Furniture | itp | 14.07 - Demolition of Road Furniture
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
a0eb8ddc-964c-54ce-937b-cc7e3ddf0ffa | checkpoint | Road furniture to be removed are as listed in MRTS14.1.
50dba266-0259-583d-8255-d1eab7cc0a1c | note | Acceptance Criteria & Frequency (Project Specific) - Signange/REGP's and Lighting to be removed
d94b4f0f-b7b7-5aec-9877-ded7c7a7b76d | note | Check Item - Check Item
f8f8ce30-a8e5-5c1a-b554-ebf8cec1511e | note | Reference - MRTS14.1
3ec151fc-7a14-5219-a30f-b9a4a331bf9a | checkpoint | Existing road furniture demolished and removed in a manner which avoids damaging any adjacent work.
9c418c35-423c-5a4a-8c63-ae826ca446b8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9185182e-2637-53e5-b0ea-2cee1efad3f4 | note | Check Item - Check Item
748c96fc-0ba4-56f4-afa1-0a5b692c0cfa | note | Reference - MRTS14 Cl.7.3
f617a132-f89d-5d9f-a5e7-2ba65e68b615 | checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state.
d36dd383-9d88-5b64-9786-dadf03747f03 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
477c3ea5-1548-53a5-9ada-b2933d5694d6 | note | Check Item - Check Item
ccda0fee-1467-5bc6-ad13-a1ce9d793e9e | note | Reference - MRTS14 Cl.7.3
7fbefe98-5458-5ea4-977d-cd85b22a2c04 | checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be salvaged in accordance with the provisions of the design documentation
f4b0a75a-cfa9-5e84-8534-5eea240757be | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Schedule
92f35fad-846e-509b-ae41-5badc2fe33fc | note | Check Item - Milestone
ccc735e3-59c6-5e41-b7f4-d6c4d37aa4ea | note | Reference - MRTS14 Cl8.2
cd704bcb-f968-5d4e-8ff9-c931d94d3414 | checkpoint | Dismantling and removal shall not commence until expiration of the seven day period
e24952ff-6f41-5d8d-b0e0-88e9d13f0f5f | note | Acceptance Criteria & Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
e13544e4-bb02-5f7a-9b90-371a079c41a6 | note | Check Item - Hold Point 1
52b79bc0-b3e0-5cf0-8b12-702a9cddf1ad | note | Reference - MRTS14 Cl8.2
0adf1bb0-670d-571b-b2f6-3190ef1c7676 | signoff | HOLD POINT
0c6e2f60-dab3-5c3d-b286-a4a6ec842c3d | checkpoint | The Contractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation
b130dfeb-bf4f-599c-a944-afa7bb451ee1 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Schedule
8aebd6f7-c3e8-5594-914b-baaf194cb176 | note | Check Item - Milestone
0b6d3023-c5be-548c-8bbf-a41b601a568c | note | Reference - MRTS14 Cl9.2
09d99500-91e6-5c90-aa00-2f201da91605 | checkpoint | Dismantling and removal shall not commence until expiration of the seven day period
1a6380cd-a0a0-5fb2-9962-8186b1105f41 | note | Acceptance Criteria & Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
aa34b54c-50dc-5074-8ad1-f65d1bc36343 | note | Check Item - Hold Point 2
305975e0-5e43-5fe1-b39e-1917b1ef3d02 | note | Reference - MRTS14 Cl9.2
3ef92b86-563b-5b5f-a17b-0bbd8770ab54 | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
c9b07bbc-788d-5973-bf4d-c39f8cce68b4 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
e19e657a-ea60-53f6-a642-33ea6af3beb6 | textbox | Print Name:
5aea718e-b45a-521f-b8b4-d27f4ffe6532 | date | Date:
50b79f80-6074-5d37-a9e5-8fa91f9f9987 | note | Project Manager Verify that the Above has been Constructed according to Specification
0da847fc-7c9a-58e7-aa28-8ff99095b47a | textbox | Print Name:
77839f2c-881e-5b29-988a-b8188fcd1936 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
f07f873f-acfd-5295-9074-6e5fa482f6ed | checklist | 14.13 - Supply and Installation of Road Signs | itp | 14.13 - Supply and Installation of Road Signs
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
f6435d67-7fdc-5a23-9cc6-2471d34c2a4d | checkpoint | Not less than seven days prior to commencement of dismantling and removal of existing road furniture, the Contractor shall submit a schedule of items of existing road furniture to be disamantled or re-erection in accordance with the provisions of the design documentation.
139505e3-cf4b-5360-9a44-bb07a46b2451 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Schedule
0678b7df-bf2e-5331-b62a-601c453e8c71 | note | Check Item - Milestone
79497021-4dca-5b47-9e6f-3af5324d7273 | note | Reference - MRTS14 Cl 9.2
3386c293-d9cc-5ed2-bb45-de5400011da5 | checkpoint | Dismantling and removal shall not commence until the experation of the seven day period.
5efc8d82-e3ab-524c-a6ed-758e598aaac4 | note | Acceptance Criteria & Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
124bceab-949f-5ca5-884f-459dc14aa2d4 | note | Check Item - Hold Point 2
694f6f97-fcff-57c0-bdd2-e3c765d7c450 | note | Reference - MRTS14 Cl 9.2
e61fd675-9d3e-5260-b804-bb54cf289654 | signoff | HOLD POINT
68feaa98-d1e4-5520-8b34-ab2617d5e7e9 | checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings.
eba90591-8cd3-5612-b4b0-3fae4bf92bb1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
82381296-a870-54f9-b098-3371ba5eea1f | note | Check Item - Check Item
1bbd3b49-b04a-59bd-bd88-2220a7c1a584 | note | Reference - MRTS14 CL 13.2
fc3ab1cb-208b-5417-8c1e-a400e926a876 | checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744.
c30b1de1-6db7-56a1-8086-41302fe3cf12 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3b33521c-e9f4-54e2-84c6-049e5e84cf08 | note | Check Item - Check Item
a0ca8f3a-31b7-537b-b429-58c5e8142878 | note | Reference - MRTS14 CL 13.2
9eda0715-a137-591a-bd68-1d3d4b12c129 | checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3.
886439b4-bf21-5bd2-9e4e-c26e9e51afd2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e2e2721b-3b55-5272-8381-6385e3cb8f57 | note | Check Item - Check Item
49f8415b-fda7-576e-a13a-6609c54e9ddd | note | Reference - MRTS14 Cl 13.3
f8bb7b49-738c-5c93-87aa-09d63deb5ce4 | checkpoint | The sign substrate shall be manufactured from aluminium. Other materials may be considered but evidence of the full approval of the department will be provided to the administrator prior to their use.
edd38d39-0fca-5766-802f-1036f3e4d61e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8cd5387e-f2a0-5132-a6ad-996d47dd9610 | note | Check Item - Hold Point 3
a6404f45-8968-54c2-b68f-7d62d2a41962 | note | Reference - MRTS14 CL 13.3.1.1
413b6df0-1de8-53a6-857c-4fbac61dcb36 | signoff | HOLD POINT
4c96277d-c939-50e0-9128-550bd73f0f3a | checkpoint | Sign faces are fabricated in accordance with the requirements of Traffic and Road Use Management Manual (TRUM) Volume 3, Part 5.
c5fc79e4-a539-5472-a0b3-b8426ada4372 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
47c35ec2-9977-5c19-8470-acba85edabb7 | note | Check Item - Check Item
4c6cf4dd-1b4f-57a9-bc04-1dd3f6e3383b | note | Reference - MRTS14 Cl 13.4
81394f7c-2e1b-52a9-991d-b80263fff971 | checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
e6e7c8a3-252b-56e5-8029-12a007033e9f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0a8c7250-b5cb-5a89-b7ff-8d398cc02d9f | note | Check Item - Check Item
250778b6-4749-50c7-9295-f48c5920e37c | note | Reference - MRTS14 Cl 14.2.3
717a32cf-4bcc-52ed-ad57-450cb62f18cc | checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required.
44fc9ab3-9255-56db-8c34-9f68a1165340 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e8d10b08-096a-53d0-9d47-08cd0232d6a2 | note | Check Item - Check Item
feb3f43c-9e36-5a5d-8e55-3a709840d8be | note | Reference - MRTS14 Cl 14.2.3
9e898f21-063f-5c62-a3f7-42681e70f9d8 | checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
1c1f0e17-b216-531d-b51e-0c5c1100c8ec | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e20e5ceb-ddff-5317-9cc9-ed9957b9e737 | note | Check Item - Check Item
d005f7a7-09fb-57e6-a59f-db59a8f9786b | note | Reference - MRTS14 Cl 14.3
09f4c342-d7eb-5893-a729-25354cd3ae36 | checkpoint | Erection of Road Signs.
e3350612-b183-5e10-b7b1-c16a97ba8d21 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
91142831-a236-5280-9020-84e7bcf0ddb3 | note | Check Item - Witness Point 1
3c8340be-1a92-5250-94ee-c166219a104f | note | Reference - MRTS14 Cl 14.4
896ada20-d08d-575e-9a2f-d2c2e6248123 | checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD.
09950ed3-c61f-59bd-b222-16dc18e52af0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e62d979b-4cda-533d-a33b-a248f96bbabf | note | Check Item - Check Item
d07d2650-21d2-502c-a1c0-4c604a09552d | note | Reference - MRTS14 Cl 14.4.2
36055701-a3e6-50be-aca0-7e78453bf4ca | checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete.
8079d4b0-a770-5e3d-b862-6f61d58aa84b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ff52eb69-106d-5f83-b1a3-43d33fa428f4 | note | Check Item - Check Item
b1418cd4-ebe8-5652-a0fd-27b6ea804a20 | note | Reference - MRTS14 Cl14.4.5
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
6447ed65-fe01-59ce-a879-0fc84c975fb4 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
a917ebfa-5855-50ba-8a1d-34e55ece322d | textbox | Print Name:
2f1b7dc2-f57b-5d36-9bf0-fd80e109285d | date | Date:
11c74cbc-ab9e-5452-a82e-e2d8daa57d6c | note | Project Manager Verify that the Above has been Constructed according to Specification
b9ba9187-ed01-5076-a477-619de7919529 | textbox | Print Name:
d3f3db22-7639-582c-9e14-36ee9be9de9b | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
42cfd8c9-f78c-52ab-af97-a99d36957842 | checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments | itp | 14.20 - Installation of Steel beam Guardrail and End Treatments
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
bccb56bd-311c-5847-8987-b4aaa7fe9e9a | checkpoint | Manufacture of steel beam guardrail post, panel components and end treats are maufactured by an approved manufacturer.
4843b0f7-68bb-5d81-828e-648df7fbae70 | note | Acceptance Criteria & Frequency (Project Specific) - Approved Manufacturer
c4543705-1cc8-58aa-b38a-5e4681084d62 | note | Check Item - Check Item
3b8bb005-74b5-5720-8137-f9082802fdde | note | Reference - MRTS14 Cl. 20.2
4dfd4e28-c628-52ff-96fe-1db7fa4fe0f7 | checkpoint | Steel beam guardrail components and end treatments shall only be supplied by an approved supplier.
c7c23e15-0346-536c-8211-f7150d83843e | note | Acceptance Criteria & Frequency (Project Specific) - Approved Supplier
b26f0dd2-1806-5cd2-9073-dfe1bf9ab2f3 | note | Check Item - Check Item
ca406fdc-bf86-5fbc-a091-c87e6dd2744e | note | Reference - MRTS14 Cl 20.3
64dde858-a9af-5ec2-b768-051c41a6f96b | checkpoint | Hexagonal head bolts and nuts shall be manufactured to the dimensions shown on Standard Drawings, and tested in accordance with MRTS78. Mushroom head (C) bolts shall be manufactured to the details shown on Standard Drawing 1479 Circular washers shall conform to the requirements of AS 1237.
d373c245-a2e7-549e-9605-cbe33fc1a3e2 | note | Acceptance Criteria & Frequency (Project Specific) - Test Certificates
a1042a09-d773-5847-aab7-6d4c4ad9bb19 | note | Check Item - Check Item
b5cbac68-6128-541a-881d-e626e71ccadb | note | Reference - MRTS14 Cl 20.4.7
e6c0b264-f95f-5004-b949-33f4a36ba685 | checkpoint | All panels, steel posts and blockouts shall be batch stamped during the manufacturing process with manufacturer's ID, Metal grade and thickness, and batch number. Single batch <2000 items.
2aaecd69-f01b-58e6-b17e-d2166a0fc79b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e0bf430f-e64d-546f-b517-96a42be3ae52 | note | Check Item - Check Item
2fc598f0-72ae-5b2a-989e-611af14cc958 | note | Reference - MRTS14 Cl20.4.2.2 Cl. 20.4.3.2
b12935fa-1206-5e02-8824-a13336fabf5a | checkpoint | All steel components shall be hot-dipped galvanised after manufacture in accordance with the requirements of AS/NZS 4680.
b5f3f925-0aaa-5e75-8240-41441560c608 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ac3e3cee-0bf7-5035-b644-7fbf7ceef79f | note | Check Item - Check Item
047fc73a-c8db-52fd-9207-5971aa2da4e6 | note | Reference - MRTS14 Cl20.4.1
57eb2a5b-44d4-59b8-87ec-4d5ab66717b2 | checkpoint | All the steel manufacturer material test certificates shall be supplied to the Administrator. The test certificates shall show the full chemical composition including the carbon equivalence, and mechanical test results for yield, tensile and elongation
e4b438a0-e316-547b-badc-a356445193e8 | note | Acceptance Criteria & Frequency (Project Specific) - Test Certificates
de652918-7465-54ff-964d-145e28404dd2 | note | Check Item - Hold Point 7
cde85703-67c3-51d8-b631-766e155e38a0 | note | Reference - MRTS14 Cl20.4.5
2a7da4d5-da5e-5f6c-b78f-29708142a448 | signoff | HOLD POINT
193edcba-2fea-5ab4-9867-393a0ff155cd | checkpoint | If required, the Administrator shall randomly select two post and two panels from each batch number for audit testing.
e42e916d-8eb5-5450-b5c4-75f1b075d421 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
36ea8405-8b6d-5dc3-80b9-d1e8209b3f8a | note | Check Item - Witness Point 3
24d6a7bb-8a25-5d49-8fd9-1bf615a58206 | note | Reference - MRTS14 Cl20.4.6.1
e6741575-1074-5d85-831d-ed629875759a | checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied for the batch of guardrail components.
47ad042e-23bb-58c6-a633-3ec13329663e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ab6bb77d-618b-5933-876c-a094ab259b75 | note | Check Item - Hold Point 8
cff5c4a8-ba7f-510a-8355-5b02fb1c30d1 | note | Reference - MRTS12 Cl20.4.6.3
7a581b62-fa4e-5756-b77e-3090c072e77c | signoff | HOLD POINT
8b15b075-b133-5dfb-958a-696983017c22 | checkpoint | A list of component parts and fabrication drawings defining the dimensions and weld sizes of the various components and the grade of materials and relevant standards with which the component materials are required to comply shall be provided to the Administrator prior to commencement of installation of the device or system.
6033cc53-ea89-5dc9-b00f-cdf99aaf4fdf | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a5f2d3a7-d802-5cf0-b606-51c8d8d1e094 | note | Check Item - Hold Point 11
653e656d-4db6-5d31-ad6a-4fd4d2775f32 | note | Reference - MRTS14 Cl21.2
10709737-7a09-5163-ba52-36596efe07be | signoff | HOLD POINT
ed14d5ec-4f68-5ae7-b827-c05ee19a9bcb | checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
7a8a28e3-765c-5d08-bebd-11028f8ff78b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
91c7fc8b-2741-59b2-be54-7ecbb8639db1 | note | Check Item - Hold Point 1
e0e7293d-1662-52af-8beb-1fb8dec23cec | note | Reference - MRTS01 Cl.8
81f69eac-c8de-5919-a272-d1197f384047 | signoff | HOLD POINT
5438f696-b871-5606-b768-0a4ab96b1533 | checkpoint | Dial before you dig consulted and services located where required prior to excacation or driving of posts
7801b06a-570c-57a9-b58c-3a47ed460925 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
08ae92d3-e41d-5ab9-b89d-2ac6d6d30d12 | note | Check Item - Check Item
7630082c-4381-5334-af70-acf5373fcd32 | checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings.
74944dd8-6d18-56fa-9f61-c6b6e043aff5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3e0fedbc-3e4a-58b8-8d60-779a2a268098 | note | Check Item - Check Item
c4134588-fc8c-563d-b27b-f682b755109c | note | Reference - MRTS14 Cl20.6.1
17dae023-0c87-5c50-986c-3729d9bfd805 | checkpoint | A proprietary road safety barrier system and/or end treatment shall be installed as shown in and required by the design documentation, and in accordance with the requirements of the installation manual
d8213d0a-0914-512a-9c8c-0ffb4a5120f7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c1f65177-bb20-5d00-a3df-ee8c6f81de66 | note | Check Item - Check Item
7665d4ab-9211-50f8-bb41-96f95404dfb7 | note | Reference - MRTS14 Cl.21.4.1
61d17285-06a2-562e-80a3-795f8f423e75 | checkpoint | Public Domain (Departure Terminal): Soil plate on type 2 departure terminal shall not be ommitted
c378cd35-b763-5ef5-8e71-cb010cb839cd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
21227753-616d-52a3-8d70-df91f44e279d | note | Check Item - Check Item
34809aab-a0b5-5182-8cd0-5017486537da | note | Reference - MRTS14 Cl20.6.3
bbee7911-1089-5cb3-964c-bef8bf397bd8 | checkpoint | Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
4163179e-d155-5f99-8dd9-7cac896679b7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a21d27c6-c36a-5600-8755-7e57fed4e158 | note | Check Item - Check Item
8a175a1b-11ac-5036-abe1-aba01c2f8237 | note | Reference - MRTS14 Cl20.6.5 Cl21.4.5
4ed78019-ec84-5d1b-8d94-c7b1d0787279 | checkpoint | Installed within Geometric Tolerances
e014b700-9a7d-561a-ab6b-6441b7472ca0 | note | Acceptance Criteria & Frequency (Project Specific) - Post Verticaloty: ± 15mm
8e502631-3027-51bc-adac-1cd6a2328cfe | note | ○ Post Height: ± 10mm
d2b35b77-63f8-5d82-8d6b-aa93f32b341c | note | ○ Rail Height: ± 10mm
572880fe-e2ca-5788-aadb-634997ec33c8 | note | Check Item - Check Item
c8ca2fad-9fa0-52a4-8bd3-72011f3b6c58 | note | Reference - MRTS14 Cl21.4.6.2
26cb5baf-f2e6-5cd6-8701-abb2a28ad792 | checkpoint | Adminstrator accepts guardrail installation as per the design documentation
85fe8378-0462-51d1-9b35-0612f12bfe6e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
75a3f85a-588c-5326-a1b8-c5880f9dd76d | note | Check Item - Hold Point 10
15a470df-5190-5b4c-8e11-0d4232c7afd9 | note | Reference - MRTS14 Cl 20.6.7
364d99ef-e800-5449-95ab-f61a5b167342 | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
0234fb0c-dffd-5973-ab2d-51fbe847731b | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
48ac5e50-0a6c-5963-b53d-e0308d80892b | textbox | Print Name:
72e1d639-565e-5dec-a1a2-787e5cef8856 | date | Date:
48b425ad-1080-54f5-bcf6-b9706814d8ee | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
5b3dadda-9d17-51c8-95fd-3eaef37262a1 | textbox | Print Name:
77cf0730-a8e0-5808-b5c9-788553660265 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
6e1f8029-c07d-5751-9a91-4482757491ae | checklist | 16.01 - Landscape and Revegetation Works | itp | 16.01 - Landscape and Revegetation Works
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
f4525b4b-3e93-5c33-b4f5-ad2605f47854 | checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
8b3c2368-0d14-59c5-8b24-36dbf5610aae | note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
709b4f82-e2f2-5922-bd0a-5ec836c135b0 | note | Check Item - Hold Point 1
7d57c00b-9685-50f5-8de7-34ae2345fba5 | note | Reference - MRTS16 Cl 5.2.1
d5d93215-34e8-543d-9053-1ba706f6ad10 | signoff | HOLD POINT
7fe6a017-35d3-5f92-b61b-f57ae46d7373 | checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
5e4270b3-ddcc-5805-a8f4-7cd01ee8d3ce | note | Acceptance Criteria & Frequency (Project Specific) - Plan
c0dcf5df-342b-54c2-b6d2-4ec2bc317f61 | note | Check Item - Hold Point 2
7897a1ad-9f91-5336-af46-b951f43a548b | note | Reference - MRTS16 Cl 5.2.2
06c2250d-9b58-55f4-9702-655cf00abfc1 | signoff | HOLD POINT
e193c30f-e675-5d3e-81e8-c22dae44b091 | checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
888831c5-e366-51f7-9be1-7e22bbaa0c77 | note | Acceptance Criteria & Frequency (Project Specific) - Plan
f5188b4d-a426-5761-8b97-5361cef5e267 | note | Check Item - Hold Point 3
469e3681-c1b7-5316-8d8c-d972f5c8d8e8 | note | Reference - MRTS16 Cl 5.3.1
fd47f945-ba30-5ff9-99f2-1d15631ffbf5 | signoff | HOLD POINT
1eb85b71-874e-53f8-9430-98d5d226e230 | checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
8907fd25-22c8-5f84-9314-78cd1596f9ae | note | Acceptance Criteria & Frequency (Project Specific) - Plan
c3d14549-b358-5dd7-a779-29f6737fcb18 | note | Check Item - Hold Point 5
6a70c16e-d0d8-5647-ba0e-49fb314f6857 | note | Reference - MRTS16 Cl 5.3.3
368c5b16-395f-50ed-af22-2f51d90df6be | signoff | HOLD POINT
ce82097e-01f5-5046-b468-719af42b3277 | checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
2c927274-1df5-54a1-a3cf-c89b28294b53 | note | Acceptance Criteria & Frequency (Project Specific) - Plan
ea082863-a23f-5b24-8476-9d141b94bbb5 | note | Check Item - Hold Point 6
95708b36-6bef-5ec6-80e1-666f8985b0fb | note | Reference - MRTS16 Cl 5.3.4
4f3d6cc1-c706-509a-b025-c392a2c7c6af | signoff | HOLD POINT
6a2e865f-c69f-5f41-af3a-40880ed4191d | section | Materials
6640008d-2130-50dd-a1ea-5831e9ca44e5 | checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
7a4073cd-bf0e-5ecf-8faf-9845076cb378 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4a462168-7aa0-5571-99c9-7035772c23d6 | note | Check Item - Check Item
f0ce6821-1816-53fa-a106-126c548f65cb | note | Reference - MRTS16 Cl 7
80d7788e-7c31-5729-842a-0b5264b26c9f | checkpoint | Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm
f37c426b-e6d8-50f7-a036-75d2c8350814 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
38ee97d4-cb0d-598e-aeb8-5d0d6b7e79a1 | note | Check Item - Check Item
7d77e463-20dc-5d79-bab7-1182e8c6e12c | note | Reference - MRTS16 Cl 7
16bccd7d-2a04-54cf-aebe-b94faa104a13 | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
844c480a-75ac-5e20-bfca-2915342e85aa | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ea29f1ee-fa05-55a5-baff-e3a38e770b90 | note | Check Item - Check Item
bc48d291-831d-5012-96f6-7ec3acbf1670 | note | Reference - MRTS16 Cl 7
642649e5-e6d9-57b2-bb96-48dc73c20b13 | checkpoint | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
c2a451a1-72e5-57fe-b0d4-50d2c7120f3e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
febdf022-4a08-5834-abc2-6cac5a72388d | note | Check Item - Check Item
77162f14-54ff-521a-8ab5-276a0e5adfda | note | Reference - MRTS16 Cl 7.6.2
22d3eb6a-b172-5803-88bd-16be984b35c6 | checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
f274402a-0810-5fc6-ad84-e09355f53410 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d31808bf-249a-55fc-8d60-55239bd51ee2 | note | Check Item - Check Item
225833c2-68d7-5ed0-b8f3-204ff4ca7627 | note | Reference - MRTS16 Cl 8
477d9518-080f-5826-b11c-f658a6e8331f | section | Subsoil and Topsoil Amelioration
a4d7d209-9695-59c4-bebe-c596930c12a5 | checkpoint | Site is weed free prior to ground preparation operations
53896974-45cf-5738-9007-5b662853e9cb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
08eb9f45-c3aa-5364-841e-03614f8defdc | note | Check Item - Witness Point 2
5533ed74-e5c3-532b-9c47-685826836a09 | note | Reference - MRTS16 Cl 8.3
e4829002-7dae-5932-b487-c27cdd7da524 | checkpoint | Administrator notified at least 3 days before each of the following:
94f2e5a7-d8b9-5955-9588-6c1b9eb8a6b0 | note | ○ Application and incorporation of amelioration agents
b2d1dd4c-4c0b-557a-9e36-ceb08921e7fb | note | ○ Ripping
b1db581b-9c26-5aae-ac61-a827b5d0e143 | note | ○ Cultivation
f70716a3-a6a4-5080-94d6-bb0d15db13dd | note | ○ Roughening
474de472-0473-5a0b-9ebe-ebece7f5f809 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
83b8a100-3345-5de0-895a-221623c5028b | note | Check Item - Witness Point 3, 4, 5
1a9d885a-44c0-5429-8bc6-4172740185e3 | note | Reference - MRTS16 Cl 8.1.1 Cl 8.4.1.1 Cl 8.4.1.2 Cl 8.4.1.3 Cl 8.4.1.4
47e7603b-1af3-5c01-88a6-303e2cb6397c | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
e2c88d37-314c-574a-b25b-8e24ff5742b1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2b9bd98f-9b4f-5c6a-8217-5854dc6f7e71 | note | Check Item - Hold Point 8
f4a7074d-7531-55bb-91ad-ffea084f59ed | note | Reference - Cl 8.4.1.1
fda196db-c581-5013-a9ae-2499eeb4e866 | signoff | HOLD POINT
56bc9d57-1653-50a0-90d9-0e067c9cb2f6 | checkpoint | Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used.
4c4dc950-a0c5-57ac-800a-edcde535badc | note | Acceptance Criteria & Frequency (Project Specific) - Visual
37c517ed-d9e9-580f-8ee3-28e83d4d46dd | note | Check Item - Hold Point 7
b2e95631-8535-5e48-80ab-d8fc89e05656 | note | Reference - MRTS16 Cl 8.2.1
699e9ed0-695d-54c0-9733-a67dd3a0f6da | signoff | HOLD POINT
9b207ff5-0972-5af0-a6ea-4de4b1495100 | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
6d81c0a8-9b2b-572e-bcdb-17bb1356a84b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
85de8604-1396-5b3e-85a4-3586f2b95d1d | note | Check Item - Witness Point 6
774453a0-2952-5563-ab48-52bb2cab8f2d | note | Reference - MRTS16 Cl 8.4.2.1
1d0bea82-beda-51de-a07a-dc51e5653431 | section | Grass seeding, Hydromulching and Turfing
e1a9af94-449a-54a4-a0ba-36d3e101662d | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by:
24d17287-e0bc-565b-a853-0548565e251f | note | a)spreading fertiliser over the topsoil and raking the surface smooth
728ec58a-5d35-55b9-9f55-0b3e2afb1216 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
729b6ce8-eaba-511b-b765-8d716cd76339 | note | c) on the day turf is delivered to site
f81c4826-0e82-5e75-af7f-3757b13a1613 | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
94614c62-6f0c-51af-924f-9ab6665f6766 | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
847bdc92-353f-5f31-986d-39048643475b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
dfd77d14-5ef4-589b-bc15-07679d839971 | note | Check Item - Check Item
bd0db70f-8e96-51fb-9702-34bccbc070ed | note | Reference - MRTS16 Cl 8.5.2
bfc99466-5253-5beb-aac9-06058e84454a | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
ed205180-09b6-55f5-ab90-c58380ab5538 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a8e4b270-cd34-5503-8ad7-5f5dfc970325 | note | Check Item - Check Item
d616e2f7-adeb-5af0-b218-7c3f400cc928 | note | Reference - MRTS16 Cl 8.5.2
fe680b4e-1870-530a-8d8c-e47c87ea75cc | checkpoint | For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1
cf47483b-06ec-561f-9d33-67ad8367170b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
81993caa-9479-55a0-a526-863d3cc17c31 | note | Check Item - Hold Point 9
3c1696c2-aba4-5ece-94d7-97ae14526708 | note | Reference - Cl 8.5.1
30c44391-7bff-56f4-ae27-012f9f833ff9 | signoff | HOLD POINT
67f86207-855a-5f41-a53b-fbf320941e61 | checkpoint | All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities
b2f26881-5549-50d7-8bed-d953511a511a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8f457a00-db57-502e-bb6d-f31c0a134010 | note | Check Item - Hold Point 7
668b65fb-246d-5569-8aea-9c4fa79c7ba0 | note | Reference - Cl 8.5.1
b58526f7-05dd-56ad-939d-4bf0cd2b5981 | signoff | HOLD POINT
f7360832-27e6-5a9b-8197-f95a6dd11ea7 | checkpoint | Broadcast seeding installed as per Cl 8.5.1.2
56a2f854-e22a-59b7-ba21-b4ef331910c8 | note | Check Item - Check Item
c4244d46-3422-57a0-9380-6ac2c84c36e5 | note | Reference - Cl 8.5.1.2
56b07827-4872-5262-acf1-115d5d9b63c5 | checkpoint | Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4
9fa0f981-ba3c-55b6-81f9-76d830acf5b7 | note | Check Item - Check Item
187c5647-acea-5273-a115-ca5be568161a | note | Reference - Cl 8.5.1.4
47c9b38c-4ddf-5392-86be-c926c060443b | section | Establishment, Monitoring and Finalisation
89c2c6bf-82eb-5415-af8c-444ed8c5412d | checkpoint | Commencement of the Establishment Period
9b3ba509-6ade-50a5-b0c4-cab4906d8b81 | note | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Commencement of the Establishment Period by the Administrator
a5a970e3-cb62-57f3-a2a0-e0aecd27207b | note | Check Item - Milestone
9744dc77-01f4-5b3c-b808-7e8afd166d03 | note | Reference - MRTS16 Cl 9.1
8235b692-7442-5a4a-b6d0-e7736e54d34f | checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
e376b206-56bf-5eae-a746-a574ac5a8c30 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
848ed7c7-3882-5d3e-b97b-9700b83a35ef | note | Check Item - Check Item
310a3ba5-e293-5076-9d28-20837b52fcbf | note | Reference - MRTS16 Cl 9.1.1
9841cf0e-ec31-5e7f-a7ed-1a76502d16e0 | checkpoint | Commencement of the Monitoring Period
ae65426b-7315-5851-b485-13f904d76da4 | note | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Commencement of the Moitoring Period by the Administrator
0b105697-ff45-5221-a9c8-e19ff9551740 | note | Check Item - Milestone
42d49c45-3da0-5ccb-b114-9b41a79425db | note | Reference - MRTS16 Cl 9.2
0bc2017e-ea5e-5b90-a544-d4e6de7c3884 | checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
00d60bc1-2dfb-5a7f-9134-472f72091a4d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a4464ddc-4f35-5864-962b-124c9bafe2fe | note | Check Item - Check Item
ced7726a-31cf-5f51-a310-1db6d87f7f9e | note | Reference - MRTS16 Cl 9.2.1
cacd6771-2e96-5ce2-8b91-32fbfada9f5b | checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
17e0360f-6e6f-5876-95f3-55056dcb2bd5 | note | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Completion of the Moitoring Period by the Administrator
cbbee0f8-f572-5df9-a2a7-e1086b125aab | note | Check Item - Milestone
c2ce8224-bf47-525b-8cf6-d7024c5ba96f | note | Reference - MRTS16 Cl 9.2.2
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
1400c426-7b28-5c6c-8b5a-c21ac63667da | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
82121f4b-453f-50fd-a4a6-ab0bd9f725f5 | textbox | Print Name:
e5751a14-d4bd-59e5-9ce4-806ab410cdb4 | date | Date:
8a23bbbc-6326-5c77-b1e6-5497cf41a280 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
5b9f2d9e-26d8-5c89-830f-1119ba570999 | textbox | Print Name:
b4b644c3-97a8-5430-a2b6-13b9de70ab29 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
951e8fe8-0f65-5779-896e-24c3a537e2ce | checklist | 28.01 - Contractor's Camp and Site Facilities | itp | 28.01 - Contractor's Camp and Site Facilities
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
0a509883-c192-5bd4-8dd4-dd99a00b44fc | checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
8757141f-9c3c-56d5-93ff-e2351151a216 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f001fe6c-cd7e-5db6-8a6c-7da5d894c290 | note | Check Item - Check Item
8f32190e-8b8a-55ea-ba9e-b37070353d25 | note | Reference - MRTS28 Cl. 4.2
3432291a-6c92-5041-b5e8-2a532b9dc889 | checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
a23121d7-9abb-53c1-8d6d-7ec30d561ba6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8681aee0-4ade-5275-ae6b-22a39cf80bb1 | note | Check Item - Check Item
bf82e08d-9c14-5d4b-ad2e-2ba8a1d7142a | note | Reference - MRTS28 Cl. 4.3
2a442f6a-503b-5b35-96e2-c6e357e4117b | checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
405d8611-6c8e-5d67-a131-f291e0b0729f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b3e74a11-558f-581a-bd63-bcea48a3578f | note | Check Item - Check Item
11d278e5-9127-5686-98aa-e9ae6f056b80 | note | Reference - MRTS28 Cl. 4.5.6
222fec6e-e4d1-54fa-b57e-52be9657ce8d | checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
eae51396-4521-5081-939a-60d4c00df778 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
00d00c6f-7ee1-5f79-a4a5-8f4ee513a731 | note | Check Item - Check Item
55b086fc-fd9b-5853-94c4-dc47e068df78 | note | Reference - MRTS52 Cl. 6
e953ca97-8139-56b7-9f2c-24d223a54b5f | checkpoint | Contractors camp complies with all requirements of MRTS28 annexure with a proposed site facility layout submitted to the administrator.
47da2a7a-40b2-52c6-a470-93c99c25bb3d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
49811547-27a8-51ef-bc1b-8b350096cc77 | note | Check Item - Check Item
011df401-2ebb-5754-8132-44a467d9e292 | note | Reference - MRTS28.1
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
c0ba1de5-0eb9-5e2b-8af3-ef49f41edb69 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
93da4d1c-1847-5b7e-8ede-a5acb050fecc | textbox | Print Name:
c02000c6-a9a8-5d62-858f-1d3bce88c992 | date | Date:
13a0fdc5-e320-5be8-b8c5-74f07ae5f462 | note | Administrator's Representative Verify that the Above has been Constructed according to Specification
c57dcba6-5b42-5b4e-913e-cb048994b9a7 | textbox | Print Name:
17df505b-5e55-5fec-8d13-f1207d32d71c | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
43bba490-97f7-485c-932e-ed17c3a22633 | checklist | 30.01 - Asphalt Pavements | itp | 30.01 - Asphalt Pavements
f86bd4a2-c626-4be5-93c3-0f04fbd50abc | section | Details
9b4b82b8-5e86-4ba0-912c-0366b65883b3 | checkpoint | Document Submission - As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
d4bc6d06-e622-53d4-a69f-2f630586536c | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
f1f2e70f-5497-53b6-8961-7ff83b0e0169 | note | Check Item - Check Item
1138ff5e-759d-4088-bfba-f4504bde98b2 | checkpoint | Traffic and Safety Controls - Traffic and safety controls are in place (eg. PPE, daily plant check)
ab532fba-cf7c-59c5-850a-8e37ad0be35a | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
637d57dc-9808-5e94-b953-9c4323f32256 | note | Check Item - Check Item
07d3b824-e43b-4d58-a449-fb70b32e0883 | checkpoint | Asphalt Quality Plan - The Contractor must develop an Asphalt Quality Plan (AQP). The AQP must be submitted to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
ee76ac65-773a-578a-9481-c129f10a1619 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
05b7381a-85f9-5f31-a7dc-53d17e424b37 | note | Check Item - MILESTONE
72d15f63-976c-5099-83f8-870b3aedc494 | note | Reference - Clause 5.2 MRTS30
8ac17a3f-134e-476d-9e39-22e67ec71864 | checkpoint | Compliance Testing - Compliance Testing shall be carried out for each lot. The Testing Frequencies shall not be less than those listed in Tables 5.4.1-A, 5.4.1-B and 5.4.1-D
216e959e-8296-5cae-b585-ca32418903f4 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
0dc647d7-920c-5479-877f-a0218b674e98 | note | Check Item - Check Item
66856491-54e9-5a99-b115-66b946c4d4fb | note | Reference - Clause 5.4.1 MRTS30
d305e37a-4aa6-4c2c-a644-4a0f9d95ae0e | checkpoint | Binder Class - Contractor shall provide evidence of the binder conformance and compliance with MRTS17 Bitumen or MRTS18 Polymer Modified Binder. The Binder Class are specified in Clause 1 of Annexure MRTS30.1 and are:
f00dacb0-e0a0-58a3-968a-04f9c634b5b6 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
41c75e34-6db8-56ab-80ea-0fd36ba42b27 | note | Check Item - Check Item
28568a00-4b12-5b26-a8a6-b38637e4f094 | note | Reference - Clause 7.1.6 MRTS30
328c3475-c138-4edc-8086-d124e428fa2f | checkpoint | Moisture Sensitivity - For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% and the average tensile strength of the freeze/thaw group must be 500 kPa for polymer modified binders and 600kPa for mixes containing all other binders. Table 7.2.5 is a list of accepted non-conformance strength ratio for 70% ≥. Where a Hold Point is required to be observed, the Contractor shall investigate the causes of the nonconformance and propose corrective action to prevent recurrence of the nonconformance. The Contractor shall submit:
90fb5dcf-60db-54dc-a55f-34e791c14ceb | note | a) test results covering the same Lot for insitu air voids and all characteristics specified in Clause 9.2, and
ff8a8596-164c-55e9-8421-9c872409dd59 | note | b) the proposed corrective action to achieve conformance.
91c6f895-f7e1-5bc5-9a62-346809652710 | note | ○ The Administrator shall consider the submitted documents prior to authorising the release of the Hold Point allowing recommencement of asphalt production.
aceb4cb9-b74b-5c04-bc4f-ac9c4f74fa79 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
5486e621-24f9-5fa2-afb4-ab053f293f75 | note | Check Item - HOLD POINT
bdd4e638-d000-591a-ab50-8066b179b56c | note | Reference - Clause 7.2.5 MRTS30
0b447f2b-80d4-4dea-a653-ba5557c9dcbd | signoff | HOLD POINT
f491e6e8-62ae-4f54-b96e-8986833d0a99 | checkpoint | Asphalt Contractor Prequalification & Operation Procedures - At least 7days before asphalt is incorporated the Contractor shall notify the Administrator in writing of the identify and address of the PAC (Prequalified Asphalt Contractor) and their operation procedures.
cd87b6c2-1efb-5611-8ba2-0a22ef41c52a | note | ○ Operation procedures
6673fdb6-567a-51cf-8772-a382c0e749f4 | note | a) laying program and rolling pattern
318a2f56-138d-5ce7-a7ee-3300910a8863 | note | b) details of any required placement trial and Technical Standard, MRTS30 Dense Graded and Open Graded Asphalt Main Roads Specifications and Technical Standards
e518a11a-6f7d-586e-8b45-0133696b7962 | note | c) Inspection and test plan.
d5dec1b9-2eab-5d26-ac42-360cbf1eac07 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
2ced9c34-3f32-562a-a6b9-462abf0c02bf | note | Check Item - Check Item
d802697f-ae56-553d-843d-fbe2de20a531 | note | Reference - Clause 6 MRTS30
02c48d8e-5d25-4ca4-b962-1c284e365a1f | checkpoint | Mix Design Submission - At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
1eec26bf-a09f-5492-ae66-bf461b2933b1 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
8a2d105b-2c04-5e2c-8814-bbf4ee37c332 | note | Check Item - MILESTONE
23dd29bb-f24e-53b6-bf14-556a4e1c6fec | note | Reference - Clause 7.3.3 MRTS30
c8e3ac9a-d4c4-459d-b231-bbf406c93629 | checkpoint | Asphalt Mix Design Registrar - The process is written in Technical note 148 Asphalt Mix Design Registration. The certificate shall be signed, the Contractor mix designer certifying the mix complies with MRTS30 and shall be submitted 28days prior to asphalt being incorporated.
5928900c-0a5a-5182-a5d7-11d887b10c8c | note | Acceptance Criteria & Frequency (Project Specific) - Approval
e74871f8-c650-5b3c-a9fd-6c62c4e48530 | note | Check Item - Check Item
701f5131-1941-50e5-8c5e-bfaa5b1372f6 | note | Reference - Clause 7.3.2 MRTS30
a62d1e4f-8b59-43c6-9ebf-8bc7813f33d1 | checkpoint | Asphalt Mix Design Acceptance - Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements or have been accepted by the Administrator for utilisation at a reduced level of service, and the following documents have been received and reviewed by the Administrator:
6a5673cc-2378-5048-b165-a067d4d7eb35 | note | a) identity of the PAC(s) who will undertake the asphalt production, placement and compaction and the address of the asphalt plant that will produce the asphalt (refer Section 6)
b2479072-2f33-54ed-91a1-7d012544c799 | note | b) the mix design certificate, which holds current registration with TMR, for each conforming mix design to be used in the Works (refer Section 7.3) or conforming revised mix design submissions (where applicable) (refer Clause 7.3.3)
bac7db94-8616-5160-af33-0305c79c30e6 | note | c) the Contractor’s AQP (refer Section 5.2)
3bac3148-18b8-5abc-884b-99b6b68831bd | note | d) the Contractor’s Aggregate Production Procedure (refer MRTS101), and
3f6bccf4-3cf4-55d0-8008-e7734d20bbe9 | note | e) the Contractor’s RAP Management Plan (where applicable).
9c0acb01-4cd7-55e1-957c-6c9116da300f | note | ○ These documents shall be submitted to the Administrator not less than seven days prior to the commencement of asphalt being incorporated into the Works.
cf7bee79-96ca-5b90-b05f-1037e7a7d880 | note | ○ Any subsequent changes to any of the above documents will require re-submission and re-release of the Hold Point.
0a2995df-ec3d-5ec8-a34d-e8ae375ce347 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
ffaabd57-7c0f-5678-ae65-4ced0b83f150 | note | Check Item - HOLD POINT
63185295-c589-5b2f-946f-0fdcca53c9ac | note | Reference - Clause 7.4.1 MRTS30
afbdb6b4-9a9c-4666-b717-5eadb589bb6d | signoff | HOLD POINT
2e9f3aa4-f4e0-4e9a-ba5e-3f8e13d8c4f9 | checkpoint | Nonconforming Mix Design - Nonconforming mix designs, that hold current registration with TMR, shall not be incorporated into the Works unless otherwise accepted in writing by the Administrator prior to the commencement of asphalt production.
58d756cb-8c04-5122-a482-5961ad4915f6 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
7a65b416-e87e-531d-bd93-424c5ba18b18 | note | Check Item - HOLD POINT
e5949c8c-33cb-512d-940f-0725dfc4d7a1 | note | Reference - Clause 7.4.1 MRTS30
4021deab-a227-40bb-80d2-22128b3eba99 | signoff | HOLD POINT
b82163f8-ab9c-47a3-b412-f205de66b909 | checkpoint | Preparation of Pavement - The surface of the pavement base/bridge deck or existing substrate shall not be wet, and shall be thoroughly swept using a rotary broom to remove any loose material or other deleterious material which may be present. Any deleterious material, which still adheres to the surface after sweeping, shall be removed by other means.
409e8421-25eb-560a-bbc5-ee0a4b5f7efc | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
a14fef67-9b3d-587b-80cd-d44d677c2ec6 | note | Check Item - Check Item
5b43eb54-77fe-57c5-bcb9-918db47d4e92 | note | Reference - Clause 8.2.2 MRTS30
c62d660b-1f60-4c49-a251-3f5923642722 | checkpoint | Crack Filling - In areas shown in the Drawings or stated in Clause 2 of Annexure MRTS30.1, cracks greater than 2 mm wide shall be filled prior to placement of any asphalt. The Contractor shall mark out in the presence of the Administrator, the extent of crack filling to be carried out. Cracks shall be filled level with the surrounding surface with a polymer modified sealant approved by the Administrator.
4a9351af-2b44-50b2-b0aa-4353ac52fa33 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4b1ca8d5-286f-5cca-ab5c-f14e3aad1b8c | note | Check Item - WITNESS POINT
1262ea6c-c395-53fa-939e-49ff45c28ed8 | note | Reference - Clause 8.2.3 MRTS30
612464a2-74f9-4fd7-9edd-1b21109321a7 | checkpoint | Strain Alleviating Fabric Strips - In the areas shown on the Drawings or stated in Clause 3 of Annexure MRTS30.1, strain alleviating fabric strips shall be applied to existing cracks prior to placement of asphalt or sprayed sealing. The Contractor shall mark out, in the presence of the Administrator, the extent of the strain alleviating fabric strips to be applied.
694f828d-2387-564d-b025-04e628d55d4d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d03d4e3f-a351-540f-bed1-b0dbece3677d | note | Check Item - WITNESS POINT
e2b4831a-25a2-5f60-ba50-4f09c25006ae | note | Reference - Clause 8.2.4 MRTS30
c5032adc-10fd-4ccb-9ecc-d52eab1b5da4 | checkpoint | Method of Placement - A self-propelled paving machine equipped with the ability to be operated with automatic thickness control and automatic joint matching facility must place the asphalt. Hand placement of asphalt is only permitted for minor corrections of the existing surface and in areas where placement with a paving machine is impractical.
92c09bf9-bb3d-5e15-bddc-ab4128aab9c3 | note | Acceptance Criteria & Frequency (Project Specific) - Check
bbaf3d2c-cac2-5442-8a71-907471436a8f | note | Check Item - Check Item
b973563d-8913-507a-b7b4-a5c716a953c0 | note | Reference - Clause 8.3 MRTS30
c28069fe-1003-463a-93ec-34ac5cbc93fb | checkpoint | Nominated Layer Thickness - The binder details are specified in Clause 1 of Annexure MRTS30. The nominated thickness of a layer of Asphalt shall be within the limits specified in Table 8.6.1
d62dc7e9-a535-54df-8235-6a13f7a03a6b | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7b5567f2-78a0-505f-a862-ef83aff530dc | note | Check Item - Check Item
c5bc5b97-9a08-5ec4-8a74-b6b621217dd9 | note | Reference - Clause 8.6 MRTS30
60556850-e446-4973-876f-12cd968376ce | checkpoint | Tie-ins to Existing Pavement - For Tie-ins, the Contractor may be required to a implement a layer thickness that does not conform with Clause 8.6.1. The Contractor shall detail the work methods to be adopted in the AQP. Placement of asphalt in a nonconforming layer thickness shall not occur until Administrator approval.
4f8001da-cc8c-5551-aec9-c2a8e9f18e42 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
e13f21c7-cb66-59f5-b18c-3fad204b0228 | note | Check Item - HOLD POINT
3552027d-84f1-50a3-bd69-0d534e3d5b85 | note | Reference - Clause 8.6.2 MRTS30
78e52ab7-c36e-4aea-bb3f-acfaead9b2c5 | signoff | HOLD POINT
b6a75dce-e9b5-4aea-8e99-844df19bf7ce | checkpoint | Pavement Temperature - The pavement surface temperature shall be measured and recorded at the point of asphalt placement on a regular basis during paving operations. The Contractor shall document the method of measuring and recording pavement temperatures in the AQP. Unless otherwise accepted by the Administrator, asphalt placement shall not commence or continue, unless the pavement surface temperature complies with the requirements of MRTS30 Table 8.7.
c5e7be9d-8f3d-59aa-b4e7-92a291f92847 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
cbebe843-3e41-50ca-bbf9-bae0c3f89247 | note | Check Item - HOLD POINT
0627a729-0414-5ec8-9d74-fab8b77f3643 | note | Reference - Clause 8.7 MRTS30
fb5a234f-6bb5-4ac4-bb1c-a2476864d59f | signoff | HOLD POINT
9f927be6-ed56-4c00-8163-0c57cbdd1689 | checkpoint | Paving and Compaction Temperatures - Contractor AQP must document the temperatures at which the asphalt is placed and compacted to achieve the insitu air voids requirements specified in Clause 9.2.1. The contractor shall nominate in the AQP the listed of requirements described in Clause 8.8.
6fe047a9-de82-5f74-91fd-0306f76e195f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
63e7da45-44d8-591a-b1c2-7b2bfc80f3f0 | note | Check Item - Check Item
811e2440-0d8d-5c92-a9bb-ed5c7a02587b | note | Reference - Clause 8.8 MRTS30
0ebac254-12a6-475c-a9df-b2142e8299bd | checkpoint | Tack Coat - Tack coat is to be applied to a clean, dry surface immediately prior to the placement of asphalt. The AQP shall state the bituminous emulsion grade and proposed tack coat.
e0d0aa8e-5ed2-5e4e-8319-daeb206f52ad | note | Acceptance Criteria & Frequency (Project Specific) - Visual Check
d0159b2f-b058-59a3-9b57-3fe02563f294 | note | Check Item - Check Item
946bbebf-aa71-5a95-94b7-37288df394a7 | note | Reference - Clause 8.9 MRTS30
ea4fbc19-db46-4e50-956c-2096f4d3486b | checkpoint | Joints - Construction of asphalt joints shall be described in the AQP and shall follow the procedures described in Clause 8.10
5b6cfca8-dc08-5c7d-8738-12c579a4297f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
84164d19-b34d-567b-bbaf-144f30cd22b9 | note | Check Item - Check Item
c692af8c-f669-573d-9579-eabf98f5c774 | note | Reference - Clause 8.10 MRTS30
3a1892fd-7a11-40c9-857d-589a27d94932 | checkpoint | Placement Trial - If specified in Clause 6 of Annexure MRTS30.1 and prior to commencing work, the plant and personnel proposed for use for the Works must be subjected to a placement trial. The Contractor shall submit a copy of the completed inspection and test plan and all relevant test results and records from the placement trial. Prior to further placement of the Contractor’s nominated mix(s) in the works, the Administrator shall review the outcomes of the placement trial. No further work shall be undertaken until the Administrator has given approval to proceed.
eb8417c4-9871-55c0-92dc-2bd6704cdd78 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
ce644968-d1d7-5529-8eb9-40fff7c79573 | note | Check Item - HOLD POINT
e4dfcdc2-1c61-5be9-b97a-fd5758a81235 | note | Reference - Clause 8.11 MRTS30
544a5089-17af-4081-a04e-6528b5fbd1f5 | signoff | HOLD POINT
41abcd91-a805-4af9-a186-d168117709e9 | checkpoint | Final Verification
4a294ee8-6b51-5bc2-ae87-102d60654b78 | note | Responsible Officer Verify that the Above has been Constructed according to Specification
a6eb1e18-8c32-5e06-940e-8c60e5a5f963 | textbox | Print Name:
c1b94e5a-1a05-515b-9a88-f5faaabe125f | date | Date:
91e0d29f-c611-5801-a7c9-463ff2bacb0c | note | Verifying Authority Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
b37da3c0-2395-58f9-be58-d94711a30e5b | textbox | Print Name:
08d146ac-e9f7-510e-9de2-6811b494da1e | date | Date:
9fcdc453-948f-4b03-b4c8-bd39b1532ece | signoff | Sign ITP
544709f1-b366-4e60-861d-fd624223c888 | section | Final Sign Offs (to be completed at closure of Lot)
d37f0dc6-0362-42b9-967c-58f315de8211 | checkpoint | Agreed Quantities
44e363bc-52b9-4658-95dd-3f42b865c0d8 | signoff | Agreed Quantities Sign Off
d2ec8c15-c969-4ec1-9235-7e2c5e049357 | checkpoint | Closure of Lot
38a0fda0-28fe-4de2-aa74-2cae3f2019e5 | signoff | Closure of Lot Sign Off
9b547435-c231-5073-94f1-0beadaef7bd8 | checklist | 45.01 - Road Surface Delineation | itp | 45.01 - Road Surface Delineation
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
3ae17b21-5037-5c9d-9802-5a5612e70796 | checkpoint | All material conforms to requirements set out in Clause 6
9aeed895-5335-5f16-8679-990e9a087125 | note | Acceptance Criteria & Frequency (Project Specific) - Material product sheets
a13b3a5a-0f6c-5938-9ed7-6ce4e0474748 | note | Check Item - Check Item
e17827ed-aed9-5258-9bac-9aed6309de12 | note | Reference - MRTS45 Cl 6
7722dc58-6caa-5d65-8af5-47ca0b2b0dc0 | checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
6bc21786-503b-5601-9338-b12c47047db9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
815e1b20-a346-5091-9e1e-e136573f82e6 | note | Check Item - Check Item
cf052198-8fc8-50b2-bada-63af9c5c434e | note | Reference - MRTS45 Cl 7.2
7e3d1f1e-3ad2-5b61-a98c-bc8be7066239 | checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
faae810d-4f11-516b-8a73-f4940ddb57a9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
06835111-3a4f-5b70-a84c-d8a0b851de1e | note | Check Item - Check Item
a8b412f4-5485-5287-9fbb-90808898c26d | note | Reference - MRTS45 Cl 7.3
90f3c565-3624-57f1-88c9-ede6886200b5 | checkpoint | In addition to the above requirements, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
c7eb54ff-414a-549f-b31c-59cafefb8dcf | note | Acceptance Criteria & Frequency (Project Specific) - Visual
541cea5f-6a55-5334-af0e-46266518a73f | note | Check Item - Hold Point 1
e35f0c44-0930-5e00-a4b5-974db6322f43 | note | Reference - MRTS45 Cl 7.3
c77633d3-b64c-5797-8648-31153b14f36d | signoff | HOLD POINT
e8ac82a2-c61b-57f1-8c4a-eb1f085601f5 | checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
39e43d19-0b02-5eb7-b1f4-74b25e2caa9d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8a975ec1-2897-5c67-98fc-7aee5dcf9656 | note | Check Item - Hold Point 2
1e2dd305-80dc-5950-abd2-1a3da453d49b | note | Reference - MRTS45 Cl 7.4.1
cda0ce3a-d738-5d4a-a497-ff27d6b510e3 | signoff | HOLD POINT
6c1def3b-7ce6-55d4-a15d-99dd1df5b6ed | checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
ea312b8c-6602-5e72-96e0-846435551e2e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0bf71d96-2cda-5061-9877-033478fa501f | note | Check Item - Check Item
18b4487b-1aee-52c5-b853-9440e9041f14 | note | Reference - MRTS45 Cl 7.5
e2729405-f82e-5d31-87c3-2d4378764a46 | checkpoint | All Markings are of uniform thickness and intensity
c4cb5054-0383-5dee-afed-4dcf107dd1af | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d075df7e-47e3-5b4d-b1cb-a44f038ed328 | note | Check Item - Check Item
004ae73d-f365-5c61-a239-4858110f8fab | note | Reference - MRTS45 Cl 7.5.2.3
8391de96-048d-5e1d-9da1-389ea59e35dc | section | Waterborne
2dfed582-2a1f-5801-8814-b3d277916b47 | checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
db6db9d9-aa2e-5628-a40e-0593efd9d7fa | note | Acceptance Criteria & Frequency (Project Specific) - Visual Table 7.5.2.4
2a2e9513-8d6e-562b-a08c-c35e2070cb42 | note | Check Item - Check Item
e8cbd5e3-9165-5a10-a354-9d081610cbbd | note | Reference - MRTS45 Cl 7.5.2.3 Cl 7.5.2.4
73ccd5df-db9b-5a27-8fe6-15446e57c311 | section | Thermoplastic
fb39b1c6-cfd2-5a66-9a23-765790ae3896 | checkpoint | If required, a primer of type recommended by manufacturer of the thermoplastic material shall be applied to the surface immediantly in advance of, but concurrent with, the application of thermoplastic material
8510d1a0-38a7-5c41-9e00-a6422f16b131 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f4b5f44d-19a8-5341-bc11-30453dd84f9e | note | Check Item - Check Item
b0d37d3a-4d96-5f6b-8632-85428e49590c | note | Reference - MRTS45 Cl 7.5.3.1
10d260d5-49bd-5488-b46e-27f97fce75ef | checkpoint | Thermoplastic shall be applied at a temperature between 180C-200C or as per the manufacturers specifications
8ad3808c-de42-54ac-a64a-f5ad743aced5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8a9c6679-883c-53d8-bdb6-25a780afb25e | note | Check Item - Check Item
e96f3184-1c15-506f-94d6-b22f393f97e7 | note | Reference - MRTS45 Cl 7.5.3.2
ea986099-54f8-55ea-86a4-f2931c00b5fb | checkpoint | Thermoplastic applied at a minimum of 2mm thickness
bf1b9b59-7707-5e25-945f-12dd3a01ab9d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
dfaf5270-c0d6-5cdd-be81-5a35933f1032 | note | Check Item - Check Item
1af4f09e-72c6-50ac-b410-0e516981e23b | note | Reference - MRTS45 Cl 7.5.3.3
34fb0dd9-24e1-5d98-94de-5daabc3ab01f | section | Cold Applied Plastic
4c5bb721-cf1a-52b0-90c7-e094ab68f428 | checkpoint | If required, a primer of the type reccommended shall be applied to the surface immediately in advance of, but concurrent with the application of the Cold Applied Plastic materials
1217dfa5-0912-5f3c-9b16-ec47a70f9230 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d256f630-b4c2-58e1-af72-4108a1c54bc1 | note | Check Item - Check Item
d09549dc-4371-5b37-a113-5f3f214a83b0 | note | Reference - MRTS45 Cl 7.5.4.1
8ec2f0d3-133a-5519-91be-f0c6d6f3e4fc | checkpoint | Cold Applied Plastic shall be applied at a temperature as per the manufacturers specifications
188f8a77-d66d-5943-b6e7-0e614182f5a7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
189c8d8e-c21e-5016-a198-9694d4ec7b54 | note | Check Item - Check Item
a04d5416-d1a7-529c-9718-1e0112a41da8 | note | Reference - MRTS45 Cl 7.5.4.2
708ad4aa-4643-57f3-b6cb-296293fad498 | checkpoint | Cold applied Plastic shall be applied at the rates specified in Table 7.5.4.2
cc9ca8e8-14d7-57d2-9375-dd5f2062c7e4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ad5afa8e-d70c-5a88-856c-20a771994368 | note | Check Item - Check Item
1feeaf12-d14e-5edd-9cf9-476c3ad09e99 | note | Reference - MRTS45 Cl 7.5.4.2
b57792ff-1f97-58d2-8691-369b2e10dc0a | checkpoint | The use of Raised Retroreflective Pavement Markers shall be in accordance with Cl 5.6.2 of the MUTCD Part 2
d5c57438-e7ea-5138-b8af-962272deb8f2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2f93e704-0525-53a8-91cb-71647ca62d58 | note | Check Item - Check Item
8fcfb9ff-df6c-59be-9930-b00e6fc2e999 | note | Reference - MRTS45 Cl 7.6.14
2b9ef598-78e6-58b6-bbe3-9c4312d8de93 | checkpoint | Material complies with luminance and retro-reflectivity requirements.
3ff9ff1f-c9e4-572a-b180-85866998c509 | note | Acceptance Criteria & Frequency (Project Specific) - Test procedure AS 4049.4
0fd77d61-be2c-54f6-94f7-61022ec320a2 | note | Check Item - Check Item
19b2e1fb-336e-5e61-8a5d-d58cfd5bc7b9 | note | Reference - MRTS45 Cl 5.3 & Cl 7.7.6
3c495a3a-1b57-54f4-9a2a-071af2f78091 | checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
e9b4494d-d61a-5b40-a4ed-081eef7de77b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c63a05dc-f6c6-51c7-8881-d14b3d0e5169 | note | Check Item - Check Item
7c64b6ea-a0f4-59c0-a9af-b1c5ea2cfead | note | Reference - MRTS45 Cl 7.8
3c337c7e-f2ed-571e-81fe-61ca0b8b7b01 | checkpoint | Completed Pavement Markings shall be uniform, clean and well-defined edges without deformation and conforms to dimensions as set out in the MUTCD
5681fe6f-b035-5cfa-be2f-a5f789be5162 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
38dd3307-ebb0-5aeb-8898-461cb1fd1742 | note | Check Item - Check Item
0224aede-2b5f-5121-bd76-4b827348b018 | note | Reference - MRTS45 Cl 7.9
c5b1013d-cad6-555a-8070-e1be8b9695e2 | checkpoint | Pavement Markings conform to all tolerances
d0f38715-694d-5cfe-a0d0-f8de9ee21227 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3dd91ba0-41fa-5c55-a347-06124efcff4c | note | Check Item - Check Item
6ec0308f-31a0-5e1e-8347-12ebbc578d20 | note | Reference - MRTS45 Cl 7.9.1
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
60fbf892-8445-512d-9062-62a8afeec09d | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
237edda6-cc1e-5acf-ae8a-ac96ca5eb698 | textbox | Print Name:
595981ac-9a51-56f2-9526-df13f6ae58f6 | date | Date:
4bfb577a-d29a-5872-81e7-7fff2bf5acad | note | Project Manager Verify that the Above has been Constructed according to Specification
59c7d2de-f827-50eb-b65a-5796494c19d4 | textbox | Print Name:
ae8383d1-f373-5347-a668-9a865819345a | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
f3e288fe-a5ac-5622-b6f9-a457f165cbf7 | checklist | 51.01 - Environmental Management Systems | itp | 51.01 - Environmental Management Systems
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
e2d98c6c-888f-5a38-a14b-8459a6dfd26e | checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with General Conditions of Contract.
1ce2ffd2-e6fe-559a-81dd-1a3efd6a9081 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of EMP
b10a1661-5f9b-588a-b3ab-0b9143a7a016 | note | Check Item - Milestone
5e1f15fe-68f3-5626-92cb-36d228befb6e | note | Reference - MRTS51 Cl. 6.3
6360f1b8-2706-5c84-b9d3-68aa827efb83 | checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
dbc3f4c2-1aa0-59f6-8083-12eb18b670c8 | note | Acceptance Criteria & Frequency (Project Specific) - EMP Approved by Administrator
6afcbf29-32dd-50f0-96b8-a43c7aa5e193 | note | Check Item - Hold Point 1
0265a7cd-48cd-5fa8-a2a8-81eaedc72948 | note | Reference - MRTS51 Cl. 6.3
2bc0754b-1f9f-5a2d-b653-d4b48e3eb959 | signoff | HOLD POINT
c560177a-09b7-5176-8b7e-680e44b8ca28 | checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
84c65eda-6dec-5e5c-b44b-d36fd3530bea | note | Check Item - Hold Point 2
860d552e-4e87-526e-bb63-4982a91f8cf3 | note | Reference - MRTS51 Cl. 6.4
cc53ac5a-852d-536e-984f-183e5f5c7e11 | signoff | HOLD POINT
7bbb90f8-bc30-5c94-abaf-482023335db0 | checkpoint | Environmental site inspections to be conducted daily, against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a monthly basis.
14aab39a-8474-5a19-bc63-5d030592fa5b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e91aca08-4a37-5652-a31e-a3887c145a0b | note | Check Item - Check Item
89b91045-e95b-5a05-85f3-927e8fb502ff | note | Reference - MRTS51 Cl. 7.1
f469e4b1-5356-5fe4-af33-06a7a831eea6 | checkpoint | Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request.
d22d827e-9b14-5021-a202-1357c5611ec3 | note | Check Item - Hold Point 3
5675dce7-83f3-5846-b088-b82adb28aaa6 | note | Reference - MRTS51 Cl. 7.8
d657d398-3f38-5c78-9cdc-c9341e9e5bc3 | signoff | HOLD POINT
b590bcbe-2411-583c-8042-0512dea7a35f | checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite
d5e662ed-1ead-50af-9f6a-d43dcd45cb8a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7ef2a8b2-f283-553b-9995-e61ad71796a4 | note | Check Item - Check Item
e4d6a16d-8e68-574f-9856-a4c9c934933e | note | Reference - MRTS51 Cl. 8.4.1
de356f17-b658-5e0a-8988-5de42e11527f | checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
5ee5ba55-a944-5924-b9db-2a6d80796b2d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e4e9933b-79db-5d7e-99a7-6f390652b487 | note | Check Item - Check Item
9934e1e8-cee7-56f2-a68b-6035bd4dd04e | note | Reference - MRTS51 Cl. 8.5.2
977a6a79-3d5a-5f50-969f-ea82eb06fcf9 | checkpoint | Project records shall include all noise monitoring results if required
06c070fc-337b-5aed-86a8-7a8ca5f9e45c | note | Check Item - Check Item
b29a1908-b64a-5c75-b050-ac3c7bbe0897 | note | Reference - MRTS51 Cl. 8.5.3
0427515b-2710-5495-b354-972881771568 | checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
81b8390e-22f5-55ba-a07d-1d4a3c19f36d | note | Acceptance Criteria & Frequency (Project Specific) - Visual (Survey Recorded)
671c7d32-0e6f-5753-a120-456f0e092c97 | note | Check Item - Check Item
19e13a8b-8bbc-5a69-871b-6876e3ae4e8f | note | Reference - MRTS51 Cl. 8.6.2.3
5a1a8817-5522-5f66-adae-fc69e46ca393 | checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
ab7e753b-bac4-5fb1-b772-fc652170ccaa | note | Check Item - Check Item
2da7441a-b6d4-5291-bf3f-bb412c629295 | note | Reference - MRTS51.1 Cl. 8.6.2
ca578709-f713-5fa9-835e-0010730ea5b8 | checkpoint | The contractor shall at all times take reasonable and practicable management measures to avoid cuasing environmental nuisance or harm due to air quality. Burning of material shall not be permitted
86a21d25-7354-5408-8b65-5f698ae6afa7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4026450a-9da7-516c-a82b-79d2c2bd6e46 | note | Check Item - Check Item
d07d717b-01ae-59d5-8551-7ca65a36773f | note | Reference - MRTS51 Cl. 8.7.2
29333b8d-8287-5f68-9cd8-d2b1a1d19d86 | checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
133af2d1-dd9f-5c58-a256-406a298f25c6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b6e8c399-cbee-50ed-b74b-6621cd8993d6 | note | Check Item - Check Item
e1ee694a-37ae-5266-8b0f-3b7d373c7a5a | note | Reference - MRTS51 Cl. 8.8
421b28f4-ee6d-51a4-a3e6-570bf33e1471 | checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
d069b5a8-fac4-5632-b53d-a835d5a7363b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
478f690f-2279-5ba4-be08-830decd53bb4 | note | Check Item - Check Item
5db450fe-5f0a-5262-ba3f-63d137d6a1aa | note | Reference - MRTS51 Cl. 8.9.1
e1685162-7941-5c97-824a-6f9468aa3afc | checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list.
8217821b-59ed-5f7f-b741-bca0d06e646c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a2b7dacc-4460-586e-a169-76ed1c40651c | note | Check Item - Check Item
48990578-4fc0-54b7-8ce8-6ec70071c405 | note | Reference - MRTS51 Cl. 8.10.1
fedd3be2-5f67-5877-8c24-6dcf4acd37d2 | checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
8dde7544-159f-5208-83f0-bc40ca4e42a1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6e8a6652-5beb-505d-b007-0682345ffcd4 | note | Check Item - Check Item
88eeb207-31bb-55b3-bc1f-a70623c9036b | note | Reference - MRTS51 Cl. 8.13.2
12ed1c33-684c-5cdb-af0c-a60fe376133f | checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
8eb881a9-1256-5216-a116-467128da3000 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8b12440d-bba8-5c5f-aa08-a9e129ba1a13 | note | Check Item - Check Item
bda62781-197c-5c0c-84cb-9a92a228372e | note | Reference - MRTS51 Cl. 8.14.1
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
b9da74c1-aae3-56a9-bf04-114fbae0ffb9 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
7678dbf0-c35d-511e-8ace-ec8cffd94c5b | textbox | Print Name:
759c80e3-9276-55cc-8085-67d4a55d5d16 | date | Date:
f81f56ad-fc1e-59bb-9125-6515fd99782f | note | Administrator's Representative Verify that the Above has been Constructed according to Specification
5dc2fd94-6cb9-51fa-a848-e264395a2e96 | textbox | Print Name:
b90bb418-a0c8-56be-9d50-40c739d1b82a | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
84f5b804-e791-5c18-9a23-4f5d4ee59f41 | checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
95461c78-7416-52c8-a341-0482f7302952 | checkpoint | Clearing and grubbing (or the use of the area for stockpiles) for that section shall not start until the ESCP for that section is assessed as suitable by the Administrator.
38df1b20-19fd-55c3-b6b2-aefa33318094 | note | Acceptance Criteria & Frequency (Project Specific) - Approval of ESCP by Administrator
537f3d52-090e-531f-8c7b-c4300e1d4dab | note | Check Item - Hold Point 1
bb8f6761-1b1d-510d-ad78-4a0713887264 | note | Reference - MRTS52 Cl. 6.1
6f73ee13-8779-5237-9c9b-67cc56397d53 | textbox | Approved in TMR Correspondence dated |  |  | PE/WS/SS __/__/____
155e4752-2d2f-587a-824f-e403daf99d51 | textbox | Approved in TMR Correspondence dated |  |  | CQR to Verify 1__/__/___
6ea23b7b-ecf2-593e-a886-0d4c1123c977 | textbox | Approved in TMR Correspondence dated |  |  | Administrator __/__/___
b34333ac-1df1-5c1a-89d2-e894c41bf43c | signoff | HOLD POINT
be1c0924-6fa8-5188-9e92-b45e3c783fb1 | checkpoint | Prior to initial earthworks operations, the Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
41eae3bf-2a41-56c6-81ca-e05c290e1880 | note | Acceptance Criteria & Frequency (Project Specific) - In accordance with approved ESCP.
ff37348b-b4c1-5653-9f19-8973ebf40ce1 | note | Check Item - Hold Point 2
91b79ee7-411f-544a-bca8-3948422a0ff7 | note | Reference - MRTS52 Cl. 7.1
69a4ddf2-3a14-5df0-84ca-9cd36b2567d0 | signoff | HOLD POINT
35e6b1a7-47ee-5b78-8b05-984a7b0ef12a | checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
9874f228-8dd2-5015-abd3-f684aff04be0 | note | Check Item - Check Item
e067f987-a9f0-5396-b755-3bd3d5a74b6c | note | Reference - MRTS52 Cl. 8.1
82c30a52-820d-5538-8a93-ad7a36c3b4aa | checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
50cc1873-ce1b-5149-9d63-eb0663b2a92f | note | Check Item - Check Item
b4e1dd57-0c3d-5029-bfd9-5fa1cc136f54 | note | Reference - MRTS51 Cl. 8.2.3.2.1
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
634fc68a-f19e-55a1-bf23-9f43d092ff9c | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
7a26c6fa-6cbb-59c8-99c5-f15282cc37b9 | textbox | Print Name:
c2b55991-c610-5244-b2ee-712d1335ba73 | date | Date:
922ba005-c722-54e2-a383-6bca8caa12e2 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
9e2298c3-bfd1-52bd-8210-3ba3162992d4 | textbox | Print Name:
fc359aa8-ba71-55b2-a7d7-f3866ab94de2 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
587064fb-c1c7-5003-8e06-31e652588ebc | checklist | 70.01 - MRTS70 Concrete | itp | 70.01 - MRTS70 Concrete
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
bcb2d049-d92a-540e-b530-54c767f2fe3c | checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
b116a167-d5e3-5378-b34f-c1efe4657066 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
da26a28e-6c2d-58cf-84b5-4ccf9859e16e | note | Check Item - Milestone
24bb1900-12bf-505e-b6f0-52442c7fb53f | note | Reference - MRTS70 Cl 9.2
bfdbf1f8-b0fe-535a-a8da-15a2f453429c | checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
c600fe9f-48fa-58c4-9e86-79b6d7d23923 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d518a1e8-e223-5a13-9a29-f90f02c40686 | note | Check Item - Milestone
856cc90c-d421-5371-b217-163c5562690e | note | Reference - MRTS70 Cl 13.1
2e8fe27d-8bef-5d77-b5a8-9e563eb92255 | checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
af5ef710-32cf-5ca4-87b0-cd18359fd620 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
de24ebfe-da42-5438-9024-49ea30144b7e | note | Check Item - Milestone
213dbea1-e34c-55b8-b9b6-6c8a5c63478e | note | Reference - MRTS70 Cl 15.11.1
b82685c2-8ec2-58aa-bcef-c8c4cba3acc1 | checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour.
7de5adbc-c0a1-54e9-8756-4afbf98025f2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3d91f89d-bf39-59cc-be47-2150df4e8d11 | note | Check Item - Milestone
c8dca6b4-f7df-510f-8be7-3d949bd143df | note | Reference - MRTS70 Cl15.5
d045d20f-0dee-5db0-9da2-c9e78fc69b2c | checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. Each trial mix shall be a Witness Point with a notice peroid of 3 days. The minimum volume of trial mix is 25% of the rated capacity of the mixer.
24253bcd-5a3b-55f3-a4e1-dd6955b5093b | note | Acceptance Criteria & Frequency (Project Specific) - f'c Each Mix
b915a332-931c-5519-a13a-487cf1908ecb | note | Check Item - Witness Point 1
0efb708d-2a44-5d31-8a4b-f0d1899e43c9 | note | Reference - MRTS70 Cl 15.1.1
94787d95-36a8-5c27-bdd1-407c8e8d1baf | checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
6e1619ac-5689-54d7-bb48-58838818c147 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d470575b-72dd-50b7-bb61-165460e35ebc | note | Check Item - Hold Point 1
24bf6b7e-0ce4-533e-83a0-8d19a09a4708 | note | Reference - MRTS70 Cl 15.1
5539fffe-53e5-5938-99fa-c331836fe632 | signoff | HOLD POINT
2bedcf89-a680-571c-89f0-bd42596bfb4f | checkpoint | Concrete placed within 75minutes (conc. Temp<=32 degrees) or 1hour (32>conc. temp < 35 degrees) from the time of charging the mixer. These times may be extended at the Administrator's discretion where set-retarding admixtures are used. No concrete may be placed the temperature of the concrete is less than 10°C or exceeds 35°C.
05f88718-0d73-51b6-8c2d-e00816a76179 | note | Acceptance Criteria & Frequency (Project Specific) - 10< Temp <35 Continuous
447d95fa-c1f8-5b8d-9184-2a4055f1c277 | note | Check Item - Check Item
c4b8531c-d4e7-5e35-ab0b-838cbee2c883 | note | Reference - MRTS70 Cl 13.1
595797df-ba90-597d-9702-8d7182f3d69c | checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
d033071b-555f-5a77-b5ce-7503bded7d7c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0152904b-0ab7-5b41-8697-c656156aeb04 | note | Check Item - Milestone
e7153527-06d9-5c86-8d3e-7907abc539bc | note | Reference - MRTS70 Cl 15.3
a75d5dac-215e-5303-b212-579f2fd95ed3 | checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
ce3e45c5-fe87-5b79-8a65-00ff21ff273f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8aff8293-cfc6-5806-8afc-c6fc03ef821e | note | Check Item - Hold Point 2
5034eb7e-0847-5131-982b-db833ceadaa2 | note | Reference - MRTS70 Cl 15.3
13c2e920-fb37-5759-ba57-597e54fc42a4 | signoff | HOLD POINT
5a1bd4b2-0a02-5238-9c9c-a17190cc80e7 | checkpoint | All formwork shall be subject to inspection and approval by the Administrator.
51e9d6fa-6d57-5b62-8cce-f2e140272337 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
97a59d78-26b3-5921-b265-331af1225225 | note | Check Item - Hold Point 3
62936186-4b26-5302-aa93-e2b1d9ae74d1 | note | Reference - MRTS70 Cl 15.4.1
811618e9-8cf4-5d3b-b051-775990ba31e8 | signoff | HOLD POINT
f62488b8-e8ee-5ecc-b4ac-549557a210f1 | checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
4daccfc0-4f20-5f69-8343-2dae11d27b2e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
85750b27-bd0b-51f0-aa32-f208553c17e2 | note | Check Item - Hold Point 4
6bca60c4-98b9-569d-a7e2-ec076f5b07c4 | note | Reference - MRTS70 Cl 15.6
1cd249ee-2b13-5490-82ec-399706caabaf | signoff | HOLD POINT
0004fac1-81cd-5d2e-af8d-f467245caad7 | checkpoint | No concrete shall be placed in the Works until:
ef1dabf1-e10a-5b3b-95fd-ae1b59cd20e7 | note | a) the formwork and reinforcement have been inspected
9b5535fb-e8cd-5c0a-a486-b9d6882c6afd | note | b) all foreign material has been completely removed from the forms
b8edd723-391d-505b-9e74-c945aceab9ee | note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
e6c41fd5-97d9-5276-bc98-110d164c4943 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
24c6ab78-b613-51a5-85fb-2c13eacf9e60 | note | Check Item - Hold Point 5
45012197-72c9-550f-b305-ea3c42e04bd4 | note | Reference - MRTS70 Cl 15.6.1
ed1b7e53-98af-5fd4-92af-382a541e126b | signoff | HOLD POINT
fd9d8ec6-18fa-5a90-a6c3-c0d0786b33f5 | checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
0cdbb839-4bc9-5b20-8955-8a49e87986cd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
041c05ed-cc40-521d-b9e5-a29e943f9eb0 | note | Check Item - Witness Point 2
e97370aa-f845-5787-b66a-2ba35ad679de | note | Reference - MRTS70 Cl 15.6.1
8b88928b-ded0-5e27-a2bd-5f19492e9777 | checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
750bf337-a747-56cf-ae52-bffc0d23780f | note | Acceptance Criteria & Frequency (Project Specific) - Slump Test:
87411e1e-ab2f-54ef-854f-af157a335154 | note | ○ <60 - ±10
474cb70b-17d0-56ff-bdb7-36af7ac95435 | note | ○ 60<80 - ±15
5dc1bda4-8c44-5808-a51e-16ae25c69bc1 | note | ○ 80<110 - ±20
6127231e-fba9-5bc0-b474-cd1acf2eeea4 | note | ○ 110<150 - ±30
0f48c3ab-ee0c-5e09-b87c-11d31091e595 | note | ○ 150< - ±40
5cac08eb-cae6-5f26-be54-44b22beabcc2 | note | ○ Every Load
a3bec57f-70f2-5d16-b71c-4479c6d92db8 | note | Check Item - Check Item
4dd4fde5-cca4-5f27-b1ed-9301f7ac43be | note | Reference - MRTS70 AS 1379 Table 6
e415a3cf-43e7-5f43-b951-99d550494cdd | checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample.
1f05d53e-f1a2-526a-b13b-48aea9b9a5bb | note | Acceptance Criteria & Frequency (Project Specific) - 1-3 Loads - Every Load
2b58bbf8-d272-5cb5-886b-57c1d1fda2bb | note | ○ 4-10 Loads - 4 Samples
1ced7c18-65f8-5ae9-a3be-b1d23b688347 | note | ○ 11-23 Loads - 5 Samples
594ff8d1-d2b6-5f6a-a47e-e7c09b402170 | note | ○ >23 Loads - 1 per 4 loads
350326c0-fa0b-5e6b-a195-79abf8b1e680 | note | Check Item - Test Results
4fa8ce53-0a65-586f-9863-375f1d1f91a8 | note | Reference - MRTS70 Cl 15.2.1 Table 15.2.2
b08b61a4-7d32-5ed4-94bc-54ec9bf242e5 | checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour.
c109c226-17a0-55a7-8bf9-7dc735781fe2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
284c0239-216b-5827-b215-a23358dfc3f2 | note | Check Item - Check Item
38aee0ee-ac5a-588a-9c74-c7aa9ceffa48 | note | Reference - MRTS70 Cl 16.5.2
64446e49-615d-5b0f-9f2b-6b7c70aab351 | checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set. If an interruption greater than 45 minutes occurs, without prio approval from the Administrator, or a cold join occurs, the precast member shall be rejected.
32a9d7e2-4b34-5f76-ac91-0e269312f99e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4c8f409b-1467-5619-a12d-2b353ead9fdb | note | Check Item - Check Item
cc90f42d-a99f-591a-bb4b-0a41df1887a8 | note | Reference - MRTS70 Cl.16.5.1
668d9b91-379c-58a9-968b-f17e3efe7283 | checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
dc948fd7-9001-546d-a483-b4e9be7588e5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2d247635-0e25-52b9-b12f-778f9cb691df | note | Check Item - Hold Point 7
3f21905f-6fa4-5830-a251-3a47d3250bd9 | note | Reference - MRTS70 Cl 15.13
16d82ef3-0105-5c32-8f7f-ba2602efe5d4 | signoff | HOLD POINT
ef1fcb93-60dc-56ad-b22f-9e2000cc5681 | checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting.
2b3f7326-244b-5649-80e8-9161cac8896d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1a45687b-a4e2-5780-8848-116a3a893eeb | note | Check Item - Hold Point 6
bccbcddf-1082-5086-bfd2-58018b3d44a7 | note | Reference - MRTS70 Cl 15.8
cbbc69fd-e2d6-5a6a-a5a1-8de3b2e0cb2f | signoff | HOLD POINT
971996cf-966e-5fe1-a333-e78a345daa64 | checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure.
e039d375-95c7-5652-9810-acdf125a4b8b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f1fe2570-54d7-596d-98d1-9d7969820196 | note | Check Item - Witness Point 4
f94a0fe2-0ec5-59ec-a16a-9bcf49109807 | note | Reference - MRTS70 Cl 15.8
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
5ef5c1df-ac8d-5a81-ac4c-56473e907cc4 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
a9953e7c-25d9-573f-b98c-486537df5193 | textbox | Print Name:
8751f047-08e9-5f96-be22-da46ec1bb9b8 | date | Date:
f1b22b04-c55d-58a8-9ad1-688e6f3055eb | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
d5ee7d69-9c69-53c1-a7b8-c712bbcf4e14 | textbox | Print Name:
975bd40f-119f-5986-95f1-3e52d5c9adf1 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
8fd469a5-c537-51a0-8f07-628d68197c30 | checklist | 71.01 - Reinforcing Steel | itp | 71.01 - Reinforcing Steel
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
86fd8225-7005-578f-829b-9e7352e25f92 | checkpoint | Submission of proposed supplier to Administrator at least 7 days prior to supply of reinforcing. Supplier must be TMR approved and a member of ACRS (Aust Certification Authority for Reinforcing Steel).
b7dd9fc9-764d-574c-a97e-0bb00819746a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3572f030-9ced-5b6b-8fc8-176b7dda29cc | note | Check Item - Milestone
4391a923-595a-583e-a54d-d8b997b5348c | note | Reference - MRTS71 Cl. 6.1
cb6c3af3-72de-5097-8f2c-4fe88b018b71 | checkpoint | Steel reinforcing not delivered to site prior to written acceptance from the Administrator
f9a506a3-9609-52b0-99e7-267e2b02bafa | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ec6eded6-281e-5ca1-b798-4d2689371736 | note | Check Item - Hold Point 1
2384320c-9956-57a1-b850-c6cb5fc0e778 | note | Reference - MRTS71 Cl. 6.1
b372d2d1-e0e2-5a68-8f8d-e520ce6c5393 | signoff | HOLD POINT
956e4b08-6bdd-55ef-8db8-dd172a7d173c | checkpoint | Submission for alternative bar grip screw couplers must be presented to Administrator at least 14 days prior to proposed use with full technical data sheet.
24025e9b-e29e-5e9b-ba11-2e3b930c491c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ff7fb61d-c982-59c7-804f-ba545737a0be | note | Check Item - Milestone
44c99e90-bd15-5781-8322-4618f67102c1 | note | Reference - MRTS71 Cl. 11.3
c94d3527-3f6d-5334-be42-1c604a6ccb1c | checkpoint | Mechanical reinforcing bar splices permitted for use are to be listed in Clause 1 of Annexure MRTS71.1. Alternative registered mechanical reinforcing bar splices shall not be used without prior approval of the Administrator.
2edccd40-c864-5996-96f1-2c9fd347850d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b624cd65-16c0-5538-b1c0-3888dff30261 | note | Check Item - Hold Point 4
607cad7a-d882-5f6e-b66b-7240a36ff01f | note | Reference - MRTS71 Cl. 11.3
40003539-d003-5a71-b2d2-44c9f02f1420 | signoff | HOLD POINT
0605bef4-9b97-53bf-9ff2-a9c8a58c3c98 | checkpoint | Substitution of different size steel shall not be made unless written application to Administrator at least 3 weeks prior to date required.
0d14750a-cf6d-5b79-be3b-fa905a5b4a95 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
db6a42a4-66d9-5e85-b411-ddef82f2cc3f | note | Check Item - Milestone
d5c1f13e-786a-5946-bfee-0f3994037ded | note | Reference - MRTS71 Cl. 13
0677b4dd-94db-56fa-8a48-41990d2bfe57 | checkpoint | Substitution of steel shall not take place until approved by the Administrator
d392870a-be75-5c7c-b0ec-4487a950e519 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
920d0027-ceed-5ff5-82c8-e055c4c32853 | note | Check Item - Hold Point 5
c830e6f9-9cc3-58d2-b805-3e78059412c3 | note | Reference - MRTS71 Cl. 13
84265651-dee4-5b52-a461-42696b310566 | signoff | HOLD POINT
f9d6914d-e5e2-5cbd-a515-102b5f1a1aa4 | checkpoint | Where authorised by Administrator, bars may be hot bent on site following conditions in Cl. 8.
327f4887-e491-552d-bea7-6f7588a1f350 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
febc6a38-b85d-53cb-8519-40e69fe15702 | note | Check Item - Hold Point 2
af33320d-a79c-5510-b533-995c51ef9cd0 | note | Reference - MRTS71 Cl.8.2
1cf1c469-2d19-5966-9b52-f87ffc2cab4e | signoff | HOLD POINT
cef0703a-d933-5be5-bdce-dc555c711b13 | checkpoint | Installation of bar grip couplers to position as shown on drawings.
1df54c90-8f5d-5694-9eaa-15869464cfcc | note | Acceptance Criteria & Frequency (Project Specific) - Visual
bf34e384-c6fc-564c-bf2d-2b11da4eb0ee | note | Check Item - Witness Point
7ee4bb37-57e5-5d46-93e0-0041ba064b10 | note | Reference - MRTS71 Cl. 11.3
8f0a490e-37b4-5efe-9ed3-f523f2409652 | checkpoint | No welding to commence until Welding Procedure Specification Sheet, process and consumables for welding of splices are approved by the Administrator
7bf8df59-f674-5025-82ec-25eb3deb3e4e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f9c17af2-35e4-56ff-88f1-c6c6a4616697 | note | Check Item - Hold Point 6
03f65681-b09a-5e0e-8688-380be27f86e4 | note | Reference - MRTS71 Cl.14.2
7de07fea-8217-5318-9d82-59e5a1c7af0e | signoff | HOLD POINT
6a413d6c-e1de-58ec-8844-3d0938dca7d5 | checkpoint | All reinforcing cages which are required to be lifted or transported into position, shall have dedicated lifting points. For large cages RPEQ certified drawing must be submitted to administrator for approval
64ae36da-d561-5b5e-8208-80812bb1207e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9f3ff2eb-4948-5d60-b4e7-8c7c8677af1f | note | Check Item - Hold Point 8
6e789e0a-bc92-5063-95bb-5130ab020476 | note | Reference - MRTS71 Cl.15.1
1f6dc9ad-dc0b-56db-9378-d3bfbf45577c | signoff | HOLD POINT
4ee17182-fe63-59b6-bbe4-830b72c2f7a2 | checkpoint | Placement of reinforcing within the concrete formwork shall not proceed until the Administrator has approved all splice welds.
d84e6354-8ba4-54e3-ad61-9df7eb7f1546 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5c20cb3e-7411-5a72-9bef-229167b2299b | note | Check Item - Hold Point 7
3c59dd21-a5c0-554e-949c-ba4c56ab796a | note | Reference - MRTS71 Cl. 14.5
8669748c-6e4c-5351-8755-9c003877bd70 | signoff | HOLD POINT
6bd07a3e-5a48-5b58-99d0-54a9cebcbbb3 | checkpoint | All steel reinforcing in position shall be inspected and approved before placement of concrete commences
4ad1eddb-d6b9-55f6-8a61-2da5a415407d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d10800ff-43c7-5f27-9c49-b6601f664144 | note | Check Item - Hold Point 3
5afd668f-0159-5d29-a79e-5dac900045d4 | note | Reference - MRTS71 Cl. 10
e64c875b-a3f6-598e-a89c-2a807566068a | signoff | HOLD POINT
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
0c68c026-5e0c-5bf9-9412-0df4e4638439 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
99b2a4da-a42a-597e-9b7d-a57f0bafa81f | textbox | Print Name:
41a04b5a-7f76-55e2-97cf-045eb34947df | date | Date:
3a3f0d08-1002-524b-b3e2-ccfe8ef9e78a | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
bce3e625-d563-51ba-9032-a4def1ac7764 | textbox | Print Name:
4d964f69-4733-5a13-bada-8cc1f7467b98 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off
05a830b6-72a7-5356-a5ed-b399e13db454 | checklist | Subcontractor ITP |  | Subcontractor ITP
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1db8791d-67af-5169-a313-01468886b10b | checkpoint | Subcontractor ITP received and attached
452744b9-0bc7-5d47-8824-e5216a44eb55 | textbox | Subcontractor Name
1ecd8d6b-4bd0-47e7-8276-7f59bdb5bb2c | section | Final Sign Offs (to be completed at closure of Lot)
47660e62-7f6e-43f8-a10d-34c9b78857e0 | checkpoint | Agreed Quantities
9b0f56f1-9473-4d6b-a22e-dbe058e35d18 | signoff | Agreed Quantities Sign Off
9a9c8394-212c-4d17-8ceb-9017b410ec3e | checkpoint | Closure of Lot
603e7f30-2f4c-4d5b-add8-1f9c67142f18 | signoff | Closure of Lot Sign Off